4469 | Water and Sewerage Management | Supply of water Pipes in dundori ward | To implement supply of water pipes in dundori ward for access to clean water and environmental sustainability | Supply of water Pipes in dundori ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.255543, 36.20922 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 2100000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2365978 | 94.6 | 2365978 | 134022 | 134022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Rimwat holdings Ltd. Assessor remarks: Good.
4470 | Water and Sewerage Management | Thugunui borehole equipping and piping | To implement thugunui borehole equipping and piping for access to clean water and environmental sustainability | Thugunui borehole equipping and piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 7700000 | 0 | 7700000 | Equitable | N/A | 7700000 | 0 | 3571500 | 0 | 3571500 | 3571501 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4471 | Water and Sewerage Management | Construction of Kasambara borehole water tower, tank and piping | To construct Kasambara borehole water tower, tank and piping | Kasambara borehole water tower, tank and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/ Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3571500 | 119 | 3571500 | 3000000 | -571500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4472 | Water and Sewerage Management | Boma Water Works | To implement boma water works for access to clean water and environmental sustainability | Boma Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.619785, 36.2412 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 23-24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2478438 | 99.1 | 2478438 | 21562 | 21562 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Value for money. Contractor: Pepesi Africa general merchants. Assessor remarks: Did well.
4473 | Water and Sewerage Management | Construction of Kasambara borehole water tower, tank and piping | To construct Kasambara borehole water tower, tank and piping | Kasambara borehole water tower, tank and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3571500 | 100 | 3571500 | 3000000 | -3571500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4474 | Water and Sewerage Management | Construction of Nderit borehole water tower, tank and piping | To construct Nderit borehole water tower, tank and piping | Nderit borehole water tower, tank and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 3571500.8 | 3571500.8 | Equitable | N/A | 3571500.8 | 0 | 3571500 | 100 | 3571500 | 3571501 | 0.8 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4475 | Water and Sewerage Management | Construction of Workers borehole, water tower tanks and piping | To construct Workers borehole, water tower tanks and piping | Workers borehole, water tower tanks and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 3500000 | 0 | 3227676.8 | Equitable | N/A | 3227676.8 | 0 | 3571500 | 100 | 3571500 | 3227677 | -3571500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4476 | Water and Sewerage Management | Eburru/Mbaruk Water Works | To implement eburru/mbaruk water works for access to clean water and environmental sustainability | Eburru/Mbaruk Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.488148, 36.156876 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 22-23 | 14832983.85 | 5177625.85 | 2636525.85 | Equitable | N/A | 2636525.85 | 0 | 2491100 | 48.1 | 2491100 | 2686526 | 2686525.85 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Value for money. Viable: Yes. Contractor: Online movers ltd box 16147-Nakuru. Assessor remarks: Well done.
4477 | Water and Sewerage Management | Kasambara Water Works | To implement kasambara water works for access to clean water and environmental sustainability | Kasambara Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.619785, 36.2412 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 23-24 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 2478438 | 100 | 2478438 | 3500000 | -2478438 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Value for money. Contractor: Pepesi Africa general merchants. Assessor remarks: Did well.
4478 | Water and Sewerage Management | Kiungururia Water Works | To implement kiungururia water works for access to clean water and environmental sustainability | Kiungururia Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.488148, 36.156876 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 22-23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3378029 | 84.5 | 3378029 | 621971 | 621971 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Value for money. Viable: Yes. Contractor: Online movers ltd box 16147-Nakuru. Assessor remarks: Well done.
4479 | Water and Sewerage Management | Piping at Gema area College road and Kagema road | To provide water distribution infrastructure at Gema area College road and Kagema road | Water piping at Gema area College road and Kagema road completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2458596 | 2458596 | Equitable | N/A | 2458596 | 0 | 2408820 | 98 | 2408820 | 49776 | 49776 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4480 | Water and Sewerage Management | Piping at Greensteds-Dehavana area | To provide water distribution infrastructure at Greensteds-Dehavana area | Water piping at Greensteds-Dehavana area completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4481 | Water and Sewerage Management | Piping at Oljorai Borehole | To provide water distribution infrastructure at Oljorai Borehole | Water piping at Oljorai Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.36445, 36.239523 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | No information | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara. Assessor remarks: Successful project.
4482 | Water and Sewerage Management | Purchase of tanks, installation of piping at Losiro Water Project | To procure tanks, installation of piping at Losiro Water Project | Tanks, installation of piping at Losiro Water Project procured | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4483 | Water and Sewerage Management | Thome Nagum Water Piping | To implement thome nagum water piping for access to clean water and environmental sustainability | Thome Nagum Water Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2555190 | 85.2 | 2555190 | 444810 | 444810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4484 | Water and Sewerage Management | Water Piping at Kasambara Murage Leleshwa | To implement water piping at kasambara murage leleshwa for access to clean water and environmental sustainability | Water Piping at Kasambara Murage Leleshwa completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1976733 | 98.8 | 1976733 | 23267 | 23267 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4485 | Water and Sewerage Management | Water Piping at Ndiuni( acacia kiwanja) | To implement water piping at ndiuni( acacia kiwanja) for access to clean water and environmental sustainability | Water Piping at Ndiuni( acacia kiwanja) completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.346735, 36.167249 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 470878 | 0 | 470878 | Equitable | N/A | 470878 | 0 | 500000 | 100 | 500000 | 470878 | -500000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Not yet completed. Contractor: Unkworn. Assessor remarks: Done Fair work.
4486 | Water and Sewerage Management | Water Piping atNdiuni( acacia kiwanja) | To implement water piping atndiuni( acacia kiwanja) for access to clean water and environmental sustainability | Water Piping atNdiuni( acacia kiwanja) completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.346735, 36.167249 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 470878 | 470878 | 470878 | Equitable | N/A | 470878 | 0 | 500000 | 106.2 | 500000 | 470878 | -29122 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Not yet completed. Contractor: Unkworn. Assessor remarks: Done Fair work.
4487 | Water and Sewerage Management | Water Works at Oljorai | To implement water works at oljorai for access to clean water and environmental sustainability | Water Works at Oljorai completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.570173, 36.188375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 24-25 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3668825 | 91.7 | 3668825 | 331175 | 331175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Not yet fully. Water be connected to household. Contractor: Riderocks ltd box 2079 Kericho. Assessor remarks: Well done.
4488 | Water and Sewerage Management | Completion of Nyariche Water Project | To complete Nyariche Water Project | Nyariche Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2235974 | 89.4 | 2235974 | 264026 | 264026 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
4489 | Water and Sewerage Management | Construction of 150m3 Water Tank at Tegat | To construct 150m3 Water Tank at Tegat | 150m3 Water Tank at Tegat constructed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | - | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
4490 | Water and Sewerage Management | Construction Of three Masonry Water Tanks (50m3) At Ribot, Nyakiambi, Arimi Villages | To construct three Masonry Water Tanks (50m3) At Ribot, Nyakiambi, Arimi Villages | Three Masonry Water Tanks (50m3) At Ribot, Nyakiambi, Arimi Villages constructed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 5200000 | 0 | 2838300.01 | Equitable | N/A | 2838300.01 | 0 | 1361700 | 100 | 1361700 | 2838300 | -1361700 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
4491 | Water and Sewerage Management | Drilling and equiping of green estate borehole | To implement drilling and equiping of green estate borehole for access to clean water and environmental sustainability | Drilling and equiping of green estate borehole completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.306163 35.800133 0 72.9000015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4951641 | 4951641 | 4951641 | Equitable | N/A | 4951641 | 0 | 2673559 | 54 | 2673559 | 2278082 | 2278082 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: O.B.T.Limited. Assessor remarks: Work on progrss.
4492 | Water and Sewerage Management | Drilling of Kapsita Borehole | To implement drilling of kapsita borehole for access to clean water and environmental sustainability | Drilling of Kapsita Borehole completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4400000 | 4400000 | 8800000 | Equitable | N/A | 8800000 | 0 | 3680654 | 83.7 | 3680654 | 4400000 | 719346 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
4493 | Water and Sewerage Management | Equipping of green estate borehole | To equip green estate borehole with necessary facilities and equipment | Green estate borehole equipped | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.308342 35.807555 2442.7 11.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2278082.28 | 0 | 2478082.28 | Equitable | N/A | 2478082.28 | 0 | 2673559 | 0 | 2673559 | 2278082 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
4494 | Water and Sewerage Management | Kasarani Water Project | To implement kasarani water project for access to clean water and environmental sustainability | Kasarani Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.294145, 35.7941 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 936234 | 100 | 936234 | 3500000 | -936234 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Only solarization was done by county government,borehole was done by NG-CDF.
4495 | Water and Sewerage Management | Lower mutamaiyo water works | To implement lower mutamaiyo water works for access to clean water and environmental sustainability | Lower mutamaiyo water works completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.260228 35.795537 2376.5 9.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187550 | 100 | 1187550 | 5000000 | -1187550 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete project.
4496 | Water and Sewerage Management | Supply and Installation of 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde | To procure and install 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde | 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.303215, 35.819011 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | - | 900000 | 757552 | 757552 | Equitable | N/A | 757552 | 0 | 757552 | 100 | 757552 | 757552 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
4497 | Water and Sewerage Management | Supply and Installation of Pipes for Nyariche Water Project | To procure and install Pipes for Nyariche Water Project | Pipes for Nyariche Water Project procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2235974 | 100 | 2235974 | 264026 | -2235974 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
4498 | Water and Sewerage Management | Supply and Installation of water pipes for cheponde water works | To procure and install water pipes for cheponde water works | Water pipes for cheponde water works procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 2905568 | 100 | 2905568 | 2905568 | -2905568 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
4499 | Water and Sewerage Management | Supply and Installation of Water pipes for Matumaiyu water works | To procure and install Water pipes for Matumaiyu water works | Water pipes for Matumaiyu water works procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 2905568 | 2905568 | Equitable | N/A | 2905568 | 0 | 2905568 | 100 | 2905568 | 2905568 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
4500 | Water and Sewerage Management | supply of pipes for Mutamaiyu Water Works | To implement supply of pipes for mutamaiyu water works for access to clean water and environmental sustainability | supply of pipes for Mutamaiyu Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.260228 35.795537 2376.5 9.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 2326200 | 100 | 2326200 | 5000000 | -2326200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete project.
4501 | Water and Sewerage Management | Construction of tank and supply of pipes for Oakland water project | To construct tank and supply of pipes for Oakland water project | Tank and supply of pipes for Oakland water project constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.567279 36.11652 1971.0999755859375 35.24100112915039 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2200000 | 0 | 1814618.16 | Equitable | N/A | 1814618.16 | 0 | 1165052 | 100 | 1165052 | 1814618 | -1165052 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4502 | Water and Sewerage Management | Drilling Of a Kahuho Nyaturu borehole | To implement drilling of a kahuho nyaturu borehole for access to clean water and environmental sustainability | Drilling Of a Kahuho Nyaturu borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.601384, 36.106642 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3300000 | 0 | 3300000 | Equitable | N/A | 3300000 | 0 | 3619344 | 100 | 3619344 | 3300000 | -3619344 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not equipped.
4503 | Water and Sewerage Management | Drilling Of Munanda Borehole | To implement drilling of munanda borehole for access to clean water and environmental sustainability | Drilling Of Munanda Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.601384, 36.106642 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3619344 | 100 | 3619344 | 3000000 | -3619344 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not equipped.
4504 | Water and Sewerage Management | Kahuho water project | To implement kahuho water project for access to clean water and environmental sustainability | Kahuho water project completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.618481 36.146879 2073.900146484375 1.034000039100647 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repair.
4505 | Water and Sewerage Management | Makongo borehole water works | To implement makongo borehole water works for access to clean water and environmental sustainability | Makongo borehole water works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.583302 36.11537 2053 6.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3300000 | 0 | 3300000 | Equitable | N/A | 3300000 | 0 | 2699650 | 100 | 2699650 | 3300000 | -2699650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Operational. Viable: Yes. Assessor remarks: Operational.
4506 | Water and Sewerage Management | Maririgua tan-construction of water tank and piping | To implement maririgua tan-construction of water tank and piping for access to clean water and environmental sustainability | Maririgua tan-construction of water tank and piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1407030.12 | 1407030.12 | Equitable | N/A | 1407030.12 | 0 | 1407030 | 100 | 1407030 | 1407030 | 0.12 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4507 | Water and Sewerage Management | Ngecha village waterworks | To implement ngecha village waterworks for access to clean water and environmental sustainability | Ngecha village waterworks completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.583302 36.11537 2053 6.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1690748 | 93.9 | 1690748 | 109252 | 109252 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Operational. Viable: Yes. Assessor remarks: Operational.
4508 | Water and Sewerage Management | Piping And Purchase of Booster Pump at Mugaa Borehole | To provide water distribution infrastructure at And Purchase of Booster Pump at Mugaa Borehole | Water piping at And Purchase of Booster Pump at Mugaa Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.636072 36.131093 1990.7 8.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Awaiting piping for water water distribution.
4509 | Water and Sewerage Management | Piping at Tee-Tangitano | To provide water distribution infrastructure at Tee-Tangitano | Water piping at Tee-Tangitano completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.632853 36.117144 2263.427 1.3279999494552612 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 456536 | 91.3 | 456536 | 43464 | 43464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purpose served.
4510 | Water and Sewerage Management | Piping Works at Cypres | To provide water distribution infrastructure at Works at Cypres | Water piping at Works at Cypres completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.604347 36.129685 2079.7001953125 1.0460000038146973 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2262703 | 83.8 | 2262703 | 437297 | 437297 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
4511 | Water and Sewerage Management | Piping Works at Jogoo, Old game | To provide water distribution infrastructure at Works at Jogoo, Old game | Water piping at Works at Jogoo, Old game completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.604347 36.129685 2079.7001953125 1.0460000038146973 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1150000 | 1150000 | 1150000 | Equitable | N/A | 1150000 | 0 | 1150000 | 100 | 1150000 | 437297 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
4512 | Water and Sewerage Management | Purchase and supply of pipes at Kiptangwanyi and Ngecha | To procure and supply pipes at Kiptangwanyi and Ngecha | Pipes at Kiptangwanyi and Ngecha procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.50908 36.061644 2059.445 1.9049999713897705 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1403866 | 73.9 | 1403866 | 354414 | 496134 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4513 | Water and Sewerage Management | Purchase And Supply Of Water Pipes For Mahiga / Settlement | To procure and supply Water Pipes For Mahiga / Settlement | Water Pipes For Mahiga / Settlement procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.529647, 36.090633 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 2092089 | 2092089 | Equitable | N/A | 2092089 | 0 | 1737675 | 83.1 | 1737675 | 354414 | 354414 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4514 | Water and Sewerage Management | Water works at Elementaita center | To implement water works at elementaita center for access to clean water and environmental sustainability | Water works at Elementaita center completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.489686, 36.156982 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1299600 | 0 | 1299600 | Equitable | N/A | 1299600 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4515 | Water and Sewerage Management | Drilling of borehole and pump installation at Maji moto including piping | To provide access to clean water through borehole drilling at and pump installation at Maji moto including piping | Borehole drilled at and pump installation at Maji moto including piping | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.490013 36.320046 1998.323974609375 5.228000164031982 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 7096399 | 4954346.4 | 3228677.04 | Equitable | N/A | 3228677.04 | 0 | 1725669 | 34.8 | 1725669 | 3228677 | 3228677.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
4516 | Water and Sewerage Management | Drilling Of Manyatta Borehole | To implement drilling of manyatta borehole for access to clean water and environmental sustainability | Drilling Of Manyatta Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.47546, 36.33015 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3416217 | 97.6 | 3416217 | 83783 | 83783 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs additional funds to operationalize.
4517 | Water and Sewerage Management | Mbegi pipeline water project-extention to zam zam | To implement mbegi pipeline water project-extention to zam zam for access to clean water and environmental sustainability | Mbegi pipeline water project-extention to zam zam completed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.533578, 36.340077 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 4203508 | 0 | 4203508 | Equitable | N/A | 4203508 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yet to start. Assessor remarks: Yet to start.
4518 | Water and Sewerage Management | Piping Kikopey Water Works | To provide water distribution infrastructure at Kikopey Water Works | Water piping at Kikopey Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.503966 36.32263 1991.4000244140625 20 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2694645 | 89.8 | 2694645 | 305355 | 305355 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Needs additional equipment.
4519 | Water and Sewerage Management | St. Patrick water works | To implement st. patrick water works for access to clean water and environmental sustainability | St. Patrick water works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.510463, 36.324657 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2694645 | 269.5 | 2694645 | 305355 | -1694645 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Helped community access water.
4520 | Water and Sewerage Management | Completion of ongoing projects (Kiamunyi water project piping) | To complete ongoing projects (Kiamunyi water project piping) | Ongoing projects (Kiamunyi water project piping) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 150000000 | 3805194 | 3805194 | Equitable | N/A | 3805194 | 0 | 3805194 | 100 | 3805194 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4521 | Water and Sewerage Management | Construction Of Small Dams And Water Pans | To construct Small Dams And Water Pans | Small Dams And Water Pans constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | N/A | 6000000 | 1436265.6 | 1436265.6 | Equitable | N/A | 1436265.6 | 0 | 1436265 | 100 | 1436265 | 3183456 | 0.6 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4522 | Water and Sewerage Management | Construction Of Water Projects | To construct Water Projects | Water Projects constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | N/A | 15070689.4 | 1936625.86 | 1936625.86 | Equitable | N/A | 1936625.86 | 0 | 1936626 | 100 | 1936626 | 1936626 | -0.14 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4523 | Water and Sewerage Management | Drilling and equipping of borehole at Banita Secondary school grounds in Kokwomoi sub location | To implement drilling and equipping of borehole at banita secondary school grounds in kokwomoi sub location for access to clean water and environmental sustainability | Drilling and equipping of borehole at Banita Secondary school grounds in Kokwomoi sub location completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 6435119 | 6435119 | 0 | Equitable | N/A | 0 | 6435119 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4524 | Water and Sewerage Management | Rapland water project | To implement rapland water project for access to clean water and environmental sustainability | Rapland water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 4855031 | 48.6 | 4855031 | 499112 | 5144969 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4525 | Water and Sewerage Management | Rehabilitation and Construction of Water Systems | To rehabilitate Construction of Water Systems to restore functionality | Construction of Water Systems rehabilitated | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 80000000 | 0 | 5727472 | Equitable | N/A | 5727472 | 0 | 2994378 | 100 | 2994378 | 5622 | -2994378 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4526 | Water and Sewerage Management | Salgaa Area Programme (World Vision) Counterpart funding | To implement salgaa area programme (world vision) counterpart funding for access to clean water and environmental sustainability | Salgaa Area Programme (World Vision) Counterpart funding completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.391082, 35.742475 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 23000000 | 0 | 15891522.37 | N/A | N/A | 15891522.37 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
4527 | Water and Sewerage Management | Mountain View Water Project (Piping, Water Tanks, Installation Of Solar Pumps) | To implement mountain view water project (piping, water tanks, installation of solar pumps) for access to clean water and environmental sustainability | Mountain View Water Project (Piping, Water Tanks, Installation Of Solar Pumps) completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.777464, 36.456934 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 2439348.2 | 2439348.2 | Equitable | N/A | 2439348.2 | 0 | 2321284 | 95.2 | 2321284 | 118064 | 118064.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is going on well , few challenges here and there.
4528 | Water and Sewerage Management | Mwiciringeri Water Works | To implement mwiciringeri water works for access to clean water and environmental sustainability | Mwiciringeri Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.778541 96.57153 2206.42666327852 13.816555427285511 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1821159 | 0 | 1821159 | Equitable | N/A | 1821159 | 0 | 3999549.79 | 100 | 3999549.79 | 1821159 | -3999549.79 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 3,000,000.
4529 | Water and Sewerage Management | Nyamathi water works | To implement nyamathi water works for access to clean water and environmental sustainability | Nyamathi water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.778541 96.57153 2206.42666327852 13.816555427285511 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2965470 | 98.8 | 2965470 | 34530 | 34530 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 3,000,000.
4530 | Water and Sewerage Management | Water works at Karai | To implement water works at karai for access to clean water and environmental sustainability | Water works at Karai completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.77028, 36.487158 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3062365 | 95.7 | 3062365 | 137635 | 137635 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project costed 3,200,000.
4531 | Water and Sewerage Management | Water works within the ward | To implement water works within the ward for access to clean water and environmental sustainability | Water works within the ward completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.770322, 36.487146 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 3062365 | 68.1 | 3062365 | 137635 | 1437635 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 4,500,000.
4532 | Water and Sewerage Management | Construction Of Water Intake and Piping at Giitu Water Project | To construct Water Intake and Piping at Giitu Water Project | Water Intake and Piping at Giitu Water Project constructed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1494013 | 100 | 1494013 | 1000000 | -1494013 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
4533 | Water and Sewerage Management | Drilling Of Borehole at Thayu Assistant Chief Office | To provide access to clean water through borehole drilling at Thayu Assistant Chief Office | Borehole drilled at Thayu Assistant Chief Office | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.21002, 36.148926 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023 | 3800000 | 0 | 1195804.99 | Equitable | N/A | 1195804.99 | 0 | 2604195 | 100 | 2604195 | 1195805 | -2604195 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterprises. Assessor remarks: Yes to start operating, commissioning to be done.
4534 | Water and Sewerage Management | Drilling Of Limuko Borehole | To implement drilling of limuko borehole for access to clean water and environmental sustainability | Drilling Of Limuko Borehole completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.217267, 36.160385 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 1476692 | 1476692 | Equitable | N/A | 1476692 | 0 | 1476692 | 100 | 1476692 | 1476692 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Hantus enterprise ltd. Assessor remarks: Borehole operational,requires more reticulation and there is an existing court case the community want the county to refund money the used to buy the land.
4535 | Water and Sewerage Management | Fencing of Thayu borehole-chain link fence | To secure Thayu borehole-chain link fence through fencing | Thayu borehole-chain link fence fenced and secured | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.210083, 36.148906 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes to be done. Viable: Not yet. Assessor remarks: Yes to be done.
4536 | Water and Sewerage Management | Piping from Mutarakwa to Kabatini main tank 4 pipes | To provide water distribution infrastructure at from Mutarakwa to Kabatini main tank 4 pipes | Water piping at from Mutarakwa to Kabatini main tank 4 pipes completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2021/22 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
4537 | Water and Sewerage Management | Purchase of PVC pipes for Kabatini Sublocation | To procure PVC pipes for Kabatini Sublocation | PVC pipes for Kabatini Sublocation procured | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2671132 | 89 | 2671132 | 328868 | 328868 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
4538 | Water and Sewerage Management | Supply Of Pipes to Connect NAWASSCO Water Connection to Teachers Residence at Mwaki Mugi Area | To implement supply of pipes to connect nawassco water connection to teachers residence at mwaki mugi area for access to clean water and environmental sustainability | Supply Of Pipes to Connect NAWASSCO Water Connection to Teachers Residence at Mwaki Mugi Area completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1619526 | 81 | 1619526 | 380474 | 380474 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
4539 | Water and Sewerage Management | Supply of water pipes within the ward | To implement supply of water pipes within the ward for access to clean water and environmental sustainability | Supply of water pipes within the ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
4540 | Water and Sewerage Management | Additional Fund To Kabazi Water Works | To implement additional fund to kabazi water works for access to clean water and environmental sustainability | Additional Fund To Kabazi Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | N/A | 4416057 | 0 | 3715287.5 | Equitable | N/A | 3715287.5 | 0 | 640770 | 100 | 640770 | 3775288 | -640770 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
4541 | Water and Sewerage Management | Construction of a storage tank, water intake and piping at Kiremba Water Project | To construct a storage tank, water intake and piping at Kiremba Water Project | A storage tank, water intake and piping at Kiremba Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.17004, 36.124855 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997398 | 100 | 1997398 | 2000000 | -1997398 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mopawa investment ltd. Assessor remarks: Requires additional pipping.
4542 | Water and Sewerage Management | Construction of storage tank and equipping of Gitura Water Project | To construct storage tank and equipping of Gitura Water Project | Storage tank and equipping of Gitura Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.17004, 36.124855 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 3000000 | 100 | 3000000 | 2000000 | -3000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mopawa investment ltd. Assessor remarks: Requires additional pipping.
4543 | Water and Sewerage Management | Drilling Of Arahuka Borehole | To implement drilling of arahuka borehole for access to clean water and environmental sustainability | Drilling Of Arahuka Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.159188 36.045365 2081.3 10.899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3184061 | 91 | 3184061 | 315939 | 315939 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Peca services ltd. Assessor remarks: To be operationalized.
4544 | Water and Sewerage Management | Drilling Of Borehole and Installation of Solar Panel for Kitur Water Project | To provide access to clean water through borehole drilling at and Installation of Solar Panel for Kitur Water Project | Borehole drilled at and Installation of Solar Panel for Kitur Water Project | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 3000000 | 100 | 3000000 | 7000000 | -3000000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
4545 | Water and Sewerage Management | Drilling Of Kipngochoch Borehole | To implement drilling of kipngochoch borehole for access to clean water and environmental sustainability | Drilling Of Kipngochoch Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.153995, 36.07318 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024/2025 | 3300000 | 0 | 3300000 | Equitable | N/A | 3300000 | 0 | 3184061 | 100 | 3184061 | 3300000 | -3184061 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Piping, solarization and further drilling of borehole to get water.
4546 | Water and Sewerage Management | Drilling Of Kirima Borehole | To implement drilling of kirima borehole for access to clean water and environmental sustainability | Drilling Of Kirima Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077942 36.170989 0 12.281660079956055 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3184061 | 100 | 3184061 | 3500000 | -3184061 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
4547 | Water and Sewerage Management | Drilling of Mwireri Borehole and Ng'enda Borehole | To implement drilling of mwireri borehole and ng'enda borehole for access to clean water and environmental sustainability | Drilling of Mwireri Borehole and Ng'enda Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.07176, 36.1704 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/24 | 7000000 | 6349988.48 | 6349988.48 | Equitable | N/A | 6349988.48 | 0 | 6305026 | 99.3 | 6305026 | 44962 | 44962.48 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be repaired.
4548 | Water and Sewerage Management | Kabazi Water Works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | N/A | 15400000 | 3712040.5 | 1165035.1 | Equitable | N/A | 1165035.1 | 0 | 2547005 | 68.6 | 2547005 | 1165035 | 1165035.5 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
4549 | Water and Sewerage Management | Piping of Ruiru Water Project | To provide water distribution infrastructure at Ruiru Water Project | Water piping at Ruiru Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 5000000 | 100 | 5000000 | 4000000 | -5000000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
4550 | Water and Sewerage Management | Buret/Kamara water works-including tank coronation and distribution | To implement buret/kamara water works-including tank coronation and distribution for access to clean water and environmental sustainability | Buret/Kamara water works-including tank coronation and distribution completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.097643, 35.68589 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 31/06/2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
4551 | Water and Sewerage Management | Choronok Water Project - Construction of 50m3 Water tank | To implement choronok water project - construction of 50m3 water tank for access to clean water and environmental sustainability | Choronok Water Project - Construction of 50m3 Water tank completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
4552 | Water and Sewerage Management | Connection Of Water from Kiptank to Bureti Tabora AIC | To implement connection of water from kiptank to bureti tabora aic for access to clean water and environmental sustainability | Connection Of Water from Kiptank to Bureti Tabora AIC completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.078727, 35.672885 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 844408 | 84.4 | 844408 | 155592 | 155592 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HEYINZ COMPANY LTD. Assessor remarks: Complete.
4553 | Water and Sewerage Management | Construction Of Tank and Piping at Haraka Village | To construct Tank and Piping at Haraka Village | Tank and Piping at Haraka Village constructed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.148153, 35.676562 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 2999995 | 100 | 2999995 | 4000000 | -2999995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project if functional.
4554 | Water and Sewerage Management | Kapkures/Lopwar Borehole Drilling | To implement kapkures/lopwar borehole drilling for access to clean water and environmental sustainability | Kapkures/Lopwar Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 1701089.02 | Equitable | N/A | 1701089.02 | 0 | 2298911 | 100 | 2298911 | 1701089 | -2298911 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4555 | Water and Sewerage Management | Kapkures/odwar water project-Equiping of borehole, power installation and Piping | To implement kapkures/odwar water project-equiping of borehole, power installation and piping for access to clean water and environmental sustainability | Kapkures/odwar water project-Equiping of borehole, power installation and Piping completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
4556 | Water and Sewerage Management | Kiptank Water Project Kamara Center | To implement kiptank water project kamara center for access to clean water and environmental sustainability | Kiptank Water Project Kamara Center completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149078, 35.715007 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2021/22 | 6500000 | 6197805.76 | 6197805.76 | Equitable | N/A | 6197805.76 | 0 | 6197806 | 100 | 6197806 | 6197806 | -0.24 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
4557 | Water and Sewerage Management | Mau Secondary Water Project - Drilling of borehole, equipping it for supply of two water tanks at Mau Village | To implement mau secondary water project - drilling of borehole, equipping it for supply of two water tanks at mau village for access to clean water and environmental sustainability | Mau Secondary Water Project - Drilling of borehole, equipping it for supply of two water tanks at Mau Village completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 7500000 | 3417318.24 | 3417318.24 | Equitable | N/A | 3417318.24 | 0 | 3025006 | 88.5 | 3025006 | 392312 | 392312.24 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
4558 | Water and Sewerage Management | Mlima Borehole Equipping and Piping to Mlima Village | To implement mlima borehole equipping and piping to mlima village for access to clean water and environmental sustainability | Mlima Borehole Equipping and Piping to Mlima Village completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.162838 35.693123 2518.6 6.599999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5871061 | 97.9 | 5871061 | 128939 | 128939 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
4559 | Water and Sewerage Management | Piping In Kamara -Kapsmotwo, Kwa Harun, Tegati, Olenguruone, Kiwanja from Olenguruone Tank | To provide water distribution infrastructure at In Kamara -Kapsmotwo, Kwa Harun, Tegati, Olenguruone, Kiwanja from Olenguruone Tank | Water piping at In Kamara -Kapsmotwo, Kwa Harun, Tegati, Olenguruone, Kiwanja from Olenguruone Tank completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2806226 | 93.5 | 2806226 | 193774 | 193774 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4560 | Water and Sewerage Management | Piping in Kiwanja Ndege | To provide water distribution infrastructure at in Kiwanja Ndege | Water piping at in Kiwanja Ndege completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.097643, 35.68589 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 31/06/2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3492870 | 349.3 | 3492870 | 1000000 | -2492870 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
4561 | Water and Sewerage Management | Piping In Mau Summit Location | To provide water distribution infrastructure at In Mau Summit Location | Water piping at In Mau Summit Location completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.175308, 35.679372 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2916716 | 97.2 | 2916716 | 83284 | 83284 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Complete.
4562 | Water and Sewerage Management | Tank Construction at Muchorwe - Kisii Ndogo Water Project | To implement tank construction at muchorwe - kisii ndogo water project for access to clean water and environmental sustainability | Tank Construction at Muchorwe - Kisii Ndogo Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.193912, 35.687647 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | Ongoing | 2000000 | 0 | 1918406 | Equitable | N/A | 1918406 | 0 | 7134661 | 100 | 7134661 | 1958406 | -7134661 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Ongoing. Contractor: Messis construction company ltd. Assessor remarks: Ongoing.
4563 | Water and Sewerage Management | Water works in mau summit location | To implement water works in mau summit location for access to clean water and environmental sustainability | Water works in mau summit location completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.175237, 35.679293 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2916716 | 41.7 | 2916716 | 83284 | 4083284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Complete.
4564 | Water and Sewerage Management | Drilling Of Borehole at Ingobor Upperhill community water project | To provide access to clean water through borehole drilling at Ingobor Upperhill community water project | Borehole drilled at Ingobor Upperhill community water project | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.309635 36.024659 1878.0291489982103 7.504000186920166 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 1904105 | 100 | 1904105 | 3500000 | -1904105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
4565 | Water and Sewerage Management | Drilling Of Borehole at Mogoon resource center | To provide access to clean water through borehole drilling at Mogoon resource center | Borehole drilled at Mogoon resource center | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.306306, 36.018533 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3539881 | 3539881 | 1635775.75 | Equitable | N/A | 1635775.75 | 0 | 1904105 | 53.8 | 1904105 | 1635776 | 1635776 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Well done and operational.
4566 | Water and Sewerage Management | Installation of water pump,Piping, Construction of water tank and installation of electricty at mogoon Reource centre borehole | To install water pump,Piping, Construction of water tank and installation of electricty at mogoon Reource centre borehole | Water pump,Piping, Construction of water tank and installation of electricty at mogoon Reource centre borehole installed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.30958, 36.024655 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction complete and operational.
4567 | Water and Sewerage Management | Mogoon resource center water works | To implement mogoon resource center water works for access to clean water and environmental sustainability | Mogoon resource center water works completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.306306 36.000514 0 2000 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 2075390.6 | Equitable | N/A | 2075390.6 | 0 | 1904105 | 100 | 1904105 | 2075391 | -1904105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Was bought but about quarter has been privatised..
4568 | Water and Sewerage Management | Water works at Resource center | To implement water works at resource center for access to clean water and environmental sustainability | Water works at Resource center completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kaptembwo | -0.315356 36.052954 1787.300048828125 26.322999954223633 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Yes,once started it will ease mobility. Contractor: Not awarded. Assessor remarks: Not yet started.
4569 | Water and Sewerage Management | Water works at Vocational training center | To implement water works at vocational training center for access to clean water and environmental sustainability | Water works at Vocational training center completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kaptembwo | -0.299728 36.045548 1803.800048828125 21.075000762939453 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S MIDRIFT GENERAL MERCHANTS. Assessor remarks: Overgrown vegetation has debris and thrush,needs unclogging.
4570 | Water and Sewerage Management | Completion of Piping at Siwot primary-Kipkoibet | To complete Piping at Siwot primary-Kipkoibet | Piping at Siwot primary-Kipkoibet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515378 35.717993 2681.7 7 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1397986 | 139.8 | 1397986 | 146014 | -397986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
4571 | Water and Sewerage Management | Construction of water tank and piping at kipsonoi | To construct water tank and piping at kipsonoi | Water tank and piping at kipsonoi constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.445935, 35.637348 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 0 | 2550000 | Equitable | N/A | 2550000 | 0 | 799008 | 100 | 799008 | 293202 | -799008 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4572 | Water and Sewerage Management | Drilling Of Borehole at Mwangate-Kipsonoi | To provide access to clean water through borehole drilling at Mwangate-Kipsonoi | Borehole drilled at Mwangate-Kipsonoi | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.445992, 35.637537 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 3800000 | 0 | 1099607.01 | Equitable | N/A | 1099607.01 | 0 | 2700393 | 100 | 2700393 | 1099607 | -2700393 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4573 | Water and Sewerage Management | Drilling of Kapkwen water borehole | To implement drilling of kapkwen water borehole for access to clean water and environmental sustainability | Drilling of Kapkwen water borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463371, 35.70985 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 2800000 | Equitable | N/A | 2800000 | 0 | 627823 | 20.9 | 627823 | 627823 | 2372177 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It will. Viable: It will. Assessor remarks: To be drilled at 2.8 million.
4574 | Water and Sewerage Management | Installation Of Water Tank, Fencing And Piping At Silibwet Water Project | To install Water Tank, Fencing And Piping At Silibwet Water Project | Water Tank, Fencing And Piping At Silibwet Water Project installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471103 35.6416 2687.900146484375 5.099999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1277612 | 319.4 | 1277612 | 400000 | -877612 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4575 | Water and Sewerage Management | Piping Of Chebaraa-Sororik Water Project | To provide water distribution infrastructure at Chebaraa-Sororik Water Project | Water piping at Chebaraa-Sororik Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471592, 35.683057 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 300369 | 0 | 300369 | Equitable | N/A | 300369 | 0 | 966983 | 100 | 966983 | 300369 | -966983 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operation al.
4576 | Water and Sewerage Management | Piping Of Kapkwen -Canaan Kapungut | To provide water distribution infrastructure at Kapkwen -Canaan Kapungut | Water piping at Kapkwen -Canaan Kapungut completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463428, 35.709877 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
4577 | Water and Sewerage Management | Piping Of Water at Tendwet | To provide water distribution infrastructure at Water at Tendwet | Water piping at Water at Tendwet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2020 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 966983 | 74.4 | 966983 | 333017 | 333017 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
4578 | Water and Sewerage Management | Piping Of Water from Kapjoshua-Daraja Mawe | To provide water distribution infrastructure at Water from Kapjoshua-Daraja Mawe | Water piping at Water from Kapjoshua-Daraja Mawe completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 333017 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
4579 | Water and Sewerage Management | Piping Of Water from Lelaibei Primary South Wards | To provide water distribution infrastructure at Water from Lelaibei Primary South Wards | Water piping at Water from Lelaibei Primary South Wards completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1397986 | 100 | 1397986 | 1000000 | -1397986 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
4580 | Water and Sewerage Management | Piping Of Water Sigowet/Soitaran -Tabaita Nursery School | To provide water distribution infrastructure at Water Sigowet/Soitaran -Tabaita Nursery School | Water piping at Water Sigowet/Soitaran -Tabaita Nursery School completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417828, 35.723693 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2022 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1397986 | 100 | 1397986 | 1000000 | -1397986 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4581 | Water and Sewerage Management | Piping Of Water Siwot Primary -Kipkoibet | To provide water distribution infrastructure at Water Siwot Primary -Kipkoibet | Water piping at Water Siwot Primary -Kipkoibet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1544000 | 1544000 | 1544000 | Equitable | N/A | 1544000 | 0 | 1397986 | 90.5 | 1397986 | 146014 | 146014 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
4582 | Water and Sewerage Management | Purchase And Supply Of Water Pipes In Keringet Ward | To procure and supply Water Pipes In Keringet Ward | Water Pipes In Keringet Ward procured and supplied | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417738, 35.723725 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2024 | 1555411 | 0 | 1059820 | Equitable | N/A | 1059820 | 0 | 3400000 | 100 | 3400000 | 1089820 | -3400000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4583 | Water and Sewerage Management | Purchase of a skip | To procure a skip | A skip procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.427111 35.693151 2683.500244140625 40.32899856567383 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: 2017. Assessor remarks: Bought but no bus park.
4584 | Water and Sewerage Management | Drilling and equipping of a borehole in Kiamaina ward | To implement drilling and equipping of a borehole in kiamaina ward for access to clean water and environmental sustainability | Drilling and equipping of a borehole in Kiamaina ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.261981 36.105315 1904.5999755859375 58.125999450683594 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1998693 | 40 | 1998693 | 5000000 | 3001307 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
4585 | Water and Sewerage Management | Proposed water works in Menengai and Kiamaina sub locations | To undertake the proposed water works in Menengai and Kiamaina sub locations | Proposed water works in Menengai and Kiamaina sub locations implemented | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.234695, 36.103767 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 6283710 | 100 | 6283710 | 25750 | -6283710 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Yes after completion. Viable: Yes if it will be complete. Assessor remarks: The contractor is on site.
4586 | Water and Sewerage Management | Purchase and supply of water pipes for Kiamaina and Gituamba water projects | To procure and supply water pipes for Kiamaina and Gituamba water projects | Water pipes for Kiamaina and Gituamba water projects procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.246945 36.092048 2193.000244140625 8.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 6283710 | 261.8 | 6283710 | 25750 | -3883710 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: No water on the lines from last year.
4587 | Water and Sewerage Management | Purchase and supply of water pipes for Menengai water project and Kiamaina water projects | To procure and supply water pipes for Menengai water project and Kiamaina water projects | Water pipes for Menengai water project and Kiamaina water projects procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.246945 36.092048 2193.000244140625 8.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 6500000 | 6309460.4 | 6309460.4 | Equitable | N/A | 6309460.4 | 0 | 6283710 | 99.6 | 6283710 | 25750 | 25750.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: No water on the lines from last year.
4588 | Water and Sewerage Management | Supply of water pipes in upper heshima | To implement supply of water pipes in upper heshima for access to clean water and environmental sustainability | Supply of water pipes in upper heshima completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.240658 36.110485 1920.5999755859375 2.799999952316284 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1126601 | 93.9 | 1126601 | 73399 | 73399 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipes were laid on Heshima water project.
4589 | Water and Sewerage Management | Construction of Elevated water tank for 2 no. 10,000L plastic tanks at Lusiru | To construct Elevated water tank for 2 no. 10,000L plastic tanks at Lusiru | Elevated water tank for 2 no. 10,000L plastic tanks at Lusiru constructed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.499133, 35.998548 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chelewa construction limited. Assessor remarks: Good.
4590 | Water and Sewerage Management | Mutito A Water Project - Drilling Of Borehole , Construction Of Water Tank And Water Kiosk And Piping Mutito A Water Project | To implement mutito a water project - drilling of borehole , construction of water tank and water kiosk and piping mutito a water project for access to clean water and environmental sustainability | Mutito A Water Project - Drilling Of Borehole , Construction Of Water Tank And Water Kiosk And Piping Mutito A Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.433157, 35.959162 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2016/17 | 2016/17 | 2024 | 6000000 | 0 | 2634393.2 | Equitable | N/A | 2634393.2 | 0 | 3145607 | 100 | 3145607 | 2854393 | -3145607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires fencing.
4591 | Water and Sewerage Management | Piping Of Mugumoini & Lusiru Water Project | To provide water distribution infrastructure at Mugumoini & Lusiru Water Project | Water piping at Mugumoini & Lusiru Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1811154 | 90.6 | 1811154 | 188846 | 188846 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
4592 | Water and Sewerage Management | Piping of Stoo Mbili water project and Mutitua Jirani Kio water project | To provide water distribution infrastructure at Stoo Mbili water project and Mutitua Jirani Kio water project | Water piping at Stoo Mbili water project and Mutitua Jirani Kio water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 3793061 | 3793061 | Equitable | N/A | 3793061 | 0 | 3793061 | 100 | 3793061 | 3793061 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
4593 | Water and Sewerage Management | Piping Of Stoo Mbili Water Project | To provide water distribution infrastructure at Stoo Mbili Water Project | Water piping at Stoo Mbili Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1387546 | 92.5 | 1387546 | 112454 | 112454 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
4594 | Water and Sewerage Management | Piping Of Subuku Water Project | To provide water distribution infrastructure at Subuku Water Project | Water piping at Subuku Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1387546 | 92.5 | 1387546 | 1500000 | 112454 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
4595 | Water and Sewerage Management | Purchase and supply of Mutitu A,Mutitu B and Subuku water project | To procure and supply Mutitu A,Mutitu B and Subuku water project | Mutitu A,Mutitu B and Subuku water project procured and supplied | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.42206 35.969528 2213.5 11.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 983325 | 44.7 | 983325 | 1000000 | 1216675 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
4596 | Water and Sewerage Management | Completion of Chebotoi, Ainamoi & Wamgong water projects | To complete Chebotoi, Ainamoi & Wamgong water projects | Chebotoi, Ainamoi & Wamgong water projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 4617560 | 4560447 | 4560447 | Equitable | N/A | 4560447 | 0 | 4560447 | 100 | 4560447 | 4560447 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
4597 | Water and Sewerage Management | Construction of water tank in Wamkong and piping | To construct water tank in Wamkong and piping | Water tank in Wamkong and piping constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.583585, 35.628392 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 3998496 | 285.6 | 3998496 | 4000000 | -2598496 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Assessor remarks: Yet to start.
4598 | Water and Sewerage Management | Kiborowa water project | To implement kiborowa water project for access to clean water and environmental sustainability | Kiborowa water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.583552 35.62763 2445.7 97.30000305175781 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1600000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910824 | 91.1 | 910824 | 1000000 | 89176 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has not been operationalized..
4599 | Water and Sewerage Management | Saptet Water Project | To implement saptet water project for access to clean water and environmental sustainability | Saptet Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1995987 | 100 | 1995987 | 1000000 | -1995987 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
4600 | Water and Sewerage Management | Drilling of Kio Water Project | To implement drilling of kio water project for access to clean water and environmental sustainability | Drilling of Kio Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.35799 35.554583 2617.9 8.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 3600000 | 2448600 | 2448600 | Equitable | N/A | 2448600 | 0 | 2444006 | 99.8 | 2444006 | 4594 | 4594 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4601 | Water and Sewerage Management | Piping in Kiptororo Center | To provide water distribution infrastructure at in Kiptororo Center | Water piping at in Kiptororo Center completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.385457, 35.486922 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 1262298.2 | Equitable | N/A | 1262298.2 | 0 | 737702 | 36.9 | 737702 | 1262298 | 1262298 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The piping has not been done.
4602 | Water and Sewerage Management | Piping of Kongoi water project | To provide water distribution infrastructure at Kongoi water project | Water piping at Kongoi water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.35799 35.554583 2617.9 8.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2800000 | 140 | 2800000 | 2800000 | -800000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4603 | Water and Sewerage Management | Sondu River village water project | To implement sondu river village water project for access to clean water and environmental sustainability | Sondu River village water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.295214, 35.490189 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3000456 | 85.7 | 3000456 | 499544 | 499544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole was drilled.
4604 | Water and Sewerage Management | Piping Of Water at Kayole Near Safar Centre Mall and Banda Village | To provide water distribution infrastructure at Water at Kayole Near Safar Centre Mall and Banda Village | Water piping at Water at Kayole Near Safar Centre Mall and Banda Village completed | 3110502 | Water Supplies and Sewerage | Naivasha | Lake View | -0.754601, 36.469403 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2802199 | 93.4 | 2802199 | 197801 | 197801 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Naivawasco supplied with pipes for laying.
4605 | Water and Sewerage Management | Drilling of borehole at Nyonjoro Dispensary | To provide access to clean water through borehole drilling at Nyonjoro Dispensary | Borehole drilled at Nyonjoro Dispensary | 3110502 | Water Supplies and Sewerage | Bahati | Lanet Umoja | -0.247859, 36.151991 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/2024 | 10500000 | 8054012.4 | 8054012.4 | Equitable | N/A | 8054012.4 | 0 | 8054012 | 100 | 8054012 | 8054012 | 0.4 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
4606 | Water and Sewerage Management | Waterworks for Murunyu water project | To implement waterworks for murunyu water project for access to clean water and environmental sustainability | Waterworks for Murunyu water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet Umoja | -0.254124, 36.160413 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1786771 | 89.3 | 1786771 | 213229 | 213229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Partially.
4607 | Water and Sewerage Management | Piping of water within Lanet-Umoja ward | To provide water distribution infrastructure at water within Lanet-Umoja ward | Water piping at water within Lanet-Umoja ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet-Umoja | -0.280857, 36.174009 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Awaiting connection by NAWASCO.
4608 | Water and Sewerage Management | Water works at Nyonjoro, Ndege ndimu and Murunyu | To implement water works at nyonjoro, ndege ndimu and murunyu for access to clean water and environmental sustainability | Water works at Nyonjoro, Ndege ndimu and Murunyu completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet-Umoja | -0.247914, 36.152229 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but not functioning. Assessor remarks: Awaiting borehole installation.
4609 | Water and Sewerage Management | Drilling Of Borehole at Murunyu Dispensary | To provide access to clean water through borehole drilling at Murunyu Dispensary | Borehole drilled at Murunyu Dispensary | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.247859, 36.151991 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2023/2024 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1773886 | 44.3 | 1773886 | 2226114 | 2226114 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
4610 | Water and Sewerage Management | Equipping Of Ndege-Ndimu Primary Bore-Hole with Pump | To equip Ndege-Ndimu Primary Bore-Hole with Pump with necessary facilities and equipment | Ndege-Ndimu Primary Bore-Hole with Pump equipped | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.313208, 36.173637 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 0 | 940721.65 | Equitable | N/A | 940721.65 | 0 | 3059278 | 100 | 3059278 | 940722 | -3059278 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4611 | Water and Sewerage Management | Water Works - Piping in Lanet-Umoja Ward | To implement water works - piping in lanet-umoja ward for access to clean water and environmental sustainability | Water Works - Piping in Lanet-Umoja Ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.277157, 36.182097 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Awaiting NAWASCO connection.
4612 | Water and Sewerage Management | Drilling of Lare borehole | To implement drilling of lare borehole for access to clean water and environmental sustainability | Drilling of Lare borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.449043 36.052612 2039.3 8.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2800000 | 2625300.4 | 2625300.4 | Equitable | N/A | 2625300.4 | 0 | 2625300 | 100 | 2625300 | 2625300 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
4613 | Water and Sewerage Management | Installation Of HDPE Water Pipes, Construction of A Water Kiosk and A 10,000 L Water Tank at Mugumo | To install HDPE Water Pipes, Construction of A Water Kiosk and A 10,000 L Water Tank at Mugumo | HDPE Water Pipes, Construction of A Water Kiosk and A 10,000 L Water Tank at Mugumo installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.512937 36.024443 2326.4 6.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1411998 | 83.1 | 1411998 | 288002 | 288002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more durable piping's for distribution.
4614 | Water and Sewerage Management | Installation Of Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria | To install Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria | Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | 2024 | 1133898 | 1122232.14 | 1122232.14 | Equitable | N/A | 1122232.14 | 0 | 1010009 | 90 | 1010009 | 112223 | 112223.14 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
4615 | Water and Sewerage Management | Maai Mahiu Water Works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 10495436 | 17617214.4 | 26331564.5 | Equitable | N/A | 26331564.5 | 0 | 2176522 | 12.4 | 2176522 | 8318914 | 15440692.4 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4616 | Water and Sewerage Management | Muthaiga, Mogas Kamuchira Water Works | To implement muthaiga, mogas kamuchira water works for access to clean water and environmental sustainability | Muthaiga, Mogas Kamuchira Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -0.977107, 36.584909 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9452446 | 94.5 | 9452446 | 547554 | 547554 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project highly impactful.
4617 | Water and Sewerage Management | Nyakinyua, Rare and Old Kijabe Water Works | To implement nyakinyua, rare and old kijabe water works for access to clean water and environmental sustainability | Nyakinyua, Rare and Old Kijabe Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1350000 | 90 | 1350000 | 150000 | 150000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4618 | Water and Sewerage Management | Water works in Maai Mahiu ward | To implement water works in maai mahiu ward for access to clean water and environmental sustainability | Water works in Maai Mahiu ward completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -0.980225, 36.578677 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 7429608 | 0 | 7205444.4 | Equitable | N/A | 7205444.4 | 0 | 0 | 0 | 0 | 7205444 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Trenches affected by erosion.
4619 | Water and Sewerage Management | Construction of high tower steel tank at Tumaini | To construct high tower steel tank at Tumaini | High tower steel tank at Tumaini constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 313361 | 18.4 | 313361 | 1500000 | 1386639 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
4620 | Water and Sewerage Management | Drilling of borehole at Kirima | To provide access to clean water through borehole drilling at Kirima | Borehole drilled at Kirima | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.83119 36.203515 0 156.89999389648438 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
4621 | Water and Sewerage Management | Drilling Of Borehole At Natooli Water Project | To provide access to clean water through borehole drilling at Natooli Water Project | Borehole drilled at Natooli Water Project | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.824917 36.203913 0 400 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | N/A | 3400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 584820 | 24.4 | 584820 | 2400000 | 1815180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
4622 | Water and Sewerage Management | Maiella Water Works in the ward | To implement maiella water works in the ward for access to clean water and environmental sustainability | Maiella Water Works in the ward completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 1600000 | Equitable | N/A | 1600000 | 0 | 1649700 | 100 | 1649700 | 1600000 | -1649700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
4623 | Water and Sewerage Management | Natooli water works | To implement natooli water works for access to clean water and environmental sustainability | Natooli water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.863628 36.18653 2353.60009765625 13.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4600000 | 4600000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2229403 | 48.5 | 2229403 | 270597 | 2370597 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Ltd. Assessor remarks: very good workmanship.
4624 | Water and Sewerage Management | Other Water Works in the ward | To implement other water works in the ward for access to clean water and environmental sustainability | Other Water Works in the ward completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1649700 | 82.5 | 1649700 | 350300 | 350300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4625 | Water and Sewerage Management | Piping And Connection Of Water At Maiella | To provide water distribution infrastructure at And Connection Of Water At Maiella | Water piping at And Connection Of Water At Maiella completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 5782480 | 0 | 2510600 | Equitable | N/A | 2510600 | 0 | 3094231 | 100 | 3094231 | 2510600 | -3094231 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
4626 | Water and Sewerage Management | Piping and installation of solar panels at Sero water project and Kipkonyo | To provide water distribution infrastructure at and installation of solar panels at Sero water project and Kipkonyo | Water piping at and installation of solar panels at Sero water project and Kipkonyo completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 5788040 | 5788040 | Equitable | N/A | 5788040 | 0 | 5788040 | 100 | 5788040 | 5788040 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
4627 | Water and Sewerage Management | Piping of Kianugu water project | To provide water distribution infrastructure at Kianugu water project | Water piping at Kianugu water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.831379, 36.205242 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 692123 | 692123 | 692123 | Equitable | N/A | 692123 | 0 | 584820 | 84.5 | 584820 | 107303 | 107303 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Aronnet Suppliers Co Ltd. Assessor remarks: In Use....
4628 | Water and Sewerage Management | Purchase and supply of water pipes across the ward | To procure and supply water pipes across the ward | Water pipes across the ward procured and supplied | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2200000 | 0 | 2200000 | Equitable | N/A | 2200000 | 0 | 1883327 | 100 | 1883327 | 644990 | -1883327 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4629 | Water and Sewerage Management | Water piping from Sero to Kongoni | To implement water piping from sero to kongoni for access to clean water and environmental sustainability | Water piping from Sero to Kongoni completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.804403, 36.248343 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023 | 600000 | 569375 | 569375 | Equitable | N/A | 569375 | 0 | 569375 | 100 | 569375 | 569375 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nemoca Enterprises Ltd. Assessor remarks: In use.
4630 | Water and Sewerage Management | Borehole drilling in Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | To provide access to clean water through borehole drilling at Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | Borehole drilled at Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.648649, 36.488825 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/24 | 5000000 | 2501128 | 2501128 | Equitable | N/A | 2501128 | 0 | 2207666 | 88.3 | 2207666 | 293462 | 293462 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4631 | Water and Sewerage Management | Installation of 12m high steel water tower, tank, inverter, water booster & Piping at Gathengera water project | To install 12m high steel water tower, tank, inverter, water booster & Piping at Gathengera water project | 12m high steel water tower, tank, inverter, water booster & Piping at Gathengera water project installed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.684685, 36.471073 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 4316500 | 3300000 | 4316551 | Equitable | N/A | 4316551 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4632 | Water and Sewerage Management | Installation of 12m high steel water tower, tank, inverter, water booster & Piping at Nyondia water project | To install 12m high steel water tower, tank, inverter, water booster & Piping at Nyondia water project | 12m high steel water tower, tank, inverter, water booster & Piping at Nyondia water project installed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.684685, 36.471073 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 4316500 | 3300000 | 4316500 | Equitable | N/A | 4316500 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4633 | Water and Sewerage Management | Installation of Water pump at St John water project | To install Water pump at St John water project | Water pump at St John water project installed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.648649, 36.488825 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1410490 | 94 | 1410490 | 89510 | 89510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4634 | Water and Sewerage Management | Malewa West Water Work - Drilling Of 4 Boreholes, Construction Of Tanks And Installation Of Solar Water Pump And Piping Of Water Of Gatamaiyu, Kwa Njonjo, Nyondia And Karati Centre Boreholes And Kasarani Solar Water Pump | To implement malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of gatamaiyu, kwa njonjo, nyondia and karati centre boreholes and kasarani solar water pump for access to clean water and environmental sustainability | Malewa West Water Work - Drilling Of 4 Boreholes, Construction Of Tanks And Installation Of Solar Water Pump And Piping Of Water Of Gatamaiyu, Kwa Njonjo, Nyondia And Karati Centre Boreholes And Kasarani Solar Water Pump completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.471211 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2017/18 | 2017/18 | 2021/22 | 4229322 | 3558689 | 3558689 | Equitable | N/A | 3558689 | 0 | 3099636 | 87.1 | 3099636 | 459053 | 459053 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well maintained.
4635 | Water and Sewerage Management | Piping From Kasarani To Tarambeta Landing Beach | To provide water distribution infrastructure at From Kasarani To Tarambeta Landing Beach | Water piping at From Kasarani To Tarambeta Landing Beach completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.291018 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2921/22 | 1180279 | 1180279 | 1180279 | Equitable | N/A | 1180279 | 0 | 1180279 | 100 | 1180279 | 1180279 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More connectivity needed.
4636 | Water and Sewerage Management | Piping Network for Water Distribution in Malewa west ward | To provide water distribution infrastructure at Network for Water Distribution in Malewa west ward | Water piping at Network for Water Distribution in Malewa west ward completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.540541 36.34396 0 2000 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 1206728.83 | Equitable | N/A | 1206728.83 | 0 | 2773271 | 100 | 2773271 | 1226729 | -2773271 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
4637 | Water and Sewerage Management | Digital water works | To implement digital water works for access to clean water and environmental sustainability | Digital water works completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.336516 35.875599 2348 27.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2024/25 | 2024/25 | 4000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2759821 | 39.4 | 2759821 | 240179 | 4240179 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Pipes are not working thus no supply of water.
4638 | Water and Sewerage Management | Ndoswa Borehole Drilling and Equipping | To implement ndoswa borehole drilling and equipping for access to clean water and environmental sustainability | Ndoswa Borehole Drilling and Equipping completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.366546 35.84684 2635.0971961053706 7.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water.
4639 | Water and Sewerage Management | Ndoswa water works | To implement ndoswa water works for access to clean water and environmental sustainability | Ndoswa water works completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.361681, 35.845651 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2759821 | 100 | 2759821 | 2000000 | -2759821 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4640 | Water and Sewerage Management | Piping Sachangwan Lawina Water Project | To provide water distribution infrastructure at Sachangwan Lawina Water Project | Water piping at Sachangwan Lawina Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.343994, 35.846228 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 0 | 4874476.6 | Equitable | N/A | 4874476.6 | 0 | 921890 | 100 | 921890 | 4874477 | -921890 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational thus no water supply.
4641 | Water and Sewerage Management | Spring protection at Daraja Mungu | To implement spring protection at daraja mungu for access to clean water and environmental sustainability | Spring protection at Daraja Mungu completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.373347, 35.777606 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
4642 | Water and Sewerage Management | Purchase and supply of water pipes in mau narok ward | To procure and supply water pipes in mau narok ward | Water pipes in mau narok ward procured and supplied | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.529072 35.968285 2526.1000000000004 10.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: In Procurement 2024/2025.
4643 | Water and Sewerage Management | Repair of water tank, Piping and Purchase of Two 5,000L Water Tanks at Ngwataniro Borehole | To rehabilitate water tank, Piping and Purchase of Two 5,000L Water Tanks at Ngwataniro Borehole to restore functionality | Water tank, Piping and Purchase of Two 5,000L Water Tanks at Ngwataniro Borehole rehabilitated | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2278000 | 94.9 | 2278000 | 122000 | 122000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
4644 | Water and Sewerage Management | Drilling Of a borehole in mauche ward water works | To implement drilling of a borehole in mauche ward water works for access to clean water and environmental sustainability | Drilling Of a borehole in mauche ward water works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.454487, 35.932407 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2431685 | 100 | 2431685 | 3000000 | -2431685 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Awaiting solarization.
4645 | Water and Sewerage Management | Drilling Of Chesoen water project | To implement drilling of chesoen water project for access to clean water and environmental sustainability | Drilling Of Chesoen water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.543692, 36.030627 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 3500000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 2861233 | 92.3 | 2861233 | 238767 | 238767 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4646 | Water and Sewerage Management | Drilling Of Kapkembu - Chebitet Water Project | To implement drilling of kapkembu - chebitet water project for access to clean water and environmental sustainability | Drilling Of Kapkembu - Chebitet Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.490862, 35.945857 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2861233 | 100 | 2861233 | 3000000 | -2861233 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs equipment.
4647 | Water and Sewerage Management | Drilling Of Kapkembu Water Project | To implement drilling of kapkembu water project for access to clean water and environmental sustainability | Drilling Of Kapkembu Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.543692, 36.030627 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2498918 | 100 | 2498918 | 3000000 | -2498918 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4648 | Water and Sewerage Management | Kamungei Water works | To implement kamungei water works for access to clean water and environmental sustainability | Kamungei Water works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.438183 35.939877 2329.2000000000003 10.899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2495244 | 0 | 1706101.8 | Equitable | N/A | 1706101.8 | 0 | 490065 | 100 | 490065 | 1706102 | -490065 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
4649 | Water and Sewerage Management | Ororwet Water Works | To implement ororwet water works for access to clean water and environmental sustainability | Ororwet Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.438183 35.939877 2329.2000000000003 10.899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 490065 | 100 | 490065 | 1500000 | -490065 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
4650 | Water and Sewerage Management | Piping Of Kanyiriri Water Springs | To provide water distribution infrastructure at Kanyiriri Water Springs | Water piping at Kanyiriri Water Springs completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.490862, 35.945857 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2498918 | 100 | 2498918 | 1000000 | -2498918 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs equipment.
4651 | Water and Sewerage Management | Piping Of Tuiyotich Water Projects and Construction of Water Kiosks at Tuiyotich, Teret and Basiriat | To provide water distribution infrastructure at Tuiyotich Water Projects and Construction of Water Kiosks at Tuiyotich, Teret and Basiriat | Water piping at Tuiyotich Water Projects and Construction of Water Kiosks at Tuiyotich, Teret and Basiriat completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2233963 | 2233963 | 691953.01 | Equitable | N/A | 691953.01 | 0 | 1542010 | 69 | 1542010 | 691953 | 691953 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4652 | Water and Sewerage Management | Piping of water projects, Tachasis, Kaptich, Kamungei, Likia police, kapsir, Kusumek, takitech, spring improvement sugutek, Koisomo | To provide water distribution infrastructure at water projects, Tachasis, Kaptich, Kamungei, Likia police, kapsir, Kusumek, takitech, spring improvement sugutek, Koisomo | Water piping at water projects, Tachasis, Kaptich, Kamungei, Likia police, kapsir, Kusumek, takitech, spring improvement sugutek, Koisomo completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 8010000 | 8010000 | 6010000 | Equitable | N/A | 6010000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4653 | Water and Sewerage Management | Supply of pipes for Kapsir, Kaptich water projects and Tendwet Village-Kamaasai | To implement supply of pipes for kapsir, kaptich water projects and tendwet village-kamaasai for access to clean water and environmental sustainability | Supply of pipes for Kapsir, Kaptich water projects and Tendwet Village-Kamaasai completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.497753, 35.960733 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023 | 2000000 | 1864245.11 | 1864245.11 | Equitable | N/A | 1864245.11 | 0 | 1589751 | 85.3 | 1589751 | 274494 | 274494.11 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4654 | Water and Sewerage Management | Borehole Drilling in Mercy Njeri or Maciaro | To provide access to clean water through borehole drilling at Mercy Njeri or Maciaro | Borehole drilled at Mercy Njeri or Maciaro | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.144462, 36.009498 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 3550000 | 3500195.6 | 1641528.6 | Equitable | N/A | 1641528.6 | 0 | 1858667 | 53.1 | 1858667 | 1641529 | 1641528.6 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Borehole did not yield water.
4655 | Water and Sewerage Management | Menengai West Water Works | To implement menengai west water works for access to clean water and environmental sustainability | Menengai West Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.168207, 35.999097 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 3902062.4 | 7402062.4 | 11304124.8 | Equitable | N/A | 11304124.8 | 0 | 0 | 0 | 0 | 3902062 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Contractor: Brightons. Assessor remarks: Yet to start.
4656 | Water and Sewerage Management | Rehabilitation of Ol- Rongai - Kwa Nyayo Borehole, Building of a water kiosk and water piping at Ol - Rongai. | To rehabilitate Ol- Rongai - Kwa Nyayo Borehole, Building of a water kiosk and water piping at Ol - Rongai to restore functionality | Ol- Rongai - Kwa Nyayo Borehole, Building of a water kiosk and water piping at Ol - Rongai rehabilitated | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.168313, 35.999075 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4794500 | 95.9 | 4794500 | 205500 | 205500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Partially met. Viable: Yes. Assessor remarks: Not yet complete.
4657 | Water and Sewerage Management | Water Piping in Ol-Rongai Number 4 Milimani area | To implement water piping in ol-rongai number 4 milimani area for access to clean water and environmental sustainability | Water Piping in Ol-Rongai Number 4 Milimani area completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.178417, 35.990588 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2600000 | 0 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 2600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4658 | Water and Sewerage Management | Completion Of Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop | To complete Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop | Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop completed | 3110502 | Water Supplies and Sewerage | Molo | Molo | -0.176436, 35.708094 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2023/2024 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070400 | 97.3 | 1070400 | 29600 | 29600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Viable.
4659 | Water and Sewerage Management | Construction Of A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan | To construct A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan | A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1195366.08 | 1195366.08 | Equitable | N/A | 1195366.08 | 0 | 1195366 | 100 | 1195366 | 1195366 | 0.08 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4660 | Water and Sewerage Management | Construction of Sachangwan water tank | To construct Sachangwan water tank | Sachangwan water tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo | -0.240585, 35.715565 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2019/20 | 2000000 | 1765520 | 1765520 | Equitable | N/A | 1765520 | 0 | 1765520 | 100 | 1765520 | 33 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice one.
4661 | Water and Sewerage Management | Drilling Of Borehole at Kabianga | To provide access to clean water through borehole drilling at Kabianga | Borehole drilled at Kabianga | 3110502 | Water Supplies and Sewerage | Molo | Molo | -0.233645, 35.772022 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3600000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 1308000 | 100 | 1308000 | 3600000 | -1308000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yest to start. Contractor: Holy and Sons ltd. Assessor remarks: Commendable but not complete.
4662 | Water and Sewerage Management | Proposed Mukinyai borehole, equipping, fencing, piping and tank repair | To undertake the proposed Mukinyai borehole, equipping, fencing, piping and tank repair | Proposed Mukinyai borehole, equipping, fencing, piping and tank repair implemented | 3110502 | Water Supplies and Sewerage | Molo | Molo | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000704 | 3000704 | 3000704 | Equitable | N/A | 3000704 | 0 | 2959485 | 98.6 | 2959485 | 41219 | 41219 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4663 | Water and Sewerage Management | Everbest water piping | To implement everbest water piping for access to clean water and environmental sustainability | Everbest water piping completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4664 | Water and Sewerage Management | Michuna water water project (Piping/purchase of pipes) | To implement michuna water water project (piping/purchase of pipes) for access to clean water and environmental sustainability | Michuna water water project (Piping/purchase of pipes) completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4665 | Water and Sewerage Management | Piping of Kiambogo water | To provide water distribution infrastructure at Kiambogo water | Water piping at Kiambogo water completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4666 | Water and Sewerage Management | Piping of migaa/mukinyai water project | To provide water distribution infrastructure at migaa/mukinyai water project | Water piping at migaa/mukinyai water project completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3805194 | 380.5 | 3805194 | 5000000 | -2805194 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4667 | Water and Sewerage Management | Water piping at sachangwan borehole | To implement water piping at sachangwan borehole for access to clean water and environmental sustainability | Water piping at sachangwan borehole completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4668 | Water and Sewerage Management | water piping in Kabianga,Tumaini and Borop | To implement water piping in kabianga,tumaini and borop for access to clean water and environmental sustainability | water piping in Kabianga,Tumaini and Borop completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 19985041 | 0 | 19985041 | 14959 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4669 | Water and Sewerage Management | Construction Of Water Tank And Piping At Matuiku Water Project | To construct Water Tank And Piping At Matuiku Water Project | Water Tank And Piping At Matuiku Water Project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.24922 35.83006 2174.3999999999996 7 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 1400000 | 1389494 | 1389494 | Equitable | N/A | 1389494 | 0 | 1389494 | 100 | 1389494 | 1389494 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Chapakaz. Assessor remarks: Good work.
4670 | Water and Sewerage Management | Construction Of Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project | To construct Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project | Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 1400000 | 0 | 1355625 | Equitable | N/A | 1355625 | 0 | 1389494 | 100 | 1389494 | 1395625 | -1389494 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
4671 | Water and Sewerage Management | Drilling and equipping of Ogilgei Borehole | To implement drilling and equipping of ogilgei borehole for access to clean water and environmental sustainability | Drilling and equipping of Ogilgei Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.30221, 35.952852 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2024 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 2857319 | 100 | 2857319 | 3500000 | -2857319 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Not yet awarded. Assessor remarks: Not yet awarded.
4672 | Water and Sewerage Management | Mbama Intake Project - Intake Works | To implement mbama intake project - intake works for access to clean water and environmental sustainability | Mbama Intake Project - Intake Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.21216, 35.816242 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2017/18 | 2017/18 | 2022 | 3093894 | 1387151 | 1387151 | Equitable | N/A | 1387151 | 0 | 1356326 | 97.8 | 1356326 | 30825 | 30825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Contractor: Roy n alvis. Assessor remarks: Stalled.
4673 | Water and Sewerage Management | Piping Kapkatet area | To provide water distribution infrastructure at Kapkatet area | Water piping at Kapkatet area completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.302632, 35.977288 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 0 | 0 | 0 | 838570 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. Contractor: Yet to start. Assessor remarks: Yet to start.
4674 | Water and Sewerage Management | Piping Matuiku water tank | To provide water distribution infrastructure at Matuiku water tank | Water piping at Matuiku water tank completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.247993, 35.809123 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2495931 | 166.4 | 2495931 | 700000 | -995931 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. Contractor: Not awarded. Assessor remarks: Not awarded.
4675 | Water and Sewerage Management | Piping Of Ngecha B Water Project | To provide water distribution infrastructure at Ngecha B Water Project | Water piping at Ngecha B Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | To be vired | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1880400 | 99 | 1880400 | 19600 | 19600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
4676 | Water and Sewerage Management | Pipping at Kerma Water Project | To implement pipping at kerma water project for access to clean water and environmental sustainability | Pipping at Kerma Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | To be vired | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 2495931 | 100 | 2495931 | 700000 | -2495931 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
4677 | Water and Sewerage Management | Gitare Borehole Water Works | To implement gitare borehole water works for access to clean water and environmental sustainability | Gitare Borehole Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Murindat | -0.411137, 36.311427 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 584640 | 100 | 584640 | 1000000 | -584640 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not done. Viable: Yet to start. Assessor remarks: Not done.
4678 | Water and Sewerage Management | Piping in Sision And Solarization of Ihindu Borehole | To provide water distribution infrastructure at in Sision And Solarization of Ihindu Borehole | Water piping at in Sision And Solarization of Ihindu Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.866935 36.535393 2473 6.122000217437744 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 859534.37 | Equitable | N/A | 859534.37 | 0 | 1140466 | 100 | 1140466 | 859534 | -1140466 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state of repair.
4679 | Water and Sewerage Management | Piping And Construction of a Reservoir Tank at Mwariki B Substation | To provide water distribution infrastructure at And Construction of a Reservoir Tank at Mwariki B Substation | Water piping at And Construction of a Reservoir Tank at Mwariki B Substation completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Nakuru East | -0.369593, 36.149855 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4355267 | 87.1 | 4355267 | 644733 | 644733 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Teribel trading limited. Assessor remarks: Tank not constructed but piping.
4680 | Water and Sewerage Management | Supply of water pipes in Mwariki B sub-location | To implement supply of water pipes in mwariki b sub-location for access to clean water and environmental sustainability | Supply of water pipes in Mwariki B sub-location completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Nakuru East | -0.369675, 36.149693 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not adequate.
4681 | Water and Sewerage Management | Construction of 100,000L water tank and piping at Kipkogo borehole | To construct 100,000L water tank and piping at Kipkogo borehole | 100,000L water tank and piping at Kipkogo borehole constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.41201, 35.936917 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2025/26 | 5000000 | 0 | 3094832.31 | Equitable | N/A | 3094832.31 | 0 | 1554958 | 100 | 1554958 | 3094832 | -1554958 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Ongoing. Viable: Ongoing. Assessor remarks: Five water kiosk for Tagitech Water project and 800 meters piping.
4682 | Water and Sewerage Management | Installation Of Tanks and Pipes in Tuei Water Project | To install Tanks and Pipes in Tuei Water Project | Tanks and Pipes in Tuei Water Project installed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3600000 | 0 | 525490.17 | Equitable | N/A | 525490.17 | 0 | 3574510 | 100 | 3574510 | 525490 | -3574510 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
4683 | Water and Sewerage Management | Pipe work at Tagitech Water project | To implement pipe work at tagitech water project for access to clean water and environmental sustainability | Pipe work at Tagitech Water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.433546 35.919276 2580.4533775178716 23.47406768798828 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom currently is being used as a staffroom because the population has grown thereby the classroom not fitting the number of pupils.
4684 | Water and Sewerage Management | Piping And Installation of Water Tanks at Kipkogo Water Project | To provide water distribution infrastructure at And Installation of Water Tanks at Kipkogo Water Project | Water piping at And Installation of Water Tanks at Kipkogo Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.392896 35.898763 2388.13560622558 27.98659896850586 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3692602 | 92.3 | 3692602 | 307398 | 307398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
4685 | Water and Sewerage Management | Piping Of Cheptoroi Water Project | To provide water distribution infrastructure at Cheptoroi Water Project | Water piping at Cheptoroi Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.371206 35.897919 2387.2192822886027 3.7899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3692602 | 100 | 3692602 | 3000000 | -3692602 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Jozkim enterprises. Assessor remarks: The road is functional and serving residents well.
4686 | Water and Sewerage Management | Takitech Borehole Water Works | To implement takitech borehole water works for access to clean water and environmental sustainability | Takitech Borehole Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.424694, 35.92853 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2019/20 | 4931746 | 0 | 4021803 | Equitable | N/A | 4021803 | 0 | 5913775 | 100 | 5913775 | 4021803 | -5913775 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds were used to construct 50M³ masonry water tank at Ruto's residence and piping done from the borehole to the water tank.
4687 | Water and Sewerage Management | Construction Of Storage Water Tank In Upper Piane | To construct Storage Water Tank In Upper Piane | Storage Water Tank In Upper Piane constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.337804, 35.993675 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1998917 | 100 | 1998917 | 1000000 | -1998917 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
4688 | Water and Sewerage Management | Construction & Purchase of 20,000 litres elevated water tank at Belbur Kapchil | To construct & Purchase of 20,000 litres elevated water tank at Belbur Kapchil | & Purchase of 20,000 litres elevated water tank at Belbur Kapchil constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.366517, 35.96516 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: yes. Viable: yes. Contractor: barnabas ent. Assessor remarks: good work.
4689 | Water and Sewerage Management | Drilling and Equiping of Sosioti borehole | To implement drilling and equiping of sosioti borehole for access to clean water and environmental sustainability | Drilling and Equiping of Sosioti borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.288202, 35.87854 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1843027 | 46.1 | 1843027 | 1872774 | 2156973 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Not available. Assessor remarks: Only drilling and lining done.
4690 | Water and Sewerage Management | Drilling And Equipping Of Njoro Police Post Borehole | To implement drilling and equipping of njoro police post borehole for access to clean water and environmental sustainability | Drilling And Equipping Of Njoro Police Post Borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.331744, 35.945973 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2018/19 | 2018/19 | 2019 | 2350423.7 | 0 | 1350423.7 | Equitable | N/A | 1350423.7 | 0 | 2649576 | 100 | 2649576 | 1350424 | -2649576 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprise. Assessor remarks: Complete awaiting Jewathu piping.
4691 | Water and Sewerage Management | Drilling & solarization of Mwigito borehole | To implement drilling & solarization of mwigito borehole for access to clean water and environmental sustainability | Drilling & solarization of Mwigito borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.326906 35.94127 2151.900146484375 23.476999282836914 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 5450000 | 5450000 | 5450000 | Equitable | N/A | 5450000 | 0 | 1843027 | 33.8 | 1843027 | 1872774 | 3606973 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Romonet enterprise Ltd. Assessor remarks: Good work.
4692 | Water and Sewerage Management | Completion and Piping of Tachasis Water Project | To complete and Piping of Tachasis Water Project | And Piping of Tachasis Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.361442, 35.708045 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2023-2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1000000 | 33.3 | 1000000 | 1000000 | 2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLDSAN HOLDINGS LTD.. Assessor remarks: Going on steadily.
4693 | Water and Sewerage Management | Construction of Tank and Piping of Seguton Water Project | To construct Tank and Piping of Seguton Water Project | Tank and Piping of Seguton Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.425385, 35.629443 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022-2023 | 3000000 | 2952937.76 | 2952937.76 | Equitable | N/A | 2952937.76 | 0 | 2952938 | 100 | 2952938 | 2952938 | -0.24 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Faucets need replacement.
4694 | Water and Sewerage Management | Drilling, Equipping And Piping Of Seguton/Langwenda Water Project | To implement drilling, equipping and piping of seguton/langwenda water project for access to clean water and environmental sustainability | Drilling, Equipping And Piping Of Seguton/Langwenda Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.37308 35.677892 2768.6 5.099999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/20 | 4250000 | 1250794.35 | 1250794.35 | Equitable | N/A | 1250794.35 | 0 | 1250794 | 100 | 1250794 | 1250794 | 0.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4695 | Water and Sewerage Management | Drilling of borehole at Temoyotta and Tachasis Water projects | To provide access to clean water through borehole drilling at Temoyotta and Tachasis Water projects | Borehole drilled at Temoyotta and Tachasis Water projects | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 2230444.4 | Equitable | N/A | 2230444.4 | 0 | 999131 | 100 | 999131 | 869 | -999131 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
4696 | Water and Sewerage Management | Drilling of Boron Secondary School | To implement drilling of boron secondary school for access to clean water and environmental sustainability | Drilling of Boron Secondary School completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.409028, 35.597138 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024-2025 | 6800000 | 6800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 2235726 | 32.9 | 2235726 | 3000000 | 4564274 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes, but once complete. Viable: Will be a viable project once completed. Assessor remarks: Will be a game-changer once complete.
4697 | Water and Sewerage Management | Drilling Of Entanki Borehole | To implement drilling of entanki borehole for access to clean water and environmental sustainability | Drilling Of Entanki Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.309208, 35.608375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2235726 | 100 | 2235726 | 3000000 | -2235726 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: YES. Viable: YES. Assessor remarks: Good, Needs Fencing.
4698 | Water and Sewerage Management | Drilling Of Masaita Borehole | To implement drilling of masaita borehole for access to clean water and environmental sustainability | Drilling Of Masaita Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.309208, 35.608375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2235726 | 100 | 2235726 | 3000000 | -2235726 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: YES. Viable: YES. Assessor remarks: Good, Needs Fencing.
4699 | Water and Sewerage Management | Drilling Of Mawingu Borehole | To implement drilling of mawingu borehole for access to clean water and environmental sustainability | Drilling Of Mawingu Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.309208, 35.608375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 3000000 | 0 | 764274 | Equitable | N/A | 764274 | 0 | 2235726 | 100 | 2235726 | 764274 | -2235726 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: YES. Viable: YES. Assessor remarks: Good, Needs Fencing.
4700 | Water and Sewerage Management | Drilling Of Valley Primary School Borehole | To implement drilling of valley primary school borehole for access to clean water and environmental sustainability | Drilling Of Valley Primary School Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.41092 35.65578 2673.7 19 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2235726 | 100 | 2235726 | 3000000 | -2235726 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good. Pump needs repairs..
4701 | Water and Sewerage Management | Piping and equipping of Mung'etho Water project | To provide water distribution infrastructure at and equipping of Mung'etho Water project | Water piping at and equipping of Mung'etho Water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.361442, 35.708045 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023-2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLDSAN HOLDINGS LTD.. Assessor remarks: Going on steadily.
4702 | Water and Sewerage Management | Piping At Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk | To provide water distribution infrastructure at Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk | Water piping at Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.352788, 35.592343 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | 2022-2023 | 2000000 | 1912719 | 1912719 | Equitable | N/A | 1912719 | 0 | 1912719 | 100 | 1912719 | 1912719 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Good. Viable: Yes. Assessor remarks: Will be if great help if complete.
4703 | Water and Sewerage Management | Piping of Seguton water works | To provide water distribution infrastructure at Seguton water works | Water piping at Seguton water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.303301, 36.074369 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2023/2024 | 1600000 | 1500000 | 1600000 | Equitable | N/A | 1600000 | 0 | 999131 | 66.6 | 999131 | 869 | 500869 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Talas. Assessor remarks: Completed and in use.
4704 | Water and Sewerage Management | Piping Of Temoyetta Water Project | To provide water distribution infrastructure at Temoyetta Water Project | Water piping at Temoyetta Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.298946, 35.55323 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999131 | 99.9 | 999131 | 869 | 869 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4705 | Water and Sewerage Management | Installation of a water tank and Piping at Hells Gate Estate | To install a water tank and Piping at Hells Gate Estate | A water tank and Piping at Hells Gate Estate installed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | -0.838284, 36.361985 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: Yet to start.
4706 | Water and Sewerage Management | Piping and tank installation at Sher Kasarani | To provide water distribution infrastructure at and tank installation at Sher Kasarani | Water piping at and tank installation at Sher Kasarani completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.836945, 36.357213 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1988875.58 | 1988875.58 | Equitable | N/A | 1988875.58 | 0 | 1988876 | 100 | 1988876 | 1988876 | -0.42 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
4707 | Water and Sewerage Management | Drilling, piping and solarisation Of Setkotes water project | To implement drilling, piping and solarisation of setkotes water project for access to clean water and environmental sustainability | Drilling, piping and solarisation Of Setkotes water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.309488, 35.67859 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 2997851 | 100 | 2997851 | 6000000 | -2997851 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Not functional now, but will solve water challenges. Assessor remarks: The project is still under implementation.
4708 | Water and Sewerage Management | Piping Of Sachoran and Baraka Shalom Water to Households | To provide water distribution infrastructure at Sachoran and Baraka Shalom Water to Households | Water piping at Sachoran and Baraka Shalom Water to Households completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.208692 35.688427 2515.2001953125 12.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2036573 | 81.5 | 2036573 | 463427 | 463427 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leakage from the base of their main tank, fencing of borehole and tank area, more pipe network to households.
4709 | Water and Sewerage Management | Tank Construction, solarisation and Piping on Nyakinywa Borehole | To implement tank construction, solarisation and piping on nyakinywa borehole for access to clean water and environmental sustainability | Tank Construction, solarisation and Piping on Nyakinywa Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.241238, 35.671508 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The project is under implementation.
4710 | Water and Sewerage Management | Tank Construction, solarisation, power installation and Piping of Sot Kotes borehole | To implement tank construction, solarisation, power installation and piping of sot kotes borehole for access to clean water and environmental sustainability | Tank Construction, solarisation, power installation and Piping of Sot Kotes borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.235177 35.662557 2740.7999999999997 13.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2533506 | 2533506 | 2533506 | Equitable | N/A | 2533506 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leaking roof noted, peeling of Wall paint, gutters need fixing.
4711 | Water and Sewerage Management | 71 Water works in Soin Ward | To implement 71 water works in soin ward for access to clean water and environmental sustainability | 71 Water works in Soin Ward completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.091051, 35.864329 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2010266 | 2010266 | 2010266 | Equitable | N/A | 2010266 | 0 | 1899129 | 94.5 | 1899129 | 111137 | 111137 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Residents are positive of the project.
4712 | Water and Sewerage Management | Construction of 100M3 Water tank at Barina | To construct 100M3 Water tank at Barina | 100M3 Water tank at Barina constructed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.065365 36.063149 1637 9.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2671062 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require renovation.
4713 | Water and Sewerage Management | Drilling Of a Borehole at Banita Dispensary | To implement drilling of a borehole at banita dispensary for access to clean water and environmental sustainability | Drilling Of a Borehole at Banita Dispensary completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.075427, 36.076482 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 3500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Contractor: Maratech Ventures. Assessor remarks: Require piping.
4714 | Water and Sewerage Management | Drilling of Borehole at Kimamoi water Project and Kokwomoi Water project | To provide access to clean water through borehole drilling at Kimamoi water Project and Kokwomoi Water project | Borehole drilled at Kimamoi water Project and Kokwomoi Water project | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.03435, 36.031945 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | FY 2025 | 7000000 | 0 | 891793.65 | Equitable | N/A | 891793.65 | 0 | 5164832 | 100 | 5164832 | 891794 | -5164832 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sagit Global Limited. Assessor remarks: Work done to satisfaction.
4715 | Water and Sewerage Management | Morop Water Works | To implement morop water works for access to clean water and environmental sustainability | Morop Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.122507, 35.949947 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | FY 2022 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2538918 | 90.7 | 2538918 | 261082 | 261082 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Residents are positive with the project.
4716 | Water and Sewerage Management | Pipe laying of Chemasusu last mile connecting at Kabarnet farm | To implement pipe laying of chemasusu last mile connecting at kabarnet farm for access to clean water and environmental sustainability | Pipe laying of Chemasusu last mile connecting at Kabarnet farm completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.096449 35.935984 1693 9 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping work needed.
4717 | Water and Sewerage Management | Rehabilitation of morop water project borehole | To rehabilitate morop water project borehole to restore functionality | Morop water project borehole rehabilitated | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.121442, 35.95206 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | FY 2023 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1990264 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: work in progress.
4718 | Water and Sewerage Management | Arutani Water Tank And Piping | To implement arutani water tank and piping for access to clean water and environmental sustainability | Arutani Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021 | 2300000 | 2298889.2 | 2298889.2 | Equitable | N/A | 2298889.2 | 0 | 2298889 | 100 | 2298889 | 2298889 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
4719 | Water and Sewerage Management | Borehole Drilling at Chemarmar and Kiametha-Arutani | To provide access to clean water through borehole drilling at Chemarmar and Kiametha-Arutani | Borehole drilled at Chemarmar and Kiametha-Arutani | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.176144 36.176929 1613.39599609375 6.4720001220703125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5730199 | 95.5 | 5730199 | 269802 | 269801 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is functional.
4720 | Water and Sewerage Management | Construction of water trough and pipes supply at Nyamamithi and Kapkatoro | To construct water trough and pipes supply at Nyamamithi and Kapkatoro | Water trough and pipes supply at Nyamamithi and Kapkatoro constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.078187 36.194685 1926.3 18.100000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1750168.56 | 1750168.56 | Equitable | N/A | 1750168.56 | 0 | 2999760 | 171.4 | 2999760 | 1750169 | -1249591.44 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: arden. Assessor remarks: The contract was terminated/vyed.
4721 | Water and Sewerage Management | Drilling Of Kasururei Water borehole | To implement drilling of kasururei water borehole for access to clean water and environmental sustainability | Drilling Of Kasururei Water borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.04684, 36.170143 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 6937743.85 | 5000000 | 15466798.85 | Equitable | N/A | 15466798.85 | 0 | 1591311 | 31.8 | 1591311 | 6937744 | 3408689 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Surgifin ltd. Assessor remarks: Good.
4722 | Water and Sewerage Management | Drilling Of Kiametha Borehole | To implement drilling of kiametha borehole for access to clean water and environmental sustainability | Drilling Of Kiametha Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.176144 36.176929 1613.39599609375 6.4720001220703125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 6500000 | 2970945 | Equitable | N/A | 2970945 | 0 | 2970945 | 45.7 | 2970945 | 6937744 | 3529055 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is functional.
4723 | Water and Sewerage Management | Kasururei Water works: Equiping, solarization, water tank and Piping | To implement kasururei water works: equiping, solarization, water tank and piping for access to clean water and environmental sustainability | Kasururei Water works: Equiping, solarization, water tank and Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.044788, 36.171572 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | September 2025 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1194431 | 29.9 | 1194431 | 1197810 | 2805569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ekay contractors and General supplies. Assessor remarks: Functional.
4724 | Water and Sewerage Management | Piping and Rehabilitation of water tank at Kamosop | To provide water distribution infrastructure at and Rehabilitation of water tank at Kamosop | Water piping at and Rehabilitation of water tank at Kamosop completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.16787 36.159957 1580.02001953125 18.270000457763672 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 953415.6 | 953415.6 | Equitable | N/A | 953415.6 | 0 | 953415 | 100 | 953415 | 953416 | 0.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete.
4725 | Water and Sewerage Management | Rehabilitation Of Limuru Water Tank And Piping | To rehabilitate Limuru Water Tank And Piping to restore functionality | Limuru Water Tank And Piping rehabilitated | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021 | 1200000 | 1197810.2 | 1197810.2 | Equitable | N/A | 1197810.2 | 0 | 1197810 | 100 | 1197810 | 1197810 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
4726 | Water and Sewerage Management | Solai Water Works project | To implement solai water works project for access to clean water and environmental sustainability | Solai Water Works project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.049474, 36.172997 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 4550169 | 2800000 | 4550168.56 | Equitable | N/A | 4550168.56 | 0 | 998215 | 35.7 | 998215 | 2200000 | 1801785 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipe supplied.
4727 | Water and Sewerage Management | Solai Water Works | To implement solai water works for access to clean water and environmental sustainability | Solai Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.049474, 36.172997 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 2200000 | 0 | 2200000 | Equitable | N/A | 2200000 | 0 | 1598853 | 100 | 1598853 | 2200000 | -1598853 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipe supplied.
4728 | Water and Sewerage Management | Drilling Of a Borehole at Arash | To implement drilling of a borehole at arash for access to clean water and environmental sustainability | Drilling Of a Borehole at Arash completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3661174 | 100 | 3661174 | 3000000 | -3661174 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
4729 | Water and Sewerage Management | Drilling Of a Borehole at Subukia Valley | To implement drilling of a borehole at subukia valley for access to clean water and environmental sustainability | Drilling Of a Borehole at Subukia Valley completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.033342, 36.17144 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 3702220 | 0 | 1170253.8 | Equitable | N/A | 1170253.8 | 0 | 2531966 | 100 | 2531966 | 1170254 | -2531966 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Completed.
4730 | Water and Sewerage Management | Drilling Of a Borehole at Tetu | To implement drilling of a borehole at tetu for access to clean water and environmental sustainability | Drilling Of a Borehole at Tetu completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3661174 | 91.5 | 3661174 | 338826 | 338826 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
4731 | Water and Sewerage Management | Gatongu Water project | To implement gatongu water project for access to clean water and environmental sustainability | Gatongu Water project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.02504, 36.175968 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2500000 | 100 | 2500000 | 3000000 | -2500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Completed and is in good working condition.
4732 | Water and Sewerage Management | Piping and fencing of Morro Water Project | To provide water distribution infrastructure at and fencing of Morro Water Project | Water piping at and fencing of Morro Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | 0.007568 36.223208 2011.8999999999999 7.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2491135 | 99.6 | 2491135 | 8865 | 8865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the boreho.
4733 | Water and Sewerage Management | Piping of ACK Munanda Water Project | To provide water distribution infrastructure at ACK Munanda Water Project | Water piping at ACK Munanda Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2994215 | 99.8 | 2994215 | 5785 | 5785 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
4734 | Water and Sewerage Management | Piping of Araki Water Project | To provide water distribution infrastructure at Araki Water Project | Water piping at Araki Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1465335.2 | 1465335.2 | Equitable | N/A | 1465335.2 | 0 | 1465335 | 100 | 1465335 | 1465335 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
4735 | Water and Sewerage Management | Piping of Subukia Valley Borehole | To provide water distribution infrastructure at Subukia Valley Borehole | Water piping at Subukia Valley Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2863256 | 2863256 | Equitable | N/A | 2863256 | 0 | 2863256 | 100 | 2863256 | 2863256 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
4736 | Water and Sewerage Management | Piping of Tetu water project | To provide water distribution infrastructure at Tetu water project | Water piping at Tetu water project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 1465335 | 100 | 1465335 | 1465335 | -1465335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
4737 | Water and Sewerage Management | Piping, Purchase And Installation Of Solar Panels Subukia Valley Borehole | To implement piping, purchase and installation of solar panels subukia valley borehole for access to clean water and environmental sustainability | Piping, Purchase And Installation Of Solar Panels Subukia Valley Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.040933 36.220476 2150.7001953125 100 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 1556509 | 1556509 | Equitable | N/A | 1556509 | 0 | 643491 | 41.3 | 643491 | 1556509 | 913018 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
4738 | Water and Sewerage Management | Quarry Water project | To implement quarry water project for access to clean water and environmental sustainability | Quarry Water project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.006327, 36.23532 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2022 | 4000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2500000 | 100 | 2500000 | 3000000 | -2500000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further measures to be taken due to tank not having water.
4739 | Water and Sewerage Management | Subukia Kirengero Water Works | To implement subukia kirengero water works for access to clean water and environmental sustainability | Subukia Kirengero Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.030765 36.234948 2103.5849609375 9.105999946594238 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 872617 | 87.3 | 872617 | 127383 | 127383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Sure the water serves the community.. Contractor: Information not available. Assessor remarks: Good work.
4740 | Water and Sewerage Management | Supply Of Pipes At Gatongu Water Project And Fencing Intake Area | To implement supply of pipes at gatongu water project and fencing intake area for access to clean water and environmental sustainability | Supply Of Pipes At Gatongu Water Project And Fencing Intake Area completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
4741 | Water and Sewerage Management | Kimugul Water Projects | To implement kimugul water projects for access to clean water and environmental sustainability | Kimugul Water Projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 3211646 | 3211646 | Equitable | N/A | 3211646 | 0 | 2953304 | 92 | 2953304 | 258342 | 258342 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4742 | Water and Sewerage Management | Piping Works at Kaplesin | To provide water distribution infrastructure at Works at Kaplesin | Water piping at Works at Kaplesin completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4743 | Water and Sewerage Management | Taita water projects | To implement taita water projects for access to clean water and environmental sustainability | Taita water projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5943082 | 99.1 | 5943082 | 56918 | 56918 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4744 | Water and Sewerage Management | Construction of a 50m3 water tank at turi farmers water project | To construct a 50m3 water tank at turi farmers water project | A 50m3 water tank at turi farmers water project constructed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.279945 35.774557 2458.800048828125 7 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 999941 | 66.7 | 999941 | 1000000 | 500059 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: The department to follow up to process the title. The water tank is not in use since the time it was constructed. No water connection. The residents are seeing it as a white elephant project.
4745 | Water and Sewerage Management | Drilling of Mkorombosi water project | To implement drilling of mkorombosi water project for access to clean water and environmental sustainability | Drilling of Mkorombosi water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.330723, 35.75336 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 0 | 617161.55 | Equitable | N/A | 617161.55 | 0 | 2638981 | 100 | 2638981 | 617162 | -2638981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Excellent work.
4746 | Water and Sewerage Management | Drilling of Turi farmers water project | To implement drilling of turi farmers water project for access to clean water and environmental sustainability | Drilling of Turi farmers water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.296542, 35.743885 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 3134157.6 | 3134157.6 | Equitable | N/A | 3134157.6 | 0 | 3134158 | 100 | 3134158 | 3134158 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes once it's completed. Viable: Yes. Assessor remarks: The project is ongoing.
4747 | Water and Sewerage Management | Kiambiriria Water Works | To implement kiambiriria water works for access to clean water and environmental sustainability | Kiambiriria Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.309072, 35.691193 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3708209 | 92.7 | 3708209 | 291791 | 291791 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete awaiting commissioning.
4748 | Water and Sewerage Management | Milima Mitatu Water Works | To implement milima mitatu water works for access to clean water and environmental sustainability | Milima Mitatu Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -1.281229 36.821402 0 291468.7964650597 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 424086 | 84.8 | 424086 | 75914 | 75914 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: the project is in use.
4749 | Water and Sewerage Management | Mkorombosi Water Works | To implement mkorombosi water works for access to clean water and environmental sustainability | Mkorombosi Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.330805, 35.75345 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 3708209 | 100 | 3708209 | 4000000 | -3708209 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Excellent work.
4750 | Water and Sewerage Management | Ndereru Water Works | To implement ndereru water works for access to clean water and environmental sustainability | Ndereru Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -1.281229 36.821402 0 291468.7964650597 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2586081 | 86.2 | 2586081 | 413919 | 413919 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: the project is in use.
4751 | Water and Sewerage Management | Piping of Valley water project, Mkorombosi water project and Kiambiriria Water project | To provide water distribution infrastructure at Valley water project, Mkorombosi water project and Kiambiriria Water project | Water piping at Valley water project, Mkorombosi water project and Kiambiriria Water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.3053, 35.689868 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 4500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 797936 | 26.6 | 797936 | 950543 | 2202064 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: There is vandalism to the manholes. Manhole covers andGate valves have been stolen.
4752 | Water and Sewerage Management | Piping Works of Monna Water Project | To provide water distribution infrastructure at Works of Monna Water Project | Water piping at Works of Monna Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.301305, 35.709012 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 750000 | 100 | 750000 | 498589 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping was done.
4753 | Water and Sewerage Management | Valley Water Works | To implement valley water works for access to clean water and environmental sustainability | Valley Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.2707, 35.756702 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 707380 | 94.3 | 707380 | 42620 | 42620 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: Good condition.
4754 | Water and Sewerage Management | Drilling Of Legetio and Murichu Borehole | To implement drilling of legetio and murichu borehole for access to clean water and environmental sustainability | Drilling Of Legetio and Murichu Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.120545, 35.88465 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2324 | 7000000 | 0 | 960297.5 | Equitable | N/A | 960297.5 | 0 | 6039703 | 100 | 6039703 | 960298 | -6039703 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lamrinet kenya limited. Assessor remarks: Good.
4755 | Water and Sewerage Management | Installation Of Water Tank for Rongai Centre | To install Water Tank for Rongai Centre | Water Tank for Rongai Centre installed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.13898 35.90486 1791.2 8.100000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 120000 | 120000 | 120000 | Equitable | N/A | 120000 | 0 | 3550334 | 2958.6 | 3550334 | 120000 | -3430334 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The conductor has broken down.
4756 | Water and Sewerage Management | Piping at Undugu, Jamii and Kware | To provide water distribution infrastructure at Undugu, Jamii and Kware | Water piping at Undugu, Jamii and Kware completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 1650018.8 | 1650018.8 | Equitable | N/A | 1650018.8 | 0 | 1650019 | 100 | 1650019 | 1650019 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4757 | Water and Sewerage Management | Piping Belbur and Lengenet (Gachau B) Water Projects | To provide water distribution infrastructure at Belbur and Lengenet (Gachau B) Water Projects | Water piping at Belbur and Lengenet (Gachau B) Water Projects completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2176030 | 90.7 | 2176030 | 223970 | 223970 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4758 | Water and Sewerage Management | Piping of Lengenet -Kapkalet NARUWASCO water | To provide water distribution infrastructure at Lengenet -Kapkalet NARUWASCO water | Water piping at Lengenet -Kapkalet NARUWASCO water completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.120545, 35.88465 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2324 | 1500000 | 1432414 | 1432414 | Equitable | N/A | 1432414 | 0 | 1432414 | 100 | 1432414 | 1432414 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lamrinet kenya limited. Assessor remarks: Good.
4759 | Water and Environment | Piping of Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank | To provide water distribution infrastructure at Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank | Water piping at Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 2800000 | 2450415.78 | 2450415.78 | Equitable | N/A | 2450415.78 | 0 | 2436957 | 99.5 | 2436957 | 13459 | 13458.78 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4760 | Water and Sewerage Management | Piping of water at Surutia | To provide water distribution infrastructure at water at Surutia | Water piping at water at Surutia completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.137292 35.824637 1889.3 9.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1170080 | 97.5 | 1170080 | 29920 | 29920 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment. Assessor remarks: Good.
4761 | Water and Sewerage Management | Drilling of gituamba borehole | To implement drilling of gituamba borehole for access to clean water and environmental sustainability | Drilling of gituamba borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146619, 36.242473 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3750000 | 3750000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Needs Solarization and piping.
4762 | Water and Sewerage Management | Drilling of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe-Kirima borehole in Waseges Ward | To implement drilling of kiriko borehole, polepole borehole, suswa borehole and kianoe-kirima borehole in waseges ward for access to clean water and environmental sustainability | Drilling of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe-Kirima borehole in Waseges Ward completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146619, 36.242473 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 14000000 | 0 | 2588263.55 | Equitable | N/A | 2588263.55 | 0 | 10458673 | 100 | 10458673 | 2588264 | -10458673 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Needs Solarization and piping.
4763 | Water and Sewerage Management | Installation Five Storage Tanks (10,000 Litres) And Construction of Platforms | To install Five Storage Tanks (10,000 Litres) And Construction of Platforms | Five Storage Tanks (10,000 Litres) And Construction of Platforms installed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.12653 36.26655 1759.5 10.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 650000 | 650000 | 650000 | Equitable | N/A | 650000 | 0 | 624335 | 96.1 | 624335 | 25665 | 25665 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
4764 | Water and Sewerage Management | Installation Of Solar Panels at Safina Haji Water Project | To install Solar Panels at Safina Haji Water Project | Solar Panels at Safina Haji Water Project installed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.032255, 36.193342 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3499813 | 100 | 3499813 | 3000000 | -3499813 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4765 | Water and Sewerage Management | Piping Of Waseges Water Works | To provide water distribution infrastructure at Waseges Water Works | Water piping at Waseges Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.187977 36.235932 1657.3999999999999 6.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 737155.15 | Equitable | N/A | 737155.15 | 0 | 1262845 | 100 | 1262845 | 737155 | -1262845 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
4766 | Water and Sewerage Management | Purchase of pipes for waseges ward | To procure pipes for waseges ward | Pipes for waseges ward procured | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02395, 36.210717 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 3179426 | 3179426 | 3179426 | Equitable | N/A | 3179426 | 0 | 0 | 0 | 0 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Complete.
4767 | Water and Sewerage Management | Purchase of pipes for Waseges | To procure pipes for Waseges | Pipes for Waseges procured | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02395, 36.210717 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1300000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Complete.
4768 | Water and Sewerage Management | Purchase of plastic tank for wiyumiririe water project | To procure plastic tank for wiyumiririe water project | Plastic tank for wiyumiririe water project procured | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
4769 | Water and Sewerage Management | Installation of pump and laying of pipes at Ndasiata | To install pump and laying of pipes at Ndasiata | Pump and laying of pipes at Ndasiata installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.638923, 35.65338 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 1480098 | 1480098 | Equitable | N/A | 1480098 | 0 | 0 | 0 | 0 | 1480098 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4770 | Water and Sewerage Management | Gicheha Borehole Additional Funding for Solarization and Pumping Installation | To implement gicheha borehole additional funding for solarization and pumping installation for access to clean water and environmental sustainability | Gicheha Borehole Additional Funding for Solarization and Pumping Installation completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2957100 | 98.6 | 2957100 | 42900 | 42900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4771 | Water and Sewerage Management | Solarization, Installation of Pump and Water Tanks at Gituru Borehole | To implement solarization, installation of pump and water tanks at gituru borehole for access to clean water and environmental sustainability | Solarization, Installation of Pump and Water Tanks at Gituru Borehole completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 1489440 | 100 | 1489440 | 6000000 | -1489440 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4772 | Water and Sewerage Management | Construction of a raised water tower at Wanyororo Borehole | To construct a raised water tower at Wanyororo Borehole | A raised water tower at Wanyororo Borehole constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252138, 36.187568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/2023 | 2000000 | 1869850.4 | 1869850.4 | Equitable | N/A | 1869850.4 | 0 | 1869850 | 100 | 1869850 | 1869850 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Kewaska company. Assessor remarks: Good require operationalization.
4773 | Water and Sewerage Management | Construction of water intakes and Piping across dundori water projects in mai-mahiu, Gathima, kanyiriri, kirima, kinale, giachonge, nyangui, bawku, cura,kiamunyeki and Bavuni-mugwathi | To construct water intakes and Piping across dundori water projects in mai-mahiu, Gathima, kanyiriri, kirima, kinale, giachonge, nyangui, bawku, cura,kiamunyeki and Bavuni-mugwathi | Water intakes and Piping across dundori water projects in mai-mahiu, Gathima, kanyiriri, kirima, kinale, giachonge, nyangui, bawku, cura,kiamunyeki and Bavuni-mugwathi constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.231442, 36.235313 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/2025 | 6350000 | 6350000 | 6350000 | Equitable | N/A | 6350000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Delivery of pipes done other works yet to commence.
4774 | Water and Sewerage Management | Desalination Of Wanyororo Dam | To implement desalination of wanyororo dam for access to clean water and environmental sustainability | Desalination Of Wanyororo Dam completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.256626, 36.185103 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/2020 | 1197111 | 0 | 261272.9 | Equitable | N/A | 261272.9 | 0 | 935838 | 100 | 935838 | 261273 | -935838 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ardent logistics. Assessor remarks: Good require desalination.
4775 | Water and Sewerage Management | Installation of solar panels for Githioro water project and Karuchwa project | To install solar panels for Githioro water project and Karuchwa project | Solar panels for Githioro water project and Karuchwa project installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.258463, 36.188812 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/2023 | 3000000 | 2046032.05 | 2046032.05 | Equitable | N/A | 2046032.05 | 0 | 1709978 | 83.6 | 1709978 | 336054 | 336054.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kabawahe company Ltd. Assessor remarks: Functional.
4776 | Water and Sewerage Management | Construction of 2 public toilets at Nderit water point and Oldupei market | To construct 2 public toilets at Nderit water point and Oldupei market | 2 public toilets at Nderit water point and Oldupei market constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1242583 | 0 | 1242583 | Equitable | N/A | 1242583 | 0 | 3571500 | 100 | 3571500 | 1242583 | -3571500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4777 | Water and Sewerage Management | Installation Of Electricity at Kirima Borehole | To install Electricity at Kirima Borehole | Electricity at Kirima Borehole installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.344725, 36.173544 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | No details | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 5799954 | 100 | 5799954 | 2500000 | -5799954 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It's viable and it meet the needs of the area. Contractor: Crater enterprises. Assessor remarks: Fairy done.
4778 | Water and Sewerage Management | Completion of Saptet Borehole | To complete Saptet Borehole | Saptet Borehole completed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.272217 35.816592 2382.3 13.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 3000000 | 100 | 3000000 | 2000000 | -3000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4779 | Water and Sewerage Management | Equipping at Mwangi Michuki borehole | To equip at Mwangi Michuki borehole with necessary facilities and equipment | At Mwangi Michuki borehole equipped | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.292714, 35.791345 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2020/21 | 2020/21 | - | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 782988 | 97.9 | 782988 | 17012 | 17012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Contractor: FINO Limited. Assessor remarks: Completed.
4780 | Water and Sewerage Management | Purchase And Installation of Submersible Water Pump at Saptet Water Project | To procure and install Submersible Water Pump at Saptet Water Project | Submersible Water Pump at Saptet Water Project procured and installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.306163 35.800133 0 72.9000015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1100000 | 0 | 1100000 | Equitable | N/A | 1100000 | 0 | 1685561 | 100 | 1685561 | 1100000 | -1685561 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: O.B.T.Limited. Assessor remarks: Work on progrss.
4781 | Water and Sewerage Management | Electricity connection at Nyarianda Borehole | To implement electricity connection at nyarianda borehole for access to clean water and environmental sustainability | Electricity connection at Nyarianda Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.60141 36.106703 2110.400146484375 7.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The borehole has not been completed.
4782 | Water and Sewerage Management | Purchase and installation of submersible water pump for Mogaa water project | To procure and install submersible water pump for Mogaa water project | Submersible water pump for Mogaa water project procured and installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.633558 36.114698 2875.204 4.869999885559082 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 3758989 | 100 | 3758989 | 1000000 | -3758989 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs renovation.
4783 | Water and Sewerage Management | Solarization and equipping of Meli Borehole | To implement solarization and equipping of meli borehole for access to clean water and environmental sustainability | Solarization and equipping of Meli Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.663792, 36.11113 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3327547 | 3327547 | Equitable | N/A | 3327547 | 0 | 3327547 | 100 | 3327547 | 3327547 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
4784 | Water and Sewerage Management | Construction and expansion of sewer lines at Pangani USAID and Kimathi Estate | To construct and expansion of sewer lines at Pangani USAID and Kimathi Estate | And expansion of sewer lines at Pangani USAID and Kimathi Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303637, 36.074191 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/2023 | 11514821 | 10395510.6 | 10395510.6 | Equitable | N/A | 10395510.6 | 0 | 10168311 | 97.8 | 10168311 | 227200 | 227199.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: BFC Enterprises. Assessor remarks: Completed and in use.
4785 | Water and Sewerage Management | Construction Of Sewer Line at Pangani Estate/ Agape | To construct Sewer Line at Pangani Estate/ Agape | Sewer Line at Pangani Estate/ Agape constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303802, 36.072862 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 10168311 | 462.2 | 10168311 | 2200000 | -7968311 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Montage. Assessor remarks: Ongoing.
4786 | Water and Sewerage Management | Expansion Of Sewer Line Pangani USAID | To expand Sewer Line Pangani USAID to increase capacity | Sewer Line Pangani USAID expanded | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303623, 36.074186 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/2024 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 10168311 | 100 | 10168311 | 3000000 | -10168311 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Taras. Assessor remarks: Completed and in use.
4787 | Water and Sewerage Management | Rehabilitation and connection to sewer lines 3 no of toilet blocks at Flamingo estate | To rehabilitate connection to sewer lines 3 no of toilet blocks at Flamingo estate to restore functionality | Connection to sewer lines 3 no of toilet blocks at Flamingo estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303767, 36.078671 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2013/2014 | 4500000 | 4045314.4 | 4045314.4 | Equitable | N/A | 4045314.4 | 0 | 4045314 | 100 | 4045314 | 4045314 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use.
4788 | Water and Sewerage Management | Equipping of Manyatta borehole borehole water works | To equip Manyatta borehole borehole water works with necessary facilities and equipment | Manyatta borehole borehole water works equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.475389, 36.33014 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 24/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3416217 | 113.9 | 3416217 | 83783 | -416217 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: .. Viable: .. Assessor remarks: Yet to start.
4789 | Water and Sewerage Management | Construction/Rehabilitation Of Sanitation Facilities | To implement construction/rehabilitation of sanitation facilities for access to clean water and environmental sustainability | Construction/Rehabilitation Of Sanitation Facilities completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/20 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 7025864 | 206.6 | 7025864 | 3400000 | -3625864 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4790 | Climate Change Resilience and County Energy Development | Establishment of Energy Centres for promotion of renewable Energy technologies | To implement establishment of energy centres for promotion of renewable energy technologies for access to clean water and environmental sustainability | Establishment of Energy Centres for promotion of renewable Energy technologies completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 50000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4791 | Climate Change Resilience and County Energy Development | Extension of Dry port water in Maai Mahiu | To expand Dry port water in Maai Mahiu to increase capacity | Dry port water in Maai Mahiu expanded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 6600000 | 5997919.2 | 5997919.2 | Equitable | N/A | 5997919.2 | 0 | 5997919 | 100 | 5997919 | 9600000 | 0.2 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4792 | Water and Sewerage Management | Fencing, construction of site office with a sanitary facility and construction of a gatehouse at Molo dumpsite | To implement fencing, construction of site office with a sanitary facility and construction of a gatehouse at molo dumpsite for access to clean water and environmental sustainability | Fencing, construction of site office with a sanitary facility and construction of a gatehouse at Molo dumpsite completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 8000000 | 4500000 | 4500000 | N/A | N/A | 4500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4793 | Water and Sewerage Management | Fencing, construction of site office with a sanitary facility and construction of a gatehouse at Tipis dumpsite | To implement fencing, construction of site office with a sanitary facility and construction of a gatehouse at tipis dumpsite for access to clean water and environmental sustainability | Fencing, construction of site office with a sanitary facility and construction of a gatehouse at Tipis dumpsite completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 0 | 2251720 | N/A | N/A | 2251720 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4794 | Water and Sewerage Management | Rehabilitation of water supplies (existing system) | To rehabilitate water supplies (existing system) to restore functionality | Water supplies (existing system) rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.695026, 36.480933 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2021/22 | 50000000 | 10979824 | 10125789.83 | N/A | N/A | 10125789.83 | 0 | 2994378 | 27.3 | 2994378 | 5622 | 7985446 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4795 | Water and Sewerage Management | Salgaa Area Programme (World Vision) Counterpart funding | To implement salgaa area programme (world vision) counterpart funding for access to clean water and environmental sustainability | Salgaa Area Programme (World Vision) Counterpart funding completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.391082, 35.742475 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 17000000 | 16970338.09 | 16970338.09 | N/A | N/A | 16970338.09 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
4796 | Water and Sewerage Management | Desilting of Ngosur Dam and Building of water Intake | To implement desilting of ngosur dam and building of water intake for access to clean water and environmental sustainability | Desilting of Ngosur Dam and Building of water Intake completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.214433 36.162776 2030.4000244140625 10.21500015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 799335 | 799335 | Equitable | N/A | 799335 | 0 | 799335 | 100 | 799335 | 799335 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Willis samwa suppliers limited. Assessor remarks: Operational.
4797 | Water and Sewerage Management | Installation of solar system at Kabatini borehole | To install solar system at Kabatini borehole | Solar system at Kabatini borehole installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231931, 36.147504 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 1841804 | 1841804 | Equitable | N/A | 1841804 | 0 | 1841804 | 100 | 1841804 | 1841804 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
4798 | Water and Sewerage Management | Rehabilitation of Gitu Borehole, solarization and Piping to Nyathuna area | To rehabilitate Gitu Borehole, solarization and Piping to Nyathuna area to restore functionality | Gitu Borehole, solarization and Piping to Nyathuna area rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.184111 36.192215 2261.89697265625 10.04699993133545 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 1425940.25 | Equitable | N/A | 1425940.25 | 0 | 2604780 | 100 | 2604780 | 1425940 | -2604780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The project was reallocated to UT borehole which was intiatially meant for gitu borehole.
4799 | Water and Sewerage Management | Rehabilitation of River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane | To rehabilitate River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane to restore functionality | River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 968745 | 96.9 | 968745 | 31255 | 31255 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
4800 | Water and Sewerage Management | Solarization and Construction of elevated tank at Limuko borehole | To implement solarization and construction of elevated tank at limuko borehole for access to clean water and environmental sustainability | Solarization and Construction of elevated tank at Limuko borehole completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231931, 36.147504 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022 | 3000000 | 2698043.6 | 2698043.6 | Equitable | N/A | 2698043.6 | 0 | 2698044 | 100 | 2698044 | 2698044 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
4801 | Water and Sewerage Management | Construction of Kipng'ochoch water tank | To construct Kipng'ochoch water tank | Kipng'ochoch water tank constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.149855 36.09075 2168.4 7.400000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2718933 | 100 | 2718933 | 499211 | -2718933 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kilofox enterprises. Assessor remarks: Popping to be done.
4802 | Water and Sewerage Management | Construction of upper Kipng'ochoch water tank | To construct upper Kipng'ochoch water tank | Upper Kipng'ochoch water tank constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.149855 36.09075 2168.4 7.400000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 900000 | 0 | 900000 | Equitable | N/A | 900000 | 0 | 2718933 | 100 | 2718933 | 499211 | -2718933 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kilofox enterprises. Assessor remarks: Popping to be done.
4803 | Water and Sewerage Management | Equiping and solarisation of Arahuka water project | To implement equiping and solarisation of arahuka water project for access to clean water and environmental sustainability | Equiping and solarisation of Arahuka water project completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2858339 | 100 | 2858339 | 4000000 | -2858339 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
4804 | Water and Sewerage Management | Equipping ,solarisation,piping,fencing and renovation of water tanks in Kitur ECDE | To equip ,solarisation,piping,fencing and renovation of water tanks in Kitur ECDE with necessary facilities and equipment | ,solarisation,piping,fencing and renovation of water tanks in Kitur ECDE equipped | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.13644, 36.080575 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | July 2025 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Carlsche Ltd. Assessor remarks: Ownership documents to be followed up.
4805 | Water and Sewerage Management | Fencing of Baraka ECDE/Ngenda borehole and mwireri borehole | To secure Baraka ECDE/Ngenda borehole and mwireri borehole through fencing | Baraka ECDE/Ngenda borehole and mwireri borehole fenced and secured | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
4806 | Water and Sewerage Management | Installation Of Solar Panel at Ng'enda Water Project | To install Solar Panel at Ng'enda Water Project | Solar Panel at Ng'enda Water Project installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2858339 | 95.3 | 2858339 | 141661 | 141661 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
4807 | Water and Sewerage Management | Installation Of Solar Panels at Mwereri Water Project | To install Solar Panels at Mwereri Water Project | Solar Panels at Mwereri Water Project installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 141661 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
4808 | Water and Sewerage Management | Renovation of water tank at kitur/langat place | To rehabilitate water tank at kitur/langat place to restore functionality | Water tank at kitur/langat place rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.158008 36.079218 1887.2 9 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | 2024/25 | 2024/25 | 2024/25 | 2024/25 | 200000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 499211 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
4809 | Water and Sewerage Management | Renovation of water tanks for marigat and fencing | To rehabilitate water tanks for marigat and fencing to restore functionality | Water tanks for marigat and fencing rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.158008 36.079218 1887.2 9 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 499211 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
4810 | Water and Sewerage Management | Control Panel Repair at Kiptenten Water Project | To implement control panel repair at kiptenten water project for access to clean water and environmental sustainability | Control Panel Repair at Kiptenten Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.181058 35.712687 2543.000244140625 4.599999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 288277 | 288277 | 288277 | Equitable | N/A | 288277 | 0 | 258599 | 89.7 | 258599 | 29678 | 29678 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable but didn't meet the needs of residents. Contractor: Unknown. Assessor remarks: The project was constructed but abandoned. Results - vandalism, window panels broken, missing internal doors, missing gutters, no water tank and needs fencing and pit latrines.
4811 | Water and Sewerage Management | Installation Of Kamara Centre Booster Pump | To install Kamara Centre Booster Pump | Kamara Centre Booster Pump installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.0881, 35.678813 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2570432 | 85.7 | 2570432 | 429568 | 429568 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: EDPAUS SUPPLIES AND CONSTRUCTION LTD. Assessor remarks: Functional but needs fencing and gate for security reasons.
4812 | Water and Sewerage Management | Jogoo water project - desilting and relaying of pipes | To implement jogoo water project - desilting and relaying of pipes for access to clean water and environmental sustainability | Jogoo water project - desilting and relaying of pipes completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 634660 | 0 | 634660 | Equitable | N/A | 634660 | 0 | 3988715.36 | 100 | 3988715.36 | 634660 | -3988715.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
4813 | Water and Sewerage Management | Protection And Piping Of Sarambei Spring | To implement protection and piping of sarambei spring for access to clean water and environmental sustainability | Protection And Piping Of Sarambei Spring completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.162838 35.693123 2518.6 6.599999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2018/19 | 2018/19 | N/A | 2999994.9 | 2999994.9 | 2999994.9 | Equitable | N/A | 2999994.9 | 0 | 2999995 | 100 | 2999995 | 2999995 | -0.1 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
4814 | Water and Sewerage Management | Construction of perimeter wall at Kapnandi water project | To construct perimeter wall at Kapnandi water project | Perimeter wall at Kapnandi water project constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.30348 36.025538 1878.9599609375 3.2160000801086426 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 2917562 | 265.2 | 2917562 | 2917562 | -1817562 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Handed over to the contractor. But yet to start.
4815 | Water and Sewerage Management | Chepkutbei trenching and piping | To implement chepkutbei trenching and piping for access to clean water and environmental sustainability | Chepkutbei trenching and piping completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.42156, 35.696098 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4816 | Water and Sewerage Management | Installation Of Water Pump and Piping of Soitaran Dam Water Project | To install Water Pump and Piping of Soitaran Dam Water Project | Water Pump and Piping of Soitaran Dam Water Project installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.499863, 35.733418 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1277612 | 100 | 1277612 | 1200000 | -1277612 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
4817 | Water and Sewerage Management | Rehabilitation of borehole | To rehabilitate borehole to restore functionality | Borehole rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.447173, 35.704185 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2024 | 1300000 | 1292141.4 | 1292141.4 | Equitable | N/A | 1292141.4 | 0 | 1292141 | 100 | 1292141 | 1292141 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
4818 | Water and Sewerage Management | Solarization Of Tulwet Borehole in Milimet | To implement solarization of tulwet borehole in milimet for access to clean water and environmental sustainability | Solarization Of Tulwet Borehole in Milimet completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.447173, 35.704185 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 892784 | 89.3 | 892784 | 107216 | 107216 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
4819 | Water and Sewerage Management | Solarization of Jirani - Kio borehole | To implement solarization of jirani - kio borehole for access to clean water and environmental sustainability | Solarization of Jirani - Kio borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.475127 35.988002 2285.2 4.199999809265137 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1433301 | 1433301 | 1433301 | Equitable | N/A | 1433301 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fencing and staff house construction.
4820 | Water and Sewerage Management | Solarization of Mutiume borehole | To implement solarization of mutiume borehole for access to clean water and environmental sustainability | Solarization of Mutiume borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.434969, 35.975684 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 3250000 | 3250000 | 3250000 | Equitable | N/A | 3250000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Musnet ventures. Assessor remarks: Good condition.
4821 | Water and Sewerage Management | Tank rehabilitation in stoo mbili and pipe supply in Lusiru | To implement tank rehabilitation in stoo mbili and pipe supply in lusiru for access to clean water and environmental sustainability | Tank rehabilitation in stoo mbili and pipe supply in Lusiru completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.456677, 35.981842 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project work to be completed.
4822 | Water and Sewerage Management | Completion Of Cheplanget Chebotoi Water Project | To complete Cheplanget Chebotoi Water Project | Cheplanget Chebotoi Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.56148, 35.63016 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 600257 | 0 | 600257 | Equitable | N/A | 600257 | 0 | 1995987 | 100 | 1995987 | 600257 | -1995987 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Not functional.
4823 | Water and Sewerage Management | Desilting of Ogilgei dam | To implement desilting of ogilgei dam for access to clean water and environmental sustainability | Desilting of Ogilgei dam completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.325895 35.49856 0 2599.9990234375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 0 | 1555792.8 | Equitable | N/A | 1555792.8 | 0 | 759293 | 100 | 759293 | 1592793 | -759293 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yes. Assessor remarks: There some equipments but require,e.g fridge, outpatient screen,weight and height weighing scale,electricity installation,drip stand , mch seats and chairs.
4824 | Water and Sewerage Management | Repair of Kio water pump | To rehabilitate Kio water pump to restore functionality | Kio water pump rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.295213, 35.490194 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 385318 | 385318 | 385318 | Equitable | N/A | 385318 | 0 | 2800000 | 726.7 | 2800000 | 2800000 | -2414682 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole is complete and protected.
4825 | Water and Sewerage Management | Replacement of solar panel, repair of electric motor at Kuresoi health centre and Piping | To implement replacement of solar panel, repair of electric motor at kuresoi health centre and piping for access to clean water and environmental sustainability | Replacement of solar panel, repair of electric motor at Kuresoi health centre and Piping completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302616 35.529461 2587.10009765625 72.9000015258789 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete but the services shifted.
4826 | Water and Sewerage Management | Solarization and piping at chumbek tulwet water project | To implement solarization and piping at chumbek tulwet water project for access to clean water and environmental sustainability | Solarization and piping at chumbek tulwet water project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.358042, 35.55575 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1492793 | 49.8 | 1492793 | 2000000 | 1507207 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4827 | Water and Sewerage Management | Construction Of Sewer Lines at Machanga Estate | To construct Sewer Lines at Machanga Estate | Sewer Lines at Machanga Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298165, 36.082478 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3500000 | 3500000 | 3500000 | Equitable | Vired | 3500000 | 0 | 3031776 | 86.6 | 3031776 | 468224 | 468224 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improve sanitation.
4828 | Water and Sewerage Management | Solarization of Lamnyondeki water project | To implement solarization of lamnyondeki water project for access to clean water and environmental sustainability | Solarization of Lamnyondeki water project completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet-Umoja | -0.265808, 36.166458 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 924462 | 46.2 | 924462 | 75538 | 1075538 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , very viable. Assessor remarks: Functional.
4829 | Water and Sewerage Management | Installation of Solar, water tank, High Mast, Water Tower & Pipes at Ndege Ndimu | To install Solar, water tank, High Mast, Water Tower & Pipes at Ndege Ndimu | Solar, water tank, High Mast, Water Tower & Pipes at Ndege Ndimu installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.313356, 36.173727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 1563999.98 | Equitable | N/A | 1563999.98 | 0 | 1436000 | 100 | 1436000 | 1564000 | -1436000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4830 | Water and Sewerage Management | Construction Of 2 Water Kiosks with Two 10,000L Water Tanks at Milimani Primary School | To construct 2 Water Kiosks with Two 10,000L Water Tanks at Milimani Primary School | 2 Water Kiosks with Two 10,000L Water Tanks at Milimani Primary School constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.490923, 36.065112 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983945 | 98.4 | 983945 | 16055 | 16055 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need completion.
4831 | Water and Sewerage Management | Construction Of a storage water tank, installation of HDPE water pipes, purchase of 10,000L Water Tank and construction of a water kiosk at Milimani | To construct a storage water tank, installation of HDPE water pipes, purchase of 10,000L Water Tank and construction of a water kiosk at Milimani | A storage water tank, installation of HDPE water pipes, purchase of 10,000L Water Tank and construction of a water kiosk at Milimani constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.477282, 36.037303 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 2800000 | 0 | 2800000 | Equitable | N/A | 2800000 | 0 | 1010009 | 100 | 1010009 | 2800000 | -1010009 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
4832 | Water and Sewerage Management | Equiping, solarization, Fencing, water kiosk & a water tank of 10,000 litres at Nganoini borehole | To implement equiping, solarization, fencing, water kiosk & a water tank of 10,000 litres at nganoini borehole for access to clean water and environmental sustainability | Equiping, solarization, Fencing, water kiosk & a water tank of 10,000 litres at Nganoini borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.439725 36.015697 2056.7 1609.281005859375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
4833 | Water and Sewerage Management | Equipping, Solarization and Water kiosk Of Pwani - Mutamaiyu Borehole | To implement equipping, solarization and water kiosk of pwani - mutamaiyu borehole for access to clean water and environmental sustainability | Equipping, Solarization and Water kiosk Of Pwani - Mutamaiyu Borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.383517, 36.014027 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
4834 | Water and Sewerage Management | Installation Of Electric Powered Water Pump at Milimani Primary NAWASSCO Station | To install Electric Powered Water Pump at Milimani Primary NAWASSCO Station | Electric Powered Water Pump at Milimani Primary NAWASSCO Station installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274104, 36.05562 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
4835 | Water and Sewerage Management | Construction Of Maai Mahiu Dumping Site Fence | To construct Maai Mahiu Dumping Site Fence | Maai Mahiu Dumping Site Fence constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.981012, 36.529232 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project at beeque stage.
4836 | Water and Sewerage Management | Construction of water towers at Sero-Moindabi | To construct water towers at Sero-Moindabi | Water towers at Sero-Moindabi constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.80447, 36.246479 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 313361 | 100 | 313361 | 1500000 | -313361 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S wheelsteps system ltd. Assessor remarks: Community satisfied.
4837 | Water and Sewerage Management | Drilling of Borehole, Solarization and Piping of Crater Water Project | To implement drilling of borehole, solarization and piping of crater water project for access to clean water and environmental sustainability | Drilling of Borehole, Solarization and Piping of Crater Water Project completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4838 | Water and Sewerage Management | Fencing and renovation of Nkampani water tank | To secure and renovation of Nkampani water tank through fencing | And renovation of Nkampani water tank fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.918573, 36.203528 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 3094231 | 442 | 3094231 | 2510600 | -2394231 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Yet to be handed over.
4839 | Water and Sewerage Management | Maiella water works | To implement maiella water works for access to clean water and environmental sustainability | Maiella water works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 1305170 | 46.6 | 1305170 | 1331984 | 1494830 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
4840 | Water and Sewerage Management | Equipping Pump, Solarization Storage Tank and Fencing and Piping Extension Network in Malewa West Ward | To equip Pump, Solarization Storage Tank and Fencing and Piping Extension Network in Malewa West Ward with necessary facilities and equipment | Pump, Solarization Storage Tank and Fencing and Piping Extension Network in Malewa West Ward equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.630631, 36.488697 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need additional fund inverter not working.
4841 | Water and Sewerage Management | Installation Of Pump in Tarambete Water Project | To install Pump in Tarambete Water Project | Pump in Tarambete Water Project installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.648649, 36.488825 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1410490 | 94 | 1410490 | 89510 | 89510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
4842 | Water and Sewerage Management | Repair Of KCC Irrigation Pump and Irrigation Pipes Improvement | To rehabilitate KCC Irrigation Pump and Irrigation Pipes Improvement to restore functionality | KCC Irrigation Pump and Irrigation Pipes Improvement rehabilitated | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.720721 36.471354 0 2000 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 363614 | 363614 | 363614 | Equitable | N/A | 363614 | 0 | 228474 | 62.8 | 228474 | 135140 | 135140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
4843 | Water and Sewerage Management | Solarization of St. John borehole | To implement solarization of st. john borehole for access to clean water and environmental sustainability | Solarization of St. John borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.648649, 36.488825 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2677889 | 99.2 | 2677889 | 430398 | 22111 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ruisa ltd. Assessor remarks: Good work.
4844 | Water and Sewerage Management | Equipping and Piping of digital-Timbelion Water Project | To equip and Piping of digital-Timbelion Water Project with necessary facilities and equipment | And Piping of digital-Timbelion Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.355552, 35.814058 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3706316 | 92.7 | 3706316 | 293684 | 293684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping supply to people.
4845 | Equipping and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes | Equipping and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes | To equip and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes with necessary facilities and equipment | And Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 8158170 | 8158170 | Equitable | N/A | 8158170 | 0 | 8158170 | 100 | 8158170 | 8158170 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
4846 | Water and Sewerage Management | Equipping, Piping & Solarization of Mukeu Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks | To implement equipping, piping & solarization of mukeu borehole, construction of two water kiosks and purchase of two 5,000l water tanks for access to clean water and environmental sustainability | Equipping, Piping & Solarization of Mukeu Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.569337 35.979258 2564.400146484375 4.400000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 5965849 | 100 | 5965849 | 34151 | -5965849 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need extra pipping.
4847 | Water and Sewerage Management | Equipping, Piping & Solarization of Nyandimu Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks | To implement equipping, piping & solarization of nyandimu borehole, construction of two water kiosks and purchase of two 5,000l water tanks for access to clean water and environmental sustainability | Equipping, Piping & Solarization of Nyandimu Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.569337 35.979258 2564.400146484375 4.400000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5965849 | 99.4 | 5965849 | 34151 | 34151 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need extra pipping.
4848 | Water and Sewerage Management | Piping of Tipis Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks | To provide water distribution infrastructure at Tipis Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks | Water piping at Tipis Borehole, Construction of Two Water Kiosks and Purchase of Two 5,000L Water Tanks completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.569337 35.979258 2564.400146484375 4.400000095367432 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1395518 | 93 | 1395518 | 104482 | 104482 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need extra pipping.
4849 | Water and Sewerage Management | Solarization, Tank repair And Piping of Segutiet Borehole | To implement solarization, tank repair and piping of segutiet borehole for access to clean water and environmental sustainability | Solarization, Tank repair And Piping of Segutiet Borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.603439, 36.013375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2891783 | 96.4 | 2891783 | 108217 | 108217 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Yes.
4850 | Water and Sewerage Management | Equiping in Kiptenden water project and Chesoen water project | To implement equiping in kiptenden water project and chesoen water project for access to clean water and environmental sustainability | Equiping in Kiptenden water project and Chesoen water project completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.517562 35.973678 2471 8.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 9000000 | 9000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2498918 | 27.8 | 2498918 | 238767 | 6501082 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good.
4851 | Water and Sewerage Management | Equipping, solarization, construction of water kiosk and fencing of Kusumek water project and piping | To implement equipping, solarization, construction of water kiosk and fencing of kusumek water project and piping for access to clean water and environmental sustainability | Equipping, solarization, construction of water kiosk and fencing of Kusumek water project and piping completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.469198, 35.952945 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2022 | 5900000 | 5900000 | 11800000 | Equitable | N/A | 11800000 | 0 | 3798997 | 64.4 | 3798997 | 5900000 | 2101003 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4852 | Water and Sewerage Management | Expansion of intake and supply of steel and normal pipes for Kitoben Water Springs | To expand intake and supply of steel and normal pipes for Kitoben Water Springs to increase capacity | Intake and supply of steel and normal pipes for Kitoben Water Springs expanded | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.478383, 35.943668 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2024 | 3000000 | 2967848.4 | 2967848.4 | Equitable | N/A | 2967848.4 | 0 | 2954102 | 99.5 | 2954102 | 13746 | 13746.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
4853 | Water and Sewerage Management | Mugeremukia WP borehole pump and motor replacement | To implement mugeremukia wp borehole pump and motor replacement for access to clean water and environmental sustainability | Mugeremukia WP borehole pump and motor replacement completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.264144, 35.757475 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | June 2025 | 2050000 | 0 | 2050000 | Equitable | N/A | 2050000 | 0 | 0 | 0 | 0 | 2050000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mafigah east African ltd. Assessor remarks: Good.
4854 | Water and Sewerage Management | Solarization of Mukinyai cattle dip borehole | To implement solarization of mukinyai cattle dip borehole for access to clean water and environmental sustainability | Solarization of Mukinyai cattle dip borehole completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.208132 35.787935 0 699.9990234375 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3350000 | 3350000 | 3350000 | Equitable | N/A | 3350000 | 0 | 3016836 | 90.1 | 3016836 | 333164 | 333164 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mafigah east African ltd. Assessor remarks: Good.
4855 | Water and Sewerage Management | Solarization of Tayari borehole and supply of water meters | To implement solarization of tayari borehole and supply of water meters for access to clean water and environmental sustainability | Solarization of Tayari borehole and supply of water meters completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.234333, 35.706697 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | July 25 | 6100000 | 0 | 6100000 | Equitable | N/A | 6100000 | 0 | 0 | 0 | 0 | 6100000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
4856 | Water and Sewerage Management | Equiping Ogilgei borehole | To implement equiping ogilgei borehole for access to clean water and environmental sustainability | Equiping Ogilgei borehole completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.302325, 35.953057 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2857319 | 95.2 | 2857319 | 3500000 | 142681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Not yet awarded. Assessor remarks: Yet to start.
4857 | Water and Sewerage Management | Fencing of Merichemi water project solar | To secure Merichemi water project solar through fencing | Merichemi water project solar fenced and secured | 3110504 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.481425, 36.393981 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4858 | Water and Sewerage Management | Sinking, equipping and solarisation of Cura borehole | To implement sinking, equipping and solarisation of cura borehole for access to clean water and environmental sustainability | Sinking, equipping and solarisation of Cura borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.481425, 36.393981 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024/25 | 9000000 | 0 | 6098724.02 | Equitable | N/A | 6098724.02 | 0 | 2901276 | 100 | 2901276 | 6098724 | -2901276 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4859 | Water and Sewerage Management | Kinungi Water works | To implement kinungi water works for access to clean water and environmental sustainability | Kinungi Water works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.817415, 36.54659 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024-25 | 3600000 | 3600000 | 7200000 | Equitable | N/A | 7200000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes borehole producing water. Contractor: Aquasans systemltd. Assessor remarks: Solarization of bore hole done.
4860 | Water and Sewerage Management | Equipping of Cheptoroi borehole | To equip Cheptoroi borehole with necessary facilities and equipment | Cheptoroi borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.433936 35.919127 2591.218994140625 3.7899999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 1990108.76 | Equitable | N/A | 1990108.76 | 0 | 0 | 0 | 0 | 1990109 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds drilled borehole, constructed control panel, 100,000 litre water tank and water kiosk..
4861 | Water and Sewerage Management | Installation of control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole | To install control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole | Control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.362587, 35.871741 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2023/24 | 6500000 | 0 | 6236858 | Equitable | N/A | 6236858 | 0 | 0 | 0 | 0 | 6292858 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Requires rehabilitation due to low volume of water output.
4862 | Water and Sewerage Management | Preparation Of a Tree Nursery and Purchase of Generator And 10,000 Litre Tank | To implement preparation of a tree nursery and purchase of generator and 10,000 litre tank for access to clean water and environmental sustainability | Preparation Of a Tree Nursery and Purchase of Generator And 10,000 Litre Tank completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.424201, 35.908083 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: FLOCAN COMPANY LIMITED. Assessor remarks: The project didn't serve its purpose since the Generator was not procured..
4863 | Water and Sewerage Management | Rehabilitation of Chebtebes and Amani dams | To rehabilitate Chebtebes and Amani dams to restore functionality | Chebtebes and Amani dams rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.424708 35.951331 2344.498779296875 9.62399959564209 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 1928105 | Equitable | N/A | 1928105 | 0 | 0 | 0 | 0 | 1928105 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor abandoned the two projects due to insufficient funds.
4864 | Water and Sewerage Management | Completion of a control Panel/ house, equipping and piping of Belbur borehole | To complete a control Panel/ house, equipping and piping of Belbur borehole | A control Panel/ house, equipping and piping of Belbur borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.303659, 35.89102 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2020 | 4791102 | 4588656 | 4588656 | Equitable | N/A | 4588656 | 0 | 4588656 | 100 | 4588656 | 4588656 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Jecy Co Ltd. Assessor remarks: Lining to be done.
4865 | Water and Sewerage Management | Equiping of Jordan Borehole - Purchase of motor | To implement equiping of jordan borehole - purchase of motor for access to clean water and environmental sustainability | Equiping of Jordan Borehole - Purchase of motor completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.331569 35.953914 2141.900146484375 4.072999954223633 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1843027 | 368.6 | 1843027 | 1872774 | -1343027 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done work.
4866 | Water and Sewerage Management | Equipping And Piping of Kenana Primary Borehole | To equip And Piping of Kenana Primary Borehole with necessary facilities and equipment | And Piping of Kenana Primary Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.303659, 35.89102 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1734206 | 86.7 | 1734206 | 265794 | 265794 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Jecy Co Ltd. Assessor remarks: Lining to be done.
4867 | Water and Sewerage Management | Equipping And Piping of Njoro Police Borehole | To equip And Piping of Njoro Police Borehole with necessary facilities and equipment | And Piping of Njoro Police Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.303659, 35.89102 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2020 | 3831163 | 3831163 | 3831163 | Equitable | N/A | 3831163 | 0 | 3219773 | 84 | 3219773 | 611390 | 611390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Jecy Co Ltd. Assessor remarks: Lining to be done.
4868 | Water and Sewerage Management | Equipping, Solarization and Piping and purchase of water tank for borehole at Njokerio Dispensary | To implement equipping, solarization and piping and purchase of water tank for borehole at njokerio dispensary for access to clean water and environmental sustainability | Equipping, Solarization and Piping and purchase of water tank for borehole at Njokerio Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2350423.7 | 4706899.03 | 4706899.03 | Equitable | N/A | 4706899.03 | 0 | 4706899 | 100 | 4706899 | 4706899 | 0.03 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
4869 | Water and Sewerage Management | Completion of Equipping, Solarisation And Piping At Lulukwet Water Project | To complete Equipping, Solarisation And Piping At Lulukwet Water Project | Equipping, Solarisation And Piping At Lulukwet Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.301692, 35.543018 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | - | 850089 | 671288.56 | 671288.56 | Equitable | N/A | 671288.56 | 0 | 600044 | 89.4 | 600044 | 71245 | 71244.56 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4870 | Water and Sewerage Management | Equiping of Entaki Water Project | To implement equiping of entaki water project for access to clean water and environmental sustainability | Equiping of Entaki Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.312307, 35.558422 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025-2026 | 6000000 | 6000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 999131 | 16.7 | 999131 | 869 | 5000869 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4871 | Water and Sewerage Management | Equiping of Terekena Water Project | To implement equiping of terekena water project for access to clean water and environmental sustainability | Equiping of Terekena Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.312307, 35.558422 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025-2026 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 999131 | 0 | 999131 | 869 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4872 | Water and Sewerage Management | Equipping solarization, installation of pump and piping at Seguton Water Project | To equip solarization, installation of pump and piping at Seguton Water Project with necessary facilities and equipment | Solarization, installation of pump and piping at Seguton Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 5360191 | 5360191 | Equitable | N/A | 5360191 | 0 | 5360191 | 100 | 5360191 | 5360191 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
4873 | Water and Sewerage Management | Beautification and Landscaping at Kamere beach | To implement beautification and landscaping at kamere beach for access to clean water and environmental sustainability | Beautification and Landscaping at Kamere beach completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.815759, 36.322371 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: No. Contractor: Domestic enterprises and general supplies. Assessor remarks: The project needs more touch.
4874 | Water and Sewerage Management | Solarisation and piping of Nyakinyua Water Project | To implement solarisation and piping of nyakinyua water project for access to clean water and environmental sustainability | Solarisation and piping of Nyakinyua Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Sirikwa | -0.23917, 35.665882 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3210486 | 160.5 | 3210486 | 2000000 | -1210486 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: This is an ongoing project.
4875 | Water and Sewerage Management | Solarization And Pumping of Lomolo Borehole | To implement solarization and pumping of lomolo borehole for access to clean water and environmental sustainability | Solarization And Pumping of Lomolo Borehole completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | 0.018472, 36.032207 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024-2025 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating.
4876 | Water and Sewerage Management | Chemarmar borehole equiping and solarization | To implement chemarmar borehole equiping and solarization for access to clean water and environmental sustainability | Chemarmar borehole equiping and solarization completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.176262, 36.176939 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2024 | 3036629 | 3036629 | 3036629 | Equitable | N/A | 3036629 | 0 | 2937700 | 96.7 | 2937700 | 98929 | 98929 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4877 | Water and Sewerage Management | Completion of valley water project solarization and piping | To complete valley water project solarization and piping | Valley water project solarization and piping completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.27073, 35.756647 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 950543 | Equitable | N/A | 950543 | 0 | 3079231 | 100 | 3079231 | 950543 | -3079231 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
4878 | Water and Sewerage Management | Ndenderu A Water Project Solarization and Piping | To implement ndenderu a water project solarization and piping for access to clean water and environmental sustainability | Ndenderu A Water Project Solarization and Piping completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.30944, 35.74908 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3222781.6 | 3222781.6 | Equitable | N/A | 3222781.6 | 0 | 3079231 | 95.5 | 3079231 | 143550 | 143550.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No, it would have been met if it was equipped. Viable: No. Assessor remarks: The borehole was only drilled but was never equipped.
4879 | Water and Sewerage Management | Ngenia water project solarization and piping at Mona center | To implement ngenia water project solarization and piping at mona center for access to clean water and environmental sustainability | Ngenia water project solarization and piping at Mona center completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1999866.68 | 1999866.68 | Equitable | N/A | 1999866.68 | 0 | 1949800 | 97.5 | 1949800 | 50067 | 50066.68 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
4880 | Water and Sewerage Management | Purchase of Water Pump and power connection for Valley Water Project | To procure Water Pump and power connection for Valley Water Project | Water Pump and power connection for Valley Water Project procured | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.270993, 35.75597 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 797936 | 57 | 797936 | 1400000 | 602064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good working condition. Piping is not fully complete.
4881 | Water and Sewerage Management | Solarisation of muricho borehole | To implement solarisation of muricho borehole for access to clean water and environmental sustainability | Solarisation of muricho borehole completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 5500000 | 0 | 5500000 | Equitable | N/A | 5500000 | 0 | 1265104 | 100 | 1265104 | 1284290 | -1265104 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
4882 | Water and Sewerage Management | Solarisation of nessuit borehole | To implement solarisation of nessuit borehole for access to clean water and environmental sustainability | Solarisation of nessuit borehole completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3132139 | 100 | 3132139 | 1284290 | -3132139 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4883 | Water and Sewerage Management | Supply of water pipes at visoi ward | To implement supply of water pipes at visoi ward for access to clean water and environmental sustainability | Supply of water pipes at visoi ward completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.125197 35.935737 1744.699951171875 6.599999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1050000 | 0 | 1050000 | Equitable | N/A | 1050000 | 0 | 485996 | 100 | 485996 | 29920 | -485996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4884 | Water and Sewerage Management | Construction of a melting kiln at Komokomo County Council | To construct a melting kiln at Komokomo County Council | A melting kiln at Komokomo County Council constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.711889, 36.43651 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: No. Assessor remarks: Not started.
4885 | Water and Sewerage Management | Rehabilitation Of Sewer In Naivasha Town CBD | To rehabilitate Sewer In Naivasha Town CBD to restore functionality | Sewer In Naivasha Town CBD rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71773 36.433963 1895.0999755859375 44.172000885009766 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 0 | 4408816.4 | Equitable | N/A | 4408816.4 | 0 | 0 | 0 | 0 | 4498816 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
4886 | Water and Sewerage Management | Desilting of Guston water source intake point | To implement desilting of guston water source intake point for access to clean water and environmental sustainability | Desilting of Guston water source intake point completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.020877, 36.250735 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 550000 | 550000 | 550000 | Equitable | N/A | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water project is operational.
4887 | Water and Sewerage Management | Equiping and Solarization of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe and Mumoi borehole in Waseges Ward | To implement equiping and solarization of kiriko borehole, polepole borehole, suswa borehole and kianoe and mumoi borehole in waseges ward for access to clean water and environmental sustainability | Equiping and Solarization of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe and Mumoi borehole in Waseges Ward completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.170393, 36.24932 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 8500000 | 0 | 4505879.02 | Equitable | N/A | 4505879.02 | 0 | 3954121 | 100 | 3954121 | 4545879 | -3954121 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and in use.
4888 | Water and Sewerage Management | Installation of Solar Panel at Kahawa Borehole in Wiyumiririe | To install Solar Panel at Kahawa Borehole in Wiyumiririe | Solar Panel at Kahawa Borehole in Wiyumiririe installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.12653 36.26655 1759.5 10.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 450442 | 22.5 | 450442 | 2000000 | 1549558 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
4889 | Water and Sewerage Management | Installation Of Solar Panels at Kahawa Borehole in Wiyumiririe | To install Solar Panels at Kahawa Borehole in Wiyumiririe | Solar Panels at Kahawa Borehole in Wiyumiririe installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.12653 36.26655 1759.5 10.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 450442 | 100 | 450442 | 1000000 | -450442 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
4890 | Water and Sewerage Management | Installation Of Solar Panels at Safina Haji Water Project | To install Solar Panels at Safina Haji Water Project | Solar Panels at Safina Haji Water Project installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.032255, 36.193342 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 3499813 | 100 | 3499813 | 3000000 | -3499813 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4891 | Water and Sewerage Management | Installation Of Subverter at Kwandeki Borehole in Mihang'o | To install Subverter at Kwandeki Borehole in Mihang'o | Subverter at Kwandeki Borehole in Mihang'o installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.12653 36.26655 1759.5 10.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 450442 | 90.1 | 450442 | 49558 | 49558 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
4892 | Water and Sewerage Management | Repair of kahawa tank | To rehabilitate kahawa tank to restore functionality | Kahawa tank rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.023015 36.204362 2021.3 4.099999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4893 | Water and Sewerage Management | Repair of simboiyon water tank | To rehabilitate simboiyon water tank to restore functionality | Simboiyon water tank rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 600000 | 600000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
4894 | Water and Sewerage Management | Test pumping and chemical analysis of Sugutex phase II water project | To implement test pumping and chemical analysis of sugutex phase ii water project for access to clean water and environmental sustainability | Test pumping and chemical analysis of Sugutex phase II water project completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
4895 | Water and Sewerage Management | Fencing of Wakarichu Borehole | To secure Wakarichu Borehole through fencing | Wakarichu Borehole fenced and secured | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.190532, 36.172791 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1476692 | 147.7 | 1476692 | 1476692 | -476692 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Was is viable it has a court case. Assessor remarks: Project is yet to start the land is encroached.
4896 | Environmental Management | Purchase of Borehole Drilling Rig and Drilling Equipment | To procure Borehole Drilling Rig and Drilling Equipment | Borehole Drilling Rig and Drilling Equipment procured | 3110799 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 75000000 | 75000000 | 75000000 | N/A | N/A | 75000000 | 0 | 1496859 | 2 | 1496859 | 1496859 | 73503141 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4897 | Water and Sewerage Management | Purchase Of Skips for Rhonda Ward | To procure Skips for Rhonda Ward | Skips for Rhonda Ward procured | 3110799 | N/A | Nakuru West | Rhonda | -0.306335, 36.062964 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 23/24 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1400000 | 100 | 1400000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Auto mobile warehouse. Assessor remarks: Complete.
4898 | Water and Sewerage Management | Purchase of drilling rig tools and associated accessories (Under County Climate Change Fund) | To procure drilling rig tools and associated accessories (Under County Climate Change Fund) | Drilling rig tools and associated accessories (Under County Climate Change Fund) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 50000000 | 13000000 | 11653514 | Equitable | N/A | 11653514 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4899 | Water and Sewerage Management | Purchase of Anti-chlorine Machine at Kapnandi borehole | To procure Anti-chlorine Machine at Kapnandi borehole | Anti-chlorine Machine at Kapnandi borehole procured | 3111120 | Purchase of Specialized Plant. - | Nakuru West | Kapkures | -0.31982, 36.022104 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 2917562 | 100 | 2917562 | 300000 | -2917562 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S SAGIT GLOBAL LTD. Assessor remarks: completed and functional.
4900 | Water and Sewerage Management | Purchase of skip Bins for Heshima and Maili Sita Markets | To procure skip Bins for Heshima and Maili Sita Markets | Skip Bins for Heshima and Maili Sita Markets procured | 3111120 | Purchase of Specialized Plant. - | Bahati | Kiamaina | -0.24492, 36.112947 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires additional one.
4901 | Water and Sewerage Management | Establishment of a tree nursery at Bondeni Primary | To implement establishment of a tree nursery at bondeni primary for access to clean water and environmental sustainability | Establishment of a tree nursery at Bondeni Primary completed | 3111305 | Beautification and Tree Planting | Nakuru East | Biashara-Nakuru | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4902 | Water and Sewerage Management | Tree Growing Programme-Gilgil Ward | To implement tree growing programme-gilgil ward for access to clean water and environmental sustainability | Tree Growing Programme-Gilgil Ward completed | 3111305 | Beautification and Tree Planting | Gilgil | Gilgil | -0.493333, 36.327824 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lithan investment ltd. Assessor remarks: Some were vandalized.
4903 | Environmental Management | Greening and beautification of Club road and Kunste roundabouts | To implement greening and beautification of club road and kunste roundabouts for access to clean water and environmental sustainability | Greening and beautification of Club road and Kunste roundabouts completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1652434 | 0 | 1652434 | N/A | N/A | 1652434 | 0 | 0 | 0 | 0 | 11500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4904 | Water and Sewerage Management | Tree Planting At Namuncha Water Catchments | To implement tree planting at namuncha water catchments for access to clean water and environmental sustainability | Tree Planting At Namuncha Water Catchments completed | 3111305 | Beautification and Tree Planting | Naivasha | Maai Mahiu | -1.062633, 36.549497 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 998176 | 998176 | Equitable | N/A | 998176 | 0 | 998176 | 100 | 998176 | 998176 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
4905 | Water and Sewerage Management | Tree Planting at Kasarani, Climate Mitigation and Beautification | To implement tree planting at kasarani, climate mitigation and beautification for access to clean water and environmental sustainability | Tree Planting at Kasarani, Climate Mitigation and Beautification completed | 3111305 | Beautification and Tree Planting | Naivasha | Olkaria | 0.836945, 36.357213 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1399957 | 93.3 | 1399957 | 100043 | 100043 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some trees dried up others didn't grow.the are along the road others in schools.
4906 | Water and Sewerage Management | Establishment Of Tree Nursery & Tree Planting in All Educational Facilities in Rhoda Ward | To implement establishment of tree nursery & tree planting in all educational facilities in rhoda ward for access to clean water and environmental sustainability | Establishment Of Tree Nursery & Tree Planting in All Educational Facilities in Rhoda Ward completed | 3111305 | Beautification and Tree Planting | Nakuru West | Rhonda | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1590480 | 99.4 | 1590480 | 9520 | 9520 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4907 | Environmental Management | Tree Planting Exercise & Establishment of Tree Nurseries in All ECDE Schools In Shabab Ward (Mama Ngina, Koinange, Muslim and Nakuru West Primary) | To implement tree planting exercise & establishment of tree nurseries in all ecde schools in shabab ward (mama ngina, koinange, muslim and nakuru west primary) for access to clean water and environmental sustainability | Tree Planting Exercise & Establishment of Tree Nurseries in All ECDE Schools In Shabab Ward (Mama Ngina, Koinange, Muslim and Nakuru West Primary) completed | 3111305 | Beautification and Tree Planting | Nakuru West | Shabab | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 580000 | 580000 | 580000 | Equitable | N/A | 580000 | 0 | 479173 | 82.6 | 479173 | 100827 | 100827 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4908 | Water and Sewerage Management | Purchase of tree seedlings for public institutions | To procure tree seedlings for public institutions | Tree seedlings for public institutions procured | 3111305 | Beautification and Tree Planting | Kuresoi North | Sirikwa | -0.249192 35.682062 2664.4 19.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1990800 | 165.9 | 1990800 | 0 | -790800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No land purchased.
4909 | General Administration, Planning and Support Services | Construction & Equipping of Ward Administrator’s Office | To construct & Equipping of Ward Administrator’s Office | & Equipping of Ward Administrator’s Office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.263059 36.187451 1987.5999755859375 48.900001525878906 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4913990 | 98.3 | 4913990 | 86010 | 86010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica building. Assessor remarks: Good.
4910 | County Coordination of Policy formulation | Construction and Equipping of Ward Office in Mauche Ward | To construct and equip Ward Office in Mauche Ward | Ward Office in Mauche Ward constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | N/A | 7500000 | 2970940 | 2970940 | N/A | N/A | 2970940 | 0 | 2483870 | 83.6 | 2483870 | 2483870 | 487070 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4911 | General Administration, Planning and Support Services | Construction of Sub County Administration office in Rongai Sub County | To construct Sub County Administration office in Rongai Sub County | Sub County Administration office in Rongai Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 2941084 | 2941084 | N/A | N/A | 2941084 | 0 | 4165126 | 141.6 | 4165126 | 2941084 | -1224042 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4912 | General Administration, Planning and Support Services | Completion Of Kiptororo Ward Office | To complete Kiptororo Ward Office | Kiptororo Ward Office completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.300889 35.533228 0 20.100000381469727 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Request for construction of toilet.
4913 | General Administration, Planning and Support Services | Construction of toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward | To construct toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward | Toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2021/22 | 2021/22 | N/A | 3500000 | 554995 | 554995 | N/A | N/A | 554995 | 0 | 2933955 | 528.6 | 2933955 | 554995 | -2378960 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4914 | Refurbishment of Fire Divisions in Molo, Naivasha and Nakuru Disaster and Rescue Centre Building | Refurbishment of Fire Divisions in Molo, Naivasha and Nakuru Disaster and Rescue Centre Building | To implement refurbishment of fire divisions in molo, naivasha and nakuru disaster and rescue centre building for improved service delivery | Refurbishment of Fire Divisions in Molo, Naivasha and Nakuru Disaster and Rescue Centre Building completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | 2024/25 | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4915 | General Administration, Planning and Support Services | Construction of fence and toilet at Elburgon County Offices | To construct fence and toilet at Elburgon County Offices | Fence and toilet at Elburgon County Offices constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.26052 35.863608 0 6199.9990234375 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2023/24 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1262250 | 97.1 | 1262250 | 37750 | 37750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair ad maintainance.
4916 | Co-ordination of Disaster Management and Humanitarian Assistance | Acquisition of Disaster response equipment | To procure Disaster response equipment | Disaster response equipment procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2023/24 | 5500000 | 0 | 1900000 | N/A | N/A | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4917 | Co-ordination of Disaster Management and Humanitarian Assistance | Construction of a perimeter wall, ablution block and gate at Subukia Sub County Offices | To construct a perimeter wall, ablution block and gate at Subukia Sub County Offices | A perimeter wall, ablution block and gate at Subukia Sub County Offices constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2023/24 | 3300000 | 3300000 | 3300000 | N/A | N/A | 3300000 | 0 | 2843795 | 86.2 | 2843795 | 2844546 | 456205 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4918 | County Coordination of Policy formulation | Construction of an ablution block at Ward Administrator's Office in Mau Narok and Solai Ward Offices | To construct an ablution block at Ward Administrator's Office in Mau Narok and Solai Ward Offices | An ablution block at Ward Administrator's Office in Mau Narok and Solai Ward Offices constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | N/A | 2800000 | 1734250 | 1734250 | N/A | N/A | 1734250 | 0 | 4165126 | 240.2 | 4165126 | 7500000 | -2430876 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4919 | Co-ordination of Disaster Management and Humanitarian Assistance | Locally fabricated furniture for Rongai, Subukia, Kuresoi South Sub County Offices, Elementaita Ward and Barut Ward Offices | To implement locally fabricated furniture for rongai, subukia, kuresoi south sub county offices, elementaita ward and barut ward offices for improved service delivery | Locally fabricated furniture for Rongai, Subukia, Kuresoi South Sub County Offices, Elementaita Ward and Barut Ward Offices completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4920 | Co-ordination of Disaster Management and Humanitarian Assistance | Rehabilitation of fire response machinery | To rehabilitate fire response machinery to restore functionality | Fire response machinery rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | 2024/25 | 8200000 | 6200000 | 5765315 | N/A | N/A | 5765315 | 0 | 0 | 0 | 0 | 1900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4921 | Co-ordination of Disaster Management and Humanitarian Assistance | Supply and installation of solar floodlights at Rongai, Subukia, Kuresoi South Sub County Offices, Elementaita Ward and Barut Ward Offices | To procure and install solar floodlights at Rongai, Subukia, Kuresoi South Sub County Offices, Elementaita Ward and Barut Ward Offices | Solar floodlights at Rongai, Subukia, Kuresoi South Sub County Offices, Elementaita Ward and Barut Ward Offices procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4922 | General Administration, Planning and Support Services | Fencing and installation of gate at Kabatini Ward Administrator’s Offices | To secure and installation of gate at Kabatini Ward Administrator’s Offices through fencing | And installation of gate at Kabatini Ward Administrator’s Offices fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.215433 36.164478 2027.0999755859375 70.4209976196289 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 971300 | 971300 | Equitable | N/A | 971300 | 0 | 971300 | 100 | 971300 | 971300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Great rift general merchants. Assessor remarks: Good and Operational.
4923 | General Administration, Planning and Support Services | Installation of electricity at Ward Administrator Office | To install electricity at Ward Administrator Office | Electricity at Ward Administrator Office installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet-Umoja | -0.28073, 36.174018 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 622415 | 622415 | 622415 | Equitable | N/A | 622415 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
4924 | General Administration, Planning and Support Services | Completion of Fencing Of Ward Administrators Office | To complete Fencing Of Ward Administrators Office | Fencing Of Ward Administrators Office completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.313608, 36.067287 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 23/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 919050 | 91.9 | 919050 | 80950 | 80950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
4925 | General Administration, Planning and Support Services | Construction Of Ward Administrations Office Toilet | To construct Ward Administrations Office Toilet | Ward Administrations Office Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.546719, 35.674632 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No .poor finishing. Viable: Yes.
4926 | General Administration, Planning and Support Services | Equipping the Office of Ward Administrator Dundori Ward | To equip the Office of Ward Administrator Dundori Ward with necessary facilities and equipment | The Office of Ward Administrator Dundori Ward equipped | 3111099 | N/A | Bahati | Dundori | -0.262916, 36.18743 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | 2024/2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 4913990 | 982.8 | 4913990 | 86010 | -4413990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4927 | General Administration, Planning and Support Services | Proposed Equipping of Kiamaina Ward Office | To undertake the proposed Equipping of Kiamaina Ward Office | Proposed Equipping of Kiamaina Ward Office implemented | 3111099 | N/A | Bahati | Kiamaina | -0.231601, 36.116886 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 220749 | 0 | 220749 | Equitable | N/A | 220749 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
4928 | General Administration, Planning and Support Services | Equipping Of Nyota Ward Office | To equip Nyota Ward Office with necessary facilities and equipment | Nyota Ward Office equipped | 3111099 | N/A | Kuresoi North | Nyota | -0.386168, 35.652856 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2024-2025 | 1030669 | 0 | 1030669 | Equitable | N/A | 1030669 | 0 | 0 | 0 | 0 | 1030669 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4929 | General Administration, Planning and Support Services | Equipping Of Ward Administrators Office | To equip Ward Administrators Office with necessary facilities and equipment | Ward Administrators Office equipped | 3111099 | N/A | Kuresoi South | Tinet | -0.420051, 35.718334 | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | 2023/24 | 454877 | 591200 | 454877 | Equitable | N/A | 454877 | 0 | 0 | 0 | 0 | 454877 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4930 | Co-ordination of County Human Resource and Performance Management | Designing and installing a digital filing system/bulk filing for Human Resource Registry | To implement designing and installing a digital filing system/bulk filing for human resource registry for improved service delivery | Designing and installing a digital filing system/bulk filing for Human Resource Registry completed | 3111112 | Purchase of Software | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4931 | General Administration, Planning and Support Services | Development of a Human Resource Management Information System | To develop a Human Resource Management Information System | A Human Resource Management Information System developed | 3111112 | Purchase of Software | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2023/24 | 2023/24 | N/A | 10500000 | 10500000 | 10500000 | N/A | N/A | 10500000 | 0 | 0 | 0 | 0 | 10500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4932 | General Administration, Planning and Support Services | Tooling and equipping of Inspectorate Band | To implement tooling and equipping of inspectorate band for improved service delivery | Tooling and equipping of Inspectorate Band completed | 3111113 | N/A | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4933 | Co-ordination of Disaster Management and Humanitarian Assistance | Acquisition of Disaster response equipment | To procure Disaster response equipment | Disaster response equipment procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4585 | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | PUBLIC SERVICE, DEVOLUTION, CITIZEN ENGAGEMENT, DISASTER MANAGEMENT AND HUMANITARIAN ASSISTANCE | N/A | 2024/25 | 2024/25 | 2024/25 | 6000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4934 | Conditional Allocation for Rehabilitation of Youth Polytechnics | Conditional Allocation for Rehabilitation of Youth Polytechnics | To implement conditional allocation for rehabilitation of youth polytechnics for access to quality education and training | Conditional Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2020/21 | N/A | 66289894 | 3026 | 0 | Equitable | N/A | 0 | 3026 | 10193360 | 336859.2 | 10193360 | 66289894 | -10190334 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4935 | Construction of VTCs Hostels | Construction of VTCs Hostels | To construct VTCs Hostels | VTCs Hostels constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 6107075 | 6107075 | Equitable | N/A | 6107075 | 0 | 19900008 | 325.9 | 19900008 | 3566331 | -13792933 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4936 | Construction Of Hostels at Ruiyobei Vocational Training Centre | Construction Of Hostels at Ruiyobei Vocational Training Centre | To construct Hostels at Ruiyobei Vocational Training Centre | Hostels at Ruiyobei Vocational Training Centre constructed | 3110201 | Residential Buildings (including hostels) | Rongai | Solai | 0.099258 36.173883 1556.7939453125 3.808000087738037 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2187090 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2023 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation, ceiling infested with bats.
4937 | Completion And Equipping of Kiptenden ECDE Classroom, Water Tank | Completion And Equipping of Kiptenden ECDE Classroom, Water Tank | To complete and equip Kiptenden ECDE Classroom, Water Tank | Kiptenden ECDE Classroom, Water Tank completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.565472, 35.697288 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1549850 | 96.9 | 1549850 | 50150 | 50150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: not yet because the ECD has got no teacher. Viable: no.
4938 | Completion Of 1 Classroom at Ndasiata and Equipping | Completion Of 1 Classroom at Ndasiata and Equipping | To complete 1 Classroom at Ndasiata and Equipping | 1 Classroom at Ndasiata and Equipping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570773 35.664502 2506.1 5.699999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 416194 | 34.7 | 416194 | 1200000 | 783806 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project done NG cdf.
4939 | Construction 1 ECDE classroom at Kwendo | Construction 1 ECDE classroom at Kwendo | To construct 1 ECDE classroom at Kwendo | 1 ECDE classroom at Kwendo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2018 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 416194 | 100 | 416194 | 1500000 | -416194 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
4940 | Construction And Equipping ECDE Class And Pupils Toilet At Lelaitich Primary School | Construction And Equipping ECDE Class And Pupils Toilet At Lelaitich Primary School | To construct and equip ECDE Class And Pupils Toilet At Lelaitich Primary School | ECDE Class And Pupils Toilet At Lelaitich Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676213, 35.657443 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 646075 | 646075 | Equitable | N/A | 646075 | 0 | 646075 | 100 | 646075 | 646075 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
4941 | Construction Of ECDE Classroom At Kabigeriet | Construction Of ECDE Classroom At Kabigeriet | To construct ECDE Classroom At Kabigeriet | ECDE Classroom At Kabigeriet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2018 | 1200000 | 1099217 | 1349217 | Equitable | N/A | 1349217 | 0 | 416194 | 37.9 | 416194 | 1349217 | 683023 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
4942 | Construction Of One ECDE Classroom At Gorofa | Construction Of One ECDE Classroom At Gorofa | To construct One ECDE Classroom At Gorofa | One ECDE Classroom At Gorofa constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2024 | 1200000 | 1099217 | 1349217 | Equitable | N/A | 1349217 | 0 | 1199956 | 109.2 | 1199956 | 1349217 | -100739 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
4943 | Construction of Sigowet ECDE classroom | Construction of Sigowet ECDE classroom | To construct Sigowet ECDE classroom | Sigowet ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2024 | 1500000 | 1429210 | 1429210 | Equitable | N/A | 1429210 | 0 | 1199956 | 84 | 1199956 | 1429210 | 229254 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
4944 | Construction Of An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | Construction Of An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | To construct An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | An ECDE Class Water Tank And Sanitation Facility At Jacaranda School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
4945 | Construction Of Wanyororo Vocational Training Center | Construction Of Wanyororo Vocational Training Center | To construct Wanyororo Vocational Training Center | Wanyororo Vocational Training Center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
4946 | Construction & Equipping of One (1) ECD Classroom at Kelelwet Primary | Construction & Equipping of One (1) ECD Classroom at Kelelwet Primary | To construct & Equipping of One (1) ECD Classroom at Kelelwet Primary | & Equipping of One (1) ECD Classroom at Kelelwet Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4947 | Construction & Equipping of One (1) ECD Classroom at Kigonor Primary | Construction & Equipping of One (1) ECD Classroom at Kigonor Primary | To construct & Equipping of One (1) ECD Classroom at Kigonor Primary | & Equipping of One (1) ECD Classroom at Kigonor Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4948 | Construction & Equipping of One (1) ECD Classroom at Parkview Primary | Construction & Equipping of One (1) ECD Classroom at Parkview Primary | To construct & Equipping of One (1) ECD Classroom at Parkview Primary | & Equipping of One (1) ECD Classroom at Parkview Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4949 | Construction and equipping of two ECD classrooms at NYS Primary School | Construction and equipping of two ECD classrooms at NYS Primary School | To construct and equip two ECD classrooms at NYS Primary School | Two ECD classrooms at NYS Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.661265, 36.48513 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 2779040 | 2779040 | Equitable | N/A | 2779040 | 0 | 2779040 | 100 | 2779040 | 2779040 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors.
4950 | Construction and equipping of 2 ECDE classes at Crates Primary School | Construction and equipping of 2 ECDE classes at Crates Primary School | To construct and equip 2 ECDE classes at Crates Primary School | 2 ECDE classes at Crates Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.285216, 36.093812 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2932410 | 2932410 | Equitable | N/A | 2932410 | 0 | 2932410 | 100 | 2932410 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4951 | Construction of Administration Block and Toilet at Kariba Road Primary and St Marys Primary | Construction of Administration Block and Toilet at Kariba Road Primary and St Marys Primary | To construct Administration Block and Toilet at Kariba Road Primary and St Marys Primary | Administration Block and Toilet at Kariba Road Primary and St Marys Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.293619, 36.073886 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 4200000 | 4200000 | 4200000 | Equitable | N/A | 4200000 | 0 | 4200000 | 100 | 4200000 | 4200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4952 | Construction of Administration Block at St Pauls Primary | Construction of Administration Block at St Pauls Primary | To construct Administration Block at St Pauls Primary | Administration Block at St Pauls Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.296069, 36.07874 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3378688 | 3378688 | Equitable | N/A | 3378688 | 0 | 3378688 | 100 | 3378688 | 3378688 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Joly general merchants.
4953 | Construction of an Administration Block at Ngala School for the deaf | Construction of an Administration Block at Ngala School for the deaf | To construct an Administration Block at Ngala School for the deaf | An Administration Block at Ngala School for the deaf constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.291864, 36.075578 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 3500000 | 3378688 | 3378688 | Equitable | N/A | 3378688 | 0 | 3378688 | 100 | 3378688 | 3378688 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Joly General merchants ltd.
4954 | Construction Of ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | Construction Of ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | To construct ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.286701, 36.069091 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1199771 | 40 | 1199771 | 3000000 | 1800229 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4955 | Construction Of one ECD Classroom and toilets at Jamhuri Primary | Construction Of one ECD Classroom and toilets at Jamhuri Primary | To construct one ECD Classroom and toilets at Jamhuri Primary | One ECD Classroom and toilets at Jamhuri Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1199771 | 60 | 1199771 | 2000000 | 800229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4956 | Construction of two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | Construction of two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | To construct two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | Two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.252302, 36.193292 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 4600000 | 4600000 | 4600000 | Equitable | N/A | 4600000 | 0 | 1200000 | 26.1 | 1200000 | 4600000 | 3400000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company.
4957 | Kaburi ECDE construction of I classroom | Kaburi ECDE construction of I classroom | To implement kaburi ecde construction of i classroom for access to quality education and training | Kaburi ECDE construction of I classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.237247 36.23572 2418 3.0999999046325684 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
4958 | Construction and equipping of ECDE classroom at Kamathatha and toilet | Construction and equipping of ECDE classroom at Kamathatha and toilet | To construct and equip ECDE classroom at Kamathatha and toilet | ECDE classroom at Kamathatha and toilet constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1738820 | 96.6 | 1738820 | 61180 | 61180 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4959 | Construction of Kapkures ECDE classroom, equipping and toilet | Construction of Kapkures ECDE classroom, equipping and toilet | To construct Kapkures ECDE classroom, equipping and toilet | Kapkures ECDE classroom, equipping and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | -0.520686, 36.126673 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | Unspecified | 1800000 | 1710442 | 1710442 | Equitable | N/A | 1710442 | 0 | 1710442 | 100 | 1710442 | 1710442 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Unspecified.
4960 | Construction and Equipping of One classroom ECD at Ndimu | Construction and Equipping of One classroom ECD at Ndimu | To construct and equip One classroom ECD at Ndimu | One classroom ECD at Ndimu constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.279925, 35.765083 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | - | 1500000 | 1478090 | 1478090 | Equitable | N/A | 1478090 | 0 | 1478089 | 100 | 1478089 | 1478090 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4961 | Construction Of One ECD Classroom, Equipping and Water Tank at Simowet | Construction Of One ECD Classroom, Equipping and Water Tank at Simowet | To construct One ECD Classroom, Equipping and Water Tank at Simowet | One ECD Classroom, Equipping and Water Tank at Simowet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.288188 35.816137 2443.8 11.800000190734863 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1194994 | 79.7 | 1194994 | 1500000 | 305006 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4962 | Design And Construction Of Mucharage ECDE | Design And Construction Of Mucharage ECDE | To design and construct Mucharage ECDE | Mucharage ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.307435 35.749389 0 2599.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repairs and maintainance.
4963 | Design And Construction Of Nyakiambi Karunga ECDE | Design And Construction Of Nyakiambi Karunga ECDE | To design and construct Nyakiambi Karunga ECDE | Nyakiambi Karunga ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.180252 35.704339 0 3299.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
4964 | Design And Construction Of Tegat ECDE | Design And Construction Of Tegat ECDE | To design and construct Tegat ECDE | Tegat ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.27156 35.816038 2145.7 13.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair and maintainance.
4965 | Construction And Equipping of ECDE Classroom at Kanorero and Mwariki ECD | Construction And Equipping of ECDE Classroom at Kanorero and Mwariki ECD | To construct and equip ECDE Classroom at Kanorero and Mwariki ECD | ECDE Classroom at Kanorero and Mwariki ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.621053, 36.099955 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1166090 | 38.9 | 1166090 | 3000000 | 1833910 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
4966 | Design And Construction Of Mbombo ECDE And Toilets | Design And Construction Of Mbombo ECDE And Toilets | To design and construct Mbombo ECDE And Toilets | Mbombo ECDE And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.555641 36.103909 1951.146 0.6809999942779541 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | N/A | 1664971 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1199700 | 120 | 1199700 | 1000000 | -199700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Stalled.
4967 | Construction of classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | Construction of classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | To construct classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | Classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.474823, 36.333885 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 1800000 | 1682085 | 1682085 | Equitable | N/A | 1682085 | 0 | 1682085 | 100 | 1682085 | 1682085 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4968 | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | To construct and equip Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Maombi ECDE, toilet and completion and equipping of Ruiru ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 779440 | 779440 | Equitable | N/A | 779440 | 0 | 269520 | 34.6 | 269520 | 509920 | 509920 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4969 | Construction of Center of Excellence Modern workshop Njoro | Construction of Center of Excellence Modern workshop Njoro | To construct Center of Excellence Modern workshop Njoro | Center of Excellence Modern workshop Njoro constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 19900008 | 663.3 | 19900008 | 3566331 | -16900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4970 | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | To construct 1 ECD classroom, toilet and water tank at Kamuyu | 1 ECD classroom, toilet and water tank at Kamuyu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 1911040 | 1911040 | Equitable | N/A | 1911040 | 0 | 1487282 | 77.8 | 1487282 | 1911040 | 423758 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
4971 | Construction of 1 ECD classroom, toilet and water tank at Mountain View | Construction of 1 ECD classroom, toilet and water tank at Mountain View | To construct 1 ECD classroom, toilet and water tank at Mountain View | 1 ECD classroom, toilet and water tank at Mountain View constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 1911040 | 1911040 | Equitable | N/A | 1911040 | 0 | 1487282 | 77.8 | 1487282 | 1911040 | 423758 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
4972 | Construction Of One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | Construction Of One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | To construct One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | One Classroom at Mirera Primary School and Construction Of 4 Door Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.782556 36.44577 1954.9000244140625 4.5320000648498535 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199658 | 48 | 1199658 | 2500000 | 1300342 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Cost of the project 2,500,000.
4973 | Construction Of One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | Construction Of One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | To construct One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.805277 36.443929 1926.5 70.96199798583984 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199658 | 48 | 1199658 | 2500000 | 1300342 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project is stalled.
4974 | Construction of a classroom at Ndungiri Vocational Training Centre | Construction of a classroom at Ndungiri Vocational Training Centre | To construct a classroom at Ndungiri Vocational Training Centre | A classroom at Ndungiri Vocational Training Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.108053, 36.054603 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2020/2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 625600 | 52.1 | 625600 | 574400 | 574400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
4975 | Construction Of Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | Construction Of Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | To construct Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.106772 36.057525 1617.2 12.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 5500000 | 3745310 | 3745310 | Equitable | N/A | 3745310 | 0 | 3745310 | 100 | 3745310 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Start back engineering and consultancy company ltdncy. Assessor remarks: Requires completion.
4976 | Construction of perimeter fence and a gate at Tulwet ECD | Construction of perimeter fence and a gate at Tulwet ECD | To construct perimeter fence and a gate at Tulwet ECD | Perimeter fence and a gate at Tulwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.329281, 36.034277 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 279231 | 18.6 | 279231 | 1500000 | 1220769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ngambo Hardware.
4977 | Construction of an ECDE Administration block at Kibowen Komen ECDE | Construction of an ECDE Administration block at Kibowen Komen ECDE | To construct an ECDE Administration block at Kibowen Komen ECDE | An ECDE Administration block at Kibowen Komen ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.310573 36.053491 1787.5 6.389999866485596 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3800000 | 100 | 3800000 | 3800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: M/S SILBO HOLDINGS. Assessor remarks: Complete.
4978 | Construction of ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | Construction of ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | To construct ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.320788 36.057104 1780.0986245613312 98.4000015258789 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 3800000 | 3595630 | 3595630 | Equitable | N/A | 3595630 | 0 | 3595630 | 100 | 3595630 | 3595630 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: A very viable project,it met the needs of the residents. Contractor: CYRUS BOIT NGAMBO HARDWARES. Assessor remarks: A very viable project.
4979 | Completion Of Ribot ECDE Classroom | Completion Of Ribot ECDE Classroom | To complete Ribot ECDE Classroom | Ribot ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.410372 35.681463 2653 21.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 667928 | 111.3 | 667928 | 600000 | -67928 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
4980 | Construction And Equipping of ECDE Classroom at Chesaror | Construction And Equipping of ECDE Classroom at Chesaror | To construct and equip ECDE Classroom at Chesaror | ECDE Classroom at Chesaror constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.527932 35.73419 2592.6 50.099998474121094 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1250000 | 1250000 | 1250000 | Equitable | N/A | 1250000 | 0 | 312620 | 25 | 312620 | 1250000 | 937380 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4981 | Construction And Equipping of ECDE Classroom at Kirandich | Construction And Equipping of ECDE Classroom at Kirandich | To construct and equip ECDE Classroom at Kirandich | ECDE Classroom at Kirandich constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.47619, 35.66288 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1250000 | 1250000 | 1250000 | Equitable | N/A | 1250000 | 0 | 312620 | 25 | 312620 | 1250000 | 937380 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
4982 | Construction & equipping of Saptet Polytechnic workshop | Construction & equipping of Saptet Polytechnic workshop | To construct & equipping of Saptet Polytechnic workshop | & equipping of Saptet Polytechnic workshop constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.484797, 35.699813 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2024 | 2000000 | 1986650 | 1986650 | Equitable | N/A | 1986650 | 0 | 1986650 | 100 | 1986650 | 1986650 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4983 | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | To construct 1 ECDE class, teacher & pupils toilet & water tank at Ribot | 1 ECDE class, teacher & pupils toilet & water tank at Ribot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.53935 35.711058 2660.000244140625 24.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1468610 | 1468610 | Equitable | N/A | 1468610 | 0 | 747140 | 50.9 | 747140 | 721470 | 721470 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Class olmost complete but toilet and water tank not yet constructed.
4984 | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | To construct 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | 2 ECDE classroom at Upendo and renovation of teta youth polytechnique constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1852800 | 84.2 | 1852800 | 2200000 | 347200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4985 | Construction of Administration block at Saptet Polytechnic | Construction of Administration block at Saptet Polytechnic | To construct Administration block at Saptet Polytechnic | Administration block at Saptet Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.485055, 35.699632 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 2500000 | 2482045 | 2482045 | Equitable | N/A | 2482045 | 0 | 2482045 | 100 | 2482045 | 2482045 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4986 | Construction Of Classroom and equipping at Saptet Polytechnic | Construction Of Classroom and equipping at Saptet Polytechnic | To construct Classroom and equipping at Saptet Polytechnic | Classroom and equipping at Saptet Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.485136, 35.699573 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1852800 | 97.5 | 1852800 | 47200 | 47200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4987 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190000 | 1190000 | Equitable | N/A | 1190000 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4988 | Construction Of Tendwet ECD Classroom | Construction Of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.50589, 35.698535 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 851232.8 | 851232.8 | Equitable | N/A | 851232.8 | 0 | 312620 | 36.7 | 312620 | 538613 | 538612.8 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4989 | Construction And Equipping of Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | Construction And Equipping of Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | To construct and equip Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kiamaina | -0.265277 36.114494 1868.5 19.634000778198242 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
4990 | Construction And Equipping Of 1 ECDE Classroom at Kipkongor | Construction And Equipping Of 1 ECDE Classroom at Kipkongor | To construct and equip 1 ECDE Classroom at Kipkongor | 1 ECDE Classroom at Kipkongor constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.578837 35.549055 2395.4 26.799999237060547 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199995 | 92.3 | 1199995 | 1300000 | 100005 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not meet. Assessor remarks: No project.
4991 | Construction And Equipping Of 1 ECDE Classroom at Kiptagich Primary | Construction And Equipping Of 1 ECDE Classroom at Kiptagich Primary | To construct and equip 1 ECDE Classroom at Kiptagich Primary | 1 ECDE Classroom at Kiptagich Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.572763 35.614065 2486.500244140625 8.199999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199995 | 92.3 | 1199995 | 1300000 | 100005 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started hence residents needs were not met.. Contractor: Don't know. Assessor remarks: There are no pit latrines under department of trade at Kiptagich market.
4992 | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | To construct 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2468070 | 2468070 | Equitable | N/A | 2468070 | 0 | 1270177 | 51.5 | 1270177 | 2468070 | 1197893 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
4993 | Construction Of Ekabugunot ECDE | Construction Of Ekabugunot ECDE | To construct Ekabugunot ECDE | Ekabugunot ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2014/15 | 2014/15 | 2014/15 | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 1199995 | 120.1 | 1199995 | 999363 | -200632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
4994 | Construction Of Emitik ECD Classroom | Construction Of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1799740 | 1799740 | Equitable | N/A | 1799740 | 0 | 1199995 | 66.7 | 1199995 | 1799740 | 599745 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
4995 | Construction Of Hostel at Cheptuech Polytechnic | Construction Of Hostel at Cheptuech Polytechnic | To construct Hostel at Cheptuech Polytechnic | Hostel at Cheptuech Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.572763 35.614065 2486.500244140625 8.199999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started hence residents needs were not met.. Contractor: Don't know. Assessor remarks: There are no pit latrines under department of trade at Kiptagich market.
4996 | Construction Of Lelpanga ECD Class | Construction Of Lelpanga ECD Class | To construct Lelpanga ECD Class | Lelpanga ECD Class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1147660 | 63.8 | 1147660 | 1800000 | 652340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
4997 | Construction and equipping of Chepuyet ECD | Construction and equipping of Chepuyet ECD | To construct and equip Chepuyet ECD | Chepuyet ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376934, 35.529857 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1458050 | 1458050 | Equitable | N/A | 1458050 | 0 | 516100 | 35.4 | 516100 | 941950 | 941950 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4998 | Construction and equipping of Kiamashamba ECD | Construction and equipping of Kiamashamba ECD | To construct and equip Kiamashamba ECD | Kiamashamba ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376934, 35.529857 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1453170 | 1453170 | Equitable | N/A | 1453170 | 0 | 1317150 | 90.6 | 1317150 | 136020 | 136020 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4999 | Construction Of An ECD Classroom At Chebuiyot | Construction Of An ECD Classroom At Chebuiyot | To construct An ECD Classroom At Chebuiyot | An ECD Classroom At Chebuiyot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1499880 | 150 | 1499880 | 1000000 | -499880 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
5000 | Construction of 5 day care classrooms at Lakeview ECDE | Construction of 5 day care classrooms at Lakeview ECDE | To construct 5 day care classrooms at Lakeview ECDE | 5 day care classrooms at Lakeview ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | -0.733707, 36.434517 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 7500000 | 7158019.8 | 7158019.8 | Equitable | N/A | 7158019.8 | 0 | 7157555 | 100 | 7157555 | 465 | 464.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yed.
5001 | Construction of one ECDE classsrooms at Unity ECD | Construction of one ECDE classsrooms at Unity ECD | To construct one ECDE classsrooms at Unity ECD | One ECDE classsrooms at Unity ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 7157555 | 100 | 7157555 | 1800000 | -7157555 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5002 | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | To construct ECDE classroom and Toilet and Equipping at Moi Primary School | ECDE classroom and Toilet and Equipping at Moi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.277232 36.067338 1862.4909989898247 8 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1763240 | 1763240 | Equitable | N/A | 1763240 | 0 | 1480 | 0.1 | 1480 | 1763240 | 1761760 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: ..
5003 | Construction And Equipping of Ngeya ECD | Construction And Equipping of Ngeya ECD | To construct and equip Ngeya ECD | Ngeya ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 818350 | 54.6 | 818350 | 1500000 | 681650 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5004 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 1199240 | 1199240 | Equitable | N/A | 1199240 | 0 | 1199672 | 100 | 1199672 | 1199240 | -432 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5005 | Construction of a Polytechnic at Maai Mahiu | Construction of a Polytechnic at Maai Mahiu | To construct a Polytechnic at Maai Mahiu | A Polytechnic at Maai Mahiu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.990353, 36.586414 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 9898670 | 9898670 | Equitable | N/A | 9898670 | 0 | 8116489 | 82 | 8116489 | 1782181 | 1782181 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Once operational hands on courses will be offered and the objective will be met.. Viable: Yes..
5006 | Design And Construction Of Karima Pry ECDE | Design And Construction Of Karima Pry ECDE | To design and construct Karima Pry ECDE | Karima Pry ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1182680 | 1182680 | Equitable | N/A | 1182680 | 0 | 1182650 | 100 | 1182650 | 30 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5007 | Construction and equipping of 1 ECD classroom at Nkapani | Construction and equipping of 1 ECD classroom at Nkapani | To construct and equip 1 ECD classroom at Nkapani | 1 ECD classroom at Nkapani constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2499394 | 166.6 | 2499394 | 1500000 | -999394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5008 | Construction And Equipping of Ngati ECD Two Door Toilets, Urinal, | Construction And Equipping of Ngati ECD Two Door Toilets, Urinal, | To construct and equip Ngati ECD Two Door Toilets, Urinal, | Ngati ECD Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 23.4 | 584286 | 2500000 | 1915714 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5009 | Construction And Equipping of Ngunyumu ECD And Two Door Toilets, Urinal, | Construction And Equipping of Ngunyumu ECD And Two Door Toilets, Urinal, | To construct and equip Ngunyumu ECD And Two Door Toilets, Urinal, | Ngunyumu ECD And Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5010 | Construction And Equipping of Sero ECD, Two Door Toilets, Urinal, | Construction And Equipping of Sero ECD, Two Door Toilets, Urinal, | To construct and equip Sero ECD, Two Door Toilets, Urinal, | Sero ECD, Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 23.4 | 584286 | 2500000 | 1915714 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5011 | Construction Of 2 ECD Classrooms In Tangi Tatu | Construction Of 2 ECD Classrooms In Tangi Tatu | To construct 2 ECD Classrooms In Tangi Tatu | 2 ECD Classrooms In Tangi Tatu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2399999 | 2399999 | Equitable | N/A | 2399999 | 0 | 2499394 | 104.1 | 2499394 | 2399999 | -99395 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5012 | Design And Construction Of ECD Classroom At Natooli | Design And Construction Of ECD Classroom At Natooli | To design and construct ECD Classroom At Natooli | ECD Classroom At Natooli designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5013 | Design And Construction Of ECD Classroom At Ndabibi Central | Design And Construction Of ECD Classroom At Ndabibi Central | To design and construct ECD Classroom At Ndabibi Central | ECD Classroom At Ndabibi Central designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2739065 | 2739065 | 2739065 | Equitable | N/A | 2739065 | 0 | 2499394 | 91.2 | 2499394 | 2739065 | 239671 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5014 | Design And Construction Of ECD Classroom At Ngondi | Design And Construction Of ECD Classroom At Ngondi | To design and construct ECD Classroom At Ngondi | ECD Classroom At Ngondi designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5015 | Nkampani Nursery School | Nkampani Nursery School | To implement nkampani nursery school for access to quality education and training | Nkampani Nursery School completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 997135 | 997135 | Equitable | N/A | 997135 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
5016 | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | To construct classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.417015 0 2000 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N//A. Viable: N//A. Assessor remarks: N//A.
5017 | Construction Of Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | Construction Of Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | To construct Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.417015 0 2000 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 2600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N//A. Viable: N//A. Assessor remarks: N//A.
5018 | Construction and Equiping of ECDE Classroom, Toilets and Water tank at Tuiyobei Classrooom | Construction and Equiping of ECDE Classroom, Toilets and Water tank at Tuiyobei Classrooom | To construct and Equiping of ECDE Classroom, Toilets and Water tank at Tuiyobei Classrooom | And Equiping of ECDE Classroom, Toilets and Water tank at Tuiyobei Classrooom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.315941 35.844828 2322.209591306301 14 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1914000 | 100 | 1914000 | 86000 | -1914000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5019 | Construction of a class and a Toilet plus equipping (Kamungei Primary ECD) | Construction of a class and a Toilet plus equipping (Kamungei Primary ECD) | To construct a class and a Toilet plus equipping (Kamungei Primary ECD) | A class and a Toilet plus equipping (Kamungei Primary ECD) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.338892 35.806045 2586 6 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1990590 | 1990590 | Equitable | N/A | 1990590 | 0 | 1990590 | 100 | 1990590 | 1990590 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partly. Viable: Partly. Assessor remarks: Toiler not contructed.
5020 | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | To construct Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.353645, 35.870354 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | N/A | 5200000 | 5199600 | 5199600 | Equitable | N/A | 5199600 | 0 | 2599800 | 50 | 2599800 | 5199600 | 2599800 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5021 | Construction of ECDE classroom at Kianugu ECD | Construction of ECDE classroom at Kianugu ECD | To construct ECDE classroom at Kianugu ECD | ECDE classroom at Kianugu ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.626036, 36.026932 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1199920 | 80 | 1199920 | 1500000 | 300080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
5022 | Completion and equipping of Sigor ECD | Completion and equipping of Sigor ECD | To complete and equip Sigor ECD | Sigor ECD completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.547133, 36.008833 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2017 | 1000000 | 992000 | 992000 | Equitable | N/A | 992000 | 0 | 0 | 0 | 0 | 992000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known.
5023 | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | To construct and equip Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.502886, 35.974852 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 6000000 | 5695960 | 5695960 | Equitable | N/A | 5695960 | 0 | 1984380 | 34.8 | 1984380 | 3711580 | 3711580 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
5024 | Construction And Equipping of Saramek and Kapsinendet ECD | Construction And Equipping of Saramek and Kapsinendet ECD | To construct and equip Saramek and Kapsinendet ECD | Saramek and Kapsinendet ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.524172 35.952538 2633.2000000000003 14.300000190734863 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1984380 | 66.1 | 1984380 | 3000000 | 1015620 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
5025 | Construction And Equipping of ECD Classroom at Nakuru Teachers Primary School | Construction And Equipping of ECD Classroom at Nakuru Teachers Primary School | To construct and equip ECD Classroom at Nakuru Teachers Primary School | ECD Classroom at Nakuru Teachers Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Menengai | -0.272842, 36.106843 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/2025 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 3499981 | 205.9 | 3499981 | 1700000 | -1799981 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5026 | Building and equipping of a workshop in Mangu Polytechnic | Building and equipping of a workshop in Mangu Polytechnic | To implement building and equipping of a workshop in mangu polytechnic for access to quality education and training | Building and equipping of a workshop in Mangu Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.225332 35.972693 1934.5 10.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3600000 | 3423400 | 3423400 | Equitable | N/A | 3423400 | 0 | 3423400 | 100 | 3423400 | 3423400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more chairs and desks.
5027 | Construction Of One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | Construction Of One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | To construct One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.503687, 36.062987 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 4500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5028 | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | To upgrade Former Mukinyai Nursery school to be an Annex Polytechnic through tarmacking for improved road connectivity | Former Mukinyai Nursery school to be an Annex Polytechnic tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.205493 35.796119 0 500 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 1963020 | 1963020 | Equitable | N/A | 1963020 | 0 | 0 | 0 | 0 | 1963020 | 0 | Stalled | 0 | N/A | needs more allocation of funds | 2022 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yet to be. Assessor remarks: Formerly ECD , converted to polytechnic.
5029 | Completion of Chepseon ECDE Classroom | Completion of Chepseon ECDE Classroom | To complete Chepseon ECDE Classroom | Chepseon ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.209656, 35.841459 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1200000 | 240 | 1200000 | 500000 | -700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Contractor: Yet to start to advertise.
5030 | Construction and equipping of one ECDE Classroom at Kirobon primary school | Construction and equipping of one ECDE Classroom at Kirobon primary school | To construct and equip one ECDE Classroom at Kirobon primary school | One ECDE Classroom at Kirobon primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.290892, 35.986887 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 1700000 | 1670660 | 1670660 | Equitable | N/A | 1670660 | 0 | 1670660 | 100 | 1670660 | 1670660 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Viable. Contractor: M/s Gold.
5031 | Construction Of 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | Construction Of 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | To construct 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.259698, 35.980502 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2951680 | 98.4 | 2951680 | 3000000 | 48320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/s claysand.
5032 | Construction of Lelechwet ECDE Classroom | Construction of Lelechwet ECDE Classroom | To construct Lelechwet ECDE Classroom | Lelechwet ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.279457 35.88394 2110.2 6.099999904632568 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1833480 | 1833480 | Equitable | N/A | 1833480 | 0 | 1200000 | 65.4 | 1200000 | 1833480 | 633480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
5033 | Construction of Wardai Polytechnic | Construction of Wardai Polytechnic | To construct Wardai Polytechnic | Wardai Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 499994 | 25 | 499994 | 2000000 | 1500006 | Stalled | 90 | 25 | Stalled — reasons to be confirmed by department | 2022 | N/A | 1500006 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
5034 | Construction of Youth Polytechnic Classrooms at Mimwata Public Land | Construction of Youth Polytechnic Classrooms at Mimwata Public Land | To construct Youth Polytechnic Classrooms at Mimwata Public Land | Youth Polytechnic Classrooms at Mimwata Public Land constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.241648, 35.909491 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 2911820 | 2911820 | Equitable | N/A | 2911820 | 0 | 2951680 | 101.4 | 2951680 | 2911820 | -39860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Gold.
5035 | Construction of Nyairoko - Kairi ECDE | Construction of Nyairoko - Kairi ECDE | To construct Nyairoko - Kairi ECDE | Nyairoko - Kairi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1200000 | 80 | 1200000 | 1500000 | 300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5036 | Construction and equipping of an ECD Classroom at Munyu | Construction and equipping of an ECD Classroom at Munyu | To construct and equip an ECD Classroom at Munyu | An ECD Classroom at Munyu constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1473625 | 1473625 | Equitable | N/A | 1473625 | 0 | 2999064 | 203.5 | 2999064 | 1473625 | -1525439 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
5037 | Construction Of 2 ECDE Classrooms at Mirugi Kariuki and Mburu Gichua Primary School | Construction Of 2 ECDE Classrooms at Mirugi Kariuki and Mburu Gichua Primary School | To construct 2 ECDE Classrooms at Mirugi Kariuki and Mburu Gichua Primary School | 2 ECDE Classrooms at Mirugi Kariuki and Mburu Gichua Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.369863, 36.15245 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2715032 | 90.5 | 2715032 | 284968 | 284968 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Jambobee incorporation limited.
5038 | Construction of Mzee Wanyama Polytechnic | Construction of Mzee Wanyama Polytechnic | To construct Mzee Wanyama Polytechnic | Mzee Wanyama Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.372659, 36.149715 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2022/23 | 2023/2024 | 5445927 | 5398000 | 5398000 | Equitable | N/A | 5398000 | 0 | 5025850 | 93.1 | 5025850 | 5000000 | 372150 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fino limited.
5039 | Construction Of Vocational Polytechnic At Free Area | Construction Of Vocational Polytechnic At Free Area | To construct Vocational Polytechnic At Free Area | Vocational Polytechnic At Free Area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.293514 36.118728 1839.199951171875 37.99700164794922 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 4344590 | 4344590 | Equitable | N/A | 4344590 | 0 | 5025850 | 115.7 | 5025850 | 4344590 | -681260 | Stalled | 75 | 100 | Stalled — reasons to be confirmed by department | 2019 | N/A | -681260 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Belistra enterprises ltd. Assessor remarks: No occupation certificate issued.
5040 | Design And Construction Of 1 ECDE Classroom At Naka Primary | Design And Construction Of 1 ECDE Classroom At Naka Primary | To design and construct 1 ECDE Classroom At Naka Primary | 1 ECDE Classroom At Naka Primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.289113 36.103626 1817.699951171875 6.599999904632568 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 226.3 | 2715032 | 1200000 | -1515032 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require funds more funds for completion.
5041 | Completion of Inginge ECD | Completion of Inginge ECD | To complete Inginge ECD | Inginge ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.401883 35.907934 2429.297805547889 4.23799991607666 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 500000 | 476480 | 476480 | Equitable | N/A | 476480 | 0 | 0 | 0 | 0 | 476480 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
5042 | Tiritagoi ECD - Construction Of 1 Classroom | Tiritagoi ECD - Construction Of 1 Classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction Of 1 Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.417516 35.906162 2476.5755676023055 30 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
5043 | Design And Construction Of Kimugui ECDE Classroom | Design And Construction Of Kimugui ECDE Classroom | To design and construct Kimugui ECDE Classroom | Kimugui ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.433627 35.887802 2581.822998046875 4.065000057220459 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 569 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The ECDE is a stand alone school. The classroom construction did not meet the standards and therefore the amount allocated didn't meet the required scope of work..
5044 | Design And Construction Of Korovio ECDE Classroom | Design And Construction Of Korovio ECDE Classroom | To design and construct Korovio ECDE Classroom | Korovio ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.410761 35.899338 2463.547607421875 10.36299991607666 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
5045 | Design And Construction Of Masaita ECDE Classroom And Toilets | Design And Construction Of Masaita ECDE Classroom And Toilets | To design and construct Masaita ECDE Classroom And Toilets | Masaita ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
5046 | Design And Construction Of Missipei ECDE Classroom And Toilets | Design And Construction Of Missipei ECDE Classroom And Toilets | To design and construct Missipei ECDE Classroom And Toilets | Missipei ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
5047 | Completion and equipping of an ECDE at Tarakuet | Completion and equipping of an ECDE at Tarakuet | To complete and equip an ECDE at Tarakuet | An ECDE at Tarakuet completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.331569 35.953914 2141.900146484375 4.072999954223633 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 939950 | 939950 | Equitable | N/A | 939950 | 0 | 939950 | 100 | 939950 | 939950 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done work.
5048 | Construction and equipping 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | Construction and equipping 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | To construct and equip 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.335879, 35.947758 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 6000000 | 5915880 | 5915880 | Equitable | N/A | 5915880 | 0 | 5915880 | 100 | 5915880 | 5915880 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch.
5049 | Construction of Mwigito village ECD | Construction of Mwigito village ECD | To construct Mwigito village ECD | Mwigito village ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.380206 35.92605 2284.955810546875 5.573999881744385 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1197000 | 59.9 | 1197000 | 2000000 | 803000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Tiecim ltd. Assessor remarks: In good state.
5050 | Construction of Piave, Nyakinywa Kware ECDE | Construction of Piave, Nyakinywa Kware ECDE | To construct Piave, Nyakinywa Kware ECDE | Piave, Nyakinywa Kware ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.324494 35.975425 2064.329345703125 10.163999557495117 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1197000 | 59.9 | 1197000 | 2000000 | 803000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
5051 | Completion Of Songo ECDE Classroom | Completion Of Songo ECDE Classroom | To complete Songo ECDE Classroom | Songo ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.404183 35.662365 2637 14.899999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 998985 | 998985 | Equitable | N/A | 998985 | 0 | 261174 | 26.1 | 261174 | 998985 | 737811 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sumcott Enterprises. Assessor remarks: Needs urgent painting.
5052 | Construction and Equipping of Githiriga ECDE | Construction and Equipping of Githiriga ECDE | To construct and equip Githiriga ECDE | Githiriga ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1469600 | 1469600 | Equitable | N/A | 1469600 | 0 | 800000 | 54.4 | 800000 | 1469600 | 669600 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5053 | Construction and Equipping of Kenjoketty ECDE | Construction and Equipping of Kenjoketty ECDE | To construct and equip Kenjoketty ECDE | Kenjoketty ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1469600 | 1469600 | Equitable | N/A | 1469600 | 0 | 115000 | 7.8 | 115000 | 1469600 | 1354600 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5054 | Construction and Equipping of Lelaitich ECDE | Construction and Equipping of Lelaitich ECDE | To construct and equip Lelaitich ECDE | Lelaitich ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1469600 | 1469600 | Equitable | N/A | 1469600 | 0 | 115000 | 7.8 | 115000 | 1469600 | 1354600 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5055 | Construction and Equipping of Nyongeres ECDE | Construction and Equipping of Nyongeres ECDE | To construct and equip Nyongeres ECDE | Nyongeres ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1469600 | 1469600 | Equitable | N/A | 1469600 | 0 | 800000 | 54.4 | 800000 | 1469600 | 669600 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5056 | Construction And Equipping of Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | Construction And Equipping of Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | To construct and equip Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.313743, 35.658717 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | - | 4400000 | 4400000 | 4400000 | Equitable | N/A | 4400000 | 0 | 2730796 | 62.1 | 2730796 | 1669204 | 1669204 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES.
5057 | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | To construct One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.365508, 35.60519 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2023-2024 | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 2207393 | 46 | 2207393 | 2592607 | 2592607 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5058 | Construction of Sugutek ECDE | Construction of Sugutek ECDE | To construct Sugutek ECDE | Sugutek ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.364767 35.727897 2851.5 5.099999904632568 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 800000 | 53.3 | 800000 | 700000 | 700000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sumcott Enterprise LTD. Assessor remarks: Good.
5059 | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | To construct Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.914466, 36.304362 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2016/17 | 1195717 | 2491717 | 2491717 | Equitable | N/A | 2491717 | 0 | 2206597 | 88.6 | 2206597 | 285120 | 285120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5060 | Mvuke ECD | Mvuke ECD | To implement mvuke ecd for access to quality education and training | Mvuke ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197888 | 1197888 | Equitable | N/A | 1197888 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
5061 | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | To construct and equip 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.836914, 36.366297 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 4500000 | 4398540 | 4398540 | Equitable | N/A | 4398540 | 0 | 2633481 | 59.9 | 2633481 | 1765059 | 1765059 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.the tank is being used from a different structure.
5062 | Completion and equipping (furniture) of Mwariki TVET | Completion and equipping (furniture) of Mwariki TVET | To complete and equip (furniture) of Mwariki TVET | (furniture) of Mwariki TVET completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Rhonda | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5063 | Construction of Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | Construction of Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | To construct Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | Classroom and workshop at Mwariki Vocational Training Centre (one storey building) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Rhonda | -0.313651, 36.067349 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 23/24 | 14000000 | 6988412 | 6988412 | Equitable | N/A | 6988412 | 0 | 6988412 | 100 | 6988412 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S CRANBERRY DESIGNERS LTD.
5064 | Completion & Equipping of Mama Ngina ECDE Highrise Classrooms | Completion & Equipping of Mama Ngina ECDE Highrise Classrooms | To complete & Equipping of Mama Ngina ECDE Highrise Classrooms | & Equipping of Mama Ngina ECDE Highrise Classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 7500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5065 | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | To construct and equip a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | A high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 9000000 | 8793630 | 8793630 | Equitable | N/A | 8793630 | 0 | 0 | 0 | 0 | 8793630 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5066 | Construction And Equipping Of 1 Classroom at Karima ECDE | Construction And Equipping Of 1 Classroom at Karima ECDE | To construct and equip 1 Classroom at Karima ECDE | 1 Classroom at Karima ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.252468, 35.657327 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1880400 | 94 | 1880400 | 119600 | 119600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5067 | Construction & Equipping of Aeriol ECDE - 1 class | Construction & Equipping of Aeriol ECDE - 1 class | To construct & Equipping of Aeriol ECDE - 1 class | & Equipping of Aeriol ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.271818 35.668245 2737.4 4.400000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1959610 | 1959610 | Equitable | N/A | 1959610 | 0 | 1880400 | 96 | 1880400 | 1959610 | 79210 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njumuru Enterprises Ltd. Assessor remarks: The classroom is in use, however they have no county employed teacher, the classroom has terrazzo floor, well painted walls, electrical works done, however the roof appears to be leaking in some sections. The school has a small field, and no permanent water source.
5068 | Construction & Equipping of Kiletien ECDE - 1 class | Construction & Equipping of Kiletien ECDE - 1 class | To construct & Equipping of Kiletien ECDE - 1 class | & Equipping of Kiletien ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.235177 35.662557 2740.7999999999997 13.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1959610 | 1959610 | Equitable | N/A | 1959610 | 0 | 1880400 | 96 | 1880400 | 1959610 | 79210 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leaking roof noted, peeling of Wall paint, gutters need fixing.
5069 | Construction And Equipping Of 1 ECDE Classroom at Kipsyenan | Construction And Equipping Of 1 ECDE Classroom at Kipsyenan | To construct and equip 1 ECDE Classroom at Kipsyenan | 1 ECDE Classroom at Kipsyenan constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.046127 36.049341 1647 9.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 862249 | 57.5 | 862249 | 637751 | 637751 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require Renovation and additional class.
5070 | Construction of classroom at Ruiyobei Vocational Training Centre | Construction of classroom at Ruiyobei Vocational Training Centre | To construct classroom at Ruiyobei Vocational Training Centre | Classroom at Ruiyobei Vocational Training Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.099258 36.173883 1556.7939453125 3.808000087738037 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 2187090 | Equitable | N/A | 2187090 | 0 | 0 | 0 | 0 | 2187090 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2022 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation, ceiling infested with bats.
5071 | Construction Of 1 Class At Kamemo Primary ECDE | Construction Of 1 Class At Kamemo Primary ECDE | To construct 1 Class At Kamemo Primary ECDE | 1 Class At Kamemo Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.030872, 36.196235 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2892 | 0.2 | 2892 | 1183015 | 1497108 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
5072 | Construction Of A ECDE Center And Equipping at Tetu | Construction Of A ECDE Center And Equipping at Tetu | To construct A ECDE Center And Equipping at Tetu | A ECDE Center And Equipping at Tetu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.040257, 36.222773 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1499984 | 75 | 1499984 | 2000000 | 500016 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5073 | Construction and Equipping Ngochopta ECDE classroom | Construction and Equipping Ngochopta ECDE classroom | To construct and equip Ngochopta ECDE classroom | Ngochopta ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.438399 35.609035 0 1899.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1457080 | 1457080 | Equitable | N/A | 1457080 | 0 | 1457080 | 100 | 1457080 | 1457080 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Potholes no teacher toilet and pupils toilet.
5074 | Construction and Equipping of Kiptongoton ECDE classroom | Construction and Equipping of Kiptongoton ECDE classroom | To construct and equip Kiptongoton ECDE classroom | Kiptongoton ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.538982 35.643548 0 2799.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1457080 | 1457080 | Equitable | N/A | 1457080 | 0 | 1457080 | 100 | 1457080 | 1457080 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5075 | Construction and Equipping of Sibo ECDE classroom | Construction and Equipping of Sibo ECDE classroom | To construct and equip Sibo ECDE classroom | Sibo ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.438399 35.609035 0 1899.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1457080 | 1457080 | Equitable | N/A | 1457080 | 0 | 1457080 | 100 | 1457080 | 1457080 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Potholes no teacher toilet and pupils toilet.
5076 | Construction Of ECDE Classroom At Busienkiruk | Construction Of ECDE Classroom At Busienkiruk | To construct ECDE Classroom At Busienkiruk | ECDE Classroom At Busienkiruk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
5077 | Construction Of ECDE Classroom At Korao | Construction Of ECDE Classroom At Korao | To construct ECDE Classroom At Korao | ECDE Classroom At Korao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1138490 | 1138490 | Equitable | N/A | 1138490 | 0 | 1319 | 0.1 | 1319 | 1138490 | 1137171 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
5078 | Construction Of ECDE Classroom At Tach Asis | Construction Of ECDE Classroom At Tach Asis | To construct ECDE Classroom At Tach Asis | ECDE Classroom At Tach Asis constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
5079 | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | To construct One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.509537 35.634567 2510.2 5.699999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 4762794 | 2374975 | 2374975 | Equitable | N/A | 2374975 | 0 | 2387819 | 100.5 | 2387819 | 2374975 | -12844 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
5080 | Construction Of Suguyek ECDE, Equipping and Installation of Water Tank | Construction Of Suguyek ECDE, Equipping and Installation of Water Tank | To construct Suguyek ECDE, Equipping and Installation of Water Tank | Suguyek ECDE, Equipping and Installation of Water Tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.538982 35.643548 0 2799.9990234375 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5081 | Construction and equipping of one Classroom at Rafiki ECD | Construction and equipping of one Classroom at Rafiki ECD | To construct and equip one Classroom at Rafiki ECD | One Classroom at Rafiki ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1473625 | 1473625 | Equitable | N/A | 1473625 | 0 | 1199940 | 81.4 | 1199940 | 1473625 | 273685 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
5082 | Construction of ECDE classroom at Ndenderu A Kahuho | Construction of ECDE classroom at Ndenderu A Kahuho | To construct ECDE classroom at Ndenderu A Kahuho | ECDE classroom at Ndenderu A Kahuho constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.34223 35.745215 2732.1 99.69999694824219 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1399966 | 0 | 1399966 | Equitable | N/A | 1399966 | 0 | 1199940 | 100 | 1199940 | 1399966 | -1199940 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs renovations.
5083 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5084 | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | To construct and equip Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 4500000 | 4383345 | 4383345 | Equitable | N/A | 4383345 | 0 | 3141914 | 71.7 | 3141914 | 1241431 | 1241431 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5085 | Construction Of 2 Classrooms at Shalom ECDE and Ngessuim ECDE | Construction Of 2 Classrooms at Shalom ECDE and Ngessuim ECDE | To construct 2 Classrooms at Shalom ECDE and Ngessuim ECDE | 2 Classrooms at Shalom ECDE and Ngessuim ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 1155310 | 32.1 | 1155310 | 3600000 | 2444690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5086 | Construction Of ECD Classroom at Kandutura Primary | Construction Of ECD Classroom at Kandutura Primary | To construct ECD Classroom at Kandutura Primary | ECD Classroom at Kandutura Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1155310 | 64.2 | 1155310 | 1800000 | 644690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5087 | Construction Of One Classroom At Rajuera ECDE | Construction Of One Classroom At Rajuera ECDE | To construct One Classroom At Rajuera ECDE | One Classroom At Rajuera ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5088 | Construction of 2 ECDE classrooms at Naivasha Central Primary School | Construction of 2 ECDE classrooms at Naivasha Central Primary School | To construct 2 ECDE classrooms at Naivasha Central Primary School | 2 ECDE classrooms at Naivasha Central Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.714838, 36.435556 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3327369 | 3208080 | 3208080 | Equitable | N/A | 3208080 | 0 | 3208039 | 100 | 3208039 | 41 | 41 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
5089 | Construction Of ECD Classroom at Naivasha Prison ECDE | Construction Of ECD Classroom at Naivasha Prison ECDE | To construct ECD Classroom at Naivasha Prison ECDE | ECD Classroom at Naivasha Prison ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.705306, 36.431194 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3208039 | 213.9 | 3208039 | 1500000 | -1708039 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5090 | Completion of Resource Center Nakuru Phase 2 | Completion of Resource Center Nakuru Phase 2 | To complete Resource Center Nakuru Phase 2 | Resource Center Nakuru Phase 2 completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 4986452 | 4986452 | Equitable | N/A | 4986452 | 0 | 0 | 0 | 0 | 4986452 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5091 | Repair of ECDE classroom at Umoja Nursery and fencing | Repair of ECDE classroom at Umoja Nursery and fencing | To rehabilitate ECDE classroom at Umoja Nursery and fencing to restore functionality | ECDE classroom at Umoja Nursery and fencing rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Dundori | -0.258357 36.2358 2331.60009765625 4.599999904632568 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 1200000 | 150 | 1200000 | 800000 | -400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Eshipah limited. Assessor remarks: Good.
5092 | Renovation & Extension of ECDE Kitchen At Race Track Primary School | Renovation & Extension of ECDE Kitchen At Race Track Primary School | To rehabilitate & Extension of ECDE Kitchen At Race Track Primary School to restore functionality | & Extension of ECDE Kitchen At Race Track Primary School rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru East | Flamingo | -0.31045, 36.070103 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Fy2023-2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 352009 | 17.6 | 352009 | 2000000 | 1647991 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5093 | Renovation of Menengai Hill primary School ECDE | Renovation of Menengai Hill primary School ECDE | To rehabilitate Menengai Hill primary School ECDE to restore functionality | Menengai Hill primary School ECDE rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Kiamaina | -0.25047, 36.090167 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5094 | Rehabilitation Of ECDE At St. Theresa Primary School | Rehabilitation Of ECDE At St. Theresa Primary School | To rehabilitate ECDE At St. Theresa Primary School to restore functionality | ECDE At St. Theresa Primary School rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru East | Kivumbini | -0.298625 36.086695 1779.699951171875 56.099998474121094 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 3793570 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5095 | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | To rehabilitate two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired to restore functionality | Two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.274307, 36.057502 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5096 | Renovation Of Gwa-share ECDE Classroom and Equipping | Renovation Of Gwa-share ECDE Classroom and Equipping | To rehabilitate Gwa-share ECDE Classroom and Equipping to restore functionality | Gwa-share ECDE Classroom and Equipping rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Gilgil | Malewa West | -0.612613, 36.398477 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5097 | Renovation Of 2 Sawaiti ECDE Classes | Renovation Of 2 Sawaiti ECDE Classes | To rehabilitate 2 Sawaiti ECDE Classes to restore functionality | 2 Sawaiti ECDE Classes rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Rongai | Soin | -0.071965 36.043668 1622.8 5.199999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 500000 | 50 | 500000 | 500000 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The school needs teachers and learners toilet,water Tank, Furnitures and outdoor play materials.
5098 | Construction Of 4 Door Bondeni ECDE Toilets and Urinal | Construction Of 4 Door Bondeni ECDE Toilets and Urinal | To construct 4 Door Bondeni ECDE Toilets and Urinal | 4 Door Bondeni ECDE Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.576548, 35.700157 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 1199956 | 150 | 1199956 | 800000 | -399956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes.
5099 | Construction Of 6 Door Kapkorio ECDE Toilets and Urinal | Construction Of 6 Door Kapkorio ECDE Toilets and Urinal | To construct 6 Door Kapkorio ECDE Toilets and Urinal | 6 Door Kapkorio ECDE Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.576548, 35.700157 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 950000 | 950000 | 950000 | Equitable | N/A | 950000 | 0 | 1000000 | 105.3 | 1000000 | 950000 | -50000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes.
5100 | Construction Of Kahawa ECDE toilets | Construction Of Kahawa ECDE toilets | To construct Kahawa ECDE toilets | Kahawa ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
5101 | Construction Of an Ablution Block at Wanyororo Vocational Training Center | Construction Of an Ablution Block at Wanyororo Vocational Training Center | To construct an Ablution Block at Wanyororo Vocational Training Center | An Ablution Block at Wanyororo Vocational Training Center constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252032, 36.193277 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/2025 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5102 | Construction of an ECD Toilet at Giachonge Primary school | Construction of an ECD Toilet at Giachonge Primary school | To construct an ECD Toilet at Giachonge Primary school | An ECD Toilet at Giachonge Primary school constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252786 36.183911 2006.5999755859375 15 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 500000 | 495760 | 495760 | Equitable | N/A | 495760 | 0 | 1199978 | 242 | 1199978 | 495760 | -704218 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alidawn ltd. Assessor remarks: Good should be operationalized.
5103 | Construction of Ebenezer and Ndibai ECDE toilets | Construction of Ebenezer and Ndibai ECDE toilets | To construct Ebenezer and Ndibai ECDE toilets | Ebenezer and Ndibai ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.541029, 36.070113 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1199700 | 63.1 | 1199700 | 1900000 | 700300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5104 | Proposed construction of 2no of toilet blocks at Racetrack Primary School | Proposed construction of 2no of toilet blocks at Racetrack Primary School | To undertake the proposed construction of 2no of toilet blocks at Racetrack Primary School | Proposed construction of 2no of toilet blocks at Racetrack Primary School implemented | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.310076, 36.06997 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | Fy-20232024 | 2000000 | 1893220 | 1893220 | Equitable | N/A | 1893220 | 0 | 1893220 | 100 | 1893220 | 1893220 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5105 | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools | To implement reconstruction of ecde toilet at langalanga, lakeview & kimathi primary schools for access to quality education and training | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30512 36.078243 1849.6 6 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2385216 | 79.5 | 2385216 | 3000000 | 614784 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo solutions limited. Assessor remarks: Ongoing.
5106 | Construction of toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | Construction of toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | To construct toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | Toilets for teachers and children for Ngomongo ECDE and Murindu ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.490006, 36.32 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 976920 | 976920 | Equitable | N/A | 976920 | 0 | 976920 | 100 | 976920 | 976920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5107 | Construction of ECD sanitation facilities | Construction of ECD sanitation facilities | To construct ECD sanitation facilities | ECD sanitation facilities constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.222936, 35.771564 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2015/2016 | 13000000 | 13000000 | 13000000 | Equitable | N/A | 13000000 | 0 | 19900008 | 153.1 | 19900008 | 13000000 | -6900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Met but lack accompanying tank and water point. Viable: To some extent.
5108 | Construction of Kitchen facilities in ECDEs for School feeding programme | Construction of Kitchen facilities in ECDEs for School feeding programme | To construct Kitchen facilities in ECDEs for School feeding programme | Kitchen facilities in ECDEs for School feeding programme constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 25000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5109 | Installation of CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | Installation of CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | To install CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 795000 | 79.5 | 795000 | 940000 | 205000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5110 | Set Up of Digital Centres | Set Up of Digital Centres | To implement set up of digital centres for access to quality education and training | Set Up of Digital Centres completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1897400 | 94.9 | 1897400 | 2813994 | 102600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5111 | Construction Of a Modern Toilet at Nyamathi ECDE | Construction Of a Modern Toilet at Nyamathi ECDE | To construct a Modern Toilet at Nyamathi ECDE | A Modern Toilet at Nyamathi ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.787454, 36.510844 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 1487282 | 185.9 | 1487282 | 800000 | -687282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5112 | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom | To implement fencing, construction of toilets and renovation of nyakiambi ecde classroom for access to quality education and training | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.13503 36.1535 0 2218 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2700000 | 180 | 2700000 | 1500000 | -1200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works ltd. Assessor remarks: Requires furniture.
5113 | Construction of perimeter fence and a gate at Mogoon ECD | Construction of perimeter fence and a gate at Mogoon ECD | To construct perimeter fence and a gate at Mogoon ECD | Perimeter fence and a gate at Mogoon ECD constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.30348 36.025538 1878.9599609375 3.2160000801086426 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 279231 | 100 | 279231 | 2500000 | -279231 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Handed over to the contractor. But yet to start.
5114 | Fencing Of Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE | Fencing Of Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE | To secure Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE through fencing | Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.310814, 36.053382 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Not yet started | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Not yet done. Contractor: Not awarded.
5115 | Installation of Solar water pump and Panels at Heshima and Kaptembwo ECDE | Installation of Solar water pump and Panels at Heshima and Kaptembwo ECDE | To install Solar water pump and Panels at Heshima and Kaptembwo ECDE | Solar water pump and Panels at Heshima and Kaptembwo ECDE installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29789 36.052599 1812.199951171875 82.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
5116 | Construction Of 2 Toilets at Kio and Mutitu ECDE | Construction Of 2 Toilets at Kio and Mutitu ECDE | To construct 2 Toilets at Kio and Mutitu ECDE | 2 Toilets at Kio and Mutitu ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.441032, 35.983992 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 219716 | 16.9 | 219716 | 600000 | 1080284 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5117 | Construction Of ECDE Toilets at Flamingo, Nakuru, Baharini & Kaloleni Primary Schools | Construction Of ECDE Toilets at Flamingo, Nakuru, Baharini & Kaloleni Primary Schools | To construct ECDE Toilets at Flamingo, Nakuru, Baharini & Kaloleni Primary Schools | ECDE Toilets at Flamingo, Nakuru, Baharini & Kaloleni Primary Schools constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.304611 36.082583 1793.5999755859375 20 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999999 | 100 | 3999999 | 1199994 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Title deed not yet processed.
5118 | Construction Of a Modern Kitchen and A Dining Area at Milimani Center of Excellence | Construction Of a Modern Kitchen and A Dining Area at Milimani Center of Excellence | To construct a Modern Kitchen and A Dining Area at Milimani Center of Excellence | A Modern Kitchen and A Dining Area at Milimani Center of Excellence constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.721779, 36.439279 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5119 | Construction of Septic Tank at Unity and Lakeview Primary | Construction of Septic Tank at Unity and Lakeview Primary | To construct Septic Tank at Unity and Lakeview Primary | Septic Tank at Unity and Lakeview Primary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.758644, 36.46218 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 1282392 | 100 | 1282392 | 700000 | -1282392 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Partially. Viable: It will.
5120 | Constuction of a kitchen and equipping of Marela ECDE | Constuction of a kitchen and equipping of Marela ECDE | To implement constuction of a kitchen and equipping of marela ecde for access to quality education and training | Constuction of a kitchen and equipping of Marela ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.708776, 36.425023 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5121 | Constuction of a kitchen and Lakeview ECDE | Constuction of a kitchen and Lakeview ECDE | To implement constuction of a kitchen and lakeview ecde for access to quality education and training | Constuction of a kitchen and Lakeview ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.734128, 36.435737 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 7157555 | 238.6 | 7157555 | 3000000 | -4157555 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No was not done.
5122 | Fencing of Lare Polytechnic with concrete post, chain link and main gate | Fencing of Lare Polytechnic with concrete post, chain link and main gate | To secure Lare Polytechnic with concrete post, chain link and main gate through fencing | Lare Polytechnic with concrete post, chain link and main gate fenced and secured | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.445005, 36.021978 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 23 | 1000000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5123 | Construction of 6 door plus Urinal at Kongoni ECD | Construction of 6 door plus Urinal at Kongoni ECD | To construct 6 door plus Urinal at Kongoni ECD | 6 door plus Urinal at Kongoni ECD constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 600000 | 584286 | 584286 | Equitable | N/A | 584286 | 0 | 584286 | 100 | 584286 | 584286 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
5124 | Construction Of Maiella Polytechnic Workshop | Construction Of Maiella Polytechnic Workshop | To construct Maiella Polytechnic Workshop | Maiella Polytechnic Workshop constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.893629, 36.199071 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2025 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 497700 | 12.4 | 497700 | 4000000 | 3502300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: NO. Viable: NO.
5125 | Construction Of 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | Construction Of 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | To construct 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.278331 36.108055 1885.7724609375 56.26599884033203 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 3499981 | 125 | 3499981 | 2800000 | -699981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: 2023/24. Assessor remarks: Functional.
5126 | Construction of ECDE Toilets in Menengai Pry Sch Mangu | Construction of ECDE Toilets in Menengai Pry Sch Mangu | To construct ECDE Toilets in Menengai Pry Sch Mangu | ECDE Toilets in Menengai Pry Sch Mangu constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.169922 36.025178 1957.8 13 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 944510 | 944510 | Equitable | N/A | 944510 | 0 | 944510 | 100 | 944510 | 944510 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but almost full.
5127 | Construction of 4 door Toilets at Nguzu River ECDE | Construction of 4 door Toilets at Nguzu River ECDE | To construct 4 door Toilets at Nguzu River ECDE | 4 door Toilets at Nguzu River ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 520000 | 499970 | 499970 | Equitable | N/A | 499970 | 0 | 729740 | 146 | 729740 | 499970 | -229770 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
5128 | Construction of Ngecha ECDE Toilet | Construction of Ngecha ECDE Toilet | To construct Ngecha ECDE Toilet | Ngecha ECDE Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | Not indicated | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 694 | 0.1 | 694 | 500000 | 499306 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
5129 | Fencing at Ngondu ECDE Compound | Fencing at Ngondu ECDE Compound | To secure at Ngondu ECDE Compound through fencing | At Ngondu ECDE Compound fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279523 35.883943 2125.1 17.100000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not awarded. Viable: Viable. Contractor: Not awarded. Assessor remarks: Not yet awarded.
5130 | Completion Of Gachuga and Kayole ECDE toilets | Completion Of Gachuga and Kayole ECDE toilets | To complete Gachuga and Kayole ECDE toilets | Gachuga and Kayole ECDE toilets completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.836761, 36.515774 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Not yet | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
5131 | Fencing And Construction Of Toilets of Karioko ECDE | Fencing And Construction Of Toilets of Karioko ECDE | To secure And Construction Of Toilets of Karioko ECDE through fencing | And Construction Of Toilets of Karioko ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.860852 36.548747 2604.6 4 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999352 | 99.9 | 999352 | 1000000 | 648 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Motorbikes sheds were vandalized they don't exist.
5132 | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | To construct Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.38946, 35.568755 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
5133 | Construction And Equipping of ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | Construction And Equipping of ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | To construct and equip ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.826569, 36.298447 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 2633481 | 73.2 | 2633481 | 3600000 | 966519 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5134 | Construction Of 4 Door Toilet at Koisamo and Equipping of The Class | Construction Of 4 Door Toilet at Koisamo and Equipping of The Class | To construct 4 Door Toilet at Koisamo and Equipping of The Class | 4 Door Toilet at Koisamo and Equipping of The Class constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.096327 35.935707 1687 7.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 1020860 | 127.6 | 1020860 | 800000 | -220860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Construction to start soon.
5135 | Construction Of 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | Construction Of 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | To construct 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.096327 35.935707 1687 7.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 348930 | 23.3 | 348930 | 1500000 | 1151070 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Construction to start soon.
5136 | Construction Of 8 Door Toilet and Equipping of Majani Mingi Polytechnic | Construction Of 8 Door Toilet and Equipping of Majani Mingi Polytechnic | To construct 8 Door Toilet and Equipping of Majani Mingi Polytechnic | 8 Door Toilet and Equipping of Majani Mingi Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.041732, 36.024525 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | FY 2023 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1020860 | 56.7 | 1020860 | 779140 | 779140 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: FY 2024.
5137 | Construction of 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | Construction of 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | To construct 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.06765 36.022245 1607 8.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1492890 | 1492890 | Equitable | N/A | 1492890 | 0 | 1492890 | 100 | 1492890 | 1492890 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No,until enrolment is done. Viable: It is viable but without children. Assessor remarks: Project complete but no enrolment.
5138 | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | To construct a Toilet block and purchase of a water tank at Our Lady of Victory Primary | A Toilet block and purchase of a water tank at Our Lady of Victory Primary constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.00426 36.23702 1995.800048828125 39.599998474121094 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. The toilet serves the ecde learners. Contractor: No information. Assessor remarks: The toilet looks good..
5139 | Construction of Morro ECD toilet and fencing | Construction of Morro ECD toilet and fencing | To construct Morro ECD toilet and fencing | Morro ECD toilet and fencing constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.010383, 36.223597 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 999980 | 66.7 | 999980 | 1500000 | 500020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5140 | Construction Of Karao ECDE 6 Door Toilets and Urinal | Construction Of Karao ECDE 6 Door Toilets and Urinal | To construct Karao ECDE 6 Door Toilets and Urinal | Karao ECDE 6 Door Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.513813 35.683561 2568.666 3.1989998817443848 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199930 | 100 | 1199930 | 1200000 | 70 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
5141 | Construction Of Toilets and Fencing at Waka ECDE | Construction Of Toilets and Fencing at Waka ECDE | To construct Toilets and Fencing at Waka ECDE | Toilets and Fencing at Waka ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.103344, 35.801517 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2033/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 970000 | 97 | 970000 | 30000 | 30000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Kapstephen contractors limited.
5142 | Construction And Equipping Of ICT Hub Facility/Hub Estate | Construction And Equipping Of ICT Hub Facility/Hub Estate | To construct and equip ICT Hub Facility/Hub Estate | ICT Hub Facility/Hub Estate constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714882 36.432885 0 200 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1499845 | 30 | 1499845 | 5000000 | 3500155 | Stalled | 90 | 30 | Stalled — reasons to be confirmed by department | 2019 | N/A | 3500155 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Effective.
5143 | Construction Of 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | Construction Of 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | To construct 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.054707, 36.214165 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5144 | Construction ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | Construction ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | To construct ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1190650 | 56.7 | 1190650 | 2100000 | 909350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5145 | Construction Of ECD Toilet at Freehold Primary | Construction Of ECD Toilet at Freehold Primary | To construct ECD Toilet at Freehold Primary | ECD Toilet at Freehold Primary constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 1190650 | 170.1 | 1190650 | 700000 | -490650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5146 | Construction Of 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | Construction Of 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | To construct 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1963990 | 115.5 | 1963990 | 1700000 | -263990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5147 | Construction Of 4 Door Toilets at Mbegi ECD and Teachers ECD | Construction Of 4 Door Toilets at Mbegi ECD and Teachers ECD | To construct 4 Door Toilets at Mbegi ECD and Teachers ECD | 4 Door Toilets at Mbegi ECD and Teachers ECD constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.534284, 36.342096 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No yet started.
5148 | Fencing Of Teachers ECD and Construction of gate | Fencing Of Teachers ECD and Construction of gate | To secure Teachers ECD and Construction of gate through fencing | Teachers ECD and Construction of gate fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.489141, 36.328335 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2022/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5149 | Fencing Of View Point ECD | Fencing Of View Point ECD | To secure View Point ECD through fencing | View Point ECD fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504762 36.328241 1989.4000244140625 17.466999053955078 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5150 | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center | To implement establishment & equipping of digital ict hub center at wendo vocational center for access to quality education and training | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center completed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
5151 | Fencing, Installation of Gate and Supply Of 10,000 Liter Tank at Limuko ECD Center | Fencing, Installation of Gate and Supply Of 10,000 Liter Tank at Limuko ECD Center | To implement fencing, installation of gate and supply of 10,000 liter tank at limuko ecd center for access to quality education and training | Fencing, Installation of Gate and Supply Of 10,000 Liter Tank at Limuko ECD Center completed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.214433 36.162776 2030.4000244140625 10.21500015258789 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 942112 | 94.2 | 942112 | 57888 | 57888 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Willis samwa suppliers limited. Assessor remarks: Operational.
5152 | Electricity Installation at Lalwet ECDE | Electricity Installation at Lalwet ECDE | To implement electricity installation at lalwet ecde for access to quality education and training | Electricity Installation at Lalwet ECDE completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.27027, 36.036437 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable and serving purpose.
5153 | Construction Of the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | Construction Of the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | To construct the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | The Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.31767, 36.052973 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5154 | Construction Of 6 Door Modern Toilet at Kamoronyo ECDE | Construction Of 6 Door Modern Toilet at Kamoronyo ECDE | To construct 6 Door Modern Toilet at Kamoronyo ECDE | 6 Door Modern Toilet at Kamoronyo ECDE constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.255707, 36.160263 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1998040 | 142.7 | 1998040 | 1400000 | -598040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, partially. Viable: Yes,very viable.
5155 | Construction Of 6 Door Modern Toilet at Mireroni ECDE | Construction Of 6 Door Modern Toilet at Mireroni ECDE | To construct 6 Door Modern Toilet at Mireroni ECDE | 6 Door Modern Toilet at Mireroni ECDE constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.255707, 36.160263 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1998040 | 142.7 | 1998040 | 1400000 | -598040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, partially. Viable: Yes,very viable.
5156 | Equipping & Fencing Mwariki ECD | Equipping & Fencing Mwariki ECD | To equip & Fencing Mwariki ECD with necessary facilities and equipment | & Fencing Mwariki ECD equipped | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.316277, 36.065867 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 23/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Davgra limited.
5157 | Edgewood ECDE Fencing, Equipping and Construction of Toilets | Edgewood ECDE Fencing, Equipping and Construction of Toilets | To implement edgewood ecde fencing, equipping and construction of toilets for access to quality education and training | Edgewood ECDE Fencing, Equipping and Construction of Toilets completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.003635, 36.206705 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1198900 | 59.9 | 1198900 | 2000000 | 801100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5158 | Fencing Of Githaiga ECDE | Fencing Of Githaiga ECDE | To secure Githaiga ECDE through fencing | Githaiga ECDE fenced and secured | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.012055, 36.21717 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 02/05/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: The facility is protected. Contractor: No information available.
5159 | Fencing Of Kabati ECD | Fencing Of Kabati ECD | To secure Kabati ECD through fencing | Kabati ECD fenced and secured | 3110599 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.719348, 36.442693 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 2948620 | 77.6 | 2948620 | 3800000 | 851380 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not met. Viable: Not viable.
5160 | Hardware and Software Platforms for Digital Centres | Hardware and Software Platforms for Digital Centres | To implement hardware and software platforms for digital centres for access to quality education and training | Hardware and Software Platforms for Digital Centres completed | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1528500 | 305.7 | 1528500 | 492500 | -1028500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5161 | Purchase Of Equipment at Barut Vocational & Youth Centre | Purchase Of Equipment at Barut Vocational & Youth Centre | To procure Equipment at Barut Vocational & Youth Centre | Equipment at Barut Vocational & Youth Centre procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Barut | -0.342342, 36.036679 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5162 | Equipping of Nakuru VTC Departments | Equipping of Nakuru VTC Departments | To equip Nakuru VTC Departments with necessary facilities and equipment | Nakuru VTC Departments equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2444091 | 2444091 | Equitable | N/A | 2444091 | 0 | 0 | 0 | 0 | 2444091 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5163 | Equipping Of Kongasis Polytechnic | Equipping Of Kongasis Polytechnic | To equip Kongasis Polytechnic with necessary facilities and equipment | Kongasis Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru/Mbaruk | -0.554731, 36.153036 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Unspecified | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 985800 | 49.3 | 985800 | 2000000 | 1014200 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
5164 | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE | To implement playing equipment for ecde at kimathi & pangani primary school ecde for access to quality education and training | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE completed | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Flamingo | -0.305394 36.078686 1776.5 11.199999809265137 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 665899 | 665899 | 665899 | Equitable | N/A | 665899 | 0 | 0 | 0 | 0 | 665899 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: No play equipment.
5165 | Kambi Somali-Additional Funds for Equipping, Playground and Fencing | Kambi Somali-Additional Funds for Equipping, Playground and Fencing | To implement kambi somali-additional funds for equipping, playground and fencing for access to quality education and training | Kambi Somali-Additional Funds for Equipping, Playground and Fencing completed | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Gilgil | -0.509502, 36.315312 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5166 | Equipping Center of Excellence - Beggi | Equipping Center of Excellence - Beggi | To equip Center of Excellence - Beggi with necessary facilities and equipment | Center of Excellence - Beggi equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1561000 | 34.7 | 1561000 | 4043398 | 2939000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5167 | Equipping Njoro Vocational training Center of Excellence | Equipping Njoro Vocational training Center of Excellence | To equip Njoro Vocational training Center of Excellence with necessary facilities and equipment | Njoro Vocational training Center of Excellence equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 5084163 | 4820000 | 4820000 | Equitable | N/A | 4820000 | 0 | 3535000 | 73.3 | 3535000 | 11157648 | 1285000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5168 | Equipping Of ECD Centers | Equipping Of ECD Centers | To equip ECD Centers with necessary facilities and equipment | ECD Centers equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | N/A | 17611176 | 9952600 | 9952600 | Equitable | N/A | 9952600 | 0 | 9787000 | 98.3 | 9787000 | 165600 | 165600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5169 | Equipping of ECD Centre | Equipping of ECD Centre | To equip ECD Centre with necessary facilities and equipment | ECD Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 9787000 | 195.7 | 9787000 | 165600 | -4787000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5170 | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | To equip Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit with necessary facilities and equipment | Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 11548737 | 9740508 | 9740508 | Equitable | N/A | 9740508 | 0 | 4123683 | 42.3 | 4123683 | 8800000 | 5616825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5171 | Equipping Of Rare ECD | Equipping Of Rare ECD | To equip Rare ECD with necessary facilities and equipment | Rare ECD equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1177460 | 392.5 | 1177460 | 300000 | -877460 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5172 | Equipping of Gathondia and Kipkonyo Polytechnics | Equipping of Gathondia and Kipkonyo Polytechnics | To equip Gathondia and Kipkonyo Polytechnics with necessary facilities and equipment | Gathondia and Kipkonyo Polytechnics equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Maiella | -0.040139, 36.11999 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2016 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2799119 | 93.3 | 2799119 | 200881 | 200881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5173 | Equipping Of Kamungei ECDE | Equipping Of Kamungei ECDE | To equip Kamungei ECDE with necessary facilities and equipment | Kamungei ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.225332 35.972693 1934.5 10.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 999200 | 333.1 | 999200 | 300000 | -699200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more chairs and desks.
5174 | Equipping Of Motor Vehicle Mechanics Workshop at Mangu VTC | Equipping Of Motor Vehicle Mechanics Workshop at Mangu VTC | To equip Motor Vehicle Mechanics Workshop at Mangu VTC with necessary facilities and equipment | Motor Vehicle Mechanics Workshop at Mangu VTC equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.225332 35.972693 1934.5 10.600000381469727 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1100000 | 91.7 | 1100000 | 100000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more chairs and desks.
5175 | Purchase Of Workshop Tools at Ogilgei VTC | Purchase Of Workshop Tools at Ogilgei VTC | To procure Workshop Tools at Ogilgei VTC | Workshop Tools at Ogilgei VTC procured | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.28437, 35.966212 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 492840 | 98.6 | 492840 | 7160 | 7160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/s Frovi.
5176 | Renovation of ECDE At Atebwo Primary | Renovation of ECDE At Atebwo Primary | To rehabilitate ECDE At Atebwo Primary to restore functionality | ECDE At Atebwo Primary rehabilitated | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.266003 35.881008 2093.4 16.5 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 497999 | 83 | 497999 | 600000 | 102001 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
5177 | Equipping Of Free Area Polytechnic | Equipping Of Free Area Polytechnic | To equip Free Area Polytechnic with necessary facilities and equipment | Free Area Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.372834, 36.149533 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/2025 | 721450 | 721450 | 721450 | Equitable | N/A | 721450 | 0 | 650940 | 90.2 | 650940 | 70510 | 70510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5178 | Equipping of Free Area Vocational Training Center (Polytechnic) | Equipping of Free Area Vocational Training Center (Polytechnic) | To equip Free Area Vocational Training Center (Polytechnic) with necessary facilities and equipment | Free Area Vocational Training Center (Polytechnic) equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.293862, 36.118139 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 5000000 | 4806300 | 4806300 | Equitable | N/A | 4806300 | 0 | 650940 | 13.5 | 650940 | 4806300 | 4155360 | Stalled | 0 | 13.5 | Stalled — reasons to be confirmed by department | 2022 | N/A | 4155360 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5179 | Equipping Of Mworoto Vocational Training Centre | Equipping Of Mworoto Vocational Training Centre | To equip Mworoto Vocational Training Centre with necessary facilities and equipment | Mworoto Vocational Training Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Nyota | -0.38879 35.653582 2664.2 18.399999618530273 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, will be impactful once complete. Assessor remarks: Stalled, Vandalized- Needs urgent attention..
5180 | Equipping Of Rangondu ECDE | Equipping Of Rangondu ECDE | To equip Rangondu ECDE with necessary facilities and equipment | Rangondu ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Nyota | -0.394602, 35.632172 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024-2025 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5181 | Equipping Of ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws | Equipping Of ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws | To equip ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws with necessary facilities and equipment | ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.833651, 36.341813 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1746200 | 87.3 | 1746200 | 253800 | 253800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5182 | Equipping of Koimugul and Ruiyobei ECDE | Equipping of Koimugul and Ruiyobei ECDE | To equip Koimugul and Ruiyobei ECDE with necessary facilities and equipment | Koimugul and Ruiyobei ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Solai | 0.099285, 36.142945 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2024 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 278420 | 92.8 | 278420 | 21580 | 21580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5183 | Equipping Of Gakingi Polytechnic | Equipping Of Gakingi Polytechnic | To equip Gakingi Polytechnic with necessary facilities and equipment | Gakingi Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Subukia | Waseges | 0.116708, 36.224264 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910200 | 91 | 910200 | 89800 | 89800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes.
5184 | Acquisition of Equipment for Public Communication Unit | Acquisition of Equipment for Public Communication Unit | To procure Equipment for Public Communication Unit | Equipment for Public Communication Unit procured | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.113577, 35.796542 | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2022/2023 | 3500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not meet the need. Contractor: Rynix construction limited.
5185 | Acquisition of e-Mail Solution for the County | Acquisition of e-Mail Solution for the County | To procure e-Mail Solution for the County | E-Mail Solution for the County procured | 3111112 | Purchase of Software | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 995000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5186 | Upgrading of County website for incorporation of Departmental, Boards and Municipalities mini-websites | Upgrading of County website for incorporation of Departmental, Boards and Municipalities mini-websites | To upgrade County website for incorporation of Departmental, Boards and Municipalities mini-websites through tarmacking for improved road connectivity | County website for incorporation of Departmental, Boards and Municipalities mini-websites tarmacked and upgraded | 3111112 | Purchase of Software | HQ | HQ | N/A | 4586 | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, E-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5187 | Conditional Allocation for Rehabilitation of Youth Polytechnics | Conditional Allocation for Rehabilitation of Youth Polytechnics | To implement conditional allocation for rehabilitation of youth polytechnics for access to quality education and training | Conditional Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 66289894 | 66289894 | 66289894 | Equitable | N/A | 66289894 | 0 | 10193360 | 15.4 | 10193360 | 66289894 | 56096534 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5188 | Construction of VTCs Hostels | Construction of VTCs Hostels | To construct VTCs Hostels | VTCs Hostels constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 6107075 | Equitable | N/A | 6107075 | 0 | 19900008 | 100 | 19900008 | 3566331 | -19900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5189 | Construction of Hostel at Saptet Polytechnic | Construction of Hostel at Saptet Polytechnic | To construct Hostel at Saptet Polytechnic | Hostel at Saptet Polytechnic constructed | 3110201 | Residential Buildings (including hostels) | Kuresoi South | Keringet | -0.485136, 35.699573 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2482045 | 82.7 | 2482045 | 2482045 | 517955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet started.
5190 | Construction Of Hostels at Ruiyobei Vocational Training Centre | Construction Of Hostels at Ruiyobei Vocational Training Centre | To construct Hostels at Ruiyobei Vocational Training Centre | Hostels at Ruiyobei Vocational Training Centre constructed | 3110201 | Residential Buildings (including hostels) | Rongai | Solai | 0.099258 36.173883 1556.7939453125 3.808000087738037 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2187090 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2023 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation, ceiling infested with bats.
5191 | Completion Of 1 Classroom at Ndasiata and Equipping | Completion Of 1 Classroom at Ndasiata and Equipping | To complete 1 Classroom at Ndasiata and Equipping | 1 Classroom at Ndasiata and Equipping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570773 35.664502 2506.1 5.699999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 416194 | 100 | 416194 | 1200000 | -416194 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project done NG cdf.
5192 | Construction 1 ECDE classroom at Kwendo | Construction 1 ECDE classroom at Kwendo | To construct 1 ECDE classroom at Kwendo | 1 ECDE classroom at Kwendo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2018 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 416194 | 100 | 416194 | 1500000 | -416194 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5193 | Construction and Equiping of Lelkoita ECDE class | Construction and Equiping of Lelkoita ECDE class | To construct and Equiping of Lelkoita ECDE class | And Equiping of Lelkoita ECDE class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676073 35.657515 2464.4 19.899999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1549850 | 70.4 | 1549850 | 1429210 | 650150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes but requires additional classroom. Viable: yes. Assessor remarks: completed.
5194 | Construction Of ECDE Classroom At Kabigeriet | Construction Of ECDE Classroom At Kabigeriet | To construct ECDE Classroom At Kabigeriet | ECDE Classroom At Kabigeriet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2018 | 1349217 | 1349217 | 1349217 | Equitable | N/A | 1349217 | 0 | 416194 | 30.8 | 416194 | 1349217 | 933023 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5195 | Construction Of One ECDE Classroom At Gorofa | Construction Of One ECDE Classroom At Gorofa | To construct One ECDE Classroom At Gorofa | One ECDE Classroom At Gorofa constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2024 | 1349217 | 0 | 1349217 | Equitable | N/A | 1349217 | 0 | 1199956 | 100 | 1199956 | 1349217 | -1199956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5196 | Construction of Sigowet ECDE classroom | Construction of Sigowet ECDE classroom | To construct Sigowet ECDE classroom | Sigowet ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2024 | 1500000 | 0 | 1429210 | Equitable | N/A | 1429210 | 0 | 1199956 | 100 | 1199956 | 1429210 | -1199956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5197 | Construction Of An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | Construction Of An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | To construct An ECDE Class Water Tank And Sanitation Facility At Jacaranda School | An ECDE Class Water Tank And Sanitation Facility At Jacaranda School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
5198 | Construction Of Wanyororo Vocational Training Center | Construction Of Wanyororo Vocational Training Center | To construct Wanyororo Vocational Training Center | Wanyororo Vocational Training Center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
5199 | Construction & Equipping of One (1) ECD Classroom at Kelelwet Primary | Construction & Equipping of One (1) ECD Classroom at Kelelwet Primary | To construct & Equipping of One (1) ECD Classroom at Kelelwet Primary | & Equipping of One (1) ECD Classroom at Kelelwet Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5200 | Construction & Equipping of One (1) ECD Classroom at Kigonor Primary | Construction & Equipping of One (1) ECD Classroom at Kigonor Primary | To construct & Equipping of One (1) ECD Classroom at Kigonor Primary | & Equipping of One (1) ECD Classroom at Kigonor Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5201 | Construction & Equipping of One (1) ECD Classroom at Parkview Primary | Construction & Equipping of One (1) ECD Classroom at Parkview Primary | To construct & Equipping of One (1) ECD Classroom at Parkview Primary | & Equipping of One (1) ECD Classroom at Parkview Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.346875, 36.034838 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5202 | Construction Of ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | Construction Of ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | To construct ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary | ECD Classroom, Equipping and Water Tank at Kisulisuli and Kenyatta Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.286701, 36.069091 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/25 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1199771 | 100 | 1199771 | 3000000 | -1199771 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5203 | Construction Of one ECD Classroom and toilets at Jamhuri Primary | Construction Of one ECD Classroom and toilets at Jamhuri Primary | To construct one ECD Classroom and toilets at Jamhuri Primary | One ECD Classroom and toilets at Jamhuri Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1199771 | 100 | 1199771 | 2000000 | -1199771 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5204 | Construction of two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | Construction of two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | To construct two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing | Two (2) Lecture Rooms at Wanyororo Vocational Training Center and fencing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.252302, 36.193292 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 4600000 | 0 | 4600000 | Equitable | N/A | 4600000 | 0 | 1200000 | 100 | 1200000 | 4600000 | -1200000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company.
5205 | Construction of Emkwen ECDE | Construction of Emkwen ECDE | To construct Emkwen ECDE | Emkwen ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.5542163, 36.150297 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 24-25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 490250 | 27.2 | 490250 | 500000 | 1309750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Ranmat ltbox 10101 Nakuru.
5206 | Construction of Olepolos ECDE (tangi tano) | Construction of Olepolos ECDE (tangi tano) | To construct Olepolos ECDE (tangi tano) | Olepolos ECDE (tangi tano) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.595977, 36.211092 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | Unspecified | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 490250 | 27.2 | 490250 | 500000 | 1309750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, have over 100 pupils. Contractor: Unspecified.
5207 | Construction of Oljorai ECDE | Construction of Oljorai ECDE | To construct Oljorai ECDE | Oljorai ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.702703, 36.471211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 490250 | 27.2 | 490250 | 500000 | 1309750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5208 | Construction and equiping of one ECDE classroom at Kapsita, Saptet and Arimi | Construction and equiping of one ECDE classroom at Kapsita, Saptet and Arimi | To construct and equiping of one ECDE classroom at Kapsita, Saptet and Arimi | And equiping of one ECDE classroom at Kapsita, Saptet and Arimi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.292714, 35.791345 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | - | 5400000 | 5400000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1478089 | 27.4 | 1478089 | 1478090 | 3921911 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: DAKUKi.
5209 | Construction of D.E.B ECDE classroom | Construction of D.E.B ECDE classroom | To construct D.E.B ECDE classroom | D.E.B ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.309157 35.80994 2403.900146484375 10.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 1194994 | 100 | 1194994 | 1200000 | -1194994 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Funtional.
5210 | Construction Of One ECD Classroom, Equipping and Water Tank at Simowet | Construction Of One ECD Classroom, Equipping and Water Tank at Simowet | To construct One ECD Classroom, Equipping and Water Tank at Simowet | One ECD Classroom, Equipping and Water Tank at Simowet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.288188 35.816137 2443.8 11.800000190734863 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1194994 | 100 | 1194994 | 1500000 | -1194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5211 | Design And Construction Of Mucharage ECDE | Design And Construction Of Mucharage ECDE | To design and construct Mucharage ECDE | Mucharage ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.307435 35.749389 0 2599.9990234375 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 100 | 1194994 | 1000000 | -1194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repairs and maintainance.
5212 | Design And Construction Of Nyakiambi Karunga ECDE | Design And Construction Of Nyakiambi Karunga ECDE | To design and construct Nyakiambi Karunga ECDE | Nyakiambi Karunga ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.180252 35.704339 0 3299.9990234375 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
5213 | Design And Construction Of Tegat ECDE | Design And Construction Of Tegat ECDE | To design and construct Tegat ECDE | Tegat ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.27156 35.816038 2145.7 13.600000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair and maintainance.
5214 | Construction And Equipping of ECDE Classroom at Kanorero and Mwariki ECD | Construction And Equipping of ECDE Classroom at Kanorero and Mwariki ECD | To construct and equip ECDE Classroom at Kanorero and Mwariki ECD | ECDE Classroom at Kanorero and Mwariki ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.621053, 36.099955 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1166090 | 100 | 1166090 | 3000000 | -1166090 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5215 | Construction of Manyeki ECDE classroom & Equiping | Construction of Manyeki ECDE classroom & Equiping | To construct Manyeki ECDE classroom & Equiping | Manyeki ECDE classroom & Equiping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.506773 36.079472 1870.807 0.781000018119812 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 80430 | 4.5 | 80430 | 1109905 | 1719570 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5216 | Construction of Ngecha ECDE classroom & Equiping | Construction of Ngecha ECDE classroom & Equiping | To construct Ngecha ECDE classroom & Equiping | Ngecha ECDE classroom & Equiping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.506773 36.079472 1870.807 0.781000018119812 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 80430 | 4.5 | 80430 | 1109905 | 1719570 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5217 | Design And Construction Of Mbombo ECDE And Toilets | Design And Construction Of Mbombo ECDE And Toilets | To design and construct Mbombo ECDE And Toilets | Mbombo ECDE And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.555641 36.103909 1951.146 0.6809999942779541 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | N/A | 1664971 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1199700 | 120 | 1199700 | 1000000 | -199700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Stalled.
5218 | Construction and equipping of ECDE classroom at Pangani Special School | Construction and equipping of ECDE classroom at Pangani Special School | To construct and equip ECDE classroom at Pangani Special School | ECDE classroom at Pangani Special School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.30523, 36.072522 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | Fy2024/2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 2385216 | 132.5 | 2385216 | 3000000 | -585216 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: No. Contractor: Not indicated.
5219 | Construction of Gilgil DEB ECDE of one (1no.) classroom | Construction of Gilgil DEB ECDE of one (1no.) classroom | To construct Gilgil DEB ECDE of one (1no.) classroom | Gilgil DEB ECDE of one (1no.) classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.498418, 36.319952 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 3509 | 0.2 | 3509 | 3509 | 1796491 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5220 | Construction of Kariandusi ECDE one classroom including 3000L water tank and furnitures | Construction of Kariandusi ECDE one classroom including 3000L water tank and furnitures | To construct Kariandusi ECDE one classroom including 3000L water tank and furnitures | Kariandusi ECDE one classroom including 3000L water tank and furnitures constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.5074 36.327349 1991 3.7899999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 3509 | 0.2 | 3509 | 3509 | 1796491 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Glasammurs construction limited. Assessor remarks: Needs additional classroom as the kids are using semi permanent classes due to increased population.
5221 | Construction of one (1no.) Kenyatta barrack ECDE classroom | Construction of one (1no.) Kenyatta barrack ECDE classroom | To construct one (1no.) Kenyatta barrack ECDE classroom | One (1no.) Kenyatta barrack ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.495494, 36.338374 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1700000 | Equitable | N/A | 1700000 | 0 | 3509 | 0.2 | 3509 | 3509 | 1796491 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5222 | Construction of Utumishi ECDE one (1no.) classroom | Construction of Utumishi ECDE one (1no.) classroom | To construct Utumishi ECDE one (1no.) classroom | Utumishi ECDE one (1no.) classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.498418, 36.319952 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 3509 | 0.2 | 3509 | 3509 | 1796491 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5223 | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | To construct and equip Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Maombi ECDE, toilet and completion and equipping of Ruiru ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 0 | 509920 | Equitable | N/A | 509920 | 0 | 269520 | 100 | 269520 | 509920 | -269520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5224 | Construction of Center of Excellence Modern workshop Njoro | Construction of Center of Excellence Modern workshop Njoro | To construct Center of Excellence Modern workshop Njoro | Center of Excellence Modern workshop Njoro constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 2944110 | Equitable | N/A | 2944110 | 0 | 19900008 | 100 | 19900008 | 3566331 | -19900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5225 | Moi primary ECDE Center (Classes, Toilets, Equipping) | Moi primary ECDE Center (Classes, Toilets, Equipping) | To implement moi primary ecde center (classes, toilets, equipping) for access to quality education and training | Moi primary ECDE Center (Classes, Toilets, Equipping) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 5000000 | 5000000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5226 | Construction and Equiping of one ECD classroom at Nyamathi Primary School | Construction and Equiping of one ECD classroom at Nyamathi Primary School | To construct and Equiping of one ECD classroom at Nyamathi Primary School | And Equiping of one ECD classroom at Nyamathi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.612613, 36.398477 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | Yet to start | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1199658 | 66.6 | 1199658 | 1199658 | 600342 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5227 | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | To construct 1 ECD classroom, toilet and water tank at Kamuyu | 1 ECD classroom, toilet and water tank at Kamuyu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 1911040 | 1911040 | Equitable | N/A | 1911040 | 0 | 1487282 | 77.8 | 1487282 | 1911040 | 423758 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
5228 | Construction of 1 ECD classroom, toilet and water tank at Mountain View | Construction of 1 ECD classroom, toilet and water tank at Mountain View | To construct 1 ECD classroom, toilet and water tank at Mountain View | 1 ECD classroom, toilet and water tank at Mountain View constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 0 | 1911040 | Equitable | N/A | 1911040 | 0 | 1487282 | 100 | 1487282 | 1911040 | -1487282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
5229 | Construction Of One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | Construction Of One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | To construct One Classroom at Mirera Primary School and Construction Of 4 Door Toilet | One Classroom at Mirera Primary School and Construction Of 4 Door Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.782556 36.44577 1954.9000244140625 4.5320000648498535 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199658 | 100 | 1199658 | 2500000 | -1199658 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Cost of the project 2,500,000.
5230 | Construction Of One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | Construction Of One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | To construct One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet | One Classroom at Rubiri Primary School, Equipping and Construction of A 4 Door Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.805277 36.443929 1926.5 70.96199798583984 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199658 | 100 | 1199658 | 2500000 | -1199658 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project is stalled.
5231 | Construction and Equiping of 1 new classroom with water tank at Githima natukanio ECDE | Construction and Equiping of 1 new classroom with water tank at Githima natukanio ECDE | To construct and Equiping of 1 new classroom with water tank at Githima natukanio ECDE | And Equiping of 1 new classroom with water tank at Githima natukanio ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.149855 36.09075 2168.4 7.400000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 37 | 0 | 37 | 37 | 1799963 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kilofox enterprises. Assessor remarks: Popping to be done.
5232 | Construction and Equiping of one new classroom with water tank at solai nyakiyua ECDE | Construction and Equiping of one new classroom with water tank at solai nyakiyua ECDE | To construct and Equiping of one new classroom with water tank at solai nyakiyua ECDE | And Equiping of one new classroom with water tank at solai nyakiyua ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.149855 36.09075 2168.4 7.400000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 37 | 0 | 37 | 37 | 1799963 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kilofox enterprises. Assessor remarks: Popping to be done.
5233 | Construction of a classroom at Ndungiri Vocational Training Centre | Construction of a classroom at Ndungiri Vocational Training Centre | To construct a classroom at Ndungiri Vocational Training Centre | A classroom at Ndungiri Vocational Training Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.108053, 36.054603 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2020/2021 | 1200000 | 1200000 | 574400 | Equitable | N/A | 574400 | 0 | 625600 | 52.1 | 625600 | 574400 | 574400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
5234 | Construction of Marigu ECDE classroom and 2 door toilet | Construction of Marigu ECDE classroom and 2 door toilet | To construct Marigu ECDE classroom and 2 door toilet | Marigu ECDE classroom and 2 door toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.160675, 36.038967 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2019/20 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 40 | 100 | 40 | 40 | -40 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
5235 | Completion of Highlands ECDE | Completion of Highlands ECDE | To complete Highlands ECDE | Highlands ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.42644 35.68664 2692.000244140625 13.300000190734863 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good but not in use.
5236 | Completion Of Ribot ECDE Classroom | Completion Of Ribot ECDE Classroom | To complete Ribot ECDE Classroom | Ribot ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.410372 35.681463 2653 21.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 667928 | 100 | 667928 | 600000 | -667928 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
5237 | Completion of tendwet ECDE | Completion of tendwet ECDE | To complete tendwet ECDE | Tendwet ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.50589, 35.698535 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 312620 | 44.7 | 312620 | 600000 | 387380 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes.
5238 | Construction And Equipping of ECDE Classroom at Chesaror | Construction And Equipping of ECDE Classroom at Chesaror | To construct and equip ECDE Classroom at Chesaror | ECDE Classroom at Chesaror constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.527932 35.73419 2592.6 50.099998474121094 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1250000 | 0 | 1250000 | Equitable | N/A | 1250000 | 0 | 312620 | 100 | 312620 | 1250000 | -312620 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5239 | Construction And Equipping of ECDE Classroom at Kirandich | Construction And Equipping of ECDE Classroom at Kirandich | To construct and equip ECDE Classroom at Kirandich | ECDE Classroom at Kirandich constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.47619, 35.66288 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1250000 | 0 | 1250000 | Equitable | N/A | 1250000 | 0 | 312620 | 100 | 312620 | 1250000 | -312620 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5240 | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | To construct 1 ECDE class, teacher & pupils toilet & water tank at Ribot | 1 ECDE class, teacher & pupils toilet & water tank at Ribot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.53935 35.711058 2660.000244140625 24.600000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 721470 | Equitable | N/A | 721470 | 0 | 747140 | 100 | 747140 | 721470 | -747140 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Class olmost complete but toilet and water tank not yet constructed.
5241 | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | To construct 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | 2 ECDE classroom at Upendo and renovation of teta youth polytechnique constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2200000 | 0 | 2200000 | Equitable | N/A | 2200000 | 0 | 1852800 | 100 | 1852800 | 2200000 | -1852800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5242 | Construction of ECDE classroom at Bararget | Construction of ECDE classroom at Bararget | To construct ECDE classroom at Bararget | ECDE classroom at Bararget constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.411007, 35.734867 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 1750000 | 1750000 | 1700000 | Equitable | N/A | 1700000 | 0 | 667928 | 38.2 | 667928 | 1250000 | 1082072 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5243 | Construction of ECDE classroom at Chebara | Construction of ECDE classroom at Chebara | To construct ECDE classroom at Chebara | ECDE classroom at Chebara constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.411007, 35.734867 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 1750000 | 1750000 | 1700000 | Equitable | N/A | 1700000 | 0 | 667928 | 38.2 | 667928 | 1250000 | 1082072 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5244 | Construction of ECDE classroom at Kiptulwo | Construction of ECDE classroom at Kiptulwo | To construct ECDE classroom at Kiptulwo | ECDE classroom at Kiptulwo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.411007, 35.734867 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 1750000 | 1750000 | 1700000 | Equitable | N/A | 1700000 | 0 | 667928 | 38.2 | 667928 | 1693833 | 1082072 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5245 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 0 | 1190000 | Equitable | N/A | 1190000 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5246 | Construction Of Tendwet ECD Classroom | Construction Of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.50589, 35.698535 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 851232.8 | 538612.8 | Equitable | N/A | 538612.8 | 0 | 312620 | 36.7 | 312620 | 538613 | 538612.8 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5247 | Construction And Equipping of Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | Construction And Equipping of Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | To construct and equip Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location | Classroom at Crater ECDE, Terrazzo Floor and Water Tank in Kiamaina sub location constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kiamaina | -0.265277 36.114494 1868.5 19.634000778198242 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
5248 | Construction And Equipping Of 1 ECDE Classroom at Kipkongor | Construction And Equipping Of 1 ECDE Classroom at Kipkongor | To construct and equip 1 ECDE Classroom at Kipkongor | 1 ECDE Classroom at Kipkongor constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.578837 35.549055 2395.4 26.799999237060547 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199995 | 100 | 1199995 | 1300000 | -1199995 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not meet. Assessor remarks: No project.
5249 | Construction And Equipping Of 1 ECDE Classroom at Kiptagich Primary | Construction And Equipping Of 1 ECDE Classroom at Kiptagich Primary | To construct and equip 1 ECDE Classroom at Kiptagich Primary | 1 ECDE Classroom at Kiptagich Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.572763 35.614065 2486.500244140625 8.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199995 | 100 | 1199995 | 1300000 | -1199995 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started hence residents needs were not met.. Contractor: Don't know. Assessor remarks: There are no pit latrines under department of trade at Kiptagich market.
5250 | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | To construct 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 0 | 2468070 | Equitable | N/A | 2468070 | 0 | 1270177 | 100 | 1270177 | 2468070 | -1270177 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
5251 | Construction Of Ekabugunot ECDE | Construction Of Ekabugunot ECDE | To construct Ekabugunot ECDE | Ekabugunot ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2014/15 | 2014/15 | 2014/15 | 999363 | 0 | 999363 | Equitable | N/A | 999363 | 0 | 1199995 | 100 | 1199995 | 999363 | -1199995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
5252 | Construction Of Emitik ECD Classroom | Construction Of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1799740 | 1799740 | 1799740 | Equitable | N/A | 1799740 | 0 | 1199995 | 66.7 | 1199995 | 1799740 | 599745 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
5253 | Construction Of Hostel at Cheptuech Polytechnic | Construction Of Hostel at Cheptuech Polytechnic | To construct Hostel at Cheptuech Polytechnic | Hostel at Cheptuech Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.572763 35.614065 2486.500244140625 8.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started hence residents needs were not met.. Contractor: Don't know. Assessor remarks: There are no pit latrines under department of trade at Kiptagich market.
5254 | Construction Of Lelpanga ECD Class | Construction Of Lelpanga ECD Class | To construct Lelpanga ECD Class | Lelpanga ECD Class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 1147660 | 100 | 1147660 | 1800000 | -1147660 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
5255 | Completion and Equiping of two Mororbei ECDE classrooms | Completion and Equiping of two Mororbei ECDE classrooms | To complete and Equiping of two Mororbei ECDE classrooms | And Equiping of two Mororbei ECDE classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.356669 35.481787 0 2099.9990234375 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1999909 | 117.6 | 1999909 | 91 | -299909 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
5256 | Completion of Tiritya ECDE classroom and Equiping | Completion of Tiritya ECDE classroom and Equiping | To complete Tiritya ECDE classroom and Equiping | Tiritya ECDE classroom and Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1499880 | 78.9 | 1499880 | 1000000 | 400120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
5257 | Construction and equipping of Chepuyet ECD | Construction and equipping of Chepuyet ECD | To construct and equip Chepuyet ECD | Chepuyet ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376934, 35.529857 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 941950 | Equitable | N/A | 941950 | 0 | 516100 | 100 | 516100 | 941950 | -516100 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5258 | Construction Of An ECD Classroom At Chebuiyot | Construction Of An ECD Classroom At Chebuiyot | To construct An ECD Classroom At Chebuiyot | An ECD Classroom At Chebuiyot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1499880 | 150 | 1499880 | 1000000 | -499880 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
5259 | Construction of one ECDE classsrooms at Unity ECD | Construction of one ECDE classsrooms at Unity ECD | To construct one ECDE classsrooms at Unity ECD | One ECDE classsrooms at Unity ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 7157555 | 100 | 7157555 | 1800000 | -7157555 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5260 | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | To construct ECDE classroom and Toilet and Equipping at Moi Primary School | ECDE classroom and Toilet and Equipping at Moi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.277232 36.067338 1862.4909989898247 8 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 0 | 1763240 | Equitable | N/A | 1763240 | 0 | 1480 | 100 | 1480 | 1763240 | -1480 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: ..
5261 | Construction And Equipping of Ngeya ECD | Construction And Equipping of Ngeya ECD | To construct and equip Ngeya ECD | Ngeya ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 818350 | 100 | 818350 | 1500000 | -818350 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5262 | Construction of a Polytechnic at Maai Mahiu | Construction of a Polytechnic at Maai Mahiu | To construct a Polytechnic at Maai Mahiu | A Polytechnic at Maai Mahiu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.990353, 36.586414 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 5087948 | 1782181 | Equitable | N/A | 1782181 | 0 | 8116489 | 159.5 | 8116489 | 1782181 | -3028541 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Once operational hands on courses will be offered and the objective will be met.. Viable: Yes..
5263 | Construction and equipping of 1 ECD classroom at Nkapani | Construction and equipping of 1 ECD classroom at Nkapani | To construct and equip 1 ECD classroom at Nkapani | 1 ECD classroom at Nkapani constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2497135 | 0 | 2497135 | Equitable | N/A | 2497135 | 0 | 2499394 | 100 | 2499394 | 1500000 | -2499394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5264 | Construction And Equipping of Ngati ECD Two Door Toilets, Urinal, | Construction And Equipping of Ngati ECD Two Door Toilets, Urinal, | To construct and equip Ngati ECD Two Door Toilets, Urinal, | Ngati ECD Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 100 | 584286 | 2500000 | -584286 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5265 | Construction And Equipping of Ngunyumu ECD And Two Door Toilets, Urinal, | Construction And Equipping of Ngunyumu ECD And Two Door Toilets, Urinal, | To construct and equip Ngunyumu ECD And Two Door Toilets, Urinal, | Ngunyumu ECD And Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5266 | Construction And Equipping of Sero ECD, Two Door Toilets, Urinal, | Construction And Equipping of Sero ECD, Two Door Toilets, Urinal, | To construct and equip Sero ECD, Two Door Toilets, Urinal, | Sero ECD, Two Door Toilets, Urinal, constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 100 | 584286 | 2500000 | -584286 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5267 | Construction Of 2 ECD Classrooms In Tangi Tatu | Construction Of 2 ECD Classrooms In Tangi Tatu | To construct 2 ECD Classrooms In Tangi Tatu | 2 ECD Classrooms In Tangi Tatu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 0 | 2399999 | Equitable | N/A | 2399999 | 0 | 2499394 | 100 | 2499394 | 2399999 | -2499394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5268 | Construction of a classroom and a 2-door latrine at Ndabibi Main ECDE | Construction of a classroom and a 2-door latrine at Ndabibi Main ECDE | To construct a classroom and a 2-door latrine at Ndabibi Main ECDE | A classroom and a 2-door latrine at Ndabibi Main ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.707827, 36.219035 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 23.4 | 584286 | 3000000 | 1915714 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Hillstone.
5269 | Construction of a classroom and a 2-door latrine at Ndibithi ECDE | Construction of a classroom and a 2-door latrine at Ndibithi ECDE | To construct a classroom and a 2-door latrine at Ndibithi ECDE | A classroom and a 2-door latrine at Ndibithi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.707827, 36.219035 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 584286 | 23.4 | 584286 | 3000000 | 1915714 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Hillstone.
5270 | Construction of one ECDE classroom at Kongoni Primary | Construction of one ECDE classroom at Kongoni Primary | To construct one ECDE classroom at Kongoni Primary | One ECDE classroom at Kongoni Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.819052, 36.256682 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2499394 | 125 | 2499394 | 2500000 | -499394 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
5271 | Design And Construction Of ECD Classroom At Natooli | Design And Construction Of ECD Classroom At Natooli | To design and construct ECD Classroom At Natooli | ECD Classroom At Natooli designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5272 | Design And Construction Of ECD Classroom At Ndabibi Central | Design And Construction Of ECD Classroom At Ndabibi Central | To design and construct ECD Classroom At Ndabibi Central | ECD Classroom At Ndabibi Central designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2739065 | 0 | 2739065 | Equitable | N/A | 2739065 | 0 | 2499394 | 100 | 2499394 | 2739065 | -2499394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5273 | Design And Construction Of ECD Classroom At Ngondi | Design And Construction Of ECD Classroom At Ngondi | To design and construct ECD Classroom At Ngondi | ECD Classroom At Ngondi designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | -2499394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
5274 | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | To construct classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.417015 0 2000 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N//A. Viable: N//A. Assessor remarks: N//A.
5275 | Construction of ECD classroom at Kangari primary school | Construction of ECD classroom at Kangari primary school | To construct ECD classroom at Kangari primary school | ECD classroom at Kangari primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685, 36.417015 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | Yet to start | 1800000 | 1600000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1197794 | 74.9 | 1197794 | 2200000 | 402206 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It will once complete. Viable: It will.
5276 | Construction of ECD classroom & renovation of the existing ECD classroom at St. John primary | Construction of ECD classroom & renovation of the existing ECD classroom at St. John primary | To construct ECD classroom & renovation of the existing ECD classroom at St. John primary | ECD classroom & renovation of the existing ECD classroom at St. John primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.489092 0 2000 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1197794 | 59.9 | 1197794 | 2200000 | 802206 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovations.
5277 | Construction Of Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | Construction Of Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | To construct Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block | Nyondia Annex ECD Terrazzo Floor Furniture Equipping Tank with Gutters, 4 Door Toilet Block constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.417015 0 2000 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2600000 | 0 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 2600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N//A. Viable: N//A. Assessor remarks: N//A.
5278 | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | To construct Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.353645, 35.870354 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | N/A | 5200000 | 2599800 | 2599800 | Equitable | N/A | 2599800 | 0 | 2599800 | 100 | 2599800 | 5199600 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5279 | Construction of ECDE classroom at Kianugu ECD | Construction of ECDE classroom at Kianugu ECD | To construct ECDE classroom at Kianugu ECD | ECDE classroom at Kianugu ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.626036, 36.026932 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1199920 | 80 | 1199920 | 1500000 | 300080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
5280 | Completion and equipping of Sigor ECD | Completion and equipping of Sigor ECD | To complete and equip Sigor ECD | Sigor ECD completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.547133, 36.008833 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2017 | 1000000 | 0 | 1292000 | Equitable | N/A | 1292000 | 0 | 0 | 0 | 0 | 992000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known.
5281 | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | To construct and equip Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.502886, 35.974852 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 6000000 | 0 | 3711580 | Equitable | N/A | 3711580 | 0 | 1984380 | 100 | 1984380 | 3711580 | -1984380 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
5282 | Construction of Kapsinendet ECD | Construction of Kapsinendet ECD | To construct Kapsinendet ECD | Kapsinendet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.535047 36.00275 2358.2 76.9000015258789 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 3000000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1199994 | 40 | 1199994 | 3000000 | 1800006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Need new classroom.
5283 | Construction And Equipping of ECD Classroom at Nakuru Teachers Primary School | Construction And Equipping of ECD Classroom at Nakuru Teachers Primary School | To construct and equip ECD Classroom at Nakuru Teachers Primary School | ECD Classroom at Nakuru Teachers Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Menengai | -0.272842, 36.106843 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/2025 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 3499981 | 205.9 | 3499981 | 1700000 | -1799981 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5284 | Construction Of One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | Construction Of One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | To construct One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE | One Classroom, Equipping, Water Tank at Tayarn ECD, Dariti ECD, Kirandich ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.503687, 36.062987 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 4500000 | 0 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 4500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5285 | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | To upgrade Former Mukinyai Nursery school to be an Annex Polytechnic through tarmacking for improved road connectivity | Former Mukinyai Nursery school to be an Annex Polytechnic tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.205493 35.796119 0 500 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 1963020 | 1963020 | Equitable | N/A | 1963020 | 0 | 0 | 0 | 0 | 1963020 | 0 | Stalled | 0 | N/A | needs more allocation of funds | 2022 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yet to be. Assessor remarks: Formerly ECD , converted to polytechnic.
5286 | Completion of Chepseon ECDE Classroom | Completion of Chepseon ECDE Classroom | To complete Chepseon ECDE Classroom | Chepseon ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.209656, 35.841459 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 1200000 | 100 | 1200000 | 500000 | -1200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Contractor: Yet to start to advertise.
5287 | Construction Of 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | Construction Of 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | To construct 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE | 2 Classrooms at Ngata Primary and EX-MAR Garet ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.259698, 35.980502 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2951680 | 100 | 2951680 | 3000000 | -2951680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/s claysand.
5288 | Construction of Lelechwet ECDE Classroom | Construction of Lelechwet ECDE Classroom | To construct Lelechwet ECDE Classroom | Lelechwet ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.279457 35.88394 2110.2 6.099999904632568 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1833480 | 0 | 1833480 | Equitable | N/A | 1833480 | 0 | 1200000 | 100 | 1200000 | 1833480 | -1200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
5289 | Construction of Wardai Polytechnic | Construction of Wardai Polytechnic | To construct Wardai Polytechnic | Wardai Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 499994 | 100 | 499994 | 2000000 | -499994 | Stalled | 90 | 100 | Stalled — reasons to be confirmed by department | 2022 | N/A | -499994 | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
5290 | Construction of Nyairoko - Kairi ECDE | Construction of Nyairoko - Kairi ECDE | To construct Nyairoko - Kairi ECDE | Nyairoko - Kairi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 1500000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1200000 | 80 | 1200000 | 1500000 | 300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5291 | Construction of one (1) classroom at Gitare primary | Construction of one (1) classroom at Gitare primary | To construct one (1) classroom at Gitare primary | One (1) classroom at Gitare primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.412435, 36.311654 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1198820 | 66.6 | 1198820 | 1200000 | 601180 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Not done l as a.
5292 | Construction and equipping of an ECD Classroom at Munyu | Construction and equipping of an ECD Classroom at Munyu | To construct and equip an ECD Classroom at Munyu | An ECD Classroom at Munyu constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1473625 | 1473625 | Equitable | N/A | 1473625 | 0 | 2999064 | 203.5 | 2999064 | 1473625 | -1525439 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
5293 | Completion of Naka ECD classroom | Completion of Naka ECD classroom | To complete Naka ECD classroom | Naka ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.289335, 36.103277 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5294 | Construction of Mzee Wanyama Polytechnic | Construction of Mzee Wanyama Polytechnic | To construct Mzee Wanyama Polytechnic | Mzee Wanyama Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.372659, 36.149715 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2022/23 | 2023/2024 | 5445927 | 0 | 5398000 | Equitable | N/A | 5398000 | 0 | 5025850 | 100 | 5025850 | 5000000 | -5025850 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fino limited.
5295 | Construction of one ECD classroom at Madaraka Comprehensive School | Construction of one ECD classroom at Madaraka Comprehensive School | To construct one ECD classroom at Madaraka Comprehensive School | One ECD classroom at Madaraka Comprehensive School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.298364, 36.129751 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 2715032 | 150.8 | 2715032 | 1200000 | -915032 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5296 | Construction of one ECD classroom at Nairobi Road Comprehensive School | Construction of one ECD classroom at Nairobi Road Comprehensive School | To construct one ECD classroom at Nairobi Road Comprehensive School | One ECD classroom at Nairobi Road Comprehensive School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.298364, 36.129751 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 2715032 | 150.8 | 2715032 | 1200000 | -915032 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5297 | Construction Of Vocational Polytechnic At Free Area | Construction Of Vocational Polytechnic At Free Area | To construct Vocational Polytechnic At Free Area | Vocational Polytechnic At Free Area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.293514 36.118728 1839.199951171875 37.99700164794922 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 0 | 4344590 | Equitable | N/A | 4344590 | 0 | 5025850 | 100 | 5025850 | 4344590 | -5025850 | Stalled | 75 | 100 | Stalled — reasons to be confirmed by department | 2019 | N/A | -5025850 | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Belistra enterprises ltd. Assessor remarks: No occupation certificate issued.
5298 | Design And Construction Of 1 ECDE Classroom At Naka Primary | Design And Construction Of 1 ECDE Classroom At Naka Primary | To design and construct 1 ECDE Classroom At Naka Primary | 1 ECDE Classroom At Naka Primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.289113 36.103626 1817.699951171875 6.599999904632568 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 100 | 2715032 | 1200000 | -2715032 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require funds more funds for completion.
5299 | Construction of Inginye ECD & Equiping, Construction of a four (4) door toilet & 10000 litres capacity water tank | Construction of Inginye ECD & Equiping, Construction of a four (4) door toilet & 10000 litres capacity water tank | To construct Inginye ECD & Equiping, Construction of a four (4) door toilet & 10000 litres capacity water tank | Inginye ECD & Equiping, Construction of a four (4) door toilet & 10000 litres capacity water tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.401924, 35.907913 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Not yet started. Viable: Not yet started.
5300 | Tiritagoi ECD - Construction Of 1 Classroom | Tiritagoi ECD - Construction Of 1 Classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction Of 1 Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.417516 35.906162 2476.5755676023055 30 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 100 | 1199431 | 1300000 | -1199431 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
5301 | Design And Construction Of Korovio ECDE Classroom | Design And Construction Of Korovio ECDE Classroom | To design and construct Korovio ECDE Classroom | Korovio ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.410761 35.899338 2463.547607421875 10.36299991607666 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
5302 | Design And Construction Of Masaita ECDE Classroom And Toilets | Design And Construction Of Masaita ECDE Classroom And Toilets | To design and construct Masaita ECDE Classroom And Toilets | Masaita ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 0 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 100 | 1199431 | 1105445 | -1199431 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
5303 | Design And Construction Of Missipei ECDE Classroom And Toilets | Design And Construction Of Missipei ECDE Classroom And Toilets | To design and construct Missipei ECDE Classroom And Toilets | Missipei ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 0 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 100 | 1199431 | 1105445 | -1199431 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
5304 | Construction of Kimakia ECDE & Equiping | Construction of Kimakia ECDE & Equiping | To construct Kimakia ECDE & Equiping | Kimakia ECDE & Equiping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.313408, 35.919649 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 110660 | 5.5 | 110660 | 110660 | 1889340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Lixam enterprises Ltd.
5305 | Construction of Mwigito village ECD | Construction of Mwigito village ECD | To construct Mwigito village ECD | Mwigito village ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.380206 35.92605 2284.955810546875 5.573999881744385 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1197000 | 100 | 1197000 | 2000000 | -1197000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Tiecim ltd. Assessor remarks: In good state.
5306 | Completion Of Songo ECDE Classroom | Completion Of Songo ECDE Classroom | To complete Songo ECDE Classroom | Songo ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.404183 35.662365 2637 14.899999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 998985 | 998985 | Equitable | N/A | 998985 | 0 | 261174 | 26.1 | 261174 | 998985 | 737811 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sumcott Enterprises. Assessor remarks: Needs urgent painting.
5307 | Construction and Equipping of Githiriga ECDE | Construction and Equipping of Githiriga ECDE | To construct and equip Githiriga ECDE | Githiriga ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 0 | 1469600 | Equitable | N/A | 1469600 | 0 | 800000 | 100 | 800000 | 1469600 | -800000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5308 | Construction and Equipping of Kenjoketty ECDE | Construction and Equipping of Kenjoketty ECDE | To construct and equip Kenjoketty ECDE | Kenjoketty ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 0 | 1469600 | Equitable | N/A | 1469600 | 0 | 115000 | 100 | 115000 | 1469600 | -115000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5309 | Construction and Equipping of Lelaitich ECDE | Construction and Equipping of Lelaitich ECDE | To construct and equip Lelaitich ECDE | Lelaitich ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 0 | 1469600 | Equitable | N/A | 1469600 | 0 | 115000 | 100 | 115000 | 1469600 | -115000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5310 | Construction and Equipping of Nyongeres ECDE | Construction and Equipping of Nyongeres ECDE | To construct and equip Nyongeres ECDE | Nyongeres ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 0 | 1469600 | Equitable | N/A | 1469600 | 0 | 800000 | 100 | 800000 | 1469600 | -800000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5311 | Construction And Equipping of Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | Construction And Equipping of Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | To construct and equip Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom | Sasumua ECDE, Songo Tarakwa B ECD, Chesirikwa ECD Classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.313743, 35.658717 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | - | 4400000 | 0 | 1669203.55 | Equitable | N/A | 1669203.55 | 0 | 2730796 | 100 | 2730796 | 1669204 | -2730796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES.
5312 | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | To construct One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.365508, 35.60519 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2023-2024 | 4800000 | 0 | 2592607.1 | Equitable | N/A | 2592607.1 | 0 | 2207393 | 100 | 2207393 | 2592607 | -2207393 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5313 | Construction of Sugutek ECDE | Construction of Sugutek ECDE | To construct Sugutek ECDE | Sugutek ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.364767 35.727897 2851.5 5.099999904632568 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 800000 | 100 | 800000 | 700000 | -800000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sumcott Enterprise LTD. Assessor remarks: Good.
5314 | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | To construct and equip 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.836914, 36.366297 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 4500000 | 4398540 | 1765059 | Equitable | N/A | 1765059 | 0 | 2633481 | 59.9 | 2633481 | 1765059 | 1765059 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.the tank is being used from a different structure.
5315 | Completion and equipping (furniture) of Mwariki TVET | Completion and equipping (furniture) of Mwariki TVET | To complete and equip (furniture) of Mwariki TVET | (furniture) of Mwariki TVET completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Rhonda | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5316 | Completion & Equipping of Mama Ngina ECDE Highrise Classrooms | Completion & Equipping of Mama Ngina ECDE Highrise Classrooms | To complete & Equipping of Mama Ngina ECDE Highrise Classrooms | & Equipping of Mama Ngina ECDE Highrise Classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 7500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5317 | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | To construct and equip a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | A high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 9000000 | 0 | 8793630 | Equitable | N/A | 8793630 | 0 | 0 | 0 | 0 | 8793630 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5318 | Construction & Equipping of Aeriol ECDE - 1 class | Construction & Equipping of Aeriol ECDE - 1 class | To construct & Equipping of Aeriol ECDE - 1 class | & Equipping of Aeriol ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.271818 35.668245 2737.4 4.400000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1959610 | 1959610 | 1909610 | Equitable | N/A | 1909610 | 0 | 1880400 | 96 | 1880400 | 1959610 | 79210 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njumuru Enterprises Ltd. Assessor remarks: The classroom is in use, however they have no county employed teacher, the classroom has terrazzo floor, well painted walls, electrical works done, however the roof appears to be leaking in some sections. The school has a small field, and no permanent water source.
5319 | Construction & Equipping of Kiletien ECDE - 1 class | Construction & Equipping of Kiletien ECDE - 1 class | To construct & Equipping of Kiletien ECDE - 1 class | & Equipping of Kiletien ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.235177 35.662557 2740.7999999999997 13.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1959610 | 0 | 1909610 | Equitable | N/A | 1909610 | 0 | 1880400 | 100 | 1880400 | 1959610 | -1880400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leaking roof noted, peeling of Wall paint, gutters need fixing.
5320 | Construction And Equipping Of 1 ECDE Classroom at Kipsyenan | Construction And Equipping Of 1 ECDE Classroom at Kipsyenan | To construct and equip 1 ECDE Classroom at Kipsyenan | 1 ECDE Classroom at Kipsyenan constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.046127 36.049341 1647 9.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 637751 | Equitable | N/A | 637751 | 0 | 862249 | 100 | 862249 | 637751 | -862249 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require Renovation and additional class.
5321 | Construction & Equiping of Kipkoi ECDE classroom | Construction & Equiping of Kipkoi ECDE classroom | To construct & Equiping of Kipkoi ECDE classroom | & Equiping of Kipkoi ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.056191, 36.076739 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1163660 | 64.6 | 1163660 | 1511226 | 636340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: It will be met once complete. Viable: It's viable and will meet the needs once completed.
5322 | Completion of ECDE classroom at Kaplelekwo ECDE | Completion of ECDE classroom at Kaplelekwo ECDE | To complete ECDE classroom at Kaplelekwo ECDE | ECDE classroom at Kaplelekwo ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | -0.015972, 36.037587 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | FY 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
5323 | Construction of classroom at Ruiyobei Vocational Training Centre | Construction of classroom at Ruiyobei Vocational Training Centre | To construct classroom at Ruiyobei Vocational Training Centre | Classroom at Ruiyobei Vocational Training Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.099258 36.173883 1556.7939453125 3.808000087738037 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 2187090 | 2187090 | 2187090 | Equitable | N/A | 2187090 | 0 | 0 | 0 | 0 | 2187090 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2022 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation, ceiling infested with bats.
5324 | Construction of two ECDE classrooms at Kapkaturu and Kamaech | Construction of two ECDE classrooms at Kapkaturu and Kamaech | To construct two ECDE classrooms at Kapkaturu and Kamaech | Two ECDE classrooms at Kapkaturu and Kamaech constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.084202, 36.171571 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024 | 8000000 | 8000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 102253 | 1.3 | 102253 | 1800000 | 7897747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Soloem construction limited.
5325 | Construction and Equiping of ECDE classroom at subukia primary | Construction and Equiping of ECDE classroom at subukia primary | To construct and Equiping of ECDE classroom at subukia primary | And Equiping of ECDE classroom at subukia primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.002873, 36.229215 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | Not yet started | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2892 | 0.1 | 2892 | 2892 | 1997108 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Deemed viable upon completion. Contractor: ALL JAY TRANS Ltd.
5326 | Construction Of 1 Class At Kamemo Primary ECDE | Construction Of 1 Class At Kamemo Primary ECDE | To construct 1 Class At Kamemo Primary ECDE | 1 Class At Kamemo Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.030872, 36.196235 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 2892 | 100 | 2892 | 1183015 | -2892 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
5327 | Construction Of A ECDE Center And Equipping at Tetu | Construction Of A ECDE Center And Equipping at Tetu | To construct A ECDE Center And Equipping at Tetu | A ECDE Center And Equipping at Tetu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.040257, 36.222773 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1499984 | 100 | 1499984 | 2000000 | -1499984 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5328 | Construction Of ECDE Classroom At Busienkiruk | Construction Of ECDE Classroom At Busienkiruk | To construct ECDE Classroom At Busienkiruk | ECDE Classroom At Busienkiruk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 0 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | -1151750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
5329 | Construction Of ECDE Classroom At Korao | Construction Of ECDE Classroom At Korao | To construct ECDE Classroom At Korao | ECDE Classroom At Korao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1138490 | 1138490 | Equitable | N/A | 1138490 | 0 | 1319 | 0.1 | 1319 | 1138490 | 1137171 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
5330 | Construction Of ECDE Classroom At Tach Asis | Construction Of ECDE Classroom At Tach Asis | To construct ECDE Classroom At Tach Asis | ECDE Classroom At Tach Asis constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 0 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | -1151750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
5331 | Construction of Kiplenjin ECDE classroom | Construction of Kiplenjin ECDE classroom | To construct Kiplenjin ECDE classroom | Kiplenjin ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.438399 35.609035 0 1899.9990234375 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 590910 | 29.5 | 590910 | 1138490 | 1409090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Potholes no teacher toilet and pupils toilet.
5332 | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | To construct One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.509537 35.634567 2510.2 5.699999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 4762794 | 0 | 2374975 | Equitable | N/A | 2374975 | 0 | 2387819 | 100 | 2387819 | 2374975 | -2387819 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
5333 | Construction Of Suguyek ECDE, Equipping and Installation of Water Tank | Construction Of Suguyek ECDE, Equipping and Installation of Water Tank | To construct Suguyek ECDE, Equipping and Installation of Water Tank | Suguyek ECDE, Equipping and Installation of Water Tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.538982 35.643548 0 2799.9990234375 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5334 | Construction and equipping of one Classroom at Rafiki ECD | Construction and equipping of one Classroom at Rafiki ECD | To construct and equip one Classroom at Rafiki ECD | One Classroom at Rafiki ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 0 | 1473625 | Equitable | N/A | 1473625 | 0 | 1199940 | 100 | 1199940 | 1473625 | -1199940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
5335 | Construction of ECDE classroom at Ndenderu A Kahuho | Construction of ECDE classroom at Ndenderu A Kahuho | To construct ECDE classroom at Ndenderu A Kahuho | ECDE classroom at Ndenderu A Kahuho constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.34223 35.745215 2732.1 99.69999694824219 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1399966 | 1399966 | 1399966 | Equitable | N/A | 1399966 | 0 | 1199940 | 85.7 | 1199940 | 1399966 | 200026 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs renovations.
5336 | Construction of Mona ECDE | Construction of Mona ECDE | To construct Mona ECDE | Mona ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.273188 35.732858 2517.6 18 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1199940 | 66.7 | 1199940 | 1199996 | 600060 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is in dilapidated condition..
5337 | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | To construct and equip Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 4500000 | 2711294.25 | 1241431.4 | Equitable | N/A | 1241431.4 | 0 | 3141914 | 115.9 | 3141914 | 1241431 | -430619.75 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5338 | Construction Of 2 Classrooms at Shalom ECDE and Ngessuim ECDE | Construction Of 2 Classrooms at Shalom ECDE and Ngessuim ECDE | To construct 2 Classrooms at Shalom ECDE and Ngessuim ECDE | 2 Classrooms at Shalom ECDE and Ngessuim ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 3600000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 1155310 | 100 | 1155310 | 3600000 | -1155310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5339 | Construction Of ECD Classroom at Kandutura Primary | Construction Of ECD Classroom at Kandutura Primary | To construct ECD Classroom at Kandutura Primary | ECD Classroom at Kandutura Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 1155310 | 100 | 1155310 | 1800000 | -1155310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5340 | Construction of Gicheha ECDE classroom | Construction of Gicheha ECDE classroom | To construct Gicheha ECDE classroom | Gicheha ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 1800000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1155310 | 64.2 | 1155310 | 600000 | 644690 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5341 | Construction of Kware Polytechnic toilets | Construction of Kware Polytechnic toilets | To construct Kware Polytechnic toilets | Kware Polytechnic toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.932339 1710.7 13.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1798100 | 100 | 1798100 | 600000 | -1798100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5342 | Construction Of One Classroom At Rajuera ECDE | Construction Of One Classroom At Rajuera ECDE | To construct One Classroom At Rajuera ECDE | One Classroom At Rajuera ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 100 | 1155310 | 1200000 | -1155310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5343 | Construction Of ECD Classroom at Naivasha Prison ECDE | Construction Of ECD Classroom at Naivasha Prison ECDE | To construct ECD Classroom at Naivasha Prison ECDE | ECD Classroom at Naivasha Prison ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.705306, 36.431194 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 3208039 | 100 | 3208039 | 1500000 | -3208039 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5344 | Completion of Resource Center Nakuru Phase 2 | Completion of Resource Center Nakuru Phase 2 | To complete Resource Center Nakuru Phase 2 | Resource Center Nakuru Phase 2 completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 0 | 4986452 | Equitable | N/A | 4986452 | 0 | 0 | 0 | 0 | 4986452 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5345 | Ruiyobei polytechnic dormitories construction and equipping | Ruiyobei polytechnic dormitories construction and equipping | To implement ruiyobei polytechnic dormitories construction and equipping for access to quality education and training | Ruiyobei polytechnic dormitories construction and equipping completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 10000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5346 | Construction of a modern kitchen at Kiburuti ECDE | Construction of a modern kitchen at Kiburuti ECDE | To construct a modern kitchen at Kiburuti ECDE | A modern kitchen at Kiburuti ECDE constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Maiella | -0.732106, 36.23342 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 497700 | 23.7 | 497700 | 2400000 | 1602300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Constructions.
5347 | Construction of a modern kitchen at Nkampani ECDE | Construction of a modern kitchen at Nkampani ECDE | To construct a modern kitchen at Nkampani ECDE | A modern kitchen at Nkampani ECDE constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Maiella | -0.732106, 36.23342 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 497700 | 23.7 | 497700 | 2400000 | 1602300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Constructions.
5348 | Construction of kitchens at Maua and Oserian ECDE centres | Construction of kitchens at Maua and Oserian ECDE centres | To construct kitchens at Maua and Oserian ECDE centres | Kitchens at Maua and Oserian ECDE centres constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Olkaria | 0.83544, 36.342166 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5349 | Repair of ECDE classroom at Umoja Nursery and fencing | Repair of ECDE classroom at Umoja Nursery and fencing | To rehabilitate ECDE classroom at Umoja Nursery and fencing to restore functionality | ECDE classroom at Umoja Nursery and fencing rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Dundori | -0.258357 36.2358 2331.60009765625 4.599999904632568 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1200000 | 100 | 1200000 | 800000 | -1200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Eshipah limited. Assessor remarks: Good.
5350 | Renovation & Extension of ECDE Kitchen At Race Track Primary School | Renovation & Extension of ECDE Kitchen At Race Track Primary School | To rehabilitate & Extension of ECDE Kitchen At Race Track Primary School to restore functionality | & Extension of ECDE Kitchen At Race Track Primary School rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru East | Flamingo | -0.31045, 36.070103 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Fy2023-2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 352009 | 100 | 352009 | 2000000 | -352009 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5351 | Maeka ECDE renovation,equipping and fencing | Maeka ECDE renovation,equipping and fencing | To implement maeka ecde renovation,equipping and fencing for access to quality education and training | Maeka ECDE renovation,equipping and fencing completed | 3110302 | Refurbishment of Non-Residential Buildings | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works Ltd. Assessor remarks: Requires equipping, toilets and kitchen.
5352 | Renovation of ndungiri/muarati ECDE and fencing | Renovation of ndungiri/muarati ECDE and fencing | To rehabilitate ndungiri/muarati ECDE and fencing to restore functionality | Ndungiri/muarati ECDE and fencing rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Subukia | Kabazi | -0.121483, 36.058353 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | October 2025 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Denken Construction Ltd.
5353 | Renovation of Kaptembwo Vocational Training Centre including terazzo, water and electricity installation | Renovation of Kaptembwo Vocational Training Centre including terazzo, water and electricity installation | To rehabilitate Kaptembwo Vocational Training Centre including terazzo, water and electricity installation to restore functionality | Kaptembwo Vocational Training Centre including terazzo, water and electricity installation rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Kaptembwo | -0.317665, 36.052974 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PAKENDA SUPPLIERSAND BUILDING CONTRACTORS.
5354 | Renovation of Menengai Hill primary School ECDE | Renovation of Menengai Hill primary School ECDE | To rehabilitate Menengai Hill primary School ECDE to restore functionality | Menengai Hill primary School ECDE rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Kiamaina | -0.25047, 36.090167 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5355 | Renovation/refurbishment of Menengai Hill Primary & Rurii ECDE classrooms | Renovation/refurbishment of Menengai Hill Primary & Rurii ECDE classrooms | To implement renovation/refurbishment of menengai hill primary & rurii ecde classrooms for access to quality education and training | Renovation/refurbishment of Menengai Hill Primary & Rurii ECDE classrooms completed | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Kiamaina | -0.26433, 36.134529 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes after completion. Viable: Yes.
5356 | Partitioning of Lake View day care center | Partitioning of Lake View day care center | To implement partitioning of lake view day care center for access to quality education and training | Partitioning of Lake View day care center completed | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Lake view | -0.734191, 36.435732 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet realized. Viable: It will meet.
5357 | Rehabilitation of Kamurunyu ECDE and movable partitioning | Rehabilitation of Kamurunyu ECDE and movable partitioning | To rehabilitate Kamurunyu ECDE and movable partitioning to restore functionality | Kamurunyu ECDE and movable partitioning rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Lanet-Umoja | -0.198863, 35.935723 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5358 | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | To rehabilitate two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired to restore functionality | Two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.274307, 36.057502 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5359 | Renovation of Crator ECDE classroom ant Crater ECDE (flooring, ceiling, painting and windows) | Renovation of Crator ECDE classroom ant Crater ECDE (flooring, ceiling, painting and windows) | To rehabilitate Crator ECDE classroom ant Crater ECDE (flooring, ceiling, painting and windows) to restore functionality | Crator ECDE classroom ant Crater ECDE (flooring, ceiling, painting and windows) rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Maiella | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5360 | Renovation Of Gwa-share ECDE Classroom and Equipping | Renovation Of Gwa-share ECDE Classroom and Equipping | To rehabilitate Gwa-share ECDE Classroom and Equipping to restore functionality | Gwa-share ECDE Classroom and Equipping rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Gilgil | Malewa West | -0.612613, 36.398477 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 500000 | 200000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5361 | Renovation and Fencing of Sunshine ECDE | Renovation and Fencing of Sunshine ECDE | To rehabilitate Fencing of Sunshine ECDE to restore functionality | Fencing of Sunshine ECDE rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Rongai | Mosop | -0.236408, 35.842665 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1198000 | 119.8 | 1198000 | 1400000 | -198000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Effective hardware.
5362 | Renovation Of 2 Sawaiti ECDE Classes | Renovation Of 2 Sawaiti ECDE Classes | To rehabilitate 2 Sawaiti ECDE Classes to restore functionality | 2 Sawaiti ECDE Classes rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Rongai | Soin | -0.071965 36.043668 1622.8 5.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The school needs teachers and learners toilet,water Tank, Furnitures and outdoor play materials.
5363 | Renovation of two ECDE classroom at Turi Sulgwite ECDE | Renovation of two ECDE classroom at Turi Sulgwite ECDE | To rehabilitate two ECDE classroom at Turi Sulgwite ECDE to restore functionality | Two ECDE classroom at Turi Sulgwite ECDE rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Molo | Turi | -0.29662 35.755398 2422.2001953125 12.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 6 | 0 | 6 | 199960 | 799994 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs to be equipped. The water gutters needs to be replaced. They are broken.
5364 | Renovation of 3 ECDE classrooms at Kabati ECDE including replacing of leaking roof, replacement of windows, flooring, painting | Renovation of 3 ECDE classrooms at Kabati ECDE including replacing of leaking roof, replacement of windows, flooring, painting | To rehabilitate 3 ECDE classrooms at Kabati ECDE including replacing of leaking roof, replacement of windows, flooring, painting to restore functionality | 3 ECDE classrooms at Kabati ECDE including replacing of leaking roof, replacement of windows, flooring, painting rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Viwandani | -0.717584, 36.442581 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: The project did not start has not met the needs.
5365 | Construction of Elevated water tank for 2 no. 10,000L plastic tanks at Ha waruoro borehole | Construction of Elevated water tank for 2 no. 10,000L plastic tanks at Ha waruoro borehole | To construct Elevated water tank for 2 no. 10,000L plastic tanks at Ha waruoro borehole | Elevated water tank for 2 no. 10,000L plastic tanks at Ha waruoro borehole constructed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.481093, 35.990023 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: MERLINZ KEYS ENTERPRISE.
5366 | Construction Of 4 Door Bondeni ECDE Toilets and Urinal | Construction Of 4 Door Bondeni ECDE Toilets and Urinal | To construct 4 Door Bondeni ECDE Toilets and Urinal | 4 Door Bondeni ECDE Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.576548, 35.700157 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1199956 | 100 | 1199956 | 800000 | -1199956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes.
5367 | Construction Of 6 Door Kapkorio ECDE Toilets and Urinal | Construction Of 6 Door Kapkorio ECDE Toilets and Urinal | To construct 6 Door Kapkorio ECDE Toilets and Urinal | 6 Door Kapkorio ECDE Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.576548, 35.700157 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 950000 | 0 | 950000 | Equitable | N/A | 950000 | 0 | 1000000 | 100 | 1000000 | 950000 | -1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes.
5368 | Construction Of Kahawa ECDE toilets | Construction Of Kahawa ECDE toilets | To construct Kahawa ECDE toilets | Kahawa ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
5369 | Construction of a 4-door pit latrine at Menengai ECDE Centre | Construction of a 4-door pit latrine at Menengai ECDE Centre | To construct a 4-door pit latrine at Menengai ECDE Centre | A 4-door pit latrine at Menengai ECDE Centre constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285648, 36.087642 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025/25 | 975000 | 975000 | 975000 | Equitable | N/A | 975000 | 0 | 1199771 | 123.1 | 1199771 | 10000000 | -224771 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Not yet. Viable: Yes.
5370 | Construction Of an Ablution Block at Wanyororo Vocational Training Center | Construction Of an Ablution Block at Wanyororo Vocational Training Center | To construct an Ablution Block at Wanyororo Vocational Training Center | An Ablution Block at Wanyororo Vocational Training Center constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252032, 36.193277 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024/2025 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5371 | Construction of an ECD Toilet at Giachonge Primary school | Construction of an ECD Toilet at Giachonge Primary school | To construct an ECD Toilet at Giachonge Primary school | An ECD Toilet at Giachonge Primary school constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252786 36.183911 2006.5999755859375 15 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 500000 | 0 | 495760 | Equitable | N/A | 495760 | 0 | 1199978 | 100 | 1199978 | 495760 | -1199978 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alidawn ltd. Assessor remarks: Good should be operationalized.
5372 | Constructions of toilets in migimo ECDE, dundori ECDE, Bavuni ECDE, Giachongi ECDE | Constructions of toilets in migimo ECDE, dundori ECDE, Bavuni ECDE, Giachongi ECDE | To implement constructions of toilets in migimo ecde, dundori ecde, bavuni ecde, giachongi ecde for access to quality education and training | Constructions of toilets in migimo ECDE, dundori ECDE, Bavuni ECDE, Giachongi ECDE completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.25862, 36.235508 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1200000 | 48 | 1200000 | 0 | 1300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Silent enterprise.
5373 | Construction of Ebenezer and Ndibai ECDE toilets | Construction of Ebenezer and Ndibai ECDE toilets | To construct Ebenezer and Ndibai ECDE toilets | Ebenezer and Ndibai ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.541029, 36.070113 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1900000 | 0 | 1900000 | Equitable | N/A | 1900000 | 0 | 1199700 | 100 | 1199700 | 1900000 | -1199700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5374 | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools | To implement reconstruction of ecde toilet at langalanga, lakeview & kimathi primary schools for access to quality education and training | Reconstruction Of ECDE Toilet at Langalanga, Lakeview & Kimathi Primary Schools completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30512 36.078243 1849.6 6 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2385216 | 100 | 2385216 | 3000000 | -2385216 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo solutions limited. Assessor remarks: Ongoing.
5375 | Construction of ECD sanitation facilities | Construction of ECD sanitation facilities | To construct ECD sanitation facilities | ECD sanitation facilities constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.222936, 35.771564 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2015/2016 | 13000000 | 13000000 | 13000000 | Equitable | N/A | 13000000 | 0 | 19900008 | 153.1 | 19900008 | 13000000 | -6900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Met but lack accompanying tank and water point. Viable: To some extent.
5376 | Construction of Kitchen facilities in ECDEs for School feeding programme | Construction of Kitchen facilities in ECDEs for School feeding programme | To construct Kitchen facilities in ECDEs for School feeding programme | Kitchen facilities in ECDEs for School feeding programme constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 25000000 | 10000000 | 9977750 | Equitable | N/A | 9977750 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5377 | Installation of CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | Installation of CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | To install CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres | CCTV Cameras at Subukia, Kagoto, Njoro and Rongai Digital Centres installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 940000 | Equitable | N/A | 940000 | 0 | 795000 | 100 | 795000 | 940000 | -795000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5378 | Rehabilitation, construction and equipping of ECDE Centers | Rehabilitation, construction and equipping of ECDE Centers | To implement rehabilitation, construction and equipping of ecde centers for access to quality education and training | Rehabilitation, construction and equipping of ECDE Centers completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 20000000 | 20000000 | 5500000 | Equitable | N/A | 5500000 | 0 | 9787000 | 48.9 | 9787000 | 165600 | 10213000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5379 | Construction Of a Modern Toilet at Nyamathi ECDE | Construction Of a Modern Toilet at Nyamathi ECDE | To construct a Modern Toilet at Nyamathi ECDE | A Modern Toilet at Nyamathi ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.787454, 36.510844 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1487282 | 100 | 1487282 | 800000 | -1487282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5380 | Fencing and renovation of classroom at Airstrip ECDE | Fencing and renovation of classroom at Airstrip ECDE | To secure and renovation of classroom at Airstrip ECDE through fencing | And renovation of classroom at Airstrip ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.793602, 36.427098 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 18th June 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Frace ventures limited.
5381 | Construction of toilets at Murungaru ECD | Construction of toilets at Murungaru ECD | To construct toilets at Murungaru ECD | Toilets at Murungaru ECD constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.186306, 36.168866 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1070 | 0.1 | 1070 | 1070 | 998930 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Contractor: Willis.
5382 | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom | To implement fencing, construction of toilets and renovation of nyakiambi ecde classroom for access to quality education and training | Fencing, construction of toilets and renovation of Nyakiambi ECDE classroom completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.13503 36.1535 0 2218 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 2700000 | 100 | 2700000 | 1500000 | -2700000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works ltd. Assessor remarks: Requires furniture.
5383 | Completion of perimeter wall at Tulwet ECDE | Completion of perimeter wall at Tulwet ECDE | To complete perimeter wall at Tulwet ECDE | Perimeter wall at Tulwet ECDE completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 279231 | 16.4 | 279231 | 1500000 | 1420769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not started.
5384 | Construction of perimeter fence and a gate at Mogoon ECD | Construction of perimeter fence and a gate at Mogoon ECD | To construct perimeter fence and a gate at Mogoon ECD | Perimeter fence and a gate at Mogoon ECD constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.30348 36.025538 1878.9599609375 3.2160000801086426 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 279231 | 100 | 279231 | 2500000 | -279231 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Handed over to the contractor. But yet to start.
5385 | Construction of perimeter fence and a gate at Tulwet ECD | Construction of perimeter fence and a gate at Tulwet ECD | To construct perimeter fence and a gate at Tulwet ECD | Perimeter fence and a gate at Tulwet ECD constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.30348 36.025538 1878.9599609375 3.2160000801086426 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 279231 | 18.6 | 279231 | 1500000 | 1220769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Handed over to the contractor. But yet to start.
5386 | Fencing Of Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE | Fencing Of Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE | To secure Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE through fencing | Eleeingochoch Primary School ECDE and Kibaren Komen Primary School ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.310814, 36.053382 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Not yet started | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Not yet done. Contractor: Not awarded.
5387 | Installation of Solar water pump and Panels at Heshima and Kaptembwo ECDE | Installation of Solar water pump and Panels at Heshima and Kaptembwo ECDE | To install Solar water pump and Panels at Heshima and Kaptembwo ECDE | Solar water pump and Panels at Heshima and Kaptembwo ECDE installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29789 36.052599 1812.199951171875 82.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
5388 | Construction of ECDE toilet at Kapsembeiywo | Construction of ECDE toilet at Kapsembeiywo | To construct ECDE toilet at Kapsembeiywo | ECDE toilet at Kapsembeiywo constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.486957, 35.71931 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 747140 | 106.7 | 747140 | 1693833 | -47140 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5389 | Construction of a 4 door pit latrine toilet at Central Prmary ECDE | Construction of a 4 door pit latrine toilet at Central Prmary ECDE | To construct a 4 door pit latrine toilet at Central Prmary ECDE | A 4 door pit latrine toilet at Central Prmary ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.24579, 36.127623 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1900000 | 1900000 | 950000 | Equitable | N/A | 950000 | 0 | 968947 | 51 | 968947 | 1045171 | 931053 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes when completed. Viable: Yes it.
5390 | Construction Of 2 Toilets at Kio and Mutitu ECDE | Construction Of 2 Toilets at Kio and Mutitu ECDE | To construct 2 Toilets at Kio and Mutitu ECDE | 2 Toilets at Kio and Mutitu ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.441032, 35.983992 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 219716 | 16.9 | 219716 | 600000 | 1080284 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5391 | Construction Of a Modern Kitchen and A Dining Area at Milimani Center of Excellence | Construction Of a Modern Kitchen and A Dining Area at Milimani Center of Excellence | To construct a Modern Kitchen and A Dining Area at Milimani Center of Excellence | A Modern Kitchen and A Dining Area at Milimani Center of Excellence constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.721779, 36.439279 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5392 | Construction of Septic Tank at Unity and Lakeview Primary | Construction of Septic Tank at Unity and Lakeview Primary | To construct Septic Tank at Unity and Lakeview Primary | Septic Tank at Unity and Lakeview Primary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.758644, 36.46218 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 1282392 | 100 | 1282392 | 700000 | -1282392 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Partially. Viable: It will.
5393 | Constuction of a kitchen and equipping of Marela ECDE | Constuction of a kitchen and equipping of Marela ECDE | To implement constuction of a kitchen and equipping of marela ecde for access to quality education and training | Constuction of a kitchen and equipping of Marela ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.708776, 36.425023 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5394 | Rehabilitation and installation of 3 phase electricity at Ndege Ndimu vocational training centre | Rehabilitation and installation of 3 phase electricity at Ndege Ndimu vocational training centre | To rehabilitate installation of 3 phase electricity at Ndege Ndimu vocational training centre to restore functionality | Installation of 3 phase electricity at Ndege Ndimu vocational training centre rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet-Umoja | -0.301903, 36.172207 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No ,not yet done. Viable: Yet to meet.
5395 | Fencing of Lare Polytechnic with concrete post, chain link and main gate | Fencing of Lare Polytechnic with concrete post, chain link and main gate | To secure Lare Polytechnic with concrete post, chain link and main gate through fencing | Lare Polytechnic with concrete post, chain link and main gate fenced and secured | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.445005, 36.021978 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 23 | 1000000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5396 | Construction of Pit latrine at Uhuru Primary ECDE | Construction of Pit latrine at Uhuru Primary ECDE | To construct Pit latrine at Uhuru Primary ECDE | Pit latrine at Uhuru Primary ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.277308, 36.027923 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1480 | 0.1 | 1480 | 1480 | 998520 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5397 | Construction Of Maiella Polytechnic Workshop | Construction Of Maiella Polytechnic Workshop | To construct Maiella Polytechnic Workshop | Maiella Polytechnic Workshop constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.893629, 36.199071 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2025 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 497700 | 100 | 497700 | 4000000 | -497700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: NO. Viable: NO.
5398 | Construction Of 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | Construction Of 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | To construct 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School | 6-Door Modern Toilet at Hyrax Primary and St Johns Primary School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.278331 36.108055 1885.7724609375 56.26599884033203 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2800000 | 0 | 2800000 | Equitable | N/A | 2800000 | 0 | 3499981 | 100 | 3499981 | 2800000 | -3499981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: 2023/24. Assessor remarks: Functional.
5399 | Construction of 4 door Toilets at Nguzu River ECDE | Construction of 4 door Toilets at Nguzu River ECDE | To construct 4 door Toilets at Nguzu River ECDE | 4 door Toilets at Nguzu River ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 520000 | 0 | 499970 | Equitable | N/A | 499970 | 0 | 729740 | 100 | 729740 | 499970 | -729740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
5400 | Construction of Ngecha ECDE Toilet | Construction of Ngecha ECDE Toilet | To construct Ngecha ECDE Toilet | Ngecha ECDE Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | Not indicated | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 694 | 100 | 694 | 500000 | -694 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
5401 | Fencing at Ngondu ECDE Compound | Fencing at Ngondu ECDE Compound | To secure at Ngondu ECDE Compound through fencing | At Ngondu ECDE Compound fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279523 35.883943 2125.1 17.100000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not awarded. Viable: Viable. Contractor: Not awarded. Assessor remarks: Not yet awarded.
5402 | Completion Of Gachuga and Kayole ECDE toilets | Completion Of Gachuga and Kayole ECDE toilets | To complete Gachuga and Kayole ECDE toilets | Gachuga and Kayole ECDE toilets completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.836761, 36.515774 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Not yet | 1400000 | 0 | 1400000 | Equitable | N/A | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
5403 | Fencing And Construction Of Toilets of Karioko ECDE | Fencing And Construction Of Toilets of Karioko ECDE | To secure And Construction Of Toilets of Karioko ECDE through fencing | And Construction Of Toilets of Karioko ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.860852 36.548747 2604.6 4 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 999352 | 100 | 999352 | 1000000 | -999352 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Motorbikes sheds were vandalized they don't exist.
5404 | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | To construct Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.38946, 35.568755 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
5405 | Construction And Equipping of ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | Construction And Equipping of ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | To construct and equip ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) | ECD Kitchen At Mvuke, Narasha and Olkaria Primary(supply of modern Jikos and 110L sufurias) constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.826569, 36.298447 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3600000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 2633481 | 100 | 2633481 | 3600000 | -2633481 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5406 | Improvement and completion of Rhoda Vocational Training | Improvement and completion of Rhoda Vocational Training | To implement improvement and completion of rhoda vocational training for access to quality education and training | Improvement and completion of Rhoda Vocational Training completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 2100000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5407 | Construction Of 4 Door Toilet at Koisamo and Equipping of The Class | Construction Of 4 Door Toilet at Koisamo and Equipping of The Class | To construct 4 Door Toilet at Koisamo and Equipping of The Class | 4 Door Toilet at Koisamo and Equipping of The Class constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.096327 35.935707 1687 7.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1020860 | 100 | 1020860 | 800000 | -1020860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Construction to start soon.
5408 | Construction Of 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | Construction Of 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | To construct 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE | 4 Door Toilets at Kipsyenan, Kinoiyo and Lelechwet ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.096327 35.935707 1687 7.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 348930 | 100 | 348930 | 1500000 | -348930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Construction to start soon.
5409 | Construction Of 8 Door Toilet and Equipping of Majani Mingi Polytechnic | Construction Of 8 Door Toilet and Equipping of Majani Mingi Polytechnic | To construct 8 Door Toilet and Equipping of Majani Mingi Polytechnic | 8 Door Toilet and Equipping of Majani Mingi Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.041732, 36.024525 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | FY 2023 | 1800000 | 0 | 779140 | Equitable | N/A | 779140 | 0 | 1020860 | 100 | 1020860 | 779140 | -1020860 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: FY 2024.
5410 | Construction of Banita ECDE toilet (4 door toilet) | Construction of Banita ECDE toilet (4 door toilet) | To construct Banita ECDE toilet (4 door toilet) | Banita ECDE toilet (4 door toilet) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.081129, 36.072284 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 396354 | 56.6 | 396354 | 400000 | 303646 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5411 | Construction of kipsyenan ECDE toilet (4 door toilet) | Construction of kipsyenan ECDE toilet (4 door toilet) | To construct kipsyenan ECDE toilet (4 door toilet) | Kipsyenan ECDE toilet (4 door toilet) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.081129, 36.072284 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 396354 | 56.6 | 396354 | 400000 | 303646 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5412 | Construction of Makongeni ECDE toilet (4 door toilet) | Construction of Makongeni ECDE toilet (4 door toilet) | To construct Makongeni ECDE toilet (4 door toilet) | Makongeni ECDE toilet (4 door toilet) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.081129, 36.072284 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 396354 | 56.6 | 396354 | 400000 | 303646 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start.
5413 | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | To construct a Toilet block and purchase of a water tank at Our Lady of Victory Primary | A Toilet block and purchase of a water tank at Our Lady of Victory Primary constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.00426 36.23702 1995.800048828125 39.599998474121094 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. The toilet serves the ecde learners. Contractor: No information. Assessor remarks: The toilet looks good..
5414 | Construction of Morro ECD toilet and fencing | Construction of Morro ECD toilet and fencing | To construct Morro ECD toilet and fencing | Morro ECD toilet and fencing constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.010383, 36.223597 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 999980 | 66.7 | 999980 | 1500000 | 500020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5415 | Construction Of Karao ECDE 6 Door Toilets and Urinal | Construction Of Karao ECDE 6 Door Toilets and Urinal | To construct Karao ECDE 6 Door Toilets and Urinal | Karao ECDE 6 Door Toilets and Urinal constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.513813 35.683561 2568.666 3.1989998817443848 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199930 | 100 | 1199930 | 1200000 | -1199930 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
5416 | Construction And Equipping Of ICT Hub Facility/Hub Estate | Construction And Equipping Of ICT Hub Facility/Hub Estate | To construct and equip ICT Hub Facility/Hub Estate | ICT Hub Facility/Hub Estate constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714882 36.432885 0 200 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 1499845 | 100 | 1499845 | 5000000 | -1499845 | Stalled | 90 | 100 | Stalled — reasons to be confirmed by department | 2019 | N/A | -1499845 | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Effective.
5417 | Construction of a 4 door latrine at central ECDE | Construction of a 4 door latrine at central ECDE | To construct a 4 door latrine at central ECDE | A 4 door latrine at central ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.715348, 36.434693 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2948620 | 294.9 | 2948620 | 3000000 | -1948620 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Partially. Viable: Viable.
5418 | Construction of concrete (masonry) fence at Highway Ecde | Construction of concrete (masonry) fence at Highway Ecde | To construct concrete (masonry) fence at Highway Ecde | Concrete (masonry) fence at Highway Ecde constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.729213, 36.44822 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2948620 | 117.9 | 2948620 | 3000000 | -448620 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable.
5419 | Construction Of 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | Construction Of 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | To construct 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD | 2 Door Pit Latrines at Simboiyon ECD, Nairobi ECD, Wei ECD constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.054707, 36.214165 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
5420 | Construction of 2 door toilet and urinal at kamumo ECDE | Construction of 2 door toilet and urinal at kamumo ECDE | To construct 2 door toilet and urinal at kamumo ECDE | 2 door toilet and urinal at kamumo ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 475000 | 475000 | 475000 | Equitable | N/A | 475000 | 0 | 137 | 0 | 137 | 1200000 | 474863 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
5421 | Construction of 2 door toilet and urinal for kiriko ECDE | Construction of 2 door toilet and urinal for kiriko ECDE | To construct 2 door toilet and urinal for kiriko ECDE | 2 door toilet and urinal for kiriko ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 475000 | 475000 | 475000 | Equitable | N/A | 475000 | 0 | 2364444 | 497.8 | 2364444 | 1200000 | -1889444 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
5422 | Levelling of ECDE playground at kiptenden primary | Levelling of ECDE playground at kiptenden primary | To implement levelling of ecde playground at kiptenden primary for access to quality education and training | Levelling of ECDE playground at kiptenden primary completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.329031, 36.039566 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Pirkvired supplies.
5423 | Construction ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | Construction ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | To construct ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary | ECD Toilet at Kenyatta, St. Joseph, Harambee Khalsa Primary constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2100000 | 0 | 2100000 | Equitable | N/A | 2100000 | 0 | 1190650 | 100 | 1190650 | 2100000 | -1190650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5424 | Construction Of ECD Toilet at Freehold Primary | Construction Of ECD Toilet at Freehold Primary | To construct ECD Toilet at Freehold Primary | ECD Toilet at Freehold Primary constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 1190650 | 100 | 1190650 | 700000 | -1190650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5425 | Fencing with a chain link for Migwathi ECDE | Fencing with a chain link for Migwathi ECDE | To secure with a chain link for Migwathi ECDE through fencing | With a chain link for Migwathi ECDE fenced and secured | 3110599 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.233175, 36.177912 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willysamwa.
5426 | Construction Of 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | Construction Of 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | To construct 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD | 4 Door Toilet and Urinal at Echaririe and Mbaruk ECD constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 1963990 | 100 | 1963990 | 1700000 | -1963990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5427 | Construction Of 4 Door Toilets at Mbegi ECD and Teachers ECD | Construction Of 4 Door Toilets at Mbegi ECD and Teachers ECD | To construct 4 Door Toilets at Mbegi ECD and Teachers ECD | 4 Door Toilets at Mbegi ECD and Teachers ECD constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.534284, 36.342096 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No yet started.
5428 | Fencing Of Teachers ECD and Construction of gate | Fencing Of Teachers ECD and Construction of gate | To secure Teachers ECD and Construction of gate through fencing | Teachers ECD and Construction of gate fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.489141, 36.328335 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2022/24 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5429 | Fencing Of View Point ECD | Fencing Of View Point ECD | To secure View Point ECD through fencing | View Point ECD fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504762 36.328241 1989.4000244140625 17.466999053955078 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5430 | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center | To implement establishment & equipping of digital ict hub center at wendo vocational center for access to quality education and training | Establishment & Equipping of Digital ICT Hub Center At Wendo Vocational Center completed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
5431 | Electricity Installation at Lalwet ECDE | Electricity Installation at Lalwet ECDE | To implement electricity installation at lalwet ecde for access to quality education and training | Electricity Installation at Lalwet ECDE completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.27027, 36.036437 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable and serving purpose.
5432 | Construction Of the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | Construction Of the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | To construct the Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center | The Toilet, Fencing & Levelling of Kaptembwo Vocational Training Center constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.31767, 36.052973 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5433 | Construction Of 6 Door Modern Toilet at Kamoronyo ECDE | Construction Of 6 Door Modern Toilet at Kamoronyo ECDE | To construct 6 Door Modern Toilet at Kamoronyo ECDE | 6 Door Modern Toilet at Kamoronyo ECDE constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.255707, 36.160263 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1998040 | 142.7 | 1998040 | 1400000 | -598040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, partially. Viable: Yes,very viable.
5434 | Construction Of 6 Door Modern Toilet at Mireroni ECDE | Construction Of 6 Door Modern Toilet at Mireroni ECDE | To construct 6 Door Modern Toilet at Mireroni ECDE | 6 Door Modern Toilet at Mireroni ECDE constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.255707, 36.160263 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 1400000 | 0 | 1400000 | Equitable | N/A | 1400000 | 0 | 1998040 | 100 | 1998040 | 1400000 | -1998040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, partially. Viable: Yes,very viable.
5435 | Fencing, gate installation and toilet Construction in Maai Mahiu Youth Vocational Training Centre | Fencing, gate installation and toilet Construction in Maai Mahiu Youth Vocational Training Centre | To implement fencing, gate installation and toilet construction in maai mahiu youth vocational training centre for access to quality education and training | Fencing, gate installation and toilet Construction in Maai Mahiu Youth Vocational Training Centre completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.990582, 36.58622 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yet to. Viable: Yes.
5436 | Modification of Menengai primary school toilets to fit the needs of the special children | Modification of Menengai primary school toilets to fit the needs of the special children | To implement modification of menengai primary school toilets to fit the needs of the special children for access to quality education and training | Modification of Menengai primary school toilets to fit the needs of the special children completed | 3110599 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5437 | Equipping & Fencing Mwariki ECD | Equipping & Fencing Mwariki ECD | To equip & Fencing Mwariki ECD with necessary facilities and equipment | & Fencing Mwariki ECD equipped | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.316277, 36.065867 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 23/24 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Davgra limited.
5438 | Fencing of Majani mingi polytechnic | Fencing of Majani mingi polytechnic | To secure Majani mingi polytechnic through fencing | Majani mingi polytechnic fenced and secured | 3110599 | Other Infrastructure and Civil Works | Rongai | Soin | -0.041777, 36.02443 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1020860 | 51 | 1020860 | 779140 | 979140 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
5439 | Edgewood ECDE Fencing, Equipping and Construction of Toilets | Edgewood ECDE Fencing, Equipping and Construction of Toilets | To implement edgewood ecde fencing, equipping and construction of toilets for access to quality education and training | Edgewood ECDE Fencing, Equipping and Construction of Toilets completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.003635, 36.206705 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1198900 | 100 | 1198900 | 2000000 | -1198900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
5440 | Fencing Of Githaiga ECDE | Fencing Of Githaiga ECDE | To secure Githaiga ECDE through fencing | Githaiga ECDE fenced and secured | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.012055, 36.21717 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 02/05/2024 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: The facility is protected. Contractor: No information available.
5441 | Fencing of Ummoja ECDE | Fencing of Ummoja ECDE | To secure Ummoja ECDE through fencing | Ummoja ECDE fenced and secured | 3110599 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.198892, 35.936085 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5442 | Fencing Of Kabati ECD | Fencing Of Kabati ECD | To secure Kabati ECD through fencing | Kabati ECD fenced and secured | 3110599 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.719348, 36.442693 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 2948620 | 77.6 | 2948620 | 3800000 | 851380 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not met. Viable: Not viable.
5443 | Hardware and Software Platforms for Digital Centres | Hardware and Software Platforms for Digital Centres | To implement hardware and software platforms for digital centres for access to quality education and training | Hardware and Software Platforms for Digital Centres completed | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 492500 | Equitable | N/A | 492500 | 0 | 1528500 | 100 | 1528500 | 492500 | -1528500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5444 | Purchase Of Equipment at Barut Vocational & Youth Centre | Purchase Of Equipment at Barut Vocational & Youth Centre | To procure Equipment at Barut Vocational & Youth Centre | Equipment at Barut Vocational & Youth Centre procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Barut | -0.342342, 36.036679 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5445 | Equipping of Nakuru VTC Departments | Equipping of Nakuru VTC Departments | To equip Nakuru VTC Departments with necessary facilities and equipment | Nakuru VTC Departments equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Biashara-Nakuru | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2444091 | 2444091 | Equitable | N/A | 2444091 | 0 | 0 | 0 | 0 | 2444091 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5446 | Equiping of Dundori vocational training centre administration block | Equiping of Dundori vocational training centre administration block | To implement equiping of dundori vocational training centre administration block for access to quality education and training | Equiping of Dundori vocational training centre administration block completed | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Dundori | -0.251722, 36.234177 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5447 | Equipping Of Kongasis Polytechnic | Equipping Of Kongasis Polytechnic | To equip Kongasis Polytechnic with necessary facilities and equipment | Kongasis Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru/Mbaruk | -0.554731, 36.153036 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | Unspecified | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 985800 | 100 | 985800 | 2000000 | -985800 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
5448 | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE | To implement playing equipment for ecde at kimathi & pangani primary school ecde for access to quality education and training | Playing Equipment for ECDE At Kimathi & Pangani Primary School ECDE completed | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Flamingo | -0.305394 36.078686 1776.5 11.199999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 665899 | 0 | 665899 | Equitable | N/A | 665899 | 0 | 0 | 0 | 0 | 665899 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: No play equipment.
5449 | Kambi Somali-Additional Funds for Equipping, Playground and Fencing | Kambi Somali-Additional Funds for Equipping, Playground and Fencing | To implement kambi somali-additional funds for equipping, playground and fencing for access to quality education and training | Kambi Somali-Additional Funds for Equipping, Playground and Fencing completed | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Gilgil | -0.509502, 36.315312 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5450 | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | To equip Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit with necessary facilities and equipment | Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/23 | 11548737 | 0 | 9740508 | Equitable | N/A | 9740508 | 0 | 4123683 | 100 | 4123683 | 8800000 | -4123683 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5451 | Supply of ECDE ICT Learning materials and software (EIDU) | Supply of ECDE ICT Learning materials and software (EIDU) | To implement supply of ecde ict learning materials and software (eidu) for access to quality education and training | Supply of ECDE ICT Learning materials and software (EIDU) completed | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5452 | Equiping of Vocational Traning Centre | Equiping of Vocational Traning Centre | To implement equiping of vocational traning centre for access to quality education and training | Equiping of Vocational Traning Centre completed | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Kaptembwo | -0.317678, 36.05293 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 10000000 | 10000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: If finalized it's objective will be met. Viable: It will be viable once complete.
5453 | Equipping Of Rare ECD | Equipping Of Rare ECD | To equip Rare ECD with necessary facilities and equipment | Rare ECD equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Maai Mahiu | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 1177460 | 100 | 1177460 | 300000 | -1177460 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5454 | Equiping of Kimonio ECDE and toilet Construction | Equiping of Kimonio ECDE and toilet Construction | To implement equiping of kimonio ecde and toilet construction for access to quality education and training | Equiping of Kimonio ECDE and toilet Construction completed | 3111109 | Purchase of Educational Aids and Related Equipment | Molo | Mariashoni | -0.380454, 35.796475 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes.
5455 | Equiping of Siryat Vocational Training Institute | Equiping of Siryat Vocational Training Institute | To implement equiping of siryat vocational training institute for access to quality education and training | Equiping of Siryat Vocational Training Institute completed | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Mauche | -0.456305 35.958233 2427.3 10.449999809265137 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 990000 | 490000 | 1390000 | Equitable | N/A | 1390000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
5456 | Equipping Of Kamungei ECDE | Equipping Of Kamungei ECDE | To equip Kamungei ECDE with necessary facilities and equipment | Kamungei ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.225332 35.972693 1934.5 10.600000381469727 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 999200 | 333.1 | 999200 | 300000 | -699200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more chairs and desks.
5457 | Equiping Mimwaita Vocational Training College | Equiping Mimwaita Vocational Training College | To implement equiping mimwaita vocational training college for access to quality education and training | Equiping Mimwaita Vocational Training College completed | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.283985 35.96633 2094.9 99.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Equipment delivered.
5458 | Equiping of Ajebwo ECDE and water tank | Equiping of Ajebwo ECDE and water tank | To implement equiping of ajebwo ecde and water tank for access to quality education and training | Equiping of Ajebwo ECDE and water tank completed | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.266435, 35.881782 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not indicated.
5459 | Equiping of Mimwaita ECDE and water tank | Equiping of Mimwaita ECDE and water tank | To implement equiping of mimwaita ecde and water tank for access to quality education and training | Equiping of Mimwaita ECDE and water tank completed | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.266435, 35.881782 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2025 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not indicated.
5460 | Purchase of tools at Ogligei Vocational Training College | Purchase of tools at Ogligei Vocational Training College | To procure tools at Ogligei Vocational Training College | Tools at Ogligei Vocational Training College procured | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.283985 35.96633 2094.9 99.5999984741211 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/25 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 492840 | 98.6 | 492840 | 7160 | 7160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Equipment delivered.
5461 | Renovation of ECDE At Atebwo Primary | Renovation of ECDE At Atebwo Primary | To rehabilitate ECDE At Atebwo Primary to restore functionality | ECDE At Atebwo Primary rehabilitated | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.266003 35.881008 2093.4 16.5 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 497999 | 100 | 497999 | 600000 | -497999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
5462 | Equiping of Mzee Wanyama Polytechnic | Equiping of Mzee Wanyama Polytechnic | To implement equiping of mzee wanyama polytechnic for access to quality education and training | Equiping of Mzee Wanyama Polytechnic completed | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.372834, 36.149533 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 650940 | 21.7 | 650940 | 70510 | 2349060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5463 | Equipping of Free Area Vocational Training Center (Polytechnic) | Equipping of Free Area Vocational Training Center (Polytechnic) | To equip Free Area Vocational Training Center (Polytechnic) with necessary facilities and equipment | Free Area Vocational Training Center (Polytechnic) equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.293862, 36.118139 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2022/23 | 2022/23 | 2022/2023 | 5000000 | 0 | 4806300 | Equitable | N/A | 4806300 | 0 | 650940 | 100 | 650940 | 4806300 | -650940 | Stalled | 0 | 100 | Stalled — reasons to be confirmed by department | 2022 | N/A | -650940 | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5464 | Purchase of furniture for Mburu Gichua ECD | Purchase of furniture for Mburu Gichua ECD | To procure furniture for Mburu Gichua ECD | Furniture for Mburu Gichua ECD procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.368662, 36.153013 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes.
5465 | Purchase of furniture for Mirugi Kariuki ECD | Purchase of furniture for Mirugi Kariuki ECD | To procure furniture for Mirugi Kariuki ECD | Furniture for Mirugi Kariuki ECD procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.368662, 36.153013 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024/2025 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes.
5466 | Equiping of Matunda ECDE | Equiping of Matunda ECDE | To implement equiping of matunda ecde for access to quality education and training | Equiping of Matunda ECDE completed | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Nyota | -0.394602, 35.632172 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | 2024-2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 115000 | 23 | 115000 | 300000 | 385000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5467 | Equipping Of Mworoto Vocational Training Centre | Equipping Of Mworoto Vocational Training Centre | To equip Mworoto Vocational Training Centre with necessary facilities and equipment | Mworoto Vocational Training Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Nyota | -0.38879 35.653582 2664.2 18.399999618530273 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, will be impactful once complete. Assessor remarks: Stalled, Vandalized- Needs urgent attention..
5468 | Equipping Of Rangondu ECDE | Equipping Of Rangondu ECDE | To equip Rangondu ECDE with necessary facilities and equipment | Rangondu ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Nyota | -0.394602, 35.632172 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | 2024-2025 | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5469 | Purchase and installation of playing equipment at central ECDE and Highway ECDE | Purchase and installation of playing equipment at central ECDE and Highway ECDE | To procure and install playing equipment at central ECDE and Highway ECDE | Playing equipment at central ECDE and Highway ECDE procured and installed | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Viwandani | -0.714728, 36.435434 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2024/25 | N/A | 2665382 | 2665382 | 2665382 | Equitable | N/A | 2665382 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Viable: Not viable.
5470 | Acquisition of Equipment for Public Communication Unit | Acquisition of Equipment for Public Communication Unit | To procure Equipment for Public Communication Unit | Equipment for Public Communication Unit procured | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.113577, 35.796542 | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2024/25 | 2023/24 | 2022/2023 | 3500000 | 2000000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not meet the need. Contractor: Rynix construction limited.
5471 | Acquisition of e-Mail Solution for the County | Acquisition of e-Mail Solution for the County | To procure e-Mail Solution for the County | E-Mail Solution for the County procured | 3111112 | Purchase of Software | HQ | HQ | N/A | 4586 | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | EDUCATION, ICT, e-GOVERNMENT AND PUBLIC COMMUNICATION | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 1000000 | 995000 | Equitable | N/A | 995000 | 0 | 0 | 0 | 0 | 995000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5472 | Administration, Planning and Support Services | Construction Of Githioro Social Hall | To construct Githioro Social Hall | Githioro Social Hall constructed | 3110299 | Construction of Buildings - Ot | Bahati | Dundori | -0.262726, 36.187222 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2022/2023 | 2000000 | 2000000 | 2000000 | Equitable | 3,801,790 | 2000000 | 0 | 0 | 0 | 0 | 58 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5473 | Administration, Planning and Support Services | Construction of Karuchua Multipurpose Hall | To construct Karuchua Multipurpose Hall | Karuchua Multipurpose Hall constructed | 3110299 | Construction of Buildings - Ot | Bahati | Dundori | -0.262328, 36.187226 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2021/22 | 2021/22 | 2023/2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 58 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Silent enterprise.
5474 | Administration, Planning and Support Services | Completion Of Elburgon Social Hall and Installation of Chain link Fence | To complete Elburgon Social Hall and Installation of Chain link Fence | Elburgon Social Hall and Installation of Chain link Fence completed | 3110299 | Construction of Buildings - Ot | Molo | Elburgon | -0.307065 35.810187 2407.60009765625 27.5 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 902215 | Equitable | 4,097,785 | 902215 | 0 | 0 | 0 | 0 | 16 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: PETMAT LTD. Assessor remarks: Ongoing.
5475 | Completion of Njoro drop-in centre | Completion of Njoro drop-in centre | To complete Njoro drop-in centre | Njoro drop-in centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 20000000 | 12000000 | 12000000 | N/A | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5476 | Expansion of the GBV Rescue Center | Expansion of the GBV Rescue Center | To expand the GBV Rescue Center to increase capacity | The GBV Rescue Center expanded | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 60000000 | 0 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5477 | Partial Completion Of A GBV Centre | Partial Completion Of A GBV Centre | To implement partial completion of a gbv centre for youth empowerment and social inclusion | Partial Completion Of A GBV Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2020/21 | 2020/21 | 2020/21 | 7714075 | 6745420 | 6745420 | N/A | N/A | 6745420 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5478 | Administration, Planning and Support Services | Construction and Equiping of a modern baby care centre at Mirera Primary | To construct and Equiping of a modern baby care centre at Mirera Primary | And Equiping of a modern baby care centre at Mirera Primary constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Hells Gate | -0.77801, 36.429729 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start.
5479 | Administration, Planning and Support Services | Completion Of Kuresoi Centre Social Hall | To complete Kuresoi Centre Social Hall | Kuresoi Centre Social Hall completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.302609 35.529459 2587.10009765625 48.900001525878906 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 1730000 | 1730000 | 342500 | Equitable | 1,387,500 | 342500 | 0 | 0 | 0 | 0 | 31 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project was completed but demolished afterwards.
5480 | Administration, Planning and Support Services | Construction Of Kinungi Social Hall and toilets | To construct Kinungi Social Hall and toilets | Kinungi Social Hall and toilets constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Naivasha East | -0.805059, 36.533681 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2024-25 | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 55 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
5481 | Administration, Planning and Support Services | Construction of a Social Hall at Kamere Beach | To construct a Social Hall at Kamere Beach | A Social Hall at Kamere Beach constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Olkaria | -0.815646, 36.322503 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes but not yet done.
5482 | Administration, Planning and Support Services | Renovation of Mogoon Resource Centre and construction of guard house | To rehabilitate Mogoon Resource Centre and construction of guard house to restore functionality | Mogoon Resource Centre and construction of guard house rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Kapkures | -0.309593, 36.02462 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No.
5483 | Administration, Planning and Support Services | Renovation of Mogoon Resource Centre | To rehabilitate Mogoon Resource Centre to restore functionality | Mogoon Resource Centre rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Kapkures | -0.306306 36.000514 0 2000 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Was bought but about quarter has been privatised..
5484 | Administration, Planning and Support Services | Renovation of Social Hall, toilet construction, installation of water and electricity in the social hall | To rehabilitate Social Hall, toilet construction, installation of water and electricity in the social hall to restore functionality | Social Hall, toilet construction, installation of water and electricity in the social hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Kaptembwo | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5485 | Administration, Planning and Support Services | Completion of Elburgon social hall | To complete Elburgon social hall | Elburgon social hall completed | 3110399 | Refurbishment of Buildgs - Oth | Molo | Elburgon | -0.29637, 35.812103 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | - | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 16 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
5486 | Rehabilitation and Equipping of the drop-in centre at Njoro Homecraft | Rehabilitation and Equipping of the drop-in centre at Njoro Homecraft | To rehabilitate Equipping of the drop-in centre at Njoro Homecraft to restore functionality | Equipping of the drop-in centre at Njoro Homecraft rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 60000000 | 9207620 | 9207620 | N/A | N/A | 9207620 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5487 | Administration, Planning and Support Services | Construction Of a Pavilion at Kamukunji Stadium | To construct a Pavilion at Kamukunji Stadium | A Pavilion at Kamukunji Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 50 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5488 | Administration, Planning and Support Services | Fencing Of Dundori Social Hall with Chain Link | To secure Dundori Social Hall with Chain Link through fencing | Dundori Social Hall with Chain Link fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.25294 36.234399 2326.300048828125 51.58000183105469 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 910165 | 910165 | 910165 | Equitable | N/A | 910165 | 0 | 0 | 0 | 0 | 15 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willy samwa supplies. Assessor remarks: Good condition needs maintenance.
5489 | Administration, Planning and Support Services | Construction of a youth empowerment Centre in Eburru-Mbaruk | To construct a youth empowerment Centre in Eburru-Mbaruk | A youth empowerment Centre in Eburru-Mbaruk constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5490 | Construction of backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | Construction of backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | To construct backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | Backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5491 | Construction Of Kamukunji Stadium | Construction Of Kamukunji Stadium | To construct Kamukunji Stadium | Kamukunji Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 742649 | 2564129 | N/A | N/A | 2564129 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5492 | Construction of perimeter wall at Alms house | Construction of perimeter wall at Alms house | To construct perimeter wall at Alms house | Perimeter wall at Alms house constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5493 | Equipping of Alms house, boarding facility, Kitchen, laundry, caretakers house | Equipping of Alms house, boarding facility, Kitchen, laundry, caretakers house | To equip Alms house, boarding facility, Kitchen, laundry, caretakers house with necessary facilities and equipment | Alms house, boarding facility, Kitchen, laundry, caretakers house equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5494 | Establishment of a Sports Centre at Keringet (Phase 1) | Establishment of a Sports Centre at Keringet (Phase 1) | To implement establishment of a sports centre at keringet (phase 1) for youth empowerment and social inclusion | Establishment of a Sports Centre at Keringet (Phase 1) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 124000000 | 38786943.4 | 54374161.4 | N/A | N/A | 54374161.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5495 | Establishment of Keringet high altitude Sports Centre Phase 1B | Establishment of Keringet high altitude Sports Centre Phase 1B | To implement establishment of keringet high altitude sports centre phase 1b for youth empowerment and social inclusion | Establishment of Keringet high altitude Sports Centre Phase 1B completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 10953178 | 3000000 | 8625588 | N/A | N/A | 8625588 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5496 | Establishment of Keringet High altitude Sports Centre | Establishment of Keringet High altitude Sports Centre | To implement establishment of keringet high altitude sports centre for youth empowerment and social inclusion | Establishment of Keringet High altitude Sports Centre completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 20823107 | 0 | 17566228 | N/A | N/A | 17566228 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5497 | Partitioning and equipping of Naivasha Empowerment Centre | Partitioning and equipping of Naivasha Empowerment Centre | To implement partitioning and equipping of naivasha empowerment centre for youth empowerment and social inclusion | Partitioning and equipping of Naivasha Empowerment Centre completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 10000000 | 0 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5498 | Renovation of the Textile Hub for the Nakuru County Youth Engagement Programme | Renovation of the Textile Hub for the Nakuru County Youth Engagement Programme | To rehabilitate the Textile Hub for the Nakuru County Youth Engagement Programme to restore functionality | The Textile Hub for the Nakuru County Youth Engagement Programme rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 4903430 | 4903430 | N/A | N/A | 4903430 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5499 | Administration, Planning and Support Services | Renovation works on solai social (Purchase of chairs and renovation of Solai social hall toilets) | To rehabilitate works on solai social (Purchase of chairs and renovation of Solai social hall toilets) to restore functionality | Works on solai social (Purchase of chairs and renovation of Solai social hall toilets) rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 200000 | 200000 | 550000 | Equitable | N/A | 550000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5500 | Administration, Planning and Support Services | Completion Of Perimeter Wall at The Social Hall in the resource center-Kaptembwo | To complete Perimeter Wall at The Social Hall in the resource center-Kaptembwo | Perimeter Wall at The Social Hall in the resource center-Kaptembwo completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.318516 36.05296 1768.8572483399244 12.072999954223633 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 4000000 | 4000000 | Equitable | 3,828,820 | 4000000 | 0 | 0 | 0 | 0 | 85 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but the gate was in wrong position. Contractor: U40. Assessor remarks: the gate was not well positioned hence it was relocated to an accessible place.
5501 | Administration, Planning and Support Services | Construction Of caretakers house and instalation of water pipes at the caretakers house and toilets Kirathimo Grounds at Gituamba sub location | To construct caretakers house and instalation of water pipes at the caretakers house and toilets Kirathimo Grounds at Gituamba sub location | Caretakers house and instalation of water pipes at the caretakers house and toilets Kirathimo Grounds at Gituamba sub location constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.236888, 36.123915 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes.
5502 | Administration, Planning and Support Services | Levelling And Fencing of Kihingo Play Ground | To implement levelling and fencing of kihingo play ground for youth empowerment and social inclusion | Levelling And Fencing of Kihingo Play Ground completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.443013 35.969212 2274.8 8.800000190734863 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | - | 1500000 | 0 | 0 | 0 | 0 | 64 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Requires fencing, levelling and installation of goalposts.
5503 | Administration, Planning and Support Services | Completion of Fencing Of Kayole Social Hall | To complete Fencing Of Kayole Social Hall | Fencing Of Kayole Social Hall completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.757211, 36.463806 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2021/22 | 2021/22 | 2021/22 | 2928770 | 2963470 | 2848770 | Equitable | 2,928,770 | 2848770 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5504 | Administration, Planning and Support Services | Completion of Fencing Of Kayole Social Hall | To complete Fencing Of Kayole Social Hall | Fencing Of Kayole Social Hall completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.757211, 36.463806 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2021/22 | 2021/22 | 2021/22 | 2180757 | 2963470 | 2963470 | Equitable | 2,928,770 | 2963470 | 0 | 669 | 0 | 669 | 322 | 2962801 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5505 | Administration, Planning and Support Services | Construction of PWDs modern toilets at public facilities in Lakeview Ward | To construct PWDs modern toilets at public facilities in Lakeview Ward | PWDs modern toilets at public facilities in Lakeview Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.733758, 36.435868 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 3019243 | 2820080 | 2820080 | Equitable | 2,820,080 | 2820080 | 0 | 673 | 0 | 673 | 0 | 2819407 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes but not in use.
5506 | Administration, Planning and Support Services | Construction of toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank | To construct toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank | Toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.512937 36.024443 2326.4 6.800000190734863 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 949390 | 949390 | Equitable | - | 949390 | 0 | 655 | 0.1 | 655 | 63 | 948735 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more durable piping's for distribution.
5507 | Administration, Planning and Support Services | Construction of modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School | To construct modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School | Modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.271878, 36.056708 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 1200000 | 1189030 | 1189030 | Equitable | 1,189,030 | 1189030 | 0 | 664 | 0.1 | 664 | 0 | 1188366 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5508 | Administration, Planning and Support Services | Refurbishment Of Railways Football Pitch, Construction of Pavilion/Shade, Goal Posts & Fencing | To implement refurbishment of railways football pitch, construction of pavilion/shade, goal posts & fencing for youth empowerment and social inclusion | Refurbishment Of Railways Football Pitch, Construction of Pavilion/Shade, Goal Posts & Fencing completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.278134 36.074304 1849.9000244140625 9 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 53 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: ..
5509 | Administration, Planning and Support Services | Refurbishment of Railways Pitch (Phase two); changing rooms, fencing & pavilion shed 50pax) | To implement refurbishment of railways pitch (phase two); changing rooms, fencing & pavilion shed 50pax) for youth empowerment and social inclusion | Refurbishment of Railways Pitch (Phase two); changing rooms, fencing & pavilion shed 50pax) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 858699 | 858699 | 858699 | Equitable | N/A | 858699 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5510 | Administration, Planning and Support Services | Fencing of Kariandusi playground (Maai mahiu stadium) | To secure Kariandusi playground (Maai mahiu stadium) through fencing | Kariandusi playground (Maai mahiu stadium) fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 789 | 0 | 789 | 0 | 2499211 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5511 | Administration, Planning and Support Services | Fencing Of Maai Mahiu Social Hall | To secure Maai Mahiu Social Hall through fencing | Maai Mahiu Social Hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.978956, 36.585812 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 839250 | Equitable | 1,660,750 | 839250 | 0 | 789 | 0 | 789 | 0 | 2499211 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5512 | Administration, Planning and Support Services | Grading, Levelling and Installation Of Goal Post In Kariandusi Playground | To implement grading, levelling and installation of goal post in kariandusi playground for youth empowerment and social inclusion | Grading, Levelling and Installation Of Goal Post In Kariandusi Playground completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 0 | 784050 | Equitable | 3,636,850 | 784050 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5513 | Administration, Planning and Support Services | Grading, levelling Kichwa ECDE playground | To implement grading, levelling kichwa ecde playground for youth empowerment and social inclusion | Grading, levelling Kichwa ECDE playground completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.122375 36.008515 1812.7 4.400000095367432 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 1022740 | 1022740 | 1022740 | Equitable | N/A | 1022740 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not. Assessor remarks: Not yet started.
5514 | Administration, Planning and Support Services | Renovation of Lanet Social Hall toilets and connection to the sewer | To rehabilitate Lanet Social Hall toilets and connection to the sewer to restore functionality | Lanet Social Hall toilets and connection to the sewer rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293847, 36.11813 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Non.
5515 | Administration, Planning and Support Services | Construction of a Sanitation Block, water connection and installation of floodlights at Jewathu Stadium | To construct a Sanitation Block, water connection and installation of floodlights at Jewathu Stadium | A Sanitation Block, water connection and installation of floodlights at Jewathu Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.333229 35.947302 2147.7001953125 4.48799991607666 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 7000000 | 0 | 3391833 | Equitable | N/A | 3391833 | 0 | 662 | 100 | 662 | 652 | -662 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: N/ A. Assessor remarks: Manhole covers missing.
5516 | Administration, Planning and Support Services | Construction of PWDs toilets within Olkaria Ward | To construct PWDs toilets within Olkaria Ward | PWDs toilets within Olkaria Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.819481 36.32143 1931.300048828125 68.4000015258789 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 73 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes if finished. Assessor remarks: The structure is complete but no septic pit.
5517 | Administration, Planning and Support Services | Construction Of Perimeter Wall In Rongai Stadium | To construct Perimeter Wall In Rongai Stadium | Perimeter Wall In Rongai Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.173526 35.860517 1868.199951171875 54.09400177001953 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2019/20 | 2019/20 | N/A | 1899318 | 286566.52 | 286566.52 | Equitable | 286,567 | 286566.52 | 0 | 0 | 0 | 0 | 314 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
5518 | Administration, Planning and Support Services | Construction of Youth friendly centre in Viwandani | To construct Youth friendly centre in Viwandani | Youth friendly centre in Viwandani constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.712569, 36.435681 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 0 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 91 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
5519 | Administration, Planning and Support Services | Fencing Of Viwandani Social Hall | To secure Viwandani Social Hall through fencing | Viwandani Social Hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.710203, 36.433009 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 0 | 2500000 | Equitable | - | 2500000 | 0 | 0 | 0 | 0 | 28 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
5520 | Administration, Planning and Support Services | Installation and fencing of Artificial Turf in Viwandani Ward | To install and fencing of Artificial Turf in Viwandani Ward | And fencing of Artificial Turf in Viwandani Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.701181 36.426027 1889.699951171875 1.3339999914169312 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
5521 | Administration, Planning and Support Services | Rehabilitation and Fencing of site play ground | To rehabilitate Fencing of site play ground to restore functionality | Fencing of site play ground rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.715344 36.437888 1915.0999755859375 44.79999923706055 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Assessor remarks: Yet to start.
5522 | Administration, Planning and Support Services | Renovation Of Studio And Amphitheatre In Industrial Area | To rehabilitate Studio And Amphitheatre In Industrial Area to restore functionality | Studio And Amphitheatre In Industrial Area rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71298 36.435601 1906.300048828125 20.15399932861328 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2020/21 | 2020/21 | N/A | 1999200 | 3000000 | 3479200 | Equitable | - | 3479200 | 0 | 0 | 0 | 0 | 1329 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Complete.
5523 | Administration, Planning and Support Services | Renovation and Equipping of London Social Hall | To rehabilitate Equipping of London Social Hall to restore functionality | Equipping of London Social Hall rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.27499, 36.049414 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 9800000 | 0 | 4562050 | Equitable | N/A | 4562050 | 0 | 0 | 0 | 0 | 41 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5524 | Equipping of Lakeview baby day care centre (beds and beddings and Washing machine) | Equipping of Lakeview baby day care centre (beds and beddings and Washing machine) | To equip Lakeview baby day care centre (beds and beddings and Washing machine) with necessary facilities and equipment | Lakeview baby day care centre (beds and beddings and Washing machine) equipped | 3110999 | N/A | HQ | HQ | -0.173672, 35.862823 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5525 | Administration, Planning and Support Services | Purchase of assistive devices for PLWDs | To procure assistive devices for PLWDs | Assistive devices for PLWDs procured | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Shabab | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | N/A | 591031 | 591031 | 591031 | Equitable | - | 591031 | 0 | 0 | 0 | 0 | 96 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5526 | Administration, Planning and Support Services | Purchase and supply of youth and women empowerment equipments within Bahati ward | To procure and supply youth and women empowerment equipments within Bahati ward | Youth and women empowerment equipments within Bahati ward procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Bahati | -0.15645, 36.146429 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5527 | Administration, Planning and Support Services | Supply of equipment for Youth and women empowerment | To implement supply of equipment for youth and women empowerment for youth empowerment and social inclusion | Supply of equipment for Youth and women empowerment completed | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Bahati | -0.156446, 36.14644 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 910165 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5528 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Biashara-Naivasha | -0.722885, 36.475212 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2025 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes.
5529 | Administration, Planning and Support Services | Equipping of Bondeni Fitness Center Gym | To equip Bondeni Fitness Center Gym with necessary facilities and equipment | Bondeni Fitness Center Gym equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Biashara-Nakuru | -0.295808, 36.079403 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5530 | Administration, Planning and Support Services | Purchase and supply of youth and women empowerment equipments in Biashara Nakuru | To procure and supply youth and women empowerment equipments in Biashara Nakuru | Youth and women empowerment equipments in Biashara Nakuru procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Biashara-Nakuru | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2800000 | 0 | 2800000 | Equitable | N/A | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5531 | Administration, Planning and Support Services | Purchase of assistive devices for people living with disabilities | To procure assistive devices for people living with disabilities | Assistive devices for people living with disabilities procured | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Dundori | -0.262969, 36.187487 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
5532 | Administration, Planning and Support Services | Youth and women empowerment | To implement youth and women empowerment for youth empowerment and social inclusion | Youth and women empowerment completed | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Dundori | -0.267554 36.184283 1965.9000244140625 19 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5533 | Administration, Planning and Support Services | Purchase and supply of empowerment equipments in Mbaruk ward | To procure and supply empowerment equipments in Mbaruk ward | Empowerment equipments in Mbaruk ward procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru-Mbaruk | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2063671 | 2063671 | 2063671 | Equitable | N/A | 2063671 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5534 | Administration, Planning and Support Services | Purchase and supply of motorbikes of over 160 cc 5 speed manual for CHPs | To procure and supply motorbikes of over 160 cc 5 speed manual for CHPs | Motorbikes of over 160 cc 5 speed manual for CHPs procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru-Mbaruk | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5535 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Elementaita | -0.566265 36.117361 1961.0999755859375 11.5 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5536 | Administration, Planning and Support Services | Purchase and distribution of youth,PLWDs and women equipments | To procure and distribution of youth,PLWDs and women equipments | And distribution of youth,PLWDs and women equipments procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Flamingo | -0.302752 36.073162 1798.300048828125 39.14099884033203 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3200000 | 3000000 | 3200000 | Equitable | N/A | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: The structures were vandalised. Does Not exist.
5537 | Administration, Planning and Support Services | Purchase Of Sport Equipment in Flamingo Ward | To procure Sport Equipment in Flamingo Ward | Sport Equipment in Flamingo Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Flamingo | -0.308232 36.079252 1789.4000244140625 38.18600082397461 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 399960 | 399960 | 399960 | Equitable | - | 399960 | 0 | 0 | 0 | 0 | 59 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well done. Operational.
5538 | Development Of Socio-Cultural Diversity, Economic Empowerment and Responsible Gaming | Equipping of the production Hub at Menengai Social Hall | To equip the production Hub at Menengai Social Hall with necessary facilities and equipment | The production Hub at Menengai Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 20000000 | 2000000 | 1767300 | Equitable | 2,964,000 | 1767300 | 0 | 0 | 0 | 0 | 184 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5539 | Development Of Socio-Cultural Diversity, Economic Empowerment and Responsible Gaming | Purchase of equipment for Menengai Textile | To procure equipment for Menengai Textile | Equipment for Menengai Textile procured | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 7000000 | 4000000 | 4000000 | Equitable | 2,964,000 | 4000000 | 0 | 0 | 0 | 0 | 184 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5540 | Administration, Planning and Support Services | Equipping of YMCA Social Hall (with chairs, tables and computers) including electricity installation | To equip YMCA Social Hall (with chairs, tables and computers) including electricity installation with necessary facilities and equipment | YMCA Social Hall (with chairs, tables and computers) including electricity installation equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Hells Gate | -0.778398, 36.429487 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1297734 | 1297734 | 1297734 | Equitable | N/A | 1297734 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet.
5541 | Administration, Planning and Support Services | Youth and women empowerment | To implement youth and women empowerment for youth empowerment and social inclusion | Youth and women empowerment completed | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Kabatini | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5542 | Administration, Planning and Support Services | Purchase and Supply of Youth and women equipments for empowerment | To procure and supply Youth and women equipments for empowerment | Youth and women equipments for empowerment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Subukia | Kabazi | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5543 | Administration, Planning and Support Services | Equipping of Mogoon Resource Centre | To equip Mogoon Resource Centre with necessary facilities and equipment | Mogoon Resource Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Kapkures | -0.324324, 36.036613 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2022/23 | 2022/23 | 2024/25 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 316 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not. Viable: Viable. But yet tobe implemented.
5544 | Administration, Planning and Support Services | Equiping of sports/arts Teams in Kaptembwa ward | To implement equiping of sports/arts teams in kaptembwa ward for youth empowerment and social inclusion | Equiping of sports/arts Teams in Kaptembwa ward completed | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Kaptembwo | -0.302648 36.04481 1806.8267321810167 3.9230000972747803 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nakuru County. Assessor remarks: Viable.
5545 | Administration, Planning and Support Services | Purchase of youth and women Equipments for empowerment | To procure youth and women Equipments for empowerment | Youth and women Equipments for empowerment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi south | Keringet | -0.428183 35.688338 2687.400146484375 4.699999809265137 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1071214 | 1071214 | 1071214 | Equitable | N/A | 1071214 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5546 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Kihingo | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2141650 | 0 | 1491650 | Equitable | N/A | 1491650 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5547 | Administration, Planning and Support Services | Purchase of youth and women Equipments for empowerment | To procure youth and women Equipments for empowerment | Youth and women Equipments for empowerment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi south | Kiptagich | -0.572797, 35.613065 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | Not yet started | 3450117 | 2850117 | 3450117 | Equitable | N/A | 3450117 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it is viable but not yet started. Contractor: Don't know.
5548 | Administration, Planning and Support Services | Purchase of youth and women Equipments for empowerment | To procure youth and women Equipments for empowerment | Youth and women Equipments for empowerment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Kiptororo | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5549 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Kivumbini | -0.303968, 36.082873 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | june 2025 | 3550255 | 3550255 | 3750255 | Equitable | N/A | 3750255 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes.
5550 | Administration, Planning and Support Services | Purchase Of Sport Equipment in Kivumbini Ward | To procure Sport Equipment in Kivumbini Ward | Sport Equipment in Kivumbini Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Kivumbini | -0.297685 36.080702 1790.699951171875 56.099998474121094 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 93 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: functional.
5551 | Administration, Planning and Support Services | Purchase and distribution of youth and women equipments | To procure and distribution of youth and women equipments | And distribution of youth and women equipments procured | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Lake view | -0.709293 36.425609 1898.4545553887665 57.90182673181159 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 2000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and operated.
5552 | Administration, Planning and Support Services | Purchase and supply of youth and women empowerment equipments in Lanet umoja | To procure and supply youth and women empowerment equipments in Lanet umoja | Youth and women empowerment equipments in Lanet umoja procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Lanet-Umoja | -0.25168, 36.159552 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 7926114 | 0 | 7926114.3 | Equitable | N/A | 7926114.3 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5553 | Administration, Planning and Support Services | Purchase Of Sport Equipment in London Ward | To procure Sport Equipment in London Ward | Sport Equipment in London Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | London | -0.279692, 36.070369 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 370515 | 0 | 370515 | Equitable | - | 370515 | 0 | 0 | 0 | 0 | 82 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2023 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
5554 | Administration, Planning and Support Services | Purchase of Sports Equipment | To procure Sports Equipment | Sports Equipment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | London | -0.279475 36.030008 1877.800048828125 48 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 0 | 0 | 0 | 82 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yea. Assessor remarks: Machines available in good working condition.
5555 | Administration, Planning and Support Services | Purchase of youth and women Equipments for empowerment | To procure youth and women Equipments for empowerment | Youth and women Equipments for empowerment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | London | -0.279475 36.030008 1877.800048828125 48 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 82 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yea. Assessor remarks: Machines available in good working condition.
5556 | Administration, Planning and Support Services | Purchase and supply of youth and women empowerment equipments | To procure and supply youth and women empowerment equipments | Youth and women empowerment equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Maai Mahiu | -0.885078, 36.499483 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
5557 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
5558 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Molo | Mariashoni | -0.40217, 35.963435 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 37895 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5559 | Administration, Planning and Support Services | Purchase and Supply of Youth,women and PLWD equipments | To procure and supply Youth,women and PLWD equipments | Youth,women and PLWD equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Mau Narok | -0.600012 36.007202 0 141 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 1400000 | Equitable | N/A | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs upgrading.
5560 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Mauche | -0.497747 35.960893 2477.6000000000004 12.399999618530273 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 42281 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
5561 | Administration, Planning and Support Services | Equiping of Menengai west youth resource centre | To implement equiping of menengai west youth resource centre for youth empowerment and social inclusion | Equiping of Menengai west youth resource centre completed | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.246617, 36.013825 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2025/26 | 547833 | 547833 | 547833 | Equitable | N/A | 547833 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Not yet. Viable: Not yet.
5562 | Administration, Planning and Support Services | Purchase and Supply of Youth and women equipments for empowerment | To procure and supply Youth and women equipments for empowerment | Youth and women equipments for empowerment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
5563 | Administration, Planning and Support Services | Purchase and supply of Sport equipments and tournerment | To procure and supply Sport equipments and tournerment | Sport equipments and tournerment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.296327, 35.956558 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated.
5564 | Administration, Planning and Support Services | Purchase and Supply of Youth and women equipments for empowerment | To procure and supply Youth and women equipments for empowerment | Youth and women equipments for empowerment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.255342 35.873297 1963.199951171875 34.70000076293945 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha Barabara program. Assessor remarks: Complete.
5565 | Administration, Planning and Support Services | Purchase and distribution of sports equipment | To procure and distribution of sports equipment | And distribution of sports equipment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Naivasha East | -0.800935, 36.533308 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2025 | 1454995 | 1454995 | 1454995 | Equitable | N/A | 1454995 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5566 | Administration, Planning and Support Services | Purchase and distribution of youth and women equipments for empowerment- Nakuru East Ward | To procure and distribution of youth and women equipments for empowerment- Nakuru East Ward | And distribution of youth and women equipments for empowerment- Nakuru East Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.292119, 36.113682 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | 2024/2025 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5567 | Administration, Planning and Support Services | Purchase and supply of sports equipments | To procure and supply sports equipments | Sports equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 90 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
5568 | Administration, Planning and Support Services | Purchase and supply of youth and women equipments | To procure and supply youth and women equipments | Youth and women equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3818468 | 1618468 | 3818468 | Equitable | N/A | 3818468 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
5569 | Administration, Planning and Support Services | Purchase Of Sport Equipment in Olkaria Ward | To procure Sport Equipment in Olkaria Ward | Sport Equipment in Olkaria Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.830138, 36.338593 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | - | 3000000 | 0 | 0 | 0 | 0 | 90 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5570 | Administration, Planning and Support Services | Purchase and supply of youth and women empowerment equipment | To procure and supply youth and women empowerment equipment | Youth and women empowerment equipment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Rhonda | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 4500000 | 0 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5571 | Administration, Planning and Support Services | Purchase Of Sport Equipment in Rhonda Ward | To procure Sport Equipment in Rhonda Ward | Sport Equipment in Rhonda Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Rhonda | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 700000 | 700000 | 700000 | Equitable | - | 700000 | 0 | 0 | 0 | 0 | 84 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5572 | Administration, Planning and Support Services | Purchase of youth and women empowerment Equipments | To procure youth and women empowerment Equipments | Youth and women empowerment Equipments procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Rhonda | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 5439811 | 4439811 | 4439811 | Equitable | N/A | 4439811 | 0 | 0 | 0 | 0 | 37900 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5573 | Administration, Planning and Support Services | Purchase Of Sports Equipment & Mechanic Equipment for Shabab Ward | To procure Sports Equipment & Mechanic Equipment for Shabab Ward | Sports Equipment & Mechanic Equipment for Shabab Ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Shabab | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 114 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5574 | Administration, Planning and Support Services | Purchase of youth and women Equipments for empowerment | To procure youth and women Equipments for empowerment | Youth and women Equipments for empowerment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Shabab | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5575 | Administration, Planning and Support Services | Purchase and Supply of Sports equipment | To procure and supply Sports equipment | Sports equipment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Soin | -0.110025 35.94125 0 1700 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs alot of repair,Needs more toilets for staffs.
5576 | Administration, Planning and Support Services | Purchase and Supply of women empowerment equipments | To procure and supply women empowerment equipments | Women empowerment equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Soin | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1826050 | 1826050 | 1826050 | Equitable | N/A | 1826050 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5577 | Administration, Planning and Support Services | Purchase of Sport equipments | To procure Sport equipments | Sport equipments procured | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Solai | -0.027433 36.129588 0 1100 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 662232 | 662232 | 662232 | Equitable | N/A | 662232 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fence is in good condition.
5578 | Administration, Planning and Support Services | Purchase and Supply of Youth equipment | To procure and supply Youth equipment | Youth equipment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 2480503 | 1500000 | 2480503 | Equitable | N/A | 2480503 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
5579 | Administration, Planning and Support Services | Women,youth and PLWD empowerment | To implement women,youth and plwd empowerment for youth empowerment and social inclusion | Women,youth and PLWD empowerment completed | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Visoi | N/A | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5580 | Administration, Planning and Support Services | Equipping Of ICT Hub | To equip ICT Hub with necessary facilities and equipment | ICT Hub equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Viwandani | -0.715125 36.432547 0 300 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 1999200 | 1999200 | Equitable | N/A | 1999200 | 0 | 0 | 0 | 0 | 42640 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
5581 | Administration, Planning and Support Services | Purchase and Supply of Youth and women equipments for empowerment | To procure and supply Youth and women equipments for empowerment | Youth and women equipments for empowerment procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4587 | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | YOUTH, SPORTS, GENDER, SOCIAL SERVICES AND INCLUSIVITY | N/A | 2024/25 | 2024/25 | N/A | 1225000 | 0 | 1225000 | Equitable | N/A | 1225000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
5582 | Cabro paving and installation of street furniture and streetlighting from GG Junction-GTI | Cabro paving and installation of street furniture and streetlighting from GG Junction-GTI | To implement cabro paving and installation of street furniture and streetlighting from gg junction-gti for improved service delivery | Cabro paving and installation of street furniture and streetlighting from GG Junction-GTI completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4588 | GILGIL MUNICIPALITY | GILGIL MUNICIPALITY | N/A | 2024/25 | 2024/25 | 2024/25 | 30000000 | 0 | 23448778 | N/A | N/A | 23448778 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5583 | Keep Left Center bus park development, on-street parking cabro paving | Keep Left Center bus park development, on-street parking cabro paving | To implement keep left center bus park development, on-street parking cabro paving for improved service delivery | Keep Left Center bus park development, on-street parking cabro paving completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4589 | MOLO MUNICIPALITY | MOLO MUNICIPALITY | N/A | 2024/25 | 2024/2025 | 2024/2025 | 12000000 | 12000000 | 12000000 | N/A | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5584 | Molo CBD NMT, street furniture and beautification | Molo CBD NMT, street furniture and beautification | To implement molo cbd nmt, street furniture and beautification for improved service delivery | Molo CBD NMT, street furniture and beautification completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4589 | MOLO MUNICIPALITY | MOLO MUNICIPALITY | N/A | 2024/25 | 2024/2025 | 2024/2025 | 12000000 | 12000000 | 12000000 | N/A | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5585 | Administration, Planning and Support Services | Construction Of Official Residence For The Deputy Governor | To construct Official Residence For The Deputy Governor | Official Residence For The Deputy Governor constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | N/A | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2019/20 | 2019/20 | N/A | 30000000 | 30000000 | 30000000 | Equitable | N/A | 30000000 | 0 | 0 | 0 | 0 | 20000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5586 | Construction Of Non-Residential Building In Mlimani | Construction Of Non-Residential Building In Mlimani | To construct Non-Residential Building In Mlimani | Non-Residential Building In Mlimani constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2019/20 | 2019/20 | 2019/20 | 51605318 | 42520758 | 67520758 | N/A | N/A | 67520758 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5587 | Administration, Planning and Support Services | Research and Publication | To implement research and publication for improved service delivery | Research and Publication completed | 3111403 | Research | HQ | HQ | N/A | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2019/20 | 2019/20 | N/A | 6534008.15 | 6534008.15 | 6534008.15 | Equitable | N/A | 6534008.15 | 0 | 2900000 | 44.4 | 2900000 | 3634008 | 3634008.15 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5588 | Administration, Planning and Support Services | Purchase Of Land For Construction Of Official Residence For The Deputy Governor | To acquire land for Construction Of Official Residence For The Deputy Governor | Land for Construction Of Official Residence For The Deputy Governor acquired | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2019/20 | 2019/20 | N/A | 20000000 | 20000000 | 20000000 | Equitable | Equitable | 20000000 | 0 | 0 | 0 | 0 | 20000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5589 | Administration, Planning and Support Services | Construction Of Sub County Office - Keringet | To construct Sub County Office - Keringet | Sub County Office - Keringet constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2018/19 | 2018/19 | 2018/19 | 16605318 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5590 | Administration, Planning and Support Services | Construction Of Sub County Office | To construct Sub County Office | Sub County Office constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2018/19 | 2018/19 | 2018/19 | 16605318 | 16605318 | 16605318 | Equitable | N/A | 16605318 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5591 | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | To implement county debt management (as per the county medium term debt management strategy paper) for improved service delivery | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2020/21 | 2020/21 | 800000000 | 324894509.72 | 284894509.72 | N/A | N/A | 284894509.72 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5592 | County Spatial Plan | County Spatial Plan | To implement county spatial plan for improved service delivery | County Spatial Plan completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 116121615 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5593 | Deposit account (Retention fund) | Deposit account (Retention fund) | To implement deposit account (retention fund) for improved service delivery | Deposit account (Retention fund) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 160682696.5 | 166682696.5 | 166682696.5 | N/A | N/A | 166682696.5 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5594 | Kenya Devolution Support Programme Level II | Kenya Devolution Support Programme Level II | To implement development programme activities under Kenya Devolution Support Programme Level II | Programme activities completed | 2630201 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 100974396 | 100974396 | 0 | N/A | N/A | 0 | 100974396 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5595 | Construction of County Treasury | Construction of County Treasury | To construct County Treasury | County Treasury constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 500000000 | 36995901 | 36995901 | N/A | N/A | 36995901 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5596 | Rehabilitation of old Town Hall | Rehabilitation of old Town Hall | To rehabilitate old Town Hall to restore functionality | Old Town Hall rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 7000000 | 7000000 | N/A | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5597 | Renovation of County Chambers | Renovation of County Chambers | To rehabilitate County Chambers to restore functionality | County Chambers rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 8123205 | 8123205 | 8123205 | N/A | N/A | 8123205 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5598 | Development of Audit Software | Development of Audit Software | To develop Audit Software | Audit Software developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 25000000 | 10274286.88 | 10274286.88 | N/A | N/A | 10274286.88 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5599 | Development of Project Implementation Management System | Development of Project Implementation Management System | To develop Project Implementation Management System | Project Implementation Management System developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 15000000 | 12000000 | 12000000 | N/A | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5600 | Development of Revenue Software | Development of Revenue Software | To develop Revenue Software | Revenue Software developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2020/21 | 2020/21 | 100000000 | 85000000 | 125000000 | N/A | N/A | 125000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5601 | Counterpart Funding (Leasing of Land for KDSP Level II) | Counterpart Funding (Leasing of Land for KDSP Level II) | To implement counterpart funding (leasing of land for kdsp level ii) for improved service delivery | Counterpart Funding (Leasing of Land for KDSP Level II) completed | 3130199 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 9000000 | 9000000 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5602 | Valuation of Assets | Valuation of Assets | To implement valuation of assets for improved service delivery | Valuation of Assets completed | 4130299 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4562 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 50000000 | 1480000 | 1480000 | N/A | N/A | 1480000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5603 | Renovation of Board offices | Renovation of Board offices | To rehabilitate Board offices to restore functionality | Board offices rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2019/20 | 2019/20 | 2019/20 | 1817929 | 1810000 | 1810000 | N/A | N/A | 1810000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5604 | Reroofing of Office, Installation of metal grills and Refurbishment of offices | Reroofing of Office, Installation of metal grills and Refurbishment of offices | To implement reroofing of office, installation of metal grills and refurbishment of offices for improved service delivery | Reroofing of Office, Installation of metal grills and Refurbishment of offices completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2020/21 | 2020/21 | 2020/21 | 3300000 | 0 | 1800000 | N/A | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5605 | Installation of Bulk Filing System | Installation of Bulk Filing System | To install Bulk Filing System | Bulk Filing System installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2020/21 | 2020/21 | 2020/21 | 1700000 | 5000000 | 3200000 | N/A | N/A | 3200000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5606 | Development of Online Application Platform | Development of Online Application Platform | To develop Online Application Platform | Online Application Platform developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5607 | Health Curative and Rehabilitative Services | Conditional Fund for Leasing of Medical Equipment | To implement conditional fund for leasing of medical equipment for access to quality healthcare services | Conditional Fund for Leasing of Medical Equipment completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2020/21 | 2020/21 | 132021277 | 132021277 | 0 | Grant | Grant | 0 | 263936171 | 124723404 | 94.5 | 124723404 | 0 | 7297873 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5608 | Health Curative and Rehabilitative Services | Conditional Health Grant For Covid-19 Emergency Response | To implement conditional health grant for covid-19 emergency response for access to quality healthcare services | Conditional Health Grant For Covid-19 Emergency Response completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 201073000 | 0 | 0 | N/A | N/A | 0 | 201073000 | 0 | 0 | 0 | 201073000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5609 | Preventive and Promotive Health Services | DANIDA Capital Transfers to Health Centres and Dispensaries | To implement danida capital transfers to health centres and dispensaries for access to quality healthcare services | DANIDA Capital Transfers to Health Centres and Dispensaries completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2020/21 | N/A | 29790000 | 29846050 | 0 | Grant | Grant | 0 | 71187181.85 | 20068710 | 67.2 | 20068710 | 19115250 | 9777340 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5610 | Preventive and Promotive Health Services | World Bank Transforming Health Systems for Universal Care (THS-UC) | To implement development programme activities under World Bank Transforming Health Systems for Universal Care (THS-UC) | Programme activities completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2018/19 | 2018/19 | 95036351 | 40503420.5 | 0 | Grant | Grant | 0 | 109673702 | 79342370 | 195.9 | 79342370 | 62835 | -38838949.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5611 | Preventive and Promotive Health Services | rehabilitation of kabatini health centre ( painting works) | To rehabilitate kabatini health centre ( painting works) to restore functionality | Kabatini health centre ( painting works) rehabilitated | 3110101 | N/A | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 399350 | 79.9 | 399350 | 500000 | 100650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
5612 | Preventive and Promotive Health Services | Completion of youth friendly center at Rhonda clinic | To complete youth friendly center at Rhonda clinic | Youth friendly center at Rhonda clinic completed | 3110101 | N/A | Nakuru West | Kaptembwo | -0.304752, 36.055188 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999530 | 100 | 1999530 | 2000000 | 470 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: PEZINA ENTERPRISES. Assessor remarks: Complete but has defective tiles needs renovation.
5613 | Preventive and Promotive Health Services | Equipping of youth friendly center at Rhonda clinic | To equip youth friendly center at Rhonda clinic with necessary facilities and equipment | Youth friendly center at Rhonda clinic equipped | 3110101 | N/A | Nakuru West | Kaptembwo | -0.304752, 36.055188 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: PEZINA ENTERPRISES. Assessor remarks: Complete but has defective tiles needs renovation.
5614 | Preventive and Promotive Health Services | Completion and equipping of Sinendet dispensary | To complete and equip Sinendet dispensary | Sinendet dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676255 35.657373 2458.322998046875 8.564000129699707 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999770 | 100 | 999770 | 230 | 230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: done.
5615 | Preventive and Promotive Health Services | Completion of construction of maternity wing at Bahati rural heath centre | To complete construction of maternity wing at Bahati rural heath centre | Construction of maternity wing at Bahati rural heath centre completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.153643, 36.153584 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999583 | 100 | 3999583 | 1000000 | 417 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
5616 | Preventive and Promotive Health Services | Purchase and installation and commissioning of a digital X-Ray machine for Bahati Sub-County hospital | To procure and install and commissioning of a digital X-Ray machine for Bahati Sub-County hospital | And commissioning of a digital X-Ray machine for Bahati Sub-County hospital procured and installed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.170153, 36.123563 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 4913793 | 98.3 | 4913793 | 86207 | 86207 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Oultral sound machine. Viable: Yes. Assessor remarks: In good working conditions.
5617 | Preventive and Promotive Health Services | Construction of an outpatient Unit at Mwariki Health Centre and installation of electricity | To construct an outpatient Unit at Mwariki Health Centre and installation of electricity | An outpatient Unit at Mwariki Health Centre and installation of electricity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.349277, 36.055207 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2935680 | 97.9 | 2935680 | 64320 | 64320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well completed.
5618 | Preventive and Promotive Health Services | Kigonor dispensary septic tank | To implement kigonor dispensary septic tank for access to quality healthcare services | Kigonor dispensary septic tank completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.324324 36.036613 0 2000 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999970 | 100 | 999970 | 0 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: No. Contractor: NiCLAW BUILDERS. Assessor remarks: Good.
5619 | Preventive and Promotive Health Services | Construction of Giachonge Dispensary (outpatient and toilet) | To construct Giachonge Dispensary (outpatient and toilet) | Giachonge Dispensary (outpatient and toilet) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.237126, 36.167582 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2023/2024 | 4000000 | 4000000 | 4000000 | Equitable | Ward Fund | 4000000 | 0 | 2845463 | 71.1 | 2845463 | 1135129 | 1154537 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
5620 | Preventive and Promotive Health Services | Rehabilitation of 5 toilets at kimathi Estate | To rehabilitate 5 toilets at kimathi Estate to restore functionality | 5 toilets at kimathi Estate rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.303736, 36.078702 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/2020 | 8500000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5699900 | 95 | 5699900 | 300100 | 300100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use and in good condition.
5621 | Preventive and Promotive Health Services | Renovation of post theater ward at Gilgil sub county hospital | To rehabilitate post theater ward at Gilgil sub county hospital to restore functionality | Post theater ward at Gilgil sub county hospital rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.504913, 36.322796 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999470 | 100 | 1999470 | 530 | 530 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mbiwa construction limited. Assessor remarks: In good state.
5622 | Health Curative and Rehabilitative Services | Completion of outpatient block at Elburgon Sub Sounty hospital | To complete outpatient block at Elburgon Sub Sounty hospital | Outpatient block at Elburgon Sub Sounty hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 200000000 | 12336169 | 12336169 | N/A | N/A | 12336169 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5623 | Health Curative and Rehabilitative Services | Construction of buildings -Inpatient complex - PGH (FIF) | To construct buildings -Inpatient complex - PGH (FIF) | Buildings -Inpatient complex - PGH (FIF) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 600000000 | 150000000 | 0 | FIF | FIF | 0 | 150000000 | 3321916 | 2.2 | 3321916 | 26043808 | 146678084 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5624 | Health Curative and Rehabilitative Services | Construction of buildings - outpatients complex (FIF) -PGH | To construct buildings - outpatients complex (FIF) -PGH | Buildings - outpatients complex (FIF) -PGH constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 550000000 | 0 | 0 | FIF | FIF | 0 | 94999999 | 3321916 | 0 | 3321916 | 26043808 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5625 | Health Curative and Rehabilitative Services | Construction of buildings - Outpatients complex (PGH) | To construct buildings - Outpatients complex (PGH) | Buildings - Outpatients complex (PGH) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2020/21 | N/A | 650000000 | 265372832 | 110000000 | N/A | N/A | 110000000 | 365745664 | 3956192 | 1.5 | 3956192 | 26043808 | 261416640 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5626 | Preventive and Promotive Health Services | Construction of Level 4 Hospital in Maai Mahiu | To construct Level 4 Hospital in Maai Mahiu | Level 4 Hospital in Maai Mahiu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 200000000 | 85000000 | 0 | Equitable | N/A | 0 | 154528397 | 750000 | 0.9 | 750000 | 0 | 84250000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5627 | Preventive and Promotive Health Services | Construction of OPD at Naivasha Subcounty hospital - Counterpart funding | To construct OPD at Naivasha Subcounty hospital - Counterpart funding | OPD at Naivasha Subcounty hospital - Counterpart funding constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 31262065 | 31262065 | 31262065 | Equitable | N/A | 31262065 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5628 | Health Curative and Rehabilitative Services | Other Developments - (FIF Facilities) | To implement other developments - (fif facilities) for access to quality healthcare services | Other Developments - (FIF Facilities) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 38000000 | 30000000 | 0 | FIF | N/A | 0 | 30000000 | 10122860 | 33.7 | 10122860 | 70000000 | 19877140 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5629 | Preventive and Promotive Health Services | Upgrading of Molo Sub County Hospital | To upgrade Molo Sub County Hospital through tarmacking for improved road connectivity | Molo Sub County Hospital tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 40000000 | 19783570 | 19783570 | Equitable | N/A | 19783570 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5630 | Preventive and Promotive Health Services | Completion and equipping youth health friendly center | To complete and equip youth health friendly center | Youth health friendly center completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.30474 36.055271 1794.3205995676594 60 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 496000 | 16.5 | 496000 | 500055 | 2504000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: VILALOXA STORES. Assessor remarks: It's fully equipped.
5631 | Preventive and Promotive Health Services | Construction of laboratory and comprehensive care center and Renovation of theater room and new born unit at rhonda clinic in kaptembwo | To construct laboratory and comprehensive care center and Renovation of theater room and new born unit at rhonda clinic in kaptembwo | Laboratory and comprehensive care center and Renovation of theater room and new born unit at rhonda clinic in kaptembwo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
5632 | Preventive and Promotive Health Services | Renovation of theater room and laboratory at Rhoda clinic | To rehabilitate theater room and laboratory at Rhoda clinic to restore functionality | Theater room and laboratory at Rhoda clinic rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.305152, 36.055388 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998450 | 99.9 | 2998450 | 1550 | 1550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes it met the needs of residents. Contractor: U11. Assessor remarks: Complete, leaking roof and defective tiles needs renovation.
5633 | Preventive and Promotive Health Services | Completion of Cheptuech Dispensary | To complete Cheptuech Dispensary | Cheptuech Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.656364 35.601863 2385.7000000000003 15.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 899416 | 899416 | 899416 | Equitable | Equitable | 899416 | 0 | 1021185 | 113.5 | 1021185 | 899416 | -121769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but needs not yet met. Assessor remarks: Need to be equipped.
5634 | Preventive and Promotive Health Services | Completion of githima dispensary | To complete githima dispensary | Githima dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.357906, 35.55465 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 637784 | 637784 | 637784 | Equitable | Equitable | 637784 | 0 | 543281 | 85.2 | 543281 | 93806 | 94503 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires minor repair.
5635 | Preventive and Promotive Health Services | Maai Mahiu Health Centre-Construction of staff houses | To implement maai mahiu health centre-construction of staff houses for access to quality healthcare services | Maai Mahiu Health Centre-Construction of staff houses completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.976952, 36.584984 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998085 | 99.9 | 2998085 | 1915 | 1915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
5636 | Preventive and Promotive Health Services | Kasarani dispensary staff house repair and septic system | To implement kasarani dispensary staff house repair and septic system for access to quality healthcare services | Kasarani dispensary staff house repair and septic system completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.702703, 36.291018 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1723711 | 1723711 | 1723711 | Equitable | N/A | 1723711 | 0 | 1693992 | 98.3 | 1693992 | 29719 | 29719 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Work well done.
5637 | Preventive and Promotive Health Services | Construction of Segut Dispensary | To construct Segut Dispensary | Segut Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.361136, 35.788569 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1989024 | 1989024 | 1989024 | Equitable | N/A | 1989024 | 0 | 1888851 | 95 | 1888851 | 100173 | 100173 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operating.
5638 | Preventive and Promotive Health Services | construction of a pharmacy, waiting area and pit latrines at Mau Narok health centre | To construct a pharmacy, waiting area and pit latrines at Mau Narok health centre | A pharmacy, waiting area and pit latrines at Mau Narok health centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.600012, 36.007202 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999910 | 100 | 1999910 | 2000000 | 90 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: not met. Viable: not viable. Assessor remarks: project stalled.
5639 | Preventive and Promotive Health Services | Construction of Dispensary at Segutiet | To construct Dispensary at Segutiet | Dispensary at Segutiet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.577825, 36.052545 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1962735 | 78.5 | 1962735 | 534438 | 537265 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Needs equiping.
5640 | Preventive and Promotive Health Services | Construction of Maternity at Likia Dispensary | To construct Maternity at Likia Dispensary | Maternity at Likia Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.534903, 35.967107 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498454 | 99.9 | 2498454 | 1197370 | 1546 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Not. Viable: Not viable. Assessor remarks: The facility needs to be equipped.
5641 | Preventive and Promotive Health Services | Completion and equipping of Menengai Health Centre | To complete and equip Menengai Health Centre | Menengai Health Centre completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Menengai | -0.275602 36.11133 1860.199951171875 20 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499520 | 100 | 1499520 | 2867983 | 480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5642 | Preventive and Promotive Health Services | Completion of Mang'u maternity | To complete Mang'u maternity | Mang'u maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.166762 36.007934 0 600 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1999824 | 100 | 1999824 | 1999824 | 176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
5643 | Preventive and Promotive Health Services | Completion of Ngecha Dispensary | To complete Ngecha Dispensary | Ngecha Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.248851 35.939649 2052.10009765625 13.512999534606934 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 499990 | 100 | 499990 | 500000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: JODIAH TRANDERS LIMITED. Assessor remarks: Good workmanship.
5644 | Preventive and Promotive Health Services | Completion of Ogilgei Maternity | To complete Ogilgei Maternity | Ogilgei Maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.296157, 35.958663 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499973 | 100 | 1499973 | 500000 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Effective. Assessor remarks: Good workmanship.
5645 | Preventive and Promotive Health Services | construction and equipping of Komothai dispensary | To construct and equip Komothai dispensary | Komothai dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.467272, 36.371306 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 3999950 | 3999950 | 3999950 | Equitable | N/A | 3999950 | 0 | 3968360 | 99.2 | 3968360 | 3999950 | 31590 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RONISAR ENTERPRISES, PEPSI AFRICA GENERAL MERCHANT LTD. Assessor remarks: Operational.
5646 | Preventive and Promotive Health Services | construction of Gatundu -Merironi dispensary | To construct Gatundu -Merironi dispensary | Gatundu -Merironi dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.503131, 36.390597 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2396460 | 2396460 | 2396460 | Equitable | N/A | 2396460 | 0 | 1049950 | 43.8 | 1049950 | 1150960 | 1346510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GLASAMMURS CONSTRUCTION LIMITED. Assessor remarks: In good condition.
5647 | Preventive and Promotive Health Services | Construction of gitare dispensary phase 1 | To construct gitare dispensary phase 1 | Gitare dispensary phase 1 constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.40869, 36.310599 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2908836 | 97 | 2908836 | 91164 | 91164 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5648 | Preventive and Promotive Health Services | Renovation of karunga dispensary | To rehabilitate karunga dispensary to restore functionality | Karunga dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998400 | 99.9 | 1998400 | 1600 | 1600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5649 | Preventive and Promotive Health Services | Construction of Kinungi Dispensary and toilet blocks | To construct Kinungi Dispensary and toilet blocks | Kinungi Dispensary and toilet blocks constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.78485, 36.541935 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998440 | 99.9 | 2998440 | 200129 | 1560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: No t yet equipped, no electricity connection and septic tank.
5650 | Preventive and Promotive Health Services | Construction of wards at Sision Maternity | To construct wards at Sision Maternity | Wards at Sision Maternity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.867373, 36.535493 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1705466 | 85.3 | 1705466 | 294534 | 294534 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5651 | Preventive and Promotive Health Services | Rehabilitation and Equipping of Nessuit Maternity | To rehabilitate Equipping of Nessuit Maternity to restore functionality | Equipping of Nessuit Maternity rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.393429 35.899456 2477.7296299869195 52.435916900634766 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997290 | 99.7 | 997290 | 2710 | 2710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The maternity is operational.
5652 | Preventive and Promotive Health Services | Completion of gacharage dispensary | To complete gacharage dispensary | Gacharage dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.289234 35.63603 2712.264136918813 13 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2211394 | 2211394 | 2211394 | Equitable | N/A | 2211394 | 0 | 2194200 | 99.2 | 2194200 | 2211394 | 17194 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use though it has no water supply.
5653 | Preventive and Promotive Health Services | Construction of a toilet at kapsetek dispensary | To construct a toilet at kapsetek dispensary | A toilet at kapsetek dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.083928, 35.874083 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 30/12/3024 | 350000 | 350000 | 350000 | Equitable | Ward Fund | 350000 | 0 | 349972 | 100 | 349972 | 28 | 28 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: M/S Laron Investment. Assessor remarks: The project is ongoing.
5654 | Preventive and Promotive Health Services | Renovation works at Majani Mingi Dispensary and construction of toilet | To rehabilitate works at Majani Mingi Dispensary and construction of toilet to restore functionality | Works at Majani Mingi Dispensary and construction of toilet rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.041777, 36.02443 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198135 | 99.8 | 1198135 | 1200000 | 1865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project on Use.
5655 | Preventive and Promotive Health Services | Edgewood dispensary - equipping and purchase of furniture and fittings | To implement edgewood dispensary - equipping and purchase of furniture and fittings for access to quality healthcare services | Edgewood dispensary - equipping and purchase of furniture and fittings completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.004847, 36.207636 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 11/02/2022 | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 674350 | 100 | 674350 | 674464 | 114 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The furniture serves the health facility workers. Contractor: Information not available. Assessor remarks: The furniture is in good condition..
5656 | Preventive and Promotive Health Services | Edgewood dispensary | To implement edgewood dispensary for access to quality healthcare services | Edgewood dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.004801, 36.207485 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 04/01/2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998346 | 99.9 | 1998346 | 1654 | 1654 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The facility serves the community. Contractor: Information not available. Assessor remarks: Good work.
5657 | Preventive and Promotive Health Services | Construction of chemaner male ward | To construct chemaner male ward | Chemaner male ward constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 733372 | 29.3 | 733372 | 347490 | 1766628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
5658 | Preventive and Promotive Health Services | Construction of kabongoi dispensary | To construct kabongoi dispensary | Kabongoi dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 1901087 | 76 | 1901087 | 2408155 | 598913 | Stalled | 75 | 76 | Intent to terminate issued | 2020 | N/A | 598913 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
5659 | Preventive and Promotive Health Services | Construction of public toilet at Randi center | To construct public toilet at Randi center | Public toilet at Randi center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.296227 35.768977 2362 8.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799130 | 99.9 | 799130 | 870 | 870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The problem was done.
5660 | Preventive and Promotive Health Services | Construction of toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary | To construct toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary | Toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -1.281229, 36.821402 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998500 | 99.9 | 1998500 | 2000000 | 1500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: FUNCTIONAL.
5661 | Preventive and Promotive Health Services | Renovation of Kiambiriria Health Centre | To rehabilitate Kiambiriria Health Centre to restore functionality | Kiambiriria Health Centre rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.323408, 35.698105 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998950 | 99.9 | 998950 | 1050 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The facility is very well built, has drugs but in need of staff.
5662 | Preventive and Promotive Health Services | Construction and equipping of Kabati Dispensary laboratory | To construct and equip Kabati Dispensary laboratory | Kabati Dispensary laboratory constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.721884, 36.444183 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 349731 | 7.8 | 349731 | 349731 | 4150269 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: The project was completed and functional.
5663 | Preventive and Promotive Health Services | Construction of Hope Well dispensary | To construct Hope Well dispensary | Hope Well dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.710429, 36.4312 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2862545 | 95.4 | 2862545 | 3000000 | 137455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: About to start.
5664 | Construction of OPD at Olenguruone Subcounty hospital | Construction of OPD at Olenguruone Subcounty hospital | To construct OPD at Olenguruone Subcounty hospital | OPD at Olenguruone Subcounty hospital constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 200000000 | 29851655 | 0 | N/A | N/A | 0 | 29851655 | 750000 | 2.5 | 750000 | 0 | 29101655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5665 | Other Development (HQ) | Other Development (HQ) | To implement other development (hq) for access to quality healthcare services | Other Development (HQ) completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 16308823 | 6308823 | 6308823 | N/A | N/A | 6308823 | 0 | 6308823 | 100 | 6308823 | 70000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5666 | Preventive and Promotive Health Services | Completion of Eco Public Toilet Bahati Sub-County hospital | To complete Eco Public Toilet Bahati Sub-County hospital | Eco Public Toilet Bahati Sub-County hospital completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.169768 36.123245 1919.9000244140625 23.655000686645508 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 371316 | 18.6 | 371316 | 382800 | 1628684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
5667 | Preventive and Promotive Health Services | Construction and equipping of dispensary/maternity at barut ward | To construct and equip dispensary/maternity at barut ward | Dispensary/maternity at barut ward constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.327065, 36.056176 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021/2022 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 349946 | 10 | 349946 | 515266 | 3150054 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jojewa Enterprises. Assessor remarks: Usable.
5668 | Preventive and Promotive Health Services | Construction of Container Toilets/cabro lions garden | To construct Container Toilets/cabro lions garden | Container Toilets/cabro lions garden constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2349900 | 94 | 2349900 | 150100 | 150100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5669 | Preventive and Promotive Health Services | Renovation of a theater at bondeni maternity | To rehabilitate a theater at bondeni maternity to restore functionality | A theater at bondeni maternity rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.295654, 36.079935 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 932131 | 93.2 | 932131 | 1000000 | 67869 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5670 | Preventive and Promotive Health Services | Construction of Septic Tank at Eburru Health Centre | To construct Septic Tank at Eburru Health Centre | Septic Tank at Eburru Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.646154, 36.271816 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 21-22 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1199840 | 399.9 | 1199840 | 300000 | -899840 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No value for money. Contractor: Unspecified. Assessor remarks: No such project exist.
5671 | Preventive and Promotive Health Services | Fencing of new canaan dispensary phase 1 | To secure new canaan dispensary phase 1 through fencing | New canaan dispensary phase 1 fenced and secured | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.341013, 36.150603 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 31-07-2023 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 499400 | 249.7 | 499400 | 200000 | -299400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Limited. Assessor remarks: Fairy done.
5672 | Preventive and Promotive Health Services | Construction of staff houses for Kiptangwanyi Dispensary | To construct staff houses for Kiptangwanyi Dispensary | Staff houses for Kiptangwanyi Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567261, 36.114487 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3484320 | 99.6 | 3484320 | 3500000 | 15680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
5673 | Preventive and Promotive Health Services | Construction of staff quarters and Equipping at Muthaiti dispensary | To construct staff quarters and Equipping at Muthaiti dispensary | Staff quarters and Equipping at Muthaiti dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617292, 36.147138 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2998971 | 85.7 | 2998971 | 501029 | 501029 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
5674 | Preventive and Promotive Health Services | Construction of staff quarters at mugaa dispensary | To construct staff quarters at mugaa dispensary | Staff quarters at mugaa dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617292, 36.147138 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999995 | 100 | 2999995 | 90 | 5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
5675 | Preventive and Promotive Health Services | Construction of staff quarters at Munanda dispensary | To construct staff quarters at Munanda dispensary | Staff quarters at Munanda dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617292, 36.147138 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 2999910 | 50 | 2999910 | 90 | 3000090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
5676 | Preventive and Promotive Health Services | Expansion of Kiptangwany health facility | To expand Kiptangwany health facility to increase capacity | Kiptangwany health facility expanded | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567, 36.11696 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5677 | Preventive and Promotive Health Services | Fencing of Muthaiti/ Munanda/Mugaa Elementaita dispensaries | To secure Muthaiti/ Munanda/Mugaa Elementaita dispensaries through fencing | Muthaiti/ Munanda/Mugaa Elementaita dispensaries fenced and secured | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489548, 36.155317 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3149990 | 78.7 | 3149990 | 3200000 | 850010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fence done at Mugaa dispensary.
5678 | Preventive and Promotive Health Services | Construction of a Sewer line in Kimathi Estate | To construct a Sewer line in Kimathi Estate | A Sewer line in Kimathi Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.305464 36.078831 1793.3 6.300000190734863 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499069 | 100 | 2499069 | 931 | 931 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Operational.
5679 | Preventive and Promotive Health Services | Rehabilitation and connection to sewer of 1 no toilet block at kimathi estate | To rehabilitate connection to sewer of 1 no toilet block at kimathi estate to restore functionality | Connection to sewer of 1 no toilet block at kimathi estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303761, 36.078667 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1196440 | 99.7 | 1196440 | 1200000 | 3560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Completed and in use.
5680 | Preventive and Promotive Health Services | Rehabilitation of 5 toilets at kimathi Estate | To rehabilitate 5 toilets at kimathi Estate to restore functionality | 5 toilets at kimathi Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303736, 36.078702 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/2020 | 8500000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5699900 | 95 | 5699900 | 300100 | 300100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use and in good condition.
5681 | Preventive and Promotive Health Services | Construction of public toilets at the Bus/Matatu Parks | To construct public toilets at the Bus/Matatu Parks | Public toilets at the Bus/Matatu Parks constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 0 | 4000000 | N/A | N/A | 4000000 | 0 | 2533450 | 0 | 2533450 | 9890259 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5682 | Preventive and Promotive Health Services | Construction of Septic Tank at Keringet Sub County Hospital | To construct Septic Tank at Keringet Sub County Hospital | Septic Tank at Keringet Sub County Hospital constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 750000 | 37.5 | 750000 | 0 | 1250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5683 | Health Curative and Rehabilitative Services | Other Developments - (FIF) | To implement other developments - (fif) for access to quality healthcare services | Other Developments - (FIF) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 300000000 | 300000000 | 0 | FIF | N/A | 0 | 250000000 | 6308823 | 2.1 | 6308823 | 70000000 | 293691177 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5684 | Preventive and Promotive Health Services | Fencing Kabatini Health Centre | To secure Kabatini Health Centre through fencing | Kabatini Health Centre fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213099, 36.162837 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 30th may 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 399350 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogra hardware and construction. Assessor remarks: Painting was done very well.
5685 | Preventive and Promotive Health Services | Fencing of Kabatini hospital | To secure Kabatini hospital through fencing | Kabatini hospital fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213583, 36.162957 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 729109 | 36.5 | 729109 | 271520 | 1270891 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogra hardware & construction ltd. Assessor remarks: It was done but the funds were not enough to complete one side.
5686 | Preventive and Promotive Health Services | Painting of kabatini health center | To implement painting of kabatini health center for access to quality healthcare services | Painting of kabatini health center completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213099, 36.162837 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 30th may 2023 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 2000000 | 500 | 2000000 | 399350 | -1600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogra hardware and construction. Assessor remarks: Painting was done very well.
5687 | Preventive and Promotive Health Services | Construction of a perimeter wall at Ingobor Health centre | To construct a perimeter wall at Ingobor Health centre | A perimeter wall at Ingobor Health centre constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499995 | 100 | 1499995 | 5 | 5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Security was enhanced. Assessor remarks: Well done and functional.
5688 | Preventive and Promotive Health Services | Completion and equipping youth health friendly center | To complete and equip youth health friendly center | Youth health friendly center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.30474 36.055271 1794.3205995676594 60 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 496000 | 16.5 | 496000 | 500055 | 2504000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: VILALOXA STORES. Assessor remarks: It's fully equipped.
5689 | Preventive and Promotive Health Services | Construction of pit latrines at kapkores dispensary | To construct pit latrines at kapkores dispensary | Pit latrines at kapkores dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466652 35.652975 2634.7999999999997 17 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 250000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 250000 | 100 | 250000 | 250000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operation al.
5690 | Preventive and Promotive Health Services | Construction of pit latrines at tegat dispensary | To construct pit latrines at tegat dispensary | Pit latrines at tegat dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466652 35.652975 2634.7999999999997 17 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 250000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 250000 | 100 | 250000 | 250000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operation al.
5691 | Preventive and Promotive Health Services | Renovation of tegat and kapkores dispensaries | To rehabilitate tegat and kapkores dispensaries to restore functionality | Tegat and kapkores dispensaries rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466475 35.653347 2574.2999999999997 6.599999904632568 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 412900 | 412900 | 412900 | Equitable | N/A | 412900 | 0 | 352087 | 85.3 | 352087 | 60793 | 60813 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5692 | Preventive and Promotive Health Services | Completion of maternity wing dispensary Tioa | To complete maternity wing dispensary Tioa | Maternity wing dispensary Tioa completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.323754, 35.553987 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 543281 | 54.3 | 543281 | 1000000 | 456719 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: The equipments are at kuresoi health center.
5693 | Preventive and Promotive Health Services | Construction of Githima dispensary nurse residential house | To construct Githima dispensary nurse residential house | Githima dispensary nurse residential house constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.325895, 35.49856 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 543281 | 36.2 | 543281 | 1494150 | 956719 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5694 | Preventive and Promotive Health Services | Construction of four sanitation blocks at Kivumbini I & II estate | To construct four sanitation blocks at Kivumbini I & II estate | Four sanitation blocks at Kivumbini I & II estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2024 | 10000000 | 10000000 | 10000000 | Equitable | Ward Fund | 10000000 | 0 | 3628118 | 36.3 | 3628118 | 1408217 | 6371882 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
5695 | Preventive and Promotive Health Services | Construction of sanitation block at kivumbini 1 | To construct sanitation block at kivumbini 1 | Sanitation block at kivumbini 1 constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1880540 | 94 | 1880540 | 2000000 | 119460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
5696 | Preventive and Promotive Health Services | Construction of sanitation block at kivumbini 2 | To construct sanitation block at kivumbini 2 | Sanitation block at kivumbini 2 constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1880540 | 94 | 1880540 | 2000000 | 119460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
5697 | Preventive and Promotive Health Services | Construction of perimeter wall at Kayole dispensary | To construct perimeter wall at Kayole dispensary | Perimeter wall at Kayole dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.751713, 36.457225 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2497230 | 99.9 | 2497230 | 2770 | 2770 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repair the gate.
5698 | Preventive and Promotive Health Services | Longonot Dispensary-Replacing Asbestos with Iron Sheets,gutters and others | To implement longonot dispensary-replacing asbestos with iron sheets,gutters and others for access to quality healthcare services | Longonot Dispensary-Replacing Asbestos with Iron Sheets,gutters and others completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.884377, 36.497402 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 762000 | 50.8 | 762000 | 738000 | 738000 | Stalled | 75 | 50.8 | To be retendered | 2019 | N/A | 738000 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. Assessor remarks: Gutters not yet installed, the roof is good condition..
5699 | Preventive and Promotive Health Services | Maai Mahiu Health Centre-Construction of staff houses | To implement maai mahiu health centre-construction of staff houses for access to quality healthcare services | Maai Mahiu Health Centre-Construction of staff houses completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.976952, 36.584984 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998085 | 99.9 | 2998085 | 1915 | 1915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
5700 | Preventive and Promotive Health Services | Construction of dispensary in Tipis | To construct dispensary in Tipis | Dispensary in Tipis constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.597785 35.999365 2574.8999999999996 3.4000000953674316 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3590190 | 99.7 | 3590190 | 3600000 | 9810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Bad state of repair.
5701 | Preventive and Promotive Health Services | Construction of modern Public toilet at Mau Narok | To construct modern Public toilet at Mau Narok | Modern Public toilet at Mau Narok constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.600012, 36.007202 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499393 | 100 | 1499393 | 607 | 607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
5702 | Preventive and Promotive Health Services | Mau Narok Health Centre Construction of Administration block and Laboratory | To implement mau narok health centre construction of administration block and laboratory for access to quality healthcare services | Mau Narok Health Centre Construction of Administration block and Laboratory completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.600012, 36.007202 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 19/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998315 | 99.9 | 2998315 | 0 | 1685 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: no. Viable: yes. Assessor remarks: needs equipping.
5703 | Preventive and Promotive Health Services | Completion of menengai dispensary perimeter wall | To complete menengai dispensary perimeter wall | Menengai dispensary perimeter wall completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266242, 36.100628 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 483060 | 96.6 | 483060 | 500000 | 16940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ascom ventures. Assessor remarks: Completed.
5704 | Preventive and Promotive Health Services | Construction of teachers market toilet | To construct teachers market toilet | Teachers market toilet constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266244, 36.100635 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2023/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499590 | 100 | 1499590 | 1500000 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Prime rift traders. Assessor remarks: Completed.
5705 | Preventive and Promotive Health Services | Fencing of Menengai Dispensary | To secure Menengai Dispensary through fencing | Menengai Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275604, 36.11132 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493255 | 99.6 | 1493255 | 6745 | 6745 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting.
5706 | Preventive and Promotive Health Services | Construction of kirobon toilets(coolant) | To construct kirobon toilets(coolant) | Kirobon toilets(coolant) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.269996 36.031468 1924.8 4.900000095367432 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999921 | 100 | 999921 | 79 | 79 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
5707 | Preventive and Promotive Health Services | Construction of a kitchen for the sachangwan dispensary | To construct a kitchen for the sachangwan dispensary | A kitchen for the sachangwan dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2533450 | 281.5 | 2533450 | 9890259 | -1633450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5708 | Preventive and Promotive Health Services | Completion and equipping of ngecha health center | To complete and equip ngecha health center | Ngecha health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499990 | 100 | 499990 | 500000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
5709 | Preventive and Promotive Health Services | Completion and equipping of Rongai Turi health center | To complete and equip Rongai Turi health center | Rongai Turi health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497600 | 99.5 | 497600 | 500000 | 2400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
5710 | Preventive and Promotive Health Services | Completion and equipping of Roret bridge health center | To complete and equip Roret bridge health center | Roret bridge health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499990 | 100 | 499990 | 500000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
5711 | Preventive and Promotive Health Services | Completion works (Staffs electricity and lab equipments) at lelechwet dispensary | To complete works (Staffs electricity and lab equipments) at lelechwet dispensary | Works (Staffs electricity and lab equipments) at lelechwet dispensary completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.248851 35.939649 2052.10009765625 13.512999534606934 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499480 | 99.9 | 499480 | 500000 | 520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: JODIAH TRANDERS LIMITED. Assessor remarks: Good workmanship.
5712 | Preventive and Promotive Health Services | Construction of 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary | To construct 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary | 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279335, 35.884997 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2025 | 2400000 | 2400000 | 2400000 | Equitable | Ward Fund | 2400000 | 0 | 733477 | 30.6 | 733477 | 1666523 | 1666523 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
5713 | Preventive and Promotive Health Services | Construction of Staff Quarters and Fencing of Lelechwet Dispensary | To construct Staff Quarters and Fencing of Lelechwet Dispensary | Staff Quarters and Fencing of Lelechwet Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.220996, 35.827697 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499300 | 100 | 1499300 | 1530000 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ngambo. Assessor remarks: Complete.
5714 | Preventive and Promotive Health Services | construction of Gatundu -Merironi dispensary phase II, toilets, fencing , installtion of gate and 10,000 litreswater tank and electrification of the facility and two security lights | To construct Gatundu -Merironi dispensary phase II, toilets, fencing , installtion of gate and 10,000 litreswater tank and electrification of the facility and two security lights | Gatundu -Merironi dispensary phase II, toilets, fencing , installtion of gate and 10,000 litreswater tank and electrification of the facility and two security lights constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.497603, 36.397703 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 805351 | 2169836 | 2169836 | Equitable | N/A | 2169836 | 0 | 1794956 | 82.7 | 1794956 | 2169836 | 374880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: ERUC AFRIC LIMITED. Assessor remarks: Streetlights not installed.
5715 | Preventive and Promotive Health Services | Completion of Sision maternity | To complete Sision maternity | Sision maternity completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.867383, 36.535491 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021-2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1349897 | 90 | 1349897 | 149989 | 150103 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: No water connection and septic tank.
5716 | Preventive and Promotive Health Services | Construction of wall, toilet and Incinerator at Munyu dispensary | To construct wall, toilet and Incinerator at Munyu dispensary | Wall, toilet and Incinerator at Munyu dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.827715, 36.535871 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019-20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998560 | 99.9 | 998560 | 999600 | 1440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed but without incenerator and burning chamber.
5717 | Preventive and Promotive Health Services | construction of perimeter wall at free area lanet dispensary | To construct perimeter wall at free area lanet dispensary | Perimeter wall at free area lanet dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292567 36.119342 1840.9000244140625 17.683000564575195 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199998 | 100 | 1199998 | 2 | 2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki consruction ltd. Assessor remarks: Project ok.
5718 | Preventive and Promotive Health Services | Rehabilitation and Equipping of Nessuit Maternity | To rehabilitate Equipping of Nessuit Maternity to restore functionality | Equipping of Nessuit Maternity rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.393429 35.899456 2477.7296299869195 52.435916900634766 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997290 | 99.7 | 997290 | 2710 | 2710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The maternity is operational.
5719 | Preventive and Promotive Health Services | Construction of dispensary quarters at Narasha | To construct dispensary quarters at Narasha | Dispensary quarters at Narasha constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.913047, 36.275996 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999992 | 100 | 2999992 | 8 | 8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Was viable but did not meet the needs since its not operational. Assessor remarks: The facility not in use.
5720 | Preventive and Promotive Health Services | Construction of administration block at mwariki dispensary in Rhonda ward | To construct administration block at mwariki dispensary in Rhonda ward | Administration block at mwariki dispensary in Rhonda ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2019 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Stalled — reasons to be confirmed by department.
5721 | Preventive and Promotive Health Services | Construction of a perimeter wall at Nakuru West clinic | To construct a perimeter wall at Nakuru West clinic | A perimeter wall at Nakuru West clinic constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 502350 | 502350 | Equitable | N/A | 502350 | 0 | 2497650 | 497.2 | 2497650 | 502320 | -1995300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5722 | Preventive and Promotive Health Services | Equipping of Majani Mingi Dispensary | To equip Majani Mingi Dispensary with necessary facilities and equipment | Majani Mingi Dispensary equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.041777 36.02443 1637.6999999999998 2094.485107421875 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 462444.4 | 462444.4 | Equitable | Ward Fund | 462444.4 | 0 | 439500 | 95 | 439500 | 462444 | 22944.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project on use.
5723 | Preventive and Promotive Health Services | Completion and equipping of laboratory at prisons dispensary | To complete and equip laboratory at prisons dispensary | Laboratory at prisons dispensary completed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.702788, 36.443555 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1006958 | 1006958 | 1006958 | Equitable | N/A | 1006958 | 0 | 997600 | 99.1 | 997600 | 1006958 | 9358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Project completed.
5724 | Preventive and Promotive Health Services | Construction of a public toilet at Kongasis auction market and fence | To construct a public toilet at Kongasis auction market and fence | A public toilet at Kongasis auction market and fence constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.552511, 36.151373 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 21-22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 594560 | 99.1 | 594560 | 5440 | 5440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Used.
5725 | Preventive and Promotive Health Services | Construction of toilets at Mbaruk Market | To construct toilets at Mbaruk Market | Toilets at Mbaruk Market constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 163588 | 163588 | Equitable | N/A | 163588 | 0 | 162640 | 99.4 | 162640 | 948 | 948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5726 | Preventive and Promotive Health Services | Construction of a public toilet at Elementaita trading centre | To construct a public toilet at Elementaita trading centre | A public toilet at Elementaita trading centre constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.487923, 36.156894 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 3991670 | 399.2 | 3991670 | 999266 | -2991670 | Stalled | 0 | 100 | Stalled -10%. Retendering of works in progress | 2019 | N/A | -2991670 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project was veried.
5727 | Preventive and Promotive Health Services | Construction of public toilets at Keringet town | To construct public toilets at Keringet town | Public toilets at Keringet town constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.426397 35.693612 2683.500244140625 5.900000095367432 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199276 | 99.9 | 1199276 | 724 | 724 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Constructed at 1.2 m.
5728 | Preventive and Promotive Health Services | Empowering volunteers community health workers | To implement empowering volunteers community health workers for access to quality healthcare services | Empowering volunteers community health workers completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5729 | Preventive and Promotive Health Services | Construction of Toilet in Githima market | To construct Toilet in Githima market | Toilet in Githima market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499994 | 100 | 1499994 | 6 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5730 | Preventive and Promotive Health Services | Equipping of Kigonor Community Dispensary | To equip Kigonor Community Dispensary with necessary facilities and equipment | Kigonor Community Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.327064 36.056176 1770 43.60900115966797 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998500 | 99.9 | 998500 | 1500 | 1500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Foresight commecial services. Assessor remarks: Equipment are operational.
5731 | Preventive and Promotive Health Services | Equipping of maternity at barut ward | To equip maternity at barut ward with necessary facilities and equipment | Maternity at barut ward equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.326905, 36.056307 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496470 | 99.8 | 1496470 | 1500000 | 3530 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Foresight Commercial Services. Assessor remarks: Usable.
5732 | Preventive and Promotive Health Services | Equipping of mwariki health center | To equip mwariki health center with necessary facilities and equipment | Mwariki health center equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.34819, 36.055632 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The equipments in sound condition.
5733 | Preventive and Promotive Health Services | Fencing of barnabas IDP dispensary | To secure barnabas IDP dispensary through fencing | Barnabas IDP dispensary fenced and secured | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Eburru-Mbaruk | -0.339112, 36.158842 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499400 | 99.9 | 499400 | 500000 | 600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes , it was objective.. Viable: It was viable .. Assessor remarks: Not existing.
5734 | Preventive and Promotive Health Services | Equipping of Kasarani health center | To equip Kasarani health center with necessary facilities and equipment | Kasarani health center equipped | 3111101 | Purchase of Medical and Dental Equipment | Molo | Elburgon | -0.303366 35.81419 0 2000 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5735 | Preventive and Promotive Health Services | Equipping of Miti-Mingi Maternity | To equip Miti-Mingi Maternity with necessary facilities and equipment | Miti-Mingi Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Elementaita | -0.528321, 36.075796 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999430 | 99.9 | 999430 | 0 | 570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5736 | Health Curative and Rehabilitative Services | Purchase of medical and dental equipment (FIF) | To procure medical and dental equipment (FIF) | Medical and dental equipment (FIF) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2020/21 | N/A | 47000000 | 58000000 | 0 | FIF | FIF | 0 | 58000000 | 76381394 | 131.7 | 76381394 | 21343623 | -18381394 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5737 | Health Curative and Rehabilitative Services | Purchase of medical and medical equipment (Nakuru West) | To procure medical and medical equipment (Nakuru West) | Medical and medical equipment (Nakuru West) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | -0.75186, 36.45704 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 303884 | 0 | N/A | N/A | 0 | 303884 | 49824 | 16.4 | 49824 | 78884 | 254060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repair the gate it is broken.
5738 | Health Curative and Rehabilitative Services | Purchase of medical and medical equipment (PGH) | To procure medical and medical equipment (PGH) | Medical and medical equipment (PGH) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 15000000 | 44627168 | 0 | FIF | FIF | 0 | 44627168 | 55588849 | 124.6 | 55588849 | 78884 | -10961681 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5739 | Preventive and Promotive Health Services | Purchase of Medical Equipments & dental Equipment for various new health centres (HQ) | To procure Medical Equipments & dental Equipment for various new health centres (HQ) | Medical Equipments & dental Equipment for various new health centres (HQ) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 48000000 | 96000000 | 92000000 | Equitable | N/A | 92000000 | 0 | 32239074 | 33.6 | 32239074 | 6109472 | 63760926 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5740 | Preventive and Promotive Health Services | Equipping at Lalwet Dispensary | To equip at Lalwet Dispensary with necessary facilities and equipment | At Lalwet Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999600 | 100 | 1999600 | 400 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Lack of Lab Technician. Viable: Not met. Being a Level 2 does not have. Assessor remarks: Equipments were supplied but are not in use. Stored..
5741 | Preventive and Promotive Health Services | Equipping of kiborowo dispensary | To equip kiborowo dispensary with necessary facilities and equipment | Kiborowo dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Kiptagich | -0.534972 35.579442 2391.5 11.699999809265137 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 963700 | 96.4 | 963700 | 1000000 | 36300 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Functional.
5742 | Preventive and Promotive Health Services | Equipping of Githima dispensary | To equip Githima dispensary with necessary facilities and equipment | Githima dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi North | Kiptororo | -0.315257, 35.48315 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1058000 | 1058000 | 1058000 | Equitable | N/A | 1058000 | 0 | 972220 | 91.9 | 972220 | 85780 | 85780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: The facility needs electricity connection and fencing of the facility.
5743 | Preventive and Promotive Health Services | Equipping of Metta Dispensary | To equip Metta Dispensary with necessary facilities and equipment | Metta Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Njoro | Mau Narok | -0.577369, 36.031396 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Equipment transffered to mau narok health centre.
5744 | Preventive and Promotive Health Services | Equipping of Laboratory at Menengai dispensary | To equip Laboratory at Menengai dispensary with necessary facilities and equipment | Laboratory at Menengai dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru East | Menengai | -0.266251, 36.100624 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 479527 | 48 | 479527 | 535034 | 520473 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Emeeland contractors. Assessor remarks: Completed.
5745 | Preventive and Promotive Health Services | Equipping of Gatundu -Merironi dispensary | To equip Gatundu -Merironi dispensary with necessary facilities and equipment | Gatundu -Merironi dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Murindat | -0.497603, 36.397703 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1472600 | 98.2 | 1472600 | 27400 | 27400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
5746 | Preventive and Promotive Health Services | Equipping of Gitare dispensary | To equip Gitare dispensary with necessary facilities and equipment | Gitare dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Murindat | -0.40869, 36.310599 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1476970 | 98.5 | 1476970 | 23030 | 23030 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5747 | Preventive and Promotive Health Services | Equipping of Nuthu dispensary | To equip Nuthu dispensary with necessary facilities and equipment | Nuthu dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Murindat | -0.40869, 36.310599 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199380 | 99.9 | 1199380 | 23030 | 620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5748 | Preventive and Promotive Health Services | Equipping of Sision Maternity | To equip Sision Maternity with necessary facilities and equipment | Sision Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Naivasha East | -0.867355, 36.535495 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 462000 | 92.4 | 462000 | 500000 | 38000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No provision of maternity beds, drugs trolley, delivery packs.
5749 | Health Curative and Rehabilitative Services | Equipping of Nakuru West clinic | To equip Nakuru West clinic with necessary facilities and equipment | Nakuru West clinic equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Shabab | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2958500 | 98.6 | 2958500 | 41500 | 41500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5750 | Preventive and Promotive Health Services | Equipping of muyesh dispensary | To equip muyesh dispensary with necessary facilities and equipment | Muyesh dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Molo | Turi | -0.302072 35.720327 2489 687.0120239257812 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499580 | 99.9 | 499580 | 420 | 420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: No title. The county government of Nakuru to facilitate the process of acquiring a title.
5751 | Health Curative and Rehabilitative Services | Acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH (FIF) | To implement acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in pgh (fif) for access to quality healthcare services | Acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH (FIF) completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 100000000 | 0 | 25000000 | FIF | FIF | 25000000 | 50000000 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5752 | Health Curative and Rehabilitative Services | Purchase of plant and machinery (FIF) | To procure plant and machinery (FIF) | Plant and machinery (FIF) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2020/21 | N/A | 10000000 | 10000000 | 0 | FIF | FIF | 0 | 30000000 | 692500 | 6.9 | 692500 | 35324805 | 9307500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5753 | Health Curative and Rehabilitative Services | Purchase of plant and machinery (Nakuru west) | To procure plant and machinery (Nakuru west) | Plant and machinery (Nakuru west) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 388680 | 0 | FIF | FIF | 0 | 388680 | 360749 | 92.8 | 360749 | 27931 | 27931 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5754 | Preventive and Promotive Health Services | Purchase of Land for construction of Kiptenda Dispensary | To acquire land for construction of Kiptenda Dispensary | Land for construction of Kiptenda Dispensary acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.338728 36.037972 1882.5 4.80000019073486 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 520384 | 34.7 | 520384 | 1500000 | 979616 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no kiptenden dispensary.
5755 | Preventive and Promotive Health Services | Purchase of Kasarani dispensary land | To procure Kasarani dispensary land | Kasarani dispensary land procured | 3130101 | Acquisition of Land | Molo | Elburgon | -0.293257 35.80205 2488.1 15.399999618530273 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000001 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 515700 | 12.9 | 515700 | 4000000 | 3484300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
5756 | Preventive and Promotive Health Services | Construction of toilets at Kaplambai Dispensary | To construct toilets at Kaplambai Dispensary | Toilets at Kaplambai Dispensary constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999073 | 99.9 | 999073 | 927 | 927 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
5757 | Preventive and Promotive Health Services | Construction of toilets at Kaplambai Dispensary | To construct toilets at Kaplambai Dispensary | Toilets at Kaplambai Dispensary constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999073 | 99.9 | 999073 | 927 | 927 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
5758 | Preventive and Promotive Health Services | Construction of a public toilet at Bahati stage | To construct a public toilet at Bahati stage | A public toilet at Bahati stage constructed | 4130299 | N/A | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997664 | 99.8 | 997664 | 382800 | 2336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
5759 | Preventive and Promotive Health Services | design and Construction of Bahati Eco public Toilets | To design and construct Bahati Eco public Toilets | Bahati Eco public Toilets designed and constructed | 4130299 | N/A | Bahati | Bahati | -0.159529 36.104999 1855.0999755859375 82.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1180027 | 78.7 | 1180027 | 319973 | 319973 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
5760 | Preventive and Promotive Health Services | Construction of 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary | To construct 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary | 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2019/20 | 2019/20 | 3500001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999996 | 100 | 2999996 | 0 | 4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5761 | Preventive and Promotive Health Services | Design and Construction of out patient department at Wangu Dispensary | To design and construct out patient department at Wangu Dispensary | Out patient department at Wangu Dispensary designed and constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000004 | 100 | 3000004 | 0 | -4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5762 | Preventive and Promotive Health Services | completion of mugwathi Githioro dispensary | To complete mugwathi Githioro dispensary | Mugwathi Githioro dispensary completed | 4130299 | N/A | Bahati | Dundori | -0.273842, 36.200992 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/2019 | 20000000 | 4057160 | 4057160 | Equitable | Ward Fund | 4057160 | 0 | 1508138 | 37.2 | 1508138 | 1508138 | 2549022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good condition.
5763 | Preventive and Promotive Health Services | Construction of Githioro dispensary | To construct Githioro dispensary | Githioro dispensary constructed | 4130299 | N/A | Bahati | Dundori | -0.273677, 36.201615 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/2018 | 10000000 | 9847120 | 9847120 | Equitable | N/A | 9847120 | 0 | 8096028 | 82.2 | 8096028 | 1751092 | 1751092 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
5764 | Preventive and Promotive Health Services | Construction of MCH at Kiwamu Health Centre | To construct MCH at Kiwamu Health Centre | MCH at Kiwamu Health Centre constructed | 4130299 | N/A | Bahati | Dundori | -0.237345, 36.167237 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/2016 | 6000000 | 9108439.7 | 9108439.7 | Equitable | Ward Fund | 9108439.7 | 0 | 4203337 | 46.1 | 4203337 | 1288168 | 4905102.7 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
5765 | Preventive and Promotive Health Services | fencing of Githioro dispensary | To secure Githioro dispensary through fencing | Githioro dispensary fenced and secured | 4130299 | N/A | Bahati | Dundori | -0.273697, 36.201733 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/2018 | 2240000 | 2240000 | 2240000 | Equitable | N/A | 2240000 | 0 | 2199140 | 98.2 | 2199140 | 1751092 | 40860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
5766 | Preventive and Promotive Health Services | Construction of Songoloi public toilet | To construct Songoloi public toilet | Songoloi public toilet constructed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 600903 | 600903 | 600903 | Equitable | N/A | 600903 | 0 | 592609 | 98.6 | 592609 | 850000 | 8294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5767 | Preventive and Promotive Health Services | Construction of staff Quarters at Eburu health Centre | To construct staff Quarters at Eburu health Centre | Staff Quarters at Eburu health Centre constructed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199840 | 100 | 1199840 | 300000 | 160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5768 | Preventive and Promotive Health Services | Construction of Kapsita Dispensary | To construct Kapsita Dispensary | Kapsita Dispensary constructed | 4130299 | N/A | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5769 | Preventive and Promotive Health Services | Design and Construction of Salama Trading Centre Public Toilet | To design and construct Salama Trading Centre Public Toilet | Salama Trading Centre Public Toilet designed and constructed | 4130299 | N/A | Molo | Elburgon | -0.297461 35.796986 2452.800048828125 18.98200035095215 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 217368.28 | 217368.28 | Equitable | N/A | 217368.28 | 0 | 208798 | 96.1 | 208798 | 6202551 | 8570.28 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not fit for use.
5770 | Preventive and Promotive Health Services | Equipping of Mwangi Michuki (Mutamaiyu dispensary) | To equip Mwangi Michuki (Mutamaiyu dispensary) with necessary facilities and equipment | Mwangi Michuki (Mutamaiyu dispensary) equipped | 4130299 | N/A | Molo | Elburgon | -0.210282 35.784866 0 899.9990234375 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 800001 | 501000 | 501000 | Equitable | N/A | 501000 | 0 | 499980 | 99.8 | 499980 | 0 | 1020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good use.
5771 | Preventive and Promotive Health Services | expanson of Arimi Dispensary ( maternity wing) | To implement expanson of arimi dispensary ( maternity wing) for access to quality healthcare services | expanson of Arimi Dispensary ( maternity wing) completed | 4130299 | N/A | Molo | Elburgon | -0.284884, 35.845889 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | - | 2500000 | 558067.2 | 558067.2 | Equitable | N/A | 558067.2 | 0 | 515700 | 92.4 | 515700 | 558067 | 42367.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No maternity wing.
5772 | Preventive and Promotive Health Services | Construction of Maternity Wing at Kiambogo dispensary | To construct Maternity Wing at Kiambogo dispensary | Maternity Wing at Kiambogo dispensary constructed | 4130299 | N/A | Gilgil | Elementaita | -0.591532, 36.127211 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4483308 | 4483308 | 4483308 | Equitable | N/A | 4483308 | 0 | 4483308 | 100 | 4483308 | 90 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maternity in use.
5773 | Preventive and Promotive Health Services | Construction of Miti Mingi dispensary | To construct Miti Mingi dispensary | Miti Mingi dispensary constructed | 4130299 | N/A | Gilgil | Elementaita | -0.516888, 36.112608 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | Ward Fund | 4000000 | 0 | 3991670 | 99.8 | 3991670 | 114973 | 8330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use..
5774 | Preventive and Promotive Health Services | Construction of staff quarters for Tangi Tano Dispensary | To construct staff quarters for Tangi Tano Dispensary | Staff quarters for Tangi Tano Dispensary constructed | 4130299 | N/A | Gilgil | Elementaita | -0.618479 36.146866 2199.106 0.8889999985694885 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798133 | 99.9 | 2798133 | 90 | 1867 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5775 | Preventive and Promotive Health Services | Design and Construction of Munanda Dispensary | To design and construct Munanda Dispensary | Munanda Dispensary designed and constructed | 4130299 | N/A | Gilgil | Elementaita | -0.596406, 36.111984 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 412779.8 | 412779.8 | Equitable | Ward Fund | 412779.8 | 0 | 409863 | 99.3 | 409863 | 90 | 2916.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5776 | Preventive and Promotive Health Services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary | To implement kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary for access to quality healthcare services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary completed | 4130299 | N/A | Gilgil | Elementaita | -0.602163, 36.131095 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4500000 | 727214 | 727214 | Equitable | Ward Fund | 727214 | 0 | 3272817 | 450 | 3272817 | 727214 | -2545603 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good working conditions..
5777 | Preventive and Promotive Health Services | Munanda Dispensary - Design and Construction of toilets | To implement munanda dispensary - design and construction of toilets for access to quality healthcare services | Munanda Dispensary - Design and Construction of toilets completed | 4130299 | N/A | Gilgil | Elementaita | -0.596053, 36.112725 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499960 | 100 | 499960 | 0 | 40 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5778 | Preventive and Promotive Health Services | Rehabilitation and equipping of maternity ward and inpatient at Langa Langa sub county hospital | To rehabilitate equipping of maternity ward and inpatient at Langa Langa sub county hospital to restore functionality | Equipping of maternity ward and inpatient at Langa Langa sub county hospital rehabilitated | 4130299 | N/A | Nakuru East | Flamingo | -0.303564, 36.072862 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 134874 | 134874 | Equitable | N/A | 134874 | 0 | 11510664 | 8534.4 | 11510664 | 134874 | -11375790 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
5779 | Preventive and Promotive Health Services | construction of a public toilet at the DCs office - Nakuru town | To construct a public toilet at the DCs office - Nakuru town | A public toilet at the DCs office - Nakuru town constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 2533450 | 126.7 | 2533450 | 9890259 | -533450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5780 | Construction of Maternity at Gilgil subcounty Hospital | Construction of Maternity at Gilgil subcounty Hospital | To construct Maternity at Gilgil subcounty Hospital | Maternity at Gilgil subcounty Hospital constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 200000000 | 3206219.5 | 0 | N/A | N/A | 0 | 3206219.5 | 750000 | 23.4 | 750000 | 0 | 2456219.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5781 | Preventive and Promotive Health Services | Design and Construction of outpatient block at Elburgon sub county hospital | To design and construct outpatient block at Elburgon sub county hospital | Outpatient block at Elburgon sub county hospital designed and constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 200000000 | 6202551 | 0 | N/A | N/A | 0 | 6202551 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5782 | Preventive and Promotive Health Services | Proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, | To undertake the proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, | Proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 723711 | 723711 | 723711 | N/A | N/A | 723711 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5783 | Preventive and Promotive Health Services | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | To undertake the proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5784 | Preventive and Promotive Health Services | Proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward | To undertake the proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward | Proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5785 | Preventive and Promotive Health Services | Purchase Of Ambulances | To procure Ambulances | Ambulances procured | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 5741133.05 | 59299908.2 | 59299908.2 | N/A | N/A | 59299908.2 | 0 | 59299908 | 100 | 59299908 | 35324805 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5786 | Preventive and Promotive Health Services | Purchase of Medical Equipments & dental Equipment for various new health centres(HQ) | To procure Medical Equipments & dental Equipment for various new health centres(HQ) | Medical Equipments & dental Equipment for various new health centres(HQ) procured | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 40000000 | 2007688.1 | 2007688.1 | N/A | N/A | 2007688.1 | 0 | 2007688 | 100 | 2007688 | 6109472 | 0.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5787 | Preventive and Promotive Health Services | Refurbishment of Health Buildings - Others | To implement refurbishment of health buildings - others for access to quality healthcare services | Refurbishment of Health Buildings - Others completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 8520378.5 | 8520378.5 | Equitable | N/A | 8520378.5 | 0 | 5400882 | 63.4 | 5400882 | 1657080 | 3119496.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5788 | Preventive and Promotive Health Services | Construction and equipping of Muriundu Dispensary | To construct and equip Muriundu Dispensary | Muriundu Dispensary constructed and equipped | 4130299 | N/A | Bahati | Kabatini | -0.231827, 36.15519 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2483264 | 99.3 | 2483264 | 2500000 | 16736 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomwaco limited. Assessor remarks: Operational.
5789 | Preventive and Promotive Health Services | Construction of public toilet in Kabatini | To construct public toilet in Kabatini | Public toilet in Kabatini constructed | 4130299 | N/A | Bahati | Kabatini | -0.213214 36.162865 2030 82.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
5790 | ECDs Toilets at (Engashura & St John) | ECDs Toilets at (Engashura & St John) | To implement ecds toilets at (engashura & st john) for access to quality healthcare services | ECDs Toilets at (Engashura & St John) completed | 4130299 | N/A | Bahati | Kabatini | -0.241725, 36.152316 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | 28th October 2015 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but needs renovation.
5791 | Preventive and Promotive Health Services | Expansion and equipping of Ruguru Dispensary | To expand and equipping of Ruguru Dispensary to increase capacity | And equipping of Ruguru Dispensary expanded | 4130299 | N/A | Bahati | Kabatini | -0.164807 36.177466 2170.87548828125 16.98200035095215 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999991 | 100 | 1999991 | 2500000 | 9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction company limited. Assessor remarks: Operational but toilets not done ,concrete water stand broken,no waiting bay.
5792 | Preventive and Promotive Health Services | Renovation of Kirima Dispensary | To rehabilitate Kirima Dispensary to restore functionality | Kirima Dispensary rehabilitated | 4130299 | N/A | Subukia | Kabazi | -0.158043 36.079285 1879 4.699999809265137 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599540 | 99.9 | 599540 | 0 | 460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Njega investment ltd. Assessor remarks: To be operationalized.
5793 | Preventive and Promotive Health Services | completion of Kamara Health Centre | To complete Kamara Health Centre | Kamara Health Centre completed | 4130299 | N/A | Kuresoi North | Kamara | -0.096473 35.680083 2504.1 7.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 271597 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs re-painting.
5794 | Preventive and Promotive Health Services | Proposed Construction of Rironi Health centre | To undertake the proposed Construction of Rironi Health centre | Proposed Construction of Rironi Health centre implemented | 4130299 | N/A | Kuresoi North | Kamara | -0.1811, 35.712733 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 271597.4 | 271597.4 | Equitable | N/A | 271597.4 | 0 | 1766373 | 650.4 | 1766373 | 271597 | -1494775.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it didn't meet the needs. Contractor: Unknown. Assessor remarks: Project needs to be completed operationalised.
5795 | Preventive and Promotive Health Services | Completion and equiping of Kapkures Maternity wing | To complete and equiping of Kapkures Maternity wing | And equiping of Kapkures Maternity wing completed | 4130299 | N/A | Nakuru West | Kapkures | -0.310643, 36.038628 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/2016 | 2941998.6 | 1805939.55 | 1805939.55 | Equitable | N/A | 1805939.55 | 0 | 1798260 | 99.6 | 1798260 | 7680 | 7679.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: Sageo investment. Assessor remarks: Well implimented.
5796 | Preventive and Promotive Health Services | Construction of Youth Friendly Health Centre Unit | To construct Youth Friendly Health Centre Unit | Youth Friendly Health Centre Unit constructed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.30479 36.055153 1791.5 14.612000465393066 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 1515728 | 1515728 | Equitable | N/A | 1515728 | 0 | 1479928 | 97.6 | 1479928 | 1515728 | 35800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable, it has helped the youths Very much,but defective toilets and urinals. Contractor: ZIBO COMPANY. Assessor remarks: Complete.
5797 | Preventive and Promotive Health Services | Construction of outpatient unit at Bararget dispensary | To construct outpatient unit at Bararget dispensary | Outpatient unit at Bararget dispensary constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.414867, 35.732468 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2020 | 1200000 | 432793.4 | 432793.4 | Equitable | N/A | 432793.4 | 0 | 432793 | 100 | 432793 | 0 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
5798 | Preventive and Promotive Health Services | Construction of general ward and staff house at Keringet sub county hospital | To construct general ward and staff house at Keringet sub county hospital | General ward and staff house at Keringet sub county hospital constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.426253, 35.68717 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 638990 | 638990 | Equitable | N/A | 638990 | 0 | 636411 | 99.6 | 636411 | 2000000 | 2579 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good and in use.
5799 | Preventive and Promotive Health Services | equipping of Mwangate dispensary | To equip Mwangate dispensary with necessary facilities and equipment | Mwangate dispensary equipped | 4130299 | N/A | Kuresoi South | Keringet | -0.446063 35.637432 2561 11.199999809265137 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299850 | 100 | 299850 | 11099 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Yes.
5800 | Preventive and Promotive Health Services | Refurbishment of Chebara Dispensary | To implement refurbishment of chebara dispensary for access to quality healthcare services | Refurbishment of Chebara Dispensary completed | 4130299 | N/A | Kuresoi South | Keringet | -0.47732, 35.679745 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2033 | 810000 | 11099 | 11099 | Equitable | N/A | 11099 | 0 | 798901 | 7198 | 798901 | 11099 | -787802 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5801 | Preventive and Promotive Health Services | Design and Construction of outpatient block | To design and construct outpatient block | Outpatient block designed and constructed | 4130299 | N/A | Bahati | Kiamaina | -0.259097, 36.134247 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999132 | 100 | 1999132 | 0 | 868 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project requires renovation.
5802 | Preventive and Promotive Health Services | Design and Construction of pharmacy and Registry block at Menengai dispensary | To design and construct pharmacy and Registry block at Menengai dispensary | Pharmacy and Registry block at Menengai dispensary designed and constructed | 4130299 | N/A | Bahati | Kiamaina | -0.259333, 36.134116 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2019/2020 | 2000001 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project requires renovation.
5803 | Preventive and Promotive Health Services | construction of Toilet blocks at Mutarakwa and kihingo dispensary | To construct Toilet blocks at Mutarakwa and kihingo dispensary | Toilet blocks at Mutarakwa and kihingo dispensary constructed | 4130299 | N/A | Njoro | Kihingo | -0.475517 35.988007 2287.2999999999997 26.18600082397461 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation is required.
5804 | Preventive and Promotive Health Services | Construction of Kiplembeiyo Dispensary | To construct Kiplembeiyo Dispensary | Kiplembeiyo Dispensary constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.534595 35.578933 2463.8 54.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 1024746.2 | 1024746.2 | Equitable | N/A | 1024746.2 | 0 | 1021185 | 99.7 | 1021185 | 3562 | 3561.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: There is no electricity and gate..
5805 | Preventive and Promotive Health Services | design and construction of Chebotoi dispensary | To design and construct Chebotoi dispensary | Chebotoi dispensary designed and constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.553555, 35.636309 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | It stalled | 4000000 | 3600000 | 3600000 | Equitable | Ward Fund | 3600000 | 0 | 2183050 | 60.6 | 2183050 | 1416950 | 1416950 | Stalled | 25 | 60.6 | More funds required to put up a new block | 2017 | N/A | 1416950 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but the needs of the residents are not met. Contractor: AI contrators. Assessor remarks: The project stalled and it is vandalized.
5806 | Preventive and Promotive Health Services | Construction Of Consultation Rooms In Kiptororo Dispensary | To construct Consultation Rooms In Kiptororo Dispensary | Consultation Rooms In Kiptororo Dispensary constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.377203, 35.505747 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1554159 | 51.8 | 1554159 | 3000000 | 1445841 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The 3 rooms are incomplete,it requires good roofing plastering painting and fiting of window pane.
5807 | Preventive and Promotive Health Services | Construction Of Murinduko Dispensary | To construct Murinduko Dispensary | Murinduko Dispensary constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.322428 35.543765 2615.219 3.438999891281128 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4084035 | 4084035 | 4084035 | Equitable | N/A | 4084035 | 0 | 1554159 | 38.1 | 1554159 | 352647 | 2529876 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Kongoi dispensary lacks sanitary facility ,fence and staff house.
5808 | Preventive and Promotive Health Services | Murinduko Dispensary-Maternity Wing - On Going | To implement murinduko dispensary-maternity wing - on going for access to quality healthcare services | Murinduko Dispensary-Maternity Wing - On Going completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.3246 35.498852 2546.3 22.100000381469727 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 3200000 | 3200000 | Equitable | Ward Fund | 3200000 | 0 | 948599 | 29.6 | 948599 | 0 | 2251401 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project is not functioning.
5809 | Preventive and Promotive Health Services | Construction of Health Centre | To construct Health Centre | Health Centre constructed | 4130299 | N/A | Naivasha | Lakeview | -0.753474, 36.461966 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 860888.9 | 467243 | 467243 | Equitable | Ward Fund | 467243 | 0 | 467243 | 100 | 467243 | 2770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state of repair.
5810 | Preventive and Promotive Health Services | Design and construction of Umoja dispensary | To design and construct Umoja dispensary | Umoja dispensary designed and constructed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.281344, 36.174332 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 2992156 | 99.7 | 2992156 | 0 | 7844 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes very viable. Assessor remarks: Renamed to Nyonjoro Health Center , functional.
5811 | Preventive and Promotive Health Services | Equipping of Kapyemit Dispensary | To equip Kapyemit Dispensary with necessary facilities and equipment | Kapyemit Dispensary equipped | 4130299 | N/A | Njoro | Lare | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 176750 | 176750 | Equitable | N/A | 176750 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
5812 | Preventive and Promotive Health Services | Naishi game dispensary fencing and dumpsite | To implement naishi game dispensary fencing and dumpsite for access to quality healthcare services | Naishi game dispensary fencing and dumpsite completed | 4130299 | N/A | Njoro | Lare | -0.396418 36.018132 2031.9 5.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999850 | 100 | 999850 | 0 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
5813 | Preventive and Promotive Health Services | Renovation of Lare Health Centre | To rehabilitate Lare Health Centre to restore functionality | Lare Health Centre rehabilitated | 4130299 | N/A | Njoro | Lare | -0.446409 36.00843 2071.900146484375 12 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 6858950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
5814 | Preventive and Promotive Health Services | Construction of a perimeter fence around Industrial Area Health Centre | To construct a perimeter fence around Industrial Area Health Centre | A perimeter fence around Industrial Area Health Centre constructed | 4130299 | N/A | Nakuru West | London | -0.283386, 36.043426 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494189 | 99.8 | 2494189 | 1100000 | 5811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
5815 | Preventive and Promotive Health Services | Construction of a waiting bay at FITC Dispensary | To construct a waiting bay at FITC Dispensary | A waiting bay at FITC Dispensary constructed | 4130299 | N/A | Nakuru West | London | -0.279623 36.031717 1873.699951171875 64.0999984741211 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999932 | 100 | 1999932 | 1000000 | 68 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Kitchen and dinning complete.
5816 | Preventive and Promotive Health Services | Expansion of moi Ndabi dispensary | To expand moi Ndabi dispensary to increase capacity | Moi Ndabi dispensary expanded | 4130299 | N/A | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 1400583.4 | 1400583.4 | Equitable | N/A | 1400583.4 | 0 | 1399870 | 99.9 | 1399870 | 1400583 | 713.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5817 | Preventive and Promotive Health Services | Sero maternity | To implement sero maternity for access to quality healthcare services | Sero maternity completed | 4130299 | N/A | Naivasha | Maiella | -0.824917 36.203913 0 400 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997670 | 99.9 | 1997670 | 2330 | 2330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
5818 | Preventive and Promotive Health Services | design and Construction of Kapsiwendet Dispensary | To design and construct Kapsiwendet Dispensary | Kapsiwendet Dispensary designed and constructed | 4130299 | N/A | Molo | Mariashoni | -0.381214, 35.795652 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 3500000 | 9919.6 | 9919.6 | Equitable | N/A | 9919.6 | 0 | 3490080 | 35183.7 | 3490080 | 9920 | -3480160.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank not operational.
5819 | Preventive and Promotive Health Services | design and construction of laboratory and drug store for Marioshoni health centre | To design and construct laboratory and drug store for Marioshoni health centre | Laboratory and drug store for Marioshoni health centre designed and constructed | 4130299 | N/A | Molo | Mariashoni | -0.368528, 35.821334 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998344 | 99.9 | 1998344 | 1656 | 1656 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5820 | Preventive and Promotive Health Services | Construction of Maternity ward and Equipping of dispensary | To construct Maternity ward and Equipping of dispensary | Maternity ward and Equipping of dispensary constructed | 4130299 | N/A | Njoro | Mau Narok | -0.600012 36.007202 0 141 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5839587 | 97.3 | 5839587 | 1197370 | 160413 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs upgrading.
5821 | Preventive and Promotive Health Services | Mwisho Wa Lami - Construction Of Dispensary | To implement mwisho wa lami - construction of dispensary for access to quality healthcare services | Mwisho Wa Lami - Construction Of Dispensary completed | 4130299 | N/A | Njoro | Mau Narok | -0.632973, 35.995962 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 1498 | 1498 | Equitable | N/A | 1498 | 0 | 3498502 | 233544.9 | 3498502 | 1498 | -3497004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: in good state of repair.
5822 | Preventive and Promotive Health Services | Construction of Teret Dispensary | To construct Teret Dispensary | Teret Dispensary constructed | 4130299 | N/A | Njoro | Mauche | -0.452938, 35.950194 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Requires renovation.
5823 | Preventive and Promotive Health Services | Construction and equipping of Taita dispensary | To construct and equip Taita dispensary | Taita dispensary constructed and equipped | 4130299 | N/A | Njoro | Mauche | -0.516652, 35.962658 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2022 | 10000000 | 5755861.6 | 5755861.6 | Equitable | N/A | 5755861.6 | 0 | 5249461 | 91.2 | 5249461 | 506401 | 506400.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Ongoing.
5824 | Preventive and Promotive Health Services | Construction of Maternity wing at Menengai Health Centre | To construct Maternity wing at Menengai Health Centre | Maternity wing at Menengai Health Centre constructed | 4130299 | N/A | Nakuru East | Menengai | -0.266242, 36.100625 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 218/19 | 3500000 | 4500000 | 4500000 | Equitable | Ward Fund | 4500000 | 0 | 1632017 | 36.3 | 1632017 | 2867983 | 2867983 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Vired.
5825 | Completion of a maternity wing and equipping | Completion of a maternity wing and equipping | To complete a maternity wing and equipping | A maternity wing and equipping completed | 4130299 | N/A | Rongai | Menengai West | -0.140853, 36.017118 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 2000000 | 100 | 2000000 | 1999824 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and operational.
5826 | Preventive and Promotive Health Services | Construction Of Menengai Health Centre | To construct Menengai Health Centre | Menengai Health Centre constructed | 4130299 | N/A | Rongai | Menengai West | -0.2466 36.013657 2010.9 9.5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1045897.8 | 1045898 | 1045898 | Equitable | N/A | 1045898 | 0 | 1000940 | 95.7 | 1000940 | 3614260 | 44958 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5827 | Construction of toilets (2 blocks ) at Ol Rongai Dispensary | Construction of toilets (2 blocks ) at Ol Rongai Dispensary | To construct toilets (2 blocks ) at Ol Rongai Dispensary | Toilets (2 blocks ) at Ol Rongai Dispensary constructed | 4130299 | N/A | Rongai | Menengai West | -0.140417, 36.017253 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 999920 | 100 | 999920 | 3614260 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kuria. Assessor remarks: Serves the purpose.
5828 | Preventive and Promotive Health Services | Maternity Wards Menengai Dispensary - On Going | To implement maternity wards menengai dispensary - on going for access to quality healthcare services | Maternity Wards Menengai Dispensary - On Going completed | 4130299 | N/A | Rongai | Menengai West | -0.140657 36.017808 1906.8999999999999 11 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2247896 | 2247896 | 2247896 | Equitable | Ward Fund | 2247896 | 0 | 999980 | 44.5 | 999980 | 1247916 | 1247916 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5829 | Preventive and Promotive Health Services | Completion and equipping of maternity wing at Mangu Dispensary | To complete and equip maternity wing at Mangu Dispensary | Maternity wing at Mangu Dispensary completed and equipped | 4130299 | N/A | Rongai | Menengai West | -0.139944 35.901417 0 699.9990234375 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2499870 | 100 | 2499870 | 2000000 | 130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
5830 | Preventive and Promotive Health Services | Completion of Women and Pediatric Wards at Molo District Hospital | To complete Women and Pediatric Wards at Molo District Hospital | Women and Pediatric Wards at Molo District Hospital completed | 4130299 | N/A | Molo | Molo Central | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5831 | Preventive and Promotive Health Services | Molo Sub County Hospital water tank | To implement molo sub county hospital water tank for access to quality healthcare services | Molo Sub County Hospital water tank completed | 4130299 | N/A | Molo | Molo Central | N/A | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5832 | Preventive and Promotive Health Services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine | To implement rongai turi health centre - renovation of staff houses, piping, and construction of a pit latrine for access to quality healthcare services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine completed | 4130299 | N/A | Rongai | Mosop | -0.252618 35.833533 2133.2999999999997 21 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 232287.6 | 232287.6 | Equitable | N/A | 232287.6 | 0 | 1767712 | 761 | 1767712 | 232288 | -1535424.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra. Assessor remarks: Good.
5833 | Preventive and Promotive Health Services | Proposed Outpatient Block at Muguga Health Centre | To undertake the proposed Outpatient Block at Muguga Health Centre | Proposed Outpatient Block at Muguga Health Centre implemented | 4130299 | N/A | Nakuru East | Nakuru East | -0.310143, 36.145533 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/2017 | 2375679.8 | 547432.8 | 547432.8 | Equitable | N/A | 547432.8 | 0 | 953474 | 174.2 | 953474 | 547433 | -406041.2 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Euphemia general supplies. Assessor remarks: Project ok.
5834 | Preventive and Promotive Health Services | Design and Construction of Nessuit public toilet | To design and construct Nessuit public toilet | Nessuit public toilet designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.389554 35.895707 2419.01162878206 4.1620001792907715 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999300 | 99.9 | 999300 | 0 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The toilet was condemned immediately after construction due to underground water fill up making it difficult to use.
5835 | Preventive and Promotive Health Services | Njokerio Dispensary | To implement njokerio dispensary for access to quality healthcare services | Njokerio Dispensary completed | 4130299 | N/A | Njoro | Njoro | -0.38976, 35.931253 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2015 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999138 | 100 | 1999138 | 862 | 862 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
5836 | Preventive and Promotive Health Services | Construction of Toilets and fencing of Masaita Dispensary | To construct Toilets and fencing of Masaita Dispensary | Toilets and fencing of Masaita Dispensary constructed | 4130299 | N/A | Kuresoi North | Nyota | -0.379295 35.726667 2777 12 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699700 | 100 | 699700 | 41520 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: DREKS ENTERPRISES. Assessor remarks: Good.
5837 | Preventive and Promotive Health Services | Construction, Equipping And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) | To construct and equip And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) | And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) constructed and equipped | 4130299 | N/A | Naivasha | Olkaria | -0.936641 36.369939 1908.19287109375 13.87600040435791 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 1923166 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 8000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes.since the facility they are using is busy. Assessor remarks: The structure there was built by kengen.
5838 | Preventive and Promotive Health Services | Design and Construction of Kamere Public toilets | To design and construct Kamere Public toilets | Kamere Public toilets designed and constructed | 4130299 | N/A | Naivasha | Olkaria | -0.819094, 36.321451 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2499892 | 100 | 2499892 | 0 | 108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project lacks water tank and septic tank needs to be covered.
5839 | Preventive and Promotive Health Services | completion of Sirikwa health centre toilet | To complete Sirikwa health centre toilet | Sirikwa health centre toilet completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.258163, 35.667396 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | 2018/19 | 2018/19 | 2018/19 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399142 | 99.8 | 399142 | 0 | 858 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project has visible cracks, the pit is almost full,.
5840 | Preventive and Promotive Health Services | Construction of Toilets at Gacharage Health Centre | To construct Toilets at Gacharage Health Centre | Toilets at Gacharage Health Centre constructed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.288902, 35.636293 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019/20 | 1200000 | 479251.4 | 479251.4 | Equitable | N/A | 479251.4 | 0 | 476394 | 99.4 | 476394 | 0 | 2857.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not met the needs of the users and residents. Assessor remarks: The project is not in use,the workmanship was poor as result the project has cracks and it has shallow pit.
5841 | Preventive and Promotive Health Services | Renovation And Repair Work At Majani Mingi Dispensary | To rehabilitate Repair Work At Majani Mingi Dispensary to restore functionality | Repair Work At Majani Mingi Dispensary rehabilitated | 4130299 | N/A | Rongai | Soin | -0.04561 36.027826 1647 8 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 537556 | 53.8 | 537556 | 462444 | 462444 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fencing is ongoing.
5842 | Preventive and Promotive Health Services | Construction of a dispensary at Lomolo | To construct a dispensary at Lomolo | A dispensary at Lomolo constructed | 4130299 | N/A | Rongai | Soin | 0.016382, 36.033423 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019/2020 | 3700000 | 1187143.4 | 1187143.4 | Equitable | N/A | 1187143.4 | 0 | 1185416 | 99.9 | 1185416 | 28 | 1727.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require a maternity.
5843 | Preventive and Promotive Health Services | Fencing and installation of a gate at Losibil Dispensary | To secure and installation of a gate at Losibil Dispensary through fencing | And installation of a gate at Losibil Dispensary fenced and secured | 4130299 | N/A | Rongai | Soin | -0.101619 35.990918 1694.5 4.400000095367432 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1223486 | 81.6 | 1223486 | 28 | 276514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Dispensary needs an extra Plastic Tank,.
5844 | Preventive and Promotive Health Services | Construction of Theatre at Subukia sub county Hospital | To construct Theatre at Subukia sub county Hospital | Theatre at Subukia sub county Hospital constructed | 4130299 | N/A | Subukia | Subukia | 0.002605, 36.230324 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2019/20 | 05/03/2019 | 4000000 | 2602037.6 | 2602037.6 | Equitable | N/A | 2602037.6 | 0 | 2536538 | 97.5 | 2536538 | 10000000 | 65499.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. At the time, the facility was in use untill it was changed use.. Viable: Yes. The complex was used as theatre until it was no longer in use as theatre. Contractor: Information not available. Assessor remarks: That's facility now used as a medical supplies store for the subcounty.
5845 | Preventive and Promotive Health Services | Design and Construction of two toilets at the town centre | To design and construct two toilets at the town centre | Two toilets at the town centre designed and constructed | 4130299 | N/A | Subukia | Subukia | 0.001269 36.231898 1992.4000244140625 18.350000381469727 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 1299353.6 | 1299353.6 | Equitable | N/A | 1299353.6 | 0 | 1250000 | 96.2 | 1250000 | 1250000 | 49353.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the project serves the boda boda riders in the area.. Contractor: Information not available. Assessor remarks: The boda boda shades are in use.
5846 | Preventive and Promotive Health Services | Ongoing Project Miloreni Dispensary | To implement ongoing project miloreni dispensary for access to quality healthcare services | Ongoing Project Miloreni Dispensary completed | 4130299 | N/A | Subukia | Subukia | -0.027587 36.17731 2064.2 5 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 0 | 0 | 0 | 674464 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Working.
5847 | Preventive and Promotive Health Services | Construction of Ngesumin-moricho dispensary Nurse station | To construct Ngesumin-moricho dispensary Nurse station | Ngesumin-moricho dispensary Nurse station constructed | 4130299 | N/A | Rongai | Visoi | -0.205477 35.849033 1900.9000244140625 56.099998474121094 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999970 | 100 | 999970 | 30 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition.
5848 | Preventive and Promotive Health Services | Construction of Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto | To construct Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto | Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1793557 | 99.6 | 1793557 | 0 | 6443 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
5849 | Preventive and Promotive Health Services | Construction and equipping of Kabati Dispensary | To construct and equip Kabati Dispensary | Kabati Dispensary constructed and equipped | 4130299 | N/A | Naivasha | Viwandani | -0.72189, 36.444124 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 105095 | 105095 | Equitable | N/A | 105095 | 0 | 105095 | 100 | 105095 | 105095 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and functional.
5850 | Preventive and Promotive Health Services | Construction and equipping of laboratory and and connection to power Simboiyon health centre | To construct and equip laboratory and and connection to power Simboiyon health centre | Laboratory and and connection to power Simboiyon health centre constructed and equipped | 4130299 | N/A | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 700000 | 70135 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
5851 | Preventive and Promotive Health Services | Construction and equipping of laboratory and power at Olgilgei Dispensary | To construct and equip laboratory and power at Olgilgei Dispensary | Laboratory and power at Olgilgei Dispensary constructed and equipped | 4130299 | N/A | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 699700 | 70135 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
5852 | Preventive and Promotive Health Services | Design and Construction of servant houses in Mbogoini | To design and construct servant houses in Mbogoini | Servant houses in Mbogoini designed and constructed | 4130299 | N/A | Subukia | Waseges | 0.193542 36.215443 1698.1 11 | VOTE NO 4565 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1700000 | 985625.6 | 985625.6 | Equitable | N/A | 985625.6 | 0 | 985476 | 100 | 985476 | 0 | 149.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and occupied.
5853 | Rehabilitation of offices | Rehabilitation of offices | To rehabilitate offices to restore functionality | Offices rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3737295 | 3737295 | 3737295 | Equitable | N/A | 3737295 | 0 | 2000000 | 53.5 | 2000000 | 18483845 | 1737295 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5854 | Construction of pit latrines and urinal at soitaran market | Construction of pit latrines and urinal at soitaran market | To construct pit latrines and urinal at soitaran market | Pit latrines and urinal at soitaran market constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.49943, 35.724502 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499837 | 100 | 499837 | 499837 | 163 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
5855 | Construction of market shade, toilets and electricity installation at park view market | Construction of market shade, toilets and electricity installation at park view market | To construct market shade, toilets and electricity installation at park view market | Market shade, toilets and electricity installation at park view market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.36542, 36.05435 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2983365 | 99.4 | 2983365 | 2983365 | 16635 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mugima enterprise. Assessor remarks: Completed.
5856 | Construction of shade at wakulima market and tomato section | Construction of shade at wakulima market and tomato section | To construct shade at wakulima market and tomato section | Shade at wakulima market and tomato section constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285266, 36.077239 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1380000 | 92 | 1380000 | 1498915 | 120000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for rehabilitation.
5857 | construction and installation of gates at Githioro market | construction and installation of gates at Githioro market | To construct and installation of gates at Githioro market | And installation of gates at Githioro market constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.263495, 36.188863 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/2019 | 448311 | 448311 | 448311 | Equitable | N/A | 448311 | 0 | 429790 | 95.9 | 429790 | 429790 | 18521 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Feroda limited. Assessor remarks: Gates vandalised, no good will from community.
5858 | Construction of Mbaruk Market stalls | Construction of Mbaruk Market stalls | To construct Mbaruk Market stalls | Mbaruk Market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.349054, 36.213601 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | No details | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999973 | 100 | 999973 | 1000000 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Contractor: No details. Assessor remarks: The project is not viable..
5859 | Construction of lock ups in Elburgon town | Construction of lock ups in Elburgon town | To construct lock ups in Elburgon town | Lock ups in Elburgon town constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.412425, 35.578782 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020-2021 | 1380000 | 1380000 | 1380000 | Equitable | N/A | 1380000 | 0 | 7995880 | 579.4 | 7995880 | 1380000 | -6615880 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it completed. Assessor remarks: Bad State.
5860 | Construction of Elementaita youth stalls | Construction of Elementaita youth stalls | To construct Elementaita youth stalls | Elementaita youth stalls constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489341, 36.156986 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 3870671 | 276.5 | 3870671 | 1299600 | -2470671 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Veried.
5861 | Purchase and supply of market umbrellas | Purchase and supply of market umbrellas | To procure and supply market umbrellas | Market umbrellas procured and supplied | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303564, 36.072862 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299999 | 100 | 299999 | 0 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: NikNash investment. Assessor remarks: Could not be traced on the ground for photos.
5862 | Construction of Gilgil market shade and gate | Construction of Gilgil market shade and gate | To construct Gilgil market shade and gate | Gilgil market shade and gate constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504771, 36.328252 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2021/22 | 3374100 | 3374100 | 3374100 | Equitable | N/A | 3374100 | 0 | 2833220 | 84 | 2833220 | 2987503 | 540880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mammeny solutions. Assessor remarks: In good state.
5863 | Construction of Kampi Moto Market | Construction of Kampi Moto Market | To construct Kampi Moto Market | Kampi Moto Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5864 | Construction of Naivasha Fish Market | Construction of Naivasha Fish Market | To construct Naivasha Fish Market | Naivasha Fish Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5865 | Market Rehabilitation and Development | Construction of toilet at Naivasha wholesale site ground | To construct toilet at Naivasha wholesale site ground | Toilet at Naivasha wholesale site ground constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 11000000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5866 | Market Rehabilitation and Development | Market Rehabilitation | To implement market rehabilitation for economic growth and market access | Market Rehabilitation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 4000000 | 2700075 | 5484655 | N/A | N/A | 5484655 | 0 | 2700072 | 100 | 2700072 | 580000 | 3 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5867 | Market Rehabilitation and Development | Naivasha wholesale site drainage works and walk-way improvement | To implement naivasha wholesale site drainage works and walk-way improvement for economic growth and market access | Naivasha wholesale site drainage works and walk-way improvement completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 11000000 | 1598250 | 1598250 | N/A | N/A | 1598250 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5868 | Rehabilitation of markets | Rehabilitation of markets | To rehabilitate markets to restore functionality | Markets rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2020/21 | N/A | 9000000 | 23000000 | 23000000 | Equitable | N/A | 23000000 | 0 | 5989050 | 26 | 5989050 | 18483845 | 17010950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5869 | Rehabilitation of Nasha Market water goods and roof drains works | Rehabilitation of Nasha Market water goods and roof drains works | To rehabilitate Nasha Market water goods and roof drains works to restore functionality | Nasha Market water goods and roof drains works rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 5989050 | 0 | 5989050 | 18483845 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5870 | Rehabilitation of offices | Rehabilitation of offices | To rehabilitate offices to restore functionality | Offices rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 18483845 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5871 | Market Rehabilitation and Development | Replacement of Asbestos roofing sheet pre-painted IT5 and polycarbonate IT5 sheet at Wakulima market | To implement replacement of asbestos roofing sheet pre-painted it5 and polycarbonate it5 sheet at wakulima market for economic growth and market access | Replacement of Asbestos roofing sheet pre-painted IT5 and polycarbonate IT5 sheet at Wakulima market completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 1215420 | 0 | 1215420 | N/A | N/A | 1215420 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5872 | Construction of market stalls in kabatini | Construction of market stalls in kabatini | To construct market stalls in kabatini | Market stalls in kabatini constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.232429, 36.147492 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 912800 | 91.3 | 912800 | 2000000 | 87200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jemach limited. Assessor remarks: Operational,more stalls are required.
5873 | Additional fund to Heshima market drainage works and finishing works | Additional fund to Heshima market drainage works and finishing works | To implement additional fund to heshima market drainage works and finishing works for economic growth and market access | Additional fund to Heshima market drainage works and finishing works completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.244253, 36.112328 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1736293 | 1736293 | 1736293 | Equitable | N/A | 1736293 | 0 | 1631760 | 94 | 1631760 | 0 | 104533 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
5874 | Completion of Heshima Market shed | Completion of Heshima Market shed | To complete Heshima Market shed | Heshima Market shed completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.243603 36.111465 1944.4000244140625 72.9000015258789 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3900000 | 3899500 | 3899500 | Equitable | N/A | 3899500 | 0 | 3899500 | 100 | 3899500 | 3899500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
5875 | Drainage works in Heshima market | Drainage works in Heshima market | To implement drainage works in heshima market for economic growth and market access | Drainage works in Heshima market completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.243576, 36.11146 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1099200 | 99.9 | 1099200 | 1099200 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
5876 | Issuing of market umbrellas for boda boda riders | Issuing of market umbrellas for boda boda riders | To implement issuing of market umbrellas for boda boda riders for economic growth and market access | Issuing of market umbrellas for boda boda riders completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274911 36.052718 1869.877279206451 48.900001525878906 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Curios were vandalised .picture taken where the curios had been constracted.
5877 | Construction of a house at longonot livestock sale yard | Construction of a house at longonot livestock sale yard | To construct a house at longonot livestock sale yard | A house at longonot livestock sale yard constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.886748, 36.498958 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997120 | 99.7 | 997120 | 2936930 | 2880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The market should be modernized.
5878 | Construction of a market at Ngondi Trading Centre | Construction of a market at Ngondi Trading Centre | To construct a market at Ngondi Trading Centre | A market at Ngondi Trading Centre constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3386560 | 3386560 | Equitable | N/A | 3386560 | 0 | 3365400 | 99.4 | 3365400 | 3386560 | 21160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5879 | Construction of modern market at Ngodi | Construction of modern market at Ngodi | To construct modern market at Ngodi | Modern market at Ngodi constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.822037, 36.203716 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995150 | 99.8 | 2995150 | 3000000 | 4850 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Tamiey Creations. Assessor remarks: vandalised gate.
5880 | Construction of a market at Ngondi Trading Centre | Construction of a market at Ngondi Trading Centre | To construct a market at Ngondi Trading Centre | A market at Ngondi Trading Centre constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3386560 | 3386560 | Equitable | N/A | 3386560 | 0 | 3365400 | 99.4 | 3365400 | 3386560 | 21160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
5881 | Construction of Market Stalls (Lock ups) | Construction of Market Stalls (Lock ups) | To construct Market Stalls (Lock ups) | Market Stalls (Lock ups) constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -1.2841, 36.8155 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995600 | 99.8 | 1995600 | 0 | 4400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: need renovation.
5882 | Construction of mangu market | Construction of mangu market | To construct mangu market | Mangu market constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.166756, 36.010995 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2021/22 | 3044694 | 2998000 | 2998000 | Equitable | N/A | 2998000 | 0 | 979740 | 32.7 | 979740 | 2998000 | 2018260 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lam_ac. Assessor remarks: Functional.
5883 | Levelling, fensing and construction of a toilet at ol rongai market | Levelling, fensing and construction of a toilet at ol rongai market | To implement levelling, fensing and construction of a toilet at ol rongai market for economic growth and market access | Levelling, fensing and construction of a toilet at ol rongai market completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.166756 36.010995 1806.5 400 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999499 | 100 | 2999499 | 3000000 | 501 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Microvision. Assessor remarks: Operational.
5884 | Reehabilitation of free area fresh food market(toilets,gates,fencing ) | Reehabilitation of free area fresh food market(toilets,gates,fencing ) | To implement reehabilitation of free area fresh food market(toilets,gates,fencing ) for economic growth and market access | Reehabilitation of free area fresh food market(toilets,gates,fencing ) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.29259, 36.119569 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/2021 | 2558423 | 2558423 | 2558423 | Equitable | N/A | 2558423 | 0 | 2492535 | 97.4 | 2492535 | 2492535 | 65888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Contractor: Greatrift general merchant. Assessor remarks: Toilet condemned and not in use.A permanent fence needed. A gate not installed.
5885 | Construction of modern market stalls at game mwisho | Construction of modern market stalls at game mwisho | To construct modern market stalls at game mwisho | Modern market stalls at game mwisho constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2960772 | 197.4 | 2960772 | 1500000 | -1460772 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
5886 | Supply of market umbrellas | Supply of market umbrellas | To implement supply of market umbrellas for economic growth and market access | Supply of market umbrellas completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499999 | 100 | 499999 | 0 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5887 | Development and Management of Markets | Construction of market shade in Turi market | To construct market shade in Turi market | Market shade in Turi market constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.331113, 35.689531 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 899000 | 99.9 | 899000 | 899000 | 1000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes, once completed. Viable: Yes, once completed. Assessor remarks: The project is from the headquarters budget.
5888 | construction of muricho market toilet | construction of muricho market toilet | To construct muricho market toilet | Muricho market toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399500 | 99.9 | 399500 | 400000 | 500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
5889 | construction of Rongai market stalls | construction of Rongai market stalls | To construct Rongai market stalls | Rongai market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.173526 35.860517 1868.199951171875 54.09400177001953 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999980 | 100 | 3999980 | 4000000 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
5890 | Market Rehabilitation and Development | rehabilitation of muricho market toilet | To rehabilitate muricho market toilet to restore functionality | Muricho market toilet rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399500 | 99.9 | 399500 | 399500 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
5891 | Construction of a market shed at retail market | Construction of a market shed at retail market | To construct a market shed at retail market | A market shed at retail market constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714599, 36.434192 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995020 | 99.8 | 1995020 | 1995020 | 4980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
5892 | Construction of Market Sheds | Construction of Market Sheds | To construct Market Sheds | Market Sheds constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71517 36.434405 1901.0999755859375 4.126999855041504 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
5893 | Additional fund for Simboyon market shed | Additional fund for Simboyon market shed | To implement additional fund for simboyon market shed for economic growth and market access | Additional fund for Simboyon market shed completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 318219 | 318219 | 318219 | Equitable | N/A | 318219 | 0 | 1300000 | 408.5 | 1300000 | 318219 | -981781 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5894 | Construction of Kanyotu market shade | Construction of Kanyotu market shade | To construct Kanyotu market shade | Kanyotu market shade constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.033662 36.226952 1960 8.899999618530273 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497707 | 99.8 | 1497707 | 1497707 | 2293 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Complete.
5895 | Construction of market shade at Simboyon markets | Construction of market shade at Simboyon markets | To construct market shade at Simboyon markets | Market shade at Simboyon markets constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
5896 | Construction of lockups at olenguruone market | Construction of lockups at olenguruone market | To construct lockups at olenguruone market | Lockups at olenguruone market constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.589072, 35.685198 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 3370224 | 3370224 | 3370224 | Equitable | N/A | 3370224 | 0 | 0 | 0 | 0 | 3370224 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: no. Viable: yes, if it was constructed. Assessor remarks: no lockups was constructed.
5897 | Construction of 6 no double unit market stalls at parkview Barut ward | Construction of 6 no double unit market stalls at parkview Barut ward | To construct 6 no double unit market stalls at parkview Barut ward | 6 no double unit market stalls at parkview Barut ward constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2021 | 1413161 | 307996 | 307996 | Equitable | N/A | 307996 | 0 | 307996 | 100 | 307996 | 307996 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SULUHISHO AFRICA LTD. Assessor remarks: Some stalls are functional and some are not.
5898 | Construction of market stalls at barut ward | Construction of market stalls at barut ward | To construct market stalls at barut ward | Market stalls at barut ward constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.32432, 36.05463 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2023 | 1854938 | 1854938 | 1854938 | Equitable | N/A | 1854938 | 0 | 1850000 | 99.7 | 1850000 | 1850000 | 4938 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ventair constructed. Assessor remarks: Completed.
5899 | Fencing and construction of stalls centre at Mlima Ugali | Fencing and construction of stalls centre at Mlima Ugali | To secure and construction of stalls centre at Mlima Ugali through fencing | And construction of stalls centre at Mlima Ugali fenced and secured | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2016 | 1413161 | 2212236 | 2212236 | Equitable | N/A | 2212236 | 0 | 212236 | 9.6 | 212236 | 212236 | 2000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cider collection. Assessor remarks: The fence was looted and stolen..
5900 | Market stalls at parkview | Market stalls at parkview | To implement market stalls at parkview for economic growth and market access | Market stalls at parkview completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2022 | 1413161 | 2613161 | 2613161 | Equitable | N/A | 2613161 | 0 | 1850000 | 70.8 | 1850000 | 1850000 | 763161 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PIKVIRD SUPPLIERS. Assessor remarks: Some stalls are functioning some are not.
5901 | Construction of modern toilet at Kinamba market | Construction of modern toilet at Kinamba market | To construct modern toilet at Kinamba market | Modern toilet at Kinamba market constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1982535 | 99.1 | 1982535 | 1982535 | 17465 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5902 | Construction of banana stalls | Construction of banana stalls | To construct banana stalls | Banana stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 3998750 | 3998750 | Equitable | N/A | 3998750 | 0 | 3998750 | 100 | 3998750 | 3998750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5903 | Construction of market shades at Sugar Cane section in Wakulima Market | Construction of market shades at Sugar Cane section in Wakulima Market | To construct market shades at Sugar Cane section in Wakulima Market | Market shades at Sugar Cane section in Wakulima Market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285277, 36.077248 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193756 | 99.5 | 1193756 | 1424265 | 6244 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Philed wells ltd. Assessor remarks: Need for rehabilitation.
5904 | Construction of market shades at Wakulima Market-Minji section | Construction of market shades at Wakulima Market-Minji section | To construct market shades at Wakulima Market-Minji section | Market shades at Wakulima Market-Minji section constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285416, 36.077196 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2020/21 | 1500000 | 1498915 | 1498915 | Equitable | N/A | 1498915 | 0 | 1498915 | 100 | 1498915 | 1498915 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for rehabilitation roof leakages and lighting.
5905 | Construction of market shades at Wakulima Market- | Construction of market shades at Wakulima Market- | To construct market shades at Wakulima Market- | Market shades at Wakulima Market- constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285416, 36.077196 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2020/21 | 3077006 | 3077006 | 3077006 | Equitable | N/A | 3077006 | 0 | 2997058 | 97.4 | 2997058 | 1498915 | 79948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for rehabilitation roof leakages and lighting.
5906 | Construction of shade at Kinuthia Mbugua Building | Construction of shade at Kinuthia Mbugua Building | To construct shade at Kinuthia Mbugua Building | Shade at Kinuthia Mbugua Building constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2997058 | 149.9 | 2997058 | 1999900 | -997058 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
5907 | construction of shade at sukuma wiki section in wakulima market | construction of shade at sukuma wiki section in wakulima market | To construct shade at sukuma wiki section in wakulima market | Shade at sukuma wiki section in wakulima market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285277, 36.077248 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1424265 | 95 | 1424265 | 1424265 | 75735 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Philed wells ltd. Assessor remarks: Need for rehabilitation.
5908 | Construction of top market shades(transparent) | Construction of top market shades(transparent) | To construct top market shades(transparent) | Top market shades(transparent) constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.284569, 36.075239 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 998160 | 998160 | 998160 | Equitable | N/A | 998160 | 0 | 2997058 | 300.3 | 2997058 | 998160 | -1998898 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5909 | enhancement of renovation of bus stage stalls | enhancement of renovation of bus stage stalls | To implement enhancement of renovation of bus stage stalls for economic growth and market access | enhancement of renovation of bus stage stalls completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 998160 | 998160 | 998160 | Equitable | N/A | 998160 | 0 | 9633950 | 965.2 | 9633950 | 998160 | -8635790 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5910 | painting Nasher market | painting Nasher market | To implement painting nasher market for economic growth and market access | painting Nasher market completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999588 | 100 | 1999588 | 900000 | 412 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5911 | painting wakulima market | painting wakulima market | To implement painting wakulima market for economic growth and market access | painting wakulima market completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999664 | 100 | 2999664 | 1424200 | 336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5912 | Purchase of rollers for the Youth | Purchase of rollers for the Youth | To procure rollers for the Youth | Rollers for the Youth procured | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999900 | 1999900 | Equitable | N/A | 1999900 | 0 | 1996950 | 99.9 | 1996950 | 1996950 | 2950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5913 | Renovation of bus stage stalls | Renovation of bus stage stalls | To rehabilitate bus stage stalls to restore functionality | Bus stage stalls rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3998750 | 399.9 | 3998750 | 1000000 | -2998750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5914 | Rehabilitation of Eburru Market (Drainage) | Rehabilitation of Eburru Market (Drainage) | To rehabilitate Eburru Market (Drainage) to restore functionality | Eburru Market (Drainage) rehabilitated | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996180 | 99.6 | 996180 | 1000000 | 3820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5915 | Construction of gilgil youths business lookups | Construction of gilgil youths business lookups | To construct gilgil youths business lookups | Gilgil youths business lookups constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.498993 36.322424 1990.699951171875 28.434999465942383 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1496820 | 1496820 | Equitable | N/A | 1496820 | 0 | 1496820 | 100 | 1496820 | 1496820 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
5916 | Development and Management of Markets | Completion of Maai Mahiu Market | To complete Maai Mahiu Market | Maai Mahiu Market completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5917 | Development and Management of Markets | Completion of Nasha deck at Nasha Market | To complete Nasha deck at Nasha Market | Nasha deck at Nasha Market completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5918 | Construction of a Market in Kuresoi North | Construction of a Market in Kuresoi North | To construct a Market in Kuresoi North | A Market in Kuresoi North constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5919 | Construction of Kinamba Market | Construction of Kinamba Market | To construct Kinamba Market | Kinamba Market constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5920 | Construction of Market in Kabazi | Construction of Market in Kabazi | To construct Market in Kabazi | Market in Kabazi constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 7000000 | 7000000 | 7000000 | N/A | N/A | 7000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5921 | Construction of Market in Kihingo | Construction of Market in Kihingo | To construct Market in Kihingo | Market in Kihingo constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5922 | construction of market in kiptagich | construction of market in kiptagich | To construct market in kiptagich | Market in kiptagich constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 7000000 | 6300000 | 6300000 | N/A | N/A | 6300000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5923 | Development and Management of Markets | Construction of market in Kiptangwanyi | To construct market in Kiptangwanyi | Market in Kiptangwanyi constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5924 | Construction of Shed and Stalls in Biashara Ward | Construction of Shed and Stalls in Biashara Ward | To construct Shed and Stalls in Biashara Ward | Shed and Stalls in Biashara Ward constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5925 | Purchase and construction of Fish Market in Naivasha | Purchase and construction of Fish Market in Naivasha | To procure and construction of Fish Market in Naivasha | And construction of Fish Market in Naivasha procured | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5926 | Development and Management of Markets | Refurbishment & Drainages works at Top Market - Nakuru East | To implement refurbishment & drainages works at top market - nakuru east for economic growth and market access | Refurbishment & Drainages works at Top Market - Nakuru East completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 8000000 | 7999800 | 7999800 | Equitable | N/A | 7999800 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5927 | Construction of market shades at Karunga Market | Construction of market shades at Karunga Market | To construct market shades at Karunga Market | Market shades at Karunga Market constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.176564, 36.165242 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Sagra holding limited. Assessor remarks: The market has never been occupied.
5928 | Construction of Ingobor stalls | Construction of Ingobor stalls | To construct Ingobor stalls | Ingobor stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.018533 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2342770 | 93.7 | 2342770 | 1000000 | 157230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not. Viable: Not viable. Inaccessibility. Stalled. Assessor remarks: Completed but Not Operational. Poor location of the project. Inaccessibility.
5929 | Construction of Lalwet stalls | Construction of Lalwet stalls | To construct Lalwet stalls | Lalwet stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.05451 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499900 | 100 | 2499900 | 2499900 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been done. Assessor remarks: Not done. There was no land by time of budgeting in 2020 and the land has just been bought recently 2025..
5930 | Construction of market stalls at Ingobor tradinq centre | Construction of market stalls at Ingobor tradinq centre | To construct market stalls at Ingobor tradinq centre | Market stalls at Ingobor tradinq centre constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498900 | 99.8 | 498900 | 2499900 | 1100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Very viable. Require electricity and lab technician and Operationaliza. Assessor remarks: Building well done. Needs electricity and lab technician to operate.
5931 | Construction of Tulwet stalls | Construction of Tulwet stalls | To construct Tulwet stalls | Tulwet stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.05451 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2499900 | 250 | 2499900 | 1000000 | -1499900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been done. Assessor remarks: Not done. There was no land by time of budgeting in 2020 and the land has just been bought recently 2025..
5932 | Additional fund for improving of fish stalls in Rhonda market | Additional fund for improving of fish stalls in Rhonda market | To implement additional fund for improving of fish stalls in rhonda market for economic growth and market access | Additional fund for improving of fish stalls in Rhonda market completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.311198, 36.059481 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3459200 | 86.5 | 3459200 | 4000000 | 540800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Yet to start.
5933 | Construction of market sheds at Mawanga | Construction of market sheds at Mawanga | To construct market sheds at Mawanga | Market sheds at Mawanga constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.268296, 36.107509 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798485 | 99.9 | 2798485 | 3899500 | 1515 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The shed is not in use.
5934 | Construction of double stalls at Burma market | Construction of double stalls at Burma market | To construct double stalls at Burma market | Double stalls at Burma market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.297696, 36.082343 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3893300 | 99.8 | 3893300 | 0 | 6700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect traders from harsh weather conditions.
5935 | Construction of Kayole Market shades | Construction of Kayole Market shades | To construct Kayole Market shades | Kayole Market shades constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.722064, 36.433286 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: On the ground and it not there.
5936 | Construction of Kihoto railway Market shades | Construction of Kihoto railway Market shades | To construct Kihoto railway Market shades | Kihoto railway Market shades constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.722064, 36.433286 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: On the ground and it not there.
5937 | Construction of modern curio shops opposite PGH Nakuru Level 5 hospital | Construction of modern curio shops opposite PGH Nakuru Level 5 hospital | To construct modern curio shops opposite PGH Nakuru Level 5 hospital | Modern curio shops opposite PGH Nakuru Level 5 hospital constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
5938 | Maai mahiu market-Gutters and corridor roofing | Maai mahiu market-Gutters and corridor roofing | To implement maai mahiu market-gutters and corridor roofing for economic growth and market access | Maai mahiu market-Gutters and corridor roofing completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2902739 | 96.8 | 2902739 | 3000000 | 97261 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5939 | Purchase of Market umbrellas for white house and kiratina stalls | Purchase of Market umbrellas for white house and kiratina stalls | To procure Market umbrellas for white house and kiratina stalls | Market umbrellas for white house and kiratina stalls procured | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.273152 36.107904 1867.699951171875 10.253000259399414 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 412864 | 412864 | 412864 | Equitable | N/A | 412864 | 0 | 411502 | 99.7 | 411502 | 0 | 1362 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The school doesn't have a special needs unit. The items were never supplied.
5940 | rehabilitation and maintenance of Kiratina market | rehabilitation and maintenance of Kiratina market | To rehabilitate maintenance of Kiratina market to restore functionality | Maintenance of Kiratina market rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.272594 36.096523 1897.699951171875 10.166999816894531 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3499975 | 3499975.2 | 3499975.2 | Equitable | N/A | 3499975.2 | 0 | 0 | 0 | 0 | 3499975 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
5941 | fencing and construction of toilets at of mang'u market | fencing and construction of toilets at of mang'u market | To secure and construction of toilets at of mang'u market through fencing | And construction of toilets at of mang'u market fenced and secured | 3110599 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.166756 36.010995 1806.5 400 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2999499 | 150 | 2999499 | 2000000 | -999499 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Microvision. Assessor remarks: Operational.
5942 | Construction of Ogilgei market stalls toilets | Construction of Ogilgei market stalls toilets | To construct Ogilgei market stalls toilets | Ogilgei market stalls toilets constructed | 3110599 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.211397 35.852585 1911.5 12.199999809265137 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 446985 | 446985 | 446985 | Equitable | N/A | 446985 | 0 | 435880 | 97.5 | 435880 | 446985 | 11105 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: It is no operational.
5943 | Construction of Langa Langa market(shade,chain-line fence,toilet,10,000L tank) | Construction of Langa Langa market(shade,chain-line fence,toilet,10,000L tank) | To construct Langa Langa market(shade,chain-line fence,toilet,10,000L tank) | Langa Langa market(shade,chain-line fence,toilet,10,000L tank) constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.499203, 36.370633 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 0 | 0 | 0 | 3900000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Not yet complete.
5944 | Construction of Animal markets in Kiambogo Centre | Construction of Animal markets in Kiambogo Centre | To construct Animal markets in Kiambogo Centre | Animal markets in Kiambogo Centre constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.871023, 36.510932 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1242000 | 82.8 | 1242000 | 1242000 | 258000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
5945 | Construction of fresh market shades at free area market | Construction of fresh market shades at free area market | To construct fresh market shades at free area market | Fresh market shades at free area market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292483, 36.119313 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/2020 | 3800000 | 3397402.2 | 3397402.2 | Equitable | N/A | 3397402.2 | 0 | 3397402 | 100 | 3397402 | 3397402 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Strafieldcontractors. Assessor remarks: Project ok.
5946 | construction of juakali shades at free area | construction of juakali shades at free area | To construct juakali shades at free area | Juakali shades at free area constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292922, 36.120356 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3498560 | 100 | 3498560 | 3498560 | 1440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterorises. Assessor remarks: Space is small.
5947 | construction of juakali stalls at free area | construction of juakali stalls at free area | To construct juakali stalls at free area | Juakali stalls at free area constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292922, 36.120356 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 3498560 | 3498560 | Equitable | N/A | 3498560 | 0 | 3498560 | 100 | 3498560 | 3498560 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterorises. Assessor remarks: Space is small.
5948 | Construction of Free area mtumba stalls | Construction of Free area mtumba stalls | To construct Free area mtumba stalls | Free area mtumba stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293153, 36.120236 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995000 | 99.8 | 2995000 | 2995000 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Magnate limited. Assessor remarks: Project ok.
5949 | Building of market shade at Narasha | Building of market shade at Narasha | To implement building of market shade at narasha for economic growth and market access | Building of market shade at Narasha completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.91594 36.267962 1948.27 1.2860000133514404 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 998770 | 998770 | Equitable | N/A | 998770 | 0 | 711889 | 71.3 | 711889 | 998770 | 286881 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: The people are not using. Assessor remarks: Not standard.
5950 | Building of market stalls at Raplands | Building of market stalls at Raplands | To implement building of market stalls at raplands for economic growth and market access | Building of market stalls at Raplands completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.938119, 36.364961 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3300044 | 3300044 | 3300044 | Equitable | N/A | 3300044 | 0 | 3287672 | 99.6 | 3287672 | 3287672 | 12372 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed awaiting electricity.
5951 | Market Rehabilitation and Development | Construction of fish market stalls | To construct fish market stalls | Fish market stalls constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817264, 36.326217 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 4834865 | 4825320 | 4825320 | Equitable | N/A | 4825320 | 0 | 4209000 | 87.2 | 4209000 | 612400 | 616320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but the model is not secure for the purpose. Contractor: Northern city. Assessor remarks: Completed but not operational.
5952 | Market Rehabilitation and Development | Costruction of fish market stalls | To implement costruction of fish market stalls for economic growth and market access | Costruction of fish market stalls completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817264, 36.326217 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 4834865 | 4834865 | 4834865 | Equitable | N/A | 4834865 | 0 | 4209000 | 87.1 | 4209000 | 4825320 | 625865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but the model is not secure for the purpose. Contractor: Northern city. Assessor remarks: Completed but not operational.
5953 | Rehabilitation of muchorwe market shed and drainage | Rehabilitation of muchorwe market shed and drainage | To rehabilitate muchorwe market shed and drainage to restore functionality | Muchorwe market shed and drainage rehabilitated | 3110599 | Other Infrastructure and Civil Works | Molo | Turi | -0.330032, 35.68764 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 773004 | 773004 | 773004 | Equitable | N/A | 773004 | 0 | 770430 | 99.7 | 770430 | 7000000 | 2574 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage is blocked.
5954 | Generator and cream separator- Suka farmers Cooperative | Generator and cream separator- Suka farmers Cooperative | To implement generator and cream separator- suka farmers cooperative for economic growth and market access | Generator and cream separator- Suka farmers Cooperative completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 8000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5955 | Purchase of land and construction of organic and fish market | Purchase of land and construction of organic and fish market | To acquire land and construct organic and fish market | Land acquired and organic and fish market constructed | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
5956 | Purchase of land for construction of a market at Kayole | Purchase of land for construction of a market at Kayole | To acquire land for construction of a market at Kayole | Land for construction of a market at Kayole acquired | 3130101 | Acquisition of Land | Naivasha | Lakeview | -0.748186, 36.465787 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No done. Assessor remarks: Land not purchased.
5957 | Purchase of land for Langalanga Centre Market | Purchase of land for Langalanga Centre Market | To acquire land for Langalanga Centre Market | Land for Langalanga Centre Market acquired | 3130101 | Acquisition of Land | Gilgil | Murindat | -0.49925, 36.370528 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2400000 | 34.3 | 2400000 | 2400000 | 4600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Peter Wambugu. Assessor remarks: Land purchased.
5958 | Purchase of land for Langalanga Centre Market | Purchase of land for Langalanga Centre Market | To acquire land for Langalanga Centre Market | Land for Langalanga Centre Market acquired | 3130101 | Acquisition of Land | Gilgil | Murindat | -0.49925, 36.370528 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2400000 | 34.3 | 2400000 | 2400000 | 4600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Peter Wambugu. Assessor remarks: Land purchased.
5959 | construction of professional shoe shine stalls | construction of professional shoe shine stalls | To construct professional shoe shine stalls | Professional shoe shine stalls constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.588741, 35.685356 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2022 | 996953.3 | 996953.3 | 996953.3 | Equitable | N/A | 996953.3 | 0 | 0 | 0 | 0 | 996953 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet started. Viable: not yet stared. Assessor remarks: it doesn't exist.
5960 | Rehabilitation of the Olenguruone Market drainage | Rehabilitation of the Olenguruone Market drainage | To rehabilitate the Olenguruone Market drainage to restore functionality | The Olenguruone Market drainage rehabilitated | 4130299 | N/A | Kuresoi South | Amalo | -0.589169, 35.685563 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2020 | 500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 996953 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: drainage needs covering to avoid accident or grid to avoid blockages.
5961 | Design and construction of Toilets and infrastractures at NASHA market | Design and construction of Toilets and infrastractures at NASHA market | To design and construct Toilets and infrastractures at NASHA market | Toilets and infrastractures at NASHA market designed and constructed | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 8000000 | 4816735 | 4816735 | Equitable | N/A | 4816735 | 0 | 4816735 | 100 | 4816735 | 1178018 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5962 | wholesale market sewer system | wholesale market sewer system | To implement wholesale market sewer system for economic growth and market access | wholesale market sewer system completed | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1493256.4 | 1493256.4 | Equitable | N/A | 1493256.4 | 0 | 1493256 | 100 | 1493256 | 1493256 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5963 | Construction and rehabilitation of Githioro market | Construction and rehabilitation of Githioro market | To construct and rehabilitation of Githioro market | And rehabilitation of Githioro market constructed | 4130299 | N/A | Bahati | Dundori | -0.263465, 36.188982 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/2019 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596977 | 99.9 | 3596977 | 429790 | 3023 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be operationalized.
5964 | Fencing and Gate at Mbaruk Market | Fencing and Gate at Mbaruk Market | To secure and Gate at Mbaruk Market through fencing | And Gate at Mbaruk Market fenced and secured | 4130299 | N/A | Gilgil | Eburru-Mbaruk | -0.34847, 36.217858 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2022 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 886900 | 98.5 | 886900 | 0 | 13100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not at all. Contractor: No details. Assessor remarks: Not viable project.
5965 | Construction of Elburgon market | Construction of Elburgon market | To construct Elburgon market | Elburgon market constructed | 4130299 | N/A | Molo | Elburgon | -0.303366 35.81419 0 2000 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 6900000 | 8300000 | 8300000 | Equitable | N/A | 8300000 | 0 | 7995880 | 96.3 | 7995880 | 1000000 | 304120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Yet to start.
5966 | Construction of Kiptangwany market | Construction of Kiptangwany market | To construct Kiptangwany market | Kiptangwany market constructed | 4130299 | N/A | Gilgil | Elementaita | -0.56569, 36.116668 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 995000 | 33.2 | 995000 | 2999100 | 2005000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but brought down to pave way for ESP Market.
5967 | Design and construction of Trade one stop shop | Design and construction of Trade one stop shop | To design and construct Trade one stop shop | Trade one stop shop designed and constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2019/20 | N/A | 10000001 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
5968 | Laying of cabro and drainage at Wakulima Wholesale Market | Laying of cabro and drainage at Wakulima Wholesale Market | To implement laying of cabro and drainage at wakulima wholesale market for economic growth and market access | Laying of cabro and drainage at Wakulima Wholesale Market completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5969 | Proposed Construction of 2 No. Markets Sheds at Molo Market, Molo Central Ward, Molo Sub County | Proposed Construction of 2 No. Markets Sheds at Molo Market, Molo Central Ward, Molo Sub County | To undertake the proposed Construction of 2 No. Markets Sheds at Molo Market, Molo Central Ward, Molo Sub County | Proposed Construction of 2 No. Markets Sheds at Molo Market, Molo Central Ward, Molo Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 8500000 | 8500000 | 8500000 | Equitable | N/A | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5970 | Proposed Construction of 2 No. Markets Sheds at Subukia Market, Subukia Ward, Subukia Sub County | Proposed Construction of 2 No. Markets Sheds at Subukia Market, Subukia Ward, Subukia Sub County | To undertake the proposed Construction of 2 No. Markets Sheds at Subukia Market, Subukia Ward, Subukia Sub County | Proposed Construction of 2 No. Markets Sheds at Subukia Market, Subukia Ward, Subukia Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 10000000 | 864687 | 864687 | Equitable | N/A | 864687 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5971 | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | To undertake the proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 10283413.1 | 5702703 | 5702703 | Equitable | N/A | 5702703 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5972 | Proposed Construction of Chainlink Fence at Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | Proposed Construction of Chainlink Fence at Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | To undertake the proposed Construction of Chainlink Fence at Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | Proposed Construction of Chainlink Fence at Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5973 | Proposed Construction of Deck at Nasha Market | Proposed Construction of Deck at Nasha Market | To undertake the proposed Construction of Deck at Nasha Market | Proposed Construction of Deck at Nasha Market implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 10000000 | 1178018.3 | 1178018.3 | Equitable | N/A | 1178018.3 | 0 | 0 | 0 | 0 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5974 | Proposed Construction of Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | Proposed Construction of Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | To undertake the proposed Construction of Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County | Proposed Construction of Longonot Livestock Auction Yard in Maai Mahiu Ward Naivasha Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5975 | Proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward | To undertake the proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 5000000 | 4501980 | 4501980 | Equitable | N/A | 4501980 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5976 | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | To undertake the proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 12000000 | 6091798.4 | 6091798.4 | Equitable | N/A | 6091798.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5977 | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | To undertake the proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 8000000 | 7636280 | 7636280 | Equitable | N/A | 7636280 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5978 | Purchase of garbage skips | Purchase of garbage skips | To procure garbage skips | Garbage skips procured | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4600000 | 92 | 4600000 | 0 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5979 | purchase of Skip loader | purchase of Skip loader | To procure Skip loader | Skip loader procured | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 8500000 | 8500000 | 8500000 | N/A | N/A | 8500000 | 0 | 4600000 | 54.1 | 4600000 | 0 | 3900000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5980 | construction of Karunga market sheds | construction of Karunga market sheds | To construct Karunga market sheds | Karunga market sheds constructed | 4130299 | N/A | Bahati | Kabatini | -0.176515 36.165128 2111.300048828125 5.685999870300293 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1395190 | 99.7 | 1395190 | 2000000 | 4810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it never met it objective. Contractor: Sagra holding ltd. Assessor remarks: Has never been occupied,market obstructed by other permanent stalls.
5981 | construction of stalls at Kapkures centre | construction of stalls at Kapkures centre | To construct stalls at Kapkures centre | Stalls at Kapkures centre constructed | 4130299 | N/A | Nakuru West | Kapkures | -0.306306, 36.036551 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1492978 | 99.5 | 1492978 | 1000000 | 7022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been implemented. Assessor remarks: Not done. There's no public land available for market and so the stalls were not constructed.
5982 | Construction of stalls at Kapnandi Centre | Construction of stalls at Kapnandi Centre | To construct stalls at Kapnandi Centre | Stalls at Kapnandi Centre constructed | 4130299 | N/A | Nakuru West | Kapkures | -0.306306, 36.036551 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493560 | 99.6 | 1493560 | 1000000 | 6440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been implemented. Assessor remarks: Not done. There's no public land available for market and so the stalls were not constructed.
5983 | Construction of stalls at Tulwet | Construction of stalls at Tulwet | To construct stalls at Tulwet | Stalls at Tulwet constructed | 4130299 | N/A | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999770 | 100 | 1999770 | 1000000 | 230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Not accessible. Assessor remarks: Done but not operational. Poor accessibility.
5984 | Construction of Pondamali fish market fish washing stand connected to the sewer line | Construction of Pondamali fish market fish washing stand connected to the sewer line | To construct Pondamali fish market fish washing stand connected to the sewer line | Pondamali fish market fish washing stand connected to the sewer line constructed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.311409, 36.059612 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499979 | 100 | 1499979 | 0 | 21 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: It was viable but it's a project that has not benefited the residents since it's not yet in use. Contractor: SANKA BUILDERS. Assessor remarks: Floor chipped and potholes,vandalized and needs total renovation to be functional.
5985 | construction of ablution block at Rhonda market | construction of ablution block at Rhonda market | To construct ablution block at Rhonda market | Ablution block at Rhonda market constructed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.311509, 36.059121 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990080 | 99.5 | 1990080 | 1450000 | 9920 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,it was viable but has not met the needs of the residents. Contractor: U187. Assessor remarks: It's fully vandalized, with no water.
5986 | construction of shades for traders in Rhonda market | construction of shades for traders in Rhonda market | To construct shades for traders in Rhonda market | Shades for traders in Rhonda market constructed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.311362, 36.059653 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019/20 | 4000001 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3982860 | 99.6 | 3982860 | 4000000 | 17140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,if secured and renovated. Contractor: FLASHDIL CONNECTIONS. Assessor remarks: Chipped floors and vandalized doorsrs.
5987 | Design and construction of market shed at Keringet market | Design and construction of market shed at Keringet market | To design and construct market shed at Keringet market | Market shed at Keringet market designed and constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.424835 35.690778 2699.500244140625 92.9000015258789 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 4617339 | 4617339 | 4617339 | Equitable | N/A | 4617339 | 0 | 4521428 | 97.9 | 4521428 | 1000000 | 95911 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
5988 | Construction of market sheds, installation of flood lights and water point in Heshima market | Construction of market sheds, installation of flood lights and water point in Heshima market | To construct market sheds, installation of flood lights and water point in Heshima market | Market sheds, installation of flood lights and water point in Heshima market constructed | 4130299 | N/A | Bahati | Kiamaina | -0.243599 36.111466 1944.4000244140625 65.03500366210938 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596178 | 99.9 | 3596178 | 0 | 3822 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
5989 | Construction of Latrine at Kiptororo market | Construction of Latrine at Kiptororo market | To construct Latrine at Kiptororo market | Latrine at Kiptororo market constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.382307, 35.503002 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599590 | 99.9 | 599590 | 600000 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: It's not complete,not functional.It requires painting and renovations of the floor and doors.
5990 | Design and construction of curios and bodaboda sheds in London centre | Design and construction of curios and bodaboda sheds in London centre | To design and construct curios and bodaboda sheds in London centre | Curios and bodaboda sheds in London centre designed and constructed | 4130299 | N/A | Nakuru West | London | -0.269087, 36.052567 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2020 | 3491553.6 | 3491554 | 3491554 | Equitable | N/A | 3491554 | 0 | 3399947 | 97.4 | 3399947 | 0 | 91607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floor of the sheds are in bad shape.
5991 | Construction of curio shops/stalls in London Ward | Construction of curio shops/stalls in London Ward | To construct curio shops/stalls in London Ward | Curio shops/stalls in London Ward constructed | 4130299 | N/A | Nakuru West | London | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3395523 | 97 | 3395523 | 0 | 104477 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
5992 | rehabilitation of Longonot Market | rehabilitation of Longonot Market | To rehabilitate Longonot Market to restore functionality | Longonot Market rehabilitated | 4130299 | N/A | Naivasha | Maai Mahiu | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3991386 | 99.8 | 3991386 | 0 | 8614 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
5993 | Construction of additional roof, gutters and cementing of Maai Mahiu Market | Construction of additional roof, gutters and cementing of Maai Mahiu Market | To construct additional roof, gutters and cementing of Maai Mahiu Market | Additional roof, gutters and cementing of Maai Mahiu Market constructed | 4130299 | N/A | Naivasha | Maai Mahiu | -0.980266, 36.584425 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999435 | 100 | 2999435 | 2032772 | 565 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floor to be renovated.
5994 | Construction of toilet at Kasarani market | Construction of toilet at Kasarani market | To construct toilet at Kasarani market | Toilet at Kasarani market constructed | 4130299 | N/A | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 500000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 699973 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
5995 | Construction of Lock-ups in Menengai West ward | Construction of Lock-ups in Menengai West ward | To construct Lock-ups in Menengai West ward | Lock-ups in Menengai West ward constructed | 4130299 | N/A | Rongai | Menengai West | -0.146632, 36.009458 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997749 | 99.9 | 2997749 | 3000000 | 2251 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: No. Assessor remarks: Not yet.
5996 | construction of open air market in menengai west | construction of open air market in menengai west | To construct open air market in menengai west | Open air market in menengai west constructed | 4130299 | N/A | Rongai | Menengai West | -0.263634 36.00289 1974.9000244140625 98.4000015258789 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997749 | 99.9 | 2997749 | 3000000 | 2251 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
5997 | Design and construction of market stalls | Design and construction of market stalls | To design and construct market stalls | Market stalls designed and constructed | 4130299 | N/A | Rongai | Mosop | -0.211397 35.852585 1911.5 12.199999809265137 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 1982730 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1951584 | 97.6 | 1951584 | 446985 | 48416 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: It is no operational.
5998 | Construction of Market sheds, toilet and water tank at Gitare market | Construction of Market sheds, toilet and water tank at Gitare market | To construct Market sheds, toilet and water tank at Gitare market | Market sheds, toilet and water tank at Gitare market constructed | 4130299 | N/A | Gilgil | Murindat | -0.409902, 36.312118 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2996964 | 99.9 | 2996964 | 3900000 | 3036 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONSTRUCTION. Assessor remarks: On-going.
5999 | Construction of market sheds and toilets at Ihendu Market | Construction of market sheds and toilets at Ihendu Market | To construct market sheds and toilets at Ihendu Market | Market sheds and toilets at Ihendu Market constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.750667 36.524997 2120.10009765625 4.375999927520752 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2987510 | 99.6 | 2987510 | 3631685 | 12490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete but not operational trade department to operationalize it.
6000 | Construction of market sheds and toilets at Kinungi Markets | Construction of market sheds and toilets at Kinungi Markets | To construct market sheds and toilets at Kinungi Markets | Market sheds and toilets at Kinungi Markets constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.750667 36.524997 2120.10009765625 4.375999927520752 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998071 | 99.9 | 2998071 | 3631685 | 1929 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete but not operational trade department to operationalize it.
6001 | Construction of market sheds and toilets at Maraigushu Market | Construction of market sheds and toilets at Maraigushu Market | To construct market sheds and toilets at Maraigushu Market | Market sheds and toilets at Maraigushu Market constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.750667 36.524997 2120.10009765625 4.375999927520752 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998020 | 99.9 | 2998020 | 3631685 | 1980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete but not operational trade department to operationalize it.
6002 | Proposed Construction of 6 No doors pit latrine for Ihindu Market | Proposed Construction of 6 No doors pit latrine for Ihindu Market | To undertake the proposed Construction of 6 No doors pit latrine for Ihindu Market | Proposed Construction of 6 No doors pit latrine for Ihindu Market implemented | 4130299 | N/A | Naivasha | Naivasha East | -0.840408, 36.550014 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2013-14 | 1053130.36 | 1053130 | 1053130 | Equitable | N/A | 1053130 | 0 | 2987510 | 283.7 | 2987510 | 1053130 | -1934380 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
6003 | Rehabilitation of Ihindu Market sheds | Rehabilitation of Ihindu Market sheds | To rehabilitate Ihindu Market sheds to restore functionality | Ihindu Market sheds rehabilitated | 4130299 | N/A | Naivasha | Naivasha East | -0.840475, 36.549935 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2021-22 | 1053131.36 | 1053130 | 1053130 | Equitable | N/A | 1053130 | 0 | 1052070 | 99.9 | 1052070 | 1052085 | 1060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
6004 | design and construction of Green food market at Free Area | design and construction of Green food market at Free Area | To design and construct Green food market at Free Area | Green food market at Free Area designed and constructed | 4130299 | N/A | Nakuru East | Nakuru East | -0.292957, 36.119988 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/2018 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1489359 | 99.3 | 1489359 | 4000000 | 10641 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction limited. Assessor remarks: Project.
6005 | design and construction of mitumba market at Free Area | design and construction of mitumba market at Free Area | To design and construct mitumba market at Free Area | Mitumba market at Free Area designed and constructed | 4130299 | N/A | Nakuru East | Nakuru East | -0.292957, 36.119988 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3991444 | 99.8 | 3991444 | 4000000 | 8556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction limited. Assessor remarks: Project.
6006 | Design and construction of Seguton Market Toilets | Design and construction of Seguton Market Toilets | To design and construct Seguton Market Toilets | Seguton Market Toilets designed and constructed | 4130299 | N/A | Kuresoi North | Nyota | -0.372456 35.685272 2759.400146484375 64.0999984741211 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497942 | 99.6 | 497942 | 690896 | 2058 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets were demolished.
6007 | Fencing and Construction of Toilets of Kamwaura market | Fencing and Construction of Toilets of Kamwaura market | To secure and Construction of Toilets of Kamwaura market through fencing | And Construction of Toilets of Kamwaura market fenced and secured | 4130299 | N/A | Kuresoi North | Nyota | -0.412588 35.578735 2528.3 12.899999618530273 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 690896 | 690896 | Equitable | N/A | 690896 | 0 | 690895 | 100 | 690895 | 690896 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: If constructed. Assessor remarks: Stalled, play ground of children..
6008 | Fencing and Construction of Toilets of Mung'etho Market toilet | Fencing and Construction of Toilets of Mung'etho Market toilet | To secure and Construction of Toilets of Mung'etho Market toilet through fencing | And Construction of Toilets of Mung'etho Market toilet fenced and secured | 4130299 | N/A | Kuresoi North | Nyota | -0.412588 35.578735 2528.3 12.899999618530273 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 690896 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: If constructed. Assessor remarks: Stalled, play ground of children..
6009 | Design and construction of stalls and bodaboda shed | Design and construction of stalls and bodaboda shed | To design and construct stalls and bodaboda shed | Stalls and bodaboda shed designed and constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.306041, 36.063317 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 19/20 | 1999937.44 | 1999937 | 1999937 | Equitable | N/A | 1999937 | 0 | 1999937 | 100 | 1999937 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
6010 | Proposed double unit curio shops and bodaboda shed in Mwariki | Proposed double unit curio shops and bodaboda shed in Mwariki | To undertake the proposed double unit curio shops and bodaboda shed in Mwariki | Proposed double unit curio shops and bodaboda shed in Mwariki implemented | 4130299 | N/A | Nakuru West | Rhonda | -0.313546, 36.060871 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 19/20 | 2999959.52 | 2999960 | 2999960 | Equitable | N/A | 2999960 | 0 | 2999960 | 100 | 2999960 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
6011 | Construction of modern stalls in Kipanga | Construction of modern stalls in Kipanga | To construct modern stalls in Kipanga | Modern stalls in Kipanga constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.306454, 36.063687 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2019/20 | 19/20 | 6000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2960772 | 98.7 | 2960772 | 1500000 | 39228 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
6012 | Design and construction of SME stalls in Githima estate | Design and construction of SME stalls in Githima estate | To design and construct SME stalls in Githima estate | SME stalls in Githima estate designed and constructed | 4130299 | N/A | Nakuru West | Shabab | N/A | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 5799981 | 5799981 | 5799981 | Equitable | N/A | 5799981 | 0 | 5799981 | 100 | 5799981 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6013 | fencing of subukia market | fencing of subukia market | To secure subukia market through fencing | Subukia market fenced and secured | 4130299 | N/A | Subukia | Subukia | 0.00313 36.229321 1992.0999755859375 32.0989990234375 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 3100000 | 2058336.45 | 2058336.45 | Equitable | N/A | 2058336.45 | 0 | 2058372 | 100 | 2058372 | 2058336 | -35.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, the safety and security issues at the facility resolved.. Viable: Yes, the premises and facilities at the market are secured by provision of fence.. Contractor: Details not availed. Assessor remarks: Proposed fencing works completed as per contract period.
6014 | Construction of toilet at Rongai market | Construction of toilet at Rongai market | To construct toilet at Rongai market | Toilet at Rongai market constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998052 | 99.8 | 998052 | 4000000 | 1948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6015 | Completion of market shed in Viwandani market | Completion of market shed in Viwandani market | To complete market shed in Viwandani market | Market shed in Viwandani market completed | 4130299 | N/A | Naivasha | Viwandani | -0.715028 36.434489 1901.199951171875 11.230999946594238 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2956408 | 98.5 | 2956408 | 366850 | 43592 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
6016 | Construction of market sheds in Viwandani market | Construction of market sheds in Viwandani market | To construct market sheds in Viwandani market | Market sheds in Viwandani market constructed | 4130299 | N/A | Naivasha | Viwandani | -0.718566 36.435168 1899.5 17.726999282836914 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3965912 | 99.1 | 3965912 | 3000000 | 34088 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
6017 | Laying of cabro and drainage works in Viwandani market | Laying of cabro and drainage works in Viwandani market | To implement laying of cabro and drainage works in viwandani market for economic growth and market access | Laying of cabro and drainage works in Viwandani market completed | 4130299 | N/A | Naivasha | Viwandani | -0.714893 36.434213 1900.199951171875 19.398000717163086 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2991640 | 99.7 | 2991640 | 366850 | 8360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
6018 | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market | To implement plumbing works, sewer connection, drainage connections and electrification at viwandani market for economic growth and market access | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market completed | 4130299 | N/A | Naivasha | Viwandani | -0.715133, 36.434178 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999850 | 100 | 2999850 | 0 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good.
6019 | Rehabilitation of toilets in Viwandani market | Rehabilitation of toilets in Viwandani market | To rehabilitate toilets in Viwandani market to restore functionality | Toilets in Viwandani market rehabilitated | 4130299 | N/A | Naivasha | Viwandani | -0.714472, 36.434091 | VOTE NO 4566 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 366850 | 366850 | Equitable | N/A | 366850 | 0 | 366850 | 100 | 366850 | 366850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
6020 | Infrastructure, Development and Maintenance | Conditional Grant-Road Maintenance Levy Fund | To implement Road Maintenance Levy Fund as per conditional grant requirements | Road Maintenance Levy Fund implemented | 2630201 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2019/20 | N/A | 60221395 | 684422889.25 | 0 | RMLF | RMLF | 0 | 1413175975.45 | 15258043 | 2.2 | 15258043 | 79595019 | 669164846.25 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6021 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Fire station) | To construct & Rehabilitation of buildings (Fire station) | & Rehabilitation of buildings (Fire station) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 7500000 | 7500000 | Equitable | N/A | 7500000 | 0 | 20181765 | 269.1 | 20181765 | 7500000 | -12681765 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6022 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Water Reserviour) | To construct & Rehabilitation of buildings (Water Reserviour) | & Rehabilitation of buildings (Water Reserviour) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 4537500 | 4537500 | Equitable | N/A | 4537500 | 0 | 20000000 | 440.8 | 20000000 | 4537500 | -15462500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6023 | Rehabilitation Non Residential Buildings | Rehabilitation Non Residential Buildings | To rehabilitate Non Residential Buildings to restore functionality | Non Residential Buildings rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 4761483 | 19522964 | 19522964 | Equitable | N/A | 19522964 | 0 | 4000000 | 20.5 | 4000000 | 10000000 | 15522964 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6024 | Infrastructure, Development and Maintenance | Rehabilitation Of Public Works Building | To rehabilitate Public Works Building to restore functionality | Public Works Building rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 4414833 | 44.1 | 4414833 | 10000000 | 5585167 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6025 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of County Major Urban Roads | To construct & Rehabilitation of County Major Urban Roads | & Rehabilitation of County Major Urban Roads constructed | 3110401 | Major Roads | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 20000000 | 100 | 20000000 | 7500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6026 | Grading and murraming and culverts for access roads in Kabazi ward | Grading and murraming and culverts for access roads in Kabazi ward | To improve road infrastructure by grading and murraming and culverts for access roads in Kabazi ward | And culverts for access roads in Kabazi ward graded and murramed | 3110401 | Major Roads | Subukia | Kabazi | -0.07772, 36.17076 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020/21 | 4989241 | 3386875 | 3386875 | Equitable | N/A | 3386875 | 0 | 3386875 | 100 | 3386875 | 3386875 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires additional drainages.
6027 | Infrastructure, Development & Maintenance | Grading and Murraming of Kapigeriet-Sigowet road | To improve road infrastructure by grading and murraming Kapigeriet-Sigowet road | Kapigeriet-Sigowet road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.638958, 35.653353 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1251901 | 89.4 | 1251901 | 80650 | 148099 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6028 | Infrastructure, Development and Maintenance | Grading and Murraming of Sachangwan -Ngeny road | To improve road infrastructure by grading and murraming Sachangwan -Ngeny road | Sachangwan -Ngeny road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.59666, 35.687903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires grading and murraming.
6029 | Infrastructure, Development & Maintenance | Purchase of 1-Acre land to open Timoi-Kapkorio road | To procure 1-Acre land to open Timoi-Kapkorio road | 1-Acre land to open Timoi-Kapkorio road procured | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.573785, 35.697712 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: road yet to be graded. Viable: not yet. Assessor remarks: land has not been bought.
6030 | Infrastructure, Development and Maintenance | Grading and Murraming of Sachangwan -Ngeny road | To improve road infrastructure by grading and murraming Sachangwan -Ngeny road | Sachangwan -Ngeny road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.59666, 35.687903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires grading and murraming.
6031 | Infrastructure, Development & Maintenance | Grading and murraming of Mwariki at Kingongor Barut | To improve road infrastructure by grading and murraming Mwariki at Kingongor Barut | Mwariki at Kingongor Barut graded and murramed | 3110499 | Construction of Roads - Other | NAKURU WEST | BARUT | -0.324324, 36.036613 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 300000 | 10 | 300000 | 3000000 | 2700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Gibboius limited. Assessor remarks: It's good.
6032 | Infrastructure, Development & Maintenance | Laying of cabros at Ravine stage | To implement laying of cabros at ravine stage for road connectivity and accessibility | Laying of cabros at Ravine stage completed | 3110499 | Construction of Roads - Other | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997195 | 99.9 | 1997195 | 0 | 2805 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6033 | Infrastructure, Development & Maintenance | Re-carpeting of Bargain Road | To upgrade Bargain Road through tarmacking for improved road connectivity | Bargain Road tarmacked and upgraded | 3110499 | Construction of Roads - Other | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 4458370 | 148.6 | 4458370 | 3000000 | -1458370 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6034 | Infrastructure, Development & Maintenance | Tarmacking of Shabab stage road | To upgrade Shabab stage road through tarmacking for improved road connectivity | Shabab stage road tarmacked and upgraded | 3110499 | Construction of Roads - Other | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4458370 | 89.2 | 4458370 | 5000000 | 541630 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6035 | Grading and murraming of Mwisho wa Lami-Wamiruri road | Grading and murraming of Mwisho wa Lami-Wamiruri road | To improve road infrastructure by grading and murraming Mwisho wa Lami-Wamiruri road | Mwisho wa Lami-Wamiruri road graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.158331, 36.11871 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1677575 | 88.3 | 1677575 | 1713601 | 222425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need grading.
6036 | Installation of culverts in bahati ward | Installation of culverts in bahati ward | To improve drainage and road access through culvert installation at in bahati ward | Culverts installed at in bahati ward | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.179883, 36.127924 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1320611 | 1320611 | 1320611 | Equitable | N/A | 1320611 | 0 | 1172922 | 88.8 | 1172922 | 1173023 | 147689 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working condition.
6037 | Infrastructure, Development & Maintenance | Construction of boda boda shade at hope well | To construct boda boda shade at hope well | Boda boda shade at hope well constructed | 3110499 | Construction of Roads - Other | Nakuru West | Barut | -0.32042, 36.042 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 409283 | 409283 | 409283 | Equitable | N/A | 409283 | 0 | 1193025 | 291.5 | 1193025 | 409283 | -783742 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s. Luwan Company Limiited. Assessor remarks: Completed.
6038 | Infrastructure, Development and Maintenance | installation of Culverts and gabions at Barut ward | To improve drainage and road access through culvert installation at and gabions at Barut ward | Culverts installed at and gabions at Barut ward | 3110499 | Construction of Roads - Other | Nakuru West | Barut | -0.3424, 36.0423 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1870183 | 93.5 | 1870183 | 2000000 | 129817 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TOPAL ENTERPRISES. Assessor remarks: Completed.
6039 | Infrastructure, Development & Maintenance | Grading and murraming of highland access roads | To improve road infrastructure by grading and murraming highland access roads | Highland access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2077943 | 2077943 | 2077943 | Equitable | N/A | 2077943 | 0 | 1778530 | 85.6 | 1778530 | 2077943 | 299413 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6040 | Infrastructure, Development & Maintenance | Grading and murraming of white weru road | To improve road infrastructure by grading and murraming white weru road | White weru road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.685052, 36.531753 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2550000 | 2550000 | 2550000 | Equitable | N/A | 2550000 | 0 | 2219740 | 87 | 2219740 | 2550000 | 330260 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be redone with gravelling,and drainages.
6041 | Grading, murraming and installation of culverts in White highland road | Grading, murraming and installation of culverts in White highland road | To implement grading, murraming and installation of culverts in white highland road for road connectivity and accessibility | Grading, murraming and installation of culverts in White highland road completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.706577, 36.515368 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 3766343 | 0 | 3766343 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poorly done,needs complete overhaul and repair .and a serious drainage issues during rainy season.
6042 | Infrastructure, Development & Maintenance | Installation of Gituru streetlights | To install Gituru streetlights | Gituru streetlights installed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999970 | 100 | 1999970 | 2000000 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6043 | Infrastructure, Development & Maintenance | Installation of Kinamba streetlights | To install Kinamba streetlights | Kinamba streetlights installed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.732811, 36.468193 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999986 | 100 | 2999986 | 3000000 | 14 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs for additional streetlights.
6044 | Installation of Ndoroto culverts | Installation of Ndoroto culverts | To install Ndoroto culverts | Ndoroto culverts installed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.688732, 36.526562 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2229056 | 92.9 | 2229056 | 0 | 170944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage enhancement and unclogging.
6045 | Installation of Nyonjoro culverts | Installation of Nyonjoro culverts | To install Nyonjoro culverts | Nyonjoro culverts installed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.688732, 36.526562 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407944 | 93.9 | 1407944 | 0 | 92056 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage enhancement and unclogging.
6046 | Infrastructure, Development & Maintenance | Completion of constructing club lane drainage | To complete constructing club lane drainage | Constructing club lane drainage completed | 3110499 | Construction of Roads - Other | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 17955 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6047 | Infrastructure, Development & Maintenance | Construction of cabro and bollards along Gussii road and drainage works | To construct cabro and bollards along Gussii road and drainage works | Cabro and bollards along Gussii road and drainage works constructed | 3110499 | Construction of Roads - Other | Nakuru East | Biashara-Nakuru | -0.285386, 36.075142 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/22 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3074125 | 87.8 | 3074125 | 3074125 | 425875 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very functional.
6048 | Infrastructure, Development & Maintenance | Maintenance of streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1606500 | 160.7 | 1606500 | 1000000 | -606500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6049 | Grading and levelling of Endarasha/ market/jua kali road | Grading and levelling of Endarasha/ market/jua kali road | To improve road accessibility by grading and levelling of Endarasha/ market/jua kali road | And levelling of Endarasha/ market/jua kali road graded | 3110499 | Construction of Roads - Other | BAHATI | DUNDORI | -0.254689, 36.236709 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1903850 | 95.2 | 1903850 | 550 | 96150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms splendid builder's and contractors ltd. Assessor remarks: Good since was done again under Imarisha Barabara.
6050 | Infrastructure, Development & Maintenance | Grading, murraming ang gravelling of roads in dundori | To implement grading, murraming ang gravelling of roads in dundori for road connectivity and accessibility | Grading, murraming ang gravelling of roads in dundori completed | 3110499 | Construction of Roads - Other | BAHATI | DUNDORI | -0.269, 36.182413 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 5700000 | 5300000 | 5300000 | Equitable | N/A | 5300000 | 0 | 2722767 | 51.4 | 2722767 | 2722767 | 2577233 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Daphy holdings Ltd. Assessor remarks: Require Maintenance.
6051 | Infrastructure, Development & Maintenance | Dundori Roads rehabilitation (hire of machinery and equipments) | To implement dundori roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Dundori Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.27406, 36.190413 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 0 | 1825079 | Equitable | N/A | 1825079 | 0 | 1825079 | 0 | 1825079 | 1825079 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance and drainage.
6052 | Grading and levelling of Endarasha/ market/jua kali road | Grading and levelling of Endarasha/ market/jua kali road | To improve road accessibility by grading and levelling of Endarasha/ market/jua kali road | And levelling of Endarasha/ market/jua kali road graded | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.254689, 36.236709 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1903850 | 95.2 | 1903850 | 550 | 96150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms splendid builder's and contractors ltd. Assessor remarks: Good since was done again under Imarisha Barabara.
6053 | Hire of equipments through boresha barabara | Hire of equipments through boresha barabara | To implement hire of equipments through boresha barabara for road connectivity and accessibility | Hire of equipments through boresha barabara completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.257888, 36.236098 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999300 | 100 | 1999300 | 2000000 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms cCenmi Marchants. Assessor remarks: Dilapidated road.
6054 | Installation of highmast floodlights meter at kiwamu dispensary and dundori health center and other repairs | Installation of highmast floodlights meter at kiwamu dispensary and dundori health center and other repairs | To improve security lighting through high mast floodlight installation at s meter at kiwamu dispensary and dundori health center and other repairs | High mast floodlight installed at s meter at kiwamu dispensary and dundori health center and other repairs | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.237126, 36.167582 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 2103400 | 2103.4 | 2103400 | 100000 | -2003400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
6055 | Infrastructure, Development and Maintenance | Murraming and culverts in Dundori access roads | To implement murraming and culverts in dundori access roads for road connectivity and accessibility | Murraming and culverts in Dundori access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 943870 | 94.4 | 943870 | 943870 | 56130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
6056 | Infrastructure, Development and Maintenance | Murraming and culverts in Githioro access roads | To implement murraming and culverts in githioro access roads for road connectivity and accessibility | Murraming and culverts in Githioro access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 978180 | 97.8 | 978180 | 978180 | 21820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
6057 | Infrastructure, Development and Maintenance | Murraming and culverts in Mugwathi giachonge access roads | To implement murraming and culverts in mugwathi giachonge access roads for road connectivity and accessibility | Murraming and culverts in Mugwathi giachonge access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 975250 | 97.5 | 975250 | 975250 | 24750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
6058 | Infrastructure, Development & Maintenance | Grading and Murraming of Highway, Laikipia university, Mbaruk, Echariria road | To improve road infrastructure by grading and murraming Highway, Laikipia university, Mbaruk, Echariria road | Highway, Laikipia university, Mbaruk, Echariria road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | EBURRU-MBARUK | -0.291385, 36.086452 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1983900 | 99.2 | 1983900 | 1983900 | 16100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No value. Viable: No , No machinary used as per information gathered. Contractor: Unspecified. Assessor remarks: Poor work.
6059 | Infrastructure, Development & Maintenance | Grading and murraming of morgen-suguloi road | To improve road infrastructure by grading and murraming morgen-suguloi road | Morgen-suguloi road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | EBURRU-MBARUK | -0.626301, 36.2802 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 18-20 | 1998220 | 1998220 | 1998220 | Equitable | N/A | 1998220 | 0 | 1893424 | 94.8 | 1893424 | 1998220 | 104796 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Need repair.
6060 | Infrastructure, Development & Maintenance | Grading and murraming of Stage I - corner mbaya Road | To improve road infrastructure by grading and murraming Stage I - corner mbaya Road | Stage I - corner mbaya Road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | EBURRU-MBARUK | -0.348556, 36.178127 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 19/20 | 2669078 | 2669078 | 2669078 | Equitable | N/A | 2669078 | 0 | 1472275 | 55.2 | 1472275 | 1602020 | 1196803 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: No. Bad state. Contractor: Unspecified. Assessor remarks: Road need murraming and expansion.
6061 | Infrastructure, Development & Maintenance | Murraming of ST. Stephen secondary Road | To implement murraming of st. stephen secondary road for road connectivity and accessibility | Murraming of ST. Stephen secondary Road completed | 3110499 | Construction of Roads - Other | MOLO | ELBURGON | -0.294954, 35.766447 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1100000 | 73.3 | 1100000 | 1500000 | 400000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road should be marked st Stephen primary,not st,Stephen secondary.
6062 | Infrastructure, Development & Maintenance | Repair of Mwangi Michuki-Witima road | To rehabilitate Mwangi Michuki-Witima road to restore functionality | Mwangi Michuki-Witima road rehabilitated | 3110499 | Construction of Roads - Other | MOLO | ELBURGON | -0.240527, 35.795847 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1292875 | 99.5 | 1292875 | 1300000 | 7125 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
6063 | Infrastructure, Development & Maintenance | rehabilitaion of roads through hire of equipment and machinery in Elementaita ward | To implement rehabilitaion of roads through hire of equipment and machinery in elementaita ward for road connectivity and accessibility | rehabilitaion of roads through hire of equipment and machinery in Elementaita ward completed | 3110499 | Construction of Roads - Other | GILGIL | ELEMENTAITA | -0.595223, 36.121223 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3800952 | 95 | 3800952 | 4000000 | 199048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
6064 | Infrastructure, Development and Maintenance | Grading and murraming of cypress-songoloi junction | To improve road infrastructure by grading and murraming cypress-songoloi junction | Cypress-songoloi junction graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru-Mbaruk | -0.635963, 36.2568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 22-23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 944300 | 94.4 | 944300 | 944300 | 55700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Contractor: Unspecified. Assessor remarks: Road in bad state.
6065 | Infrastructure, Development & Maintenance | Grading and murraming of Galile to transformer road | To improve road infrastructure by grading and murraming Galile to transformer road | Galile to transformer road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 945200 | 94.5 | 945200 | 945200 | 54800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6066 | Infrastructure, Development & Maintenance | Grading and murraming of Stage I - corner mbaya Road | To improve road infrastructure by grading and murraming Stage I - corner mbaya Road | Stage I - corner mbaya Road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru-Mbaruk | -0.348556, 36.178127 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 19/20 | 2669078 | 4267739 | 4267739 | Equitable | N/A | 4267739 | 0 | 1472275 | 34.5 | 1472275 | 1602020 | 2795464 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: No. Bad state. Contractor: Unspecified. Assessor remarks: Road need murraming and expansion.
6067 | Infrastructure, Development & Maintenance | Installation of culverts across the ward | To improve drainage and road access through culvert installation at across the ward | Culverts installed at across the ward | 3110499 | Construction of Roads - Other | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936400 | 93.6 | 936400 | 936400 | 63600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6068 | Infrastructure, Development and Maintenance | hire of machinery and purchase of murram for Arimi, chieponde, Kasarani comrade, Eastleigh, Jerusalem, Turi farmers Roads | To implement hire of machinery and purchase of murram for arimi, chieponde, kasarani comrade, eastleigh, jerusalem, turi farmers roads for road connectivity and accessibility | hire of machinery and purchase of murram for Arimi, chieponde, Kasarani comrade, Eastleigh, Jerusalem, Turi farmers Roads completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.303366, 35.81419 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 3900088 | 3900088 | 3900088 | Equitable | N/A | 3900088 | 0 | 3900088 | 100 | 3900088 | 3900088 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6069 | Infrastructure, Development and Maintenance | Installation of culverts at kapsita roads | To improve drainage and road access through culvert installation at kapsita roads | Culverts installed at kapsita roads | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.289915, 35.773951 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 920145 | 76.7 | 920145 | 1186660 | 279855 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Ye. Viable: Ye. Assessor remarks: Shed need some repair and maintainance.
6070 | Murraming of Kapsita Mitate road | Murraming of Kapsita Mitate road | To implement murraming of kapsita mitate road for road connectivity and accessibility | Murraming of Kapsita Mitate road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.307435, 35.749389 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1100000 | 100 | 1100000 | 1100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6071 | Infrastructure, Development & Maintenance | Repair of Mwangi Michuki-Wetima road | To rehabilitate Mwangi Michuki-Wetima road to restore functionality | Mwangi Michuki-Wetima road rehabilitated | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.240527, 35.795847 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 1300000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1292875 | 129.3 | 1292875 | 1300000 | -292875 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
6072 | Streetlight maintenance across the ward | Streetlight maintenance across the ward | To implement streetlight maintenance across the ward for road connectivity and accessibility | Streetlight maintenance across the ward completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.303366 35.81419 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 385789 | 385789 | 385789 | Equitable | N/A | 385789 | 0 | 0 | 0 | 0 | 385789 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6073 | Infrastructure, Development and Maintenance | Supply of murram at kasarani road | To implement supply of murram at kasarani road for road connectivity and accessibility | Supply of murram at kasarani road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.294048, 35.802135 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1000000 | 50 | 1000000 | 2000000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ys. Assessor remarks: Good roads.
6074 | Infrastructure, Development & Maintenance | Supply of murram at Ndimu primary road | To implement supply of murram at ndimu primary road for road connectivity and accessibility | Supply of murram at Ndimu primary road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.258464, 35.763718 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road motorable.
6075 | Infrastructure, Development and Maintenance | Supply of murram for nyakiambi karunga road | To implement supply of murram for nyakiambi karunga road for road connectivity and accessibility | Supply of murram for nyakiambi karunga road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.284884, 35.845889 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996682 | 99.7 | 996682 | 1000000 | 3318 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
6076 | Infrastructure, Development and Maintenance | completion and back filling of munanda depression culverts | To complete and back filling of munanda depression culverts | And back filling of munanda depression culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.584147, 36.114305 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996948 | 99.8 | 1996948 | 1998100 | 3052 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6077 | Completion of Ndibai bridge | Completion of Ndibai bridge | To complete Ndibai bridge | Ndibai bridge completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.565311 36.117069 1962.699951171875 77.5999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799940 | 100 | 1799940 | 3394694 | 60 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Paved way for market construction.
6078 | Infrastructure, Development and Maintenance | Hire of equipments for maintenance of access roads in Elementaita ward | To implement hire of equipments for maintenance of access roads in elementaita ward for road connectivity and accessibility | Hire of equipments for maintenance of access roads in Elementaita ward completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.559358 36.111862 1961.0999755859375 19.200000762939453 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 8009636 | 6209636 | 15308736 | Equitable | N/A | 15308736 | 0 | 22308736 | 359.3 | 22308736 | 15308736 | -16099100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Most of it has been carried away by Rain.
6079 | Installation of floodlights at Kiambogo,Kanorero,Mitimingi and Kiptangwanyi | Installation of floodlights at Kiambogo,Kanorero,Mitimingi and Kiptangwanyi | To install floodlights at Kiambogo,Kanorero,Mitimingi and Kiptangwanyi | Floodlights at Kiambogo,Kanorero,Mitimingi and Kiptangwanyi installed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.59724, 36.131596 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2403972 | 2403972 | 2403972 | Equitable | N/A | 2403972 | 0 | 2289625 | 95.2 | 2289625 | 2403972 | 114347 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6080 | maintenance of highmast streetlights in Elementaita ward | maintenance of highmast streetlights in Elementaita ward | To implement maintenance of highmast streetlights in elementaita ward for road connectivity and accessibility | maintenance of highmast streetlights in Elementaita ward completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.489651, 36.156922 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 22308736 | 4461.7 | 22308736 | 1500000 | -21808736 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need routine Maintenance.
6081 | Infrastructure, Development & Maintenance | rehabilitaion of roads through hire of equipment and machinery in Elementaita ward | To implement rehabilitaion of roads through hire of equipment and machinery in elementaita ward for road connectivity and accessibility | rehabilitaion of roads through hire of equipment and machinery in Elementaita ward completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.595223, 36.121223 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3800952 | 95 | 3800952 | 4000000 | 199048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
6082 | Infrastructure, Development & Maintenance | Re-tarmacking of 600 metres kisumu road in langa langa estate | To implement re-tarmacking of 600 metres kisumu road in langa langa estate for road connectivity and accessibility | Re-tarmacking of 600 metres kisumu road in langa langa estate completed | 3110499 | Construction of Roads - Other | NAKURU EAST | FLAMINGO | -0.306047, 36.070295 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3447786 | 88.4 | 3447786 | 3900000 | 452214 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Done.
6083 | Infrastructure, Development and Maintenance | Re-tarmacking of 300 m of Nyamira drive in race course estate | To implement re-tarmacking of 300 m of nyamira drive in race course estate for road connectivity and accessibility | Re-tarmacking of 300 m of Nyamira drive in race course estate completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.305175, 36.071498 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/2022 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3426965 | 90.2 | 3426965 | 8839 | 373035 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: In good state.
6084 | Infrastructure, Development & Maintenance | Re-tarmacking of 600 metres kisumu road in langa langa estate | To implement re-tarmacking of 600 metres kisumu road in langa langa estate for road connectivity and accessibility | Re-tarmacking of 600 metres kisumu road in langa langa estate completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.306047, 36.070295 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3447786 | 88.4 | 3447786 | 3900000 | 452214 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Done.
6085 | spot-patching of 500 m of kabete road from Mashindano road(philadelphia church junction) to othaya road junction in the border of race course and langalanga estates | spot-patching of 500 m of kabete road from Mashindano road(philadelphia church junction) to othaya road junction in the border of race course and langalanga estates | To implement spot-patching of 500 m of kabete road from mashindano road(philadelphia church junction) to othaya road junction in the border of race course and langalanga estates for road connectivity and accessibility | spot-patching of 500 m of kabete road from Mashindano road(philadelphia church junction) to othaya road junction in the border of race course and langalanga estates completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.306037, 36.070529 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020-2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998356 | 99.9 | 1998356 | 0 | 1644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Geeel construction. Assessor remarks: Operational.
6086 | Street maintenance across flamingo ward | Street maintenance across flamingo ward | To implement street maintenance across flamingo ward for road connectivity and accessibility | Street maintenance across flamingo ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.302334, 36.072589 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 949100 | 189.8 | 949100 | 500000 | -449100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
6087 | Infrastructure, Development & Maintenance | Grading and gravelling, compaction of bondeni /site B roads and installation of culverts | To improve road accessibility by grading and gravelling, compaction of bondeni /site B roads and installation of culverts | And gravelling, compaction of bondeni /site B roads and installation of culverts graded | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.478848, 36.330813 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1948700 | 97.4 | 1948700 | 2000000 | 51300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6088 | Infrastructure, Development and Maintenance | Grading and gravelling, compaction of Milimani/rereshwa road and installation of culverts. | To improve road accessibility by grading and gravelling, compaction of Milimani/rereshwa road and installation of culverts | And gravelling, compaction of Milimani/rereshwa road and installation of culverts graded | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1970182 | 98.5 | 1970182 | 2000000 | 29818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6089 | Infrastructure, Development & Maintenance | Grading and gravelling, compaction of Ngomongo road, installation of culverts. | To improve road accessibility by grading and gravelling, compaction of Ngomongo road, installation of culverts | And gravelling, compaction of Ngomongo road, installation of culverts graded | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.478848, 36.330813 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1927398 | 96.4 | 1927398 | 1999999 | 72602 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6090 | Infrastructure, Development & Maintenance | Grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | To improve road accessibility by grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | And gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads graded | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.508071, 36.319004 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1855387 | 92.8 | 1855387 | 2000000 | 144613 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainance.
6091 | grading and murraming of teachers A-bishop avenue roads and culverts | grading and murraming of teachers A-bishop avenue roads and culverts | To improve road infrastructure by grading and murraming teachers A-bishop avenue roads and culverts | Teachers A-bishop avenue roads and culverts graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.489145, 36.328342 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1722690 | 86.1 | 1722690 | 277310 | 277310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintainance and culverts needed.
6092 | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge | To implement grading, gravelling and compacting of kariandusi primary school road and installation of culverts / foot bridge for road connectivity and accessibility | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.536368, 36.344783 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990000 | 99.5 | 1990000 | 1990000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Njasing enterprises Ltd. Assessor remarks: Maintainance.
6093 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts | To implement grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1989814 | 99.5 | 1989814 | 1989950 | 10186 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6094 | Infrastructure, Development & Maintenance | Grading, gravelling and compaction of kekopey masai and P.C.E.A church and installation of culverts | To implement grading, gravelling and compaction of kekopey masai and p.c.e.a church and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of kekopey masai and P.C.E.A church and installation of culverts completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.480768, 36.301989 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1809547 | 90.5 | 1809547 | 2000000 | 190453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Mengro production Limited. Assessor remarks: Needs maintainance.
6095 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of mbegi primary school and installation of culverts | To implement grading, gravelling and compaction of mbegi primary school and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of mbegi primary school and installation of culverts completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1952100 | 97.6 | 1952100 | 2000000 | 47900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6096 | Infrastructure, Development and Maintenance | Grading gravelling and compaction of teachers B-flower farm road and installation of culverts | To improve road accessibility by grading gravelling and compaction of teachers B-flower farm road and installation of culverts | Gravelling and compaction of teachers B-flower farm road and installation of culverts graded | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1931872 | 96.6 | 1931872 | 2000000 | 68128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6097 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts and compacting of teachers A - Ebenezar Road | To implement grading, gravelling, installation of culverts and compacting of teachers a - ebenezar road for road connectivity and accessibility | Grading, gravelling, installation of culverts and compacting of teachers A - Ebenezar Road completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.488405, 36.32907 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1982774 | 99.1 | 1982774 | 168 | 17226 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: Needs maintainance and culverts.
6098 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts and compaction of Yu Mwema - Manyatta road | To implement grading, gravelling, installation of culverts and compaction of yu mwema - manyatta road for road connectivity and accessibility | Grading, gravelling, installation of culverts and compaction of Yu Mwema - Manyatta road completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.479745, 36.298072 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1993400 | 99.7 | 1993400 | 1993400 | 6600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s phelmon limited. Assessor remarks: Requires maintainance.
6099 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts at Kekopey police line estate Road | To implement grading, gravelling, installation of culverts at kekopey police line estate road for road connectivity and accessibility | Grading, gravelling, installation of culverts at Kekopey police line estate Road completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.474783, 36.289046 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1951377 | 97.6 | 1951377 | 3623 | 48623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Oriel General suppliers and contractors. Assessor remarks: Regular maintainance of other feeder roads at the estate.
6100 | Infrastructure, Development & Maintenance | Grading, gravelling, Installation of culverts compaction of maji moto - Kigogo road | To implement grading, gravelling, installation of culverts compaction of maji moto - kigogo road for road connectivity and accessibility | Grading, gravelling, Installation of culverts compaction of maji moto - Kigogo road completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.488406 36.329024 2004.300048828125 3.7899999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2929910 | 97.7 | 2929910 | 1410 | 70090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Maintainance.
6101 | grading,gravelling and compaction of syndicate/milimani roads and culverts | grading,gravelling and compaction of syndicate/milimani roads and culverts | To implement grading,gravelling and compaction of syndicate/milimani roads and culverts for road connectivity and accessibility | grading,gravelling and compaction of syndicate/milimani roads and culverts completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.485923, 36.326486 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1952100 | 97.6 | 1952100 | 2000000 | 47900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6102 | Construction of gilgil murindat mbeggi bridge | Construction of gilgil murindat mbeggi bridge | To construct gilgil murindat mbeggi bridge | Gilgil murindat mbeggi bridge constructed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.538348, 36.359 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/2024 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 828680 | 47.4 | 828680 | 1750000 | 921320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Cubango. Assessor remarks: Okay.
6103 | Infrastructure, Development & Maintenance | Gilgil Roads rehabilitation (hire of machinery and equipments) | To implement gilgil roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Gilgil Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.504809 36.322724 1991 11.029999732971191 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496900 | 0 | 1496900 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Petronic Automatic. Assessor remarks: Extention of power from the main power house to the outpatient facility to serve the whole hospital.
6104 | Infrastructure, Development & Maintenance | Grading and gravelling, compaction of bondeni /site B roads and installation of culverts | To improve road accessibility by grading and gravelling, compaction of bondeni /site B roads and installation of culverts | And gravelling, compaction of bondeni /site B roads and installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.478848, 36.330813 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1948700 | 97.4 | 1948700 | 2000000 | 51300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6105 | Infrastructure, Development and Maintenance | Grading and gravelling, compaction of Milimani/rereshwa road and installation of culverts. | To improve road accessibility by grading and gravelling, compaction of Milimani/rereshwa road and installation of culverts | And gravelling, compaction of Milimani/rereshwa road and installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1970182 | 98.5 | 1970182 | 2000000 | 29818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6106 | Infrastructure, Development & Maintenance | Grading and gravelling, compaction of Ngomongo road, installation of culverts. | To improve road accessibility by grading and gravelling, compaction of Ngomongo road, installation of culverts | And gravelling, compaction of Ngomongo road, installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.478848, 36.330813 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999999 | 1999999 | Equitable | N/A | 1999999 | 0 | 1927398 | 96.4 | 1927398 | 1999999 | 72601 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6107 | Infrastructure, Development & Maintenance | Grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | To improve road accessibility by grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | And gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.508071, 36.319004 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1855387 | 92.8 | 1855387 | 2000000 | 144613 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainance.
6108 | grading and murraming of teachers A-bishop avenue roads and culverts | grading and murraming of teachers A-bishop avenue roads and culverts | To improve road infrastructure by grading and murraming teachers A-bishop avenue roads and culverts | Teachers A-bishop avenue roads and culverts graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.489145, 36.328342 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1722690 | 86.1 | 1722690 | 277310 | 277310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintainance and culverts needed.
6109 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts | To implement grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1989814 | 99.5 | 1989814 | 1989950 | 10186 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6110 | Infrastructure, Development & Maintenance | Grading, gravelling and compaction of kekopey masai and P.C.E.A church and installation of culverts | To implement grading, gravelling and compaction of kekopey masai and p.c.e.a church and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of kekopey masai and P.C.E.A church and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.480768, 36.301989 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1809547 | 90.5 | 1809547 | 2000000 | 190453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Mengro production Limited. Assessor remarks: Needs maintainance.
6111 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of mbegi primary school and installation of culverts | To implement grading, gravelling and compaction of mbegi primary school and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of mbegi primary school and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1952100 | 97.6 | 1952100 | 2000000 | 47900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6112 | Infrastructure, Development and Maintenance | Grading gravelling and compaction of teachers B-flower farm road and installation of culverts | To improve road accessibility by grading gravelling and compaction of teachers B-flower farm road and installation of culverts | Gravelling and compaction of teachers B-flower farm road and installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1931872 | 96.6 | 1931872 | 2000000 | 68128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
6113 | grading,gravelling and compaction of syndicate/milimani roads and culverts | grading,gravelling and compaction of syndicate/milimani roads and culverts | To implement grading,gravelling and compaction of syndicate/milimani roads and culverts for road connectivity and accessibility | grading,gravelling and compaction of syndicate/milimani roads and culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.485923, 36.326486 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1952100 | 97.6 | 1952100 | 2000000 | 47900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6114 | Infrastructure, Development & Maintenance | Hire of machines for grading,murraming and installation of culverts | To implement hire of machines for grading,murraming and installation of culverts for road connectivity and accessibility | Hire of machines for grading,murraming and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.514378 36.113223 1835.4000244140625 6 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5999562 | 100 | 5999562 | 6000000 | 438 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6115 | Infrastructure, Development & Maintenance | Labour based drainage and culverts cleaning, bush clearing in Gilgil ward | To implement labour based drainage and culverts cleaning, bush clearing in gilgil ward for road connectivity and accessibility | Labour based drainage and culverts cleaning, bush clearing in Gilgil ward completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.471135 36.286586 1885.699951171875 87.5999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997500 | 99.8 | 997500 | 1000000 | 2500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: Needs maintainance and culverts.
6116 | Infrastructure, Development and Maintenance | Grading and murraming of Mirera Inn-Sanctuary Road | To improve road infrastructure by grading and murraming Mirera Inn-Sanctuary Road | Mirera Inn-Sanctuary Road graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | HELLS GATE | -0.786791, 36.451923 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3752327 | 3752327 | 3752327 | Equitable | N/A | 3752327 | 0 | 420062 | 11.2 | 420062 | 420062 | 3332265 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable and a boost to the community.
6117 | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | To improve road infrastructure by grading and murraming Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | HELLS GATE | -0.778707 36.434856 1925.0999755859375 7.124000072479248 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5790256 | 96.5 | 5790256 | 4467177 | 209744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was at a cost of 2,802,096 some the road was later tarmarked.
6118 | Infrastructure, Development and Maintenance | Cabro paving at Blankets, Free area | To implement cabro paving at blankets, free area for road connectivity and accessibility | Cabro paving at Blankets, Free area completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6119 | Infrastructure, Development & Maintenance | Grading and murraming of Tee Tangi Tano - ndabibi road | To improve road infrastructure by grading and murraming Tee Tangi Tano - ndabibi road | Tee Tangi Tano - ndabibi road graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6120 | Infrastructure, Development & Maintenance | Opening of Industrial Park roads | To improve the condition of Industrial Park roads | Industrial Park roads improved | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 40000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 20000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6121 | Infrastructure, Development and Maintenance | Upgrading of roads in Gilgil | To upgrade roads in Gilgil through tarmacking for improved road connectivity | Roads in Gilgil tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 40000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6122 | Infrastructure, Development and Maintenance | Upgrading of roads in Kiptagich | To upgrade roads in Kiptagich through tarmacking for improved road connectivity | Roads in Kiptagich tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 30000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6123 | Infrastructure, Development & Maintenance | Grading and murraming of laini nyamathi primary road | To improve road infrastructure by grading and murraming laini nyamathi primary road | Laini nyamathi primary road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.78745, 36.508636 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2418750 | 96.8 | 2418750 | 2500000 | 81250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was well done.
6124 | Infrastructure, Development and Maintenance | Grading and murraming of Mirera Inn-Sanctuary Road | To improve road infrastructure by grading and murraming Mirera Inn-Sanctuary Road | Mirera Inn-Sanctuary Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.786791, 36.451923 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3752327 | 3752327 | 3752327 | Equitable | N/A | 3752327 | 0 | 420062 | 11.2 | 420062 | 420062 | 3332265 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable and a boost to the community.
6125 | Infrastructure, Development & Maintenance | Grading and murraming of mwiciringiri mirera road | To improve road infrastructure by grading and murraming mwiciringiri mirera road | Mwiciringiri mirera road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.820065, 36.513418 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2791040 | 93 | 2791040 | 3000000 | 208960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road really needs rehabilitation and bush clearing.
6126 | Infrastructure, Development & Maintenance | Grading and murraming of sactuary full gospel road | To improve road infrastructure by grading and murraming sactuary full gospel road | Sactuary full gospel road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.793857, 36.436324 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2282495 | 2282495 | 2282495 | Equitable | N/A | 2282495 | 0 | 2167320 | 95 | 2167320 | 2282495 | 115175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is still accessible needs few spot filling.
6127 | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | To improve road infrastructure by grading and murraming Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.778707 36.434856 1925.0999755859375 7.124000072479248 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5790256 | 96.5 | 5790256 | 4467177 | 209744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was at a cost of 2,802,096 some the road was later tarmarked.
6128 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of dr ngige road | To implement grading, murraming and compaction of dr ngige road for road connectivity and accessibility | Grading, murraming and compaction of dr ngige road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1768978 | 88.4 | 1768978 | 1768978 | 231022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
6129 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of miti mingi road | To implement grading, murraming and compaction of miti mingi road for road connectivity and accessibility | Grading, murraming and compaction of miti mingi road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2233240 | 89.3 | 2233240 | 2233240 | 266760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
6130 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of mwafrika-makutano road | To implement grading, murraming and compaction of mwafrika-makutano road for road connectivity and accessibility | Grading, murraming and compaction of mwafrika-makutano road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2215345 | 88.6 | 2215345 | 2215345 | 284655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
6131 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of polytechnic nginga road | To implement grading, murraming and compaction of polytechnic nginga road for road connectivity and accessibility | Grading, murraming and compaction of polytechnic nginga road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1773909 | 88.7 | 1773909 | 1773909 | 226091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
6132 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of rubiri road | To implement grading, murraming and compaction of rubiri road for road connectivity and accessibility | Grading, murraming and compaction of rubiri road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1795128 | 89.8 | 1795128 | 1795128 | 204872 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
6133 | Infrastructure, Development & Maintenance | Grading and murraming of Engashura gishagi road | To improve road infrastructure by grading and murraming Engashura gishagi road | Engashura gishagi road graded and murramed | 3110499 | Construction of Roads - Other | BAHATI | KABATINI | -0.222688, 36.170243 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1694984 | 84.7 | 1694984 | 1694982 | 305016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes then. Viable: Yes. Assessor remarks: The road is operational but requires routine maintenance and bush clearing.
6134 | Infrastructure, Development & Maintenance | Murraming and grading of Kigera Road | To implement murraming and grading of kigera road for road connectivity and accessibility | Murraming and grading of Kigera Road completed | 3110499 | Construction of Roads - Other | BAHATI | KABATINI | -0.202596, 36.158646 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495370 | 99.8 | 2495370 | 50 | 4630 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s jateneve enterprises limited. Assessor remarks: Operational.
6135 | Mwaki mugi road works | Mwaki mugi road works | To implement mwaki mugi road works for road connectivity and accessibility | Mwaki mugi road works completed | 3110499 | Construction of Roads - Other | BAHATI | KABATINI | -0.227313, 36.114974 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 1971713 | 1971713 | 1971713 | Equitable | N/A | 1971713 | 0 | 1995780 | 101.2 | 1995780 | 1995780 | -24067 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but needs routine maintenance.
6136 | Infrastructure, Development & Maintenance | Grading, murraming and culverts of access roads in Kabazi | To implement grading, murraming and culverts of access roads in kabazi for road connectivity and accessibility | Grading, murraming and culverts of access roads in Kabazi completed | 3110499 | Construction of Roads - Other | SUBUKIA | KABAZI | -0.100577 36.127123 0 296.77459716796875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3934983 | 3934983 | 3934983 | Equitable | N/A | 3934983 | 0 | 700600 | 17.8 | 700600 | 753183 | 3234383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
6137 | Infrastructure, Development & Maintenance | Kabazi-Gitura road improvement | To implement kabazi-gitura road improvement for road connectivity and accessibility | Kabazi-Gitura road improvement completed | 3110499 | Construction of Roads - Other | SUBUKIA | KABAZI | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 989405 | 98.9 | 989405 | 990100 | 10595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6138 | Infrastructure, Development & Maintenance | Kihoto, Kabazi secondary and Maombi roads improvement | To implement kihoto, kabazi secondary and maombi roads improvement for road connectivity and accessibility | Kihoto, Kabazi secondary and Maombi roads improvement completed | 3110499 | Construction of Roads - Other | SUBUKIA | KABAZI | -0.09011, 36.16711 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2543700 | 97.8 | 2543700 | 2543700 | 56300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
6139 | Infrastructure, Development & Maintenance | Gravelling and grading of Kabianga road | To implement gravelling and grading of kabianga road for road connectivity and accessibility | Gravelling and grading of Kabianga road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2402699 | 2402699 | 2402699 | Equitable | N/A | 2402699 | 0 | 2399705 | 99.9 | 2399705 | 1500000 | 2994 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6140 | Infrastructure, Development & Maintenance | Gravelling and grading of kamara sigowet road | To implement gravelling and grading of kamara sigowet road for road connectivity and accessibility | Gravelling and grading of kamara sigowet road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996766 | 99.8 | 1996766 | 1000000 | 3234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
6141 | Gravelling at boror- haraka road | Gravelling at boror- haraka road | To implement gravelling at boror- haraka road for road connectivity and accessibility | Gravelling at boror- haraka road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.1489, 35.676812 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 200/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498438 | 99.9 | 1498438 | 919820 | 1562 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs repairs and maintenance.
6142 | Gravelling of ADC-Kimogol road | Gravelling of ADC-Kimogol road | To implement gravelling of adc-kimogol road for road connectivity and accessibility | Gravelling of ADC-Kimogol road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.165487, 35.712508 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1775000 | 98.6 | 1775000 | 886760 | 25000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
6143 | Infrastructure, Development & Maintenance | Gravelling of Kamara mau road | To implement gravelling of kamara mau road for road connectivity and accessibility | Gravelling of Kamara mau road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6144 | Gravelling of twin pick to jogoo Road | Gravelling of twin pick to jogoo Road | To implement gravelling of twin pick to jogoo road for road connectivity and accessibility | Gravelling of twin pick to jogoo Road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.17825 35.711258 2501.3 4.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1492937 | 99.5 | 1492937 | 6063 | 7063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
6145 | Infrastructure, Development & Maintenance | Re-carpeting of roads in Kamara ward | To upgrade roads in Kamara ward through tarmacking for improved road connectivity | Roads in Kamara ward tarmacked and upgraded | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.097348 35.675729 2535.7001953125 49.63999938964844 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
6146 | Infrastructure, Development & Maintenance | Grading and gravelling of Kaporus-Kapkali Road | To improve road infrastructure by grading and murraming Kaporus-Kapkali Road | Kaporus-Kapkali Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KERINGET | -0.544877, 35.703545 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6147 | Infrastructure, Development and Maintenance | Grading and gravelling of Chebotoi- Kibirech road | To improve road infrastructure by grading and murraming Chebotoi- Kibirech road | Chebotoi- Kibirech road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.552683, 35.635952 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 980159 | 32.7 | 980159 | 980159 | 2019841 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
6148 | Infrastructure, Development & Maintenance | Grading and gravelling of Kipsongon Road | To improve road infrastructure by grading and murraming Kipsongon Road | Kipsongon Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.579112, 35.549627 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999983 | 100 | 1999983 | 999425 | 17 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable but needs not meet. Assessor remarks: Poor road,.
6149 | Grading and murraming of Kanoito road in Emitik | Grading and murraming of Kanoito road in Emitik | To improve road infrastructure by grading and murraming Kanoito road in Emitik | Kanoito road in Emitik graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.586868 35.6182 2503.6 22.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999860 | 100 | 999860 | 999860 | 140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: In good condition.
6150 | Infrastructure, Development & Maintenance | Grading and murraming of KAPCHELUOCH-TEA ZONE road | To improve road infrastructure by grading and murraming KAPCHELUOCH-TEA ZONE road | KAPCHELUOCH-TEA ZONE road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.643788, 35.602347 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995085 | 99.5 | 995085 | 995085 | 4915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable but high rainfall is a challenge and doesn't adequately meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete but high rainfall is destroying it.
6151 | Infrastructure, Development and Maintenance | Grading and murraming of KOISEGUT-AINAMOI ROAD | To improve road infrastructure by grading and murraming KOISEGUT-AINAMOI ROAD | KOISEGUT-AINAMOI ROAD graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1954250 | 97.7 | 1954250 | 1998080 | 45750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6152 | Infrastructure, Development & Maintenance | Grading and murraming of SAPTET-KIPTAGICH-KAPCHESIMET road | To improve road infrastructure by grading and murraming SAPTET-KIPTAGICH-KAPCHESIMET road | SAPTET-KIPTAGICH-KAPCHESIMET road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.571085 35.613306 2486.000244140625 14.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998833 | 99.9 | 1998833 | 1999849 | 1167 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6153 | Infrastructure, Development & Maintenance | Graveling of 2km road at kongoi secondary-kongoi primary | To implement graveling of 2km road at kongoi secondary-kongoi primary for road connectivity and accessibility | Graveling of 2km road at kongoi secondary-kongoi primary completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.324475, 35.537975 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1962952 | 98.1 | 1962952 | 1962952 | 37048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.The uphill is slippery and muddy , It is impassable during raining season.
6154 | Infrastructure, Development & Maintenance | Gravelling of 1km Kongoi road | To implement gravelling of 1km kongoi road for road connectivity and accessibility | Gravelling of 1km Kongoi road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.177052 35.697812 2487.8 6.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1438000 | 143.8 | 1438000 | 1000000 | -438000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
6155 | Infrastructure, Development & Maintenance | Gravelling of Franksways - Taragonik road | To implement gravelling of franksways - taragonik road for road connectivity and accessibility | Gravelling of Franksways - Taragonik road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.301405, 35.504565 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1438000 | 95.9 | 1438000 | 1438000 | 62000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement should be done,the road is very narrow,poor drainage.
6156 | Infrastructure, Development & Maintenance | Gravelling of Korabarret - Ogilgei corner 7Kms | To implement gravelling of korabarret - ogilgei corner 7kms for road connectivity and accessibility | Gravelling of Korabarret - Ogilgei corner 7Kms completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.177052 35.697812 2487.8 6.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4191310 | 83.8 | 4191310 | 4191500 | 808690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
6157 | Infrastructure, Development & Maintenance | expansion of shuleni tarmac Road in kivumbini ward | To expand shuleni tarmac Road in kivumbini ward to increase capacity | Shuleni tarmac Road in kivumbini ward expanded | 3110499 | Construction of Roads - Other | NAKURU EAST | KIVUMBINI | -0.304157, 36.082921 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july 2022 | 5600001 | 5600000 | 5600000 | Equitable | N/A | 5600000 | 0 | 2132182 | 38.1 | 2132182 | 2133064 | 3467818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes,. Viable: yes. Assessor remarks: chipped with potholes.
6158 | Infrastructure, Development and Maintenance | Construction of Boda boda sheds in kabatini | To construct Boda boda sheds in kabatini | Boda boda sheds in kabatini constructed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.216572 36.163938 2027.0999755859375 24.496999740600586 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 499898 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s alidawn limited. Assessor remarks: The shade was demolished during fencing of the esp market.
6159 | Infrastructure, Development & Maintenance | Grading and murraming of Engashura gishagi road | To improve road infrastructure by grading and murraming Engashura gishagi road | Engashura gishagi road graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.222688, 36.170243 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1694984 | 84.7 | 1694984 | 1694982 | 305016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes then. Viable: Yes. Assessor remarks: The road is operational but requires routine maintenance and bush clearing.
6160 | Infrastructure, Development and Maintenance | Installation of culverts at zakaria access road and murunyu police post | To improve drainage and road access through culvert installation at zakaria access road and murunyu police post | Culverts installed at zakaria access road and murunyu police post | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.216169 36.164536 2031.300048828125 77.5999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 341470 | 85.4 | 341470 | 341470 | 58530 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: Yes. Contractor: Bitro construction ltd. Assessor remarks: Nawasco was handed over but there are unable to manage because of an ongoing court case,.
6161 | Infrastructure, Development and Maintenance | Installation of streetlights across kabatini ward | To improve lighting and safety through installation of solar streetlights at across kabatini ward | Solar streetlights installed at across kabatini ward | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.230574, 36.163072 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 742900 | 49.5 | 742900 | 1500000 | 757100 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational, sensor should be checked.
6162 | Infrastructure, Development & Maintenance | Murraming and grading of Kigera Road | To implement murraming and grading of kigera road for road connectivity and accessibility | Murraming and grading of Kigera Road completed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.202596, 36.158646 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2500000 | 2495420 | 2495420 | Equitable | N/A | 2495420 | 0 | 2495370 | 100 | 2495370 | 50 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s jateneve enterprises limited. Assessor remarks: Operational.
6163 | Mwaki mugi road works | Mwaki mugi road works | To implement mwaki mugi road works for road connectivity and accessibility | Mwaki mugi road works completed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.227313, 36.114974 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 1971713 | 1995780 | 1995780 | Equitable | N/A | 1995780 | 0 | 1995780 | 100 | 1995780 | 1995780 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but needs routine maintenance.
6164 | Additional fund to installation of streetlights in kabazi ward | Additional fund to installation of streetlights in kabazi ward | To implement additional fund to installation of streetlights in kabazi ward for road connectivity and accessibility | Additional fund to installation of streetlights in kabazi ward completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.07772, 36.17076 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 1497715 | 1497.7 | 1497715 | 100000 | -1397715 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires repairs.
6165 | Additional fund to streetlights maintenance in kabazi ward | Additional fund to streetlights maintenance in kabazi ward | To implement additional fund to streetlights maintenance in kabazi ward for road connectivity and accessibility | Additional fund to streetlights maintenance in kabazi ward completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 82646 | 82646 | 82646 | Equitable | N/A | 82646 | 0 | 117354 | 142 | 117354 | 82646 | -34708 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6166 | Enhancement of fuel (murram and machinery) | Enhancement of fuel (murram and machinery) | To implement enhancement of fuel (murram and machinery) for road connectivity and accessibility | Enhancement of fuel (murram and machinery) completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.08223 36.16987 0 1381 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3900000 | 3900000 | 10600000 | Equitable | N/A | 10600000 | 0 | 2410440 | 61.8 | 2410440 | 2411560 | 1489560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
6167 | Infrastructure, Development & Maintenance | Grading, murraming and culverts of access roads in Kabazi | To implement grading, murraming and culverts of access roads in kabazi for road connectivity and accessibility | Grading, murraming and culverts of access roads in Kabazi completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.100577 36.127123 0 296.77459716796875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3934983 | 3934983 | 3934983 | Equitable | N/A | 3934983 | 0 | 700600 | 17.8 | 700600 | 753183 | 3234383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
6168 | Infrastructure, Development and Maintenance | Installation of streetlights in kabazi ward | To improve lighting and safety through installation of solar streetlights at kabazi ward | Solar streetlights installed at kabazi ward | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.077859, 36.171008 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024/25 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 1073520 | 1073.5 | 1073520 | 100000 | -973520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires maintenance.
6169 | Infrastructure, Development & Maintenance | Kabazi-Gitura road improvement | To implement kabazi-gitura road improvement for road connectivity and accessibility | Kabazi-Gitura road improvement completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 990100 | 990100 | Equitable | N/A | 990100 | 0 | 989405 | 99.9 | 989405 | 990100 | 695 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6170 | Infrastructure, Development & Maintenance | Kihoto, Kabazi secondary and Maombi roads improvement | To implement kihoto, kabazi secondary and maombi roads improvement for road connectivity and accessibility | Kihoto, Kabazi secondary and Maombi roads improvement completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.09011, 36.16711 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2600000 | 2543700 | 2543700 | Equitable | N/A | 2543700 | 0 | 2543700 | 100 | 2543700 | 2543700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
6171 | Renovation of boda boda shed | Renovation of boda boda shed | To rehabilitate boda boda shed to restore functionality | Boda boda shed rehabilitated | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.13503, 36.1535 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/22 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: Not Indicated. Assessor remarks: Okay.
6172 | Infrastructure, Development and Maintenance | Streetlight maintenance in kabazi ward | To implement streetlight maintenance in kabazi ward for road connectivity and accessibility | Streetlight maintenance in kabazi ward completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.077907 36.170967 2259.4 8.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 117354 | 117354 | 117354 | Equitable | N/A | 117354 | 0 | 117354 | 100 | 117354 | 117354 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires floor renovation.
6173 | construction of Maigoya bridge | construction of Maigoya bridge | To construct Maigoya bridge | Maigoya bridge constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.20553, 35.711062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998600 | 99.9 | 998600 | 1000000 | 1400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs emergency maintenance with gabions and the road needs to be graded, gravelling and compacting as soon as possible.
6174 | Infrastructure, Development & Maintenance | construction of Muchorwe miti tano road | To construct Muchorwe miti tano road | Muchorwe miti tano road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.07866 35.672895 2565.1 2.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1125810 | 93.8 | 1125810 | 1200000 | 74190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
6175 | Infrastructure, Development & Maintenance | Grading of new roads in kamara ward | To improve road accessibility by grading new roads in kamara ward | New roads in kamara ward graded | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.097348 35.675729 2535.7001953125 49.63999938964844 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1976750 | 98.8 | 1976750 | 2000000 | 23250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
6176 | Infrastructure, Development & Maintenance | Gravelling of Bureti road | To implement gravelling of bureti road for road connectivity and accessibility | Gravelling of Bureti road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.091485 35.684655 2526.9 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1358004 | 90.5 | 1358004 | 1358004 | 141996 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
6177 | Infrastructure, Development & Maintenance | Gravelling of choronok road | To implement gravelling of choronok road for road connectivity and accessibility | Gravelling of choronok road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.194323, 35.678015 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 866056 | 86.6 | 866056 | 973382 | 133944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: The road needs recarpeting, culverts, drainage and expansion.
6178 | Infrastructure, Development & Maintenance | Gravelling of Jogoo - Rironi road | To implement gravelling of jogoo - rironi road for road connectivity and accessibility | Gravelling of Jogoo - Rironi road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.091485 35.684655 2526.9 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1357595 | 90.5 | 1357595 | 1357595 | 142405 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
6179 | Infrastructure, Development & Maintenance | Gravelling of Kabianga Koisegem road | To implement gravelling of kabianga koisegem road for road connectivity and accessibility | Gravelling of Kabianga Koisegem road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.164543 35.706225 2567.9 4.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491780 | 99.5 | 1491780 | 1500000 | 8220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
6180 | Infrastructure, Development & Maintenance | Gravelling of Kamara mau road | To implement gravelling of kamara mau road for road connectivity and accessibility | Gravelling of Kamara mau road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6181 | Infrastructure, Development & Maintenance | Gravelling of Kamara road | To implement gravelling of kamara road for road connectivity and accessibility | Gravelling of Kamara road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6182 | Infrastructure, Development & Maintenance | Gravelling of Kiptenden - Kabianga road | To implement gravelling of kiptenden - kabianga road for road connectivity and accessibility | Gravelling of Kiptenden - Kabianga road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.084693 35.672665 2494 5.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
6183 | Gravelling of koige jogoo road | Gravelling of koige jogoo road | To implement gravelling of koige jogoo road for road connectivity and accessibility | Gravelling of koige jogoo road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.165487, 35.712508 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 886760 | 88.7 | 886760 | 886760 | 113240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
6184 | Gravelling of lower haraka road | Gravelling of lower haraka road | To implement gravelling of lower haraka road for road connectivity and accessibility | Gravelling of lower haraka road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.1489, 35.676812 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 200/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 919820 | 92 | 919820 | 919820 | 80180 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs repairs and maintenance.
6185 | Infrastructure, Development & Maintenance | Gravelling of maraba road | To implement gravelling of maraba road for road connectivity and accessibility | Gravelling of maraba road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 973114 | 97.3 | 973114 | 973114 | 26886 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6186 | Infrastructure, Development & Maintenance | Gravelling of mau road | To implement gravelling of mau road for road connectivity and accessibility | Gravelling of mau road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2348676 | 2348676 | 2348676 | Equitable | N/A | 2348676 | 0 | 2247805 | 95.7 | 2247805 | 2247805 | 100871 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
6187 | Infrastructure, Development & Maintenance | Gravelling of Mau sublocation road | To implement gravelling of mau sublocation road for road connectivity and accessibility | Gravelling of Mau sublocation road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1285930 | 107.2 | 1285930 | 1200000 | -85930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
6188 | Infrastructure, Development & Maintenance | Gravelling of mau summit road | To implement gravelling of mau summit road for road connectivity and accessibility | Gravelling of mau summit road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 975311 | 97.5 | 975311 | 975311 | 24689 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
6189 | Gravelling of mititano and boror road | Gravelling of mititano and boror road | To implement gravelling of mititano and boror road for road connectivity and accessibility | Gravelling of mititano and boror road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17527, 35.70579 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 974555 | 97.5 | 974555 | 974555 | 25445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
6190 | Gravelling of olenguruoni kapsimo two road | Gravelling of olenguruoni kapsimo two road | To implement gravelling of olenguruoni kapsimo two road for road connectivity and accessibility | Gravelling of olenguruoni kapsimo two road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.084835, 35.671908 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2386676 | 95.5 | 2386676 | 2386676 | 113324 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
6191 | Gravelling of sigowet kipsinendet road | Gravelling of sigowet kipsinendet road | To implement gravelling of sigowet kipsinendet road for road connectivity and accessibility | Gravelling of sigowet kipsinendet road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.096665, 35.687013 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1445821 | 96.4 | 1445821 | 1445821 | 54179 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs repairs and maintenance.
6192 | Infrastructure, Development & Maintenance | Gravelling of tarakwet kiwanja road | To implement gravelling of tarakwet kiwanja road for road connectivity and accessibility | Gravelling of tarakwet kiwanja road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.162348, 35.691225 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 916337 | 91.6 | 916337 | 916337 | 83663 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Needs maintenance.
6193 | Gravelling of twin pick to jogoo Road | Gravelling of twin pick to jogoo Road | To implement gravelling of twin pick to jogoo road for road connectivity and accessibility | Gravelling of twin pick to jogoo Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17825 35.711258 2501.3 4.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499000 | 1499000 | Equitable | N/A | 1499000 | 0 | 1492937 | 99.6 | 1492937 | 6063 | 6063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
6194 | Installation high mast (mulika mwizi) across the ward | Installation high mast (mulika mwizi) across the ward | To install high mast (mulika mwizi) across the ward | High mast (mulika mwizi) across the ward installed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.085515, 35.672085 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Perfect.
6195 | Infrastructure, Development & Maintenance | Re-carpeting of roads in Kamara ward | To upgrade roads in Kamara ward through tarmacking for improved road connectivity | Roads in Kamara ward tarmacked and upgraded | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.097348 35.675729 2535.7001953125 49.63999938964844 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
6196 | Installation of streetlights in Kaptembwo Ward | Installation of streetlights in Kaptembwo Ward | To improve lighting and safety through installation of solar streetlights at Kaptembwo Ward | Solar streetlights installed at Kaptembwo Ward | 3110499 | Construction of Roads - Other | Nakuru West | Kaptembwo | -0.30596, 36.050162 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2778520 | 92.6 | 2778520 | 2778520 | 221480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S QUEJ ENTERPRISES. Assessor remarks: In good condition.
6197 | Grading and murraming of bandiat manyibei amab road | Grading and murraming of bandiat manyibei amab road | To improve road infrastructure by grading and murraming bandiat manyibei amab road | Bandiat manyibei amab road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.521822, 35.733788 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1160100 | 89.2 | 1160100 | 1300000 | 139900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
6198 | Infrastructure, Development & Maintenance | Grading and murraming of kapkwen kabungut canaan road | To improve road infrastructure by grading and murraming kapkwen kabungut canaan road | Kapkwen kabungut canaan road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.463515, 35.71759 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1408514 | 88 | 1408514 | 1466400 | 191486 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
6199 | Infrastructure, Development & Maintenance | Grading and murraming of kapsimbeiwo chepitet road | To improve road infrastructure by grading and murraming kapsimbeiwo chepitet road | Kapsimbeiwo chepitet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.485568, 35.718275 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1122417 | 1122417 | 1122417 | Equitable | N/A | 1122417 | 0 | 891958 | 79.5 | 891958 | 925800 | 230459 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
6200 | Infrastructure, Development & Maintenance | Grading and murraming of siongiroi tertit,lelaibei kampi chura road | To improve road infrastructure by grading and murraming siongiroi tertit,lelaibei kampi chura road | Siongiroi tertit,lelaibei kampi chura road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.516748, 35.732193 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1413030 | 88.3 | 1413030 | 1432200 | 186970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
6201 | Infrastructure, Development & Maintenance | Grading and murraming of tendwetn kiptenden danger road | To improve road infrastructure by grading and murraming tendwetn kiptenden danger road | Tendwetn kiptenden danger road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.51114, 35.696668 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2212232 | 88.5 | 2212232 | 2347500 | 287768 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6202 | Infrastructure, Development and Maintenance | Grading and murraming of tulwet jeptagum road | To improve road infrastructure by grading and murraming tulwet jeptagum road | Tulwet jeptagum road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.485652, 35.71835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1904300 | 95.2 | 1904300 | 1904300 | 95700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6203 | Infrastructure, Development & Maintenance | Hiring of wet road equipments | To implement hiring of wet road equipments for road connectivity and accessibility | Hiring of wet road equipments completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.441352, 35.649258 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1000050 | 1000050 | 1000050 | Equitable | N/A | 1000050 | 0 | 1000050 | 100 | 1000050 | 1000050 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yrs. Assessor remarks: Bad.
6204 | Infrastructure, Development & Maintenance | installation of culvert across Keringet ward | To improve drainage and road access through culvert installation at across Keringet ward | Culverts installed at across Keringet ward | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.424285, 35.69566 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 422214 | 84.4 | 422214 | 480480 | 77786 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
6205 | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) | To implement road rehabilitation (hire of machinery (wet rate) for rehabilitation of keringet ward access roads) for road connectivity and accessibility | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.432205, 35.678418 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6206 | Infrastructure, Development & Maintenance | Grading and gravelling of Kaporus-Kapkali Road | To improve road infrastructure by grading and murraming Kaporus-Kapkali Road | Kaporus-Kapkali Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.544877, 35.703545 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6207 | Infrastructure, Development & Maintenance | Grading and murraming of Chepkubei road | To improve road infrastructure by grading and murraming Chepkubei road | Chepkubei road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.421188, 35.696143 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 999532 | 999532 | 999532 | Equitable | N/A | 999532 | 0 | 999532 | 100 | 999532 | 999532 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yrs. Assessor remarks: Good.
6208 | Infrastructure, Development & Maintenance | Grading and murraming of Tendwet Ngunyunyat road | To improve road infrastructure by grading and murraming Tendwet Ngunyunyat road | Tendwet Ngunyunyat road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.501345, 35.701217 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6209 | Infrastructure, Development & Maintenance | Gituamba sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) | To implement gituamba sub location road works(grading,murraming,compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Gituamba sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1694983 | 67.8 | 1694983 | 1694983 | 805017 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
6210 | Infrastructure, Development & Maintenance | Kiamaina sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) | To implement kiamaina sub location road works(grading,murraming,compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Kiamaina sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
6211 | Infrastructure, Development & Maintenance | Menengai sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) | To implement menengai sub location road works(grading,murraming,compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Menengai sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
6212 | Infrastructure, Development and Maintenance | Murraming and compaction of Mchanganyiko access road | To implement murraming and compaction of mchanganyiko access road for road connectivity and accessibility | Murraming and compaction of Mchanganyiko access road completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.261981 36.105315 1904.5999755859375 58.125999450683594 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 397325 | 0 | 397325 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
6213 | Infrastructure, Development and Maintenance | Purchase of culverts for emergency drainage mitigations in the ward | To procure culverts for emergency drainage mitigations in the ward | Culverts for emergency drainage mitigations in the ward procured | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231627 36.116888 1940.699951171875 39.599998474121094 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 752037 | 752037 | 752037 | Equitable | N/A | 752037 | 0 | 750000 | 99.7 | 750000 | 752037 | 2037 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
6214 | Purchase of murram for kiamaina roads projects | Purchase of murram for kiamaina roads projects | To procure murram for kiamaina roads projects | Murram for kiamaina roads projects procured | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231544, 36.116881 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The murram was used for Kiamaina access roads.
6215 | Infrastructure, Development & Maintenance | Rurii sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) | To implement rurii sub location road works(grading,murraming,compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Rurii sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
6216 | Infrastructure, Development & Maintenance | Workers sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) | To implement workers sub location road works(grading,murraming,compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Workers sub location road works(grading,murraming,compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2496750 | 99.9 | 2496750 | 2500000 | 3250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
6217 | Infrastructure, Development & Maintenance | construction and installation of Davishon culverts | To construct and installation of Davishon culverts | And installation of Davishon culverts constructed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.491807 35.995308 2269.3999999999996 13.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2999999 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 971718 | 97.2 | 971718 | 1000000 | 28282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
6218 | Infrastructure, Development & Maintenance | Construction of Kwa ford foot bridge | To construct Kwa ford foot bridge | Kwa ford foot bridge constructed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.475127 35.988002 2285.2 4.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 922621 | 92.3 | 922621 | 1000000 | 77379 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fencing and staff house construction.
6219 | Infrastructure, Development & Maintenance | Hire of equipments for road works | To implement hire of equipments for road works for road connectivity and accessibility | Hire of equipments for road works completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
6220 | Infrastructure, Development & Maintenance | Hire of road works equipments | To implement hire of road works equipments for road connectivity and accessibility | Hire of road works equipments completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2373502 | 2373502 | 2373502 | Equitable | N/A | 2373502 | 0 | 2373502 | 100 | 2373502 | 2373502 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
6221 | Infrastructure, Development & Maintenance | Installation of culverts in kihingo ward | To improve drainage and road access through culvert installation at in kihingo ward | Culverts installed at in kihingo ward | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.397138 35.959772 2227.2000000000003 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1266636 | 84.4 | 1266636 | 1266636 | 233364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6222 | Infrastructure, Development & Maintenance | Kihingo Roads rehabilitation (hire of machinery and equipments) | To implement kihingo roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Kihingo Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.3964, 35.963397 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires grading murraming and compaction.
6223 | Stoo mbili access roads | Stoo mbili access roads | To implement stoo mbili access roads for road connectivity and accessibility | Stoo mbili access roads completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1521944 | 1521944 | 1521944 | Equitable | N/A | 1521944 | 0 | 0 | 0 | 0 | 1334321 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
6224 | Infrastructure, Development & Maintenance | Supply of murram for roads | To implement supply of murram for roads for road connectivity and accessibility | Supply of murram for roads completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
6225 | Infrastructure, Development and Maintenance | Grading and gravelling of Chebotoi- Kibirech road | To improve road infrastructure by grading and murraming Chebotoi- Kibirech road | Chebotoi- Kibirech road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.552683, 35.635952 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2961799 | 2961799 | Equitable | N/A | 2961799 | 0 | 980159 | 33.1 | 980159 | 980159 | 1981640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
6226 | Grading and murraming of Kanoito road in Emitik | Grading and murraming of Kanoito road in Emitik | To improve road infrastructure by grading and murraming Kanoito road in Emitik | Kanoito road in Emitik graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.586868 35.6182 2503.6 22.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999860 | 999860 | Equitable | N/A | 999860 | 0 | 999860 | 100 | 999860 | 999860 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: In good condition.
6227 | Infrastructure, Development & Maintenance | Grading and murraming of KAPCHELUOCH-TEA ZONE road | To improve road infrastructure by grading and murraming KAPCHELUOCH-TEA ZONE road | KAPCHELUOCH-TEA ZONE road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.643788, 35.602347 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 995085 | 995085 | Equitable | N/A | 995085 | 0 | 995085 | 100 | 995085 | 995085 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable but high rainfall is a challenge and doesn't adequately meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete but high rainfall is destroying it.
6228 | Infrastructure, Development and Maintenance | Grading and murraming of kelungula-saptonok road | To improve road infrastructure by grading and murraming kelungula-saptonok road | Kelungula-saptonok road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.58695 35.617962 2455.6 24.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999662 | 100 | 999662 | 999662 | 338 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it is viable. Contractor: Don't know. Assessor remarks: The project is good and it is operational.
6229 | Infrastructure, Development and Maintenance | Grading and murraming of kipkongor road | To improve road infrastructure by grading and murraming kipkongor road | Kipkongor road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 984690 | 98.5 | 984690 | 999425 | 15310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6230 | Infrastructure, Development & Maintenance | Grading and murraming of Kiptagich center access roads | To improve road infrastructure by grading and murraming Kiptagich center access roads | Kiptagich center access roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.570045, 35.622817 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1429390 | 1429390 | 1429390 | Equitable | N/A | 1429390 | 0 | 1363704 | 95.4 | 1363704 | 1399000 | 65686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6231 | Infrastructure, Development and Maintenance | Grading and murraming of KOISEGUT-AINAMOI ROAD | To improve road infrastructure by grading and murraming KOISEGUT-AINAMOI ROAD | KOISEGUT-AINAMOI ROAD graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 2000000 | 1998080 | 1998080 | Equitable | N/A | 1998080 | 0 | 1954250 | 97.8 | 1954250 | 1998080 | 43830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6232 | Infrastructure, Development and Maintenance | Grading and murraming of lelpanga road | To improve road infrastructure by grading and murraming lelpanga road | Lelpanga road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 988500 | 98.9 | 988500 | 999425 | 11500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6233 | Infrastructure, Development and Maintenance | Grading and murraming of Saoset chebotoi road | To improve road infrastructure by grading and murraming Saoset chebotoi road | Saoset chebotoi road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.608392 35.600555 2382.4 90.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999120 | 99.9 | 999120 | 999500 | 880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The road needs to be repaired.
6234 | Infrastructure, Development & Maintenance | Grading and murraming of SAPTET-KIPTAGICH-KAPCHESIMET road | To improve road infrastructure by grading and murraming SAPTET-KIPTAGICH-KAPCHESIMET road | SAPTET-KIPTAGICH-KAPCHESIMET road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.571085 35.613306 2486.000244140625 14.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999849 | 1999849 | Equitable | N/A | 1999849 | 0 | 1998833 | 99.9 | 1998833 | 1999849 | 1016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6235 | Infrastructure, Development and Maintenance | Grading and murraming of suburb bondet road | To improve road infrastructure by grading and murraming suburb bondet road | Suburb bondet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799595 | 99.9 | 799595 | 799600 | 405 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6236 | Infrastructure, Development and Maintenance | Grading and murraming of wamgong road | To improve road infrastructure by grading and murraming wamgong road | Wamgong road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799970 | 100 | 799970 | 799201 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
6237 | Infrastructure, Development and Maintenance | Grading and murraming of zakai soi ararwet road | To improve road infrastructure by grading and murraming zakai soi ararwet road | Zakai soi ararwet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.58695 35.617962 2455.6 24.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799201 | 99.9 | 799201 | 799700 | 799 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it is viable. Contractor: Don't know. Assessor remarks: The project is good and it is operational.
6238 | Infrastructure, Development & Maintenance | Kiptagich Roads rehabilitation (hire of machinery and equipments) | To implement kiptagich roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Kiptagich Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.51523 35.718283 2655.3 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yrs. Assessor remarks: Pump failed.
6239 | Infrastructure, Development & Maintenance | Grading and gravelling of kipkewa-kiamashama road | To improve road infrastructure by grading and murraming kipkewa-kiamashama road | Kipkewa-kiamashama road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.325623, 35.503235 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1459962 | 1459962 | 1459962 | Equitable | N/A | 1459962 | 0 | 1448643 | 99.2 | 1448643 | 1448643 | 11319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It requires routine maintenance,and additional culvert.
6240 | Infrastructure, Development & Maintenance | Grading and murraming of Githima factory-frankyway roads | To improve road infrastructure by grading and murraming Githima factory-frankyway roads | Githima factory-frankyway roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.351533 35.471193 2449 6.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1801260 | 90.1 | 1801260 | 1802235 | 198740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Spor improvement and culvert installation works are due.
6241 | Infrastructure, Development and Maintenance | Grading and murraming of keo primary-kapkilel road | To improve road infrastructure by grading and murraming keo primary-kapkilel road | Keo primary-kapkilel road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.29459, 35.493035 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1459962 | 97.3 | 1459962 | 1459962 | 40038 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
6242 | Infrastructure, Development and Maintenance | grading and murraming of Kuresoi tea - kio primary road | To improve road infrastructure by grading and murraming Kuresoi tea - kio primary road | Kuresoi tea - kio primary road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.29459, 35.493035 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1459962 | 146 | 1459962 | 1000000 | -459962 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
6243 | Infrastructure, Development & Maintenance | Grading, murraming and compaction of Githima banda to Kapsiele road | To implement grading, murraming and compaction of githima banda to kapsiele road for road connectivity and accessibility | Grading, murraming and compaction of Githima banda to Kapsiele road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.302533, 35.5297 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1418630 | 88.7 | 1418630 | 1418630 | 181370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6244 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Kio centre - Githima dispensary road | To implement grading, murraming and compaction of kio centre - githima dispensary road for road connectivity and accessibility | Grading, murraming and compaction of Kio centre - Githima dispensary road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.302533, 35.5297 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In a good stare.
6245 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Migingo Taragonie village road | To implement grading, murraming and compaction of migingo taragonie village road for road connectivity and accessibility | Grading, murraming and compaction of Migingo Taragonie village road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.307553, 35.489587 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1379382 | 86.2 | 1379382 | 1379382 | 220618 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.
6246 | Kiptororo Roads rehabilitation (hire of machinery and equipments) | Kiptororo Roads rehabilitation (hire of machinery and equipments) | To implement kiptororo roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Kiptororo Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.377203, 35.505747 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1200323 | 0 | 1200323 | Equitable | N/A | 1200323 | 0 | 0 | 0 | 0 | 1200323 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was completed.
6247 | Infrastructure, Development and Maintenance | construction of boda boda shed in kivumbini ward | To construct boda boda shed in kivumbini ward | Boda boda shed in kivumbini ward constructed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.296226, 36.084967 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999130 | 99.9 | 999130 | 999900 | 870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Offer shelter for boda boda riders.
6248 | Infrastructure, Development & Maintenance | expansion of shuleni tarmac Road in kivumbini ward | To expand shuleni tarmac Road in kivumbini ward to increase capacity | Shuleni tarmac Road in kivumbini ward expanded | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.304157, 36.082921 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july 2022 | 5600001 | 2200096 | 2200096 | Equitable | N/A | 2200096 | 0 | 2132182 | 96.9 | 2132182 | 2133064 | 67914 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes,. Viable: yes. Assessor remarks: chipped with potholes.
6249 | Infrastructure, Development & Maintenance | Maintenance of street lights across the ward | To implement maintenance of street lights across the ward for road connectivity and accessibility | Maintenance of street lights across the ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.30403, 36.082783 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6250 | Infrastructure, Development & Maintenance | re- tarmacking of roads in kivumbini ward | To implement re- tarmacking of roads in kivumbini ward for road connectivity and accessibility | re- tarmacking of roads in kivumbini ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.304117, 36.082753 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2100500 | 87.5 | 2100500 | 2001400 | 299500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes,provided access to other areas. Assessor remarks: functional but particularly chipped.
6251 | Rehabilitation of road Infrastructure in lakeview ward through boresha barabara | Rehabilitation of road Infrastructure in lakeview ward through boresha barabara | To rehabilitate road Infrastructure in lakeview ward through boresha barabara to restore functionality | Road Infrastructure in lakeview ward through boresha barabara rehabilitated | 3110499 | Construction of Roads - Other | NAIVASHA | LAKEVIEW | -0.751001, 36.459783 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6252 | Infrastructure, Development & Maintenance | Bridge construction on Karimi-Kenyatta | To implement bridge construction on karimi-kenyatta for road connectivity and accessibility | Bridge construction on Karimi-Kenyatta completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.45155 36.029847 2058.1 5.400000095367432 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5900000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3198850 | 100 | 3198850 | 0 | 1150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road need construction.
6253 | Infrastructure, Development & Maintenance | Construction and installation of culverts at Wagatimu | To construct and installation of culverts at Wagatimu | And installation of culverts at Wagatimu constructed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.47127, 36.052492 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1800205 | 360 | 1800205 | 500000 | -1300205 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
6254 | Infrastructure, Development and Maintenance | Grading and murraming of Bagaria - Mwenyere road. | To improve road infrastructure by grading and murraming Bagaria - Mwenyere road | Bagaria - Mwenyere road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2327800 | 93.1 | 2327800 | 2327800 | 172200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
6255 | Infrastructure, Development & Maintenance | Grading and murraming of Caravat - Kianugu - Milimani road. | To improve road infrastructure by grading and murraming Caravat - Kianugu - Milimani road | Caravat - Kianugu - Milimani road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.524718, 36.039202 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999800 | 100 | 1999800 | 1999800 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic condition and need maintenance.
6256 | Infrastructure, Development & Maintenance | Grading and murraming of Gitene - Sinendet Road. | To improve road infrastructure by grading and murraming Gitene - Sinendet Road | Gitene - Sinendet Road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.492042, 36.040327 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499001 | 99.9 | 1499001 | 1499001 | 999 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintence.
6257 | Infrastructure, Development & Maintenance | Grading and murraming of Mugumo - Kwale - Muthiga road. | To improve road infrastructure by grading and murraming Mugumo - Kwale - Muthiga road | Mugumo - Kwale - Muthiga road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.431365, 36.045213 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 40165 | 2 | 40165 | 40165 | 1959835 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need murraming.
6258 | Infrastructure, Development and Maintenance | Grading and murraming of Mwenyere-Milimani road. | To improve road infrastructure by grading and murraming Mwenyere-Milimani road | Mwenyere-Milimani road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 999450 | 66.6 | 999450 | 1000000 | 500550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
6259 | Infrastructure, Development & Maintenance | Grading and murraming of Wambia - Nduriri - Nduriri Juu Borehole road. | To improve road infrastructure by grading and murraming Wambia - Nduriri - Nduriri Juu Borehole road | Wambia - Nduriri - Nduriri Juu Borehole road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.467588 36.031073 2039.4 6.099999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1996550 | 79.9 | 1996550 | 1996550 | 503450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6260 | Infrastructure, Development & Maintenance | Grading, Murraming on Karimi-Kenyatta road | To implement grading, murraming on karimi-kenyatta road for road connectivity and accessibility | Grading, Murraming on Karimi-Kenyatta road completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.384527, 36.016745 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 5900000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2923687 | 97.5 | 2923687 | 2110574 | 76313 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6261 | Infrastructure, Development & Maintenance | Murraming and culverting in Nguriga Centre roads | To implement murraming and culverting in nguriga centre roads for road connectivity and accessibility | Murraming and culverting in Nguriga Centre roads completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.442215, 36.0103 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999144 | 100 | 1999144 | 1808250 | 856 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6262 | construction of motor bikes sheds in Lakeview ward | construction of motor bikes sheds in Lakeview ward | To construct motor bikes sheds in Lakeview ward | Motor bikes sheds in Lakeview ward constructed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.728236, 36.443564 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1495485 | 99.7 | 1495485 | 1500000 | 4515 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6263 | Infrastructure, Development & Maintenance | Grading and gravelling of Catholic, PCEA and game roaf at unity farm | To improve road infrastructure by grading and murraming Catholic, PCEA and game roaf at unity farm | Catholic, PCEA and game roaf at unity farm graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.747324, 36.44922 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2249090 | 90 | 2249090 | 2500000 | 250910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use but need rehabilitation.
6264 | Infrastructure, Development & Maintenance | Grading and gravelling of dumping Road at unity | To improve road infrastructure by grading and murraming dumping Road at unity | Dumping Road at unity graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.762495, 36.464028 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3396260 | 3396260 | 3396260 | Equitable | N/A | 3396260 | 0 | 356233 | 10.5 | 356233 | 356233 | 3040027 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6265 | Infrastructure, Development and Maintenance | Grading and gravelling of Kihoto access road | To improve road infrastructure by grading and murraming Kihoto access road | Kihoto access road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.731075, 36.440704 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2970792 | 84.9 | 2970792 | 3500000 | 529208 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs drainage system.
6266 | Infrastructure, Development and Maintenance | Grading and gravelling of Lakeview estates Road | To improve road infrastructure by grading and murraming Lakeview estates Road | Lakeview estates Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726785, 36.439953 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1784364 | 1784364 | 1784364 | Equitable | N/A | 1784364 | 0 | 1605550 | 90 | 1605550 | 1784364 | 178814 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6267 | Grading and gravelling of landing beach and manera road | Grading and gravelling of landing beach and manera road | To improve road infrastructure by grading and murraming landing beach and manera road | Landing beach and manera road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2229750 | 89.2 | 2229750 | 2500000 | 270250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6268 | Grading and gravelling of Shamahoho Road at Kayole | Grading and gravelling of Shamahoho Road at Kayole | To improve road infrastructure by grading and murraming Shamahoho Road at Kayole | Shamahoho Road at Kayole graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.753103, 36.461344 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 648088 | 92.6 | 648088 | 700000 | 51912 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Accessible.
6269 | Infrastructure, Development & Maintenance | Grading and gravelling of Suberico Road in Lakeview ward | To improve road infrastructure by grading and murraming Suberico Road in Lakeview ward | Suberico Road in Lakeview ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726585, 36.443845 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1454811 | 1454811 | 1454811 | Equitable | N/A | 1454811 | 0 | 1313000 | 90.3 | 1313000 | 1454811 | 141811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need drainages.
6270 | Rehabilitation of road Infrastructure in lakeview ward through boresha barabara | Rehabilitation of road Infrastructure in lakeview ward through boresha barabara | To rehabilitate road Infrastructure in lakeview ward through boresha barabara to restore functionality | Road Infrastructure in lakeview ward through boresha barabara rehabilitated | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.751001, 36.459783 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6271 | Infrastructure, Development & Maintenance | Installation of high mast lighting | To improve security lighting through high mast floodlight installation at lighting | High mast floodlight installed at lighting | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.73156, 36.446771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3797814 | 3797814 | 3797814 | Equitable | N/A | 3797814 | 0 | 3795650 | 99.9 | 3795650 | 3795650 | 2164 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6272 | Infrastructure, Development & Maintenance | Upgrade of access roads in lake view using boresha barabara | To implement upgrade of access roads in lake view using boresha barabara for road connectivity and accessibility | Upgrade of access roads in lake view using boresha barabara completed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726771, 36.43997 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3850000 | 3850000 | 3850000 | Equitable | N/A | 3850000 | 0 | 3850000 | 100 | 3850000 | 3850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6273 | Infrastructure, Development and Maintenance | Grading and murraming of Bagari A road | To improve road infrastructure by grading and murraming Bagari A road | Bagari A road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1825825 | 96.1 | 1825825 | 1853150 | 74175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6274 | Infrastructure, Development and Maintenance | Grading and murraming of Block three road | To improve road infrastructure by grading and murraming Block three road | Block three road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1863883 | 98.1 | 1863883 | 1867950 | 36117 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6275 | Infrastructure, Development and Maintenance | Grading and murraming of Forest road | To improve road infrastructure by grading and murraming Forest road | Forest road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2767829 | 92.3 | 2767829 | 2110574 | 232171 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6276 | Infrastructure, Development and Maintenance | Grading and murraming of Gichobo road | To improve road infrastructure by grading and murraming Gichobo road | Gichobo road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 2296980 | 120.9 | 2296980 | 103020 | -396980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6277 | Infrastructure, Development and Maintenance | Grading and murraming of Matanya-Block 2 road | To improve road infrastructure by grading and murraming Matanya-Block 2 road | Matanya-Block 2 road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1374400 | 91.6 | 1374400 | 987937 | 125600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
6278 | hire of machinery and murram for Lare ward | hire of machinery and murram for Lare ward | To implement hire of machinery and murram for lare ward for road connectivity and accessibility | hire of machinery and murram for Lare ward completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.455725, 36.016665 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1861152 | 1861152 | 1861152 | Equitable | N/A | 1861152 | 0 | 1860650 | 100 | 1860650 | 1861152 | 502 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2021. Assessor remarks: Need maintenance.
6279 | Installation of Mulika mwizi across Lare ward | Installation of Mulika mwizi across Lare ward | To install Mulika mwizi across Lare ward | Mulika mwizi across Lare ward installed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.386115, 35.969257 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 1700000 | 485.7 | 1700000 | 350000 | -1350000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6280 | Infrastructure, Development and Maintenance | Grading and murraming of Bagaria - Mwenyere road. | To improve road infrastructure by grading and murraming Bagaria - Mwenyere road | Bagaria - Mwenyere road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2327800 | 93.1 | 2327800 | 2327800 | 172200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
6281 | Infrastructure, Development & Maintenance | Grading and murraming of Caravat - Kianugu - Milimani road. | To improve road infrastructure by grading and murraming Caravat - Kianugu - Milimani road | Caravat - Kianugu - Milimani road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.524718, 36.039202 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 2000000 | 1999800 | 1999800 | Equitable | N/A | 1999800 | 0 | 1999800 | 100 | 1999800 | 1999800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic condition and need maintenance.
6282 | Infrastructure, Development & Maintenance | Grading and murraming of Gitene - Sinendet Road. | To improve road infrastructure by grading and murraming Gitene - Sinendet Road | Gitene - Sinendet Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.492042, 36.040327 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 1499001 | 1499001 | Equitable | N/A | 1499001 | 0 | 1499001 | 100 | 1499001 | 1499001 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintence.
6283 | Infrastructure, Development & Maintenance | Grading and murraming of Mugumo - Kwale - Muthiga road. | To improve road infrastructure by grading and murraming Mugumo - Kwale - Muthiga road | Mugumo - Kwale - Muthiga road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.431365, 36.045213 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 40165 | 2 | 40165 | 40165 | 1959835 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need murraming.
6284 | Infrastructure, Development and Maintenance | Grading and murraming of Mwenyere-Milimani road. | To improve road infrastructure by grading and murraming Mwenyere-Milimani road | Mwenyere-Milimani road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 2498849.92 | 2498849.92 | Equitable | N/A | 2498849.92 | 0 | 999450 | 40 | 999450 | 1000000 | 1499399.92 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
6285 | Infrastructure, Development & Maintenance | Grading and murraming of Wambia - Nduriri - Nduriri Juu Borehole road. | To improve road infrastructure by grading and murraming Wambia - Nduriri - Nduriri Juu Borehole road | Wambia - Nduriri - Nduriri Juu Borehole road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.467588 36.031073 2039.4 6.099999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1996550 | 79.9 | 1996550 | 1996550 | 503450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6286 | Infrastructure, Development & Maintenance | Grading and Murraming and installation of culverts of Muthiga – Karogoe road. | To improve road infrastructure by grading and murraming and installation of culverts of Muthiga – Karogoe road | And installation of culverts of Muthiga – Karogoe road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.462187, 36.050997 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1800205 | 90 | 1800205 | 1808250 | 199795 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6287 | Installation of 5 Mulika mwizi in lare Ward. | Installation of 5 Mulika mwizi in lare Ward. | To install 5 Mulika mwizi in lare Ward | 5 Mulika mwizi in lare Ward installed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.386115, 35.969257 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 1700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6288 | Construction of drainage system at Guba road | Construction of drainage system at Guba road | To construct drainage system at Guba road | Drainage system at Guba road constructed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.26982, 36.051237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2425821 | 80.9 | 2425821 | 2433916 | 574179 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs cleaning.
6289 | Construction of drainage system at St. Michael Catholic church | Construction of drainage system at St. Michael Catholic church | To construct drainage system at St. Michael Catholic church | Drainage system at St. Michael Catholic church constructed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.271517, 36.05234 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1736413 | 86.8 | 1736413 | 1994430 | 263587 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs cleaning.
6290 | Construction of drainage system on 300M hilton road | Construction of drainage system on 300M hilton road | To construct drainage system on 300M hilton road | Drainage system on 300M hilton road constructed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.26982, 36.051237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1239675 | 1239675 | 1239675 | Equitable | N/A | 1239675 | 0 | 1239675 | 100 | 1239675 | 1239675 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs cleaning.
6291 | Infrastructure, Development & Maintenance | Erection and installation of streetlights in bangladesh | To implement erection and installation of streetlights in bangladesh for road connectivity and accessibility | Erection and installation of streetlights in bangladesh completed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.288092, 36.054717 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2968460 | 98.9 | 2968460 | 2968460 | 31540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yea. Assessor remarks: Regularly maintained.
6292 | Road works in longonot culverts and murraming | Road works in longonot culverts and murraming | To implement road works in longonot culverts and murraming for road connectivity and accessibility | Road works in longonot culverts and murraming completed | 3110499 | Construction of Roads - Other | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495800 | 99.8 | 2495800 | 2495800 | 4200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6293 | Roadworks in maai mahiu,culverts and murraming | Roadworks in maai mahiu,culverts and murraming | To implement roadworks in maai mahiu,culverts and murraming for road connectivity and accessibility | Roadworks in maai mahiu,culverts and murraming completed | 3110499 | Construction of Roads - Other | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495800 | 99.8 | 2495800 | 2500000 | 4200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6294 | Infrastructure, Development & Maintenance | Grading, murraming and compaction and drainage of NYS-Gatamaiyo-Nyakinyua road | To implement grading, murraming and compaction and drainage of nys-gatamaiyo-nyakinyua road for road connectivity and accessibility | Grading, murraming and compaction and drainage of NYS-Gatamaiyo-Nyakinyua road completed | 3110499 | Construction of Roads - Other | GILGIL | MALEWA WEST | -0.612613, 36.398477 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2882615 | 96.1 | 2882615 | 3000000 | 117385 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been consistently maintained.
6295 | Infrastructure, Development & Maintenance | Grading and gravelling of disital kaliet road | To improve road infrastructure by grading and murraming disital kaliet road | Disital kaliet road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MARIASHONI | -0.350431, 35.812051 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2138191 | 2138191 | 2138191 | Equitable | N/A | 2138191 | 0 | 2136530 | 99.9 | 2136530 | 2136530 | 1661 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6296 | Infrastructure, Development & Maintenance | Grading and levelling Kapchepokazi-Kalegu road | To improve road accessibility by grading and levelling Kapchepokazi-Kalegu road | And levelling Kapchepokazi-Kalegu road graded | 3110499 | Construction of Roads - Other | MOLO | MARIASHONI | -0.386159, 35.809073 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996360 | 99.6 | 996360 | 996360 | 3640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly. Viable: Yes. Assessor remarks: Poor road.
6297 | Infrastructure, Development & Maintenance | Grading and levelling Ndoswa-Ndashatai Road | To improve road accessibility by grading and levelling Ndoswa-Ndashatai Road | And levelling Ndoswa-Ndashatai Road graded | 3110499 | Construction of Roads - Other | MOLO | MARIASHONI | -0.369206, 35.841966 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799000 | 99.9 | 1799000 | 1799000 | 1000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
6298 | Infrastructure, Development & Maintenance | Grading and murraming of Bondeni-Waweru farm road | To improve road infrastructure by grading and murraming Bondeni-Waweru farm road | Bondeni-Waweru farm road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | MAU NAROK | -0.597775, 36.005282 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499370 | 100 | 2499370 | 630 | 630 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
6299 | Infrastructure, Development & Maintenance | Grading and murraming of Mau-Narok-Centre road | To improve road infrastructure by grading and murraming Mau-Narok-Centre road | Mau-Narok-Centre road graded and murramed | 3110499 | Construction of Roads - Other | NJORO | MAU NAROK | -0.598002 36.005328 2574.8999999999996 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1963766 | 98.2 | 1963766 | 2366632 | 36234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
6300 | Infrastructure, Development and Maintenance | Construction of drainage and culverts at Tayari farm road | To construct drainage and culverts at Tayari farm road | Drainage and culverts at Tayari farm road constructed | 3110499 | Construction of Roads - Other | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6301 | Infrastructure, Development & Maintenance | Grading and gravelling of Kibunja Secondary school road | To improve road infrastructure by grading and murraming Kibunja Secondary school road | Kibunja Secondary school road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6302 | Infrastructure, Development & Maintenance | Grading and gravelling of Soin-Chesoen road | To improve road infrastructure by grading and murraming Soin-Chesoen road | Soin-Chesoen road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6303 | Infrastructure, Development & Maintenance | Grading and gravelling of Tayari-Moto road | To improve road infrastructure by grading and murraming Tayari-Moto road | Tayari-Moto road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6304 | Infrastructure, Development & Maintenance | Grading,murraming and gravelling of tayari primary school -dam road | To implement grading,murraming and gravelling of tayari primary school -dam road for road connectivity and accessibility | Grading,murraming and gravelling of tayari primary school -dam road completed | 3110499 | Construction of Roads - Other | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2237797 | 2237797 | 2237797 | Equitable | N/A | 2237797 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6305 | Infrastructure, Development and Maintenance | Grading and Murraming of Mimwaita road | To improve road infrastructure by grading and murraming Mimwaita road | Mimwaita road graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | MOSOP | -0.244286, 35.909447 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1495750 | 99.7 | 1495750 | 1500000 | 4250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: DANJACQUE. Assessor remarks: In good condition.
6306 | Infrastructure, Development & Maintenance | Grading, gravelling and compaction and a foot bridge (catholic Jeremiah road) | To implement grading, gravelling and compaction and a foot bridge (catholic jeremiah road) for road connectivity and accessibility | Grading, gravelling and compaction and a foot bridge (catholic Jeremiah road) completed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.408691, 36.310595 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2442336 | 122.1 | 2442336 | 2000000 | -442336 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6307 | Infrastructure, Development and Maintenance | Rehabilitation of selected roads in Langa Langa | To rehabilitate selected roads in Langa Langa to restore functionality | Selected roads in Langa Langa rehabilitated | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.520737, 36.375889 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022/23 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2685385 | 99.5 | 2685385 | 2692328 | 14615 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S KEMEMO WORKS AND SUPPLIES. Assessor remarks: Good.
6308 | Infrastructure, Development & Maintenance | Grading and gravelling at Ha Nderitu-Kagumu primary Road | To improve road infrastructure by grading and murraming at Ha Nderitu-Kagumu primary Road | At Ha Nderitu-Kagumu primary Road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.402038, 36.293648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 812223 | 73.8 | 812223 | 191977 | 287777 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ahnna Supplies Company Ltd. Assessor remarks: Good.
6309 | Grading and gravelling of Kangai- chemichemi road | Grading and gravelling of Kangai- chemichemi road | To improve road infrastructure by grading and murraming Kangai- chemichemi road | Kangai- chemichemi road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.50413, 36.381348 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1981343 | 99.1 | 1981343 | 17357 | 18657 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Durhas Construction. Assessor remarks: Good.
6310 | Infrastructure, Development & Maintenance | Rehabilitation of Mbegi Road | To rehabilitate Mbegi Road to restore functionality | Mbegi Road rehabilitated | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.520936, 36.331016 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4611590 | 307.4 | 4611590 | 1500000 | -3111590 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
6311 | Infrastructure, Development & Maintenance | Completion of Governor bridge | To complete Governor bridge | Governor bridge completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.966875, 36.546208 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498569 | 99.9 | 1498569 | 1500000 | 1431 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6312 | Infrastructure, Development & Maintenance | Completion of wagachunga bridge | To complete wagachunga bridge | Wagachunga bridge completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3665650 | 244.4 | 3665650 | 1500000 | -2165650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6313 | Infrastructure, Development & Maintenance | construction of Governor village footbridge | To construct Governor village footbridge | Governor village footbridge constructed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.966875, 36.546208 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999638 | 100 | 1999638 | 2000000 | 362 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6314 | Infrastructure, Development & Maintenance | Construction of wagacunga bridge | To construct wagacunga bridge | Wagacunga bridge constructed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2450000 | 2450000 | 2450000 | Equitable | N/A | 2450000 | 0 | 2450000 | 100 | 2450000 | 2450000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6315 | Erection of gabions and murraming at Ereri road | Erection of gabions and murraming at Ereri road | To implement erection of gabions and murraming at ereri road for road connectivity and accessibility | Erection of gabions and murraming at Ereri road completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1844100 | 1844100 | 1844100 | Equitable | N/A | 1844100 | 0 | 1640275 | 88.9 | 1640275 | 1640275 | 203825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6316 | Infrastructure, Development and Maintenance | Erection of gabions and murraming at lari road | To implement erection of gabions and murraming at lari road for road connectivity and accessibility | Erection of gabions and murraming at lari road completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 898120 | 89.8 | 898120 | 898120 | 101880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6317 | Infrastructure, Development and Maintenance | Erection of gabions at karatu road | To implement erection of gabions at karatu road for road connectivity and accessibility | Erection of gabions at karatu road completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -1.007981, 36.522231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 857034 | 85.7 | 857034 | 857033 | 142966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs bush clearing and maintenance.
6318 | Infrastructure, Development and Maintenance | Erection of gabions at longonot kiambogo road | To implement erection of gabions at longonot kiambogo road for road connectivity and accessibility | Erection of gabions at longonot kiambogo road completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 856672 | 85.7 | 856672 | 856672 | 143328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6319 | Infrastructure, Development & Maintenance | Grading, murraming and culverts installation in maai mahiu town access roads | To implement grading, murraming and culverts installation in maai mahiu town access roads for road connectivity and accessibility | Grading, murraming and culverts installation in maai mahiu town access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.979395, 36.583706 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1314200 | 87.6 | 1314200 | 1314200 | 185800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
6320 | Infrastructure, Development and Maintenance | Rehabilitation of Roads and hire of equipments and machinery and | To rehabilitate Roads and hire of equipments and machinery and to restore functionality | Roads and hire of equipments and machinery and rehabilitated | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.991272, 36.571424 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: To be maintained.
6321 | Road works in longonot culverts and murraming | Road works in longonot culverts and murraming | To implement road works in longonot culverts and murraming for road connectivity and accessibility | Road works in longonot culverts and murraming completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2495800 | 2495800 | Equitable | N/A | 2495800 | 0 | 2495800 | 100 | 2495800 | 2495800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6322 | Roadworks in maai mahiu,culverts and murraming | Roadworks in maai mahiu,culverts and murraming | To implement roadworks in maai mahiu,culverts and murraming for road connectivity and accessibility | Roadworks in maai mahiu,culverts and murraming completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495800 | 99.8 | 2495800 | 2500000 | 4200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6323 | Infrastructure, Development and Maintenance | Rock filling and gabions on munengi road landslide at longonot | To implement rock filling and gabions on munengi road landslide at longonot for road connectivity and accessibility | Rock filling and gabions on munengi road landslide at longonot completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.91047, 36.525415 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1305680 | 87 | 1305680 | 1305680 | 194320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start.
6324 | Infrastructure, Development and Maintenance | Streetlighting maintenance in maai mahiu and longonot | To implement streetlighting maintenance in maai mahiu and longonot for road connectivity and accessibility | Streetlighting maintenance in maai mahiu and longonot completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3000000 | 600 | 3000000 | 500000 | -2500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6325 | Infrastructure, Development and Maintenance | Malewa West Roads rehabilitation (hire of machinery and equipments) | To implement malewa west roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Malewa West Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.666667 36.39886 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999405 | 0 | 2999405 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6326 | Infrastructure, Development & Maintenance | construction of Kamungei bridge | To construct Kamungei bridge | Kamungei bridge constructed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.346125, 35.818593 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 780855 | 39 | 780855 | 780855 | 1219145 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
6327 | Infrastructure, Development & Maintenance | Grading and gravelling of disital kaliet road | To improve road infrastructure by grading and murraming disital kaliet road | Disital kaliet road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.350431, 35.812051 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2138191 | 2136530 | 2136530 | Equitable | N/A | 2136530 | 0 | 2136530 | 100 | 2136530 | 2136530 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6328 | Infrastructure, Development & Maintenance | Grading and levelling Kapchepokazi-Kalegu road | To improve road accessibility by grading and levelling Kapchepokazi-Kalegu road | And levelling Kapchepokazi-Kalegu road graded | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.386159, 35.809073 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996360 | 99.6 | 996360 | 996360 | 3640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly. Viable: Yes. Assessor remarks: Poor road.
6329 | Infrastructure, Development & Maintenance | Grading and levelling Ndoswa-Ndashatai Road | To improve road accessibility by grading and levelling Ndoswa-Ndashatai Road | And levelling Ndoswa-Ndashatai Road graded | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.369206, 35.841966 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799000 | 99.9 | 1799000 | 1799000 | 1000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
6330 | Infrastructure, Development & Maintenance | Grading and murraming Marioshoni-Taragonic road | To improve road infrastructure by grading and murraming Marioshoni-Taragonic road | Marioshoni-Taragonic road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.340543, 35.814798 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1813140 | 90.7 | 1813140 | 2000000 | 186860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6331 | Infrastructure, Development and Maintenance | Grading and murraming of kapsinendet-vikingi road | To improve road infrastructure by grading and murraming kapsinendet-vikingi road | Kapsinendet-vikingi road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.378993, 35.796751 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2894130 | 96.5 | 2894130 | 1931829 | 105870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance needed.
6332 | Infrastructure, Development and Maintenance | Grading and murraming of mawe mbili-kalwet road | To improve road infrastructure by grading and murraming mawe mbili-kalwet road | Mawe mbili-kalwet road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.343871, 35.791629 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1664905 | 1664905 | 1664905 | Equitable | N/A | 1664905 | 0 | 444660 | 26.7 | 444660 | 444660 | 1220245 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road to town good.
6333 | Infrastructure, Development & Maintenance | Grading and murraming of Munyukwa-Marioshoni road | To improve road infrastructure by grading and murraming Munyukwa-Marioshoni road | Munyukwa-Marioshoni road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.370821, 35.82629 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1798140 | 89.9 | 1798140 | 2000000 | 201860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6334 | Infrastructure, Development and Maintenance | Grading and murraming of oinoptich kapgarang road | To improve road infrastructure by grading and murraming oinoptich kapgarang road | Oinoptich kapgarang road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 404155 | 20.2 | 404155 | 404155 | 1595845 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
6335 | Infrastructure, Development and Maintenance | Grading and murraming of Rombei-Kapsita road | To improve road infrastructure by grading and murraming Rombei-Kapsita road | Rombei-Kapsita road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600443 | 1600443 | 1600443 | Equitable | N/A | 1600443 | 0 | 1418690 | 88.6 | 1418690 | 1600443 | 181753 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
6336 | Installation of culverts at tummo quarry and osama area | Installation of culverts at tummo quarry and osama area | To improve drainage and road access through culvert installation at tummo quarry and osama area | Culverts installed at tummo quarry and osama area | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.336442, 35.883617 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 5255 | 0.7 | 5255 | 5255 | 794745 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
6337 | Infrastructure, Development & Maintenance | Grading and gravelling of Tipis center access road | To improve road infrastructure by grading and murraming Tipis center access road | Tipis center access road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.529072 35.968285 2526.1000000000004 10.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2161201 | 2161201 | 2161201 | Equitable | N/A | 2161201 | 0 | 1987883 | 92 | 1987883 | 2000246 | 173318 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: In Procurement 2024/2025.
6338 | Infrastructure, Development & Maintenance | Grading and murraming of Bondeni-Waweru farm road | To improve road infrastructure by grading and murraming Bondeni-Waweru farm road | Bondeni-Waweru farm road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.597775, 36.005282 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499370 | 100 | 2499370 | 630 | 630 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
6339 | Routine Maintainance, Grading and Gravelling of Mau Narok Access Roads (Utalii - Kastem Road; Kahuho- Dam Road) | Routine Maintainance, Grading and Gravelling of Mau Narok Access Roads (Utalii - Kastem Road; Kahuho- Dam Road) | To implement routine maintainance, grading and gravelling of mau narok access roads (utalii - kastem road; kahuho- dam road) for road connectivity and accessibility | Routine Maintainance, Grading and Gravelling of Mau Narok Access Roads (Utalii - Kastem Road; Kahuho- Dam Road) completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.59621, 35.995702 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 2983330 | 96.2 | 2983330 | 1468429 | 116670 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Bad condition at moment.
6340 | Construction of kwa rono bridge | Construction of kwa rono bridge | To construct kwa rono bridge | Kwa rono bridge constructed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.481217, 35.963408 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2780640 | 92.7 | 2780640 | 2832500 | 219360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
6341 | Infrastructure, Development & Maintenance | construction of Mariakani teachers stormwater drainage works | To construct Mariakani teachers stormwater drainage works | Mariakani teachers stormwater drainage works constructed | 3110499 | Construction of Roads - Other | Nakuru East | Menengai | -0.271371, 36.111308 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4303910 | 86.1 | 4303910 | 4240 | 696090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6342 | Streetlight maintenanace in Menengai ward | Streetlight maintenanace in Menengai ward | To implement streetlight maintenanace in menengai ward for road connectivity and accessibility | Streetlight maintenanace in Menengai ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Menengai | -0.266246, 36.100626 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1325500 | 88.4 | 1325500 | 1500000 | 174500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Only done at one area, ( teachers).
6343 | Gravelling, murraming and installation of culverts at kwa jogoo-olrongai primary road | Gravelling, murraming and installation of culverts at kwa jogoo-olrongai primary road | To implement gravelling, murraming and installation of culverts at kwa jogoo-olrongai primary road for road connectivity and accessibility | Gravelling, murraming and installation of culverts at kwa jogoo-olrongai primary road completed | 3110499 | Construction of Roads - Other | Rongai | Menengai West | -0.166756, 36.010995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6344 | Infrastructure, Development & Maintenance | Grading and gravelling of Kibunja Secondary school road | To improve road infrastructure by grading and murraming Kibunja Secondary school road | Kibunja Secondary school road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1488830 | 1488830 | Equitable | N/A | 1488830 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6345 | Infrastructure, Development & Maintenance | Grading and gravelling of Soin-Chesoen road | To improve road infrastructure by grading and murraming Soin-Chesoen road | Soin-Chesoen road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1499070 | 1499070 | Equitable | N/A | 1499070 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6346 | Infrastructure, Development & Maintenance | Grading and gravelling of Tayari-Moto road | To improve road infrastructure by grading and murraming Tayari-Moto road | Tayari-Moto road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6347 | Infrastructure, Development & Maintenance | Grading and murraming of Chepalungu road at sachangwan | To improve road infrastructure by grading and murraming Chepalungu road at sachangwan | Chepalungu road at sachangwan graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6348 | Infrastructure, Development & Maintenance | Grading and murraming of Chesilogo road at sachagwan, | To improve road infrastructure by grading and murraming Chesilogo road at sachagwan, | Chesilogo road at sachagwan, graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6349 | Infrastructure, Development & Maintenance | Grading and murraming of kalyet-kurkong road at sachangwan | To improve road infrastructure by grading and murraming kalyet-kurkong road at sachangwan | Kalyet-kurkong road at sachangwan graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6350 | Infrastructure, Development & Maintenance | Grading and murraming of kiambogo bridge road | To improve road infrastructure by grading and murraming kiambogo bridge road | Kiambogo bridge road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6351 | Infrastructure, Development & Maintenance | Grading and murraming of molo ward access roads | To improve road infrastructure by grading and murraming molo ward access roads | Molo ward access roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 4598331 | 4598331 | 4598331 | Equitable | N/A | 4598331 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6352 | Infrastructure, Development & Maintenance | Grading and murraming of sagoo research road | To improve road infrastructure by grading and murraming sagoo research road | Sagoo research road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6353 | Infrastructure, Development & Maintenance | Grading and murraming of tayari primary-tombo road | To improve road infrastructure by grading and murraming tayari primary-tombo road | Tayari primary-tombo road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6354 | Infrastructure, Development & Maintenance | Grading,murraming and gravelling of tayari primary school -dam road | To implement grading,murraming and gravelling of tayari primary school -dam road for road connectivity and accessibility | Grading,murraming and gravelling of tayari primary school -dam road completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2237797 | 2237797 | 2237797 | Equitable | N/A | 2237797 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6355 | Infrastructure, Development and Maintenance | hiring of machinery and supply of murram for lower molo academy primary school | To implement hiring of machinery and supply of murram for lower molo academy primary school for road connectivity and accessibility | hiring of machinery and supply of murram for lower molo academy primary school completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6356 | Infrastructure, Development and Maintenance | Installation of 8 mlika mwizi across molo ward at sachangwan dispensary,gitingi sachangwan,kwa ndung'u,behind molo academy primary school,munju bridge-kwa muriu, kenyatta estate phase 2,Lower kaloleni-kwa munyoris and kampi mpya sokoni | To install 8 mlika mwizi across molo ward at sachangwan dispensary,gitingi sachangwan,kwa ndung'u,behind molo academy primary school,munju bridge-kwa muriu, kenyatta estate phase 2,Lower kaloleni-kwa munyoris and kampi mpya sokoni | 8 mlika mwizi across molo ward at sachangwan dispensary,gitingi sachangwan,kwa ndung'u,behind molo academy primary school,munju bridge-kwa muriu, kenyatta estate phase 2,Lower kaloleni-kwa munyoris and kampi mpya sokoni installed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6357 | Infrastructure, Development and Maintenance | Installation of mulika mwizi at kisii ndogo,opposite BP station kwa chang'aa,kwa baba kamau shopping center,kwa ndung'u shopping center,kwa sagoo forest road,kwa kibunja highway primary school,kiambogo shopping center,matumaini shopping center and millenium posho mill road | To install mulika mwizi at kisii ndogo,opposite BP station kwa chang'aa,kwa baba kamau shopping center,kwa ndung'u shopping center,kwa sagoo forest road,kwa kibunja highway primary school,kiambogo shopping center,matumaini shopping center and millenium posho mill road | Mulika mwizi at kisii ndogo,opposite BP station kwa chang'aa,kwa baba kamau shopping center,kwa ndung'u shopping center,kwa sagoo forest road,kwa kibunja highway primary school,kiambogo shopping center,matumaini shopping center and millenium posho mill road installed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6358 | Infrastructure, Development and Maintenance | Installation of tayari west culverts | To install tayari west culverts | Tayari west culverts installed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6359 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the ward completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.350801, 36.219177 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 24/25 | 312596 | 312596 | 312596 | Equitable | N/A | 312596 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
6360 | Infrastructure, Development and Maintenance | Grading and Murraming of Mimwaita road | To improve road infrastructure by grading and murraming Mimwaita road | Mimwaita road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.244286, 35.909447 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1495750 | 99.7 | 1495750 | 1500000 | 4250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: DANJACQUE. Assessor remarks: In good condition.
6361 | Infrastructure, Development & Maintenance | Installation of high mast lights in mosop ward | To improve security lighting through high mast floodlight installation at lights in mosop ward | High mast floodlight installed at lights in mosop ward | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.213155 35.844007 1903.300048828125 16.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599200 | 100 | 1599200 | 1599200 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated q. Assessor remarks: Good.
6362 | Infrastructure, Development & Maintenance | Installation of streetlights across mosop ward | To improve lighting and safety through installation of solar streetlights at across mosop ward | Solar streetlights installed at across mosop ward | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.27141, 36.006577 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1453100 | 103.8 | 1453100 | 1453100 | -53100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Complete.
6363 | Infrastructure, Development & Maintenance | Road works across mosop ward (Purchase of fuel and murram,culverts and hire of machines) | To implement road works across mosop ward (purchase of fuel and murram,culverts and hire of machines) for road connectivity and accessibility | Road works across mosop ward (Purchase of fuel and murram,culverts and hire of machines) completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.252383 35.840025 2064.6 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3667621 | 3667621 | 3667621 | Equitable | N/A | 3667621 | 0 | 3667621 | 100 | 3667621 | 3667621 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
6364 | Salgaa B drainage works- improvement of drainage at Salgaa centre | Salgaa B drainage works- improvement of drainage at Salgaa centre | To implement salgaa b drainage works- improvement of drainage at salgaa centre for road connectivity and accessibility | Salgaa B drainage works- improvement of drainage at Salgaa centre completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.20603, 35.847668 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1318398 | 87.9 | 1318398 | 0 | 181602 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
6365 | Infrastructure, Development and Maintenance | Construction of gilgil-murindat mbegi bridge | To construct gilgil-murindat mbegi bridge | Gilgil-murindat mbegi bridge constructed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 3426808 | 195.8 | 3426808 | 1750000 | -1676808 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6366 | Infrastructure, Development & Maintenance | Construction of Kahuho bridge in Murindat | To construct Kahuho bridge in Murindat | Kahuho bridge in Murindat constructed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.420368, 36.330678 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2743027 | 91.4 | 2743027 | 3000000 | 256973 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Benline Limited. Assessor remarks: Operational.
6367 | Infrastructure, Development & Maintenance | Construction of nicesuit bridge | To construct nicesuit bridge | Nicesuit bridge constructed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.425456, 36.314081 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3426808 | 92.6 | 3426808 | 3700000 | 273192 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Amogracia Contractors Ltd. Assessor remarks: Operational.
6368 | Infrastructure, Development & Maintenance | Gravelling, dozing and back filling of Kahuho Bridge | To implement gravelling, dozing and back filling of kahuho bridge for road connectivity and accessibility | Gravelling, dozing and back filling of Kahuho Bridge completed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2453350 | 0 | 2453350 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6369 | Infrastructure, Development and Maintenance | Rehabilitation of selected roads in Langa Langa | To rehabilitate selected roads in Langa Langa to restore functionality | Selected roads in Langa Langa rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.520737, 36.375889 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022/23 | 2700000 | 2692328 | 2692328 | Equitable | N/A | 2692328 | 0 | 2685385 | 99.7 | 2685385 | 2692328 | 6943 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S KEMEMO WORKS AND SUPPLIES. Assessor remarks: Good.
6370 | Infrastructure, Development & Maintenance | Grading and gravelling at Ha Nderitu-Kagumu primary Road | To improve road infrastructure by grading and murraming at Ha Nderitu-Kagumu primary Road | At Ha Nderitu-Kagumu primary Road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.402038, 36.293648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1004200 | 1004200 | Equitable | N/A | 1004200 | 0 | 812223 | 80.9 | 812223 | 191977 | 191977 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ahnna Supplies Company Ltd. Assessor remarks: Good.
6371 | Grading and gravelling of Kangai- chemichemi road | Grading and gravelling of Kangai- chemichemi road | To improve road infrastructure by grading and murraming Kangai- chemichemi road | Kangai- chemichemi road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.50413, 36.381348 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1998700 | 1998700 | Equitable | N/A | 1998700 | 0 | 1981343 | 99.1 | 1981343 | 17357 | 17357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Durhas Construction. Assessor remarks: Good.
6372 | Grading and gravelling of Nyakairo -Mwega road | Grading and gravelling of Nyakairo -Mwega road | To improve road infrastructure by grading and murraming Nyakairo -Mwega road | Nyakairo -Mwega road graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | NAIVASHA EAST | -0.778058, 36.533234 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999656 | 100 | 1999656 | 1999656 | 344 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
6373 | Infrastructure, Development and Maintenance | Grading and gravelling of Nyakairo road | To improve road infrastructure by grading and murraming Nyakairo road | Nyakairo road graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | NAIVASHA EAST | -0.792455, 36.534807 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 991637 | 99.2 | 991637 | 1000000 | 8363 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require addition of culverts.
6374 | Grading and gravelling of Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | Grading and gravelling of Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | To improve road infrastructure by grading and murraming Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | NAIVASHA EAST | -0.842973 36.556068 2599 6.122000217437744 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2993293 | 99.8 | 2993293 | 1873 | 6707 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor drainage requires caravat.
6375 | Infrastructure, Development & Maintenance | Grading and Murraming of Kamara-Kamasit roads | To improve road infrastructure by grading and murraming Kamara-Kamasit roads | Kamara-Kamasit roads graded and murramed | 3110499 | Construction of Roads - Other | NJORO | NESSUIT | -0.419334, 35.932833 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2333210 | 233.3 | 2333210 | 997604 | -1333210 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Beliot investment limited. Assessor remarks: The road requires regular maintenance.
6376 | Infrastructure, Development & Maintenance | Grading, Murraming and culverting of Cutline-Kamasut Road | To implement grading, murraming and culverting of cutline-kamasut road for road connectivity and accessibility | Grading, Murraming and culverting of Cutline-Kamasut Road completed | 3110499 | Construction of Roads - Other | NJORO | NESSUIT | -0.428558, 35.933756 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995518 | 99.8 | 1995518 | 1999490 | 4482 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition, it just needs regular maintenance.
6377 | Infrastructure, Development & Maintenance | Grading, Murraming and culverting of Junction-KAP JONA-CHEPORGEI | To implement grading, murraming and culverting of junction-kap jona-cheporgei for road connectivity and accessibility | Grading, Murraming and culverting of Junction-KAP JONA-CHEPORGEI completed | 3110499 | Construction of Roads - Other | NJORO | NESSUIT | -0.417985, 35.882619 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1840920 | 92 | 1840920 | 1840920 | 159080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in poor condition and requires urgent improvement.
6378 | Infrastructure, Development & Maintenance | Installation of Culverts at Beeston Feeder Roads | To improve drainage and road access through culvert installation at Beeston Feeder Roads | Culverts installed at Beeston Feeder Roads | 3110499 | Construction of Roads - Other | NJORO | NJORO | -0.366398, 35.907184 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
6379 | Infrastructure, Development & Maintenance | Construction of polytechnic access roads | To construct polytechnic access roads | Polytechnic access roads constructed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.365343 35.587382 2625.3 24.899999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999500 | 100 | 999500 | 399950 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well accomplished.
6380 | Infrastructure, Development and Maintenance | Grading and Murraming of Chesingele - Omari Road | To improve road infrastructure by grading and murraming Chesingele - Omari Road | Chesingele - Omari Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.388303, 35.628555 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024-2025 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 561629 | 32.1 | 561629 | 190721 | 1188371 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Yes. Assessor remarks: Side grills are missing, Refl.
6381 | Infrastructure, Development & Maintenance | Grading and Murraming of Hill academy-Church Road | To improve road infrastructure by grading and murraming Hill academy-Church Road | Hill academy-Church Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.298933, 35.553238 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019-2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996844 | 99.8 | 1996844 | 1828545 | 3156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent attention: General routine Maintenance..
6382 | Infrastructure, Development & Maintenance | Grading and Murraming of Matunda Primary-Soweto road | To improve road infrastructure by grading and murraming Matunda Primary-Soweto road | Matunda Primary-Soweto road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.393417, 35.630455 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023-2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 989860 | 66 | 989860 | 1000000 | 510140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional spot patches grading & Murruming.
6383 | Infrastructure, Development and Maintenance | Grading and Murraming of Nyota Roads | To improve road infrastructure by grading and murraming Nyota Roads | Nyota Roads graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.378012, 35.688995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024-2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998884 | 99.9 | 1998884 | 1499715 | 1116 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
6384 | Infrastructure, Development and Maintenance | Grading and Murraming of Tarakwa Roads | To improve road infrastructure by grading and murraming Tarakwa Roads | Tarakwa Roads graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.355807 35.688607 2814.6 13.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999849 | 100 | 1999849 | 1828545 | 151 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: CEDER RED INVESTMENTS LTD.. Assessor remarks: Done to Completion.
6385 | Infrastructure, Development and Maintenance | Grading,murraming and gravelling of sasimua road | To implement grading,murraming and gravelling of sasimua road for road connectivity and accessibility | Grading,murraming and gravelling of sasimua road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.308548, 35.645022 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | _ | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1419999 | 94.7 | 1419999 | 1491999 | 80001 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: ACCESSIBLE.
6386 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Mawingu Centre to lami juu road | To implement gravelling and murraming of 3km of mawingu centre to lami juu road for road connectivity and accessibility | Gravelling and murraming of 3km of Mawingu Centre to lami juu road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2962988 | 98.8 | 2962988 | 2962988 | 37012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
6387 | Grading and gravelling of Nyakairo -Mwega road | Grading and gravelling of Nyakairo -Mwega road | To improve road infrastructure by grading and murraming Nyakairo -Mwega road | Nyakairo -Mwega road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.778058, 36.533234 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 2000000 | 1999656 | 1999656 | Equitable | N/A | 1999656 | 0 | 1999656 | 100 | 1999656 | 1999656 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
6388 | Infrastructure, Development and Maintenance | Grading and gravelling of Nyakairo road | To improve road infrastructure by grading and murraming Nyakairo road | Nyakairo road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.792455, 36.534807 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 991637 | 99.2 | 991637 | 1000000 | 8363 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require addition of culverts.
6389 | Grading and gravelling of Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | Grading and gravelling of Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | To improve road infrastructure by grading and murraming Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha | Thome Wa munyu road-GUCUGA AP post,sindano road,run-together road and kahuho road through boresha graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.842973 36.556068 2599 6.122000217437744 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2995165 | 2995165 | Equitable | N/A | 2995165 | 0 | 2993293 | 99.9 | 2993293 | 1873 | 1872 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor drainage requires caravat.
6390 | Infrastructure, Development and Maintenance | Grading and murraming of acre moja-kiambogo road | To improve road infrastructure by grading and murraming acre moja-kiambogo road | Acre moja-kiambogo road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.86648, 36.538122 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 768900 | 76.9 | 768900 | 768900 | 231100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require gravelling.
6391 | Grading and murraming of Kenvash-Guchuga road and Kinungi-Nyandarua road | Grading and murraming of Kenvash-Guchuga road and Kinungi-Nyandarua road | To improve road infrastructure by grading and murraming Kenvash-Guchuga road and Kinungi-Nyandarua road | Kenvash-Guchuga road and Kinungi-Nyandarua road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.840637, 36.54841 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020-21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 718600 | 71.9 | 718600 | 718600 | 281400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6392 | road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) | road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) | To implement road rehabilitation and maintenance (hire of machinery for rehabiltation of naivasha east access roads) for road connectivity and accessibility | road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) completed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.861268, 36.541282 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance and gravelling.
6393 | Infrastructure, Development & Maintenance | Routine maintenance of Kayole-Italian-Kinamba road | To maintain Kayole-Italian-Kinamba road in serviceable condition | Kayole-Italian-Kinamba road maintained | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.74819 36.470822 2071.60009765625 4.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 787539 | 78.8 | 787539 | 787539 | 212461 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
6394 | Grading and murraming of california estate | Grading and murraming of california estate | To improve road infrastructure by grading and murraming california estate | California estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1353000 | 90.2 | 1353000 | 1500000 | 147000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
6395 | Grading and murraming of mwangaza estate | Grading and murraming of mwangaza estate | To improve road infrastructure by grading and murraming mwangaza estate | Mwangaza estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2244300 | 89.8 | 2244300 | 2500000 | 255700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
6396 | Infrastructure, Development and Maintenance | Grading and punching of JB-mzee wanyama road | To improve road accessibility by grading and punching of JB-mzee wanyama road | And punching of JB-mzee wanyama road graded | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.360122 36.149943 1876.5 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1636482 | 1636482 | 1636482 | Equitable | N/A | 1636482 | 0 | 1411015 | 86.2 | 1411015 | 0 | 225467 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Techfield system limited. Assessor remarks: Its in good condition.
6397 | Grading and murraming of Imperial estate | Grading and murraming of Imperial estate | To improve road infrastructure by grading and murraming Imperial estate | Imperial estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2387000 | 95.5 | 2387000 | 1500000 | 113000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
6398 | Grading and murraming of JB estate | Grading and murraming of JB estate | To improve road infrastructure by grading and murraming JB estate | JB estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1476400 | 92.3 | 1476400 | 2500000 | 123600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
6399 | Infrastructure, Development and Maintenance | Grading and murraming of Mzee wanyama estate | To improve road infrastructure by grading and murraming Mzee wanyama estate | Mzee wanyama estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.405637, 36.14086 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2385400 | 95.4 | 2385400 | 1419 | 114600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot enterprises. Assessor remarks: Grading needed.
6400 | Infrastructure, Development & Maintenance | Grading and Murraming of Kamara-Kamasit roads | To improve road infrastructure by grading and murraming Kamara-Kamasit roads | Kamara-Kamasit roads graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.419334, 35.932833 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 997604 | 997604 | Equitable | N/A | 997604 | 0 | 2333210 | 233.9 | 2333210 | 997604 | -1335606 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Beliot investment limited. Assessor remarks: The road requires regular maintenance.
6401 | Infrastructure, Development & Maintenance | Grading, Murraming and culverting of Cutline-Kamasut Road | To implement grading, murraming and culverting of cutline-kamasut road for road connectivity and accessibility | Grading, Murraming and culverting of Cutline-Kamasut Road completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.428558, 35.933756 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999490.2 | 1999490.2 | Equitable | N/A | 1999490.2 | 0 | 1995518 | 99.8 | 1995518 | 1999490 | 3972.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition, it just needs regular maintenance.
6402 | Infrastructure, Development & Maintenance | Grading, Murraming and culverting of Junction-KAP JONA-CHEPORGEI | To implement grading, murraming and culverting of junction-kap jona-cheporgei for road connectivity and accessibility | Grading, Murraming and culverting of Junction-KAP JONA-CHEPORGEI completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.417985, 35.882619 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1840920 | 92 | 1840920 | 1840920 | 159080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in poor condition and requires urgent improvement.
6403 | Hire of machineries and Road equipments | Hire of machineries and Road equipments | To implement hire of machineries and road equipments for road connectivity and accessibility | Hire of machineries and Road equipments completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.429181, 35.914642 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Project yet to start. Viable: Project yet to start. Assessor remarks: Project stalled due to lack of fuel for the equipments.
6404 | Installation of culverts across nessuit ward | Installation of culverts across nessuit ward | To improve drainage and road access through culvert installation at across nessuit ward | Culverts installed at across nessuit ward | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.369043, 35.898225 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1794420 | 89.7 | 1794420 | 1797420 | 205580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The culverts need unclogging.
6405 | Infrastructure, Development & Maintenance | Labourer for bush clearing and drainage works | To implement labourer for bush clearing and drainage works for road connectivity and accessibility | Labourer for bush clearing and drainage works completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6406 | Supply of murram though boresha barabara | Supply of murram though boresha barabara | To implement supply of murram though boresha barabara for road connectivity and accessibility | Supply of murram though boresha barabara completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.415382, 35.918672 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Project yet to start. Assessor remarks: Project yet to start.
6407 | Grading and murraming of Kahuho piave road networks | Grading and murraming of Kahuho piave road networks | To improve road infrastructure by grading and murraming Kahuho piave road networks | Kahuho piave road networks graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.311463, 35.984126 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1768850 | 88.4 | 1768850 | 69979 | 231150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wikagi contractors. Assessor remarks: In fair state.
6408 | Infrastructure, Development & Maintenance | Hiring of boresha barabara machineries | To implement hiring of boresha barabara machineries for road connectivity and accessibility | Hiring of boresha barabara machineries completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.302031 35.891603 2245.38916015625 10.288999557495117 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 8300000 | 8300000 | 8300000 | Equitable | N/A | 8300000 | 0 | 6997045 | 84.3 | 6997045 | 8000000 | 1302955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Worn out due to rain.
6409 | Infrastructure, Development & Maintenance | Installation of Culverts at Beeston Feeder Roads | To improve drainage and road access through culvert installation at Beeston Feeder Roads | Culverts installed at Beeston Feeder Roads | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.366398, 35.907184 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
6410 | Infrastructure, Development & Maintenance | Construction of chesirikwa shed | To construct chesirikwa shed | Chesirikwa shed constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.410803 35.655528 2673.7 13.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 317534 | 79.4 | 317534 | 317534 | 82466 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent painting..
6411 | Infrastructure, Development & Maintenance | Grading and murraming mkeu road | To improve road infrastructure by grading and murraming mkeu road | Mkeu road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499575 | 100 | 1499575 | 1499575 | 425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
6412 | Infrastructure, Development and Maintenance | Grading and murraming of 3 PS road | To improve road infrastructure by grading and murraming 3 PS road | 3 PS road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498217 | 99.9 | 1498217 | 1499461 | 1783 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
6413 | Infrastructure, Development & Maintenance | Grading and murraming of baringo valley road | To improve road infrastructure by grading and murraming baringo valley road | Baringo valley road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1374920 | 91.7 | 1374920 | 1374920 | 125080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
6414 | Infrastructure, Development and Maintenance | Grading and Murraming of Chesingele - Omari Road | To improve road infrastructure by grading and murraming Chesingele - Omari Road | Chesingele - Omari Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.388303, 35.628555 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024-2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 561629 | 22.5 | 561629 | 190721 | 1938371 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Yes. Assessor remarks: Side grills are missing, Refl.
6415 | Infrastructure, Development & Maintenance | Grading and murraming of Kamore road | To improve road infrastructure by grading and murraming Kamore road | Kamore road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1828545 | 91.4 | 1828545 | 1828545 | 171455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
6416 | Infrastructure, Development and Maintenance | Grading and murraming of masaita road | To improve road infrastructure by grading and murraming masaita road | Masaita road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499715 | 100 | 1499715 | 1499715 | 285 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
6417 | Infrastructure, Development and Maintenance | Grading and murraming of Sasimua road | To improve road infrastructure by grading and murraming Sasimua road | Sasimua road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1836395 | 91.8 | 1836395 | 1836395 | 163605 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
6418 | Infrastructure, Development and Maintenance | Grading and Murraming of Songo Musola Road | To improve road infrastructure by grading and murraming Songo Musola Road | Songo Musola Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 2400000 | 0 | 2400000 | Equitable | N/A | 2400000 | 0 | 1966913 | 0 | 1966913 | 362100 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
6419 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Aremi Sitoito road | To implement grading, gravelling and compaction of aremi sitoito road for road connectivity and accessibility | Grading, Gravelling and compaction of Aremi Sitoito road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.37899, 35.585875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2017-2018 | 1412958 | 2912958 | 2912958 | Equitable | N/A | 2912958 | 0 | 2912958 | 100 | 2912958 | 2912958 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: No. Viable: Yes if done. Assessor remarks: Bad state- Needs urgent attention..
6420 | Infrastructure, Development and Maintenance | Grading,murraming and gravelling of sasimua road | To implement grading,murraming and gravelling of sasimua road for road connectivity and accessibility | Grading,murraming and gravelling of sasimua road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.308548, 35.645022 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | _ | 1500000 | 1491999 | 1491999 | Equitable | N/A | 1491999 | 0 | 1419999 | 95.2 | 1419999 | 1491999 | 72000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: ACCESSIBLE.
6421 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Mawingu Centre to lami juu road | To implement gravelling and murraming of 3km of mawingu centre to lami juu road for road connectivity and accessibility | Gravelling and murraming of 3km of Mawingu Centre to lami juu road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2962988 | 2962988 | Equitable | N/A | 2962988 | 0 | 2962988 | 100 | 2962988 | 2962988 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
6422 | Infrastructure, Development & Maintenance | Construction of drainage system along kwa kahato road | To construct drainage system along kwa kahato road | Drainage system along kwa kahato road constructed | 3110499 | Construction of Roads - Other | Nakuru West | Rhonda | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1597200 | 79.9 | 1597200 | 1597200 | 402800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6423 | Infrastructure, Development & Maintenance | Construction of drainages along sewerage-PCEA road | To construct drainages along sewerage-PCEA road | Drainages along sewerage-PCEA road constructed | 3110499 | Construction of Roads - Other | Nakuru West | Rhonda | -0.316155, 36.062155 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 21/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1534800 | 76.7 | 1534800 | 1534800 | 465200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Aimers construction ltd. Assessor remarks: Complete.
6424 | Infrastructure, Development and Maintenance | Drainages at mwariki,lake area | To implement drainages at mwariki,lake area for road connectivity and accessibility | Drainages at mwariki,lake area completed | 3110499 | Construction of Roads - Other | Nakuru West | Rhonda | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1700328 | 85 | 1700328 | 1700328 | 299672 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6425 | Infrastructure, Development & Maintenance | Construction of Gacharage roads | To construct Gacharage roads | Gacharage roads constructed | 3110499 | Construction of Roads - Other | KURESOI NORTH | SIRIKWA | -0.289234 35.63603 2712.264136918813 13 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2643077 | 2643077 | 2643077 | Equitable | N/A | 2643077 | 0 | 2618608 | 99.1 | 2618608 | 2643077 | 24469 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use though it has no water supply.
6426 | Infrastructure, Development & Maintenance | Grading and gravelling of sirikwa center- bondet road | To improve road infrastructure by grading and murraming sirikwa center- bondet road | Sirikwa center- bondet road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | SIRIKWA | -0.277388, 35.661785 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2994583 | 99.8 | 2994583 | 189430 | 5417 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road in use,, however some sections needs, murraming afresh, bush clearing.
6427 | Infrastructure, Development & Maintenance | Kamonde-sawati road construction | To implement kamonde-sawati road construction for road connectivity and accessibility | Kamonde-sawati road construction completed | 3110499 | Construction of Roads - Other | RONGAI | SOIN | -0.07098, 36.048205 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199200 | 99.9 | 1199200 | 1199200 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs repair.
6428 | Infrastructure, Development & Maintenance | Grading and murraming of Kapsetek centre-Kalasinga farm road | To improve road infrastructure by grading and murraming Kapsetek centre-Kalasinga farm road | Kapsetek centre-Kalasinga farm road graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOIN | -0.055935 36.076458 1641.2 3.200000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1482680 | 98.8 | 1482680 | 119 | 17320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
6429 | Infrastructure, Development & Maintenance | Grading of peter chotara-sawaiti-Benita-border road | To improve road accessibility by grading peter chotara-sawaiti-Benita-border road | Peter chotara-sawaiti-Benita-border road graded | 3110499 | Construction of Roads - Other | RONGAI | SOIN | -0.118689 35.950928 1739 7.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 759300 | 94.9 | 759300 | 759300 | 40700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
6430 | Infrastructure, Development & Maintenance | Grading and Murraming Kiboronjo-Kithire-Mutitaithia Road | To improve road infrastructure by grading and murraming Kiboronjo-Kithire-Mutitaithia Road | Kiboronjo-Kithire-Mutitaithia Road graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1894512 | 94.7 | 1894512 | 1999330 | 105488 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6431 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road | To improve road accessibility by grading and Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road | And Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road graded | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997920 | 99.9 | 1997920 | 1999080 | 2080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6432 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Lower Solai-Machine-Koimogul Road | To improve road accessibility by grading and Murraming/culverts Lower Solai-Machine-Koimogul Road | And Murraming/culverts Lower Solai-Machine-Koimogul Road graded | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2650000 | 2650000 | 2650000 | Equitable | N/A | 2650000 | 0 | 2540215 | 95.9 | 2540215 | 2650000 | 109785 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6433 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Tegunot-Rocks road | To improve road accessibility by grading and Murraming/culverts Tegunot-Rocks road | And Murraming/culverts Tegunot-Rocks road graded | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1296254 | 99.7 | 1296254 | 1299432 | 3746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6434 | Infrastructure, Development & Maintenance | Grading and murraming of Aruus-kwamusa-cherono roads | To improve road infrastructure by grading and murraming Aruus-kwamusa-cherono roads | Aruus-kwamusa-cherono roads graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991500 | 99.6 | 1991500 | 1000616 | 8500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6435 | Infrastructure, Development & Maintenance | Grading and murraming of Tuiyomoi road | To improve road infrastructure by grading and murraming Tuiyomoi road | Tuiyomoi road graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000610 | 100.1 | 1000610 | 1000616 | -610 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6436 | Infrastructure, Development and Maintenance | Grading, Murraming and construction of Gabion at white rock-Dip road | To implement grading, murraming and construction of gabion at white rock-dip road for road connectivity and accessibility | Grading, Murraming and construction of Gabion at white rock-Dip road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.159874 36.164702 1611.9619140625 8.440999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 252511 | 8.4 | 252511 | 252511 | 2747489 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is well maintained.
6437 | Infrastructure, Development & Maintenance | Murraming, construction of drift and light grading of Murram-Sigito road | To implement murraming, construction of drift and light grading of murram-sigito road for road connectivity and accessibility | Murraming, construction of drift and light grading of Murram-Sigito road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.046738 36.12905 1518.959228515625 3.7899999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2490729 | 99.6 | 2490729 | 2471 | 9271 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6438 | Infrastructure, Development & Maintenance | Spot Murraming and grading of Tuyotich-Chemasis road | To implement spot murraming and grading of tuyotich-chemasis road for road connectivity and accessibility | Spot Murraming and grading of Tuyotich-Chemasis road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.023199, 36.126949 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 105750 | 5.3 | 105750 | 105750 | 1894250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6439 | Infrastructure, Development & Maintenance | Grading and murraming of rumathi-grogon road | To improve road infrastructure by grading and murraming rumathi-grogon road | Rumathi-grogon road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | SUBUKIA | -0.020588, 36.22147 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 01/12/2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1500000 | 60 | 1500000 | 2500000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. Contractor: Information not available. Assessor remarks: Good work.
6440 | Infrastructure, Development and Maintenance | Cabro paving at Shaabab Market | To implement cabro paving at shaabab market for road connectivity and accessibility | Cabro paving at Shaabab Market completed | 3110499 | Construction of Roads - Other | Nakuru West | Shabab | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2774426 | 2774426 | 2774426 | Equitable | N/A | 2774426 | 0 | 2614300 | 94.2 | 2614300 | 2614300 | 160126 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6441 | Infrastructure, Development and Maintenance | Drainage system at mariakani road | To implement drainage system at mariakani road for road connectivity and accessibility | Drainage system at mariakani road completed | 3110499 | Construction of Roads - Other | Nakuru West | Shabab | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 3022758 | 3022758 | 3022758 | Equitable | N/A | 3022758 | 0 | 2839444 | 93.9 | 2839444 | 2839600 | 183314 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6442 | Infrastructure, Development and Maintenance | Drainage works at Lokichar Road | To implement drainage works at lokichar road for road connectivity and accessibility | Drainage works at Lokichar Road completed | 3110499 | Construction of Roads - Other | Nakuru West | Shabab | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2265900 | 90.6 | 2265900 | 2265900 | 234100 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6443 | Infrastructure, Development and Maintenance | Drainage works at Sondu Drive | To implement drainage works at sondu drive for road connectivity and accessibility | Drainage works at Sondu Drive completed | 3110499 | Construction of Roads - Other | Nakuru West | Shabab | -0.530098, 36.383684 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2315000 | 89 | 2315000 | 2315000 | 285000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
6444 | Infrastructure, Development & Maintenance | Construction of Gacharage roads | To construct Gacharage roads | Gacharage roads constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.289234 35.63603 2712.264136918813 13 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2643077 | 2643077 | 2643077 | Equitable | N/A | 2643077 | 0 | 2618608 | 99.1 | 2618608 | 2643077 | 24469 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use though it has no water supply.
6445 | Grading and murraming of ADC- cheptagum road | Grading and murraming of ADC- cheptagum road | To improve road infrastructure by grading and murraming ADC- cheptagum road | ADC- cheptagum road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.27362, 35.661595 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1881885 | 94.1 | 1881885 | 1881885 | 118115 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is still in use, however the road needs reshaping, and murraming afresh, bush clearing and culverting in some sections.
6446 | Infrastructure, Development & Maintenance | Grading and murraming of kangawa-upendo roads | To improve road infrastructure by grading and murraming kangawa-upendo roads | Kangawa-upendo roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.209732, 35.702143 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1810570 | 90.5 | 1810570 | 1810570 | 189430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project has recently been repaired by county government.
6447 | Infrastructure, Development & Maintenance | Grading and murraming of sirikwa secondary-taachasis road | To improve road infrastructure by grading and murraming sirikwa secondary-taachasis road | Sirikwa secondary-taachasis road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.256867, 35.66989 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1617590 | 80.9 | 1617590 | 189430 | 382410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, but at the moment it is challenging especially during raining days. Viable: Yes. Assessor remarks: The project is in poor state, needs to be worked on afresh.
6448 | Infrastructure, Development and Maintenance | Grading, murraming and culverts installation in Kaptembwa access road | To implement grading, murraming and culverts installation in kaptembwa access road for road connectivity and accessibility | Grading, murraming and culverts installation in Kaptembwa access road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.252485 35.680303 2662.7 14.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1602345 | 53.4 | 1602345 | 3000000 | 1397655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs reshaping, culvert unblocking and installation of new, bush clearing.
6449 | Infrastructure, Development and Maintenance | Grading, murraming and culverts installation in Sirikwa road networks | To implement grading, murraming and culverts installation in sirikwa road networks for road connectivity and accessibility | Grading, murraming and culverts installation in Sirikwa road networks completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.252485 35.680303 2662.7 14.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2237235 | 111.9 | 2237235 | 2000000 | -237235 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs reshaping, culvert unblocking and installation of new, bush clearing.
6450 | Infrastructure, Development & Maintenance | Grading, murraming and drainage works of Motto access road | To implement grading, murraming and drainage works of motto access road for road connectivity and accessibility | Grading, murraming and drainage works of Motto access road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.26333, 35.665958 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1602345 | 80.1 | 1602345 | 1602345 | 397655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Reshaping, drainage, culverting, and culvert unblocking and murraming works needed.
6451 | Infrastructure, Development & Maintenance | Grading, murraming and drainage works of Sirikwa roads | To implement grading, murraming and drainage works of sirikwa roads for road connectivity and accessibility | Grading, murraming and drainage works of Sirikwa roads completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.26333, 35.665958 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3190625 | 3190625 | 3190625 | Equitable | N/A | 3190625 | 0 | 2237235 | 70.1 | 2237235 | 693970 | 953390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Reshaping, drainage, culverting, and culvert unblocking and murraming works needed.
6452 | Infrastructure, Development and Maintenance | Installation of highmast lights in Sirikwa | To improve security lighting through high mast floodlight installation at lights in Sirikwa | High mast floodlight installed at lights in Sirikwa | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.288318, 35.642182 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2100000 | 2100000 | 2975797 | Equitable | N/A | 2975797 | 0 | 2840000 | 135.2 | 2840000 | 2975797 | -740000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes, however the faulty ones need repairs while Kenya power needs to reconnect the rest. Assessor remarks: The mast at Baringo is faulty while the rest were disconnected by Kenya power.
6453 | Construction of a bridge/culverts along Lomolo A-Lomolo B road | Construction of a bridge/culverts along Lomolo A-Lomolo B road | To construct a bridge/culverts along Lomolo A-Lomolo B road | A bridge/culverts along Lomolo A-Lomolo B road constructed | 3110499 | Construction of Roads - Other | Rongai | Soin | 0.00414, 36.036628 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | FY 2020 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 748000 | 93.5 | 748000 | 748000 | 52000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
6454 | Construction of boda boda shed at morop stage | Construction of boda boda shed at morop stage | To construct boda boda shed at morop stage | Boda boda shed at morop stage constructed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.121653, 35.948328 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/2022 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 289700 | 96.6 | 289700 | 600000 | 10300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
6455 | Infrastructure, Development & Maintenance | Installation of highmast light at kapsetek center | To improve security lighting through high mast floodlight installation at light at kapsetek center | High mast floodlight installed at light at kapsetek center | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.081677, 35.872422 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 234000 | 78 | 234000 | 300000 | 66000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Community are grateful.
6456 | Installation of highmast lights at kiroyo(4),morop stage(1),athinai(1) and lesibil (1) | Installation of highmast lights at kiroyo(4),morop stage(1),athinai(1) and lesibil (1) | To improve security lighting through high mast floodlight installation at lights at kiroyo(4),morop stage(1),athinai(1) and lesibil (1) | High mast floodlight installed at lights at kiroyo(4),morop stage(1),athinai(1) and lesibil (1) | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.124768, 35.943304 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1985750 | 94.6 | 1985750 | 1985750 | 114250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require routine maintenance.
6457 | Infrastructure, Development & Maintenance | Kamonde-sawati road construction | To implement kamonde-sawati road construction for road connectivity and accessibility | Kamonde-sawati road construction completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.07098, 36.048205 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199200 | 1199200 | Equitable | N/A | 1199200 | 0 | 1199200 | 100 | 1199200 | 1199200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs repair.
6458 | Soin Road rehabilitation ( Hire of machines / fuels for road maintenance and rehabilitation | Soin Road rehabilitation ( Hire of machines / fuels for road maintenance and rehabilitation | To implement soin road rehabilitation ( hire of machines / fuels for road maintenance and rehabilitation for road connectivity and accessibility | Soin Road rehabilitation ( Hire of machines / fuels for road maintenance and rehabilitation completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.080693, 35.871902 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2990500 | 99.7 | 2990500 | 3000000 | 9500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RAHASA VENTURES LTD. Assessor remarks: Require repair.
6459 | Infrastructure, Development & Maintenance | Grading of peter chotara-sawaiti-Benita-border road | To improve road accessibility by grading peter chotara-sawaiti-Benita-border road | Peter chotara-sawaiti-Benita-border road graded | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.118689 35.950928 1739 7.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 759300 | 94.9 | 759300 | 759300 | 40700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
6460 | Infrastructure, Development & Maintenance | Grading and Murraming Kiboronjo-Kithire-Mutitaithia Road | To improve road infrastructure by grading and murraming Kiboronjo-Kithire-Mutitaithia Road | Kiboronjo-Kithire-Mutitaithia Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999330 | 1999330 | Equitable | N/A | 1999330 | 0 | 1894512 | 94.8 | 1894512 | 1999330 | 104818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6461 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road | To improve road accessibility by grading and Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road | And Murraming/culverts Kapkoros-Mahinga-Ngendaptich Road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997920 | 99.9 | 1997920 | 1999080 | 2080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6462 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Lower Solai-Machine-Koimogul Road | To improve road accessibility by grading and Murraming/culverts Lower Solai-Machine-Koimogul Road | And Murraming/culverts Lower Solai-Machine-Koimogul Road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2650000 | 2650000 | 2650000 | Equitable | N/A | 2650000 | 0 | 2540215 | 95.9 | 2540215 | 2650000 | 109785 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6463 | Infrastructure, Development & Maintenance | Grading and Murraming/culverts Tegunot-Rocks road | To improve road accessibility by grading and Murraming/culverts Tegunot-Rocks road | And Murraming/culverts Tegunot-Rocks road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1299432 | 1299432 | Equitable | N/A | 1299432 | 0 | 1296254 | 99.8 | 1296254 | 1299432 | 3178 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6464 | Rebabilitation of chemasis,arutani,ruyobei roads through hire of equipments and machineries and culverts installation | Rebabilitation of chemasis,arutani,ruyobei roads through hire of equipments and machineries and culverts installation | To implement rebabilitation of chemasis,arutani,ruyobei roads through hire of equipments and machineries and culverts installation for road connectivity and accessibility | Rebabilitation of chemasis,arutani,ruyobei roads through hire of equipments and machineries and culverts installation completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.011106 36.145174 1538.291259765625 27.833999633789062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2227851 | 2227851 | 2227851 | Equitable | N/A | 2227851 | 0 | 2227851 | 100 | 2227851 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6465 | Rehabilitation of roads through hire of machinery and equipment in koisamo area | Rehabilitation of roads through hire of machinery and equipment in koisamo area | To rehabilitate roads through hire of machinery and equipment in koisamo area to restore functionality | Roads through hire of machinery and equipment in koisamo area rehabilitated | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.011106 36.145174 1538.291259765625 27.833999633789062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6466 | Rehabilitation of roads through hire of machinery and equipment in Lower Solai area | Rehabilitation of roads through hire of machinery and equipment in Lower Solai area | To rehabilitate roads through hire of machinery and equipment in Lower Solai area to restore functionality | Roads through hire of machinery and equipment in Lower Solai area rehabilitated | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.011106 36.145174 1538.291259765625 27.833999633789062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6467 | Rehabilitation of roads through hire of machinery and equipment in murram-Sigito-Chemasis Nyandarua roads | Rehabilitation of roads through hire of machinery and equipment in murram-Sigito-Chemasis Nyandarua roads | To rehabilitate roads through hire of machinery and equipment in murram-Sigito-Chemasis Nyandarua roads to restore functionality | Roads through hire of machinery and equipment in murram-Sigito-Chemasis Nyandarua roads rehabilitated | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.011106 36.145174 1538.291259765625 27.833999633789062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3500000 | 100 | 3500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6468 | Rehabilitation of roads through hire of machinery and equipment in Ngendaptich-Arus-Maji tamu roads | Rehabilitation of roads through hire of machinery and equipment in Ngendaptich-Arus-Maji tamu roads | To rehabilitate roads through hire of machinery and equipment in Ngendaptich-Arus-Maji tamu roads to restore functionality | Roads through hire of machinery and equipment in Ngendaptich-Arus-Maji tamu roads rehabilitated | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.011106 36.145174 1538.291259765625 27.833999633789062 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6469 | Infrastructure, Development & Maintenance | Grading and murraming of Tuiyomoi road | To improve road infrastructure by grading and murraming Tuiyomoi road | Tuiyomoi road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000610 | 100.1 | 1000610 | 1000616 | -610 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6470 | Infrastructure, Development and Maintenance | Grading, Murraming and construction of Gabion at white rock-Dip road | To implement grading, murraming and construction of gabion at white rock-dip road for road connectivity and accessibility | Grading, Murraming and construction of Gabion at white rock-Dip road completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.159874 36.164702 1611.9619140625 8.440999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2987147 | 2987147 | Equitable | N/A | 2987147 | 0 | 252511 | 8.5 | 252511 | 252511 | 2734636 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is well maintained.
6471 | Infrastructure, Development & Maintenance | Spot Murraming and grading of Tuyotich-Chemasis road | To implement spot murraming and grading of tuyotich-chemasis road for road connectivity and accessibility | Spot Murraming and grading of Tuyotich-Chemasis road completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.023199, 36.126949 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 105750 | 105750 | Equitable | N/A | 105750 | 0 | 105750 | 100 | 105750 | 105750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6472 | Infrastructure, Development and Maintenance | Grading and gravelling of kimoni taribo road | To improve road infrastructure by grading and murraming kimoni taribo road | Kimoni taribo road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.029452, 36.236129 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1482400 | 98.8 | 1482400 | 1500000 | 17600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: The road serves the community. Contractor: Information not available. Assessor remarks: Good work.
6473 | Infrastructure, Development & Maintenance | Grading and murraming and construction of bridge of Grogon Kwa Maina Tetu road | To improve road infrastructure by grading and murraming and construction of bridge of Grogon Kwa Maina Tetu road | And construction of bridge of Grogon Kwa Maina Tetu road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.031797 36.1717 2081.5 2 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1894176 | 75.8 | 1894176 | 591246 | 605824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to be redo.
6474 | Infrastructure, Development & Maintenance | Grading and murraming of Arash Mande road | To improve road infrastructure by grading and murraming Arash Mande road | Arash Mande road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.020588, 36.22147 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 01/12/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. Contractor: Information not available. Assessor remarks: Good work.
6475 | Grading and murraming of Kibe-Hyrax-Magomano secondary Road at Gatongu | Grading and murraming of Kibe-Hyrax-Magomano secondary Road at Gatongu | To improve road infrastructure by grading and murraming Kibe-Hyrax-Magomano secondary Road at Gatongu | Kibe-Hyrax-Magomano secondary Road at Gatongu graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.031748, 36.171823 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1927800 | 96.4 | 1927800 | 1927800 | 72200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Need to be redone.
6476 | Grading and murraming of Subukia day-soko mjinga,Wainaina muchori,-paul Gakuha road | Grading and murraming of Subukia day-soko mjinga,Wainaina muchori,-paul Gakuha road | To improve road infrastructure by grading and murraming Subukia day-soko mjinga,Wainaina muchori,-paul Gakuha road | Subukia day-soko mjinga,Wainaina muchori,-paul Gakuha road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.019127, 36.215098 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes road opened up and upgraded. Viable: Yes. Contractor: Details not ot available. Assessor remarks: Requires more murraming.
6477 | Infrastructure, Development and Maintenance | Grading and murraming of thungura-wakamau-chiefs office road in kijabe | To improve road infrastructure by grading and murraming thungura-wakamau-chiefs office road in kijabe | Thungura-wakamau-chiefs office road in kijabe graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.0247, 36.239128 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, access road opened up. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires more murraming and continuous grading.
6478 | Infrastructure, Development & Maintenance | Grading ,murraming and installation of culverts at rukuini-grave yard-mosque-JEC church and Kwa Michael road in subukia center | To improve road accessibility by grading ,murraming and installation of culverts at rukuini-grave yard-mosque-JEC church and Kwa Michael road in subukia center | ,murraming and installation of culverts at rukuini-grave yard-mosque-JEC church and Kwa Michael road in subukia center graded | 3110499 | Construction of Roads - Other | Subukia | Subukia | 0.003171, 36.233178 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access to trading centre, homes and work places enhanced. Contractor: Details not availed. Assessor remarks: Road is in good state.
6479 | Infrastructure, Development and Maintenance | Grading,culverts and murraming of mugumoini-gichu road in muthaiga kianoe | To implement grading,culverts and murraming of mugumoini-gichu road in muthaiga kianoe for road connectivity and accessibility | Grading,culverts and murraming of mugumoini-gichu road in muthaiga kianoe completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.980495, 36.581642 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1069856 | 1069856 | 1069856 | Equitable | N/A | 1069856 | 0 | 377505 | 35.3 | 377505 | 692351 | 692351 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6480 | Infrastructure, Development and Maintenance | Grading,murraming and culverts installation at ngomongo road in tetu | To implement grading,murraming and culverts installation at ngomongo road in tetu for road connectivity and accessibility | Grading,murraming and culverts installation at ngomongo road in tetu completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.052713, 36.22759 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 10/04/2023 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Sure.. Contractor: Information not available. Assessor remarks: Good work.
6481 | Infrastructure, Development & Maintenance | Hire of Equipments for road maintenance,grading and gravelling at arash location and subukia east location in subukia ward | To implement hire of equipments for road maintenance,grading and gravelling at arash location and subukia east location in subukia ward for road connectivity and accessibility | Hire of Equipments for road maintenance,grading and gravelling at arash location and subukia east location in subukia ward completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.018708, 36.195552 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3900000 | 100 | 3900000 | 3900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access road to the village and farms opened up. Contractor: Details not availed. Assessor remarks: The road is well maintained.
6482 | Infrastructure, Development & Maintenance | Hire of Equipments for road maintenance,grading and gravelling at Munanda location in subukia ward | To implement hire of equipments for road maintenance,grading and gravelling at munanda location in subukia ward for road connectivity and accessibility | Hire of Equipments for road maintenance,grading and gravelling at Munanda location in subukia ward completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.018708, 36.195552 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 3100000 | 100 | 3100000 | 3100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access road to the village and farms opened up. Contractor: Details not availed. Assessor remarks: The road is well maintained.
6483 | Infrastructure, Development & Maintenance | Grading and murraming of kapsita road | To improve road infrastructure by grading and murraming kapsita road | Kapsita road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | TURI | -0.266688 35.739926 2554.4 13.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996950 | 99.8 | 1996950 | 2890 | 3050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Newly graded again but not good during rainy season.
6484 | Infrastructure, Development & Maintenance | Grading and Murraming Yatta Road | To improve road infrastructure by grading and murraming Yatta Road | Yatta Road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | TURI | -0.310717, 35.700182 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1067329 | 1067329 | 1067329 | Equitable | N/A | 1067329 | 0 | 1067329 | 100 | 1067329 | 1067329 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In bad state, in need of rehabilitation.
6485 | Infrastructure, Development & Maintenance | Grading and gravelling of Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | To improve road infrastructure by grading and murraming Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads graded and murramed | 3110499 | Construction of Roads - Other | MOLO | TURI | -0.32764, 35.739845 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5200000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2524633 | 72.1 | 2524633 | 975367 | 975367 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Is good use.
6486 | Infrastructure, Development and Maintenance | Construction of chepsoet bridge | To construct chepsoet bridge | Chepsoet bridge constructed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1999113 | 66.6 | 1999113 | 2741140 | 1000887 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
6487 | Infrastructure, Development & Maintenance | hiring of machines and Fuelling for Tinet road networks and culverts installation | To implement hiring of machines and fuelling for tinet road networks and culverts installation for road connectivity and accessibility | hiring of machines and Fuelling for Tinet road networks and culverts installation completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.436869 35.625097 0 5199.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 10019025 | 10019025 | 10019025 | Equitable | N/A | 10019025 | 0 | 4784648 | 47.8 | 4784648 | 10019025 | 5234377 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad state.
6488 | Infrastructure, Development & Maintenance | Grading and gravelling of Inooro -Managu road | To improve road infrastructure by grading and murraming Inooro -Managu road | Inooro -Managu road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.330458, 35.729053 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
6489 | Grading and gravelling of kiambiriria primary to tarmac road | Grading and gravelling of kiambiriria primary to tarmac road | To improve road infrastructure by grading and murraming kiambiriria primary to tarmac road | Kiambiriria primary to tarmac road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.299992, 35.695237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Rehabilitation has been done recently.
6490 | Grading and gravelling of michatha eastleigh roads | Grading and gravelling of michatha eastleigh roads | To improve road infrastructure by grading and murraming michatha eastleigh roads | Michatha eastleigh roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.28505, 35.739501 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 225310 | 22.5 | 225310 | 225310 | 774690 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6491 | Infrastructure, Development & Maintenance | Grading and gravelling of Ngwataniro road (kirangi) | To improve road infrastructure by grading and murraming Ngwataniro road (kirangi) | Ngwataniro road (kirangi) graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.322798 35.738772 2674.6 8.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 701405 | 701405 | 701405 | Equitable | N/A | 701405 | 0 | 701405 | 100 | 701405 | 701405 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road has been redone last financial year.
6492 | Infrastructure, Development & Maintenance | Grading and gravelling of Turi center road | To improve road infrastructure by grading and murraming Turi center road | Turi center road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.282736, 35.75818 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It has been graded gravelled recently.
6493 | Infrastructure, Development & Maintenance | Grading and murraming of kapsita road | To improve road infrastructure by grading and murraming kapsita road | Kapsita road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.266688 35.739926 2554.4 13.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999840 | 1999840 | Equitable | N/A | 1999840 | 0 | 1996950 | 99.9 | 1996950 | 2890 | 2890 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Newly graded again but not good during rainy season.
6494 | Infrastructure, Development & Maintenance | Grading and Murraming of milima mitatu roads | To improve road infrastructure by grading and murraming milima mitatu roads | Milima mitatu roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.266712 35.73983 2554.4 11.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 208990 | 17.4 | 208990 | 208990 | 991010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road was graded but was not gravelled. It needs gravelling as it impassable during rainy season.
6495 | Infrastructure, Development & Maintenance | Grading and Murraming Yatta Road | To improve road infrastructure by grading and murraming Yatta Road | Yatta Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.310717, 35.700182 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1067329 | 1067329 | 1067329 | Equitable | N/A | 1067329 | 0 | 1067329 | 100 | 1067329 | 1067329 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In bad state, in need of rehabilitation.
6496 | Infrastructure, Development & Maintenance | grading, dozing and gravelling of roads mona center to tarmac road | To implement grading, dozing and gravelling of roads mona center to tarmac road for road connectivity and accessibility | grading, dozing and gravelling of roads mona center to tarmac road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.282278 35.758575 2480.10009765625 39.599998474121094 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road network has been adversely affected by the ongoing heavy rains.
6497 | Infrastructure, Development & Maintenance | hiring of machinery and supply of murrum for ndenderu A and Turi farmers roads | To implement hiring of machinery and supply of murrum for ndenderu a and turi farmers roads for road connectivity and accessibility | hiring of machinery and supply of murrum for ndenderu A and Turi farmers roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.305733, 35.749693 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 798613 | 99.8 | 798613 | 800000 | 1387 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition.
6498 | hiring of machinery at net rate and supply of murrum for mkorombosi kavido road | hiring of machinery at net rate and supply of murrum for mkorombosi kavido road | To implement hiring of machinery at net rate and supply of murrum for mkorombosi kavido road for road connectivity and accessibility | hiring of machinery at net rate and supply of murrum for mkorombosi kavido road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -1.28019, 36.818118 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: COMPLETED AND OPERATIONAL.
6499 | hiring of machinery at net rate and supply of murrum for ndenderu B roads | hiring of machinery at net rate and supply of murrum for ndenderu B roads | To implement hiring of machinery at net rate and supply of murrum for ndenderu b roads for road connectivity and accessibility | hiring of machinery at net rate and supply of murrum for ndenderu B roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -1.28019, 36.818118 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: COMPLETED AND OPERATIONAL.
6500 | Infrastructure, Development & Maintenance | Hiring of machinery at wet rate and supply of murram for Mona,ngerefu kiambiriria and kapsita road | To implement hiring of machinery at wet rate and supply of murram for mona,ngerefu kiambiriria and kapsita road for road connectivity and accessibility | Hiring of machinery at wet rate and supply of murram for Mona,ngerefu kiambiriria and kapsita road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.330763 35.72908 2767.2000000000003 12.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
6501 | Infrastructure, Development & Maintenance | Installation of highmasts (Muilika mwizi) inn turi ward | To improve security lighting through high mast floodlight installation at s (Muilika mwizi) inn turi ward | High mast floodlight installed at s (Muilika mwizi) inn turi ward | 3110499 | Construction of Roads - Other | Molo | Turi | -0.301427, 35.696895 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1752750 | 292.1 | 1752750 | 600000 | -1152750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
6502 | Infrastructure, Development & Maintenance | Grading and gravelling of Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | To improve road infrastructure by grading and murraming Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.32764, 35.739845 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5200000 | 975367 | 975367 | Equitable | N/A | 975367 | 0 | 2524633 | 258.8 | 2524633 | 975367 | -1549266 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Is good use.
6503 | Grading and murraming of Kilombe to Kanga ,Moricho-mawe, | Grading and murraming of Kilombe to Kanga ,Moricho-mawe, | To improve road infrastructure by grading and murraming Kilombe to Kanga ,Moricho-mawe, | Kilombe to Kanga ,Moricho-mawe, graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | VISOI | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2653741 | 2653741 | 2653741 | Equitable | N/A | 2653741 | 0 | 2576410 | 97.1 | 2576410 | 2598960 | 77331 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6504 | Grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | Grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | To improve road accessibility by grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | And spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani graded | 3110499 | Construction of Roads - Other | RONGAI | VISOI | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1796290 | 99.8 | 1796290 | 1797300 | 3710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6505 | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe | To implement grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe for road connectivity and accessibility | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe completed | 3110499 | Construction of Roads - Other | RONGAI | VISOI | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1058326 | 105.8 | 1058326 | 1000000 | -58326 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6506 | Infrastructure, Development and Maintenance | Construction of viwandani access roads | To construct viwandani access roads | Viwandani access roads constructed | 3110499 | Construction of Roads - Other | NAIVASHA | VIWANDANI | -0.701188, 36.426037 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 1561259 | 22.3 | 1561259 | 1561243 | 5438741 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
6507 | Infrastructure, Development and Maintenance | Construction of Thirandu bridge | To construct Thirandu bridge | Thirandu bridge constructed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1009490 | 100.9 | 1009490 | 1000000 | -9490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6508 | Grading and culverts installation of Lenginet road network | Grading and culverts installation of Lenginet road network | To improve road accessibility by grading and culverts installation of Lenginet road network | And culverts installation of Lenginet road network graded | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.125318, 35.94229 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1301316 | 86.8 | 1301316 | 1794000 | 198684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road need repair.
6509 | Grading and murraming of ex butler and ngessumin networks | Grading and murraming of ex butler and ngessumin networks | To improve road infrastructure by grading and murraming ex butler and ngessumin networks | Ex butler and ngessumin networks graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2223175 | 88.9 | 2223175 | 2598960 | 276825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6510 | Grading and murraming of Kilombe to Kanga ,Moricho-mawe, | Grading and murraming of Kilombe to Kanga ,Moricho-mawe, | To improve road infrastructure by grading and murraming Kilombe to Kanga ,Moricho-mawe, | Kilombe to Kanga ,Moricho-mawe, graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2653741 | 2598960 | 2598960 | Equitable | N/A | 2598960 | 0 | 2576410 | 99.1 | 2576410 | 2598960 | 22550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6511 | Grading and murraming of Legetio-Magare-Mogolwet Molo river | Grading and murraming of Legetio-Magare-Mogolwet Molo river | To improve road infrastructure by grading and murraming Legetio-Magare-Mogolwet Molo river | Legetio-Magare-Mogolwet Molo river graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1049093 | 87.4 | 1049093 | 2598960 | 150907 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6512 | Grading and murraming of makanisa mingi-kwa kihuga road in kandutura | Grading and murraming of makanisa mingi-kwa kihuga road in kandutura | To improve road infrastructure by grading and murraming makanisa mingi-kwa kihuga road in kandutura | Makanisa mingi-kwa kihuga road in kandutura graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.12381 35.938642 1734.7 4.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1010774 | 1010774 | 1010774 | Equitable | N/A | 1010774 | 0 | 1058485 | 104.7 | 1058485 | 1500000 | -47711 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Road is worn out.
6513 | Grading and murraming of moricho-nyamwea-jamaica-butler road | Grading and murraming of moricho-nyamwea-jamaica-butler road | To improve road infrastructure by grading and murraming moricho-nyamwea-jamaica-butler road | Moricho-nyamwea-jamaica-butler road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.109025, 35.857873 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1071480 | 107.1 | 1071480 | 1500000 | -71480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not good,need repair.
6514 | Grading and murraming of Thirando access road network | Grading and murraming of Thirando access road network | To improve road infrastructure by grading and murraming Thirando access road network | Thirando access road network graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1054503 | 87.9 | 1054503 | 2990100 | 145497 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6515 | Infrastructure, Development & Maintenance | Grading and spot murraming of Bongoloia-muricho road | To improve road accessibility by grading and spot murraming of Bongoloia-muricho road | And spot murraming of Bongoloia-muricho road graded | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2576410 | 171.8 | 2576410 | 1500000 | -1076410 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6516 | Grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | Grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | To improve road accessibility by grading and spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani | And spot murraming of Kamukunji to Kware ,Independence church to Kahawa Factory,kahawa factory to kwa kirani graded | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1797300 | 1797300 | Equitable | N/A | 1797300 | 0 | 1796290 | 99.9 | 1796290 | 1797300 | 1010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6517 | Grading of kampi ya moto access roads networks | Grading of kampi ya moto access roads networks | To improve road accessibility by grading kampi ya moto access roads networks | Kampi ya moto access roads networks graded | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.11676, 35.922263 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1058485 | 88.2 | 1058485 | 0 | 141515 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair need rehabilitation.
6518 | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe | To implement grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe for road connectivity and accessibility | Grading,murraming,compaction and culverts of kwa kirani-oasis road,thirandu to kilombe completed | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1058326 | 105.8 | 1058326 | 1000000 | -58326 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6519 | Installation of culverts in Visoi Ward | Installation of culverts in Visoi Ward | To improve drainage and road access through culvert installation at in Visoi Ward | Culverts installed at in Visoi Ward | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.148545 35.873142 1880.4 14.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1096290 | 91.4 | 1096290 | 1794000 | 103710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6520 | Infrastructure, Development and Maintenance | installatiuon of floodlights (mulika mwizi ) at lenginet , visoi and muricho center | To implement installatiuon of floodlights (mulika mwizi ) at lenginet , visoi and muricho center for road connectivity and accessibility | installatiuon of floodlights (mulika mwizi ) at lenginet , visoi and muricho center completed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.148545 35.873142 1880.4 14.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6521 | Infrastructure, Development and Maintenance | Construction of viwandani access roads | To construct viwandani access roads | Viwandani access roads constructed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.701188, 36.426037 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 1561259 | 22.3 | 1561259 | 1561243 | 5438741 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
6522 | Laying of cabros in Viwandani | Laying of cabros in Viwandani | To implement laying of cabros in viwandani for road connectivity and accessibility | Laying of cabros in Viwandani completed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.717643, 36.434209 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 7081842 | 6331842 | 6331842 | Equitable | N/A | 6331842 | 0 | 0 | 0 | 0 | 6331842 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
6523 | installations of culverts and drainage works in Naivasha town | installations of culverts and drainage works in Naivasha town | To implement installations of culverts and drainage works in naivasha town for road connectivity and accessibility | installations of culverts and drainage works in Naivasha town completed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.717648 36.433385 1892.9000244140625 11.151000022888184 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 6973399 | 6973399 | 6973399 | Equitable | N/A | 6973399 | 0 | 0 | 0 | 0 | 6973399 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good.
6524 | Infrastructure, Development & Maintenance | Grading and Gravelling of Akuisi-kiriko road | To improve road infrastructure by grading and murraming Akuisi-kiriko road | Akuisi-kiriko road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1294500 | 99.6 | 1294500 | 1300000 | 5500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6525 | Infrastructure, Development & Maintenance | Grading and Gravelling of baharini-Kericho road | To improve road infrastructure by grading and murraming baharini-Kericho road | Baharini-Kericho road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 857463 | 42.9 | 857463 | 901112 | 1142537 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6526 | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | To improve road infrastructure by grading and murraming Wiyumiriria mbata moja -Ogilgei | Wiyumiriria mbata moja -Ogilgei graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1979543 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6527 | Infrastructure, Development & Maintenance | Grading and levelling Komu-Kaharagwe Road | To improve road accessibility by grading and levelling Komu-Kaharagwe Road | And levelling Komu-Kaharagwe Road graded | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2160655 | 108 | 2160655 | 2160655 | -160655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6528 | Infrastructure, Development & Maintenance | Grading and Murraming Kanyotu Baraka Road | To improve road infrastructure by grading and murraming Kanyotu Baraka Road | Kanyotu Baraka Road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.145993, 36.251227 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1857447 | 92.9 | 1857447 | 1998000 | 142553 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6529 | Infrastructure, Development & Maintenance | Grading of Mwiteithia-Suswa road (Kahuruko) | To improve road accessibility by grading Mwiteithia-Suswa road (Kahuruko) | Mwiteithia-Suswa road (Kahuruko) graded | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.16629, 36.249878 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 193044 | 14.8 | 193044 | 193044 | 1106956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6530 | Infrastructure, Development & Maintenance | Grading and Gravelling of Akuisi-kiriko road | To improve road infrastructure by grading and murraming Akuisi-kiriko road | Akuisi-kiriko road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1294500 | 99.6 | 1294500 | 1300000 | 5500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6531 | Infrastructure, Development & Maintenance | Grading and Gravelling of baharini-Kericho road | To improve road infrastructure by grading and murraming baharini-Kericho road | Baharini-Kericho road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 901112 | 901112 | Equitable | N/A | 901112 | 0 | 857463 | 95.2 | 857463 | 901112 | 43649 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6532 | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | To improve road infrastructure by grading and murraming Wiyumiriria mbata moja -Ogilgei | Wiyumiriria mbata moja -Ogilgei graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1979543 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6533 | Infrastructure, Development & Maintenance | Grading and levelling Komu-Kaharagwe Road | To improve road accessibility by grading and levelling Komu-Kaharagwe Road | And levelling Komu-Kaharagwe Road graded | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2160655 | 108 | 2160655 | 2160655 | -160655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6534 | Infrastructure, Development & Maintenance | Grading and Murraming Kanyotu Baraka Road | To improve road infrastructure by grading and murraming Kanyotu Baraka Road | Kanyotu Baraka Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.145993, 36.251227 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1998000 | 1998000 | Equitable | N/A | 1998000 | 0 | 1857447 | 93 | 1857447 | 1998000 | 140553 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6535 | Infrastructure, Development & Maintenance | Grading of Mwiteithia-Suswa road (Kahuruko) | To improve road accessibility by grading Mwiteithia-Suswa road (Kahuruko) | Mwiteithia-Suswa road (Kahuruko) graded | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.16629, 36.249878 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 193044 | 193044 | Equitable | N/A | 193044 | 0 | 193044 | 100 | 193044 | 193044 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
6536 | Infrastructure, Development & Maintenance | Hire of machinery and supply of murram | To implement hire of machinery and supply of murram for road connectivity and accessibility | Hire of machinery and supply of murram completed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.021193 36.258142 2118.1 8.399999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 4000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5999700 | 150 | 5999700 | 6000000 | -1999700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable road.
6537 | Infrastructure, Development and Maintenance | Construction of Mzalendo - Kiptenden bridge in Amalo Ward | To construct Mzalendo - Kiptenden bridge in Amalo Ward | Mzalendo - Kiptenden bridge in Amalo Ward constructed | 3110501 | Bridges | KURESOI SOUTH | AMALO | -0.574555, 35.69361 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2024 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1997200 | 95.1 | 1997200 | 67380 | 102800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
6538 | Infrastructure, Development and Maintenance | Construction of Mzalendo - Kiptenden bridge in Amalo Ward | To construct Mzalendo - Kiptenden bridge in Amalo Ward | Mzalendo - Kiptenden bridge in Amalo Ward constructed | 3110501 | Bridges | Kuresoi South | Amalo | -0.574555, 35.69361 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2024 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1997200 | 95.1 | 1997200 | 67380 | 102800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
6539 | Infrastructure, Development & Maintenance | Construction of Salama -ndimu linking bridge | To construct Salama -ndimu linking bridge | Salama -ndimu linking bridge constructed | 3110501 | Bridges | MOLO | ELBURGON | -0.279925 35.765083 0 2299.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 6043892 | 6043892 | 6043892 | Equitable | N/A | 6043892 | 0 | 2948335 | 48.8 | 2948335 | 6043892 | 3095557 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Pikverd supplies. Assessor remarks: Ongoing well.
6540 | Infrastructure, Development and Maintenance | Construction of Njeru bridge | To construct Njeru bridge | Njeru bridge constructed | 3110501 | Bridges | GILGIL | ELEMENTAITA | -0.581721 36.082011 2049.59 0.9729999899864197 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3392375 | 99.8 | 3392375 | 3394694 | 7625 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6541 | Construction of Mwatu A drainage | Construction of Mwatu A drainage | To construct Mwatu A drainage | Mwatu A drainage constructed | 3110501 | Bridges | Molo | Elburgon | -0.292988, 35.799262 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | -- | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2948335 | 98.3 | 2948335 | 12135 | 51665 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
6542 | Construction of Mwatu B Kasarani drainage | Construction of Mwatu B Kasarani drainage | To construct Mwatu B Kasarani drainage | Mwatu B Kasarani drainage constructed | 3110501 | Bridges | Molo | Elburgon | -0.292988, 35.799262 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | -- | 3043892 | 3043892 | 3043892 | Equitable | N/A | 3043892 | 0 | 3004757 | 98.7 | 3004757 | 15713 | 39135 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
6543 | Infrastructure, Development & Maintenance | installation of Elburgon ward culverts | To install Elburgon ward culverts | Elburgon ward culverts installed | 3110501 | Bridges | Molo | Elburgon | -0.303366, 35.81419 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 662173 | 94.6 | 662173 | 1858 | 37827 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6544 | Infrastructure, Development and Maintenance | Construction of Njeru bridge | To construct Njeru bridge | Njeru bridge constructed | 3110501 | Bridges | Gilgil | Elementaita | -0.581721 36.082011 2049.59 0.9729999899864197 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3394694 | 3394694 | Equitable | N/A | 3394694 | 0 | 3392375 | 99.9 | 3392375 | 3394694 | 2319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6545 | Infrastructure, Development & Maintenance | Construction of Chechina Bridge | To construct Chechina Bridge | Chechina Bridge constructed | 3110501 | Bridges | NAIVASHA | HELLS GATE | -0.784768, 36.455826 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983500 | 98.4 | 983500 | 983500 | 16500 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is passable but in need of reinforcement.
6546 | Infrastructure, Development & Maintenance | Construction of bridges at Musaka, Kuiwait and Nyamathi | To construct bridges at Musaka, Kuiwait and Nyamathi | Bridges at Musaka, Kuiwait and Nyamathi constructed | 3110501 | Bridges | NAIVASHA | HELLS GATE | -0.777804, 36.45138 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1815785 | 90.8 | 1815785 | 139627 | 184215 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is passable but it needs reinforcement.
6547 | Infrastructure, Development & Maintenance | Construction of Motorable and Foot-Bridges | To construct Motorable and Foot-Bridges | Motorable and Foot-Bridges constructed | 3110501 | Bridges | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 6978545 | 46.5 | 6978545 | 15000000 | 8021455 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6548 | Infrastructure, Development & Maintenance | Construction of Chechina Bridge | To construct Chechina Bridge | Chechina Bridge constructed | 3110501 | Bridges | Naivasha | Hells Gate | -0.784768, 36.455826 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 983500 | 983500 | Equitable | N/A | 983500 | 0 | 983500 | 100 | 983500 | 983500 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is passable but in need of reinforcement.
6549 | Grading and murraming and culverts for access roads in Kabazi ward | Grading and murraming and culverts for access roads in Kabazi ward | To improve road infrastructure by grading and murraming and culverts for access roads in Kabazi ward | And culverts for access roads in Kabazi ward graded and murramed | 3110501 | Bridges | SUBUKIA | KABAZI | -0.07772, 36.17076 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020/21 | 4989241 | 3489241 | 3489241 | Equitable | N/A | 3489241 | 0 | 3386875 | 97.1 | 3386875 | 3386875 | 102366 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires additional drainages.
6550 | Infrastructure, Development & Maintenance | Construction bridges & drainages and installation of Culverts | To construct bridges & drainages and installation of Culverts | Bridges & drainages and installation of Culverts constructed | 3110501 | Bridges | KURESOI NORTH | KAMARA | -0.172682 35.679654 2519.9 36.900001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 499284 | 23.8 | 499284 | 499284 | 1600716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs renovation.
6551 | Infrastructure, Development & Maintenance | Construction of a foot Bridge at mutirima-18 village | To construct a foot Bridge at mutirima-18 village | A foot Bridge at mutirima-18 village constructed | 3110501 | Bridges | NJORO | KIHINGO | -0.474738, 35.982825 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Refilling and murraming.
6552 | Infrastructure, Development & Maintenance | Construction of a foot Bridge at Wahome- waford road | To construct a foot Bridge at Wahome- waford road | A foot Bridge at Wahome- waford road constructed | 3110501 | Bridges | NJORO | KIHINGO | -0.439018 35.973144 2285.10009765625 32.0989990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Vandalized.
6553 | Infrastructure, Development & Maintenance | Construction of footbridge at mutito B | To construct footbridge at mutito B | Footbridge at mutito B constructed | 3110501 | Bridges | NJORO | KIHINGO | -0.440014 35.974624 2303.300048828125 98.4000015258789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
6554 | Infrastructure, Development & Maintenance | Construction of footbridge at subuku-munanda | To construct footbridge at subuku-munanda | Footbridge at subuku-munanda constructed | 3110501 | Bridges | NJORO | KIHINGO | -0.426452 35.9737 2257.5 14.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
6555 | Infrastructure, Development & Maintenance | Construction of Kigomba bridge | To construct Kigomba bridge | Kigomba bridge constructed | 3110501 | Bridges | KURESOI SOUTH | KIPTAGICH | -0.572478 35.61443 2486.500244140625 21.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable but it never met the required standard. Contractor: Don't know. Assessor remarks: The project was done as an ordinary pit latrine instead of the flushing system.
6556 | Infrastructure, Development & Maintenance | Construction of Buchege - Ogilgei foot bridge | To construct Buchege - Ogilgei foot bridge | Buchege - Ogilgei foot bridge constructed | 3110501 | Bridges | KURESOI NORTH | KIPTORORO | -0.377203 35.505747 0 800 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1272998 | 318.2 | 1272998 | 400000 | -872998 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
6557 | Infrastructure, Development & Maintenance | Construction of foot bridge at Kwa Muiruri - Kamuingi | To construct foot bridge at Kwa Muiruri - Kamuingi | Foot bridge at Kwa Muiruri - Kamuingi constructed | 3110501 | Bridges | KURESOI NORTH | KIPTORORO | -0.168805 35.689275 2517.4 3.799999952316284 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1272998 | 424.3 | 1272998 | 300000 | -972998 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete but needs tank and pit latrines.
6558 | Infrastructure, Development & Maintenance | installation of culverts and road works across kabazi ward | To improve drainage and road access through culvert installation at and road works across kabazi ward | Culverts installed at and road works across kabazi ward | 3110501 | Bridges | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4828453 | 321.9 | 4828453 | 1441100 | -3328453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
6559 | Infrastructure, Development & Maintenance | Renovation of Boda Boda sheds | To rehabilitate Boda Boda sheds to restore functionality | Boda Boda sheds rehabilitated | 3110501 | Bridges | Subukia | Kabazi | -0.14564 36.042843 1893.8 3.799999952316284 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398010 | 99.5 | 398010 | 400000 | 1990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
6560 | Infrastructure, Development & Maintenance | Construction bridges & drainages and installation of Culverts | To construct bridges & drainages and installation of Culverts | Bridges & drainages and installation of Culverts constructed | 3110501 | Bridges | Kuresoi North | Kamara | -0.172682 35.679654 2519.9 36.900001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2098400 | 2098400 | Equitable | N/A | 2098400 | 0 | 499284 | 23.8 | 499284 | 499284 | 1599116 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs renovation.
6561 | Infrastructure, Development & Maintenance | Construction of footbridge at mutito B | To construct footbridge at mutito B | Footbridge at mutito B constructed | 3110501 | Bridges | Njoro | Kihingo | -0.440014 35.974624 2303.300048828125 98.4000015258789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
6562 | Infrastructure, Development & Maintenance | Construction of footbridge at subuku-munanda | To construct footbridge at subuku-munanda | Footbridge at subuku-munanda constructed | 3110501 | Bridges | Njoro | Kihingo | -0.426452 35.9737 2257.5 14.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
6563 | Infrastructure, Development & Maintenance | grading and murraming of Maranatha gwa kimwaki road | To improve road infrastructure by grading and murraming Maranatha gwa kimwaki road | Maranatha gwa kimwaki road graded and murramed | 3110501 | Bridges | Njoro | Kihingo | -0.476213 35.988603 2288 17.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | 2020/21 | 2020/21 | 2020/21 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: At that time yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
6564 | Infrastructure, Development & Maintenance | Grading, murraming and compaction of access road in kihingo and machinery | To implement grading, murraming and compaction of access road in kihingo and machinery for road connectivity and accessibility | Grading, murraming and compaction of access road in kihingo and machinery completed | 3110501 | Bridges | Njoro | Kihingo | -0.45582 35.983998 2286.60009765625 13.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2368382 | 2368382 | 2368382 | Equitable | N/A | 2368382 | 0 | 2368382 | 100 | 2368382 | 2368382 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6565 | Infrastructure, Development & Maintenance | grading, murraming and compaction of stoo mbili munanda mutiume road | To implement grading, murraming and compaction of stoo mbili munanda mutiume road for road connectivity and accessibility | grading, murraming and compaction of stoo mbili munanda mutiume road completed | 3110501 | Bridges | Njoro | Kihingo | -0.45582 35.983998 2286.60009765625 13.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6566 | grading and murraming of Gikamba road | grading and murraming of Gikamba road | To improve road infrastructure by grading and murraming Gikamba road | Gikamba road graded and murramed | 3110501 | Bridges | Kuresoi South | Kiptagich | -0.651713, 35.602562 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3972828 | 794.6 | 3972828 | 500000 | -3472828 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road.
6567 | Infrastructure, Development & Maintenance | Construction of bridge at Ngaci-Mireroni | To construct bridge at Ngaci-Mireroni | Bridge at Ngaci-Mireroni constructed | 3110501 | Bridges | BAHATI | LANET/UMOJA | -0.2962, 36.179403 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995888 | 99.6 | 995888 | 999200 | 4112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6568 | Infrastructure, Development and Maintenance | Construction of Jerusalem Bridge-Mireroni | To construct Jerusalem Bridge-Mireroni | Jerusalem Bridge-Mireroni constructed | 3110501 | Bridges | BAHATI | LANET/UMOJA | -0.303562, 36.179645 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 339500 | 34 | 339500 | 622450 | 660500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs upgrading.
6569 | Infrastructure, Development & Maintenance | Construction of bridge at Ngaci-Mireroni | To construct bridge at Ngaci-Mireroni | Bridge at Ngaci-Mireroni constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.2962, 36.179403 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999200 | 999200 | Equitable | N/A | 999200 | 0 | 995888 | 99.7 | 995888 | 999200 | 3312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6570 | Infrastructure, Development & Maintenance | Construction of bridge at Nyonjoro river | To construct bridge at Nyonjoro river | Bridge at Nyonjoro river constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.279715, 36.174596 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 776672 | 776672 | 776672 | Equitable | N/A | 776672 | 0 | 737225 | 94.9 | 737225 | 775 | 39447 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6571 | Infrastructure, Development and Maintenance | Construction of Jerusalem Bridge-Mireroni | To construct Jerusalem Bridge-Mireroni | Jerusalem Bridge-Mireroni constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.303562, 36.179645 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 961950 | 961950 | Equitable | N/A | 961950 | 0 | 339500 | 35.3 | 339500 | 622450 | 622450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs upgrading.
6572 | Infrastructure, Development & Maintenance | Construction of Vumilia Governor -AP Foot Bridge | To construct Vumilia Governor -AP Foot Bridge | Vumilia Governor -AP Foot Bridge constructed | 3110501 | Bridges | NAIVASHA | MAAI MAHIU | -0.966875, 36.546208 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1954020 | 97.7 | 1954020 | 2000000 | 45980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6573 | Infrastructure, Development & Maintenance | drainage and culverts for Maai mahiu Roads | To implement drainage and culverts for maai mahiu roads for road connectivity and accessibility | drainage and culverts for Maai mahiu Roads completed | 3110501 | Bridges | NAIVASHA | MAAI MAHIU | -0.980223, 36.587151 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4817870 | 240.9 | 4817870 | 1932328 | -2817870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs unclogging and maintenance.
6574 | installation of high mast streetlights | installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110501 | Bridges | NAIVASHA | MAAI MAHIU | -0.979929, 36.578177 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933030 | 96.7 | 1933030 | 1933030 | 66970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Destroyed by flash floods.
6575 | Infrastructure, Development & Maintenance | Completion of nyondia bridge | To complete nyondia bridge | Nyondia bridge completed | 3110501 | Bridges | GILGIL | MALEWA WEST | -0.702703, 36.489231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 149052 | 149052 | 149052 | Equitable | N/A | 149052 | 0 | 0 | 0 | 0 | 149052 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Survey done.
6576 | Infrastructure, Development & Maintenance | Construction of bridge at Kap Arusei | To construct bridge at Kap Arusei | Bridge at Kap Arusei constructed | 3110501 | Bridges | NJORO | MAUCHE | -0.48123, 35.963507 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2925371 | 97.5 | 2925371 | 74597 | 74629 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
6577 | Infrastructure, Development and Maintenance | Construction of bridge at Tayari- Molo | To construct bridge at Tayari- Molo | Bridge at Tayari- Molo constructed | 3110501 | Bridges | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6578 | Infrastructure, Development and Maintenance | Construction of Kivulini Bridge | To construct Kivulini Bridge | Kivulini Bridge constructed | 3110501 | Bridges | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6579 | Infrastructure, Development & Maintenance | Construction of Vumilia Governor -AP Foot Bridge | To construct Vumilia Governor -AP Foot Bridge | Vumilia Governor -AP Foot Bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.966875, 36.546208 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1954020 | 97.7 | 1954020 | 2000000 | 45980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6580 | Infrastructure, Development & Maintenance | drainage and culverts for Maai mahiu Roads | To implement drainage and culverts for maai mahiu roads for road connectivity and accessibility | drainage and culverts for Maai mahiu Roads completed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.980223, 36.587151 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1932328 | 1932328 | Equitable | N/A | 1932328 | 0 | 4817870 | 249.3 | 4817870 | 1932328 | -2885542 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs unclogging and maintenance.
6581 | installation of high mast streetlights | installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.979929, 36.578177 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933030 | 96.7 | 1933030 | 1933030 | 66970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Destroyed by flash floods.
6582 | Infrastructure, Development & Maintenance | Completion of nyondia bridge | To complete nyondia bridge | Nyondia bridge completed | 3110501 | Bridges | Gilgil | Malewa West | -0.702703, 36.489231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 149052 | 149052 | 149052 | Equitable | N/A | 149052 | 0 | 0 | 0 | 0 | 149052 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Survey done.
6583 | Infrastructure, Development & Maintenance | Construction of bridge at Kap Arusei | To construct bridge at Kap Arusei | Bridge at Kap Arusei constructed | 3110501 | Bridges | Njoro | Mauche | -0.48123, 35.963507 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019 | 3000000 | 2999968 | 2999968 | Equitable | N/A | 2999968 | 0 | 2925371 | 97.5 | 2925371 | 74597 | 74597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
6584 | construction of Kapsawe bridge | construction of Kapsawe bridge | To construct Kapsawe bridge | Kapsawe bridge constructed | 3110501 | Bridges | Njoro | Mauche | -0.496008, 35.952415 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 836662 | 27.9 | 836662 | 836662 | 2163338 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
6585 | Infrastructure, Development & Maintenance | Grading and murraming of Mauche centre | To improve road infrastructure by grading and murraming Mauche centre | Mauche centre graded and murramed | 3110501 | Bridges | Njoro | Mauche | -0.513187, 35.97513 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 2719822 | 2719822 | 2719822 | Equitable | N/A | 2719822 | 0 | 2719822 | 100 | 2719822 | 2719822 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
6586 | Infrastructure, Development & Maintenance | Grading and murraming of Taita Health - techasis primary road | To improve road infrastructure by grading and murraming Taita Health - techasis primary road | Taita Health - techasis primary road graded and murramed | 3110501 | Bridges | Njoro | Mauche | -0.524523, 35.952498 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2918606 | 97.3 | 2918606 | 2918606 | 81394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
6587 | Infrastructure, Development & Maintenance | installation of culvert across the ward | To improve drainage and road access through culvert installation at across the ward | Culverts installed at across the ward | 3110501 | Bridges | Njoro | Mauche | -0.516872, 35.961768 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 938904 | 93.9 | 938904 | 938904 | 61096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
6588 | Infrastructure, Development and Maintenance | Construction of bridge at Tayari- Molo | To construct bridge at Tayari- Molo | Bridge at Tayari- Molo constructed | 3110501 | Bridges | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6589 | Infrastructure, Development and Maintenance | Construction of Kivulini Bridge | To construct Kivulini Bridge | Kivulini Bridge constructed | 3110501 | Bridges | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3700000 | 3694344 | 3694344 | Equitable | N/A | 3694344 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6590 | Infrastructure, Development and Maintenance | Construction of a bridge (donkey factory) | To construct a bridge (donkey factory) | A bridge (donkey factory) constructed | 3110501 | Bridges | NAIVASHA | NAIVASHA EAST | -0.749061 36.530254 2084.900146484375 5.611999988555908 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1394868 | 93 | 1394868 | 1500000 | 105132 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
6591 | Infrastructure, Development & Maintenance | Construction of Kiambogo bridge | To construct Kiambogo bridge | Kiambogo bridge constructed | 3110501 | Bridges | NAIVASHA | NAIVASHA EAST | -0.851778, 36.515645 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019-20 | 1599910 | 1599910 | 1599910 | Equitable | N/A | 1599910 | 0 | 1589910 | 99.4 | 1589910 | 1589910 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6592 | Infrastructure, Development & Maintenance | Construction of a bridge and culverting at Kap Gorogoro | To construct a bridge and culverting at Kap Gorogoro | A bridge and culverting at Kap Gorogoro constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.361119 35.873546 2413.553466796875 4.578999996185303 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1936850 | 96.8 | 1936850 | 1999640 | 63150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Functional and operational.
6593 | Construction of a bridge at Kap Lembika | Construction of a bridge at Kap Lembika | To construct a bridge at Kap Lembika | A bridge at Kap Lembika constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.40223 35.886298 2457.300409930854 5.961999893188477 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1936850 | 161.4 | 1936850 | 1199700 | -736850 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bridge is in good condition, access road needs to be improved.
6594 | Infrastructure, Development & Maintenance | construction of Kallangat police post bridge | To construct Kallangat police post bridge | Kallangat police post bridge constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.378313, 35.9119 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2296800 | 255.2 | 2296800 | 900000 | -1396800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Non. Viable: No. Assessor remarks: The project never commenced due to insufficient funds on the scope of work needed. The money was reallocated to another project. The residents need a bride constructed for safety of the users.
6595 | Infrastructure, Development and Maintenance | construction of Kamugulet bridge | To construct Kamugulet bridge | Kamugulet bridge constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.430448, 35.905942 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2296800 | 99.9 | 2296800 | 2296800 | 3200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: The bridge serves a big population especially school going children that use it to access school..
6596 | Infrastructure, Development & Maintenance | Construction of soliat masaita bridge | To construct soliat masaita bridge | Soliat masaita bridge constructed | 3110501 | Bridges | KURESOI NORTH | NYOTA | -0.30826, 35.604622 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 317534 | 15.9 | 317534 | 1993645 | 1682466 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: Good.
6597 | Infrastructure, Development and Maintenance | Construction of a bridge (donkey factory) | To construct a bridge (donkey factory) | A bridge (donkey factory) constructed | 3110501 | Bridges | Naivasha | Naivasha East | -0.749061 36.530254 2084.900146484375 5.611999988555908 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1394868 | 93 | 1394868 | 1500000 | 105132 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
6598 | Infrastructure, Development & Maintenance | Construction of Kiambogo bridge | To construct Kiambogo bridge | Kiambogo bridge constructed | 3110501 | Bridges | Naivasha | Naivasha East | -0.851778, 36.515645 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019-20 | 1599910 | 1589910 | 1589910 | Equitable | N/A | 1589910 | 0 | 1589910 | 100 | 1589910 | 1589910 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6599 | Infrastructure, Development & Maintenance | Construction of a bridge and culverting at Kap Gorogoro | To construct a bridge and culverting at Kap Gorogoro | A bridge and culverting at Kap Gorogoro constructed | 3110501 | Bridges | Njoro | Nessuit | -0.361119 35.873546 2413.553466796875 4.578999996185303 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999640 | 1999640 | Equitable | N/A | 1999640 | 0 | 1936850 | 96.9 | 1936850 | 1999640 | 62790 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Functional and operational.
6600 | Construction of a bridge at Kap Lembika | Construction of a bridge at Kap Lembika | To construct a bridge at Kap Lembika | A bridge at Kap Lembika constructed | 3110501 | Bridges | Njoro | Nessuit | -0.40223 35.886298 2457.300409930854 5.961999893188477 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199700 | 1199700 | Equitable | N/A | 1199700 | 0 | 1936850 | 161.4 | 1936850 | 1199700 | -737150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bridge is in good condition, access road needs to be improved.
6601 | Infrastructure, Development & Maintenance | construction of Kallangat police post bridge | To construct Kallangat police post bridge | Kallangat police post bridge constructed | 3110501 | Bridges | Njoro | Nessuit | -0.378313, 35.9119 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2296800 | 255.2 | 2296800 | 900000 | -1396800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Non. Viable: No. Assessor remarks: The project never commenced due to insufficient funds on the scope of work needed. The money was reallocated to another project. The residents need a bride constructed for safety of the users.
6602 | Infrastructure, Development and Maintenance | construction of Kamugulet bridge | To construct Kamugulet bridge | Kamugulet bridge constructed | 3110501 | Bridges | Njoro | Nessuit | -0.430448, 35.905942 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2296800 | 2296800 | Equitable | N/A | 2296800 | 0 | 2296800 | 100 | 2296800 | 2296800 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: The bridge serves a big population especially school going children that use it to access school..
6603 | Infrastructure, Development & Maintenance | Construction of soliat masaita bridge | To construct soliat masaita bridge | Soliat masaita bridge constructed | 3110501 | Bridges | Kuresoi North | Nyota | -0.30826, 35.604622 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 2000000 | 1993645 | 1993645 | Equitable | N/A | 1993645 | 0 | 317534 | 15.9 | 317534 | 1993645 | 1676111 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: Good.
6604 | Construction of a footbridge at Kapsepeiywo | Construction of a footbridge at Kapsepeiywo | To construct a footbridge at Kapsepeiywo | A footbridge at Kapsepeiywo constructed | 3110501 | Bridges | RONGAI | SOIN | -0.068868, 36.044463 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499900 | 100 | 1499900 | 1500000 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repair.
6605 | Construction of a footbridge at Kapsepeiywo | Construction of a footbridge at Kapsepeiywo | To construct a footbridge at Kapsepeiywo | A footbridge at Kapsepeiywo constructed | 3110501 | Bridges | Rongai | Soin | -0.068868, 36.044463 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499900 | 100 | 1499900 | 1500000 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repair.
6606 | Infrastructure, Development & Maintenance | Construction of Kereswa-Kapket Bridge and road | To construct Kereswa-Kapket Bridge and road | Kereswa-Kapket Bridge and road constructed | 3110501 | Bridges | KURESOI SOUTH | TINET | -0.529565, 35.610744 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3817640 | 95.4 | 3817640 | 3817640 | 182360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain.
6607 | Infrastructure, Development and Maintenance | Construction of Kimaech Bridge | To construct Kimaech Bridge | Kimaech Bridge constructed | 3110501 | Bridges | KURESOI SOUTH | TINET | -0.445126 35.609035 0 2200 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2634354 | 87.8 | 2634354 | 318368 | 365646 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
6608 | Infrastructure, Development and Maintenance | Construction of Tinet Dispensary Bridge | To construct Tinet Dispensary Bridge | Tinet Dispensary Bridge constructed | 3110501 | Bridges | KURESOI SOUTH | TINET | -0.47504 35.631932 0 2400 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998415 | 99.9 | 2998415 | 3000000 | 1585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
6609 | Infrastructure, Development & Maintenance | Construction of bridge and culverts across Turi ward | To construct bridge and culverts across Turi ward | Bridge and culverts across Turi ward constructed | 3110501 | Bridges | MOLO | TURI | -0.288588, 35.693317 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1805852 | 90.3 | 1805852 | 2000000 | 194148 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The bridge was well constructed but there is no road ahead since it requires heavy dozing for the road to be operational. No backfilling was done to the bridge.
6610 | Infrastructure, Development & Maintenance | Construction of bridges at Nyeki and Kanyiriri (Ndenderu A) | To construct bridges at Nyeki and Kanyiriri (Ndenderu A) | Bridges at Nyeki and Kanyiriri (Ndenderu A) constructed | 3110501 | Bridges | MOLO | TURI | -0.289708, 35.738825 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1174638 | 97.9 | 1174638 | 186 | 25362 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is a movement of people from both sides of the valley.
6611 | Infrastructure, Development & Maintenance | Construction of Kereswa-Kapket Bridge and road | To construct Kereswa-Kapket Bridge and road | Kereswa-Kapket Bridge and road constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.529565, 35.610744 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3817640 | 95.4 | 3817640 | 3817640 | 182360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain.
6612 | Infrastructure, Development and Maintenance | Construction of Kimaech Bridge | To construct Kimaech Bridge | Kimaech Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2634354 | 87.8 | 2634354 | 318368 | 365646 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
6613 | Infrastructure, Development and Maintenance | Construction of Tinet Dispensary Bridge | To construct Tinet Dispensary Bridge | Tinet Dispensary Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998415 | 99.9 | 2998415 | 3000000 | 1585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
6614 | Infrastructure, Development & Maintenance | Construction of bridge and culverts across Turi ward | To construct bridge and culverts across Turi ward | Bridge and culverts across Turi ward constructed | 3110501 | Bridges | Molo | Turi | -0.288588, 35.693317 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1805852 | 90.3 | 1805852 | 2000000 | 194148 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The bridge was well constructed but there is no road ahead since it requires heavy dozing for the road to be operational. No backfilling was done to the bridge.
6615 | grading and murraming of Muchorwe dispensary - kayole road | grading and murraming of Muchorwe dispensary - kayole road | To improve road infrastructure by grading and murraming Muchorwe dispensary - kayole road | Muchorwe dispensary - kayole road graded and murramed | 3110501 | Bridges | Molo | Turi | -0.316518, 35.710677 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1155527 | 48.1 | 1155527 | 1080503 | 1244473 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In need of rehabilitation.
6616 | Infrastructure, Development & Maintenance | Construction of Kayole-Boito Bridge | To construct Kayole-Boito Bridge | Kayole-Boito Bridge constructed | 3110501 | Bridges | RONGAI | VISOI | -0.160137, 35.871107 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1400000 | 100 | 1400000 | 1400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6617 | Infrastructure, Development and Maintenance | Construction of magare bridge | To construct magare bridge | Magare bridge constructed | 3110501 | Bridges | RONGAI | VISOI | -0.102878 35.914592 1711.9 6.099999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1360750 | 97.2 | 1360750 | 1400000 | 39250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6618 | Infrastructure, Development and Maintenance | Repair of bridges at kware, thirandu and kanga | To rehabilitate bridges at kware, thirandu and kanga to restore functionality | Bridges at kware, thirandu and kanga rehabilitated | 3110501 | Bridges | RONGAI | VISOI | -0.139406 35.905676 1808.19482421875 5.670000076293945 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1237905 | 88.4 | 1237905 | 1400000 | 162095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6619 | Infrastructure, Development & Maintenance | Construction of Kayole-Boito Bridge | To construct Kayole-Boito Bridge | Kayole-Boito Bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.160137, 35.871107 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1400000 | 100 | 1400000 | 1400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6620 | Infrastructure, Development and Maintenance | Construction of magare bridge | To construct magare bridge | Magare bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1360750 | 97.2 | 1360750 | 1400000 | 39250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6621 | Infrastructure, Development and Maintenance | Repair of bridges at kware, thirandu and kanga | To rehabilitate bridges at kware, thirandu and kanga to restore functionality | Bridges at kware, thirandu and kanga rehabilitated | 3110501 | Bridges | Rongai | Visoi | -0.139406 35.905676 1808.19482421875 5.670000076293945 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1237905 | 88.4 | 1237905 | 1400000 | 162095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6622 | Construction of Wei cross bridge | Construction of Wei cross bridge | To construct Wei cross bridge | Wei cross bridge constructed | 3110501 | Bridges | SUBUKIA | WASEGES | 0.005697 36.25448 2085.5 13.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2019/20 | 3500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 941839 | 94.2 | 941839 | 1096 | 58161 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The is in use.
6623 | Construction of Wei cross bridge | Construction of Wei cross bridge | To construct Wei cross bridge | Wei cross bridge constructed | 3110501 | Bridges | Subukia | Waseges | 0.005697 36.25448 2085.5 13.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2019/20 | 3500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 941839 | 94.2 | 941839 | 1096 | 58161 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The is in use.
6624 | Infrastructure, Development and Maintenance | installation of highmast streetlights (mulika mwizi) in Bahati ward | To improve security lighting through high mast floodlight installation at streetlights (mulika mwizi) in Bahati ward | High mast floodlight installed at streetlights (mulika mwizi) in Bahati ward | 3110504 | Other Infrastructure and Civil Works | BAHATI | BAHATI | -0.194242, 36.133374 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
6625 | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | To construct Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | 0.353373, 36.049497 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193025 | 99.4 | 1193025 | 1200000 | 6975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Gibous Ventures. Assessor remarks: Complete and in use..
6626 | Infrastructure, Development and Maintenance | Installation of high mast streetlights at Kelekwet Barut | To improve security lighting through high mast floodlight installation at streetlights at Kelekwet Barut | High mast floodlight installed at streetlights at Kelekwet Barut | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | -1.2841, 36.8155 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999000 | 100 | 2999000 | 2958300 | 1000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: site handed over.
6627 | Infrastructure, Development & Maintenance | Construction of club lane drainage | To construct club lane drainage | Club lane drainage constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 782046 | 195.5 | 782046 | 17955 | -382046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6628 | Infrastructure, Development & Maintenance | rehabilitation of drainage in Lumumba estate | To rehabilitate drainage in Lumumba estate to restore functionality | Drainage in Lumumba estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6629 | Infrastructure, Development and Maintenance | installation of highmast streetlights (mulika mwizi) in Bahati ward | To improve security lighting through high mast floodlight installation at streetlights (mulika mwizi) in Bahati ward | High mast floodlight installed at streetlights (mulika mwizi) in Bahati ward | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.194242, 36.133374 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
6630 | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | To construct Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.353373, 36.049497 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193025 | 99.4 | 1193025 | 1200000 | 6975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Gibous Ventures. Assessor remarks: Complete and in use..
6631 | Infrastructure, Development and Maintenance | Installation of high mast streetlights at Kelekwet Barut | To improve security lighting through high mast floodlight installation at streetlights at Kelekwet Barut | High mast floodlight installed at streetlights at Kelekwet Barut | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -1.2841, 36.8155 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999000 | 100 | 2999000 | 2958300 | 1000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: site handed over.
6632 | Infrastructure, Development & Maintenance | Construction of club lane drainage | To construct club lane drainage | Club lane drainage constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 782046 | 195.5 | 782046 | 17955 | -382046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6633 | Infrastructure, Development & Maintenance | rehabilitation of drainage in Lumumba estate | To rehabilitate drainage in Lumumba estate to restore functionality | Drainage in Lumumba estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6634 | Infrastructure, Development & Maintenance | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.254746, 36.233905 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 871400 | 87.1 | 871400 | 1000000 | 128600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Holy sons. Assessor remarks: Good require maintenance.
6635 | Infrastructure, Development & Maintenance | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.254746, 36.233905 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 871400 | 87.1 | 871400 | 1000000 | 128600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Holy sons. Assessor remarks: Good require maintenance.
6636 | Infrastructure, Development & Maintenance | Installation of 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | To install 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate installed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.302653, 36.072775 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 2000000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1420750 | 78.9 | 1420750 | 1497250 | 379250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
6637 | Infrastructure, Development & Maintenance | Installation of 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | To install 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.302653, 36.072775 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 2000000 | 1497250 | 1497250 | Equitable | N/A | 1497250 | 0 | 1420750 | 94.9 | 1420750 | 1497250 | 76500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
6638 | Repairs, maintenance of existing roads, installation of culverts in gilgil town | Repairs, maintenance of existing roads, installation of culverts in gilgil town | To implement repairs, maintenance of existing roads, installation of culverts in gilgil town for road connectivity and accessibility | Repairs, maintenance of existing roads, installation of culverts in gilgil town completed | 3110504 | Other Infrastructure and Civil Works | GILGIL | GILGIL | -0.503546 36.321522 1991.5999755859375 10.17300033569336 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1686831 | 1686831 | 1686831 | Equitable | N/A | 1686831 | 0 | 1194674 | 70.8 | 1194674 | 1195700 | 492157 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No project. Viable: No project. Assessor remarks: No project on site.
6639 | Repairs, maintenance of existing roads, installation of culverts in gilgil town | Repairs, maintenance of existing roads, installation of culverts in gilgil town | To implement repairs, maintenance of existing roads, installation of culverts in gilgil town for road connectivity and accessibility | Repairs, maintenance of existing roads, installation of culverts in gilgil town completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.503546 36.321522 1991.5999755859375 10.17300033569336 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1686831 | 1686831 | 1686831 | Equitable | N/A | 1686831 | 0 | 1194674 | 70.8 | 1194674 | 1195700 | 492157 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No project. Viable: No project. Assessor remarks: No project on site.
6640 | Infrastructure, Development and Maintenance | Construction of Bus Park/Matatu terminus | To construct Bus Park/Matatu terminus | Bus Park/Matatu terminus constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 48000000 | 40000000 | 40000000 | Equitable | N/A | 40000000 | 0 | 30510811 | 76.3 | 30510811 | 1082853 | 9489189 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6641 | Infrastructure, Development and Maintenance | Construction of Storm water Drains | To construct Storm water Drains | Storm water Drains constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 10000000 | 7500000 | Equitable | N/A | 7500000 | 0 | 6978545 | 69.8 | 6978545 | 3021455 | 3021455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6642 | Infrastructure, Development and Maintenance | Counterpart funding acquisition of Fire Engines from UK Government | To implement counterpart funding acquisition of fire engines from uk government for road connectivity and accessibility | Counterpart funding acquisition of Fire Engines from UK Government completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 11602898 | 11602898 | 11602898 | Equitable | N/A | 11602898 | 0 | 0 | 0 | 0 | 11602898 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6643 | Infrastructure, Development and Maintenance | Installation of streetlights in Royal Estate area in Eburru Mbaruk Ward | To improve lighting and safety through installation of solar streetlights at Royal Estate area in Eburru Mbaruk Ward | Solar streetlights installed at Royal Estate area in Eburru Mbaruk Ward | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 34189000 | 1709.5 | 34189000 | 5811000 | -32189000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6644 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights across the county | To rehabilitate streetlights across the county to restore functionality | Streetlights across the county rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 6083300 | 0 | 6083300 | Equitable | N/A | 6083300 | 0 | 5568840 | 0 | 5568840 | 6083300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6645 | Infrastructure, Development & Maintenance | Construction of boda boda shades at solai and Kirima Ndugiri | To construct boda boda shades at solai and Kirima Ndugiri | Boda boda shades at solai and Kirima Ndugiri constructed | 3110504 | Other Infrastructure and Civil Works | SUBUKIA | KABAZI | -0.11158, 36.05567 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 989167 | 98.9 | 989167 | 989167 | 10833 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs drainage works.
6646 | Construction of boda boda shades | Construction of boda boda shades | To construct boda boda shades | Boda boda shades constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.169028, 35.703205 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | U2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998600 | 99.9 | 998600 | 981402 | 1400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Seats vandalised, needs re-painting.
6647 | Draining Cheptebe stagnant Water | Draining Cheptebe stagnant Water | To implement draining cheptebe stagnant water for road connectivity and accessibility | Draining Cheptebe stagnant Water completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.166107 35.72444 2546.5 6.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs to be fully operational.
6648 | Infrastructure, Development & Maintenance | Installation of 4 sets of high mast security lights | To install 4 sets of high mast security lights | 4 sets of high mast security lights installed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.176363, 35.7124 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995000 | 99.8 | 1995000 | 1995000 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance. Some of them are not functional.
6649 | Infrastructure, Development & Maintenance | Rehabiltation of drainage system | To implement rehabiltation of drainage system for road connectivity and accessibility | Rehabiltation of drainage system completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.288288, 36.036492 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493907 | 99.6 | 1493907 | 0 | 6093 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved on water drainage. Assessor remarks: Done and serving well. Draining water efficiently.
6650 | Infrastructure, Development & Maintenance | Construction of drainage system | To construct drainage system | Drainage system constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.299728 36.045548 1803.800048828125 21.075000762939453 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2497522 | 83.3 | 2497522 | 3000000 | 502478 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S MIDRIFT GENERAL MERCHANTS. Assessor remarks: Overgrown vegetation has debris and thrush,needs unclogging.
6651 | Infrastructure, Development and Maintenance | Rehabilitation of drainage system in Kaptembwo | To rehabilitate drainage system in Kaptembwo to restore functionality | Drainage system in Kaptembwo rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.298518 36.046052 1808.800048828125 64.54000091552734 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 922599 | 92.3 | 922599 | 32451 | 77401 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PICVERD SUPPLIES. Assessor remarks: Defective,has debris and thrush,clogged,.
6652 | maintenance of drainages and foot bridges | maintenance of drainages and foot bridges | To implement maintenance of drainages and foot bridges for road connectivity and accessibility | maintenance of drainages and foot bridges completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.302037 36.061704 1798.800048828125 52.400001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3399000 | 100 | 3399000 | 3400000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S LEGIO GENERAL. Assessor remarks: Clogged, needs rehabilitation.
6653 | Infrastructure, Development & Maintenance | streetlighting maintenance | To implement streetlighting maintenance for road connectivity and accessibility | streetlighting maintenance completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.302265, 36.058547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It's a viable project, it's has met the needs of the residents. Contractor: Y72. Assessor remarks: It functional.
6654 | Infrastructure, Development & Maintenance | Construction of Storm water drains in Rurii, workers and Menengai | To construct Storm water drains in Rurii, workers and Menengai | Storm water drains in Rurii, workers and Menengai constructed | 3110504 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.268282 36.11517 1863.800048828125 4.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3302288 | 82.6 | 3302288 | 3302288 | 697712 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
6655 | Installation of a foot bridge and culvert along river Munyaka | Installation of a foot bridge and culvert along river Munyaka | To install a foot bridge and culvert along river Munyaka | A foot bridge and culvert along river Munyaka installed | 3110504 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.240843, 36.133888 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1319488 | 1319488 | 1319488 | Equitable | N/A | 1319488 | 0 | 1299393 | 98.5 | 1299393 | 20095 | 20095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Culverts are well maintained.
6656 | Infrastructure, Development & Maintenance | Installation of streetlights In the ward | To improve lighting and safety through installation of solar streetlights at the ward | Solar streetlights installed at the ward | 3110504 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.231536 36.116876 1940.9000244140625 19.493999481201172 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 5899024 | 5899024 | Equitable | N/A | 5899024 | 0 | 3613850 | 61.3 | 3613850 | 5899024 | 2285174 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The contractor is yet to begin the works.
6657 | Infrastructure, Development and Maintenance | Construction of bodaboda Shades in ndeffo and kihingo | To construct bodaboda Shades in ndeffo and kihingo | Bodaboda Shades in ndeffo and kihingo constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.433992, 35.972122 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 990780 | 198.2 | 990780 | 500000 | -490780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's in good state.
6658 | Infrastructure, Development & Maintenance | Construction of drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages | To construct drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages | Drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.407653, 35.965057 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 5400000 | 5400000 | 5400000 | Equitable | N/A | 5400000 | 0 | 5108568 | 94.6 | 5108568 | 89624 | 291432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6659 | Infrastructure, Development & Maintenance | Grading and murraming of Kihingo Centre, and Ndeffo centre roads | To improve road infrastructure by grading and murraming Kihingo Centre, and Ndeffo centre roads | Kihingo Centre, and Ndeffo centre roads graded and murramed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.433545, 35.973563 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4284631 | 85.7 | 4284631 | 58361 | 715369 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance required.
6660 | Infrastructure, Development & Maintenance | Rehabilitation of drainages at Kivumbini | To rehabilitate drainages at Kivumbini to restore functionality | Drainages at Kivumbini rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.303707, 36.082663 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 576500 | 57.6 | 576500 | 1000000 | 423500 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improve drainage.
6661 | Infrastructure, Development and Maintenance | Installation of security lights | To install security lights | Security lights installed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.296244, 36.084835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497250 | 99.8 | 1497250 | 1500000 | 2750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6662 | Infrastructure, Development & Maintenance | maintenance of Streetlights in kivumbini ward | To implement maintenance of streetlights in kivumbini ward for road connectivity and accessibility | maintenance of Streetlights in kivumbini ward completed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.298543, 36.086344 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
6663 | Infrastructure, Development & Maintenance | Construction of boda boda shades at solai and Kirima Ndugiri | To construct boda boda shades at solai and Kirima Ndugiri | Boda boda shades at solai and Kirima Ndugiri constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.11158, 36.05567 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 989166.8 | 989166.8 | Equitable | N/A | 989166.8 | 0 | 989167 | 100 | 989167 | 989167 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs drainage works.
6664 | Construction of boda boda shades | Construction of boda boda shades | To construct boda boda shades | Boda boda shades constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.169028, 35.703205 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | U2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998600 | 99.9 | 998600 | 981402 | 1400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Seats vandalised, needs re-painting.
6665 | Draining Cheptebe stagnant Water | Draining Cheptebe stagnant Water | To implement draining cheptebe stagnant water for road connectivity and accessibility | Draining Cheptebe stagnant Water completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.166107 35.72444 2546.5 6.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs to be fully operational.
6666 | Infrastructure, Development & Maintenance | Installation of 4 sets of high mast security lights | To install 4 sets of high mast security lights | 4 sets of high mast security lights installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.176363, 35.7124 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1995000 | 1995000 | Equitable | N/A | 1995000 | 0 | 1995000 | 100 | 1995000 | 1995000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance. Some of them are not functional.
6667 | Infrastructure, Development & Maintenance | Construction of drainage system | To construct drainage system | Drainage system constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.299728 36.045548 1803.800048828125 21.075000762939453 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2497522 | 83.3 | 2497522 | 3000000 | 502478 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S MIDRIFT GENERAL MERCHANTS. Assessor remarks: Overgrown vegetation has debris and thrush,needs unclogging.
6668 | Infrastructure, Development and Maintenance | Rehabilitation of drainage system in Kaptembwo | To rehabilitate drainage system in Kaptembwo to restore functionality | Drainage system in Kaptembwo rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.298518 36.046052 1808.800048828125 64.54000091552734 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 922599 | 92.3 | 922599 | 32451 | 77401 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PICVERD SUPPLIES. Assessor remarks: Defective,has debris and thrush,clogged,.
6669 | maintenance of drainages and foot bridges | maintenance of drainages and foot bridges | To implement maintenance of drainages and foot bridges for road connectivity and accessibility | maintenance of drainages and foot bridges completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302037 36.061704 1798.800048828125 52.400001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3399000 | 100 | 3399000 | 3400000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S LEGIO GENERAL. Assessor remarks: Clogged, needs rehabilitation.
6670 | Infrastructure, Development & Maintenance | streetlighting maintenance | To implement streetlighting maintenance for road connectivity and accessibility | streetlighting maintenance completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302265, 36.058547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It's a viable project, it's has met the needs of the residents. Contractor: Y72. Assessor remarks: It functional.
6671 | Infrastructure, Development & Maintenance | Drainage works in Heshima market | To implement drainage works in heshima market for road connectivity and accessibility | Drainage works in Heshima market completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.243603 36.111465 1944.4000244140625 72.9000015258789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | 2020/21 | 2020/21 | 2020/21 | 2021/22 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1952135 | 177.5 | 1952135 | 1100000 | -852135 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
6672 | Installation of a foot bridge and culvert along river Munyaka | Installation of a foot bridge and culvert along river Munyaka | To install a foot bridge and culvert along river Munyaka | A foot bridge and culvert along river Munyaka installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.240843, 36.133888 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1319488 | 1319488 | 1319488 | Equitable | N/A | 1319488 | 0 | 1299393 | 98.5 | 1299393 | 20095 | 20095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Culverts are well maintained.
6673 | labour based drainage works of heshima eatate access road | labour based drainage works of heshima eatate access road | To implement labour based drainage works of heshima eatate access road for road connectivity and accessibility | labour based drainage works of heshima eatate access road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.242746, 36.113191 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1952135 | 97.6 | 1952135 | 2000000 | 47865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project requires routine maintenance.
6674 | Infrastructure, Development and Maintenance | labour based drainage works of menengai crater dispensary access road | To implement labour based drainage works of menengai crater dispensary access road for road connectivity and accessibility | labour based drainage works of menengai crater dispensary access road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.246042 36.117933 1898.300048828125 7 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1899024 | 1899024 | 1899024 | Equitable | N/A | 1899024 | 0 | 345135 | 18.2 | 345135 | 345135 | 1553889 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
6675 | labour based drainage works of poshomill - bee valley access road | labour based drainage works of poshomill - bee valley access road | To implement labour based drainage works of poshomill - bee valley access road for road connectivity and accessibility | labour based drainage works of poshomill - bee valley access road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.242746, 36.113191 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1919341 | 96 | 1919341 | 2000000 | 80659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project requires routine maintenance.
6676 | labour based drainage works of poshomill -kiangai road | labour based drainage works of poshomill -kiangai road | To implement labour based drainage works of poshomill -kiangai road for road connectivity and accessibility | labour based drainage works of poshomill -kiangai road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.257445, 36.107897 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1670315 | 98.3 | 1670315 | 2000000 | 29685 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage requires maintenance.
6677 | labour based drainage works of sauti ya mwananch- kiangai road | labour based drainage works of sauti ya mwananch- kiangai road | To implement labour based drainage works of sauti ya mwananch- kiangai road for road connectivity and accessibility | labour based drainage works of sauti ya mwananch- kiangai road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.257823, 36.108582 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1674955 | 98.5 | 1674955 | 2000000 | 25045 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
6678 | Infrastructure, Development and Maintenance | Installation of security lights | To install security lights | Security lights installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296244, 36.084835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497250 | 99.8 | 1497250 | 1500000 | 2750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6679 | Infrastructure, Development & Maintenance | maintenance of Streetlights in kivumbini ward | To implement maintenance of streetlights in kivumbini ward for road connectivity and accessibility | maintenance of Streetlights in kivumbini ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298543, 36.086344 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
6680 | Infrastructure, Development & Maintenance | Installation of High mast streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | To improve security lighting through high mast floodlight installation at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | High mast floodlight installed at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | 3110504 | Other Infrastructure and Civil Works | BAHATI | LANET/UMOJA | -0.275097, 36.174683 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 762100 | 23.8 | 762100 | 3198500 | 2437900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6681 | Construction of Motorcycle sheds at Bagaria centre and Naishi centre. | Construction of Motorcycle sheds at Bagaria centre and Naishi centre. | To construct Motorcycle sheds at Bagaria centre and Naishi centre | Motorcycle sheds at Bagaria centre and Naishi centre constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | LARE | -0.44275, 36.012303 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699670 | 100 | 699670 | 700000 | 330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6682 | Infrastructure, Development & Maintenance | Installation of streetlights in Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | To improve lighting and safety through installation of solar streetlights at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | Solar streetlights installed at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | 3110504 | Other Infrastructure and Civil Works | NJORO | LARE | -0.409943, 36.002193 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799920 | 100 | 1799920 | 1799920 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installed sub standard lights and need maintenance.
6683 | Construction of drainage system in Hilton | Construction of drainage system in Hilton | To construct drainage system in Hilton | Drainage system in Hilton constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.276938, 36.052831 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 3455390 | 138.2 | 3455390 | 2500000 | -955390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage was demolished due to Kissip 1 which did a tarmack road drainage.
6684 | Construction of drainage system in London | Construction of drainage system in London | To construct drainage system in London | Drainage system in London constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.276938, 36.052831 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3455390 | 98.7 | 3455390 | 4716 | 44610 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage was demolished due to Kissip 1 which did a tarmack road drainage.
6685 | Infrastructure, Development & Maintenance | Construction of motorcycle sheds in Chomabase | To construct motorcycle sheds in Chomabase | Motorcycle sheds in Chomabase constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.27722 36.052943 1866.199951171875 29.358999252319336 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496325 | 99.8 | 1496325 | 1499950 | 3675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
6686 | Infrastructure, Development & Maintenance | Construction of drainage and culverts in London Ward | To construct drainage and culverts in London Ward | Drainage and culverts in London Ward constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498125 | 99.9 | 2498125 | 4716 | 1875 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
6687 | Infrastructure, Development and Maintenance | Installation of high mast flood lights in London Ward | To improve security lighting through high mast floodlight installation at flood lights in London Ward | High mast floodlight installed at flood lights in London Ward | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274075, 36.058162 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2880600 | 82.3 | 2880600 | 3500000 | 619400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
6688 | Infrastructure, Development & Maintenance | Installation of High mast streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | To improve security lighting through high mast floodlight installation at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | High mast floodlight installed at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.275097, 36.174683 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 762100 | 23.8 | 762100 | 3198500 | 2437900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6689 | Infrastructure, Development and Maintenance | labour based Road maintenance and rehabilitation ( purchase of murram and casuals) | To implement labour based road maintenance and rehabilitation ( purchase of murram and casuals) for road connectivity and accessibility | labour based Road maintenance and rehabilitation ( purchase of murram and casuals) completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.278138, 36.176558 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6690 | Infrastructure, Development and Maintenance | Supply of murram | To implement supply of murram for road connectivity and accessibility | Supply of murram completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.283788, 36.174979 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999565 | 100 | 999565 | 1000000 | 435 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6691 | Construction of Motorcycle sheds at Bagaria centre and Naishi centre. | Construction of Motorcycle sheds at Bagaria centre and Naishi centre. | To construct Motorcycle sheds at Bagaria centre and Naishi centre | Motorcycle sheds at Bagaria centre and Naishi centre constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.44275, 36.012303 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699670 | 100 | 699670 | 700000 | 330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
6692 | Infrastructure, Development & Maintenance | Installation of streetlights in Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | To improve lighting and safety through installation of solar streetlights at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | Solar streetlights installed at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.409943, 36.002193 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1800000 | 1799920 | 1799920 | Equitable | N/A | 1799920 | 0 | 1799920 | 100 | 1799920 | 1799920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installed sub standard lights and need maintenance.
6693 | Construction of drainage system in London | Construction of drainage system in London | To construct drainage system in London | Drainage system in London constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.276938, 36.052831 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3460106.2 | 3460106.2 | Equitable | N/A | 3460106.2 | 0 | 3455390 | 99.9 | 3455390 | 4716 | 4716.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage was demolished due to Kissip 1 which did a tarmack road drainage.
6694 | Infrastructure, Development & Maintenance | Construction of motorcycle sheds in Chomabase | To construct motorcycle sheds in Chomabase | Motorcycle sheds in Chomabase constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.27722 36.052943 1866.199951171875 29.358999252319336 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496325 | 99.8 | 1496325 | 1499950 | 3675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
6695 | Infrastructure, Development and Maintenance | Installation of high mast flood lights in London Ward | To improve security lighting through high mast floodlight installation at flood lights in London Ward | High mast floodlight installed at flood lights in London Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274075, 36.058162 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2880600 | 82.3 | 2880600 | 3500000 | 619400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
6696 | Infrastructure, Development & Maintenance | Construction of motorbike shades in green valley | To construct motorbike shades in green valley | Motorbike shades in green valley constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.720721, 36.471354 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
6697 | Infrastructure, Development and Maintenance | Construction of motorbike shades in kasarani | To construct motorbike shades in kasarani | Motorbike shades in kasarani constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.684685, 36.471073 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done well.
6698 | Infrastructure, Development & Maintenance | Installation of High mast Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | To improve security lighting through high mast floodlight installation at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | High mast floodlight installed at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703, 36.489231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999100 | 99.9 | 999100 | 999100 | 900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2019/20. Assessor remarks: Good work.
6699 | Installation of drainage and culverts along Mau-Narok Centre | Installation of drainage and culverts along Mau-Narok Centre | To install drainage and culverts along Mau-Narok Centre | Drainage and culverts along Mau-Narok Centre installed | 3110504 | Other Infrastructure and Civil Works | NJORO | MAU NAROK | -0.600012 36.007202 0 212 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 987670 | 82.3 | 987670 | 1200000 | 212330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: ok.
6700 | Infrastructure, Development & Maintenance | Installation of high mast lights at Mau Narok, metta AP Camp and utalii dam | To improve security lighting through high mast floodlight installation at lights at Mau Narok, metta AP Camp and utalii dam | High mast floodlight installed at lights at Mau Narok, metta AP Camp and utalii dam | 3110504 | Other Infrastructure and Civil Works | NJORO | MAU NAROK | -0.58119, 36.034068 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 512900 | 85.5 | 512900 | 87100 | 87100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
6701 | Infrastructure, Development and Maintenance | Construction of Bodaboda Sheds at Teacher and kiratina | To construct Bodaboda Sheds at Teacher and kiratina | Bodaboda Sheds at Teacher and kiratina constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.289183, 36.115024 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022/23 | 945221 | 945221 | 945221 | Equitable | N/A | 945221 | 0 | 642390 | 68 | 642390 | 1000000 | 302831 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6702 | Construction of drainage system at Kiratina in Menengai East | Construction of drainage system at Kiratina in Menengai East | To construct drainage system at Kiratina in Menengai East | Drainage system at Kiratina in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.28519 36.122662 1848.699951171875 42.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000003 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997950 | 99.9 | 2997950 | 2997950 | 2050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6703 | Construction of drainage system at Lower teachers in Menengai East | Construction of drainage system at Lower teachers in Menengai East | To construct drainage system at Lower teachers in Menengai East | Drainage system at Lower teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.27977 36.122899 1868.849365234375 56.99399948120117 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000002 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995741 | 99.9 | 2995741 | 2980455 | 4259 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6704 | Construction of drainage system at upper teachers in Menengai East | Construction of drainage system at upper teachers in Menengai East | To construct drainage system at upper teachers in Menengai East | Drainage system at upper teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.275859 36.11542 1856.699951171875 4.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2980455 | 99.3 | 2980455 | 2997556 | 19545 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs cleaning and clearing.
6705 | Construction of boda boda sheds | Construction of boda boda sheds | To construct boda boda sheds | Boda boda sheds constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MENENGAI WEST | -0.224428, 36.000562 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3482055 | 232.1 | 3482055 | 1500000 | -1982055 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6706 | Infrastructure, Development and Maintenance | Construction of drainage and culverts at Kenyatta Estate | To construct drainage and culverts at Kenyatta Estate | Drainage and culverts at Kenyatta Estate constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6707 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of floodlight at Tayari | To install floodlight at Tayari | Floodlight at Tayari installed | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6708 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights at Chazon and Gateiguru | To improve lighting and safety through installation of solar streetlights at Chazon and Gateiguru | Solar streetlights installed at Chazon and Gateiguru | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6709 | Completion of ongoing Salgaa drainage works | Completion of ongoing Salgaa drainage works | To complete ongoing Salgaa drainage works | Ongoing Salgaa drainage works completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.205574, 35.8469 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999630 | 100 | 999630 | 999630 | 370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
6710 | Infrastructure, Development & Maintenance | grading and murraming of Roret AIC road | To improve road infrastructure by grading and murraming Roret AIC road | Roret AIC road graded and murramed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.26713 36.001962 2029.9000244140625 8.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
6711 | Infrastructure, Development & Maintenance | Construction of Salgaa drainage system | To construct Salgaa drainage system | Salgaa drainage system constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.207391, 35.847733 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3727314 | 93.2 | 3727314 | 1239800 | 272686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: No indicated. Assessor remarks: Good.
6712 | Infrastructure, Development & Maintenance | Drainage Works at Ngumo Road | To implement drainage works at ngumo road for road connectivity and accessibility | Drainage Works at Ngumo Road completed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MURINDAT | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6713 | Culverts installation across maai mahiu ward | Culverts installation across maai mahiu ward | To implement culverts installation across maai mahiu ward for road connectivity and accessibility | Culverts installation across maai mahiu ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.957908, 36.557244 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930176 | 96.5 | 1930176 | 2000000 | 69824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6714 | Infrastructure, Development & Maintenance | Construction of motorbike shades in green valley | To construct motorbike shades in green valley | Motorbike shades in green valley constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.720721, 36.471354 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
6715 | Infrastructure, Development and Maintenance | Construction of motorbike shades in kasarani | To construct motorbike shades in kasarani | Motorbike shades in kasarani constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.684685, 36.471073 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done well.
6716 | Infrastructure, Development & Maintenance | Installation of High mast Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | To improve security lighting through high mast floodlight installation at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | High mast floodlight installed at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.489231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999100 | 99.9 | 999100 | 999100 | 900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2019/20. Assessor remarks: Good work.
6717 | Installation of drainage and culverts along Mau-Narok Centre | Installation of drainage and culverts along Mau-Narok Centre | To install drainage and culverts along Mau-Narok Centre | Drainage and culverts along Mau-Narok Centre installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.600012 36.007202 0 212 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 987670 | 82.3 | 987670 | 1200000 | 212330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: ok.
6718 | Infrastructure, Development & Maintenance | Installation of high mast lights at Mau Narok, metta AP Camp and utalii dam | To improve security lighting through high mast floodlight installation at lights at Mau Narok, metta AP Camp and utalii dam | High mast floodlight installed at lights at Mau Narok, metta AP Camp and utalii dam | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.58119, 36.034068 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 512900 | 85.5 | 512900 | 87100 | 87100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
6719 | Infrastructure, Development and Maintenance | Construction of Bodaboda Sheds at Teacher and kiratina | To construct Bodaboda Sheds at Teacher and kiratina | Bodaboda Sheds at Teacher and kiratina constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.289183, 36.115024 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022/23 | 945221 | 945221 | 945221 | Equitable | N/A | 945221 | 0 | 642390 | 68 | 642390 | 1000000 | 302831 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6720 | Construction of drainage system at Kiratina in Menengai East | Construction of drainage system at Kiratina in Menengai East | To construct drainage system at Kiratina in Menengai East | Drainage system at Kiratina in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.28519 36.122662 1848.699951171875 42.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000003 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997950 | 99.9 | 2997950 | 2997950 | 2050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6721 | Construction of drainage system at Lower teachers in Menengai East | Construction of drainage system at Lower teachers in Menengai East | To construct drainage system at Lower teachers in Menengai East | Drainage system at Lower teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.27977 36.122899 1868.849365234375 56.99399948120117 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000002 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995741 | 99.9 | 2995741 | 2980455 | 4259 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6722 | Construction of drainage system at upper teachers in Menengai East | Construction of drainage system at upper teachers in Menengai East | To construct drainage system at upper teachers in Menengai East | Drainage system at upper teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275859 36.11542 1856.699951171875 4.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2980455 | 99.3 | 2980455 | 2997556 | 19545 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs cleaning and clearing.
6723 | Infrastructure, Development and Maintenance | Construction of 10 boda boda shed in Menengai West | To construct 10 boda boda shed in Menengai West | 10 boda boda shed in Menengai West constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.225937, 35.975482 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3482055 | 0 | 3482055 | 3500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
6724 | Infrastructure, Development & Maintenance | Installation of highmast streetlights in Menengai West ward | To improve security lighting through high mast floodlight installation at streetlights in Menengai West ward | High mast floodlight installed at streetlights in Menengai West ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.212507 36.020413 2043.9000244140625 9.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2825750 | 0 | 2825750 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6725 | Infrastructure, Development and Maintenance | Construction of drainage and culverts at Kenyatta Estate | To construct drainage and culverts at Kenyatta Estate | Drainage and culverts at Kenyatta Estate constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6726 | Infrastructure, Development and Maintenance | installation of 3 floodlights mulika mwizi across the ward | To install 3 floodlights mulika mwizi across the ward | 3 floodlights mulika mwizi across the ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6727 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of floodlight at Tayari | To install floodlight at Tayari | Floodlight at Tayari installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6728 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights at Chazon and Gateiguru | To improve lighting and safety through installation of solar streetlights at Chazon and Gateiguru | Solar streetlights installed at Chazon and Gateiguru | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6729 | Completion of ongoing Salgaa drainage works | Completion of ongoing Salgaa drainage works | To complete ongoing Salgaa drainage works | Ongoing Salgaa drainage works completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.205574, 35.8469 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 999630 | 999630 | Equitable | N/A | 999630 | 0 | 999630 | 100 | 999630 | 999630 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
6730 | Infrastructure, Development & Maintenance | grading and murraming of Roret AIC road | To improve road infrastructure by grading and murraming Roret AIC road | Roret AIC road graded and murramed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.26713 36.001962 2029.9000244140625 8.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
6731 | Infrastructure, Development & Maintenance | grading and gravelling woodard cemetery road and Drainage Works at Ngumo Road | To improve road infrastructure by grading and murraming woodard cemetery road and Drainage Works at Ngumo Road | Woodard cemetery road and Drainage Works at Ngumo Road graded and murramed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.511012, 36.368231 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2442336 | 97.7 | 2442336 | 57664 | 57664 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Cubango East Limited. Assessor remarks: In good condition.
6732 | Infrastructure, Development & Maintenance | Installation of high mast flood lights in Njoro ward | To improve security lighting through high mast floodlight installation at flood lights in Njoro ward | High mast floodlight installed at flood lights in Njoro ward | 3110504 | Other Infrastructure and Civil Works | NJORO | NJORO | -0.335004, 35.960373 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 765700 | 85.1 | 765700 | 133300 | 134300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rivtok contractors Ltd. Assessor remarks: In good state.
6733 | Infrastructure, Development & Maintenance | Grading and murraming of Kamukunji and shimo mbili estate | To improve road infrastructure by grading and murraming Kamukunji and shimo mbili estate | Kamukunji and shimo mbili estate graded and murramed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.405603, 36.155024 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 20202021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1349085 | 89.9 | 1349085 | 1350000 | 150915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Techfieod system limited. Assessor remarks: Project complete.
6734 | grading and murraming of Piave roads | grading and murraming of Piave roads | To improve road infrastructure by grading and murraming Piave roads | Piave roads graded and murramed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.306099, 35.98802 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3529450 | 88.2 | 3529450 | 69979 | 470550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wikagi contractors. Assessor remarks: In good state.
6735 | Infrastructure, Development & Maintenance | Installation of high mast flood lights in Njoro ward | To improve security lighting through high mast floodlight installation at flood lights in Njoro ward | High mast floodlight installed at flood lights in Njoro ward | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.335004, 35.960373 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 765700 | 85.1 | 765700 | 133300 | 134300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rivtok contractors Ltd. Assessor remarks: In good state.
6736 | Supply of murram | Supply of murram | To implement supply of murram for road connectivity and accessibility | Supply of murram completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.376968 35.942036 2214.500244140625 42.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3792710 | 189.6 | 3792710 | 2000000 | -1792710 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair state.
6737 | Infrastructure, Development and Maintenance | Construction of muchorwe shade | To construct muchorwe shade | Muchorwe shade constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.377837 35.709362 2720.8 5.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 317534 | 79.4 | 317534 | 399950 | 82466 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No- Was constructed far from other classes. Viable: No. Contractor: M/S WAMKONG CONSTRUCTION & SuPPLIES LTD. Assessor remarks: Needs renovation.
6738 | Infrastructure, Development and Maintenance | Construction of a drainage at Matunguru in mwariki | To construct a drainage at Matunguru in mwariki | A drainage at Matunguru in mwariki constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930720 | 96.5 | 1930720 | 2000000 | 69280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6739 | Infrastructure, Development and Maintenance | Construction of drainage in top ten-ponda mali | To construct drainage in top ten-ponda mali | Drainage in top ten-ponda mali constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.306746, 36.064687 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 22/23 | 2670451 | 2670451 | 2670451 | Equitable | N/A | 2670451 | 0 | 2200258 | 82.4 | 2200258 | 2670451 | 470193 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Aimers. Assessor remarks: Needs rehabilitation.
6740 | Infrastructure, Development & Maintenance | Construction of sewer line at public toilet in pondamali | To construct sewer line at public toilet in pondamali | Sewer line at public toilet in pondamali constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1248085 | 1248085 | 1248085 | Equitable | N/A | 1248085 | 0 | 2200258 | 176.3 | 2200258 | 1248085 | -952173 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6741 | Construction of drainage system in Rhonda | Construction of drainage system in Rhonda | To construct drainage system in Rhonda | Drainage system in Rhonda constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.308484, 36.063407 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 18/20 | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4991500 | 99.8 | 4991500 | 5000000 | 8500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s biscon construction. Assessor remarks: Needs rehabilitation.
6742 | Infrastructure, Development and Maintenance | Construction of a drainage at Matunguru in mwariki | To construct a drainage at Matunguru in mwariki | A drainage at Matunguru in mwariki constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930720 | 96.5 | 1930720 | 2000000 | 69280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6743 | Infrastructure, Development and Maintenance | Construction of drainage in top ten-ponda mali | To construct drainage in top ten-ponda mali | Drainage in top ten-ponda mali constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306746, 36.064687 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 22/23 | 2670451 | 2670451 | 2670451 | Equitable | N/A | 2670451 | 0 | 2200258 | 82.4 | 2200258 | 2670451 | 470193 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Aimers. Assessor remarks: Needs rehabilitation.
6744 | Construction of drainage system in Rhonda | Construction of drainage system in Rhonda | To construct drainage system in Rhonda | Drainage system in Rhonda constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.308484, 36.063407 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 18/20 | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4991500 | 99.8 | 4991500 | 5000000 | 8500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s biscon construction. Assessor remarks: Needs rehabilitation.
6745 | Infrastructure, Development and Maintenance | Construction of a drainage system at Githima | To construct a drainage system at Githima | A drainage system at Githima constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1988303 | 99.4 | 1988303 | 1991450 | 11697 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6746 | Construction of drainage systems at Gilanis Estate | Construction of drainage systems at Gilanis Estate | To construct drainage systems at Gilanis Estate | Drainage systems at Gilanis Estate constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996713 | 99.8 | 1996713 | 1967 | 3287 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6747 | Construction of drainage systems at Githima Estate | Construction of drainage systems at Githima Estate | To construct drainage systems at Githima Estate | Drainage systems at Githima Estate constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4291953 | 286.1 | 4291953 | 1500000 | -2791953 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6748 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights at Sondu Drive | To improve lighting and safety through installation of solar streetlights at Sondu Drive | Solar streetlights installed at Sondu Drive | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3497000 | 99.9 | 3497000 | 3000 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6749 | Infrastructure, Development and Maintenance | Rehabilitation of drainage along john momanyi road | To rehabilitate drainage along john momanyi road to restore functionality | Drainage along john momanyi road rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2460785 | 2460785 | 2460785 | Equitable | N/A | 2460785 | 0 | 2459954 | 100 | 2459954 | 2459954 | 831 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6750 | Infrastructure, Development and Maintenance | Unblocking of drainage system in Shabab Ward | To implement unblocking of drainage system in shabab ward for road connectivity and accessibility | Unblocking of drainage system in Shabab Ward completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1987956 | 198.8 | 1987956 | 1000000 | -987956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6751 | Construction of 5 boda boda sheds | Construction of 5 boda boda sheds | To construct 5 boda boda sheds | 5 boda boda sheds constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | SIRIKWA | -0.256499, 35.719607 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499300 | 100 | 1499300 | 1499300 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: Project is good and it serves the public.
6752 | Infrastructure, Development & Maintenance | Installation of 1 floodlights at Banita Goat auction ground | To install 1 floodlights at Banita Goat auction ground | 1 floodlights at Banita Goat auction ground installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.065528, 36.063015 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299700 | 99.9 | 299700 | 299700 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floodlight is ok.
6753 | Infrastructure, Development & Maintenance | Installation of 4 floodlights at rafiki area | To install 4 floodlights at rafiki area | 4 floodlights at rafiki area installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.150125, 35.958591 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1164900 | 97.1 | 1164900 | 1200000 | 35100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require repair and additional streetlight at the end of the street.
6754 | Infrastructure, Development & Maintenance | Installation of floodlights at Kamundu Centre | To install floodlights at Kamundu Centre | Floodlights at Kamundu Centre installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.082257 35.872951 1817 10 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 280000 | 93.3 | 280000 | 300000 | 20000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Two lights not working.
6755 | Installation of floodlights at majai mingy | Installation of floodlights at majai mingy | To install floodlights at majai mingy | Floodlights at majai mingy installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.055765 36.026265 1647.0999755859375 6.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299450 | 99.8 | 299450 | 299450 | 550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working in good condition.
6756 | Infrastructure, Development & Maintenance | Culverting and spot murraming at Majitamu Academy-Dairy road | To implement culverting and spot murraming at majitamu academy-dairy road for road connectivity and accessibility | Culverting and spot murraming at Majitamu Academy-Dairy road completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOLAI | 0.00759, 36.157721 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691724 | 99.5 | 1691724 | 1000616 | 8276 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
6757 | Infrastructure, Development and Maintenance | Construction of a drainage system at Githima | To construct a drainage system at Githima | A drainage system at Githima constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1988303 | 99.4 | 1988303 | 1991450 | 11697 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6758 | Construction of drainage systems at Gilanis Estate | Construction of drainage systems at Gilanis Estate | To construct drainage systems at Gilanis Estate | Drainage systems at Gilanis Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996713 | 99.8 | 1996713 | 1967 | 3287 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6759 | Construction of drainage systems at Githima Estate | Construction of drainage systems at Githima Estate | To construct drainage systems at Githima Estate | Drainage systems at Githima Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4291953 | 286.1 | 4291953 | 1500000 | -2791953 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6760 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights at Sondu Drive | To improve lighting and safety through installation of solar streetlights at Sondu Drive | Solar streetlights installed at Sondu Drive | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.408907, 36.360101 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3497000 | 99.9 | 3497000 | 3000 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6761 | Infrastructure, Development and Maintenance | Rehabilitation of drainage along john momanyi road | To rehabilitate drainage along john momanyi road to restore functionality | Drainage along john momanyi road rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2460785 | 2460785 | 2460785 | Equitable | N/A | 2460785 | 0 | 2459954 | 100 | 2459954 | 2459954 | 831 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6762 | Infrastructure, Development and Maintenance | Unblocking of drainage system in Shabab Ward | To implement unblocking of drainage system in shabab ward for road connectivity and accessibility | Unblocking of drainage system in Shabab Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1987956 | 198.8 | 1987956 | 1000000 | -987956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6763 | Construction of 5 boda boda sheds | Construction of 5 boda boda sheds | To construct 5 boda boda sheds | 5 boda boda sheds constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Sirikwa | -0.256499, 35.719607 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499300 | 1499300 | Equitable | N/A | 1499300 | 0 | 1499300 | 100 | 1499300 | 1499300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: Project is good and it serves the public.
6764 | Infrastructure, Development & Maintenance | Hire of machines to repair kapsetek roads | To implement hire of machines to repair kapsetek roads for road connectivity and accessibility | Hire of machines to repair kapsetek roads completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.054612 35.86942 1837.6 11 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads need regular maintenance and drainage.
6765 | Infrastructure, Development & Maintenance | Installation of 1 floodlights at Banita Goat auction ground | To install 1 floodlights at Banita Goat auction ground | 1 floodlights at Banita Goat auction ground installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.065528, 36.063015 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 299700 | 299700 | Equitable | N/A | 299700 | 0 | 299700 | 100 | 299700 | 299700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floodlight is ok.
6766 | Infrastructure, Development & Maintenance | Installation of 4 floodlights at rafiki area | To install 4 floodlights at rafiki area | 4 floodlights at rafiki area installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.150125, 35.958591 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1164900 | 97.1 | 1164900 | 1200000 | 35100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require repair and additional streetlight at the end of the street.
6767 | Infrastructure, Development & Maintenance | Installation of floodlights at Kamundu Centre | To install floodlights at Kamundu Centre | Floodlights at Kamundu Centre installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.082257 35.872951 1817 10 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 280000 | 93.3 | 280000 | 300000 | 20000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Two lights not working.
6768 | Installation of floodlights at majai mingy | Installation of floodlights at majai mingy | To install floodlights at majai mingy | Floodlights at majai mingy installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.055765 36.026265 1647.0999755859375 6.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 299450 | 299450 | Equitable | N/A | 299450 | 0 | 299450 | 100 | 299450 | 299450 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working in good condition.
6769 | Infrastructure, Development & Maintenance | Construction of drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary | To construct drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary | Drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | TURI | -0.248077 35.730962 2517.6 200 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
6770 | Infrastructure, Development & Maintenance | installation of culverts across Turi ward | To improve drainage and road access through culvert installation at across Turi ward | Culverts installed at across Turi ward | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.309382 35.7569 2571.8 10.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good.
6771 | Infrastructure, Development and Maintenance | Installation of four high mast in barut | To install four high mast in barut | Four high mast in barut installed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | -0.32524 36.0458 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2040992 | 2040992 | 2040992 | Equitable | N/A | 2040992 | 0 | 1991750 | 97.6 | 1991750 | 1991750 | 49242 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They are functional.
6772 | Infrastructure, Development & Maintenance | Installation, repair and replacement of streetlights in Biashara ward | To implement installation, repair and replacement of streetlights in biashara ward for road connectivity and accessibility | Installation, repair and replacement of streetlights in Biashara ward completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 599500 | 30 | 599500 | 2000000 | 1400500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6773 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights in biashara ward | To rehabilitate streetlights in biashara ward to restore functionality | Streetlights in biashara ward rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599500 | 99.9 | 599500 | 599500 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6774 | Infrastructure, Development and Maintenance | Installation of four high mast in barut | To install four high mast in barut | Four high mast in barut installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.32524 36.0458 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2040992 | 2040992 | 2040992 | Equitable | N/A | 2040992 | 0 | 1991750 | 97.6 | 1991750 | 1991750 | 49242 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They are functional.
6775 | Infrastructure, Development and Maintenance | Installation of fluorescent lighting at nasher market | To install fluorescent lighting at nasher market | Fluorescent lighting at nasher market installed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.28682, 36.075562 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 1500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1500000 | 75 | 1500000 | 500000 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very functional.
6776 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights in biashara ward | To rehabilitate streetlights in biashara ward to restore functionality | Streetlights in biashara ward rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 599500 | 599500 | Equitable | N/A | 599500 | 0 | 599500 | 100 | 599500 | 599500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6777 | Infrastructure, Development & Maintenance | Construction of boda-boda sheds in Dundori ward | To construct boda-boda sheds in Dundori ward | Boda-boda sheds in Dundori ward constructed | 3110599 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.247407, 36.182378 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 498406 | 49.8 | 498406 | 896622 | 501594 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin construction ltd. Assessor remarks: Good three in number.
6778 | Infrastructure, Development & Maintenance | Installation of High Mast Street Lighting floodlights in dundori ward | To improve security lighting through high mast floodlight installation at Street Lighting floodlights in dundori ward | High mast floodlight installed at Street Lighting floodlights in dundori ward | 3110599 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.262936, 36.190874 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2791150 | 99.7 | 2791150 | 2800000 | 8850 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Holy son. Assessor remarks: Good.
6779 | Infrastructure, Development & Maintenance | Installation of flood lights across the ward | To install flood lights across the ward | Flood lights across the ward installed | 3110599 | Other Infrastructure and Civil Works | GILGIL | EBURRU-MBARUK | -0.6478203, 36.6266263 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21-22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4765250 | 95.3 | 4765250 | 4765250 | 234750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not specified. Assessor remarks: More needed.
6780 | Infrastructure, Development & Maintenance | Construction of Wakajane-Meli culverts | To construct Wakajane-Meli culverts | Wakajane-Meli culverts constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | ELEMENTAITA | -0.640033, 36.115242 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1248109 | 1248109 | 1248109 | Equitable | N/A | 1248109 | 0 | 1246020 | 99.8 | 1246020 | 1246020 | 2089 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Useful since the area is hilly has rendered the adjacent road impassable..
6781 | Installation of culverts at Kiambogo area | Installation of culverts at Kiambogo area | To improve drainage and road access through culvert installation at Kiambogo area | Culverts installed at Kiambogo area | 3110599 | Other Infrastructure and Civil Works | GILGIL | ELEMENTAITA | -0.599097, 36.131986 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1765992 | 1765992 | 1765992 | Equitable | N/A | 1765992 | 0 | 1763921 | 99.9 | 1763921 | 1764592 | 2071 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some culverts have been removed to pave way for construction of Elementaita Kiambogo road.
6782 | Infrastructure, Development & Maintenance | Installation of flood lights across the ward | To install flood lights across the ward | Flood lights across the ward installed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.6478203, 36.6266263 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21-22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4765250 | 95.3 | 4765250 | 4765250 | 234750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not specified. Assessor remarks: More needed.
6783 | Infrastructure, Development & Maintenance | Construction of Wakajane-Meli culverts | To construct Wakajane-Meli culverts | Wakajane-Meli culverts constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.640033, 36.115242 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1248109 | 1246020 | 1246020 | Equitable | N/A | 1246020 | 0 | 1246020 | 100 | 1246020 | 1246020 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Useful since the area is hilly has rendered the adjacent road impassable..
6784 | Installation of culverts at Kiambogo area | Installation of culverts at Kiambogo area | To improve drainage and road access through culvert installation at Kiambogo area | Culverts installed at Kiambogo area | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.599097, 36.131986 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1765992 | 1765992 | 1765992 | Equitable | N/A | 1765992 | 0 | 1763921 | 99.9 | 1763921 | 1764592 | 2071 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some culverts have been removed to pave way for construction of Elementaita Kiambogo road.
6785 | Infrastructure, Development & Maintenance | Installation of 5 no (13m) high mast street lights at lake view and race course estates | To install 5 no (13m) high mast street lights at lake view and race course estates | 5 no (13m) high mast street lights at lake view and race course estates installed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.310232, 36.073934 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2018/2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1420750 | 94.7 | 1420750 | 1420750 | 79250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Leogeo general agencies. Assessor remarks: Functional.
6786 | Streetlight maintanance in flamingo ward | Streetlight maintanance in flamingo ward | To implement streetlight maintanance in flamingo ward for road connectivity and accessibility | Streetlight maintanance in flamingo ward completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.302334, 36.072589 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 949100 | 189.8 | 949100 | 500000 | -449100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
6787 | Infrastructure, Development & Maintenance | Installation of 5 no (13m) high mast street lights at lake view and race course estates | To install 5 no (13m) high mast street lights at lake view and race course estates | 5 no (13m) high mast street lights at lake view and race course estates installed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.310232, 36.073934 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2018/2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1420750 | 94.7 | 1420750 | 1420750 | 79250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Leogeo general agencies. Assessor remarks: Functional.
6788 | Streetlight maintanance in flamingo ward | Streetlight maintanance in flamingo ward | To implement streetlight maintanance in flamingo ward for road connectivity and accessibility | Streetlight maintanance in flamingo ward completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.302334, 36.072589 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 949100 | 189.8 | 949100 | 500000 | -449100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
6789 | Construction and rehabilitation of roads - Boresha Barabara | Construction and rehabilitation of roads - Boresha Barabara | To construct and rehabilitation of roads - Boresha Barabara | And rehabilitation of roads - Boresha Barabara constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 69181764 | 20181765 | 20181765 | Equitable | N/A | 20181765 | 0 | 20181765 | 100 | 20181765 | 7500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6790 | Construction & Rehabilitation of buildings(Water Reservoir) | Construction & Rehabilitation of buildings(Water Reservoir) | To construct & Rehabilitation of buildings(Water Reservoir) | & Rehabilitation of buildings(Water Reservoir) constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 20000000 | 400 | 20000000 | 4537500 | -15000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6791 | Infrastructure, Development & Maintenance | Rehabilitation of bus park and other Parking bays | To rehabilitate bus park and other Parking bays to restore functionality | Bus park and other Parking bays rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 1537405 | 15.4 | 1537405 | 1537405 | 8462595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6792 | Infrastructure, Development & Maintenance | Kabazi ward streetlights | To implement kabazi ward streetlights for road connectivity and accessibility | Kabazi ward streetlights completed | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | KABAZI | -0.058853, 36.126021 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998140 | 99.8 | 998140 | 998140 | 1860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not identified. Assessor remarks: To be repaired.
6793 | Construction of four boda-boda sheds | Construction of four boda-boda sheds | To construct four boda-boda sheds | Four boda-boda sheds constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.181143 35.712828 2481.3 2.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998600 | 99.9 | 998600 | 0 | 1400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs seats and painting.
6794 | Installation of streetlights in kaptembwo ward | Installation of streetlights in kaptembwo ward | To improve lighting and safety through installation of solar streetlights at kaptembwo ward | Solar streetlights installed at kaptembwo ward | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.30596, 36.050162 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2778520 | 277.9 | 2778520 | 2778520 | -1778520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S QUEJ ENTERPRISES. Assessor remarks: In good condition.
6795 | Infrastructure, Development and Maintenance | Maintanance of streetlights in kaptembwo ward | To implement maintanance of streetlights in kaptembwo ward for road connectivity and accessibility | Maintanance of streetlights in kaptembwo ward completed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.302372, 36.06287 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1787300 | 178.7 | 1787300 | 1000000 | -787300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has curbed insecurity issues. Contractor: U115. Assessor remarks: In good condition.
6796 | Installation of flood lights at Kiamaina | Installation of flood lights at Kiamaina | To install flood lights at Kiamaina | Flood lights at Kiamaina installed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.237962 36.119598 1921.699951171875 20.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999982 | 100 | 999982 | 1000000 | 18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6797 | Infrastructure, Development & Maintenance | Installation of flood lights at Workers | To install flood lights at Workers | Flood lights at Workers installed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.265858, 36.10787 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999950 | 100 | 1999950 | 1999950 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6798 | Installation of flood lights in Gituamba | Installation of flood lights in Gituamba | To install flood lights in Gituamba | Flood lights in Gituamba installed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.237962 36.119598 1921.699951171875 20.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499950 | 100 | 2499950 | 2500000 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6799 | Installation of flood lights in Menengai | Installation of flood lights in Menengai | To install flood lights in Menengai | Flood lights in Menengai installed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.264246 36.117193 1875.0999755859375 44.797000885009766 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999850 | 100 | 999850 | 1000000 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6800 | Installation of flood lights In Rurii | Installation of flood lights In Rurii | To install flood lights In Rurii | Flood lights In Rurii installed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.264246 36.117193 1875.0999755859375 44.797000885009766 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3204800 | 80.1 | 3204800 | 4000000 | 795200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6801 | Infrastructure, Development and Maintenance | Installation of streetlights at Kivumbini | To improve lighting and safety through installation of solar streetlights at Kivumbini | Solar streetlights installed at Kivumbini | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.296395, 36.085107 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 766000 | 766000 | 766000 | Equitable | N/A | 766000 | 0 | 1852500 | 241.8 | 1852500 | 766000 | -1086500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6802 | Infrastructure, Development & Maintenance | maintanance of street lights at kivumbini | To implement maintanance of street lights at kivumbini for road connectivity and accessibility | maintanance of street lights at kivumbini completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.298543, 36.086344 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | july2022 | 597638 | 597638 | 597638 | Equitable | N/A | 597638 | 0 | 576500 | 96.5 | 576500 | 597638 | 21138 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
6803 | Infrastructure, Development & Maintenance | Kabazi ward streetlights | To implement kabazi ward streetlights for road connectivity and accessibility | Kabazi ward streetlights completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.058853, 36.126021 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 998140 | 998140 | Equitable | N/A | 998140 | 0 | 998140 | 100 | 998140 | 998140 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not identified. Assessor remarks: To be repaired.
6804 | Construction of four boda-boda sheds | Construction of four boda-boda sheds | To construct four boda-boda sheds | Four boda-boda sheds constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.181143 35.712828 2481.3 2.9000000953674316 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 998600 | 998600 | Equitable | N/A | 998600 | 0 | 998600 | 100 | 998600 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs seats and painting.
6805 | Infrastructure, Development & Maintenance | Construction of boda boda sheds alongside ingobor-mombasa road | To construct boda boda sheds alongside ingobor-mombasa road | Boda boda sheds alongside ingobor-mombasa road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.000456 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 550895 | 550895 | 550895 | Equitable | N/A | 550895 | 0 | 550895 | 100 | 550895 | 550895 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Has better work environment. Assessor remarks: Done but is in bad state.
6806 | Construction of boda boda sheds at KB area | Construction of boda boda sheds at KB area | To construct boda boda sheds at KB area | Boda boda sheds at KB area constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Improved transport services. Assessor remarks: Done and in use.
6807 | Infrastructure, Development & Maintenance | Installation of Mulika mwizi at ingobor upper | To install Mulika mwizi at ingobor upper | Mulika mwizi at ingobor upper installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.313727, 36.014906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 880000 | 88 | 880000 | 880000 | 120000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: well installed and in use.
6808 | Infrastructure, Development & Maintenance | Installation of streetlights 180 watts at ingobor and laluet | To improve lighting and safety through installation of solar streetlights at 180 watts at ingobor and laluet | Solar streetlights installed at 180 watts at ingobor and laluet | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.000514 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2340800 | 93.6 | 2340800 | 2340800 | 159200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but vandalism has stalled it. Assessor remarks: Well done, but solar panels stolen.
6809 | Installation of streetlights in kaptembwo ward | Installation of streetlights in kaptembwo ward | To improve lighting and safety through installation of solar streetlights at kaptembwo ward | Solar streetlights installed at kaptembwo ward | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.30596, 36.050162 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2778520 | 277.9 | 2778520 | 2778520 | -1778520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S QUEJ ENTERPRISES. Assessor remarks: In good condition.
6810 | Infrastructure, Development and Maintenance | Maintanance of streetlights in kaptembwo ward | To implement maintanance of streetlights in kaptembwo ward for road connectivity and accessibility | Maintanance of streetlights in kaptembwo ward completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302372, 36.06287 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1787300 | 178.7 | 1787300 | 1000000 | -787300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has curbed insecurity issues. Contractor: U115. Assessor remarks: In good condition.
6811 | Installation of flood lights at Kiamaina | Installation of flood lights at Kiamaina | To install flood lights at Kiamaina | Flood lights at Kiamaina installed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.237962 36.119598 1921.699951171875 20.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999982 | 100 | 999982 | 1000000 | 18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6812 | Infrastructure, Development & Maintenance | Installation of flood lights at Workers | To install flood lights at Workers | Flood lights at Workers installed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.265858, 36.10787 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999950 | 100 | 1999950 | 1999950 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6813 | Installation of flood lights in Menengai | Installation of flood lights in Menengai | To install flood lights in Menengai | Flood lights in Menengai installed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.264246 36.117193 1875.0999755859375 44.797000885009766 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999850 | 100 | 999850 | 1000000 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6814 | Installation of flood lights In Rurii | Installation of flood lights In Rurii | To install flood lights In Rurii | Flood lights In Rurii installed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.264246 36.117193 1875.0999755859375 44.797000885009766 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3204800 | 80.1 | 3204800 | 4000000 | 795200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6815 | Infrastructure, Development & Maintenance | Installation of Solar flood lights in Gituamba | To install Solar flood lights in Gituamba | Solar flood lights in Gituamba installed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.237962 36.119598 1921.699951171875 20.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499950 | 0 | 2499950 | 2499950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
6816 | Infrastructure, Development and Maintenance | Installation of streetlights at Kivumbini | To improve lighting and safety through installation of solar streetlights at Kivumbini | Solar streetlights installed at Kivumbini | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296395, 36.085107 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 766000 | 766000 | 766000 | Equitable | N/A | 766000 | 0 | 1852500 | 241.8 | 1852500 | 766000 | -1086500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6817 | Infrastructure, Development & Maintenance | maintanance of street lights at kivumbini | To implement maintanance of street lights at kivumbini for road connectivity and accessibility | maintanance of street lights at kivumbini completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298543, 36.086344 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | july2022 | 597638 | 597638 | 597638 | Equitable | N/A | 597638 | 0 | 576500 | 96.5 | 576500 | 597638 | 21138 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
6818 | Infrastructure, Development & Maintenance | Installation of security lights in lare ward | To install security lights in lare ward | Security lights in lare ward installed | 3110599 | Other Infrastructure and Civil Works | NJORO | LARE | -0.447315, 36.01064 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 683920 | 97.7 | 683920 | 700000 | 16080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance to work.
6819 | Infrastructure, Development & Maintenance | Installation of security lights in lare ward | To install security lights in lare ward | Security lights in lare ward installed | 3110599 | Other Infrastructure and Civil Works | Njoro | Lare | -0.447315, 36.01064 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 683920 | 97.7 | 683920 | 700000 | 16080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance to work.
6820 | Infrastructure, Development & Maintenance | Drainage works (unclogging) | To implement drainage works (unclogging) for road connectivity and accessibility | Drainage works (unclogging) completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6821 | Infrastructure, Development & Maintenance | Maintanance of streetlights -maai mahiu and longonot | To implement maintanance of streetlights -maai mahiu and longonot for road connectivity and accessibility | Maintanance of streetlights -maai mahiu and longonot completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | MAAI MAHIU | -0.938114, 36.539008 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3000000 | 600 | 3000000 | 500000 | -2500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6822 | Infrastructure, Development and Maintenance | Construction of one motorbike shade at high junction to Kasarani | To construct one motorbike shade at high junction to Kasarani | One motorbike shade at high junction to Kasarani constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.630631 36.398601 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Vandalism common in the area. The project destroyed through vandalism.
6823 | Installation of highmast streetlights at Mauche, Kamasai and Teret Centres | Installation of highmast streetlights at Mauche, Kamasai and Teret Centres | To improve security lighting through high mast floodlight installation at streetlights at Mauche, Kamasai and Teret Centres | High mast floodlight installed at streetlights at Mauche, Kamasai and Teret Centres | 3110599 | Other Infrastructure and Civil Works | NJORO | MAUCHE | -0.495153, 35.957838 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 825200 | 82.5 | 825200 | 825200 | 174800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Tes. Contractor: Not known. Assessor remarks: Good.
6824 | Infrastructure, Development and Maintenance | Mlika mwizi at munju/kanyoni/tayari | To implement mlika mwizi at munju/kanyoni/tayari for road connectivity and accessibility | Mlika mwizi at munju/kanyoni/tayari completed | 3110599 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6825 | Infrastructure, Development & Maintenance | Installation of street lighting on selected spots in murindat | To install street lighting on selected spots in murindat | Street lighting on selected spots in murindat installed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MURINDAT | -0.409823, 36.312041 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6826 | Infrastructure, Development & Maintenance | Drainage works (unclogging) | To implement drainage works (unclogging) for road connectivity and accessibility | Drainage works (unclogging) completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6827 | Infrastructure, Development & Maintenance | Maintanance of streetlights -maai mahiu and longonot | To implement maintanance of streetlights -maai mahiu and longonot for road connectivity and accessibility | Maintanance of streetlights -maai mahiu and longonot completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.938114, 36.539008 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3000000 | 600 | 3000000 | 500000 | -2500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6828 | Infrastructure, Development and Maintenance | Construction of one motorbike shade at high junction to Kasarani | To construct one motorbike shade at high junction to Kasarani | One motorbike shade at high junction to Kasarani constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.630631 36.398601 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Vandalism common in the area. The project destroyed through vandalism.
6829 | Installation of highmast streetlights at Mauche, Kamasai and Teret Centres | Installation of highmast streetlights at Mauche, Kamasai and Teret Centres | To improve security lighting through high mast floodlight installation at streetlights at Mauche, Kamasai and Teret Centres | High mast floodlight installed at streetlights at Mauche, Kamasai and Teret Centres | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.495153, 35.957838 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 825200 | 82.5 | 825200 | 825200 | 174800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Tes. Contractor: Not known. Assessor remarks: Good.
6830 | Infrastructure, Development and Maintenance | Mlika mwizi at munju/kanyoni/tayari | To implement mlika mwizi at munju/kanyoni/tayari for road connectivity and accessibility | Mlika mwizi at munju/kanyoni/tayari completed | 3110599 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6831 | Infrastructure, Development and Maintenance | installation of street lighting at kayole,kinungi,ihindu and kiambogo | To install street lighting at kayole,kinungi,ihindu and kiambogo | Street lighting at kayole,kinungi,ihindu and kiambogo installed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | NAIVASHA EAST | -0.867617 36.522882 2311.6000000000004 6 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 496100 | 99.2 | 496100 | 500000 | 3900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6832 | Rehabilitation of drainage at Free Area Market | Rehabilitation of drainage at Free Area Market | To rehabilitate drainage at Free Area Market to restore functionality | Drainage at Free Area Market rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | NAKURU EAST | -0.293118, 36.120055 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1711252 | 85.6 | 1711252 | 1715073 | 288748 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomikoka construction limited. Assessor remarks: Extension needed.
6833 | Infrastructure, Development & Maintenance | construction of Boda boda sheds at Njoro | To construct Boda boda sheds at Njoro | Boda boda sheds at Njoro constructed | 3110599 | Other Infrastructure and Civil Works | NJORO | NJORO | -0.332853, 35.943837 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1296168 | 1296168 | 1296168 | Equitable | N/A | 1296168 | 0 | 1199768 | 92.6 | 1199768 | 1 | 96400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Solid Floor not provided.
6834 | Infrastructure, Development and Maintenance | installation of street lighting at kayole,kinungi,ihindu and kiambogo | To install street lighting at kayole,kinungi,ihindu and kiambogo | Street lighting at kayole,kinungi,ihindu and kiambogo installed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.867617 36.522882 2311.6000000000004 6 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 496100 | 99.2 | 496100 | 500000 | 3900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6835 | Rehabilitation of drainage at Free Area Market | Rehabilitation of drainage at Free Area Market | To rehabilitate drainage at Free Area Market to restore functionality | Drainage at Free Area Market rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293118, 36.120055 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1711252 | 85.6 | 1711252 | 1715073 | 288748 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomikoka construction limited. Assessor remarks: Extension needed.
6836 | Infrastructure, Development & Maintenance | construction of Boda boda sheds at Njoro | To construct Boda boda sheds at Njoro | Boda boda sheds at Njoro constructed | 3110599 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.332853, 35.943837 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1296168 | 1296168 | 1296168 | Equitable | N/A | 1296168 | 0 | 1199768 | 92.6 | 1199768 | 1 | 96400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Solid Floor not provided.
6837 | Purchase of ELD bulbs | Purchase of ELD bulbs | To procure ELD bulbs | ELD bulbs procured | 3110599 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.384685 35.935928 2293.6 10.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
6838 | Infrastructure, Development & Maintenance | Provision of security lights-high mast at May Flowers,Sher Moi , Kasarani and YMCA | To implement provision of security lights-high mast at may flowers,sher moi , kasarani and ymca for road connectivity and accessibility | Provision of security lights-high mast at May Flowers,Sher Moi , Kasarani and YMCA completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | OLKARIA | -0.835328, 36.353169 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 5999330 | 150 | 5999330 | 5999330 | -1999330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
6839 | Infrastructure, Development & Maintenance | Installation of security lights in mwariki rhoda ward | To install security lights in mwariki rhoda ward | Security lights in mwariki rhoda ward installed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.307327, 36.065712 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21/22 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2068000 | 98.5 | 2068000 | 2100000 | 32000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
6840 | Infrastructure, Development & Maintenance | Installation of security lights in mwariki rhoda ward | To install security lights in mwariki rhoda ward | Security lights in mwariki rhoda ward installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.307327, 36.065712 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21/22 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2068000 | 98.5 | 2068000 | 2100000 | 32000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
6841 | Infrastructure, Development and Maintenance | Construction of streets lights along John Momanyi Road | To construct streets lights along John Momanyi Road | Streets lights along John Momanyi Road constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3628020 | 3628020 | 3628020 | Equitable | N/A | 3628020 | 0 | 3613850 | 99.6 | 3613850 | 3613860 | 14170 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6842 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of streetlights at Shabab | To implement maintenance of streetlights at shabab for road connectivity and accessibility | Maintenance of streetlights at Shabab completed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | -0.350801, 36.219177 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 24/25 | 2043960 | 2043960 | 2043960 | Equitable | N/A | 2043960 | 0 | 1920015 | 93.9 | 1920015 | 2043960 | 123945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
6843 | Supply and installation of 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | Supply and installation of 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | To procure and install 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) procured and installed | 3110599 | Other Infrastructure and Civil Works | RONGAI | SOLAI | 0.001971, 36.155 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193300 | 99.4 | 1193300 | 1193300 | 6700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
6844 | Construction of culverts at Morro, Arash and Munanda | Construction of culverts at Morro, Arash and Munanda | To construct culverts at Morro, Arash and Munanda | Culverts at Morro, Arash and Munanda constructed | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | SUBUKIA | -0.00903, 36.209893 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2017/2018 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497035 | 99.4 | 497035 | 498650 | 2965 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires Continuous maintenance works.
6845 | Infrastructure, Development and Maintenance | Construction of streets lights along John Momanyi Road | To construct streets lights along John Momanyi Road | Streets lights along John Momanyi Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3628020 | 3613860.2 | 3613860.2 | Equitable | N/A | 3613860.2 | 0 | 3613850 | 100 | 3613850 | 3613860 | 10.2 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
6846 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of streetlights at Shabab | To implement maintenance of streetlights at shabab for road connectivity and accessibility | Maintenance of streetlights at Shabab completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.350801, 36.219177 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 24/25 | 2043960 | 2043960 | 2043960 | Equitable | N/A | 2043960 | 0 | 1920015 | 93.9 | 1920015 | 2043960 | 123945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
6847 | Supply and installation of 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | Supply and installation of 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | To procure and install 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) | 6 solar flood lights (1 lower solai,1 murram,1 masitamu,1 KFA and 2 kiboronjo) procured and installed | 3110599 | Other Infrastructure and Civil Works | Rongai | Solai | 0.001971, 36.155 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193300 | 99.4 | 1193300 | 1193300 | 6700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
6848 | Construction of culverts at Morro, Arash and Munanda | Construction of culverts at Morro, Arash and Munanda | To construct culverts at Morro, Arash and Munanda | Culverts at Morro, Arash and Munanda constructed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.00903, 36.209893 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2017/2018 | 500000 | 498650 | 498650 | Equitable | N/A | 498650 | 0 | 497035 | 99.7 | 497035 | 498650 | 1615 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires Continuous maintenance works.
6849 | Enhancement of streetlighting in viwandani ward | Enhancement of streetlighting in viwandani ward | To implement enhancement of streetlighting in viwandani ward for road connectivity and accessibility | Enhancement of streetlighting in viwandani ward completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.722943 36.443031 0 100 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6600740 | 94.3 | 6600740 | 7000000 | 399260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Stalled project.
6850 | Enhancement of streetlighting in viwandani ward | Enhancement of streetlighting in viwandani ward | To implement enhancement of streetlighting in viwandani ward for road connectivity and accessibility | Enhancement of streetlighting in viwandani ward completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.722943 36.443031 0 100 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6600740 | 94.3 | 6600740 | 7000000 | 399260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Stalled project.
6851 | Infrastructure, Development & Maintenance | Laying of culverts at academy ,kwa ngori road | To implement laying of culverts at academy ,kwa ngori road for road connectivity and accessibility | Laying of culverts at academy ,kwa ngori road completed | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | WASEGES | 0.08815 36.229812 1777.6 13.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 861835 | 861835 | 861835 | Equitable | N/A | 861835 | 0 | 776725 | 90.1 | 776725 | 776725 | 85110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets is in use.
6852 | Infrastructure, Development & Maintenance | Laying of culverts at academy ,kwa ngori road | To implement laying of culverts at academy ,kwa ngori road for road connectivity and accessibility | Laying of culverts at academy ,kwa ngori road completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.08815 36.229812 1777.6 13.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 861835 | 861835 | 861835 | Equitable | N/A | 861835 | 0 | 776725 | 90.1 | 776725 | 776725 | 85110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets is in use.
6853 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Tippers 4No) | To rehabilitate Rural Road(Provision for purchase of Tippers 4No) to restore functionality | Rural Road(Provision for purchase of Tippers 4No) rehabilitated | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 35000000 | 35000000 | 35000000 | Equitable | N/A | 35000000 | 0 | 49500000 | 141.4 | 49500000 | 5870000 | -14500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6854 | Boresha barabara (Purchase of machinery) | Boresha barabara (Purchase of machinery) | To implement boresha barabara (purchase of machinery) for road connectivity and accessibility | Boresha barabara (Purchase of machinery) completed | 3110799 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 450000000 | 177000000 | 177000000 | Equitable | N/A | 177000000 | 0 | 156873660 | 88.6 | 156873660 | 10126340 | 20126340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6855 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Grader 4No) | To rehabilitate Rural Road(Provision for purchase of Grader 4No) to restore functionality | Rural Road(Provision for purchase of Grader 4No) rehabilitated | 3111116 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 47047812 | 47047812 | 47047812 | Equitable | N/A | 47047812 | 0 | 49500000 | 105.2 | 49500000 | 5870000 | -2452188 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6856 | Infrastructure, Development and Maintenance | Rehabilitation of plants and equipment | To rehabilitate plants and equipment to restore functionality | Plants and equipment rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 10370000 | 0 | 10370000 | Equitable | N/A | 10370000 | 0 | 4000000 | 0 | 4000000 | 5271862 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6857 | Infrastructure, Development & Maintenance | Construction and installation of BCC Culvert | To construct and installation of BCC Culvert | And installation of BCC Culvert constructed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.63986, 36.517267 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2199355 | 100 | 2199355 | 2200000 | 645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
6858 | Infrastructure, Development & Maintenance | Grading and murraming of good faith - Israel access road | To improve road infrastructure by grading and murraming good faith - Israel access road | Good faith - Israel access road graded and murramed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.70884, 36.48434 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2273598 | 90.9 | 2273598 | 2273598 | 226402 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs further gravelling and spot maintenance.
6859 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Nyonjoro borehole road | To implement grading, gravelling and compaction of nyonjoro borehole road for road connectivity and accessibility | Grading, Gravelling and compaction of Nyonjoro borehole road completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.664802, 36.484093 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 3000001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999289 | 100 | 2999289 | 3298560 | 711 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors. Assessor remarks: Routine maintenance and drainages ..
6860 | Infrastructure, Development & Maintenance | grading, gravelling and culvert installation of Gituru estate roads | To implement grading, gravelling and culvert installation of gituru estate roads for road connectivity and accessibility | grading, gravelling and culvert installation of Gituru estate roads completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3300000 | 3300000 | 3300000 | Equitable | N/A | 3300000 | 0 | 3298559 | 100 | 3298559 | 1 | 1441 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6861 | Infrastructure, Development & Maintenance | Grading, murraming and culvert installation of Kinamba Road | To implement grading, murraming and culvert installation of kinamba road for road connectivity and accessibility | Grading, murraming and culvert installation of Kinamba Road completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.722996, 36.476839 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2913801 | 97.1 | 2913801 | 2913801 | 86199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: No. Assessor remarks: Installation of drainage system, encroachment my developers,.
6862 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County | To maintain Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1198860 | 1198860 | 1198860 | Equitable | N/A | 1198860 | 0 | 1198860 | 100 | 1198860 | 24244 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6863 | Infrastructure, Development & Maintenance | Construction and installation of BCC Culvert | To construct and installation of BCC Culvert | And installation of BCC Culvert constructed | 3111504 | N/A | Naivasha | Biashara-Naivasha | -0.63986, 36.517267 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2199355 | 100 | 2199355 | 2200000 | 645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
6864 | Grading, Gravelling and compaction of Kinamba town Roads | Grading, Gravelling and compaction of Kinamba town Roads | To implement grading, gravelling and compaction of kinamba town roads for road connectivity and accessibility | Grading, Gravelling and compaction of Kinamba town Roads completed | 3111504 | N/A | Naivasha | Biashara-Naivasha | -0.725703, 36.475149 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 3091003 | 3091003 | 3091003 | Equitable | N/A | 3091003 | 0 | 2996475 | 96.9 | 2996475 | 2996475 | 94528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage system maintaining.
6865 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Mutethia access road | To implement grading, gravelling and compaction of mutethia access road for road connectivity and accessibility | Grading, Gravelling and compaction of Mutethia access road completed | 3111504 | N/A | Naivasha | Biashara-Naivasha | -0.7239, 36.512203 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2359350 | 94.4 | 2359350 | 2359350 | 140650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs grading.
6866 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Nyonjoro borehole road | To implement grading, gravelling and compaction of nyonjoro borehole road for road connectivity and accessibility | Grading, Gravelling and compaction of Nyonjoro borehole road completed | 3111504 | N/A | Naivasha | Biashara-Naivasha | -0.664802, 36.484093 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 3000001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999289 | 100 | 2999289 | 3298560 | 711 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors. Assessor remarks: Routine maintenance and drainages ..
6867 | Elburgon Ward Streetlights - Continuation/ Completion | Elburgon Ward Streetlights - Continuation/ Completion | To implement elburgon ward streetlights - continuation/ completion for road connectivity and accessibility | Elburgon Ward Streetlights - Continuation/ Completion completed | 3111504 | N/A | MOLO | ELBURGON | -0.264914, 35.831575 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | - | 1999978 | 1999978 | 1999978 | Equitable | N/A | 1999978 | 0 | 2933630 | 146.7 | 2933630 | 1999978 | -933652 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6868 | Elburgon Ward Streetlights - Continuation/ Completion | Elburgon Ward Streetlights - Continuation/ Completion | To implement elburgon ward streetlights - continuation/ completion for road connectivity and accessibility | Elburgon Ward Streetlights - Continuation/ Completion completed | 3111504 | N/A | Molo | Elburgon | -0.264914, 35.831575 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | - | 1999978 | 2992717 | 2992717 | Equitable | N/A | 2992717 | 0 | 2933630 | 98 | 2933630 | 1999978 | 59087 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6869 | Design and Construction of boda boda shades | Design and Construction of boda boda shades | To design and construct boda boda shades | Boda boda shades designed and constructed | 3111504 | N/A | NAKURU EAST | FLAMINGO | -0.30603, 36.070332 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 2000000 | 18 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin. Assessor remarks: In use.
6870 | Design and Construction of boda boda shades | Design and Construction of boda boda shades | To design and construct boda boda shades | Boda boda shades designed and constructed | 3111504 | N/A | Nakuru East | Flamingo | -0.30603, 36.070332 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 2000000 | 18 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin. Assessor remarks: In use.
6871 | Murraming & Grading of Kamuyu Roads | Murraming & Grading of Kamuyu Roads | To implement murraming & grading of kamuyu roads for road connectivity and accessibility | Murraming & Grading of Kamuyu Roads completed | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.83107, 36.508986 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2993292 | 99.8 | 2993292 | 2985260 | 6708 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done @2,985,260.
6872 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | To undertake the proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.787946, 36.439583 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2873088 | 1527803.95 | 1527803.95 | Equitable | N/A | 1527803.95 | 0 | 3953280 | 258.8 | 3953280 | 1527804 | -2425476.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Cost of the project was 1,527,804.
6873 | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | To maintain Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County in serviceable condition | Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.786956, 36.440088 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3953280 | 3953280 | 3953280 | Equitable | N/A | 3953280 | 0 | 3953280 | 100 | 3953280 | 3953280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's a very busy route which needs regular maintaince.
6874 | Infrastructure, Development and Maintenance | Highmast for Mbaruk | To implement highmast for mbaruk for road connectivity and accessibility | Highmast for Mbaruk completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6875 | Infrastructure, Development & Maintenance | Installation of highmast streetlights across the county | To improve security lighting through high mast floodlight installation at streetlights across the county | High mast floodlight installed at streetlights across the county | 3111504 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9793000 | 97.9 | 9793000 | 9793000 | 207000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6876 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 6000000 | 1643700 | 1643700 | Equitable | N/A | 1643700 | 0 | 1643700 | 100 | 1643700 | 1643700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6877 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county | To maintain Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county in serviceable condition | Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3988605 | 3988605 | 3988605 | Equitable | N/A | 3988605 | 0 | 5237600 | 131.3 | 5237600 | 5237600 | -1248995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6878 | Murraming & Grading of Kamuyu Roads | Murraming & Grading of Kamuyu Roads | To implement murraming & grading of kamuyu roads for road connectivity and accessibility | Murraming & Grading of Kamuyu Roads completed | 3111504 | N/A | Naivasha | Hells Gate | -0.83107, 36.508986 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2985260 | 2985260 | Equitable | N/A | 2985260 | 0 | 2993292 | 100.3 | 2993292 | 2985260 | -8032 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done @2,985,260.
6879 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | To undertake the proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County implemented | 3111504 | N/A | Naivasha | Hells Gate | -0.787946, 36.439583 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2873088 | 1527803.95 | 1527803.95 | Equitable | N/A | 1527803.95 | 0 | 3953280 | 258.8 | 3953280 | 1527804 | -2425476.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Cost of the project was 1,527,804.
6880 | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | To maintain Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County in serviceable condition | Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Hells Gate | -0.786956, 36.440088 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3953280 | 3953280 | 3953280 | Equitable | N/A | 3953280 | 0 | 3953280 | 100 | 3953280 | 3953280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's a very busy route which needs regular maintaince.
6881 | Infrastructure, Development & Maintenance | Design and Construction of Bridge in Kongoi | To design and construct Bridge in Kongoi | Bridge in Kongoi designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.327652, 35.53791 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yess. Viable: Yess. Assessor remarks: There is only 3 Calverts but no bridge.
6882 | Infrastructure, Development & Maintenance | design and Construction of Bridge of Chepkosa bridge | To design and construct Bridge of Chepkosa bridge | Bridge of Chepkosa bridge designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.339452 35.480974 2456.8 4.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1272998 | 106.1 | 1272998 | 1950830 | -72998 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They need additional classroom.the existing classroomm is partitioned,PP1 and pp2 share one classroom.
6883 | Infrastructure, Development & Maintenance | design and Construction of Bridge of kiplongony bridge | To design and construct Bridge of kiplongony bridge | Bridge of kiplongony bridge designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.37964, 35.548857 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1272998 | 63.6 | 1272998 | 2000000 | 727002 | Stalled | 0 | 63.6 | RECOMMENDED FOR TERMINATION | 2017 | N/A | 727002 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yess. Viable: No. Assessor remarks: Underfunded,not yet started.
6884 | Infrastructure, Development and Maintenance | Installation of Security lights, Kivumbini ward | To install Security lights, Kivumbini ward | Security lights, Kivumbini ward installed | 3111504 | N/A | NAKURU EAST | KIVUMBINI | -0.296244, 36.084835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1852500 | 185.2 | 1852500 | 880200 | -852500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6885 | Infrastructure, Development & Maintenance | design and Construction of Bridge of kiplongony bridge | To design and construct Bridge of kiplongony bridge | Bridge of kiplongony bridge designed and constructed | 3111504 | N/A | Kuresoi North | Kiptororo | -0.37964, 35.548857 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1272998 | 63.6 | 1272998 | 2000000 | 727002 | Stalled | 0 | 63.6 | RECOMMENDED FOR TERMINATION | 2017 | N/A | 727002 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yess. Viable: No. Assessor remarks: Underfunded,not yet started.
6886 | Infrastructure, Development and Maintenance | Installation of Security lights, Kivumbini ward | To install Security lights, Kivumbini ward | Security lights, Kivumbini ward installed | 3111504 | N/A | Nakuru East | Kivumbini | -0.296244, 36.084835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1852500 | 185.2 | 1852500 | 880200 | -852500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
6887 | Construction and installation of Culverts in lakeview ward | Construction and installation of Culverts in lakeview ward | To construct and installation of Culverts in lakeview ward | And installation of Culverts in lakeview ward constructed | 3111504 | N/A | NAIVASHA | LAKEVIEW | -0.745187, 36.460478 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997000 | 99.7 | 997000 | 1000000 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6888 | Infrastructure, Development & Maintenance | installation of 20 Highmasts streetlights in lakeview ward | To install 20 Highmasts streetlights in lakeview ward | 20 Highmasts streetlights in lakeview ward installed | 3111504 | N/A | NAIVASHA | LAKEVIEW | -0.727709, 36.443981 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998000 | 99.9 | 1998000 | 1998000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6889 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | LAKEVIEW | -0.75025, 36.456875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3498746 | 1737866 | 1737866 | Equitable | N/A | 1737866 | 0 | 1364334 | 78.5 | 1364334 | 1737866 | 373532 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
6890 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | LAKEVIEW | -0.75025, 36.456875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1488280 | 1488280 | 1488280 | Equitable | N/A | 1488280 | 0 | 1364334 | 91.7 | 1364334 | 1737866 | 123946 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
6891 | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | To improve security lighting through high mast floodlight installation at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | High mast floodlight installed at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | 3111504 | N/A | BAHATI | LANET/UMOJA | -0.287591, 36.152474 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3204800 | 80.1 | 3204800 | 4000000 | 795200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6892 | Construction and installation of Culverts in lakeview ward | Construction and installation of Culverts in lakeview ward | To construct and installation of Culverts in lakeview ward | And installation of Culverts in lakeview ward constructed | 3111504 | N/A | Naivasha | Lakeview | -0.745187, 36.460478 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997000 | 99.7 | 997000 | 1000000 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6893 | Infrastructure, Development & Maintenance | installation of 20 Highmasts streetlights in lakeview ward | To install 20 Highmasts streetlights in lakeview ward | 20 Highmasts streetlights in lakeview ward installed | 3111504 | N/A | Naivasha | Lakeview | -0.727709, 36.443981 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998000 | 99.9 | 1998000 | 1998000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6894 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Lakeview | -0.75025, 36.456875 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3498746 | 1737866 | 1737866 | Equitable | N/A | 1737866 | 0 | 1364334 | 78.5 | 1364334 | 1737866 | 373532 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
6895 | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | To improve security lighting through high mast floodlight installation at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | High mast floodlight installed at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | 3111504 | N/A | Bahati | Lanet/Umoja | -0.287591, 36.152474 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3204800 | 80.1 | 3204800 | 4000000 | 795200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
6896 | Infrastructure, Development & Maintenance | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads | To implement gravelling and murraming and culvert installation of maai mahiu / longonot access roads for road connectivity and accessibility | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads completed | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -1.016438, 36.622719 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 985072 | 49.3 | 985072 | 1014928 | 1014928 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yea. Assessor remarks: Complete.
6897 | installation of floodlights at maai mahiu / longonot | installation of floodlights at maai mahiu / longonot | To install floodlights at maai mahiu / longonot | Floodlights at maai mahiu / longonot installed | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.979019, 36.585983 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 2998280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not functional. Needs repair.
6898 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County | To undertake the proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County | Proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -1.006983, 36.521808 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1993808 | 1993808 | 1993808 | Equitable | N/A | 1993808 | 0 | 1993808 | 100 | 1993808 | 1993808 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6899 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | To undertake the proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.983497, 36.58729 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 588924 | 588924 | 588924 | Equitable | N/A | 588924 | 0 | 588924 | 100 | 588924 | 588924 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs spot filling.
6900 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.870717, 36.555893 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1904720 | 1904720 | 1904720 | Equitable | N/A | 1904720 | 0 | 588924 | 30.9 | 588924 | 1523725 | 1315796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
6901 | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6902 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3050800 | 6050800 | 6050800 | Equitable | N/A | 6050800 | 0 | 6050800 | 100 | 6050800 | 6050800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6903 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2987232 | 2987232 | 2987232 | Equitable | N/A | 2987232 | 0 | 2950463 | 98.8 | 2950463 | 2987232 | 36769 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6904 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3373394 | 91.2 | 3373394 | 3700000 | 326606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6905 | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1730720 | 1730720 | 1730720 | Equitable | N/A | 1730720 | 0 | 1695820 | 98 | 1695820 | 1695820 | 34900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6906 | Grading and Murraming of Molem- Mariashoni Road | Grading and Murraming of Molem- Mariashoni Road | To improve road infrastructure by grading and murraming Molem- Mariashoni Road | Molem- Mariashoni Road graded and murramed | 3111504 | N/A | MOLO | MARIASHONI | -0.372008, 35.824192 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999550 | 100 | 1999550 | 7902 | 450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6907 | Infrastructure, Development & Maintenance | construction of drainage system of Teachers Muhoro Road | To construct drainage system of Teachers Muhoro Road | Drainage system of Teachers Muhoro Road constructed | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275864, 36.115309 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2982800 | 99.4 | 2982800 | 2982800 | 17200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs cleaning and clearing.
6908 | installation of 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | installation of 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | To install 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward installed | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.279546 36.122457 1856.4000244140625 13.560999870300293 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3972851.2 | 3972851 | 3972851 | Equitable | N/A | 3972851 | 0 | 3760840 | 94.7 | 3760840 | 3760840 | 212011 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: 2017/18.
6909 | installation of highmast streetlighting at Kiratina in Menengai ward | installation of highmast streetlighting at Kiratina in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Kiratina in Menengai ward | High mast floodlight installed at streetlighting at Kiratina in Menengai ward | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275968, 36.114339 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000001 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 100 | 3499400 | 600 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6910 | installation of highmast streetlighting at Teachers in Menengai ward | installation of highmast streetlighting at Teachers in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Teachers in Menengai ward | High mast floodlight installed at streetlighting at Teachers in Menengai ward | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275968, 36.114339 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000002 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 100 | 3499400 | 600 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6911 | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | To undertake the proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County implemented | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.278052, 36.117906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016/17 | 677672 | 677672 | 677672 | Equitable | N/A | 677672 | 0 | 2990484 | 441.3 | 2990484 | 677672 | -2312812 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
6912 | Infrastructure, Development and Maintenance | Construction of Drainange and waste bins | To construct Drainange and waste bins | Drainange and waste bins constructed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6913 | Infrastructure, Development and Maintenance | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines | To implement molo central bridge in molo cental ward molo sub county: 1200mm id - 2lines for road connectivity and accessibility | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6914 | Infrastructure, Development and Maintenance | Rehabilitation of molo central access roads | To rehabilitate molo central access roads to restore functionality | Molo central access roads rehabilitated | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6915 | Infrastructure, Development and Maintenance | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy | To implement rehabillitation of streetlights and maintainance in molo ward, molo sub county, mologreen garden area @tayari,mutirithia kwa daktari, behind molo academy for road connectivity and accessibility | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 789728 | 3789728 | 3789728 | Equitable | N/A | 3789728 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6916 | Infrastructure, Development and Maintenance | Repair of Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County | To rehabilitate Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County to restore functionality | Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County rehabilitated | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6917 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County | To maintain Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County in serviceable condition | Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County maintained | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1817024 | 1817024 | 1817024 | Equitable | N/A | 1817024 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6918 | Infrastructure, Development & Maintenance | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads | To implement gravelling and murraming and culvert installation of maai mahiu / longonot access roads for road connectivity and accessibility | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads completed | 3111504 | N/A | Naivasha | Maai Mahiu | -1.016438, 36.622719 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 1014928 | 1014928 | Equitable | N/A | 1014928 | 0 | 985072 | 97.1 | 985072 | 1014928 | 29856 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yea. Assessor remarks: Complete.
6919 | installation of floodlights at maai mahiu / longonot | installation of floodlights at maai mahiu / longonot | To install floodlights at maai mahiu / longonot | Floodlights at maai mahiu / longonot installed | 3111504 | N/A | Naivasha | Maai Mahiu | -0.979019, 36.585983 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 2998280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not functional. Needs repair.
6920 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | To undertake the proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County implemented | 3111504 | N/A | Naivasha | Maai Mahiu | -0.983497, 36.58729 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 588924 | 588924 | 588924 | Equitable | N/A | 588924 | 0 | 588924 | 100 | 588924 | 588924 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs spot filling.
6921 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maai Mahiu | -0.870717, 36.555893 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1904720 | 1904720 | 1904720 | Equitable | N/A | 1904720 | 0 | 588924 | 30.9 | 588924 | 1523725 | 1315796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
6922 | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maiella | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6923 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maiella | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3050800 | 6050800 | 6050800 | Equitable | N/A | 6050800 | 0 | 6050800 | 100 | 6050800 | 6050800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6924 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maiella | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2987232 | 2987232 | 2987232 | Equitable | N/A | 2987232 | 0 | 2950463 | 98.8 | 2950463 | 2987232 | 36769 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6925 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maiella | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3373394 | 91.2 | 3373394 | 3700000 | 326606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6926 | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Maiella | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1730720 | 1695820 | 1695820 | Equitable | N/A | 1695820 | 0 | 1695820 | 100 | 1695820 | 1695820 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6927 | installation of 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | installation of 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | To install 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward | 13 highmast streetlighting in Raviella, pemways, nguta, mireri estate in Menengai ward installed | 3111504 | N/A | Nakuru East | Menengai | -0.279546 36.122457 1856.4000244140625 13.560999870300293 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3972851.2 | 3972851 | 3972851 | Equitable | N/A | 3972851 | 0 | 3760840 | 94.7 | 3760840 | 3760840 | 212011 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: 2017/18.
6928 | installation of highmast streetlighting at Kiratina in Menengai ward | installation of highmast streetlighting at Kiratina in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Kiratina in Menengai ward | High mast floodlight installed at streetlighting at Kiratina in Menengai ward | 3111504 | N/A | Nakuru East | Menengai | -0.275968, 36.114339 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000001 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 100 | 3499400 | 600 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6929 | installation of highmast streetlighting at Teachers in Menengai ward | installation of highmast streetlighting at Teachers in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Teachers in Menengai ward | High mast floodlight installed at streetlighting at Teachers in Menengai ward | 3111504 | N/A | Nakuru East | Menengai | -0.275968, 36.114339 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000002 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 100 | 3499400 | 600 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6930 | Infrastructure, Development and Maintenance | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines | To implement molo central bridge in molo cental ward molo sub county: 1200mm id - 2lines for road connectivity and accessibility | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines completed | 3111504 | N/A | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6931 | Infrastructure, Development and Maintenance | Rehabilitation of molo central access roads | To rehabilitate molo central access roads to restore functionality | Molo central access roads rehabilitated | 3111504 | N/A | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6932 | Infrastructure, Development and Maintenance | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy | To implement rehabillitation of streetlights and maintainance in molo ward, molo sub county, mologreen garden area @tayari,mutirithia kwa daktari, behind molo academy for road connectivity and accessibility | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy completed | 3111504 | N/A | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 789728 | 3789728 | 3789728 | Equitable | N/A | 3789728 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6933 | Infrastructure, Development and Maintenance | Repair of Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County | To rehabilitate Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County to restore functionality | Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County rehabilitated | 3111504 | N/A | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6934 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County | To maintain Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County in serviceable condition | Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County maintained | 3111504 | N/A | Molo | Molo Central | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1817024 | 1817024 | 1817024 | Equitable | N/A | 1817024 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6935 | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.817755 36.544871 2503.067626953125 33.86399841308594 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1199440 | 1199440 | 1199440 | Equitable | N/A | 1199440 | 0 | 1199440 | 100 | 1199440 | 1199440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes by that time. Viable: Yes during that time. Assessor remarks: Road in bad condition.
6936 | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.866736 36.534226 2501.2000000000003 4.900000095367432 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996000 | 99.6 | 996000 | 1000000 | 4000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
6937 | Infrastructure, Development & Maintenance | Design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka | To implement design and installation of highmast streetlighting at wanyama, muguga, free area and naka for road connectivity and accessibility | Design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka completed | 3111504 | N/A | NAKURU EAST | NAKURU EAST | -0.292381, 36.119131 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 11000000 | 11000000 | 11000000 | Equitable | N/A | 11000000 | 0 | 10690650 | 97.2 | 10690650 | 10690650 | 309350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kilewe electrohard and electronics. Assessor remarks: Require maintainance.
6938 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Cheptebes- Elkana road | To improve road infrastructure by grading and murraming and Culverts of Cheptebes- Elkana road | And Culverts of Cheptebes- Elkana road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.412079, 35.937341 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 619480 | 31 | 619480 | 619480 | 1380520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
6939 | Infrastructure, Development & Maintenance | Grading and gravelling of Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | To improve road infrastructure by grading and murraming Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road graded and murramed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.350325 35.637462 2686.6 22.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 8500000 | 3349718 | 3349718 | Equitable | N/A | 3349718 | 0 | 3349718 | 100 | 3349718 | 3349718 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6940 | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Naivasha East | -0.817755 36.544871 2503.067626953125 33.86399841308594 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1199440 | 1199440 | 1199440 | Equitable | N/A | 1199440 | 0 | 1199440 | 100 | 1199440 | 1199440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes by that time. Viable: Yes during that time. Assessor remarks: Road in bad condition.
6941 | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | Naivasha | Naivasha East | -0.866736 36.534226 2501.2000000000003 4.900000095367432 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996000 | 99.6 | 996000 | 1000000 | 4000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
6942 | Infrastructure, Development & Maintenance | Design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka | To implement design and installation of highmast streetlighting at wanyama, muguga, free area and naka for road connectivity and accessibility | Design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka completed | 3111504 | N/A | Nakuru East | Nakuru East | -0.292381, 36.119131 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 11000000 | 11000000 | 11000000 | Equitable | N/A | 11000000 | 0 | 10690650 | 97.2 | 10690650 | 10690650 | 309350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kilewe electrohard and electronics. Assessor remarks: Require maintainance.
6943 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Cheptebes- Elkana road | To improve road infrastructure by grading and murraming and Culverts of Cheptebes- Elkana road | And Culverts of Cheptebes- Elkana road graded and murramed | 3111504 | N/A | Njoro | Nessuit | -0.412079, 35.937341 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 1996940 | 1996940 | Equitable | N/A | 1996940 | 0 | 619480 | 31 | 619480 | 619480 | 1377460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
6944 | Infrastructure, Development & Maintenance | Grading and gravelling of Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | To improve road infrastructure by grading and murraming Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road graded and murramed | 3111504 | N/A | Kuresoi North | Nyota | -0.350325 35.637462 2686.6 22.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 8500000 | 3349718 | 3349718 | Equitable | N/A | 3349718 | 0 | 3349718 | 100 | 3349718 | 3349718 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6945 | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | To install foot bridges at Kadenye / Sirikwa / Muthenji footbridges | Foot bridges at Kadenye / Sirikwa / Muthenji footbridges installed | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.264967, 35.68218 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999412 | 100 | 1999412 | 2000000 | 588 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Install guard rails and expand the culverts by construction a box culvert.
6946 | Infrastructure, Development & Maintenance | Installation of Streetlights in Sirikwa ward | To improve lighting and safety through installation of solar streetlights at Sirikwa ward | Solar streetlights installed at Sirikwa ward | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.289543, 35.636241 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 4400000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988254 | 99.7 | 3988254 | 3999600 | 11746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is partially functional, builbs and sensors need to be repaired.
6947 | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | To install foot bridges at Kadenye / Sirikwa / Muthenji footbridges | Foot bridges at Kadenye / Sirikwa / Muthenji footbridges installed | 3111504 | N/A | Kuresoi North | Sirikwa | -0.264967, 35.68218 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999412 | 100 | 1999412 | 2000000 | 588 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Install guard rails and expand the culverts by construction a box culvert.
6948 | Infrastructure, Development & Maintenance | Installation of Streetlights in Sirikwa ward | To improve lighting and safety through installation of solar streetlights at Sirikwa ward | Solar streetlights installed at Sirikwa ward | 3111504 | N/A | Kuresoi North | Sirikwa | -0.289543, 35.636241 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 4400000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988254 | 99.7 | 3988254 | 3999600 | 11746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is partially functional, builbs and sensors need to be repaired.
6949 | Infrastructure, Development and Maintenance | Construction of Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | To construct Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County constructed | 3111504 | N/A | KURESOI SOUTH | TINET | -0.47504 35.631932 0 2400 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1951320 | 1951320 | 1951320 | Equitable | N/A | 1951320 | 0 | 1926890 | 98.7 | 1926890 | 1926890 | 24430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it was never started. Assessor remarks: Never started/established.
6950 | Infrastructure, Development & Maintenance | Construction of the Bridge | To construct the Bridge | The Bridge constructed | 3111504 | N/A | MOLO | TURI | -0.30929, 35.700715 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1805852 | 180.6 | 1805852 | 1000000 | -805852 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6951 | Infrastructure, Development & Maintenance | Grading and Gravelling of Duka Mbili - meza Road | To improve road infrastructure by grading and murraming Duka Mbili - meza Road | Duka Mbili - meza Road graded and murramed | 3111504 | N/A | MOLO | TURI | -0.313392, 35.716743 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1603775 | 80.2 | 1603775 | 1603775 | 396225 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
6952 | Infrastructure, Development & Maintenance | Grading and Gravelling of Kayole- Milimani Road | To improve road infrastructure by grading and murraming Kayole- Milimani Road | Kayole- Milimani Road graded and murramed | 3111504 | N/A | MOLO | TURI | -0.313392, 35.716743 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
6953 | Infrastructure, Development & Maintenance | Grading and Gravelling of Michatha-Eastleigh Road (2 corners) | To improve road infrastructure by grading and murraming Michatha-Eastleigh Road (2 corners) | Michatha-Eastleigh Road (2 corners) graded and murramed | 3111504 | N/A | MOLO | TURI | -0.286399, 35.74018 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491373 | 99.4 | 1491373 | 8627 | 8627 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road is good but in need of rehabilitation.
6954 | Infrastructure, Development & Maintenance | Grading and Gravelling of Turi spring-turi farmers’ nursery-Miarizim road | To improve road infrastructure by grading and murraming Turi spring-turi farmers’ nursery-Miarizim road | Turi spring-turi farmers’ nursery-Miarizim road graded and murramed | 3111504 | N/A | MOLO | TURI | -1.281229, 36.821402 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1483248 | 98.9 | 1483248 | 16752 | 16752 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: in good condition.
6955 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County | To maintain Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.289744 35.695144 2803.7 76.5999984741211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1498952 | 1498952 | 1498952 | Equitable | N/A | 1498952 | 0 | 1498952 | 100 | 1498952 | 1498952 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Due to the ongoing heavy rains, the road is adversely affected. It requires rehabilitation.
6956 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Rafiki Roads Turi Ward Molo Sub County | To maintain Spot Improvement of Rafiki Roads Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Rafiki Roads Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1457880 | 97.2 | 1457880 | 1500000 | 42120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
6957 | Infrastructure, Development and Maintenance | Construction of Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | To construct Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County constructed | 3111504 | N/A | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1951320 | 1951320 | 1951320 | Equitable | N/A | 1951320 | 0 | 1926890 | 98.7 | 1926890 | 1926890 | 24430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it was never started. Assessor remarks: Never started/established.
6958 | Infrastructure, Development & Maintenance | Grading and Gravelling of Kayole- Milimani Road | To improve road infrastructure by grading and murraming Kayole- Milimani Road | Kayole- Milimani Road graded and murramed | 3111504 | N/A | Molo | Turi | -0.313392, 35.716743 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
6959 | Grading and murraming of kiambu road | Grading and murraming of kiambu road | To improve road infrastructure by grading and murraming kiambu road | Kiambu road graded and murramed | 3111504 | N/A | Molo | Turi | -0.266688 35.739926 2554.4 13.600000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 979110 | 97.9 | 979110 | 979110 | 20890 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Newly graded again but not good during rainy season.
6960 | Grading and murraming of St. Brenden Managu road | Grading and murraming of St. Brenden Managu road | To improve road infrastructure by grading and murraming St. Brenden Managu road | St. Brenden Managu road graded and murramed | 3111504 | N/A | Molo | Turi | -0.32778, 35.741407 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1448990 | 96.6 | 1448990 | 1448990 | 51010 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
6961 | Infrastructure, Development & Maintenance | installation of culverts and construction of drainage system at kiambu | To improve drainage and road access through culvert installation at and construction of drainage system at kiambu | Culverts installed at and construction of drainage system at kiambu | 3111504 | N/A | Molo | Turi | -0.309382 35.7569 2571.8 10.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good.
6962 | Infrastructure, Development & Maintenance | Routine Maintenance of Rafiki B Roads Turi Ward | To maintain Rafiki B Roads Turi Ward in serviceable condition | Rafiki B Roads Turi Ward maintained | 3111504 | N/A | Molo | Turi | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1450960 | 96.7 | 1450960 | 1450960 | 49040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
6963 | design and installation of Viwandani highmast streetlighting | design and installation of Viwandani highmast streetlighting | To implement design and installation of viwandani highmast streetlighting for road connectivity and accessibility | design and installation of Viwandani highmast streetlighting completed | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.710361 36.433995 1907.199951171875 10.710000038146973 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6599810 | 94.3 | 6599810 | 7000000 | 400190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Working.
6964 | design and installation of Viwandani highmast streetlighting | design and installation of Viwandani highmast streetlighting | To implement design and installation of viwandani highmast streetlighting for road connectivity and accessibility | design and installation of Viwandani highmast streetlighting completed | 3111504 | N/A | Naivasha | Viwandani | -0.710361 36.433995 1907.199951171875 10.710000038146973 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6599810 | 94.3 | 6599810 | 7000000 | 400190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Working.
6965 | Purchase of land for an Acess road at Sumeek-Atebwo Primary | Purchase of land for an Acess road at Sumeek-Atebwo Primary | To acquire land for an Acess road at Sumeek-Atebwo Primary | Land for an Acess road at Sumeek-Atebwo Primary acquired | 3130101 | Acquisition of Land | RONGAI | MOSOP | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
6966 | Purchase of land for an Acess road at Sumeek-Atebwo Primary | Purchase of land for an Acess road at Sumeek-Atebwo Primary | To acquire land for an Acess road at Sumeek-Atebwo Primary | Land for an Acess road at Sumeek-Atebwo Primary acquired | 3130101 | Acquisition of Land | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
6967 | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | To improve road infrastructure by grading and murraming Lower Kapjorwa- Ketyenya Junction Road | Lower Kapjorwa- Ketyenya Junction Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.611516, 35.683798 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2000000 | 404826 | 404826 | Equitable | N/A | 404826 | 0 | 404826 | 100 | 404826 | 404826 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: 2021.
6968 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County | To maintain Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.572453 35.70533 2542.400146484375 4.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999360 | 1999360 | 1999360 | Equitable | N/A | 1999360 | 0 | 1983000 | 99.2 | 1983000 | 1999360 | 16360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: partially. Assessor remarks: road requires murraming.
6969 | Infrastructure, Development & Maintenance | Grading and Murraming of Chesoen -Tuiyobei road | To improve road infrastructure by grading and murraming Chesoen -Tuiyobei road | Chesoen -Tuiyobei road graded and murramed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.603778, 35.676228 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 947399 | 94.7 | 947399 | 947400 | 52601 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
6970 | Grading and Murraming of Kiptaragon-Comboni road | Grading and Murraming of Kiptaragon-Comboni road | To improve road infrastructure by grading and murraming Kiptaragon-Comboni road | Kiptaragon-Comboni road graded and murramed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.560058, 35.691749 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070680 | 97.3 | 1070680 | 0 | 29320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires murraming.
6971 | Grading and Murraming of TTI- Bondet Church road | Grading and Murraming of TTI- Bondet Church road | To improve road infrastructure by grading and murraming TTI- Bondet Church road | TTI- Bondet Church road graded and murramed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.56301, 35.680885 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966126 | 98.9 | 2966126 | 2966126 | 33874 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires routine maintenance and spot gravelling.
6972 | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | To improve road infrastructure by grading and murraming Lower Kapjorwa- Ketyenya Junction Road | Lower Kapjorwa- Ketyenya Junction Road graded and murramed | 4130299 | N/A | Kuresoi South | Amalo | -0.611516, 35.683798 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2000000 | 404826 | 404826 | Equitable | N/A | 404826 | 0 | 404826 | 100 | 404826 | 404826 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: 2021.
6973 | Grading and Murraming of Kiptaragon-Comboni road | Grading and Murraming of Kiptaragon-Comboni road | To improve road infrastructure by grading and murraming Kiptaragon-Comboni road | Kiptaragon-Comboni road graded and murramed | 4130299 | N/A | Kuresoi South | Amalo | -0.560058, 35.691749 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 1100000 | 1070680 | 1070680 | Equitable | N/A | 1070680 | 0 | 1070680 | 100 | 1070680 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires murraming.
6974 | Grading and Murraming of TTI- Bondet Church road | Grading and Murraming of TTI- Bondet Church road | To improve road infrastructure by grading and murraming TTI- Bondet Church road | TTI- Bondet Church road graded and murramed | 4130299 | N/A | Kuresoi South | Amalo | -0.56301, 35.680885 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 3000000 | 2966125.8 | 2966125.8 | Equitable | N/A | 2966125.8 | 0 | 2966126 | 100 | 2966126 | 2966126 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires routine maintenance and spot gravelling.
6975 | Infrastructure, Development & Maintenance | Grading and Murruming of St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County | To improve road infrastructure by grading and murraming St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County | St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County graded and murramed | 4130299 | N/A | NAKURU WEST | BARUT | -0.306306, 36.036551 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016 | 2991350 | 2991350 | 2991350 | Equitable | N/A | 2991350 | 0 | 2991350 | 100 | 2991350 | 2991350 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Nyati E.A Ltd. Assessor remarks: The road is good.
6976 | Infrastructure, Development & Maintenance | installation of barut centre highmast streetlights | To install barut centre highmast streetlights | Barut centre highmast streetlights installed | 4130299 | N/A | NAKURU WEST | BARUT | -0.32425 36.4568 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933050 | 96.7 | 1933050 | 1933050 | 66950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M.s Topal Enterprises. Assessor remarks: In good state of repair.
6977 | Infrastructure, Development & Maintenance | installation of Mwariki muungano streetlights | To install Mwariki muungano streetlights | Mwariki muungano streetlights installed | 4130299 | N/A | NAKURU WEST | BARUT | -0.3424 36.042 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599000 | 99.9 | 1599000 | 1599000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are functional.
6978 | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County | To implement drainage works at abongoloya estate in biashara ward nakuru east sub county for road connectivity and accessibility | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County completed | 4130299 | N/A | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2126583 | 236.3 | 2126583 | 900000 | -1226583 | Stalled | 0 | 100 | Recommended for terminated | 2016 | N/A | -1226583 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Recommended for terminated. % completion at stalling: 100.0%. Estimated cost to complete: KShs -1,226,583.
6979 | Infrastructure, Development & Maintenance | replacement of lights in the whole sale market | To implement replacement of lights in the whole sale market for road connectivity and accessibility | replacement of lights in the whole sale market completed | 4130299 | N/A | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6980 | Infrastructure, Development & Maintenance | installation of barut centre highmast streetlights | To install barut centre highmast streetlights | Barut centre highmast streetlights installed | 4130299 | N/A | Nakuru West | Barut | -0.32425 36.4568 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933050 | 96.7 | 1933050 | 1933050 | 66950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M.s Topal Enterprises. Assessor remarks: In good state of repair.
6981 | Infrastructure, Development & Maintenance | installation of Mwariki muungano streetlights | To install Mwariki muungano streetlights | Mwariki muungano streetlights installed | 4130299 | N/A | Nakuru West | Barut | -0.3424 36.042 0 2000 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599000 | 99.9 | 1599000 | 1599000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are functional.
6982 | Installation mof high mast streetlighting | Installation mof high mast streetlighting | To install mof high mast streetlighting | Mof high mast streetlighting installed | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1500000 | 150 | 1500000 | 1000000 | -500000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
6983 | Construction of 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | Construction of 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | To construct 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.237125, 36.167581 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498406 | 99.7 | 498406 | 498406 | 1594 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Arlington company Ltd. Assessor remarks: In good condition, inaccessible.
6984 | Infrastructure, Development and Maintenance | Grading and gravelling of Dundori access roads | To improve road infrastructure by grading and murraming Dundori access roads | Dundori access roads graded and murramed | 4130299 | N/A | BAHATI | DUNDORI | -0.26376, 36.191805 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 3200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1785904 | 81.2 | 1785904 | 1789870 | 414096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Gatemax enterprises limited. Assessor remarks: Good.
6985 | Infrastructure, Development & Maintenance | purchase and installation of culverts in Githioro / Mugwathi access roads | To procure and install culverts in Githioro / Mugwathi access roads | Culverts in Githioro / Mugwathi access roads procured and installed | 4130299 | N/A | BAHATI | DUNDORI | -0.237125, 36.167581 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/2016 | 0 | 999800 | 999800 | Equitable | N/A | 999800 | 0 | 106553 | 10.7 | 106553 | 106553 | 893247 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance.
6986 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County maintained | 4130299 | N/A | BAHATI | DUNDORI | -0.261632, 36.190737 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 988200 | 988200 | 988200 | Equitable | N/A | 988200 | 0 | 1382968 | 139.9 | 1382968 | 988200 | -394768 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
6987 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County maintained | 4130299 | N/A | BAHATI | DUNDORI | -0.261632, 36.190737 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 1488879.3 | 1488879.3 | 1488879.3 | Equitable | N/A | 1488879.3 | 0 | 1382968 | 92.9 | 1382968 | 1488879 | 105911.3 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
6988 | Infrastructure, Development and Maintenance | Grading and gravelling of Dundori access roads | To improve road infrastructure by grading and murraming Dundori access roads | Dundori access roads graded and murramed | 4130299 | N/A | Bahati | Dundori | -0.26376, 36.191805 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 3200000 | 1789870 | 1789870 | Equitable | N/A | 1789870 | 0 | 1785904 | 99.8 | 1785904 | 1789870 | 3966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Gatemax enterprises limited. Assessor remarks: Good.
6989 | Infrastructure, Development & Maintenance | purchase and installation of culverts in Githioro / Mugwathi access roads | To procure and install culverts in Githioro / Mugwathi access roads | Culverts in Githioro / Mugwathi access roads procured and installed | 4130299 | N/A | Bahati | Dundori | -0.237125, 36.167581 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/2016 | 0 | 999800 | 999800 | Equitable | N/A | 999800 | 0 | 106553 | 10.7 | 106553 | 106553 | 893247 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance.
6990 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County maintained | 4130299 | N/A | Bahati | Dundori | -0.261632, 36.190737 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 988200 | 988200 | 988200 | Equitable | N/A | 988200 | 0 | 1382968 | 139.9 | 1382968 | 988200 | -394768 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
6991 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County maintained | 4130299 | N/A | Bahati | Dundori | -0.261632, 36.190737 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 1488879.3 | 1488879.3 | 1488879.3 | Equitable | N/A | 1488879.3 | 0 | 1382968 | 92.9 | 1382968 | 1488879 | 105911.3 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
6992 | Infrastructure, Development & Maintenance | Completion of Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County | To complete Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County | Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County completed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | -0.591883, 36.26228 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 19/20 | 1990000 | 1990000 | 1990000 | Equitable | N/A | 1990000 | 0 | 1990000 | 100 | 1990000 | 1990000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Water channels is the main problem.
6993 | Infrastructure, Development & Maintenance | Grading and Murraming of Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | To improve road infrastructure by grading and murraming Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County graded and murramed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1999950 | 1999950 | 1999950 | Equitable | N/A | 1999950 | 0 | 716255 | 35.8 | 716255 | 1283695 | 1283695 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6994 | Infrastructure, Development & Maintenance | Grading and Murraming of Thome, Cedar,Sogoroi feeder roads | To improve road infrastructure by grading and murraming Thome, Cedar,Sogoroi feeder roads | Thome, Cedar,Sogoroi feeder roads graded and murramed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | -0.607279, 36.274573 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 19-20 | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1472275 | 147.2 | 1472275 | 1000000 | -472275 | Stalled | 75 | 100 | terminated | 2017 | N/A | -472275 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Work done well.
6995 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County | To maintain Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County in serviceable condition | Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998000 | 99.8 | 998000 | 998000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6996 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County | To maintain Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County in serviceable condition | Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1491000 | 1491000 | 1491000 | Equitable | N/A | 1491000 | 0 | 1491000 | 100 | 1491000 | 1491000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
6997 | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County maintained | 4130299 | N/A | MOLO | ELBURGON | -0.302023, 35.813376 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1298411 | 86.6 | 1298411 | 200589 | 201589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6998 | Routine Maintenance and Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County maintained | 4130299 | N/A | MOLO | ELBURGON | -0.302023, 35.813376 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1099912 | 73.3 | 1099912 | 400088 | 400088 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
6999 | Construction of drainage system at Eastleigh/ Jerusalem | Construction of drainage system at Eastleigh/ Jerusalem | To construct drainage system at Eastleigh/ Jerusalem | Drainage system at Eastleigh/ Jerusalem constructed | 4130299 | N/A | MOLO | ELBURGON | -0.288188 35.816137 2443.8 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999990 | 100 | 999990 | 77950 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7000 | Infrastructure, Development & Maintenance | Grading and Murraming of Njeru - Gwachati road | To improve road infrastructure by grading and murraming Njeru - Gwachati road | Njeru - Gwachati road graded and murramed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.594433, 36.110205 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 1850794 | 52.9 | 1850794 | 3500000 | 1649206 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor state. Road needs Routine Maintenance.
7001 | grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | To improve road accessibility by grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | And sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) graded | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.658063, 36.11461 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes but maintanance needed. Viable: Yes. Assessor remarks: Needs renovation.
7002 | Infrastructure, Development & Maintenance | Grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | To improve road accessibility by grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | And spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) graded | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.583917 36.112665 2077.4 5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596052 | 99.9 | 3596052 | 2848 | 3948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7003 | Infrastructure, Development & Maintenance | Grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | To improve road accessibility by grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | Sport gravelling of Munada Kanorero - Munyaka Road (2015/16) graded | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.601874 36.106719 2106.511 0.8220000267028809 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent attention.
7004 | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge (2015/16) | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge (2015/16) | To implement kanorero - quarry bridge -construction of kanorero -quarry bridge (2015/16) for road connectivity and accessibility | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge (2015/16) completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.609053, 36.103382 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3390606 | 99.7 | 3390606 | 3390996 | 9394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
7005 | Infrastructure, Development & Maintenance | purchase and installation of Kiptangwany culverts | To procure and install Kiptangwany culverts | Kiptangwany culverts procured and installed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.56309, 36.117448 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2326985 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 6424879 | 279.3 | 6424879 | 2300000 | -4124879 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but requires Maintenance.
7006 | Infrastructure, Development & Maintenance | Grading and Murraming of Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | To improve road infrastructure by grading and murraming Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County graded and murramed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1999950 | 1283694.85 | 1283694.85 | Equitable | N/A | 1283694.85 | 0 | 716255 | 55.8 | 716255 | 1283695 | 567439.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7007 | Grading and Murraming of Highway - Mbaruk Road | Grading and Murraming of Highway - Mbaruk Road | To improve road infrastructure by grading and murraming Highway - Mbaruk Road | Highway - Mbaruk Road graded and murramed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | -0.267019, 36.193393 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 20/21 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1351440 | 96.5 | 1351440 | 1400000 | 48560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Need rehabilitation.
7008 | Infrastructure, Development & Maintenance | Grading and Murraming of Morgen to Muraimo Road | To improve road infrastructure by grading and murraming Morgen to Muraimo Road | Morgen to Muraimo Road graded and murramed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | -0.616511, 36.2546 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21-22 | 1998220 | 1998220 | 1998220 | Equitable | N/A | 1998220 | 0 | 1893424 | 94.8 | 1893424 | 1893450 | 104796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Yes. Contractor: Unspecified. Assessor remarks: Bad state of road.
7009 | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County maintained | 4130299 | N/A | Molo | Elburgon | -0.302023, 35.813376 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1298411 | 86.6 | 1298411 | 200589 | 201589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7010 | Construction of drainage system at Eastleigh/ Jerusalem | Construction of drainage system at Eastleigh/ Jerusalem | To construct drainage system at Eastleigh/ Jerusalem | Drainage system at Eastleigh/ Jerusalem constructed | 4130299 | N/A | Molo | Elburgon | -0.288188 35.816137 2443.8 11.800000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999990 | 100 | 999990 | 77950 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7011 | grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | To improve road accessibility by grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | And sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) graded | 4130299 | N/A | Gilgil | Elementaita | -0.658063, 36.11461 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes but maintanance needed. Viable: Yes. Assessor remarks: Needs renovation.
7012 | Infrastructure, Development & Maintenance | Grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | To improve road accessibility by grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | And spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) graded | 4130299 | N/A | Gilgil | Elementaita | -0.583917 36.112665 2077.4 5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3600000 | 3598900 | 3598900 | Equitable | N/A | 3598900 | 0 | 3596052 | 99.9 | 3596052 | 2848 | 2848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7013 | Infrastructure, Development & Maintenance | Grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | To improve road accessibility by grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | Sport gravelling of Munada Kanorero - Munyaka Road (2015/16) graded | 4130299 | N/A | Gilgil | Elementaita | -0.601874 36.106719 2106.511 0.8220000267028809 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent attention.
7014 | Drainage Works at Lakeview Estate (Maragoli Road) | Drainage Works at Lakeview Estate (Maragoli Road) | To implement drainage works at lakeview estate (maragoli road) for road connectivity and accessibility | Drainage Works at Lakeview Estate (Maragoli Road) completed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.302897, 36.073214 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/2019 | 3999680 | 3999680 | 3999680 | Equitable | N/A | 3999680 | 0 | 3999680 | 100 | 3999680 | 3999680 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dentritic construction company. Assessor remarks: In good condition.
7015 | Infrastructure, Development & Maintenance | re-tarmacking of 350 metres othaya road racecourse estate | To implement re-tarmacking of 350 metres othaya road racecourse estate for road connectivity and accessibility | re-tarmacking of 350 metres othaya road racecourse estate completed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.273198, 36.105845 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2017/18 | 3000000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 2921344 | 91.3 | 2921344 | 8839 | 278656 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7016 | Construction of 3 no motorbike sheds in flamingo ward | Construction of 3 no motorbike sheds in flamingo ward | To construct 3 no motorbike sheds in flamingo ward | 3 no motorbike sheds in flamingo ward constructed | 4130299 | N/A | Nakuru East | Flamingo | -0.302169, 36.072709 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 925920 | 92.6 | 925920 | 42460 | 74080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bemiah ventures. Assessor remarks: In use.
7017 | Drainage Works at Lakeview Estate (Maragoli Road) | Drainage Works at Lakeview Estate (Maragoli Road) | To implement drainage works at lakeview estate (maragoli road) for road connectivity and accessibility | Drainage Works at Lakeview Estate (Maragoli Road) completed | 4130299 | N/A | Nakuru East | Flamingo | -0.302897, 36.073214 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/2019 | 3999680 | 3999680 | 3999680 | Equitable | N/A | 3999680 | 0 | 3999680 | 100 | 3999680 | 3999680 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dentritic construction company. Assessor remarks: In good condition.
7018 | Infrastructure, Development & Maintenance | Grading and Murraming of Kambi Somali roads | To improve road infrastructure by grading and murraming Kambi Somali roads | Kambi Somali roads graded and murramed | 4130299 | N/A | GILGIL | GILGIL | -0.50936, 36.317204 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498425 | 99.9 | 1498425 | 575 | 1575 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yed. Assessor remarks: Need culverts, drainage and maintainance.
7019 | Infrastructure, Development & Maintenance | Grading and Murraming of Karura Dispensary road | To improve road infrastructure by grading and murraming Karura Dispensary road | Karura Dispensary road graded and murramed | 4130299 | N/A | GILGIL | GILGIL | -0.509335 36.317226 2005.0999755859375 5.428999900817871 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Elias company limited. Assessor remarks: Road needs maintainance.
7020 | Infrastructure, Development & Maintenance | Grading and Murraming of Kigogo Majimoto roads | To improve road infrastructure by grading and murraming Kigogo Majimoto roads | Kigogo Majimoto roads graded and murramed | 4130299 | N/A | GILGIL | GILGIL | -0.50936, 36.317204 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 575 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yed. Assessor remarks: Need culverts, drainage and maintainance.
7021 | Infrastructure, Development & Maintenance | grading of Elina road at Kikopey trading centre | To improve road accessibility by grading Elina road at Kikopey trading centre | Elina road at Kikopey trading centre graded | 4130299 | N/A | GILGIL | GILGIL | -0.475429, 36.295122 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1979975 | 99 | 1979975 | 1979975 | 20025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Githioro highlands and contractors limited. Assessor remarks: Requires routine maintainance and installation of culverts.
7022 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | GILGIL | -0.486773 36.296013 1900.35205078125 10.619999885559082 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2499500 | 2499500 | 2499500 | Equitable | N/A | 2499500 | 0 | 2499500 | 100 | 2499500 | 2499500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dakes construction. Assessor remarks: Requires routine maintainance and installation of culverts.
7023 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | GILGIL | -0.486773 36.296013 1900.35205078125 10.619999885559082 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3974000 | 3974000 | 3974000 | Equitable | N/A | 3974000 | 0 | 3974000 | 100 | 3974000 | 3974000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dakes construction. Assessor remarks: Requires routine maintainance and installation of culverts.
7024 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | GILGIL | -0.486773 36.296013 1900.35205078125 10.619999885559082 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1993576 | 1993576 | 1993576 | Equitable | N/A | 1993576 | 0 | 1993576 | 100 | 1993576 | 1993576 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dakes construction. Assessor remarks: Requires routine maintainance and installation of culverts.
7025 | Construction of bodaboda sheds | Construction of bodaboda sheds | To construct bodaboda sheds | Bodaboda sheds constructed | 4130299 | N/A | Gilgil | Gilgil | -0.504777 36.328234 1989.4000244140625 15.168999671936035 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 828680 | 82.9 | 828680 | 600000 | 171320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cider collection. Assessor remarks: Functional but needs rehabilitation and extensive drainage works and additional sheds.
7026 | Construction of 7No. Motor Cycle Sheds at Nakuru County Headquarter | Construction of 7No. Motor Cycle Sheds at Nakuru County Headquarter | To construct 7No. Motor Cycle Sheds at Nakuru County Headquarter | 7No. Motor Cycle Sheds at Nakuru County Headquarter constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2104460.4 | 2104460.4 | 2104460.4 | Equitable | N/A | 2104460.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7027 | Infrastructure, Development & Maintenance | Construction of Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | To construct Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2547151.2 | 2547151.2 | 2547151.2 | Equitable | N/A | 2547151.2 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7028 | construction of Kio bridge in kihingo ward | construction of Kio bridge in kihingo ward | To construct Kio bridge in kihingo ward | Kio bridge in kihingo ward constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 6978545 | 697.9 | 6978545 | 4000000 | -5978545 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7029 | Infrastructure, Development & Maintenance | Construction of Lorry Park | To construct Lorry Park | Lorry Park constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 6978545 | 69.8 | 6978545 | 10000000 | 3021455 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7030 | Infrastructure, Development & Maintenance | Construction of Motorable and Foot-Bridges | To construct Motorable and Foot-Bridges | Motorable and Foot-Bridges constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 70000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 6978545 | 69.8 | 6978545 | 15000000 | 3021455 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7031 | Infrastructure, Development and Maintenance | Construction of Storm water Drains | To construct Storm water Drains | Storm water Drains constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 40000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 6978545 | 69.8 | 6978545 | 3021455 | 3021455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7032 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) | To construct & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) | & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 180000000 | 27212000 | 27212000 | Equitable | N/A | 27212000 | 0 | 27212000 | 100 | 27212000 | 7500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7033 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) | To construct & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) | & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 180000001 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 6000000 | 100 | 6000000 | 7500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7034 | Infrastructure, Development & Maintenance | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county | To implement improvement of mashambani matatu stage in biashara ward in nakuru east sub county for road connectivity and accessibility | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 4706955 | 4706955 | 4706955 | Equitable | N/A | 4706955 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7035 | Infrastructure, Development & Maintenance | installation of highmast streetlighting at Greenstead and Barnabas | To improve security lighting through high mast floodlight installation at streetlighting at Greenstead and Barnabas | High mast floodlight installed at streetlighting at Greenstead and Barnabas | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 9793000 | 244.8 | 9793000 | 9793000 | -5793000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7036 | Infrastructure, Development & Maintenance | Periodic and routine Maintenance of Menengai Drive to capita Hill Road (1km) in Menengai Ward Nakuru East Sub County | To implement periodic and routine maintenance of menengai drive to capita hill road (1km) in menengai ward nakuru east sub county for road connectivity and accessibility | Periodic and routine Maintenance of Menengai Drive to capita Hill Road (1km) in Menengai Ward Nakuru East Sub County completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 10620032 | 10620032 | 10620032 | Equitable | N/A | 10620032 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7037 | Infrastructure, Development and Maintenance | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | To undertake the proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 18204565 | 2427.3 | 18204565 | 0 | -17454565 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7038 | Infrastructure, Development & Maintenance | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | To undertake the proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 4619070 | 1316020 | 1316020 | Equitable | N/A | 1316020 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7039 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County | Proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998919 | 2998919 | 2998919 | Equitable | N/A | 2998919 | 0 | 5237600 | 174.6 | 5237600 | 5237600 | -2238681 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7040 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4027926 | 860526 | 860526 | Equitable | N/A | 860526 | 0 | 5237600 | 608.7 | 5237600 | 5237600 | -4377074 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7041 | Infrastructure, Development & Maintenance | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | To undertake the proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 6029900 | 492788.4 | 492788.4 | Equitable | N/A | 492788.4 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7042 | Infrastructure, Development & Maintenance | Provision for Purchase of Fire Engine (1No) | To implement provision for purchase of fire engine (1no) for road connectivity and accessibility | Provision for Purchase of Fire Engine (1No) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 100000000 | 5870000 | 5870000 | Equitable | N/A | 5870000 | 0 | 49500000 | 843.3 | 49500000 | 5870000 | -43630000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7043 | Infrastructure, Development & Maintenance | Rehabilitation of bus park and other Parking bays | To rehabilitate bus park and other Parking bays to restore functionality | Bus park and other Parking bays rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 44000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 1537405 | 15.4 | 1537405 | 1537405 | 8462595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7044 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Excavator 4No) | To rehabilitate Rural Road(Provision for purchase of Excavator 4No) to restore functionality | Rural Road(Provision for purchase of Excavator 4No) rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 56000000 | 50967870.55 | 50967870.55 | Equitable | N/A | 50967870.55 | 0 | 49500000 | 97.1 | 49500000 | 5870000 | 1467870.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7045 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Rollers 4No) | To rehabilitate Rural Road(Provision for purchase of Rollers 4No) to restore functionality | Rural Road(Provision for purchase of Rollers 4No) rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 32000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 49500000 | 2475 | 49500000 | 5870000 | -47500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7046 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 852509.2 | 852509.2 | Equitable | N/A | 852509.2 | 0 | 1643700 | 192.8 | 1643700 | 1643700 | -791190.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7047 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County | To maintain Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County in serviceable condition | Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999660 | 1999660 | 1999660 | Equitable | N/A | 1999660 | 0 | 5237600 | 261.9 | 5237600 | 5237600 | -3237940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7048 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County | To maintain Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County in serviceable condition | Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1989963 | 1989963 | 1989963 | Equitable | N/A | 1989963 | 0 | 5237600 | 263.2 | 5237600 | 5237600 | -3247637 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7049 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County | To maintain Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County in serviceable condition | Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 8492708 | 5454396 | 5454396 | Equitable | N/A | 5454396 | 0 | 5237600 | 96 | 5237600 | 5237600 | 216796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7050 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County | To maintain Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County in serviceable condition | Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2484000 | 2484000 | 2484000 | Equitable | N/A | 2484000 | 0 | 5237600 | 210.9 | 5237600 | 5237600 | -2753600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7051 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County | To maintain Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County in serviceable condition | Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 12169900 | 5237600 | 5237600 | Equitable | N/A | 5237600 | 0 | 5237600 | 100 | 5237600 | 5237600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7052 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County | To maintain Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County in serviceable condition | Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 10504000 | 10504000 | 10504000 | Equitable | N/A | 10504000 | 0 | 5237600 | 49.9 | 5237600 | 5237600 | 5266400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7053 | Infrastructure, Development & Maintenance | Construction of motorbike sheds at dispensary,BN riders,villa,mwichiringiri and karai | To construct motorbike sheds at dispensary,BN riders,villa,mwichiringiri and karai | Motorbike sheds at dispensary,BN riders,villa,mwichiringiri and karai constructed | 4130299 | N/A | Naivasha | Hells Gate | -0.796999, 36.434324 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1115760 | 62 | 1115760 | 1800000 | 684240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project costed 1,141,720.
7054 | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | To install floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location installed | 4130299 | N/A | BAHATI | KABATINI | -0.222876, 36.1213 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2404500 | 95.4 | 2404500 | 2404800 | 115500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7055 | Routine Maintenance and Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County | Routine Maintenance and Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County | To maintain Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County in serviceable condition | Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County maintained | 4130299 | N/A | BAHATI | KABATINI | -0.229651, 36.150158 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2917980 | 2917980 | 2917980 | Equitable | N/A | 2917980 | 0 | 0 | 0 | 0 | 2914651 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes then. Viable: Yes. Contractor: Briter homes limited. Assessor remarks: Operational.
7056 | Infrastructure, Development and Maintenance | construction of Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | To construct Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward constructed | 4130299 | N/A | SUBUKIA | KABAZI | -0.23853 35.86724 2237 0 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1757447 | 35.1 | 1757447 | 1209627 | 3242553 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details available. Assessor remarks: Requires additional ecd classroom, toilets and kitchen.
7057 | design and construction of Boda boda shades at Kabazi centre and solai | design and construction of Boda boda shades at Kabazi centre and solai | To design and construct Boda boda shades at Kabazi centre and solai | Boda boda shades at Kabazi centre and solai designed and constructed | 4130299 | N/A | SUBUKIA | KABAZI | -0.077876, 36.170985 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 993122 | 99.3 | 993122 | 993122 | 6878 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
7058 | Infrastructure, Development & Maintenance | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch | To implement design and installation highmast streetlights at kabazi, solai and kipngochoch for road connectivity and accessibility | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch completed | 4130299 | N/A | SUBUKIA | KABAZI | -0.152618, 36.074977 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497715 | 99.8 | 1497715 | 1497715 | 2285 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
7059 | Infrastructure, Development & Maintenance | Baraka twin bridge in Kamara Ward Kuresoi South Sub County : 1200mm - 1line | To implement baraka twin bridge in kamara ward kuresoi south sub county : 1200mm - 1line for road connectivity and accessibility | Baraka twin bridge in Kamara Ward Kuresoi South Sub County : 1200mm - 1line completed | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.172694 35.679614 2519.9 48.900001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs concrete fence.
7060 | grading and levelling of Twinpik - Jogoo road | grading and levelling of Twinpik - Jogoo road | To improve road accessibility by grading and levelling of Twinpik - Jogoo road | And levelling of Twinpik - Jogoo road graded | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.17825 35.711258 2501.3 4.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491536 | 99.4 | 1491536 | 8464 | 8464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
7061 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County | To maintain Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.1583 35.693597 2533.000244140625 63.867000579833984 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2997672 | 2997672 | 2997672 | Equitable | N/A | 2997672 | 0 | 2997672 | 100 | 2997672 | 2997672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
7062 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County | To maintain Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County in serviceable condition | Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County maintained | 4130299 | N/A | NAKURU WEST | KAPKURES | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2813580 | 2813580 | 2813580 | Equitable | N/A | 2813580 | 0 | 2813580 | 100 | 2813580 | 2813580 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7063 | Construction of Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | Construction of Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | To construct Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County constructed | 4130299 | N/A | NAKURU WEST | KAPTEMBWO | -0.300876, 36.041345 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019 | 1999840 | 202803 | 202803 | Equitable | N/A | 202803 | 0 | 202803 | 100 | 202803 | 202803 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it reduced flooding. Contractor: Warehouse construction ltd. Assessor remarks: Needs unclogging.
7064 | Infrastructure, Development & Maintenance | Design and construction of Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road | To design and construct Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road | Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road designed and constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.54442, 35.702437 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 1999982 | 18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7065 | Infrastructure, Development and Maintenance | Grading and murraming of Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | To improve road infrastructure by grading and murraming Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road graded and murramed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.303966, 36.082876 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11600000 | 10802091 | 10802091 | Equitable | N/A | 10802091 | 0 | 10530782 | 97.5 | 10530782 | 10530782 | 271309 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
7066 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.460018 35.694096 0 899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1998620 | 1998620 | 1998620 | Equitable | N/A | 1998620 | 0 | 1998620 | 100 | 1998620 | 1998620 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7067 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.460018 35.694096 0 899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1998950 | 218858.45 | 218858.45 | Equitable | N/A | 218858.45 | 0 | 1780092 | 813.4 | 1780092 | 218858 | -1561233.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7068 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.460018 35.694096 0 899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2993600 | 2993600 | 2993600 | Equitable | N/A | 2993600 | 0 | 2947251 | 98.5 | 2947251 | 46349 | 46349 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7069 | Infrastructure, Development & Maintenance | Grading and gravelling of Keringet - Ndabidit Road | To improve road infrastructure by grading and murraming Keringet - Ndabidit Road | Keringet - Ndabidit Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.43114, 35.688835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 950681 | 55.9 | 950681 | 950681 | 749319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7070 | Infrastructure, Development & Maintenance | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) | To implement murraming, culverts installation,grading heshima to menengai road (kiamaina roads) for road connectivity and accessibility | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) completed | 4130299 | N/A | BAHATI | KIAMAINA | -0.242741 36.113229 1940.9000244140625 21.8700008392334 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 1237275 | 1237275 | 1237275 | Equitable | N/A | 1237275 | 0 | 1236769 | 100 | 1236769 | 1237275 | 506 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires marking.
7071 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County | To undertake the proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County | Proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County implemented | 4130299 | N/A | NJORO | KIHINGO | -0.433671, 35.973471 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019 | 1799973 | 1799973 | 1799973 | Equitable | N/A | 1799973 | 0 | 1799973 | 100 | 1799973 | 1799973 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7072 | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | To maintain Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County in serviceable condition | Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | KIHINGO | -0.464663, 35.987248 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2115840 | 2115840 | 2115840 | Equitable | N/A | 2115840 | 0 | 2115840 | 100 | 2115840 | 2115840 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
7073 | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | To improve the condition of and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | And Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County improved | 4130299 | N/A | NJORO | KIHINGO | -0.397138 35.959772 2227.2000000000003 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1988356 | 1988356 | 1988356 | Equitable | N/A | 1988356 | 0 | 1988356 | 100 | 1988356 | 1988356 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7074 | grading and murraming of Kio - Kihonge Road | grading and murraming of Kio - Kihonge Road | To improve road infrastructure by grading and murraming Kio - Kihonge Road | Kio - Kihonge Road graded and murramed | 4130299 | N/A | NJORO | KIHINGO | -0.42804 35.966713 2277.300048828125 27.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3190965 | 3190965 | Equitable | N/A | 3190965 | 0 | 3190965 | 100 | 3190965 | 3190965 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7075 | Infrastructure, Development & Maintenance | grading and murraming of Wendani - mutitu road (ndeffo) | To improve road infrastructure by grading and murraming Wendani - mutitu road (ndeffo) | Wendani - mutitu road (ndeffo) graded and murramed | 4130299 | N/A | NJORO | KIHINGO | -0.483175, 35.996643 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1854672 | 92.7 | 1854672 | 1854672 | 145328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: At that time. Viable: That time it met. Assessor remarks: Bush clearing, grading murraming and compaction required.
7076 | Infrastructure, Development & Maintenance | grading and murraming of Emitik - Gikamba road | To improve road infrastructure by grading and murraming Emitik - Gikamba road | Emitik - Gikamba road graded and murramed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.623375, 35.608362 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 0 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3972828 | 99.3 | 3972828 | 3979032 | 27172 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes but needs not met. Assessor remarks: Need concrete road.
7077 | Infrastructure, Development & Maintenance | grading and murraming of irector - Lel Banga Road | To improve road infrastructure by grading and murraming irector - Lel Banga Road | Irector - Lel Banga Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.576235, 35.58879 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 4000000 | 211512.5 | 211512.5 | Equitable | N/A | 211512.5 | 0 | 988500 | 467.3 | 988500 | 211513 | -776987.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is good.
7078 | grading and murraming of K.T.D.A - Riprip Road | grading and murraming of K.T.D.A - Riprip Road | To improve road infrastructure by grading and murraming K.T.D.A - Riprip Road | K.T.D.A - Riprip Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.561157, 35.592887 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3568147 | 89.2 | 3568147 | 3568147 | 431853 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good.
7079 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County | To maintain Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.598075 35.639577 2372.7999999999997 59.900001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 4999600 | 4999600 | Equitable | N/A | 4999600 | 0 | 1332100 | 26.6 | 1332100 | 1332100 | 3667500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and needs met. Assessor remarks: Functional.
7080 | Grading, Culverts and Murraming of Tiriyta Roads | Grading, Culverts and Murraming of Tiriyta Roads | To implement grading, culverts and murraming of tiriyta roads for road connectivity and accessibility | Grading, Culverts and Murraming of Tiriyta Roads completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.377203, 35.505747 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2490077 | 83 | 2490077 | 3000000 | 509923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
7081 | Infrastructure, Development & Maintenance | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County | To implement grading, murraming and culverts for korongo - motogir road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2497065.6 | 2497065.6 | 2497065.6 | Equitable | N/A | 2497065.6 | 0 | 2480265 | 99.3 | 2480265 | 2480265 | 16800.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7082 | Infrastructure, Development & Maintenance | Gravelling of factory lithia road | To implement gravelling of factory lithia road for road connectivity and accessibility | Gravelling of factory lithia road completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.325895, 35.49856 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2989000 | 99.6 | 2989000 | 2989000 | 11000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.it is impassable during rainy season.
7083 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3999854 | 3999854 | 3999854 | Equitable | N/A | 3999854 | 0 | 3971350 | 99.3 | 3971350 | 3971350 | 28504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7084 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998841.25 | 2998841.25 | 2998841.25 | Equitable | N/A | 2998841.25 | 0 | 2970080 | 99 | 2970080 | 2970080 | 28761.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7085 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kibaraa road works in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999561 | 1999561 | 1999561 | Equitable | N/A | 1999561 | 0 | 1999561 | 100 | 1999561 | 1999561 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7086 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Kongoi - Bochege road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kongoi - bochege road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kongoi - Bochege road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1498604 | 1498604 | 1498604 | Equitable | N/A | 1498604 | 0 | 1348714 | 90 | 1348714 | 1498604 | 149890 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7087 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Korabariet Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for korabariet road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Korabariet Road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1499316.24 | 1499316.24 | 1499316.24 | Equitable | N/A | 1499316.24 | 0 | 1499316 | 100 | 1499316 | 1499316 | 0.24 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7088 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Ong'ira - Chorwa Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for ong'ira - chorwa road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Ong'ira - Chorwa Road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999501.18 | 1999501.18 | 1999501.18 | Equitable | N/A | 1999501.18 | 0 | 1999501 | 100 | 1999501 | 1999501 | 0.18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7089 | Infrastructure, Development & Maintenance | Construction and Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) | To construct and Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) | And Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) constructed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.297692, 36.080703 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 6400000 | 6400000 | 6400000 | Equitable | N/A | 6400000 | 0 | 6219047 | 97.2 | 6219047 | 6400000 | 180953 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs maintenance.
7090 | Infrastructure, Development & Maintenance | Rehabilitation of Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County | To rehabilitate Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County to restore functionality | Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County rehabilitated | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.301853, 36.084754 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | June 2020 | 2999641 | 545107.05 | 545107.05 | Equitable | N/A | 545107.05 | 0 | 545107 | 100 | 545107 | 545107 | 0.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in use.
7091 | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | To install floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location installed | 4130299 | N/A | Bahati | Kabatini | -0.222876, 36.1213 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2404500 | 95.4 | 2404500 | 2404800 | 115500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7092 | Infrastructure, Development and Maintenance | construction of Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | To construct Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward constructed | 4130299 | N/A | Subukia | Kabazi | -0.23853 35.86724 2237 0 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 3002074 | 3002074 | Equitable | N/A | 3002074 | 0 | 1757447 | 58.5 | 1757447 | 1209627 | 1244627 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details available. Assessor remarks: Requires additional ecd classroom, toilets and kitchen.
7093 | design and construction of Boda boda shades at Kabazi centre and solai | design and construction of Boda boda shades at Kabazi centre and solai | To design and construct Boda boda shades at Kabazi centre and solai | Boda boda shades at Kabazi centre and solai designed and constructed | 4130299 | N/A | Subukia | Kabazi | -0.077876, 36.170985 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 1000000 | 993122 | 993122 | Equitable | N/A | 993122 | 0 | 993122 | 100 | 993122 | 993122 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
7094 | Infrastructure, Development & Maintenance | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch | To implement design and installation highmast streetlights at kabazi, solai and kipngochoch for road connectivity and accessibility | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch completed | 4130299 | N/A | Subukia | Kabazi | -0.152618, 36.074977 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497715 | 99.8 | 1497715 | 1497715 | 2285 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
7095 | grading and levelling of Twinpik - Jogoo road | grading and levelling of Twinpik - Jogoo road | To improve road accessibility by grading and levelling of Twinpik - Jogoo road | And levelling of Twinpik - Jogoo road graded | 4130299 | N/A | Kuresoi North | Kamara | -0.17825 35.711258 2501.3 4.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491536 | 99.4 | 1491536 | 8464 | 8464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
7096 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County | To maintain Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kamara | -0.1583 35.693597 2533.000244140625 63.867000579833984 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2997672 | 2997672 | 2997672 | Equitable | N/A | 2997672 | 0 | 2997672 | 100 | 2997672 | 2997672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
7097 | Infrastructure, Development and Maintenance | Grading and murraming of Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | To improve road infrastructure by grading and murraming Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road graded and murramed | 4130299 | N/A | Kuresoi South | Keringet | -0.303966, 36.082876 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11600000 | 10802091 | 10802091 | Equitable | N/A | 10802091 | 0 | 10530782 | 97.5 | 10530782 | 10530782 | 271309 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
7098 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Keringet | -0.460018 35.694096 0 899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2993600 | 2993600 | 2993600 | Equitable | N/A | 2993600 | 0 | 2947251 | 98.5 | 2947251 | 46349 | 46349 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7099 | Infrastructure, Development & Maintenance | Grading and gravelling of Keringet - Ndabidit Road | To improve road infrastructure by grading and murraming Keringet - Ndabidit Road | Keringet - Ndabidit Road graded and murramed | 4130299 | N/A | Kuresoi South | Keringet | -0.43114, 35.688835 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1700000 | 950681 | 950681 | Equitable | N/A | 950681 | 0 | 950681 | 100 | 950681 | 950681 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7100 | Infrastructure, Development & Maintenance | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) | To implement murraming, culverts installation,grading heshima to menengai road (kiamaina roads) for road connectivity and accessibility | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) completed | 4130299 | N/A | Bahati | Kiamaina | -0.242741 36.113229 1940.9000244140625 21.8700008392334 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 1237275 | 1237275 | 1237275 | Equitable | N/A | 1237275 | 0 | 1236769 | 100 | 1236769 | 1237275 | 506 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires marking.
7101 | grading and murraming of Kio - Kihonge Road | grading and murraming of Kio - Kihonge Road | To improve road infrastructure by grading and murraming Kio - Kihonge Road | Kio - Kihonge Road graded and murramed | 4130299 | N/A | Njoro | Kihingo | -0.42804 35.966713 2277.300048828125 27.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3190965 | 3190965 | Equitable | N/A | 3190965 | 0 | 3190965 | 100 | 3190965 | 3190965 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7102 | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | To maintain Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County in serviceable condition | Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Kihingo | -0.464663, 35.987248 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2115840 | 2115840 | 2115840 | Equitable | N/A | 2115840 | 0 | 2115840 | 100 | 2115840 | 2115840 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
7103 | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | To improve the condition of and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | And Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County improved | 4130299 | N/A | Njoro | Kihingo | -0.397138 35.959772 2227.2000000000003 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1988356 | 1988356 | 1988356 | Equitable | N/A | 1988356 | 0 | 1988356 | 100 | 1988356 | 1988356 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7104 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County | To maintain Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Kiptagich | -0.598075 35.639577 2372.7999999999997 59.900001525878906 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 1332100 | 1332100 | Equitable | N/A | 1332100 | 0 | 1332100 | 100 | 1332100 | 1332100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and needs met. Assessor remarks: Functional.
7105 | Grading, Culverts and Murraming of Tiriyta Roads | Grading, Culverts and Murraming of Tiriyta Roads | To implement grading, culverts and murraming of tiriyta roads for road connectivity and accessibility | Grading, Culverts and Murraming of Tiriyta Roads completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.377203, 35.505747 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2490077 | 83 | 2490077 | 3000000 | 509923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
7106 | Infrastructure, Development & Maintenance | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County | To implement grading, murraming and culverts for korongo - motogir road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2497065.6 | 2497065.6 | 2497065.6 | Equitable | N/A | 2497065.6 | 0 | 2480265 | 99.3 | 2480265 | 2480265 | 16800.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7107 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kiptororo | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3999854 | 3999854 | 3999854 | Equitable | N/A | 3999854 | 0 | 3971350 | 99.3 | 3971350 | 3971350 | 28504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7108 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kiptororo | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998841.25 | 2998841.25 | 2998841.25 | Equitable | N/A | 2998841.25 | 0 | 2970080 | 99 | 2970080 | 2970080 | 28761.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7109 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kibaraa road works in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.407175, 35.526648 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999561 | 1999561 | 1999561 | Equitable | N/A | 1999561 | 0 | 1999561 | 100 | 1999561 | 1999561 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
7110 | Construction of Milimani bridge in Lare Ward Njoro Sub County | Construction of Milimani bridge in Lare Ward Njoro Sub County | To construct Milimani bridge in Lare Ward Njoro Sub County | Milimani bridge in Lare Ward Njoro Sub County constructed | 4130299 | N/A | NJORO | LARE | -0.392153 36.025158 2016.2 25.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2999870 | 2999870 | 2999870 | Equitable | N/A | 2999870 | 0 | 2741870 | 91.4 | 2741870 | 258000 | 258000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not equipped.
7111 | Infrastructure, Development & Maintenance | construction of soweto mbatia footbridge | To construct soweto mbatia footbridge | Soweto mbatia footbridge constructed | 4130299 | N/A | NJORO | LARE | -0.448588, 36.008315 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need rails.
7112 | Infrastructure, Development & Maintenance | grading and murraming of kware - muthiga road | To improve road infrastructure by grading and murraming kware - muthiga road | Kware - muthiga road graded and murramed | 4130299 | N/A | NJORO | LARE | -0.476343, 36.033237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498937 | 100 | 2498937 | 2000000 | 1063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
7113 | Infrastructure, Development & Maintenance | grading and murraming of Soweto - Matindi -Gathiru road | To improve road infrastructure by grading and murraming Soweto - Matindi -Gathiru road | Soweto - Matindi -Gathiru road graded and murramed | 4130299 | N/A | NJORO | LARE | -0.472562, 36.023302 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 60564 | 2 | 60564 | 60564 | 2939436 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
7114 | Infrastructure, Development & Maintenance | Grading of Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre | To improve road accessibility by grading Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre | Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre graded | 4130299 | N/A | NJORO | LARE | -0.439725, 36.015697 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 5000000 | 1826289 | 1826289 | Equitable | N/A | 1826289 | 0 | 1826289 | 100 | 1826289 | 2996141 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance and has.
7115 | Installation/laying of Cabro Blocks in London Ward Road Works | Installation/laying of Cabro Blocks in London Ward Road Works | To implement installation/laying of cabro blocks in london ward road works for road connectivity and accessibility | Installation/laying of Cabro Blocks in London Ward Road Works completed | 4130299 | N/A | NAKURU WEST | LONDON | -0.273027, 36.05145 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 7084874 | 35.4 | 7084874 | 1165540 | 12915126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
7116 | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | To undertake the proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County implemented | 4130299 | N/A | NAKURU WEST | LONDON | -0.278201, 36.073897 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 3960356 | 323656.7 | 323656.7 | Equitable | N/A | 323656.7 | 0 | 323657 | 100 | 323657 | 323657 | -0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
7117 | Rehabilitation and Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County | Rehabilitation and Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County | To rehabilitate Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County to restore functionality | Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County rehabilitated | 4130299 | N/A | NAKURU WEST | LONDON | -0.296095, 35.95845 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499500 | 100 | 2499500 | 2499500 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: The road has pot holes.
7118 | Infrastructure, Development & Maintenance | grading and murraming of Lare zone C road | To improve road infrastructure by grading and murraming Lare zone C road | Lare zone C road graded and murramed | 4130299 | N/A | Njoro | Lare | -0.476343, 36.033237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | 2020/21 | 2020/21 | 2020/21 | 2022 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1453700 | 90.9 | 1453700 | 2389250 | 146300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
7119 | Infrastructure, Development & Maintenance | Grading and murraming of Lare Zone D road | To improve road infrastructure by grading and murraming Lare Zone D road | Lare Zone D road graded and murramed | 4130299 | N/A | Njoro | Lare | -0.476343, 36.033237 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2022 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2389250 | 99.6 | 2389250 | 2389250 | 10750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
7120 | Infrastructure, Development & Maintenance | grading and murraming of Soweto - Matindi -Gathiru road | To improve road infrastructure by grading and murraming Soweto - Matindi -Gathiru road | Soweto - Matindi -Gathiru road graded and murramed | 4130299 | N/A | Njoro | Lare | -0.472562, 36.023302 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 60564 | 60564 | Equitable | N/A | 60564 | 0 | 60564 | 100 | 60564 | 60564 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
7121 | Installation/laying of Cabro Blocks in London Ward Road Works | Installation/laying of Cabro Blocks in London Ward Road Works | To implement installation/laying of cabro blocks in london ward road works for road connectivity and accessibility | Installation/laying of Cabro Blocks in London Ward Road Works completed | 4130299 | N/A | Nakuru West | London | -0.273027, 36.05145 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 8250414 | 8250414 | Equitable | N/A | 8250414 | 0 | 7084874 | 85.9 | 7084874 | 1165540 | 1165540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
7122 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County maintained | 4130299 | N/A | NAIVASHA | MAAI MAHIU | -0.979368, 36.583679 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 2225120 | 2225120 | Equitable | N/A | 2225120 | 0 | 588924 | 26.5 | 588924 | 1934900 | 1636196 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state, storm drains to be rennovated.
7123 | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County | To implement culvert installation across the ward in malewa west ward gilgil sub county for road connectivity and accessibility | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County completed | 4130299 | N/A | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3599695 | 599.9 | 3599695 | 600000 | -2999695 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for more culverts installation.
7124 | Infrastructure, Development & Maintenance | Installation of Culverts at KK Quarry Road | To improve drainage and road access through culvert installation at KK Quarry Road | Culverts installed at KK Quarry Road | 4130299 | N/A | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more installation of culverts.
7125 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County | To maintain Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County in serviceable condition | Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | MALEWA WEST | -0.702703, 36.435173 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/19 | 2593667 | 757987 | 757987 | Equitable | N/A | 757987 | 0 | 757987 | 100 | 757987 | 2593667 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7126 | Infrastructure, Development & Maintenance | construction of Kamungei bridge | To construct Kamungei bridge | Kamungei bridge constructed | 4130299 | N/A | MOLO | MARIASHONI | -0.346125, 35.818593 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 780855 | 39 | 780855 | 780855 | 1219145 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
7127 | Grading and Murraming of Black- pine Kapsinendet Road | Grading and Murraming of Black- pine Kapsinendet Road | To improve road infrastructure by grading and murraming Black- pine Kapsinendet Road | Black- pine Kapsinendet Road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.378629, 35.800637 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1793970 | 89.7 | 1793970 | 2000000 | 206030 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance to be done.
7128 | Grading and Murraming of Daraja Mungu- Chaimoto Road | Grading and Murraming of Daraja Mungu- Chaimoto Road | To improve road infrastructure by grading and murraming Daraja Mungu- Chaimoto Road | Daraja Mungu- Chaimoto Road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.359266, 35.78789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Repetitive projects.
7129 | Grading and Murraming of Kaplabos - Kwa Jack Road | Grading and Murraming of Kaplabos - Kwa Jack Road | To improve road infrastructure by grading and murraming Kaplabos - Kwa Jack Road | Kaplabos - Kwa Jack Road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997010 | 99.9 | 1997010 | 979 | 2990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7130 | Grading and Murraming of Kapsuman - Kaprop Road | Grading and Murraming of Kapsuman - Kaprop Road | To improve road infrastructure by grading and murraming Kapsuman - Kaprop Road | Kapsuman - Kaprop Road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7131 | Infrastructure, Development & Maintenance | Grading and Murraming of Kiptunga- Tertit Road | To improve road infrastructure by grading and murraming Kiptunga- Tertit Road | Kiptunga- Tertit Road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7132 | Infrastructure, Development & Maintenance | grading and murraming of Rombei road- Tuiyobei road | To improve road infrastructure by grading and murraming Rombei road- Tuiyobei road | Rombei road- Tuiyobei road graded and murramed | 4130299 | N/A | MOLO | MARIASHONI | -0.341913 35.790872 2619.225 1.9689999818801 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995060 | 99.8 | 1995060 | 1600443 | 4940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
7133 | installation of culverts at Kondamet footbidge | installation of culverts at Kondamet footbidge | To improve drainage and road access through culvert installation at Kondamet footbidge | Culverts installed at Kondamet footbidge | 4130299 | N/A | MOLO | MARIASHONI | -0.334026, 35.892891 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bridge construction was done well.
7134 | installation of culverts at Marioshoni centre | installation of culverts at Marioshoni centre | To improve drainage and road access through culvert installation at Marioshoni centre | Culverts installed at Marioshoni centre | 4130299 | N/A | MOLO | MARIASHONI | -0.370649, 35.824203 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor workmanship.
7135 | Infrastructure, Development & Maintenance | installation of culverts at Nduswa - Biston junction road | To improve drainage and road access through culvert installation at Nduswa - Biston junction road | Culverts installed at Nduswa - Biston junction road | 4130299 | N/A | MOLO | MARIASHONI | -0.363089, 35.866439 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
7136 | Infrastructure, Development & Maintenance | installation of Kapkein culvert | To install Kapkein culvert | Kapkein culvert installed | 4130299 | N/A | MOLO | MARIASHONI | -0.34134, 35.886222 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1869923 | 1869923 | 1869923 | Equitable | N/A | 1869923 | 0 | 1869923 | 100 | 1869923 | 1869923 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7137 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county | To maintain Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county in serviceable condition | Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county maintained | 4130299 | N/A | MOLO | MARIASHONI | -0.306335 35.8112 2410.2001953125 7.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 998760 | 152934.4 | 152934.4 | Equitable | N/A | 152934.4 | 0 | 845826 | 553.1 | 845826 | 152934 | -692891.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7138 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County | To maintain Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County in serviceable condition | Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County maintained | 4130299 | N/A | MOLO | MARIASHONI | -0.369206, 35.841966 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2898492 | 246617 | 246617 | Equitable | N/A | 246617 | 0 | 1491329 | 604.7 | 1491329 | 246617 | -1244712 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7139 | Routine Maintenance & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County | Routine Maintenance & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County | To maintain & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County in serviceable condition | & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County maintained | 4130299 | N/A | MOLO | MARIASHONI | -0.316734, 35.85321 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1491329.28 | 1491329.28 | 1491329.28 | Equitable | N/A | 1491329.28 | 0 | 1491329 | 100 | 1491329 | 1491329 | 0.28 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7140 | Routine Maintenance and Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | MAU NAROK | -0.601323, 36.011188 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1448144 | 1448144 | 1448144 | Equitable | N/A | 1448144 | 0 | 1448144 | 100 | 1448144 | 1468429 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes. Assessor remarks: needs improvement.
7141 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | MAU NAROK | -0.588187 36.013644 0 0 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2968440 | 1468430 | 1468430 | Equitable | N/A | 1468430 | 0 | 1468430 | 100 | 1468430 | 1468430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
7142 | Infrastructure, Development & Maintenance | Routine Maintenance of Tepesuet -Major Rop Bridge Road | To maintain Tepesuet -Major Rop Bridge Road in serviceable condition | Tepesuet -Major Rop Bridge Road maintained | 4130299 | N/A | NJORO | MAUCHE | -0.493315, 35.967238 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2020 | 606100 | 606100 | 606100 | Equitable | N/A | 606100 | 0 | 606100 | 100 | 606100 | 606100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7143 | Infrastructure, Development & Maintenance | Spot Improvement and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | To improve the condition of and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | And Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County improved | 4130299 | N/A | NJORO | MAUCHE | -0.513477, 35.962448 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2021 | 593436 | 593436 | 593436 | Equitable | N/A | 593436 | 0 | 593436 | 100 | 593436 | 593436 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
7144 | Infrastructure, Development & Maintenance | Proopsed improvement of Nakuru Blanket Road in Menengai ward Nakru East Sub County | To implement proopsed improvement of nakuru blanket road in menengai ward nakru east sub county for road connectivity and accessibility | Proopsed improvement of Nakuru Blanket Road in Menengai ward Nakru East Sub County completed | 4130299 | N/A | NAKURU EAST | MENENGAI | -0.283971, 36.116543 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1987660 | 201272 | 201272 | Equitable | N/A | 201272 | 0 | 1798568 | 893.6 | 1798568 | 201272 | -1597296 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Few flood lights were done, only at teacher's, and ranges view, no flood light in Nyamarutu.
7145 | Routine Maintenance and Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County | Routine Maintenance and Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County | To maintain Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County in serviceable condition | Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County maintained | 4130299 | N/A | NAKURU EAST | MENENGAI | -0.274942, 36.117787 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2984680 | 2984680 | 2984680 | Equitable | N/A | 2984680 | 0 | 2990484 | 100.2 | 2990484 | 2984680 | -5804 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7146 | Infrastructure, Development and Maintenance | Installation of HighMast security lights at Eden and Mercy Njeri | To improve security lighting through high mast floodlight installation at security lights at Eden and Mercy Njeri | High mast floodlight installed at security lights at Eden and Mercy Njeri | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.26736, 36.028102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2023/24 | 6500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5475750 | 182.5 | 5475750 | 2825750 | -2475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7147 | Routine Maintenance and Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County | Routine Maintenance and Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County | To maintain Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County maintained | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.151362 36.01104 1764.7 19.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1442638 | 1442638 | 1442638 | Equitable | N/A | 1442638 | 0 | 1442638 | 100 | 1442638 | 2389600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7148 | Routine Maintenance and Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County | Routine Maintenance and Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County | To maintain Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County maintained | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.171907, 36.011055 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2389600 | 2389600 | 2389600 | Equitable | N/A | 2389600 | 0 | 2389600 | 100 | 2389600 | 2389600 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: 2018. Assessor remarks: Not working needs repair.
7149 | Infrastructure, Development & Maintenance | Drainage Works at Molo Market | To implement drainage works at molo market for road connectivity and accessibility | Drainage Works at Molo Market completed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | N/A | 603518 | 264413 | 264413 | Equitable | N/A | 264413 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7150 | Infrastructure, Development & Maintenance | Construction of Salgaa Lorry Park (Drainage Works) in Rongai Sub county | To construct Salgaa Lorry Park (Drainage Works) in Rongai Sub county | Salgaa Lorry Park (Drainage Works) in Rongai Sub county constructed | 4130299 | N/A | RONGAI | MOSOP | -0.206783, 35.849527 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2019 | 3975474 | 3975474 | 3975474 | Equitable | N/A | 3975474 | 0 | 3975474 | 100 | 3975474 | 3975474 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Complete.
7151 | mosop ward culverts, drainage works and bridges | mosop ward culverts, drainage works and bridges | To implement mosop ward culverts, drainage works and bridges for road connectivity and accessibility | mosop ward culverts, drainage works and bridges completed | 4130299 | N/A | RONGAI | MOSOP | -0.252383 35.840025 2064.6 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000001 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995200 | 99.8 | 1995200 | 1995200 | 4800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
7152 | Infrastructure, Development & Maintenance | murraming, drainage and culvert in Salgaa, Rigogo and Sumeek | To implement murraming, drainage and culvert in salgaa, rigogo and sumeek for road connectivity and accessibility | murraming, drainage and culvert in Salgaa, Rigogo and Sumeek completed | 4130299 | N/A | RONGAI | MOSOP | -0.266963 36.0019 2029.9000244140625 20 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 0 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
7153 | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | To construct drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | Drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road constructed | 4130299 | N/A | RONGAI | MOSOP | -0.266963 36.0019 2029.9000244140625 20 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1199200 | 75 | 1199200 | 1600000 | 400800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
7154 | Infrastructure, Development & Maintenance | design and construction of JM bridge | To design and construct JM bridge | JM bridge designed and constructed | 4130299 | N/A | GILGIL | MURINDAT | -0.41071, 36.312388 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1980250 | 99 | 1980250 | 1983716 | 19750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Josi Construction Company. Assessor remarks: Operational.
7155 | Infrastructure, Development & Maintenance | design and construction of Kiarumbwa bridge | To design and construct Kiarumbwa bridge | Kiarumbwa bridge designed and constructed | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999989 | 100 | 1999989 | 11 | 11 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7156 | Infrastructure, Development & Maintenance | Grading and Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County | To improve road accessibility by grading and Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County | And Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County graded | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999800 | 1999800 | 1999800 | Equitable | N/A | 1999800 | 0 | 1999800 | 100 | 1999800 | 1999800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7157 | Infrastructure, Development & Maintenance | Proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County | To undertake the proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County | Proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County implemented | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3999950 | 3999950 | 3999950 | Equitable | N/A | 3999950 | 0 | 1999800 | 50 | 1999800 | 3999950 | 2000150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7158 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County | To maintain Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County in serviceable condition | Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County maintained | 4130299 | N/A | GILGIL | MURINDAT | -0.482094, 36.362844 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2989320 | 244299.6 | 244299.6 | Equitable | N/A | 244299.6 | 0 | 244300 | 100 | 244300 | 244300 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Joylene Supplies & Constr. Assessor remarks: Good.
7159 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County maintained | 4130299 | N/A | Naivasha | Maai Mahiu | -0.979368, 36.583679 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 2225120 | 2225120 | Equitable | N/A | 2225120 | 0 | 588924 | 26.5 | 588924 | 1934900 | 1636196 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state, storm drains to be rennovated.
7160 | Grading and Murraming of Black- pine Kapsinendet Road | Grading and Murraming of Black- pine Kapsinendet Road | To improve road infrastructure by grading and murraming Black- pine Kapsinendet Road | Black- pine Kapsinendet Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.378629, 35.800637 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1793970 | 89.7 | 1793970 | 2000000 | 206030 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance to be done.
7161 | Grading and Murraming of Daraja Mungu- Chaimoto Road | Grading and Murraming of Daraja Mungu- Chaimoto Road | To improve road infrastructure by grading and murraming Daraja Mungu- Chaimoto Road | Daraja Mungu- Chaimoto Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.359266, 35.78789 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Repetitive projects.
7162 | Grading and Murraming of Kaplabos - Kwa Jack Road | Grading and Murraming of Kaplabos - Kwa Jack Road | To improve road infrastructure by grading and murraming Kaplabos - Kwa Jack Road | Kaplabos - Kwa Jack Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1997989 | 1997989 | Equitable | N/A | 1997989 | 0 | 1997010 | 100 | 1997010 | 979 | 979 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7163 | Grading and Murraming of Kapsuman - Kaprop Road | Grading and Murraming of Kapsuman - Kaprop Road | To improve road infrastructure by grading and murraming Kapsuman - Kaprop Road | Kapsuman - Kaprop Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7164 | Infrastructure, Development & Maintenance | Grading and Murraming of Kiptunga- Tertit Road | To improve road infrastructure by grading and murraming Kiptunga- Tertit Road | Kiptunga- Tertit Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
7165 | installation of culverts at Kondamet footbidge | installation of culverts at Kondamet footbidge | To improve drainage and road access through culvert installation at Kondamet footbidge | Culverts installed at Kondamet footbidge | 4130299 | N/A | Molo | Mariashoni | -0.334026, 35.892891 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bridge construction was done well.
7166 | installation of culverts at Marioshoni centre | installation of culverts at Marioshoni centre | To improve drainage and road access through culvert installation at Marioshoni centre | Culverts installed at Marioshoni centre | 4130299 | N/A | Molo | Mariashoni | -0.370649, 35.824203 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor workmanship.
7167 | Infrastructure, Development & Maintenance | installation of culverts at Nduswa - Biston junction road | To improve drainage and road access through culvert installation at Nduswa - Biston junction road | Culverts installed at Nduswa - Biston junction road | 4130299 | N/A | Molo | Mariashoni | -0.363089, 35.866439 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
7168 | Infrastructure, Development & Maintenance | installation of Kapkein culvert | To install Kapkein culvert | Kapkein culvert installed | 4130299 | N/A | Molo | Mariashoni | -0.34134, 35.886222 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1869923 | 1869923 | 1869923 | Equitable | N/A | 1869923 | 0 | 1869923 | 100 | 1869923 | 1869923 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7169 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Mau Narok | -0.588187 36.013644 0 0 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2968440 | 1468430 | 1468430 | Equitable | N/A | 1468430 | 0 | 1468430 | 100 | 1468430 | 1468430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
7170 | Infrastructure, Development & Maintenance | Routine Maintenance of Tepesuet -Major Rop Bridge Road | To maintain Tepesuet -Major Rop Bridge Road in serviceable condition | Tepesuet -Major Rop Bridge Road maintained | 4130299 | N/A | Njoro | Mauche | -0.493315, 35.967238 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2020 | 606100 | 606100 | 606100 | Equitable | N/A | 606100 | 0 | 606100 | 100 | 606100 | 606100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7171 | Infrastructure, Development & Maintenance | Spot Improvement and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | To improve the condition of and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | And Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County improved | 4130299 | N/A | Njoro | Mauche | -0.513477, 35.962448 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2021 | 593436 | 593436 | 593436 | Equitable | N/A | 593436 | 0 | 593436 | 100 | 593436 | 593436 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
7172 | Infrastructure, Development & Maintenance | CTC - water treatment plant gravelling and murraming and culverts | To implement ctc - water treatment plant gravelling and murraming and culverts for road connectivity and accessibility | CTC - water treatment plant gravelling and murraming and culverts completed | 4130299 | N/A | Rongai | Menengai West | -0.12535 36.008185 1778.4 2.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2389600 | 2389600 | 2389600 | Equitable | N/A | 2389600 | 0 | 2321833 | 97.2 | 2321833 | 2321833 | 67767 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7173 | Infrastructure, Development & Maintenance | gravelling , compacting and drainage and murraming of Olive stage - Eden Road | To implement gravelling , compacting and drainage and murraming of olive stage - eden road for road connectivity and accessibility | gravelling , compacting and drainage and murraming of Olive stage - Eden Road completed | 4130299 | N/A | Rongai | Menengai West | -0.144707 36.007533 1806.5 56.099998474121094 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2674548 | 95.5 | 2674548 | 2896590 | 125452 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs improvement.
7174 | Infrastructure, Development and Maintenance | Installation of HighMast security lights at Eden and Mercy Njeri | To improve security lighting through high mast floodlight installation at security lights at Eden and Mercy Njeri | High mast floodlight installed at security lights at Eden and Mercy Njeri | 4130299 | N/A | Rongai | Menengai West | -0.26736, 36.028102 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2023/24 | 6500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5475750 | 182.5 | 5475750 | 2825750 | -2475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7175 | Infrastructure, Development & Maintenance | Construction of Salgaa Lorry Park (Drainage Works) in Rongai Sub county | To construct Salgaa Lorry Park (Drainage Works) in Rongai Sub county | Salgaa Lorry Park (Drainage Works) in Rongai Sub county constructed | 4130299 | N/A | Rongai | Mosop | -0.206783, 35.849527 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2019 | 3975474 | 3975474 | 3975474 | Equitable | N/A | 3975474 | 0 | 3975474 | 100 | 3975474 | 3975474 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Complete.
7176 | mosop ward culverts, drainage works and bridges | mosop ward culverts, drainage works and bridges | To implement mosop ward culverts, drainage works and bridges for road connectivity and accessibility | mosop ward culverts, drainage works and bridges completed | 4130299 | N/A | Rongai | Mosop | -0.252383 35.840025 2064.6 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000001 | 1995200 | 1995200 | Equitable | N/A | 1995200 | 0 | 1995200 | 100 | 1995200 | 1995200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
7177 | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | To construct drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | Drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road constructed | 4130299 | N/A | Rongai | Mosop | -0.266963 36.0019 2029.9000244140625 20 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1199200 | 75 | 1199200 | 1600000 | 400800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
7178 | Infrastructure, Development & Maintenance | design and construction of Kiarumbwa bridge | To design and construct Kiarumbwa bridge | Kiarumbwa bridge designed and constructed | 4130299 | N/A | Gilgil | Murindat | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999989 | 100 | 1999989 | 11 | 11 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7179 | Routine Maintenance and Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County maintained | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.74819 36.470822 2071.60009765625 4.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1974088 | 335194 | 335194 | Equitable | N/A | 335194 | 0 | 335194 | 100 | 335194 | 1974088 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
7180 | Infrastructure, Development & Maintenance | Construction of Motorcycle sheds within the ward | To construct Motorcycle sheds within the ward | Motorcycle sheds within the ward constructed | 4130299 | N/A | NAKURU EAST | NAKURU EAST | -0.296102 36.128055 1847.4000244140625 4.599999904632568 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988358 | 99.7 | 3988358 | 4000000 | 11642 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cleafield contractors limited. Assessor remarks: Project ok.
7181 | Infrastructure, Development & Maintenance | Roads maintenance within the ward | To implement roads maintenance within the ward for road connectivity and accessibility | Roads maintenance within the ward completed | 4130299 | N/A | NAKURU EAST | NAKURU EAST | -0.291608, 36.114337 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 946472.6 | 946472.6 | Equitable | N/A | 946472.6 | 0 | 3058340 | 323.1 | 3058340 | 946473 | -2111867.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Glenwood construction limited. Assessor remarks: Project ok.
7182 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Amos Arap Kangongo road | To improve road infrastructure by grading and murraming and Culverts of Amos Arap Kangongo road | And Culverts of Amos Arap Kangongo road graded and murramed | 4130299 | N/A | NJORO | NESSUIT | -0.415259, 35.949121 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999400 | 100 | 1999400 | 1999400 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
7183 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of British- Center Juu Road | To improve road infrastructure by grading and murraming and Culverts of British- Center Juu Road | And Culverts of British- Center Juu Road graded and murramed | 4130299 | N/A | NJORO | NESSUIT | -0.418358, 35.896046 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2018/19 | 2200000 | 232290 | 232290 | Equitable | N/A | 232290 | 0 | 1967711 | 847.1 | 1967711 | 10089 | -1735421 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road requires improvement, it is in poor conditions especially during the rainy season.
7184 | Grading and Murraming and Culverts of Centre Chini- timsales road | Grading and Murraming and Culverts of Centre Chini- timsales road | To improve road infrastructure by grading and murraming and Culverts of Centre Chini- timsales road | And Culverts of Centre Chini- timsales road graded and murramed | 4130299 | N/A | NJORO | NESSUIT | -0.377829, 35.911439 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999834 | 100 | 1999834 | 1999834 | 166 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation to fully operate.
7185 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Sojami- Mangwai- Recho road | To improve road infrastructure by grading and murraming and Culverts of Sojami- Mangwai- Recho road | And Culverts of Sojami- Mangwai- Recho road graded and murramed | 4130299 | N/A | NJORO | NESSUIT | -0.415259, 35.949121 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2500000 | 261733.6 | 261733.6 | Equitable | N/A | 261733.6 | 0 | 2238266 | 855.2 | 2238266 | 245178 | -1976532.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
7186 | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | To improve drainage and road access through culvert installation at Sigotik in Nessuit Ward Njoro Sub County | Culverts installed at Sigotik in Nessuit Ward Njoro Sub County | 4130299 | N/A | NJORO | NESSUIT | -0.392896 35.898763 2388.13560622558 27.98659896850586 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 973936 | 973936 | 973936 | Equitable | N/A | 973936 | 0 | 1794420 | 184.2 | 1794420 | 973936 | -820484 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
7187 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | NESSUIT | -0.416054, 35.949283 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 975149 | 97.5 | 975149 | 975212 | 24851 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
7188 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | NESSUIT | -0.416054, 35.949283 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 2037424 | 2037424 | 2037424 | Equitable | N/A | 2037424 | 0 | 2037424 | 100 | 2037424 | 2037424 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
7189 | Infrastructure, Development & Maintenance | design and construction of utafiti bridge | To design and construct utafiti bridge | Utafiti bridge designed and constructed | 4130299 | N/A | NJORO | NJORO | -0.38562 35.936234 2263.509521484375 16.58799934387207 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
7190 | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County maintained | 4130299 | N/A | NJORO | NJORO | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 780100 | 780100 | 780100 | Equitable | N/A | 780100 | 0 | 780100 | 100 | 780100 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7191 | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | To improve road infrastructure by grading and murraming Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County graded and murramed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.39393, 35.69199 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016-2017 | 2983700 | 2983700 | 2983700 | Equitable | N/A | 2983700 | 0 | 2999183 | 100.5 | 2999183 | 2983700 | -15483 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7192 | Infrastructure, Development & Maintenance | Grading and murraming of Soliat - Masaita dispensary Road | To improve road infrastructure by grading and murraming Soliat - Masaita dispensary Road | Soliat - Masaita dispensary Road graded and murramed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1891670 | 94.6 | 1891670 | 88680 | 108330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
7193 | Infrastructure, Development & Maintenance | Grading and murraming of umoja secondary - Chepkinoyo Road | To improve road infrastructure by grading and murraming umoja secondary - Chepkinoyo Road | Umoja secondary - Chepkinoyo Road graded and murramed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1994977 | 99.7 | 1994977 | 5023 | 5023 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
7194 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Kaplelach balozi masaita road | To implement gravelling and murraming of 3km of kaplelach balozi masaita road for road connectivity and accessibility | Gravelling and murraming of 3km of Kaplelach balozi masaita road completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.390357, 35.690508 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018-2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2991943 | 99.7 | 2991943 | 2991944 | 8057 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
7195 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire | To implement gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire for road connectivity and accessibility | Gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.352807, 35.604305 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018-2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2992550 | 99.8 | 2992550 | 2992551 | 7450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, just spot patches needed in some sections..
7196 | Infrastructure, Development & Maintenance | Gravelling and murraming of 6km road at Seguton to Langwenda road | To implement gravelling and murraming of 6km road at seguton to langwenda road for road connectivity and accessibility | Gravelling and murraming of 6km road at Seguton to Langwenda road completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.386155, 35.649127 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019-2020 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 4947850 | 82.5 | 4947850 | 4947850 | 1052150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Spot patches needed in some sections..
7197 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.350272 35.637452 2686 16.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1996440 | 1996440 | 1996440 | Equitable | N/A | 1996440 | 0 | 1997195 | 100 | 1997195 | 1996440 | -755 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage at some points needed., Culverts as well..
7198 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.350272 35.637452 2686 16.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691046 | 99.5 | 1691046 | 1692000 | 8954 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage at some points needed., Culverts as well..
7199 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.350272 35.637452 2686 16.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2295610 | 2295610 | 2295610 | Equitable | N/A | 2295610 | 0 | 1997195 | 87 | 1997195 | 2295610 | 298415 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage at some points needed., Culverts as well..
7200 | Routine Maintenance and Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County | Routine Maintenance and Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.391555, 35.569833 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017-2018 | 3998440 | 3998440 | 3998440 | Equitable | N/A | 3998440 | 0 | 3998440 | 100 | 3998440 | 3998440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good- spot patches on some sections..
7201 | Infrastructure, Development & Maintenance | Roads maintenance within the ward | To implement roads maintenance within the ward for road connectivity and accessibility | Roads maintenance within the ward completed | 4130299 | N/A | Nakuru East | Nakuru East | -0.291608, 36.114337 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 946472.6 | 946472.6 | Equitable | N/A | 946472.6 | 0 | 3058340 | 323.1 | 3058340 | 946473 | -2111867.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Glenwood construction limited. Assessor remarks: Project ok.
7202 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Amos Arap Kangongo road | To improve road infrastructure by grading and murraming and Culverts of Amos Arap Kangongo road | And Culverts of Amos Arap Kangongo road graded and murramed | 4130299 | N/A | Njoro | Nessuit | -0.415259, 35.949121 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999400 | 100 | 1999400 | 1999400 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
7203 | Grading and Murraming and Culverts of Centre Chini- timsales road | Grading and Murraming and Culverts of Centre Chini- timsales road | To improve road infrastructure by grading and murraming and Culverts of Centre Chini- timsales road | And Culverts of Centre Chini- timsales road graded and murramed | 4130299 | N/A | Njoro | Nessuit | -0.377829, 35.911439 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 2000000 | 1999834 | 1999834 | Equitable | N/A | 1999834 | 0 | 1999834 | 100 | 1999834 | 1999834 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation to fully operate.
7204 | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | To improve drainage and road access through culvert installation at Sigotik in Nessuit Ward Njoro Sub County | Culverts installed at Sigotik in Nessuit Ward Njoro Sub County | 4130299 | N/A | Njoro | Nessuit | -0.392896 35.898763 2388.13560622558 27.98659896850586 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 973936 | 973936 | 973936 | Equitable | N/A | 973936 | 0 | 1794420 | 184.2 | 1794420 | 973936 | -820484 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
7205 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Nessuit | -0.416054, 35.949283 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 1000000 | 975212 | 975212 | Equitable | N/A | 975212 | 0 | 975149 | 100 | 975149 | 975212 | 63 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
7206 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Nessuit | -0.416054, 35.949283 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 2037424 | 2037424 | 2037424 | Equitable | N/A | 2037424 | 0 | 2037424 | 100 | 2037424 | 2037424 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
7207 | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Njoro | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 780100 | 780100 | 780100 | Equitable | N/A | 780100 | 0 | 780100 | 100 | 780100 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7208 | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | To improve road infrastructure by grading and murraming Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County graded and murramed | 4130299 | N/A | Kuresoi North | Nyota | -0.39393, 35.69199 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016-2017 | 2983700 | 2983700 | 2983700 | Equitable | N/A | 2983700 | 0 | 2999183 | 100.5 | 2999183 | 2983700 | -15483 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7209 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Nyota | -0.350272 35.637452 2686 16.299999237060547 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1996440 | 1996440 | 1996440 | Equitable | N/A | 1996440 | 0 | 1997195 | 100 | 1997195 | 1996440 | -755 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage at some points needed., Culverts as well..
7210 | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | To construct 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County constructed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.818589 36.259024 1883.4000244140625 10.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1188257 | 1188257 | 1188257 | Equitable | N/A | 1188257 | 0 | 1188257 | 100 | 1188257 | 1188257 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes the residents are making use of it. Assessor remarks: The project need some mentainance.
7211 | Infrastructure, Development & Maintenance | Rehabilitation of Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County | To rehabilitate Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County to restore functionality | Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County rehabilitated | 4130299 | N/A | NAIVASHA | OLKARIA | -0.915222, 36.281005 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 682277 | 682277 | 682277 | Equitable | N/A | 682277 | 0 | 682277 | 100 | 682277 | 682277 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: The project long due cant find the whole information. Assessor remarks: The project is long due it not identifiable.
7212 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County maintained | 4130299 | N/A | NAIVASHA | OLKARIA | -0.838224 36.362161 1883.0999755859375 11.142999649047852 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2994784 | 1322790 | 1322790 | Equitable | N/A | 1322790 | 0 | 1034800 | 78.2 | 1034800 | 287990 | 287990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Solar light operational.
7213 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County maintained | 4130299 | N/A | NAIVASHA | OLKARIA | -0.937926 36.364853 1912.552734375 8.583000183105469 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999760 | 100 | 2999760 | 2999760 | 240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
7214 | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | To construct 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County constructed | 4130299 | N/A | Naivasha | Olkaria | -0.818589 36.259024 1883.4000244140625 10.5 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1188257 | 1188257 | 1188257 | Equitable | N/A | 1188257 | 0 | 1188257 | 100 | 1188257 | 1188257 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes the residents are making use of it. Assessor remarks: The project need some mentainance.
7215 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County maintained | 4130299 | N/A | Naivasha | Olkaria | -0.838224 36.362161 1883.0999755859375 11.142999649047852 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2994784 | 1322790 | 1322790 | Equitable | N/A | 1322790 | 0 | 1034800 | 78.2 | 1034800 | 287990 | 287990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Solar light operational.
7216 | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | To design and construct drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts designed and constructed | 4130299 | N/A | NAKURU WEST | RHONDA | -0.31665, 36.063007 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 17/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4958000 | 99.2 | 4958000 | 5000000 | 42000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
7217 | Infrastructure, Development & Maintenance | Maintance and repair projects,drainage,culverts, streetlights | To implement maintance and repair projects,drainage,culverts, streetlights for road connectivity and accessibility | Maintance and repair projects,drainage,culverts, streetlights completed | 4130299 | N/A | NAKURU WEST | RHONDA | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1649414 | 1649414 | Equitable | N/A | 1649414 | 0 | 0 | 0 | 0 | 1649414 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7218 | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | To design and construct drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts designed and constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.31665, 36.063007 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 17/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4958000 | 99.2 | 4958000 | 5000000 | 42000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
7219 | Infrastructure, Development & Maintenance | installation of floodlights | To install floodlights | Floodlights installed | 4130299 | N/A | Nakuru West | Rhonda | -0.30749, 36.065682 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 21/22 | 2000000 | 1649414 | 1649414 | Equitable | N/A | 1649414 | 0 | 5018500 | 304.3 | 5018500 | 1649414 | -3369086 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
7220 | Infrastructure, Development & Maintenance | Grading and murraming of Ronald Ngala and Mariakani road, Sondu drive, upper Lokicha road | To improve road infrastructure by grading and murraming Ronald Ngala and Mariakani road, Sondu drive, upper Lokicha road | Ronald Ngala and Mariakani road, Sondu drive, upper Lokicha road graded and murramed | 4130299 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2845813 | 94.9 | 2845813 | 2999800 | 154187 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7221 | Infrastructure, Development & Maintenance | Installation of highmast 20m at Gilanis, Pyrethrum and Ngei estate | To improve security lighting through high mast floodlight installation at 20m at Gilanis, Pyrethrum and Ngei estate | High mast floodlight installed at 20m at Gilanis, Pyrethrum and Ngei estate | 4130299 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1996713 | 44.4 | 1996713 | 4500000 | 2503287 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7222 | Infrastructure, Development & Maintenance | Periodic and Routine Maintenance of Mbamba Road(300m) and Part of John Momanyi Road (400m)in Shabab Ward Nakuru West Sub County | To implement periodic and routine maintenance of mbamba road(300m) and part of john momanyi road (400m)in shabab ward nakuru west sub county for road connectivity and accessibility | Periodic and Routine Maintenance of Mbamba Road(300m) and Part of John Momanyi Road (400m)in Shabab Ward Nakuru West Sub County completed | 4130299 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 15819359 | 2285954 | 2285954 | Equitable | N/A | 2285954 | 0 | 2285954 | 100 | 2285954 | 2285954 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7223 | Infrastructure, Development & Maintenance | Grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | To improve road accessibility by grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | And installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads graded | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.253453, 35.671288 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3281000 | 82 | 3281000 | 715107 | 719000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bush clearing, culverting, drainage, murraming,, the residents have recently worked the road.
7224 | Infrastructure, Development & Maintenance | Grading, Gravelling and installation of culverts at Bygum-Set Kotes Road | To implement grading, gravelling and installation of culverts at bygum-set kotes road for road connectivity and accessibility | Grading, Gravelling and installation of culverts at Bygum-Set Kotes Road completed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.311883, 35.68324 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997000 | 99.9 | 2997000 | 2997001 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Expansion of culvert and installation of guard rails.
7225 | Installation of Culverts and grading of Sirikwa Access road | Installation of Culverts and grading of Sirikwa Access road | To improve drainage and road access through culvert installation at and grading of Sirikwa Access road | Culverts installed at and grading of Sirikwa Access road | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.278465 35.661547 2738.7 13.399999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999000 | 100 | 3999000 | 4000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
7226 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County | To undertake the proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County implemented | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.257902 35.667988 2735.5 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3908156 | 319390.7 | 319390.7 | Equitable | N/A | 319390.7 | 0 | 319391 | 100 | 319391 | 319391 | -0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: The project was not implemented, the facility needs maternity and maternity washrooms, piping, soak pit, septic tank, placenta pit, burning is incomplete, staff toilets are needed and the facility needs water supply and, and ceiling of existing rooms, floor is chipped, and has potholes.
7227 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County | To maintain Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County in serviceable condition | Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County maintained | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.241737, 35.686483 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998948 | 261624 | 261624 | Equitable | N/A | 261624 | 0 | 261624 | 100 | 261624 | 261624 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project needs grading,murraming, bush clearing, culvert installation and culvert unblocking.
7228 | Infrastructure, Development & Maintenance | Design and construction of bridge connecting Arash and Kijabe-Bridge murraming | To design and construct bridge connecting Arash and Kijabe-Bridge murraming | Bridge connecting Arash and Kijabe-Bridge murraming designed and constructed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.026248, 36.231765 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: Yes. Contractor: Details not availed. Assessor remarks: The bridge was meant to serve motor vehicle users. But the state of the road doesn't allow vehicles to go through e of the road.
7229 | Infrastructure, Development & Maintenance | Grading and murraming of Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road | To improve road infrastructure by grading and murraming Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road | Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road graded and murramed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.030753, 36.197117 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2018 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997926 | 99.9 | 1997926 | 1997926 | 2074 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good condition.
7230 | Infrastructure, Development & Maintenance | Installation of highmast 20m at Gilanis, Pyrethrum and Ngei estate | To improve security lighting through high mast floodlight installation at 20m at Gilanis, Pyrethrum and Ngei estate | High mast floodlight installed at 20m at Gilanis, Pyrethrum and Ngei estate | 4130299 | N/A | Nakuru West | Shabab | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1996713 | 44.4 | 1996713 | 4500000 | 2503287 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7231 | Infrastructure, Development & Maintenance | Grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | To improve road accessibility by grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | And installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads graded | 4130299 | N/A | Kuresoi North | Sirikwa | -0.253453, 35.671288 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3281000 | 82 | 3281000 | 715107 | 719000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bush clearing, culverting, drainage, murraming,, the residents have recently worked the road.
7232 | Installation of Culverts and grading of Sirikwa Access road | Installation of Culverts and grading of Sirikwa Access road | To improve drainage and road access through culvert installation at and grading of Sirikwa Access road | Culverts installed at and grading of Sirikwa Access road | 4130299 | N/A | Kuresoi North | Sirikwa | -0.278465 35.661547 2738.7 13.399999618530273 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999000 | 100 | 3999000 | 4000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
7233 | Infrastructure, Development & Maintenance | Design and construction of bridge connecting Arash and Kijabe and murraming of Lucia Moraa connection road | To design and construct bridge connecting Arash and Kijabe and murraming of Lucia Moraa connection road | Bridge connecting Arash and Kijabe and murraming of Lucia Moraa connection road designed and constructed | 4130299 | N/A | Subukia | Subukia | 0.002262 36.227867 1993.800048828125 20.100000381469727 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: The project has benefitted many learners. Viable: Yes. The project has been a learning facility to many learners. Contractor: Information not available. Assessor remarks: The classroom is in use, as well as latrines.
7234 | Infrastructure, Development & Maintenance | Construction of Taita Kapno Bridge | To construct Taita Kapno Bridge | Taita Kapno Bridge constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.445126 35.609035 0 2200 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2971834 | 99.1 | 2971834 | 20966 | 28166 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
7235 | Infrastructure, Development & Maintenance | Design and construction of Kipsotet-chepkesigen bridge, | To design and construct Kipsotet-chepkesigen bridge, | Kipsotet-chepkesigen bridge, designed and constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.509848, 35.664498 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2981947 | 99.4 | 2981947 | 2998930 | 18053 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state.
7236 | Grading and Gravelling of Chebalungu Road | Grading and Gravelling of Chebalungu Road | To improve road infrastructure by grading and murraming Chebalungu Road | Chebalungu Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999588 | 100 | 1999588 | 1999588 | 412 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
7237 | Grading and Gravelling of Kamwaura- Angurwet Road | Grading and Gravelling of Kamwaura- Angurwet Road | To improve road infrastructure by grading and murraming Kamwaura- Angurwet Road | Kamwaura- Angurwet Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2979535 | 99.3 | 2979535 | 15586 | 20465 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
7238 | Infrastructure, Development & Maintenance | Grading and Gravelling of Sotiki Chepsoi Road | To improve road infrastructure by grading and murraming Sotiki Chepsoi Road | Sotiki Chepsoi Road graded and murramed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.547201, 35.674632 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2952403 | 98.4 | 2952403 | 43364 | 47597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage because of heavy rain.
7239 | Grading, gravelling, onTMC-chemaner road | Grading, gravelling, onTMC-chemaner road | To implement grading, gravelling, ontmc-chemaner road for road connectivity and accessibility | Grading, gravelling, onTMC-chemaner road completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4999000 | 100 | 4999000 | 5000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
7240 | murraming and grvelling of Kapkembu - Tirigoi road | murraming and grvelling of Kapkembu - Tirigoi road | To implement murraming and grvelling of kapkembu - tirigoi road for road connectivity and accessibility | murraming and grvelling of Kapkembu - Tirigoi road completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.538982 35.643548 0 2900 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2595274 | 99.8 | 2595274 | 2600000 | 4726 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes due to heavy rain.
7241 | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | TINET | -0.495392, 35.646623 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3099360 | 239797.5 | 239797.5 | Equitable | N/A | 239797.5 | 0 | 239798 | 100 | 239798 | 239798 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes murrurum wash away by rain.
7242 | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | TINET | -0.495392, 35.646623 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 999900 | 999900 | 999900 | Equitable | N/A | 999900 | 0 | 999900 | 100 | 999900 | 999900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes murrurum wash away by rain.
7243 | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | To maintain Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County in serviceable condition | Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County maintained | 4130299 | N/A | KURESOI SOUTH | TINET | -0.438399, 35.609035 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 869300 | 869300 | 869300 | Equitable | N/A | 869300 | 0 | 869300 | 100 | 869300 | 869300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain water.
7244 | Infrastructure, Development & Maintenance | Design and construction of Kipsotet-chepkesigen bridge, | To design and construct Kipsotet-chepkesigen bridge, | Kipsotet-chepkesigen bridge, designed and constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.509848, 35.664498 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2981947 | 99.4 | 2981947 | 2998930 | 18053 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state.
7245 | Grading and Gravelling of Chebalungu Road | Grading and Gravelling of Chebalungu Road | To improve road infrastructure by grading and murraming Chebalungu Road | Chebalungu Road graded and murramed | 4130299 | N/A | Kuresoi South | Tinet | -0.478177 35.670193 0 1899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 1999587.7 | 1999587.7 | Equitable | N/A | 1999587.7 | 0 | 1999588 | 100 | 1999588 | 1999588 | -0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
7246 | Grading, gravelling, onTMC-chemaner road | Grading, gravelling, onTMC-chemaner road | To implement grading, gravelling, ontmc-chemaner road for road connectivity and accessibility | Grading, gravelling, onTMC-chemaner road completed | 4130299 | N/A | Kuresoi South | Tinet | -0.478177 35.670193 0 1899.9990234375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4999000 | 100 | 4999000 | 5000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
7247 | murraming and grvelling of Kapkembu - Tirigoi road | murraming and grvelling of Kapkembu - Tirigoi road | To implement murraming and grvelling of kapkembu - tirigoi road for road connectivity and accessibility | murraming and grvelling of Kapkembu - Tirigoi road completed | 4130299 | N/A | Kuresoi South | Tinet | -0.538982 35.643548 0 2900 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2595274 | 99.8 | 2595274 | 2600000 | 4726 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes due to heavy rain.
7248 | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Tinet | -0.495392, 35.646623 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3099360 | 239797.5 | 239797.5 | Equitable | N/A | 239797.5 | 0 | 239798 | 100 | 239798 | 239798 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes murrurum wash away by rain.
7249 | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Tinet | -0.495392, 35.646623 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 999900 | 999900 | 999900 | Equitable | N/A | 999900 | 0 | 999900 | 100 | 999900 | 999900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes murrurum wash away by rain.
7250 | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | To maintain Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County in serviceable condition | Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Tinet | -0.438399, 35.609035 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 869300 | 869300 | 869300 | Equitable | N/A | 869300 | 0 | 869300 | 100 | 869300 | 869300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain water.
7251 | Infrastructure, Development & Maintenance | Grading and Murraming of County Council- Kayole road | To improve road infrastructure by grading and murraming County Council- Kayole road | County Council- Kayole road graded and murramed | 4130299 | N/A | RONGAI | VISOI | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2395128 | 79.8 | 2395128 | 2990100 | 604872 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7252 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County | To undertake the proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County | Proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County implemented | 4130299 | N/A | RONGAI | VISOI | -0.156022, 35.848131 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2999040.8 | 2999040.8 | 2999040.8 | Equitable | N/A | 2999040.8 | 0 | 2999041 | 100 | 2999041 | 2999041 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: 2023. Viable: Yes. Assessor remarks: Goodness.
7253 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County maintained | 4130299 | N/A | RONGAI | VISOI | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1932560 | 527638 | 527638 | Equitable | N/A | 527638 | 0 | 1404922 | 266.3 | 1404922 | 527638 | -877284 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7254 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County maintained | 4130299 | N/A | RONGAI | VISOI | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2800240 | 2800240 | 2800240 | Equitable | N/A | 2800240 | 0 | 2500000 | 89.3 | 2500000 | 2800240 | 300240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7255 | Infrastructure, Development & Maintenance | Construction of Shoe Shiner Sheds in Viwandani ward Naivasha Sub County | To construct Shoe Shiner Sheds in Viwandani ward Naivasha Sub County | Shoe Shiner Sheds in Viwandani ward Naivasha Sub County constructed | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.717914, 36.435199 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 849398.4 | 318524.4 | 318524.4 | Equitable | N/A | 318524.4 | 0 | 318524 | 100 | 318524 | 318524 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: operation.
7256 | Infrastructure, Development & Maintenance | Proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county | To undertake the proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county | Proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county implemented | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.71598 36.438907 1917.365 3.75600004196167 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 990864 | 990864 | 990864 | Equitable | N/A | 990864 | 0 | 990864 | 100 | 990864 | 990864 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
7257 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County maintained | 4130299 | N/A | Rongai | Visoi | N/A | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2800240 | 2800240 | 2800240 | Equitable | N/A | 2800240 | 0 | 2500000 | 89.3 | 2500000 | 2800240 | 300240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7258 | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | To construct Ndatho bridge Box Culvert 3.0mx2.5x500 long | Ndatho bridge Box Culvert 3.0mx2.5x500 long constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.058923, 36.236265 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494797 | 99.8 | 2494797 | 2500000 | 5203 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is in use and in good condition.
7259 | Infrastructure, Development & Maintenance | Grading and murraming of Limuru - St. Ulrich road | To improve road infrastructure by grading and murraming Limuru - St. Ulrich road | Limuru - St. Ulrich road graded and murramed | 4130299 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1051700 | 87.6 | 1051700 | 1052100 | 148300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
7260 | Infrastructure, Development & Maintenance | Grading and murraming of Wiyumiririe ( ngombe mbili to ponda mali road | To improve road infrastructure by grading and murraming Wiyumiririe ( ngombe mbili to ponda mali road | Wiyumiririe ( ngombe mbili to ponda mali road graded and murramed | 4130299 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1473135 | 98.2 | 1473135 | 26865 | 26865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
7261 | installation of waseges ward highmast streetlighting | installation of waseges ward highmast streetlighting | To install waseges ward highmast streetlighting | Waseges ward highmast streetlighting installed | 4130299 | N/A | SUBUKIA | WASEGES | 0.166308, 36.249808 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900400 | 90 | 900400 | 1000000 | 99600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
7262 | Infrastructure, Development & Maintenance | Proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County | To undertake the proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County | Proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County implemented | 4130299 | N/A | SUBUKIA | WASEGES | 0.098648 36.250163 1819.6 8 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 791676 | 791676 | 791676 | Equitable | N/A | 791676 | 0 | 791676 | 100 | 791676 | 791676 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in good conditions.
7263 | Infrastructure, Development & Maintenance | Proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County | To undertake the proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County | Proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County implemented | 4130299 | N/A | SUBUKIA | WASEGES | 0.017343 36.246975 2017.2 6.199999809265137 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1510900 | 1510900 | 1510900 | Equitable | N/A | 1510900 | 0 | 1510900 | 100 | 1510900 | 1510900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Good Condition.
7264 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County | To maintain Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County in serviceable condition | Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County maintained | 4130299 | N/A | SUBUKIA | WASEGES | 0.09975 36.262692 1855.2 3.799999952316284 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1697776 | 1697776 | 1697776 | Equitable | N/A | 1697776 | 0 | 1697776 | 100 | 1697776 | 1697776 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in use.
7265 | Infrastructure, Development & Maintenance | grading, murraming and culvert installation at Akuis - mama Karuga junction- Baraka - kwa Muchiri Road | To implement grading, murraming and culvert installation at akuis - mama karuga junction- baraka - kwa muchiri road for road connectivity and accessibility | grading, murraming and culvert installation at Akuis - mama Karuga junction- Baraka - kwa Muchiri Road completed | 4130299 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2484720 | 99.4 | 2484720 | 2484720 | 15280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
7266 | installation of Waseges highmast streetlights | installation of Waseges highmast streetlights | To install Waseges highmast streetlights | Waseges highmast streetlights installed | 4130299 | N/A | SUBUKIA | WASEGES | 0.166308, 36.249808 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1416745 | 1416744 | 1416744 | Equitable | N/A | 1416744 | 0 | 1404200 | 99.1 | 1404200 | 1416744 | 12544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
7267 | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | To construct Ndatho bridge Box Culvert 3.0mx2.5x500 long | Ndatho bridge Box Culvert 3.0mx2.5x500 long constructed | 4130299 | N/A | Subukia | Waseges | 0.058923, 36.236265 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494797 | 99.8 | 2494797 | 2500000 | 5203 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is in use and in good condition.
7268 | Infrastructure, Development & Maintenance | Grading and murraming of Limuru - St. Ulrich road | To improve road infrastructure by grading and murraming Limuru - St. Ulrich road | Limuru - St. Ulrich road graded and murramed | 4130299 | N/A | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1051700 | 87.6 | 1051700 | 1052100 | 148300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
7269 | Infrastructure, Development & Maintenance | Grading and murraming of Wiyumiririe ( ngombe mbili to ponda mali road | To improve road infrastructure by grading and murraming Wiyumiririe ( ngombe mbili to ponda mali road | Wiyumiririe ( ngombe mbili to ponda mali road graded and murramed | 4130299 | N/A | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 26865 | 26865 | Equitable | N/A | 26865 | 0 | 1473135 | 5483.5 | 1473135 | 26865 | -1446270 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
7270 | installation of waseges ward highmast streetlighting | installation of waseges ward highmast streetlighting | To install waseges ward highmast streetlighting | Waseges ward highmast streetlighting installed | 4130299 | N/A | Subukia | Waseges | 0.166308, 36.249808 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900400 | 90 | 900400 | 1000000 | 99600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
7271 | installation of Waseges highmast streetlights | installation of Waseges highmast streetlights | To install Waseges highmast streetlights | Waseges highmast streetlights installed | 4130299 | N/A | Subukia | Waseges | 0.166308, 36.249808 | VOTE NO 4567 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1416745 | 1416744 | 1416744 | Equitable | N/A | 1416744 | 0 | 1404200 | 99.1 | 1404200 | 1416744 | 12544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
7272 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 2640499 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 5500000 | 5500000 | 5500000 | Equitable | EQUITABLE | 5500000 | 0 | 1500000 | 27.3 | 1500000 | 4500000 | 4000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7273 | Crop Development and Management | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640499 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 6500000 | 6500000 | 6500000 | Equitable | Equitable | 6500000 | 0 | 6500000 | 100 | 6500000 | 3910461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7274 | Crop Development and Management | Agricultural Sector Development Support Projects (ASDSP) | To implement agricultural sector development support projects (asdsp) for agricultural development and food production | Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2020/21 | 2020/21 | 14171667 | 14171667 | 0 | ASDSP II | ASDSP II | 0 | 32679168 | 197358 | 1.4 | 197358 | 696453 | 13974309 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7275 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 5500000 | 5500000 | 5500000 | ASDSP II | ASDSP II | 5500000 | 0 | 1500000 | 27.3 | 1500000 | 4500000 | 4000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7276 | Crop Development and Management | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 6500000 | 11500000 | 11500000 | NARIGP | NARIGP | 11500000 | 0 | 6500000 | 56.5 | 6500000 | 3910461 | 5000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7277 | Crop Development and Management | National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2020/21 | 2020/21 | 198441600 | 198441600 | 0 | NARIGP | NARIGP | 0 | 552556780.55 | 351365 | 0.2 | 351365 | 3910461 | 198090235 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7278 | Administration, Planning and Support Services | Construction of Slaughter House and fencing | To construct Slaughter House and fencing | Slaughter House and fencing constructed | 3110299 | Construction of Buildings - Ot | Gilgil | Gilgil | -0.460048, 36.296729 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 4000000 | 4000000 | Equitable | equitable | 4000000 | 0 | 3894270 | 97.4 | 3894270 | 3894270 | 105730 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yet to start. Contractor: M/s Gactor enterprises ltd. Assessor remarks: In good state.
7279 | Fisheries Development | Export slaughter House and Feedlot facility in Naivasha - Phase I | To implement export slaughter house and feedlot facility in naivasha - phase i for agricultural development and food production | Export slaughter House and Feedlot facility in Naivasha - Phase I completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2022/23 | N/A | 150000000 | 4524000 | 4524000 | Equitable | N/A | 4524000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7280 | Administration, Planning and Support Services | Renovation of Kandutura Cereal Store | To rehabilitate Kandutura Cereal Store to restore functionality | Kandutura Cereal Store rehabilitated | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | equitable | 600000 | 0 | 524100 | 87.4 | 524100 | 600000 | 75900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
7281 | Administration, Planning and Support Services | Completion Kandutura Cereal store | To complete Kandutura Cereal store | Kandutura Cereal store completed | 3110299 | Construction of Buildings - Ot | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
7282 | Administration, Planning and Support Services | Purchase and supply of incubators | To procure and supply incubators | Incubators procured and supplied | 3110302 | Refurbishment of Non-Residential Buildings | Kuresoi North | Kiptororo | -0.356669 35.481787 0 2099.9990234375 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 991000 | 99.1 | 991000 | 1000000 | 9000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
7283 | Administration, Planning and Support Services | Completion of Kaptaragon tea buying centre | To complete Kaptaragon tea buying centre | Kaptaragon tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2024 | 700000 | 700000 | 700000 | Equitable | EQUITABLE | 700000 | 0 | 680540 | 97.2 | 680540 | 680540 | 19460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7284 | Administration, Planning and Support Services | Completion of tea buying centre at Bondet | To complete tea buying centre at Bondet | Tea buying centre at Bondet completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 700000 | 700000 | Equitable | Equitable | 700000 | 0 | 699950 | 100 | 699950 | 699886 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7285 | Administration, Planning and Support Services | Completion of tea buying centre at Cornerstone | To complete tea buying centre at Cornerstone | Tea buying centre at Cornerstone completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 700000 | 700000 | Equitable | Equitable | 700000 | 0 | 680660 | 97.2 | 680660 | 680660 | 19340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7286 | Administration, Planning and Support Services | Completion of tea buying centre at Kaplamboi | To complete tea buying centre at Kaplamboi | Tea buying centre at Kaplamboi completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 480030 | 96 | 480030 | 480030 | 19970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7287 | Administration, Planning and Support Services | Completion of tea buying centre at Nukiat | To complete tea buying centre at Nukiat | Tea buying centre at Nukiat completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 700000 | 700000 | Equitable | Equitable | 700000 | 0 | 699950 | 100 | 699950 | 699950 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7288 | Administration, Planning and Support Services | Completion of bondet tea buying center | To complete bondet tea buying center | Bondet tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 1000000 | 333.3 | 1000000 | 300000 | -700000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7289 | Administration, Planning and Support Services | Completion of Kaptaragon tea buying centre | To complete Kaptaragon tea buying centre | Kaptaragon tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2024 | 700000 | 700000 | 700000 | Equitable | EQUITABLE | 700000 | 0 | 680540 | 97.2 | 680540 | 680540 | 19460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7290 | Administration, Planning and Support Services | Completion of nukiat tea buying center | To complete nukiat tea buying center | Nukiat tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 530015 | 176.7 | 530015 | 300000 | -230015 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7291 | Administration, Planning and Support Services | Completion of tea buying centre at Bondet | To complete tea buying centre at Bondet | Tea buying centre at Bondet completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 699886 | 699886 | Equitable | Equitable | 699886 | 0 | 699950 | 100 | 699950 | 699886 | -64 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7292 | Administration, Planning and Support Services | Completion of tea buying centre at Cornerstone | To complete tea buying centre at Cornerstone | Tea buying centre at Cornerstone completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 700000 | 700000 | Equitable | Equitable | 700000 | 0 | 680660 | 97.2 | 680660 | 680660 | 19340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7293 | Administration, Planning and Support Services | Completion of tea buying centre at Kaplamboi | To complete tea buying centre at Kaplamboi | Tea buying centre at Kaplamboi completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 480030 | 96 | 480030 | 480030 | 19970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7294 | Administration, Planning and Support Services | Completion of tea buying centre at Nukiat | To complete tea buying centre at Nukiat | Tea buying centre at Nukiat completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 699950 | 699950 | Equitable | Equitable | 699950 | 0 | 699950 | 100 | 699950 | 699950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7295 | Administration, Planning and Support Services | Completion of tebeswet tea buying center | To complete tebeswet tea buying center | Tebeswet tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 530015 | 176.7 | 530015 | 300000 | -230015 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7296 | Administration, Planning and Support Services | Completion of tuyobei tea buying center | To complete tuyobei tea buying center | Tuyobei tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7297 | Administration, Planning and Support Services | Kirima milk cooler - installation of three phase electricity power and highmast lights | To implement kirima milk cooler - installation of three phase electricity power and highmast lights for agricultural development and food production | Kirima milk cooler - installation of three phase electricity power and highmast lights completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.632653, 36.48875 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 980084 | 98 | 980084 | 1000000 | 19916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
7298 | Crop Development and Management | construction and reniovation of cattle trough in ainamoi dam | To construct and reniovation of cattle trough in ainamoi dam | And reniovation of cattle trough in ainamoi dam constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 499844 | 100 | 499844 | 0 | 156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7299 | Administration, Planning and Support Services | Completion of Hide and skin structure in Elburgon Ward Molo Sub County | To complete Hide and skin structure in Elburgon Ward Molo Sub County | Hide and skin structure in Elburgon Ward Molo Sub County completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7300 | Administration, Planning and Support Services | Construction and equiping slaughter house in Lake View ward Naivasha sub county | To construct and equiping slaughter house in Lake View ward Naivasha sub county | And equiping slaughter house in Lake View ward Naivasha sub county constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 9916356 | 9807280 | 9807280 | Equitable | EQUITABLE | 9807280 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7301 | Crop Development and Management | Equipping and operationalization of fish processing plant in Naivasha | To equip and operationalization of fish processing plant in Naivasha with necessary facilities and equipment | And operationalization of fish processing plant in Naivasha equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 6544400 | 5459432 | 5459432 | Equitable | EQUITABLE | 5459432 | 0 | 1998820 | 36.6 | 1998820 | 5459432 | 3460612 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7302 | Administration, Planning and Support Services | Extra works for proposed Construction of slaughter slab at Malewa West Naivasha sub county | To implement extra works for proposed construction of slaughter slab at malewa west naivasha sub county for agricultural development and food production | Extra works for proposed Construction of slaughter slab at Malewa West Naivasha sub county completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 450000 | 0 | 450000 | Equitable | EQUITABLE | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7303 | Fisheries Development | Procure and delivery of pond liners to leaning institutions and schools. | To implement procure and delivery of pond liners to leaning institutions and schools. for agricultural development and food production | Procure and delivery of pond liners to leaning institutions and schools. completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 4349910 | 4349910 | N/A | N/A | 4349910 | 0 | 7941466 | 182.6 | 7941466 | 0 | -3591556 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7304 | Fisheries Development | Procure and restock fingerlings in dams and ponds | To implement procure and restock fingerlings in dams and ponds for agricultural development and food production | Procure and restock fingerlings in dams and ponds completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 4000000 | 4000000 | Equitable | equitable | 4000000 | 0 | 1414000 | 35.4 | 1414000 | 0 | 2586000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7305 | Administration, Planning and Support Services | Proposed construction of cattle dip at Kipkewa, Okligei, Kongoi Haraki and Tiloa In Kiptoro ward Kuresoi North sub county | To undertake the proposed construction of cattle dip at Kipkewa, Okligei, Kongoi Haraki and Tiloa In Kiptoro ward Kuresoi North sub county | Proposed construction of cattle dip at Kipkewa, Okligei, Kongoi Haraki and Tiloa In Kiptoro ward Kuresoi North sub county implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500090 | 2500090 | 2500090 | Equitable | EQUITABLE | 2500090 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7306 | Administration, Planning and Support Services | Provision of water to the cooling plant at Elementaita ward Gilgil sub county | To implement provision of water to the cooling plant at elementaita ward gilgil sub county for agricultural development and food production | Provision of water to the cooling plant at Elementaita ward Gilgil sub county completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 4999314 | 4999314 | Equitable | EQUITABLE | 4999314 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7307 | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip | To implement kabianga cattle dip - purchase of land and construction of kabianga cattle dip for agricultural development and food production | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.131288, 35.609787 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Land was never purchased. Cattles get vaccinated along Kabianga Kiplelechon road..
7308 | Administration, Planning and Support Services | Promotion of Youth and women urban agriculture | To implement promotion of youth and women urban agriculture for agricultural development and food production | Promotion of Youth and women urban agriculture completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.312069, 36.053022 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 499290 | 49.9 | 499290 | 501200 | 500710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No since it was vandalized after two years of completion. Viable: Yes it was a very viable project if not for vandalism. Contractor: Arthritis enterprises. Assessor remarks: The project was vandalized hence it's not working.
7309 | Administration, Planning and Support Services | Completion of tegat milk cooler | To complete tegat milk cooler | Tegat milk cooler completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KERINGET | -0.466427, 35.65346 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 0 | 0 | 0 | 799650 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
7310 | Crop Development and Management | Construction of cut-off drain in farms at Njuguni-Kigecha village | To construct cut-off drain in farms at Njuguni-Kigecha village | Cut-off drain in farms at Njuguni-Kigecha village constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.424258, 35.969678 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998484 | 99.9 | 2998484 | 15000 | 1516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
7311 | Administration, Planning and Support Services | Completion of BONDET tea buying center | To complete BONDET tea buying center | BONDET tea buying center completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 700000 | 700000 | 700000 | Equitable | EQUITABLE | 700000 | 0 | 694982 | 99.3 | 694982 | 694983 | 5018 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7312 | Administration, Planning and Support Services | Completion of Kapugunot tea buying centre | To complete Kapugunot tea buying centre | Kapugunot tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 700000 | 700000 | 700000 | Equitable | EQUITABLE | 700000 | 0 | 693262 | 99 | 693262 | 693262 | 6738 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7313 | Administration, Planning and Support Services | Completion of Ketitui tea buying centre | To complete Ketitui tea buying centre | Ketitui tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 399272 | 133.1 | 399272 | 300000 | -99272 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7314 | Administration, Planning and Support Services | Completion of kibirech tea buying center | To complete kibirech tea buying center | Kibirech tea buying center completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 200000 | 200000 | 200000 | Equitable | EQUITABLE | 200000 | 0 | 199189 | 99.6 | 199189 | 199189 | 811 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7315 | Administration, Planning and Support Services | Completion of Kondamet tea buying centre | To complete Kondamet tea buying centre | Kondamet tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 399272 | 99.8 | 399272 | 399272 | 728 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7316 | Administration, Planning and Support Services | Completion of Saptonok tea buying centre | To complete Saptonok tea buying centre | Saptonok tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 393820 | 98.5 | 393820 | 393820 | 6180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7317 | Administration, Planning and Support Services | Completion of Seger tea buying center | To complete Seger tea buying center | Seger tea buying center completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7318 | Administration, Planning and Support Services | Completion of chorwa tea buying center | To complete chorwa tea buying center | Chorwa tea buying center completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.335513, 35.484805 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 197800 | 98.9 | 197800 | 200000 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7319 | Crop Development and Management | purchase and supply of chicken incubators | To procure and supply chicken incubators | Chicken incubators procured and supplied | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.215427, 36.164444 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 1256428 | 1256428 | 1256428 | Equitable | EQUITABLE | 1256428 | 0 | 1256290 | 100 | 1256290 | 0 | 138 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sylent enterprise limited. Assessor remarks: Operational but consumes to much electricity and they lack enough eggs for hatching.
7320 | Administration, Planning and Support Services | Construction of underground tank at kibowen komen for urban agriculture | To construct underground tank at kibowen komen for urban agriculture | Underground tank at kibowen komen for urban agriculture constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.312177, 36.052969 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 499290 | 49.9 | 499290 | 699700 | 500710 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: No. Contractor: Carofa enterprises. Assessor remarks: Yet to be started.
7321 | Administration, Planning and Support Services | Promotion of Youth and women urban agriculture | To implement promotion of youth and women urban agriculture for agricultural development and food production | Promotion of Youth and women urban agriculture completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.312069, 36.053022 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 501200 | 501200 | Equitable | equitable | 501200 | 0 | 499290 | 99.6 | 499290 | 501200 | 1910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No since it was vandalized after two years of completion. Viable: Yes it was a very viable project if not for vandalism. Contractor: Arthritis enterprises. Assessor remarks: The project was vandalized hence it's not working.
7322 | Administration, Planning and Support Services | Completion of tegat milk cooler | To complete tegat milk cooler | Tegat milk cooler completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466427, 35.65346 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 800000 | 799650 | 799650 | Equitable | EQUITABLE | 799650 | 0 | 0 | 0 | 0 | 799650 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
7323 | Administration, Planning and Support Services | Construction of cut off drains in agricultural farm lands | To construct cut off drains in agricultural farm lands | Cut off drains in agricultural farm lands constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.451828, 35.976993 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | equitable | 2500000 | 0 | 1160000 | 46.4 | 1160000 | 15000 | 1340000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Requires maintenance.
7324 | Administration, Planning and Support Services | Completion of ararwet marisim tea buying center | To complete ararwet marisim tea buying center | Ararwet marisim tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 396390 | 99.1 | 396390 | 400000 | 3610 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7325 | Administration, Planning and Support Services | Completion of Banana tea buying center | To complete Banana tea buying center | Banana tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 400000 | 100 | 400000 | 399310 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7326 | Administration, Planning and Support Services | Completion of Bondet tea buying center | To complete Bondet tea buying center | Bondet tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 700000 | 694983 | 694983 | Equitable | EQUITABLE | 694983 | 0 | 694982 | 100 | 694982 | 694983 | 1 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7327 | Administration, Planning and Support Services | Completion of Kapugunot tea buying centre | To complete Kapugunot tea buying centre | Kapugunot tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 700000 | 700000 | 700000 | Equitable | EQUITABLE | 700000 | 0 | 693262 | 99 | 693262 | 693262 | 6738 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7328 | Administration, Planning and Support Services | Completion of Ketitui tea buying centre | To complete Ketitui tea buying centre | Ketitui tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 399272 | 133.1 | 399272 | 300000 | -99272 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7329 | Administration, Planning and Support Services | Completion of kibirech tea buying center | To complete kibirech tea buying center | Kibirech tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 200000 | 200000 | 200000 | Equitable | EQUITABLE | 200000 | 0 | 199189 | 99.6 | 199189 | 199189 | 811 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7330 | Administration, Planning and Support Services | Completion of Kondamet tea buying centre | To complete Kondamet tea buying centre | Kondamet tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 399272 | 99.8 | 399272 | 399272 | 728 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7331 | Administration, Planning and Support Services | Completion of Saptonok tea buying centre | To complete Saptonok tea buying centre | Saptonok tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 393820 | 98.5 | 393820 | 393820 | 6180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7332 | Administration, Planning and Support Services | Completion of Seger tea buying center | To complete Seger tea buying center | Seger tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
7333 | Administration, Planning and Support Services | Completion of tea buying center at chepkiswet | To complete tea buying center at chepkiswet | Tea buying center at chepkiswet completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.64907 2515.7999999999997 7.400000095367432 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and met the needs. Assessor remarks: Functional.
7334 | Administration, Planning and Support Services | Completion of tea buying center at chepnyalilo | To complete tea buying center at chepnyalilo | Tea buying center at chepnyalilo completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.64907 2515.7999999999997 7.400000095367432 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and met the needs. Assessor remarks: Functional.
7335 | Administration, Planning and Support Services | Construction of Ararwet mbaley tea buying center | To construct Ararwet mbaley tea buying center | Ararwet mbaley tea buying center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.562995, 35.589517 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | Not yet started | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 396390 | 39.6 | 396390 | 927290 | 603610 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: The project was viable but it never met the objectives of the residents.. Contractor: Don't know. Assessor remarks: The project has not started.
7336 | Administration, Planning and Support Services | Completion of chorwa tea buying center | To complete chorwa tea buying center | Chorwa tea buying center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.335513, 35.484805 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 197800 | 98.9 | 197800 | 200000 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7337 | Crop Development and Management | Kasarani youths fish pond | To implement kasarani youths fish pond for agricultural development and food production | Kasarani youths fish pond completed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499948 | 100 | 499948 | 0 | 52 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The equipping is to go on.
7338 | Crop Development and Management | Nyondia youths fish pond | To implement nyondia youths fish pond for agricultural development and food production | Nyondia youths fish pond completed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499670 | 99.9 | 499670 | 0 | 330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Need repairing.
7339 | Crop Development and Management | Tarabeta beach electric fence | To implement tarabeta beach electric fence for agricultural development and food production | Tarabeta beach electric fence completed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.612613 36.380458 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7340 | Crop Development and Management | Purchase of hutcheries | To procure hutcheries | Hutcheries procured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.881478, 36.489213 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 488600 | 97.7 | 488600 | 488600 | 11400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning normally ,big challenge electricity.
7341 | Administration, Planning and Support Services | Purchase and supply of nets,fishing hooks and life savers at talambeta landing beach | To procure and supply nets,fishing hooks and life savers at talambeta landing beach | Nets,fishing hooks and life savers at talambeta landing beach procured and supplied | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.774775 36.291606 0 4300 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1197800 | 99.8 | 1197800 | 1200000 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good initiative.
7342 | Administration, Planning and Support Services | Construction of a potato cooling plant in Masai Centre in Mauche Ward | To construct a potato cooling plant in Masai Centre in Mauche Ward | A potato cooling plant in Masai Centre in Mauche Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.50456, 35.958508 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 5500000 | 5299999.48 | 5299999.48 | Equitable | equitable | 5299999.48 | 0 | 5299999 | 100 | 5299999 | 5299999 | 0.48 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Solar panels vandalized and stolen.
7343 | Crop Development and Management | Construction of a toilet at Mauka cereal store in Mauche Ward | To construct a toilet at Mauka cereal store in Mauche Ward | A toilet at Mauka cereal store in Mauche Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.50878, 35.971729 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 5299999 | 1060 | 5299999 | 500000 | -4799999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7344 | Crop Development and Management | Construction of a toilet at potato cooling plant in Mauche Ward | To construct a toilet at potato cooling plant in Mauche Ward | A toilet at potato cooling plant in Mauche Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.50878, 35.971729 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 5299999 | 1060 | 5299999 | 500000 | -4799999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7345 | Crop Development and Management | Fencing of Mauka cereal store | To secure Mauka cereal store through fencing | Mauka cereal store fenced and secured | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.508777, 35.971722 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2850000 | 95 | 2850000 | 2850000 | 150000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7346 | Administration, Planning and Support Services | Purchase of cooler(milk cooler) | To procure cooler(milk cooler) | Cooler(milk cooler) procured | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.168534, 36.011825 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2790000 | 139.5 | 2790000 | 2000000 | -790000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7347 | Crop Development and Management | Installation and building of fish freeze at kamere beach | To install and building of fish freeze at kamere beach | And building of fish freeze at kamere beach installed | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | OLKARIA | -0.817132 36.32586 1922.199951171875 24.67099952697754 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1998705 | 99.9 | 1998705 | 1998705 | 1295 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
7348 | Crop Development and Management | Installation and building of fish freeze at kamere beach | To install and building of fish freeze at kamere beach | And building of fish freeze at kamere beach installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817132 36.32586 1922.199951171875 24.67099952697754 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1998705 | 1998705 | Equitable | EQUITABLE | 1998705 | 0 | 1998705 | 100 | 1998705 | 1998705 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
7349 | Crop Development and Management | Purchase and supply of incubators,solar panel generators and hatching trays | To procure and supply incubators,solar panel generators and hatching trays | Incubators,solar panel generators and hatching trays procured and supplied | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.938607 36.369038 1912.6000000000001 4.900000095367432 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 2969200 | 296.9 | 2969200 | 978500 | -1969200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Understand construction still. Assessor remarks: Supply of modern jikos and 110litres sufuria not yet.
7350 | Crop Development and Management | Kokwomoi cattle dip completion | To implement kokwomoi cattle dip completion for agricultural development and food production | Kokwomoi cattle dip completion completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.021861, 36.075789 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating but requires renovation.
7351 | Crop Development and Management | Losibil cattle dip completion | To implement losibil cattle dip completion for agricultural development and food production | Losibil cattle dip completion completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.021861, 36.075789 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 598000 | 99.7 | 598000 | 600000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating but requires renovation.
7352 | Crop Development and Management | Renovation of Lower Solai slaughter house | To rehabilitate Lower Solai slaughter house to restore functionality | Lower Solai slaughter house rehabilitated | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOLAI | 0.112278 36.221875 1849.1999999999998 9.600000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 858237 | 858237 | 858237 | Equitable | EQUITABLE | 858237 | 0 | 857800 | 99.9 | 857800 | 857800 | 437 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Pick verd. Assessor remarks: Good.
7353 | Administration, Planning and Support Services | Construction of Barina sub location Cattle dip | To construct Barina sub location Cattle dip | Barina sub location Cattle dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.083409 35.873848 1801 9.5 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1882696 | 1882696 | 1882696 | Equitable | equitable | 1882696 | 0 | 1882696 | 100 | 1882696 | 1882696 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require water supply.
7354 | Crop Development and Management | Kokwomoi cattle dip completion | To implement kokwomoi cattle dip completion for agricultural development and food production | Kokwomoi cattle dip completion completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.021861, 36.075789 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating but requires renovation.
7355 | Administration, Planning and Support Services | Construction of Kamosop cattle dip | To construct Kamosop cattle dip | Kamosop cattle dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.01178, 36.144923 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1990000 | 99.5 | 1990000 | 1990000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7356 | Crop Development and Management | Renovation of Lower Solai slaughter house | To rehabilitate Lower Solai slaughter house to restore functionality | Lower Solai slaughter house rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.112278 36.221875 1849.1999999999998 9.600000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 858237 | 857800 | 857800 | Equitable | EQUITABLE | 857800 | 0 | 857800 | 100 | 857800 | 857800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Pick verd. Assessor remarks: Good.
7357 | Crop Development and Management | Renovation of rongai slaughter slab | To rehabilitate rongai slaughter slab to restore functionality | Rongai slaughter slab rehabilitated | 3110504 | Other Infrastructure and Civil Works | RONGAI | VISOI | -0.173053 35.86075 1861.5999755859375 10.399999618530273 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 399968 | 100 | 399968 | 400000 | 32 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7358 | Crop Development and Management | Renovation of rongai slaughter slab | To rehabilitate rongai slaughter slab to restore functionality | Rongai slaughter slab rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.173053 35.86075 1861.5999755859375 10.399999618530273 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 399968 | 100 | 399968 | 400000 | 32 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7359 | Administration, Planning and Support Services | Construction of chepakundi tea buying center | To construct chepakundi tea buying center | Chepakundi tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.653843, 35.62003 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | equitable | 1300000 | 0 | 1297450 | 99.8 | 1297450 | 1500000 | 2550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
7360 | Administration, Planning and Support Services | Construction of tea buying centre at Chorwet Kiptenden | To construct tea buying centre at Chorwet Kiptenden | Tea buying centre at Chorwet Kiptenden constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.584763 35.680692 2496 12 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1300000 | 1300000 | Equitable | EQUITABLE | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
7361 | Administration, Planning and Support Services | Construction of tea buying centre at Saptet Kapkwen | To construct tea buying centre at Saptet Kapkwen | Tea buying centre at Saptet Kapkwen constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.584673 35.680673 2593.1 4.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1300000 | 1300000 | Equitable | EQUITABLE | 1300000 | 0 | 1215610 | 93.5 | 1215610 | 83560 | 84390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project ongoing.
7362 | Administration, Planning and Support Services | Construction of tebeswet tea buying center | To construct tebeswet tea buying center | Tebeswet tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.653843, 35.62003 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1199469 | 100 | 1199469 | 1199469 | 531 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
7363 | Administration, Planning and Support Services | Construction of chepakundi tea buying center | To construct chepakundi tea buying center | Chepakundi tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.653843, 35.62003 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | equitable | 1300000 | 0 | 1297450 | 99.8 | 1297450 | 1500000 | 2550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
7364 | Administration, Planning and Support Services | Construction of cheptangule tea buying center | To construct cheptangule tea buying center | Cheptangule tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.6786 35.654126 2470.228759765625 8.189000129699707 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1451750 | 96.8 | 1451750 | 1500000 | 48250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: done.
7365 | Administration, Planning and Support Services | Construction of kiptenden tea buying center | To construct kiptenden tea buying center | Kiptenden tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.573443, 35.689997 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1479580 | 98.6 | 1479580 | 1500000 | 20420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project ongoing.
7366 | Administration, Planning and Support Services | Construction of koilenget tea buying center | To construct koilenget tea buying center | Koilenget tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.651707, 35.666838 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1479580 | 98.6 | 1479580 | 1500000 | 20420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: good.
7367 | Administration, Planning and Support Services | Construction of tea buying centre at Chorwet Kiptenden | To construct tea buying centre at Chorwet Kiptenden | Tea buying centre at Chorwet Kiptenden constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.584763 35.680692 2496 12 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1300000 | 1300000 | Equitable | EQUITABLE | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
7368 | Administration, Planning and Support Services | Construction of tea buying centre at Saptet Kapkwen | To construct tea buying centre at Saptet Kapkwen | Tea buying centre at Saptet Kapkwen constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.584673 35.680673 2593.1 4.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1299170 | 1299170 | Equitable | EQUITABLE | 1299170 | 0 | 1215610 | 93.6 | 1215610 | 83560 | 83560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project ongoing.
7369 | Administration, Planning and Support Services | Construction of tebeswet tea buying center | To construct tebeswet tea buying center | Tebeswet tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.653843, 35.62003 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1199469 | 1199469 | Equitable | equitable | 1199469 | 0 | 1199469 | 100 | 1199469 | 1199469 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
7370 | Crop Development and Management | Construction of milk cooler unit at Giachonge | To construct milk cooler unit at Giachonge | Milk cooler unit at Giachonge constructed | 3110599 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.23694, 36.178335 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/2020 | 6500000 | 6500000 | 6500000 | Equitable | EQUITABLE | 6500000 | 0 | 6499870 | 100 | 6499870 | 6499870 | 130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Expert general Marchant. Assessor remarks: Project had been vandalised.
7371 | Crop Development and Management | Construction of milk cooler unit at Giachonge | To construct milk cooler unit at Giachonge | Milk cooler unit at Giachonge constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.23694, 36.178335 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/2020 | 6500000 | 6499870 | 6499870 | Equitable | EQUITABLE | 6499870 | 0 | 6499870 | 100 | 6499870 | 6499870 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Expert general Marchant. Assessor remarks: Project had been vandalised.
7372 | Proposed construction of 1.no bee hive at ATC Soilo | Proposed construction of 1.no bee hive at ATC Soilo | To undertake the proposed construction of 1.no bee hive at ATC Soilo | Proposed construction of 1.no bee hive at ATC Soilo implemented | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 150000 | 150000 | 150000 | Equitable | Equitable | 150000 | 0 | 2299932 | 1533.3 | 2299932 | 2000000 | -2149932 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7373 | Proposed Renovation of Kibagenge cattle dip in Amalo ward Kuresoi South sub county | Proposed Renovation of Kibagenge cattle dip in Amalo ward Kuresoi South sub county | To undertake the proposed Renovation of Kibagenge cattle dip in Amalo ward Kuresoi South sub county | Proposed Renovation of Kibagenge cattle dip in Amalo ward Kuresoi South sub county implemented | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | N/A | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7374 | Crop Development and Management | Construction and installation of potato cold store | To construct and installation of potato cold store | And installation of potato cold store constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KERINGET | -0.427544, 35.68904 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 5369583 | 5369583 | 5369583 | Equitable | EQUITABLE | 5369583 | 0 | 0 | 0 | 0 | 5290000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Vandalized and demolished.
7375 | Crop Development and Management | Construction of CHEPNYALILO KWENET TEA buying center | To construct CHEPNYALILO KWENET TEA buying center | CHEPNYALILO KWENET TEA buying center constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.597523, 35.618778 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 1198750 | 99.9 | 1198750 | 1198750 | 1250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs to be met. Assessor remarks: Not completed.
7376 | Administration, Planning and Support Services | Construction of Kapsilibwo tea buying centre | To construct Kapsilibwo tea buying centre | Kapsilibwo tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.631137, 35.606343 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1199109 | 99.9 | 1199109 | 1199109 | 891 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but still under construction. Contractor: Don't know. Assessor remarks: The project is ongoing. No painting, no table tops and no toilets..
7377 | Administration, Planning and Support Services | Construction of Kiborowo Tea buying centre | To construct Kiborowo Tea buying centre | Kiborowo Tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1299580 | 108.3 | 1299580 | 1299600 | -99580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7378 | Crop Development and Management | Construction of tuiyobei tebesonik tea buying centre | To construct tuiyobei tebesonik tea buying centre | Tuiyobei tebesonik tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 1199600 | 100 | 1199600 | 1199600 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7379 | Crop Development and Management | Construction of a tea buying center at arorwet | To construct a tea buying center at arorwet | A tea buying center at arorwet constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.356669, 35.481787 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | EQUITABLE | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: Completed but was not painted.
7380 | Administration, Planning and Support Services | Construction of a tea buying center at chematich | To construct a tea buying center at chematich | A tea buying center at chematich constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.432266, 35.519267 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1175350 | 97.9 | 1175350 | 1200000 | 24650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The structure is incomplete.
7381 | Administration, Planning and Support Services | Construction of a tea buying center at karabariet | To construct a tea buying center at karabariet | A tea buying center at karabariet constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.302533 35.5297 0 800 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | equitable | 1400000 | 0 | 1399920 | 100 | 1399920 | 1399920 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
7382 | Administration, Planning and Support Services | Construction of a tea buying center at mwaragania | To construct a tea buying center at mwaragania | A tea buying center at mwaragania constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.302533 35.5297 0 800 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | Equitable | 1400000 | 0 | 666950 | 47.6 | 666950 | 666950 | 733050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
7383 | Crop Development and Management | Construction of a tea buying centre at Kio | To construct a tea buying centre at Kio | A tea buying centre at Kio constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.356669, 35.481787 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | EQUITABLE | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: Completed but was not painted.
7384 | Crop Development and Management | Construction and installation of potato cold store | To construct and installation of potato cold store | And installation of potato cold store constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427544, 35.68904 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 5369583 | 5290000 | 5290000 | Equitable | EQUITABLE | 5290000 | 0 | 0 | 0 | 0 | 5290000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Vandalized and demolished.
7385 | Crop Development and Management | Construction of Chepnyalilo Kwenet Tea buying center | To construct Chepnyalilo Kwenet Tea buying center | Chepnyalilo Kwenet Tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.597523, 35.618778 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1198750 | 1198750 | Equitable | EQUITABLE | 1198750 | 0 | 1198750 | 100 | 1198750 | 1198750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs to be met. Assessor remarks: Not completed.
7386 | Administration, Planning and Support Services | Construction of Kapsilibwo tea buying centre | To construct Kapsilibwo tea buying centre | Kapsilibwo tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.631137, 35.606343 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1199109.4 | 1199109.4 | Equitable | equitable | 1199109.4 | 0 | 1199109 | 100 | 1199109 | 1199109 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but still under construction. Contractor: Don't know. Assessor remarks: The project is ongoing. No painting, no table tops and no toilets..
7387 | Administration, Planning and Support Services | Construction of Kiborowo Tea buying centre | To construct Kiborowo Tea buying centre | Kiborowo Tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199600 | 1199600 | Equitable | equitable | 1199600 | 0 | 1299580 | 108.3 | 1299580 | 1299600 | -99980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7388 | Administration, Planning and Support Services | Construction of tea buying center at ararwet | To construct tea buying center at ararwet | Tea buying center at ararwet constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7389 | Administration, Planning and Support Services | Construction of tea buying center at lelechwet | To construct tea buying center at lelechwet | Tea buying center at lelechwet constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7390 | Administration, Planning and Support Services | Construction of tea buying center at tilalwo irongo | To construct tea buying center at tilalwo irongo | Tea buying center at tilalwo irongo constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7391 | Administration, Planning and Support Services | Construction of tea buying center kokwet | To construct tea buying center kokwet | Tea buying center kokwet constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.579408 35.574193 2412.1 4.199999809265137 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 399504 | 99.9 | 399504 | 399504 | 496 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: The project is viable but it doesn't meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is at lintel level and has stalled..
7392 | Crop Development and Management | Construction of tuiyobei tebesonik tea buying centre | To construct tuiyobei tebesonik tea buying centre | Tuiyobei tebesonik tea buying centre constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199600 | 1199600 | Equitable | EQUITABLE | 1199600 | 0 | 1199600 | 100 | 1199600 | 1199600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7393 | Administration, Planning and Support Services | completion and refurbishment of Kipkewa tea buying centre | To complete and refurbishment of Kipkewa tea buying centre | And refurbishment of Kipkewa tea buying centre completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.32762, 35.498182 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | equitable | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for a latrine.
7394 | Crop Development and Management | Construction of a tea buying center at arorwet | To construct a tea buying center at arorwet | A tea buying center at arorwet constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.356669, 35.481787 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | EQUITABLE | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: Completed but was not painted.
7395 | Administration, Planning and Support Services | Construction of a tea buying center at chematich | To construct a tea buying center at chematich | A tea buying center at chematich constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.432266, 35.519267 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1175350 | 97.9 | 1175350 | 1200000 | 24650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The structure is incomplete.
7396 | Administration, Planning and Support Services | Construction of a tea buying center at karabariet | To construct a tea buying center at karabariet | A tea buying center at karabariet constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1399920 | 1399920 | Equitable | equitable | 1399920 | 0 | 1399920 | 100 | 1399920 | 1399920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
7397 | Administration, Planning and Support Services | Construction of a tea buying center at mwaragania | To construct a tea buying center at mwaragania | A tea buying center at mwaragania constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | Equitable | 1400000 | 0 | 666950 | 47.6 | 666950 | 666950 | 733050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
7398 | Crop Development and Management | Construction of a tea buying centre at Kio | To construct a tea buying centre at Kio | A tea buying centre at Kio constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.356669, 35.481787 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | EQUITABLE | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: Completed but was not painted.
7399 | Administration, Planning and Support Services | Construction of Githima tea buying center | To construct Githima tea buying center | Githima tea buying center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.313788, 35.483612 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1046650 | 52.3 | 1046650 | 1097450 | 953350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is funtional.
7400 | Administration, Planning and Support Services | Kasarani slaughter house | To implement kasarani slaughter house for agricultural development and food production | Kasarani slaughter house completed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703, 36.309037 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1499999 | 100 | 1499999 | 1499999 | 1 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Land has been encroached.
7401 | Administration, Planning and Support Services | Completion of cereal store at msingi mwema | To complete cereal store at msingi mwema | Cereal store at msingi mwema completed | 3110599 | Other Infrastructure and Civil Works | MOLO | MARIASHONI | -0.340229, 35.808263 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Masonry walls do not exist.
7402 | Administration, Planning and Support Services | Construction of a slaughter slab at Mariashoni centre | To construct a slaughter slab at Mariashoni centre | A slaughter slab at Mariashoni centre constructed | 3110599 | Other Infrastructure and Civil Works | MOLO | MARIASHONI | -0.36843, 35.821484 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1300000 | 1300000 | 1300000 | Equitable | equitable | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Does not exist.
7403 | Crop Development and Management | Fencing of cattle auction | To secure cattle auction through fencing | Cattle auction fenced and secured | 3110599 | Other Infrastructure and Civil Works | NJORO | MAUCHE | -0.513917, 35.97637 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 1800000 | 1800000 | 1800000 | Equitable | EQUITABLE | 1800000 | 0 | 1812357 | 100.7 | 1812357 | 1812357 | -12357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7404 | Construction of perimeter wall in kenyatta slaughter house | Construction of perimeter wall in kenyatta slaughter house | To construct perimeter wall in kenyatta slaughter house | Perimeter wall in kenyatta slaughter house constructed | 3110599 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7405 | Administration, Planning and Support Services | Construction and expansion of Gatamaiyu Fish Pond | To construct and expansion of Gatamaiyu Fish Pond | And expansion of Gatamaiyu Fish Pond constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.612613, 36.380458 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 499800 | 100 | 499800 | 499800 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need close monitoring of groups management.
7406 | Administration, Planning and Support Services | Kasarani slaughter house | To implement kasarani slaughter house for agricultural development and food production | Kasarani slaughter house completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.309037 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 1500000 | 1499999 | 1499999 | Equitable | Equitable | 1499999 | 0 | 1499999 | 100 | 1499999 | 1499999 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Land has been encroached.
7407 | Administration, Planning and Support Services | Completion of cereal store at msingi mwema | To complete cereal store at msingi mwema | Cereal store at msingi mwema completed | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.340229, 35.808263 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Masonry walls do not exist.
7408 | Administration, Planning and Support Services | Construction of a slaughter slab at Mariashoni centre | To construct a slaughter slab at Mariashoni centre | A slaughter slab at Mariashoni centre constructed | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.36843, 35.821484 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1300000 | 1300000 | 1300000 | Equitable | equitable | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Does not exist.
7409 | Crop Development and Management | Fencing of cattle auction | To secure cattle auction through fencing | Cattle auction fenced and secured | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.513917, 35.97637 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 1800000 | 1812357 | 1812357 | Equitable | EQUITABLE | 1812357 | 0 | 1812357 | 100 | 1812357 | 1812357 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
7410 | Construction of perimeter wall in kenyatta slaughter house | Construction of perimeter wall in kenyatta slaughter house | To construct perimeter wall in kenyatta slaughter house | Perimeter wall in kenyatta slaughter house constructed | 3110599 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7411 | Crop Development and Management | Construction of fish store at Kamere Beach | To construct fish store at Kamere Beach | Fish store at Kamere Beach constructed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | OLKARIA | -0.817132 36.32586 1922.199951171875 24.67099952697754 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1499994 | 100 | 1499994 | 1499994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
7412 | Administration, Planning and Support Services | buying of motor boat for kamere beach youth groups and beach hustler group | To procure motor boat for kamere beach youth groups and beach hustler group | Motor boat for kamere beach youth groups and beach hustler group procured | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.819698 36.322931 1932.699951171875 35.104000091552734 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | equitable | 4000000 | 0 | 3965000 | 99.1 | 3965000 | 3965000 | 35000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Once the project is finished since there is no other hospital. Assessor remarks: The containers are being refurbished but handing over done.
7413 | Crop Development and Management | Construction of fish store at Kamere Beach | To construct fish store at Kamere Beach | Fish store at Kamere Beach constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817132 36.32586 1922.199951171875 24.67099952697754 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499994 | 1499994 | Equitable | EQUITABLE | 1499994 | 0 | 1499994 | 100 | 1499994 | 1499994 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
7414 | Crop Development and Management | Construction of toilet at kokwomoi cattle dip | To construct toilet at kokwomoi cattle dip | Toilet at kokwomoi cattle dip constructed | 3110599 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.022283, 36.075469 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/2020 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 297848 | 85.1 | 297848 | 268000 | 52152 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: N/S. Assessor remarks: Require repair and water supply.
7415 | Administration, Planning and Support Services | Construction of Taita Slaughter Slab | To construct Taita Slaughter Slab | Taita Slaughter Slab constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | TINET | -0.570268 35.61587 0 500 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 852725 | 42.6 | 852725 | 1699838 | 1147275 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing almost complete.
7416 | Crop Development and Management | Fencing of Cooling Plant at Milima Mitatu | To secure Cooling Plant at Milima Mitatu through fencing | Cooling Plant at Milima Mitatu fenced and secured | 3110599 | Other Infrastructure and Civil Works | MOLO | TURI | -0.297121 35.713899 2654.8 72.9000015258789 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
7417 | Administration, Planning and Support Services | Construction of Taita Slaughter Slab | To construct Taita Slaughter Slab | Taita Slaughter Slab constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.570268 35.61587 0 500 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 1999838.44 | 1999838.44 | Equitable | N/A | 1999838.44 | 0 | 852725 | 42.6 | 852725 | 1699838 | 1147113.44 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing almost complete.
7418 | Administration, Planning and Support Services | Renovation of Kandutura Cereal Store | To rehabilitate Kandutura Cereal Store to restore functionality | Kandutura Cereal Store rehabilitated | 3110599 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | equitable | 600000 | 0 | 524100 | 87.4 | 524100 | 600000 | 75900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
7419 | purchase of mechanization equipment (Tractor, Bailer and mower | purchase of mechanization equipment (Tractor, Bailer and mower | To procure mechanization equipment (Tractor, Bailer and mower | Mechanization equipment (Tractor, Bailer and mower procured | 3110706 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 14311668.6 | 14311668.6 | Equitable | N/A | 14311668.6 | 0 | 6199852 | 43.3 | 6199852 | 0 | 8111816.6 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7420 | Crop Development and Management | Purchase of Fishing Gear | To procure Fishing Gear | Fishing Gear procured | 3111103 | Purchase of Agricultural Machinery and Equipment | NAIVASHA | LAKEVIEW | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999000 | 99.9 | 999000 | 0 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7421 | Crop Development and Management | Purchase of feed formulation mixer for poultry | To procure feed formulation mixer for poultry | Feed formulation mixer for poultry procured | 3111120 | Purchase of Specialized Plant. - | BAHATI | BAHATI | -0.181879, 36.131532 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It has been in use.
7422 | Administration, Planning and Support Services | Kirima milk cooler - installation of milk cooler and accessories | To implement kirima milk cooler - installation of milk cooler and accessories for agricultural development and food production | Kirima milk cooler - installation of milk cooler and accessories completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Biashara-Naivasha | -0.632517, 36.488908 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 5000000 | 0 | 5000000 | Equitable | equitable | 5000000 | 0 | 8100000 | 0 | 8100000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working perfectly.
7423 | Crop Development and Management | Elementaita livestock farm input support program | To implement elementaita livestock farm input support program for agricultural development and food production | Elementaita livestock farm input support program completed | 3111120 | Purchase of Specialized Plant. - | Gilgil | Elementaita | -0.615563 36.128245 2174.5 5.599999904632568 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | EQUITABLE | 4000000 | 0 | 3997940 | 99.9 | 3997940 | 0 | 2060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7424 | Crop Development and Management | Gilgil youth chicken incubators | To implement gilgil youth chicken incubators for agricultural development and food production | Gilgil youth chicken incubators completed | 3111120 | Purchase of Specialized Plant. - | GILGIL | GILGIL | -0.498993 36.322424 1990.699951171875 28.434999465942383 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999999 | 100 | 999999 | 0 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
7425 | Administration, Planning and Support Services | Procurement of coffee pulping machine for Wikurie co operetive Society in Wesege ward subukia sub county | To procure and supply coffee pulping machine for Wikurie co operetive Society in Wesege ward subukia sub county | Coffee pulping machine for Wikurie co operetive Society in Wesege ward subukia sub county procured and supplied | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7426 | Administration, Planning and Support Services | Procurement of coffee pulping machine for Wikurie cooperative Society in Waseges ward subukia sub county | To procure and supply coffee pulping machine for Wikurie cooperative Society in Waseges ward subukia sub county | Coffee pulping machine for Wikurie cooperative Society in Waseges ward subukia sub county procured and supplied | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 1997500 | 1997500 | Equitable | N/A | 1997500 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7427 | Administration, Planning and Support Services | purchase and installation of pulping machine for Jumatato sacco cooperative | To procure and install pulping machine for Jumatato sacco cooperative | Pulping machine for Jumatato sacco cooperative procured and installed | 3111120 | Purchase of Specialized Plant. - | SUBUKIA | KABAZI | -0.13503 36.1535 0 2218 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1000000 | 50 | 1000000 | 2000000 | 1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Delight pro ltd. Assessor remarks: Requires drying beds.
7428 | Administration, Planning and Support Services | Purchase of Pulping Machine for Jumatatu society | To procure Pulping Machine for Jumatatu society | Pulping Machine for Jumatatu society procured | 3111120 | Purchase of Specialized Plant. - | SUBUKIA | KABAZI | -0.08223 36.16987 0 1381 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1900000 | 1900000 | Equitable | equitable | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
7429 | Administration, Planning and Support Services | purchase and installation of pulping machine for Jumatato sacco cooperative | To procure and install pulping machine for Jumatato sacco cooperative | Pulping machine for Jumatato sacco cooperative procured and installed | 3111120 | Purchase of Specialized Plant. - | Subukia | Kabazi | -0.13503 36.1535 0 2218 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1000000 | 50 | 1000000 | 2000000 | 1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Delight pro ltd. Assessor remarks: Requires drying beds.
7430 | Administration, Planning and Support Services | Purchase of Pulping Machine for Jumatatu society | To procure Pulping Machine for Jumatatu society | Pulping Machine for Jumatatu society procured | 3111120 | Purchase of Specialized Plant. - | Subukia | Kabazi | -0.08223 36.16987 0 1381 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1900000 | 1900000 | Equitable | equitable | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
7431 | Crop Development and Management | purchase of 4 no. hatcheries and eggs for breeding | To procure 4 no. hatcheries and eggs for breeding | 4 no. hatcheries and eggs for breeding procured | 3111120 | Purchase of Specialized Plant. - | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 973190 | 973190 | 973190 | Equitable | N/A | 973190 | 0 | 922740 | 94.8 | 922740 | 488600 | 50450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7432 | Administration, Planning and Support Services | Completion of Purchase and Installation of milk Coolers in central | To complete Purchase and Installation of milk Coolers in central | Purchase and Installation of milk Coolers in central completed | 3111120 | Purchase of Specialized Plant. - | NAIVASHA | MAIELLA | -0.729928, 36.230427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 3500000 | 3500000 | Equitable | equitable | 3500000 | 0 | 2168567 | 62 | 2168567 | 3500000 | 1331433 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
7433 | Administration, Planning and Support Services | Completion of Purchase and Installation of milk Coolers in maiella | To complete Purchase and Installation of milk Coolers in maiella | Purchase and Installation of milk Coolers in maiella completed | 3111120 | Purchase of Specialized Plant. - | NAIVASHA | MAIELLA | -0.729928, 36.230427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 3500000 | 3500000 | Equitable | equitable | 3500000 | 0 | 2168567 | 62 | 2168567 | 3500000 | 1331433 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
7434 | Administration, Planning and Support Services | Malewa youth and women group incubator | To implement malewa youth and women group incubator for agricultural development and food production | Malewa youth and women group incubator completed | 3111120 | Purchase of Specialized Plant. - | GILGIL | MALEWA WEST | -0.684685, 36.453053 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 985100 | 98.5 | 985100 | 985100 | 14900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
7435 | Administration, Planning and Support Services | Construction of a potato cooling plant in Masai Centre in Mauche Ward | To construct a potato cooling plant in Masai Centre in Mauche Ward | A potato cooling plant in Masai Centre in Mauche Ward constructed | 3111120 | Purchase of Specialized Plant. - | NJORO | MAUCHE | -0.50456, 35.958508 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 5500000 | 5500000 | 5500000 | Equitable | equitable | 5500000 | 0 | 5299999 | 96.4 | 5299999 | 5299999 | 200001 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Solar panels vandalized and stolen.
7436 | Crop Development and Management | Purchase of incubators for wemen groups | To procure incubators for wemen groups | Incubators for wemen groups procured | 3111120 | Purchase of Specialized Plant. - | GILGIL | MURINDAT | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 855020 | 855020 | 855020 | Equitable | N/A | 855020 | 0 | 851760 | 99.6 | 851760 | 0 | 3260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7437 | Administration, Planning and Support Services | Completion of Purchase and Installation of milk Coolers in central | To complete Purchase and Installation of milk Coolers in central | Purchase and Installation of milk Coolers in central completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.729928, 36.230427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 3500000 | 3500000 | Equitable | equitable | 3500000 | 0 | 2168567 | 62 | 2168567 | 3500000 | 1331433 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
7438 | Administration, Planning and Support Services | Completion of Purchase and Installation of milk Coolers in maiella | To complete Purchase and Installation of milk Coolers in maiella | Purchase and Installation of milk Coolers in maiella completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.729928, 36.230427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 3500000 | 3500000 | Equitable | equitable | 3500000 | 0 | 2168567 | 62 | 2168567 | 3500000 | 1331433 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
7439 | Administration, Planning and Support Services | Malewa youth and women group incubator | To implement malewa youth and women group incubator for agricultural development and food production | Malewa youth and women group incubator completed | 3111120 | Purchase of Specialized Plant. - | Gilgil | Malewa West | -0.684685, 36.453053 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 1000000 | 998200 | 998200 | Equitable | equitable | 998200 | 0 | 985100 | 98.7 | 985100 | 985100 | 13100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
7440 | Crop Development and Management | Purchase of Bee hives | To procure Bee hives | Bee hives procured | 3111120 | Purchase of Specialized Plant. - | RONGAI | SOIN | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 513121 | 513121 | 513121 | Equitable | N/A | 513121 | 0 | 512940 | 100 | 512940 | 848331 | 181 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7441 | Administration, Planning and Support Services | purchase and supply of fishing equipments for Kenyatta dam | To procure and supply fishing equipments for Kenyatta dam | Fishing equipments for Kenyatta dam procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi North | Sirikwa | -0.29891, 35.63593 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 199050 | 99.5 | 199050 | 200000 | 950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,,but proper documentation is needed when supplying the equipments. Assessor remarks: No fishing at the site,and no known individuals owning the equipments.
7442 | Crop Development and Management | Purchase of Hass Avocado Seedlings for distribution | To procure Hass Avocado Seedlings for distribution | Hass Avocado Seedlings for distribution procured | 3111301 | Purchase of Certified Crop Seed | GILGIL | ELEMENTAITA | -0.583749, 36.108703 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999600 | 100 | 3999600 | 0 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well coming.
7443 | Crop Development and Management | Supply of avocado seedlings to elburgon ward farmers | To implement supply of avocado seedlings to elburgon ward farmers for agricultural development and food production | Supply of avocado seedlings to elburgon ward farmers completed | 3111301 | Purchase of Certified Crop Seed | Molo | Elburgon | -0.300373 35.797558 0 52.400001525878906 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2990000 | 99.7 | 2990000 | 183 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7444 | Crop Development and Management | Purchases of avocado seedlings | To implement purchases of avocado seedlings for agricultural development and food production | Purchases of avocado seedlings completed | 3111301 | Purchase of Certified Crop Seed | BAHATI | KABATINI | -0.231617 36.155611 1942.34033203125 15.652999877929688 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7445 | Crop Development and Management | Supply of avocado seedlings | To implement supply of avocado seedlings for agricultural development and food production | Supply of avocado seedlings completed | 3111301 | Purchase of Certified Crop Seed | KURESOI NORTH | KIPTORORO | -0.300981 35.531995 2587.10009765625 60 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999700 | 100 | 2999700 | 0 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Due for repair. Viable: Yes. Assessor remarks: Floor improvement.
7446 | Crop Development and Management | Purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111301 | Purchase of Certified Crop Seed | Kuresoi North | Kiptororo | -0.300981 35.531995 2587.10009765625 60 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1993140 | 99.7 | 1993140 | 0 | 6860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Due for repair. Viable: Yes. Assessor remarks: Floor improvement.
7447 | Crop Development and Management | Purchase of avocado seedlings (hass) for distribution to farmers in the Ward | To procure avocado seedlings (hass) for distribution to farmers in the Ward | Avocado seedlings (hass) for distribution to farmers in the Ward procured | 3111301 | Purchase of Certified Crop Seed | NJORO | MAU NAROK | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/20 | 2018/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999900 | 100 | 999900 | 0 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7448 | Crop Development and Management | Purchases of avocado seedlings | To implement purchases of avocado seedlings for agricultural development and food production | Purchases of avocado seedlings completed | 3111301 | Purchase of Certified Crop Seed | RONGAI | MENENGAI WEST | -0.14054, 35.997803 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1839855 | 1839855 | 1839855 | Equitable | EQUITABLE | 1839855 | 0 | 1839855 | 100 | 1839855 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: More seedlings should be distributed.
7449 | Crop Development and Management | Avocado seedlings in sumeek/boror | To implement avocado seedlings in sumeek/boror for agricultural development and food production | Avocado seedlings in sumeek/boror completed | 3111301 | Purchase of Certified Crop Seed | RONGAI | MOSOP | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999800 | 100 | 1999800 | 0 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
7450 | Crop Development and Management | Avocados seedlings in Ngata/ogilgei | To implement avocados seedlings in ngata/ogilgei for agricultural development and food production | Avocados seedlings in Ngata/ogilgei completed | 3111301 | Purchase of Certified Crop Seed | RONGAI | MOSOP | -0.30116, 35.955023 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999900 | 100 | 999900 | 0 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Kapkoros group.
7451 | Crop Development and Management | Purchase and supply of dwaf pawpaws to nyondia farmers | To procure and supply dwaf pawpaws to nyondia farmers | Dwaf pawpaws to nyondia farmers procured and supplied | 3111301 | Purchase of Certified Crop Seed | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2793371 | 2793371 | 2793371 | Equitable | EQUITABLE | 2793371 | 0 | 2690080 | 96.3 | 2690080 | 2690800 | 103291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7452 | Crop Development and Management | purchase of drips and 1000 litres tanks for Nyondia farmers | To procure drips and 1000 litres tanks for Nyondia farmers | Drips and 1000 litres tanks for Nyondia farmers procured | 3111301 | Purchase of Certified Crop Seed | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1999660 | 100 | 1999660 | 2690800 | 340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7453 | Crop Development and Management | Purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111301 | Purchase of Certified Crop Seed | Rongai | Menengai West | -0.14054, 35.997803 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2790000 | 93 | 2790000 | 2000000 | 210000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: More seedlings should be distributed.
7454 | Crop Development and Management | Purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111301 | Purchase of Certified Crop Seed | NAIVASHA | NAIVASHA EAST | -0.80511, 36.533803 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799800 | 100 | 799800 | 0 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ovacadoes supplied but not sufficient.
7455 | Crop Development and Management | Purchase of avocado seedlings (hass) for distribution to farmers in the Ward | To procure avocado seedlings (hass) for distribution to farmers in the Ward | Avocado seedlings (hass) for distribution to farmers in the Ward procured | 3111301 | Purchase of Certified Crop Seed | NJORO | NJORO | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999800 | 100 | 1999800 | 0 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7456 | Crop Development and Management | Buying of pyrethrum seedlings | To procure pyrethrum seedlings | Pyrethrum seedlings procured | 3111301 | Purchase of Certified Crop Seed | KURESOI NORTH | NYOTA | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1474566 | 1474566 | 1474566 | Equitable | N/A | 1474566 | 0 | 1474566 | 100 | 1474566 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
7457 | Crop Development and Management | Hass avocado seedlings for Subukia ward | To implement hass avocado seedlings for subukia ward for agricultural development and food production | Hass avocado seedlings for Subukia ward completed | 3111301 | Purchase of Certified Crop Seed | SUBUKIA | SUBUKIA | -0.023041, 36.201896 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The hass avocado trees are doing well in the farms.
7458 | Crop Development and Management | Construction of umoja tea buying center at ambiska | To construct umoja tea buying center at ambiska | Umoja tea buying center at ambiska constructed | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Amalo | -0.615322, 35.65657 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1215610 | 81 | 1215610 | 1500000 | 284390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7459 | Administration, Planning and Support Services | Rehabilitation of ambosket dip | To rehabilitate ambosket dip to restore functionality | Ambosket dip rehabilitated | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Amalo | -0.588523 35.684659 2531.300048828125 77.5999984741211 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: works done well.
7460 | Administration, Planning and Support Services | Rehabilitation of kitoben dip | To rehabilitate kitoben dip to restore functionality | Kitoben dip rehabilitated | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Amalo | -0.632327, 35.673543 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 406972 | 406972 | 406972 | Equitable | equitable | 406972 | 0 | 0 | 0 | 0 | 406972 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: work not done.
7461 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha | To implement procure and supply of one (1) month old improved kienyenji chicks for women group in biashara ward naivasha for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | NAIVASHA | BIASHARA-NAIVASHA | -0.631927, 36.508452 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 4000000 | 4000000 | 4000000 | Equitable | EQUITABLE | 4000000 | 0 | 3999880 | 100 | 3999880 | 3999880 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Capacity building ,and supply of more.
7462 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for Gituru women group in Biashara ward Naivasha | To implement procure and supply of one (1) month old improved kienyenji chicks for gituru women group in biashara ward naivasha for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for Gituru women group in Biashara ward Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Biashara-Naivasha | -0.631927, 36.508452 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | EQUITABLE | 2500000 | 0 | 2392035 | 95.7 | 2392035 | 3999880 | 107965 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Capacity building ,and supply of more.
7463 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for Kinamba women group in Biashara ward Naivasha | To implement procure and supply of one (1) month old improved kienyenji chicks for kinamba women group in biashara ward naivasha for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for Kinamba women group in Biashara ward Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Biashara-Naivasha | -0.631927, 36.508452 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | EQUITABLE | 2500000 | 0 | 2392035 | 95.7 | 2392035 | 3999880 | 107965 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Capacity building ,and supply of more.
7464 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha | To implement procure and supply of one (1) month old improved kienyenji chicks for women group in biashara ward naivasha for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Biashara-Naivasha | -0.631927, 36.508452 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 4000000 | 3999880 | 3999880 | Equitable | EQUITABLE | 3999880 | 0 | 3999880 | 100 | 3999880 | 3999880 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Capacity building ,and supply of more.
7465 | Crop Development and Management | purchase and supply of 1 month month old chicks for farmers in Dundori ward | To procure and supply 1 month month old chicks for farmers in Dundori ward | 1 month month old chicks for farmers in Dundori ward procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Bahati | Dundori | -0.263156, 36.187378 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 956814 | 95.7 | 956814 | 0 | 43186 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Can not be traced since it's longtime since the exercise was undertaken..
7466 | Administration, Planning and Support Services | Supply of improved kienyeji chicken to Elburgon farmers. | To implement supply of improved kienyeji chicken to elburgon farmers. for agricultural development and food production | Supply of improved kienyeji chicken to Elburgon farmers. completed | 3111302 | Purchase of Animals and Breeding Stock | Molo | Elburgon | -0.294731 35.799338 0 838.1790161132812 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000289 | 1000289 | 1000289 | Equitable | equitable | 1000289 | 0 | 1000289 | 100 | 1000289 | 183 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7467 | Crop Development and Management | Equipping and operationalization of fish processing plant in Naivasha | To equip and operationalization of fish processing plant in Naivasha with necessary facilities and equipment | And operationalization of fish processing plant in Naivasha equipped | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 6544400 | 6544400 | 6544400 | Equitable | EQUITABLE | 6544400 | 0 | 1998820 | 30.5 | 1998820 | 5459432 | 4545580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7468 | Livestock Resource Management and Development | Procure and delivery of breeding dopper sheep in Elementaita ward | To implement procure and delivery of breeding dopper sheep in elementaita ward for agricultural development and food production | Procure and delivery of breeding dopper sheep in Elementaita ward completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 999999 | 50 | 999999 | 0 | 1000001 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7469 | Livestock Resource Management and Development | Procure and delivery of breeding stock beef | To implement procure and delivery of breeding stock beef for agricultural development and food production | Procure and delivery of breeding stock beef completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 32480684 | 216.5 | 32480684 | 2519316 | -17480684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7470 | Fisheries Development | Procure and delivery of breeding stock sheep and goats | To implement procure and delivery of breeding stock sheep and goats for agricultural development and food production | Procure and delivery of breeding stock sheep and goats completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 13000000 | 13000000 | Equitable | equitable | 13000000 | 0 | 7941466 | 61.1 | 7941466 | 2519316 | 5058534 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7471 | Livestock Resource Management and Development | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha | To implement procure and supply of one (1) month old improved kienyenji chicks for women group in biashara ward naivasha for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for women group in Biashara ward Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000001 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7472 | Livestock Resource Management and Development | Procure and supply of one (1) month old improved kienyenji chicks for women groups in Elementaita ward | To implement procure and supply of one (1) month old improved kienyenji chicks for women groups in elementaita ward for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for women groups in Elementaita ward completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000002 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7473 | Livestock Resource Management and Development | Procure and supply of one (1) month old improved kienyenji chicks for women groups | To implement procure and supply of one (1) month old improved kienyenji chicks for women groups for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for women groups completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 5000000 | 5000000 | Equitable | EQUITABLE | 5000000 | 0 | 11132287 | 222.6 | 11132287 | 0 | -6132287 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7474 | Livestock Resource Management and Development | Procurement and delivery of one month old chicks to Simotwet self help group in Kiptororo ward, Kuresoi North Sub county | To procure and supply and delivery of one month old chicks to Simotwet self help group in Kiptororo ward, Kuresoi North Sub county | And delivery of one month old chicks to Simotwet self help group in Kiptororo ward, Kuresoi North Sub county procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1976000 | 1976000 | 1976000 | Equitable | N/A | 1976000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7475 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for different groups | To implement procure and supply of one (1) month old improved kienyenji chicks for different groups for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for different groups completed | 3111302 | Purchase of Animals and Breeding Stock | Bahati | Kabatini | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1909000 | 95.5 | 1909000 | 0 | 91000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7476 | Crop Development and Management | purchase of milking goat | To procure milking goat | Milking goat procured | 3111302 | Purchase of Animals and Breeding Stock | Bahati | Kabatini | -0.214959 36.16585 2031.300048828125 39.106998443603516 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2914651 | 2914651 | 2914651 | Equitable | EQUITABLE | 2914651 | 0 | 2914066 | 100 | 2914066 | 0 | 585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Currently the borehole has a court case however nawasco is not able to do management it's done by residents.
7477 | Administration, Planning and Support Services | Youth empowerment (Purchase of 10 Incubators) | To implement youth empowerment (purchase of 10 incubators) for agricultural development and food production | Youth empowerment (Purchase of 10 Incubators) completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 991000 | 99.1 | 991000 | 1000000 | 9000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Done and in operation.
7478 | Administration, Planning and Support Services | Fencing potato cooler at keringet | To secure potato cooler at keringet through fencing | Potato cooler at keringet fenced and secured | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Keringet | -0.427567, 35.68865 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project vandalized by heavy storm then materials were stolen by residence.
7479 | Administration, Planning and Support Services | purchase and supply of eggs incubators | To procure and supply eggs incubators | Eggs incubators procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Keringet | -0.431263, 35.6896 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 666960 | 66.7 | 666960 | 998200 | 333040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
7480 | Administration, Planning and Support Services | Youths/women empowerment(incubators) | To implement youths/women empowerment(incubators) for agricultural development and food production | Youths/women empowerment(incubators) completed | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Kiptagich | -0.59902 35.61123 2497.2000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | equitable | 1300000 | 0 | 1297600 | 99.8 | 1297600 | 1297600 | 2400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: In bad condition.
7481 | Crop Development and Management | Malewa women daily goats | To implement malewa women daily goats for agricultural development and food production | Malewa women daily goats completed | 3111302 | Purchase of Animals and Breeding Stock | GILGIL | MALEWA WEST | -0.684685 36.471073 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999000 | 99.9 | 999000 | 0 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been maintained over years.
7482 | Crop Development and Management | Purchase of Chicks for Community Based Organization in Menengai and Kiratina | To procure Chicks for Community Based Organization in Menengai and Kiratina | Chicks for Community Based Organization in Menengai and Kiratina procured | 3111302 | Purchase of Animals and Breeding Stock | NAKURU EAST | MENENGAI | -0.275685 36.115371 1856.300048828125 16.059999465942383 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4997190 | 99.9 | 4997190 | 0 | 2810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs renovation.
7483 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 3500000 | 3500000 | Equitable | EQUITABLE | 3500000 | 0 | 1431750 | 40.9 | 1431750 | 0 | 2068250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7484 | Crop Development and Management | Purchase of improved kienyeji | To procure improved kienyeji | Improved kienyeji procured | 3111302 | Purchase of Animals and Breeding Stock | Molo | Mariashoni | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 956814 | 95.7 | 956814 | 0 | 43186 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7485 | Crop Development and Management | Purchase of daily goats | To procure daily goats | Daily goats procured | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Mauche | -0.49481 35.957357 2463.5 12.600000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 3098368 | 3098368 | 3098368 | Equitable | EQUITABLE | 3098368 | 0 | 2988368 | 96.4 | 2988368 | 1924100 | 110000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
7486 | Crop Development and Management | Kiratina great women co-op society supply of 1 day old chicks | To implement kiratina great women co-op society supply of 1 day old chicks for agricultural development and food production | Kiratina great women co-op society supply of 1 day old chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7487 | Administration, Planning and Support Services | Menengai ward supply of 1 day old chicks to PLWD | To implement menengai ward supply of 1 day old chicks to plwd for agricultural development and food production | Menengai ward supply of 1 day old chicks to PLWD completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.275696 36.115354 1856.300048828125 19.395999908447266 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 980441 | 98 | 980441 | 1000000 | 19559 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs renovation.
7488 | Crop Development and Management | Supply of incubators and 2 feed mixers to Menengai women co-op society | To implement supply of incubators and 2 feed mixers to menengai women co-op society for agricultural development and food production | Supply of incubators and 2 feed mixers to Menengai women co-op society completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.275785, 36.115287 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1944000 | 97.2 | 1944000 | 0 | 56000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The incubators aren't working.
7489 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1980200 | 99 | 1980200 | 0 | 19800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
7490 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for Naivasha East | To implement procure and supply of one (1) month old improved kienyenji chicks for naivasha east for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for Naivasha East completed | 3111302 | Purchase of Animals and Breeding Stock | NAIVASHA | NAIVASHA EAST | -0.805147, 36.53381 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1698980 | 99.9 | 1698980 | 0 | 1020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Chicks supplied majority didn't survive.
7491 | Crop Development and Management | Procure and delivery of breeding of Dairy goat project in Njoro Ward | To implement procure and delivery of breeding of dairy goat project in njoro ward for agricultural development and food production | Procure and delivery of breeding of Dairy goat project in Njoro Ward completed | 3111302 | Purchase of Animals and Breeding Stock | NJORO | NJORO | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997930 | 99.9 | 2997930 | 0 | 2070 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
7492 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks for Njoro | To implement procure and supply of one (1) month old improved kienyenji chicks for njoro for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks for Njoro completed | 3111302 | Purchase of Animals and Breeding Stock | NJORO | NJORO | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 3177917 | 3177917 | 3177917 | Equitable | N/A | 3177917 | 0 | 3164840 | 99.6 | 3164840 | 0 | 13077 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7493 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Nessuit | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1485150 | 99 | 1485150 | 0 | 14850 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7494 | Administration, Planning and Support Services | Purchase and supply of one month old chicks | To procure and supply one month old chicks | One month old chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Njoro | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2072775 | 2072775 | 2072775 | Equitable | equitable | 2072775 | 0 | 2072395 | 100 | 2072395 | 0 | 380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
7495 | Administration, Planning and Support Services | Additional fund to construction of barina cattle dip | To implement additional fund to construction of barina cattle dip for agricultural development and food production | Additional fund to construction of barina cattle dip completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | -0.065365 36.063149 1637 9.5 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 117304 | 117304 | 117304 | Equitable | equitable | 117304 | 0 | 107304 | 91.5 | 107304 | 107304 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require renovation.
7496 | Administration, Planning and Support Services | Purchase of 4 manual honey extractor to different groups | To procure 4 manual honey extractor to different groups | 4 manual honey extractor to different groups procured | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 450000 | 450000 | 450000 | Equitable | equitable | 450000 | 0 | 370869 | 82.4 | 370869 | 370869 | 79131 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7497 | Administration, Planning and Support Services | Purchase of bee hives to soin groups | To procure bee hives to soin groups | Bee hives to soin groups procured | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 848331 | 848331 | 848331 | Equitable | equitable | 848331 | 0 | 848331 | 100 | 848331 | 848331 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
7498 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Solai | 0.086992 36.134488 1509.3238525390625 10.145999908447266 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1336816 | 1336816 | 1336816 | Equitable | EQUITABLE | 1336816 | 0 | 1299300 | 97.2 | 1299300 | 0 | 37516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done although it still needs maintenance.
7499 | Crop Development and Management | Supply of one month old improved kienyeji chicks to solai women group | To implement supply of one month old improved kienyeji chicks to solai women group for agricultural development and food production | Supply of one month old improved kienyeji chicks to solai women group completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Solai | 0.086992 36.134488 1509.3238525390625 10.145999908447266 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | EQUITABLE | 1800000 | 0 | 1799640 | 100 | 1799640 | 0 | 360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done although it still needs maintenance.
7500 | Crop Development and Management | Purchase of 174 hatchery capacity incubators and back up generators | To procure 174 hatchery capacity incubators and back up generators | 174 hatchery capacity incubators and back up generators procured | 3111302 | Purchase of Animals and Breeding Stock | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 650000 | 650000 | 650000 | Equitable | EQUITABLE | 650000 | 0 | 644000 | 99.1 | 644000 | 650000 | 6000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7501 | Crop Development and Management | Woman empowerment(Procure and supply of one (1) month old improved kienyenji chicks) | To implement woman empowerment(procure and supply of one (1) month old improved kienyenji chicks) for agricultural development and food production | Woman empowerment(Procure and supply of one (1) month old improved kienyenji chicks) completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Visoi | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 954500 | 95.5 | 954500 | 0 | 45500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7502 | Crop Development and Management | Supply of one month old chicks to shg/PLWD/youth | To implement supply of one month old chicks to shg/plwd/youth for agricultural development and food production | Supply of one month old chicks to shg/PLWD/youth completed | 3111302 | Purchase of Animals and Breeding Stock | SUBUKIA | WASEGES | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995000 | 99.8 | 1995000 | 0 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7503 | Crop Development and Management | Purchase of 1 month old chicks for women groups and PLWD | To procure 1 month old chicks for women groups and PLWD | 1 month old chicks for women groups and PLWD procured | 3111302 | Purchase of Animals and Breeding Stock | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2649167 | 2649167 | 2649167 | Equitable | EQUITABLE | 2649167 | 0 | 2530000 | 95.5 | 2530000 | 0 | 119167 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
7504 | Crop Development and Management | Procurement and distribution of Avocado seedlings to selected farmers in the Biashara Naivasha ward | To procure and supply and distribution of Avocado seedlings to selected farmers in the Biashara Naivasha ward | And distribution of Avocado seedlings to selected farmers in the Biashara Naivasha ward procured and supplied | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 32870900 | 1643.5 | 32870900 | 2700003 | -30870900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7505 | Crop Development and Management | Procurement and distribution of Avocado seedlings to selected farmers in the target areas | To procure and supply and distribution of Avocado seedlings to selected farmers in the target areas | And distribution of Avocado seedlings to selected farmers in the target areas procured and supplied | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 35000000 | 33000000 | 33000000 | Equitable | N/A | 33000000 | 0 | 32870900 | 99.6 | 32870900 | 2700003 | 129100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7506 | Crop Development and Management | Procurement and distribution of seedlings (pyrethrum) | To procure and supply and distribution of seedlings (pyrethrum) | And distribution of seedlings (pyrethrum) procured and supplied | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 35000000 | 2369790.7 | 2369790.7 | Equitable | EQUITABLE | 2369790.7 | 0 | 2000000 | 84.4 | 2000000 | 2700003 | 369790.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7507 | Crop Development and Management | purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | Bahati | Kabatini | -0.216826, 36.162034 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019 | 2100000 | 2100000 | 2100000 | Equitable | EQUITABLE | 2100000 | 0 | 2093000 | 99.7 | 2093000 | 0 | 7000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Crop input supplies. Assessor remarks: Project was partially successful those who survived are currently been harvested.
7508 | Crop Development and Management | purchase of Avocado seedling in kihingo ward | To procure Avocado seedling in kihingo ward | Avocado seedling in kihingo ward procured | 3111305 | Beautification and Tree Planting | Njoro | Kihingo | -0.482525, 35.981882 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2025 | 863236 | 863236 | 863236 | Equitable | EQUITABLE | 863236 | 0 | 860330 | 99.7 | 860330 | 0 | 2906 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Individual farmers were given seedlings.
7509 | Administration, Planning and Support Services | Supply of pyrethrum seedlings | To implement supply of pyrethrum seedlings for agricultural development and food production | Supply of pyrethrum seedlings completed | 3111305 | Beautification and Tree Planting | Kuresoi North | Kiptororo | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7510 | Crop Development and Management | Purchase of Certified Crop Seeds (Potato Seeds) | To procure Certified Crop Seeds (Potato Seeds) | Certified Crop Seeds (Potato Seeds) procured | 3111305 | Beautification and Tree Planting | Njoro | Mau Narok | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1538799 | 1538799 | 1538799 | Equitable | EQUITABLE | 1538799 | 0 | 1536000 | 99.8 | 1536000 | 0 | 2799 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7511 | Crop Development and Management | purchase and supply of Hass avocado seedlings | To procure and supply Hass avocado seedlings | Hass avocado seedlings procured and supplied | 3111305 | Beautification and Tree Planting | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 100000 | 100000 | 100000 | Equitable | EQUITABLE | 100000 | 0 | 98570 | 98.6 | 98570 | 0 | 1430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7512 | Crop Development and Management | Construction of animal feed store, purchase and Installation of animal feed machine unit | To construct animal feed store, purchase and Installation of animal feed machine unit | Animal feed store, purchase and Installation of animal feed machine unit constructed | 3111504 | N/A | BAHATI | DUNDORI | -0.263738 36.189005 1987.199951171875 12.300000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: NANROTS CONTRACTORS. Assessor remarks: Not in use waterlogged and accessibility a challenge, traders relocated to the main road.
7513 | Administration, Planning and Support Services | erecting of a fence around Olenguruone Dairies society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | erecting of a fence around Olenguruone Dairies society completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.592109, 35.684406 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2023 | 2000001 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
7514 | Crop Development and Management | Kaptembwo tea buying centre - construction of kaptembwo tea buying centre | To implement kaptembwo tea buying centre - construction of kaptembwo tea buying centre for agricultural development and food production | Kaptembwo tea buying centre - construction of kaptembwo tea buying centre completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.634983, 35.657973 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936166 | 93.6 | 936166 | 1500000 | 63834 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7515 | Crop Development and Management | Singorwet tea buying centre - completion of a tea buying centre at Singorwet | To implement singorwet tea buying centre - completion of a tea buying centre at singorwet for agricultural development and food production | Singorwet tea buying centre - completion of a tea buying centre at Singorwet completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.62289, 35.672618 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998602 | 99.9 | 998602 | 699886 | 1398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
7516 | Construction of Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | Construction of Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | To construct Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.615343 35.656623 2472.1 55.29999923706055 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5360000 | 5360000 | 5360000 | Equitable | equitable | 5360000 | 0 | 891679 | 16.6 | 891679 | 279520 | 4468321 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7517 | Administration, Planning and Support Services | erecting of a fence around Olenguruone Dairies society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | erecting of a fence around Olenguruone Dairies society completed | 4130299 | N/A | Kuresoi South | Amalo | -0.592109, 35.684406 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2023 | 2000001 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
7518 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 4130299 | N/A | Kuresoi South | Amalo | -0.59198 35.68623 2553.2999999999997 8 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2240000 | 2240000 | 2240000 | Equitable | EQUITABLE | 2240000 | 0 | 2178650 | 97.3 | 2178650 | 0 | 61350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: yes. Assessor remarks: facility fully operational.
7519 | Construction of Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | Construction of Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | To construct Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.615343 35.656623 2472.1 55.29999923706055 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5360000 | 2761228.5 | 2761228.5 | Equitable | equitable | 2761228.5 | 0 | 891679 | 32.3 | 891679 | 279520 | 1869549.5 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7520 | Crop Development and Management | Construction of Milk Bulking and Chilling Plant in Naivasha | To construct Milk Bulking and Chilling Plant in Naivasha | Milk Bulking and Chilling Plant in Naivasha constructed | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 8399983.4 | 8399983 | 8399983 | Equitable | N/A | 8399983 | 0 | 8399983 | 100 | 8399983 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7521 | Crop Development and Management | Fencing and construction of a latrine for Kirima milk coolers | To secure and construction of a latrine for Kirima milk coolers through fencing | And construction of a latrine for Kirima milk coolers fenced and secured | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.632532, 36.489073 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2021 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1488800 | 99.3 | 1488800 | 1488800 | 11200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: only the gate is existing the fence and the toilet were brought down NARIG PROJECT for a permanent fence and toilet..
7522 | Crop Development and Management | Fencing and construction of a latrine for Kirima milk coolers | To secure and construction of a latrine for Kirima milk coolers through fencing | And construction of a latrine for Kirima milk coolers fenced and secured | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.632532, 36.489073 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2021 | 1500000 | 1488800 | 1488800 | Equitable | EQUITABLE | 1488800 | 0 | 1488800 | 100 | 1488800 | 1488800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: only the gate is existing the fence and the toilet were brought down NARIG PROJECT for a permanent fence and toilet..
7523 | Crop Development and Management | construction of of milk cooler house at Mutamaiyo | To construct of milk cooler house at Mutamaiyo | Of milk cooler house at Mutamaiyo constructed | 4130299 | N/A | MOLO | ELBURGON | -0.267627, 35.796427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | - | 1500000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1371380 | 98 | 1371380 | 1400000 | 28620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational.
7524 | Crop Development and Management | Livestock support ( breeding of Dorpers) for Elementaita ward | To implement livestock support ( breeding of dorpers) for elementaita ward for agricultural development and food production | Livestock support ( breeding of Dorpers) for Elementaita ward completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.583778, 36.10824 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499800 | 100 | 1499800 | 0 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
7525 | Crop Development and Management | construction of of milk cooler house at Mutamaiyo | To construct of milk cooler house at Mutamaiyo | Of milk cooler house at Mutamaiyo constructed | 4130299 | N/A | Molo | Elburgon | -0.267627, 35.796427 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | - | 1500000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1371380 | 98 | 1371380 | 1400000 | 28620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational.
7526 | Crop Development and Management | Purchase and supply of chicken incubators and fertilised eggs | To procure and supply chicken incubators and fertilised eggs | Chicken incubators and fertilised eggs procured and supplied | 4130299 | N/A | Gilgil | Gilgil | -0.503495, 36.320416 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 962246 | 96.2 | 962246 | 0 | 37754 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yed. Assessor remarks: Functional.
7527 | Administration, Planning and Support Services | ATC (8 km) Farm perimeter / concrete pillar posts / chain link | To implement atc (8 km) farm perimeter / concrete pillar posts / chain link for agricultural development and food production | ATC (8 km) Farm perimeter / concrete pillar posts / chain link completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 622823.8 | 622823.8 | Equitable | equitable | 622823.8 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7528 | Administration, Planning and Support Services | Construction of Data collection shades at fish landing beaches.. | To construct Data collection shades at fish landing beaches | Data collection shades at fish landing beaches constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 999800 | 999800 | Equitable | equitable | 999800 | 0 | 0 | 0 | 0 | 999800 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7529 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 1500000 | 150 | 1500000 | 4500000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7530 | Crop Development and Management | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 6500000 | 433.3 | 6500000 | 3910461 | -5000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7531 | Administration, Planning and Support Services | Counterpart funding - Purchase of Pulping Machine for Jumatatu society in Kabazi | To implement counterpart funding - purchase of pulping machine for jumatatu society in kabazi for agricultural development and food production | Counterpart funding - Purchase of Pulping Machine for Jumatatu society in Kabazi completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 0 | 591600 | Equitable | equitable | 591600 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7532 | Administration, Planning and Support Services | Development, Demarcation, provision of tap water and fencing and Kamere beach area, Naivasha | To implement development, demarcation, provision of tap water and fencing and kamere beach area, naivasha for agricultural development and food production | Development, Demarcation, provision of tap water and fencing and Kamere beach area, Naivasha completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1550000 | 1497908 | 1497908 | Equitable | equitable | 1497908 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7533 | Crop Development and Management | Planting materials support projects-Avocado Seedlings | To implement planting materials support projects-avocado seedlings for agricultural development and food production | Planting materials support projects-Avocado Seedlings completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 1225728 | 184128 | Equitable | N/A | 184128 | 0 | 13399497 | 1093.2 | 13399497 | 1 | -12173769 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7534 | Crop Development and Management | Planting materials support projects-Coffee seedlings | To implement planting materials support projects-coffee seedlings for agricultural development and food production | Planting materials support projects-Coffee seedlings completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 4966169.6 | 966169.6 | 966169.6 | Equitable | N/A | 966169.6 | 0 | 1999999 | 207 | 1999999 | 1 | -1033829.4 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7535 | Crop Development and Management | Planting materials support projects-Macadamia Seedlings | To implement planting materials support projects-macadamia seedlings for agricultural development and food production | Planting materials support projects-Macadamia Seedlings completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 13399497 | 191.4 | 13399497 | 1 | -6399497 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
7536 | Administration, Planning and Support Services | Potato Stores in Kuresoi South and Njoro | To implement potato stores in kuresoi south and njoro for agricultural development and food production | Potato Stores in Kuresoi South and Njoro completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 2998855.2 | 2998855.2 | Equitable | equitable | 2998855.2 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7537 | Administration, Planning and Support Services | Procure 1 farm tractor | To implement procure 1 farm tractor for agricultural development and food production | Procure 1 farm tractor completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 95000 | 95000 | Equitable | equitable | 95000 | 0 | 3404999 | 3584.2 | 3404999 | 1 | -3309999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7538 | Crop Development and Management | Procurement and installation of fish pond liners. | To procure and supply and installation of fish pond liners | And installation of fish pond liners procured and supplied | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997000 | 99.9 | 1997000 | 0 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7539 | Crop Development and Management | Procurement and stocking of fish fingerlings. | To procure and supply and stocking of fish fingerlings | And stocking of fish fingerlings procured and supplied | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 4533338 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7540 | Crop Development and Management | Proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County. | To undertake the proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County | Proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County implemented | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 8046747.16 | 247400 | 247400 | Equitable | N/A | 247400 | 0 | 247400 | 100 | 247400 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7541 | Crop Development and Management | Purchase of milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives | To procure milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives | Milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives procured | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 17500000 | 8191456 | 8191456 | Equitable | EQUITABLE | 8191456 | 0 | 8191456 | 100 | 8191456 | 8191456 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7542 | Crop Development and Management | Rehabilitation of KMC SLAUGHTER House in Nakuru East | To rehabilitate KMC SLAUGHTER House in Nakuru East to restore functionality | KMC SLAUGHTER House in Nakuru East rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2980492 | 99.3 | 2980492 | 0 | 19508 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7543 | Supply of supplies for production - Supply of avocado, macadamia seedlings | Supply of supplies for production - Supply of avocado, macadamia seedlings | To implement supply of supplies for production - supply of avocado, macadamia seedlings for agricultural development and food production | Supply of supplies for production - Supply of avocado, macadamia seedlings completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 10500000 | 1625250 | 1625250 | Equitable | N/A | 1625250 | 0 | 10397600 | 639.8 | 10397600 | 2519316 | -8772350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7544 | Crop Development and Management | Supply installation of Green House and Water Tank at Bahati Sub-County Kabatini Ward | To implement supply installation of green house and water tank at bahati sub-county kabatini ward for agricultural development and food production | Supply installation of Green House and Water Tank at Bahati Sub-County Kabatini Ward completed | 4130299 | N/A | BAHATI | KABATINI | -0.217183, 36.161807 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2017 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes by then. Viable: Yes. Contractor: M/s pro max general supplies. Assessor remarks: Green house need repair for it to be in use again(pvc paper is torn),was functional for 2 year.
7545 | Crop Development and Management | youth and woment urban farming support | To implement youth and woment urban farming support for agricultural development and food production | youth and woment urban farming support completed | 4130299 | N/A | NAKURU WEST | KAPTEMBWO | -0.312059, 36.053008 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2020/21 | 4000000 | 4000000 | 4000000 | Equitable | EQUITABLE | 4000000 | 0 | 1999996 | 50 | 1999996 | 501200 | 2000004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly since the residents benefited from the incubators. Viable: Had it not been vandalized it could been a viable project. Contractor: WEIROD LIMITED. Assessor remarks: The incubators served its purpose but the greenhouses were vandalized and driplines and seedbeds destroyed s.
7546 | completion of Saptet tea buying centre | completion of Saptet tea buying centre | To complete Saptet tea buying centre | Saptet tea buying centre completed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.56761, 35.625987 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399040 | 99.8 | 399040 | 393820 | 960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Functional but not completed.
7547 | Administration, Planning and Support Services | construction of Chepkiswet tea buying centre | To construct Chepkiswet tea buying centre | Chepkiswet tea buying centre constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 600000 | 50 | 600000 | 698687 | 600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7548 | Administration, Planning and Support Services | construction of Seger Kap mugei tea buying centre | To construct Seger Kap mugei tea buying centre | Seger Kap mugei tea buying centre constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.631137, 35.606343 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2022 | 800000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but still under construction. Contractor: Don't know. Assessor remarks: The project is ongoing. No painting, no table tops and no toilets..
7549 | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | To construct Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Tea Buying Centres at banana, Ainamoi, and Kapset buying centre constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.604183 35.596885 2414.8 10.899999618530273 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 3600000 | 3600000 | Equitable | EQUITABLE | 3600000 | 0 | 1199220 | 33.3 | 1199220 | 1303809 | 2400780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good and functional.
7550 | Administration, Planning and Support Services | construction of Tuyobei Ketit tea buying centre | To construct Tuyobei Ketit tea buying centre | Tuyobei Ketit tea buying centre constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7551 | Crop Development and Management | kiptororo cooling plant - completion of Kiptororo cooling plant | To implement kiptororo cooling plant - completion of kiptororo cooling plant for agricultural development and food production | kiptororo cooling plant - completion of Kiptororo cooling plant completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.300889 35.533228 0 20.100000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999956 | 100 | 1999956 | 0 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Request for construction of toilet.
7552 | Crop Development and Management | youth and woment urban farming support | To implement youth and woment urban farming support for agricultural development and food production | youth and woment urban farming support completed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.312059, 36.053008 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2020/21 | 4000000 | 2018720 | 2018720 | Equitable | EQUITABLE | 2018720 | 0 | 1999996 | 99.1 | 1999996 | 501200 | 18724 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly since the residents benefited from the incubators. Viable: Had it not been vandalized it could been a viable project. Contractor: WEIROD LIMITED. Assessor remarks: The incubators served its purpose but the greenhouses were vandalized and driplines and seedbeds destroyed s.
7553 | Crop Development and Management | Women empowerment ( incubators) | To implement women empowerment ( incubators) for agricultural development and food production | Women empowerment ( incubators) completed | 4130299 | N/A | Njoro | Kihingo | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 750000 | 750000 | 750000 | Equitable | EQUITABLE | 750000 | 0 | 749930 | 100 | 749930 | 0 | 70 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7554 | Administration, Planning and Support Services | construction of Chepkiswet tea buying centre | To construct Chepkiswet tea buying centre | Chepkiswet tea buying centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1198687 | 1198687 | Equitable | EQUITABLE | 1198687 | 0 | 600000 | 50.1 | 600000 | 698687 | 598687 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7555 | Administration, Planning and Support Services | construction of Seger Kap mugei tea buying centre | To construct Seger Kap mugei tea buying centre | Seger Kap mugei tea buying centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.631137, 35.606343 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2022 | 800000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but still under construction. Contractor: Don't know. Assessor remarks: The project is ongoing. No painting, no table tops and no toilets..
7556 | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | To construct Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Tea Buying Centres at banana, Ainamoi, and Kapset buying centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.604183 35.596885 2414.8 10.899999618530273 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 1303809.1 | 1303809.1 | Equitable | EQUITABLE | 1303809.1 | 0 | 1199220 | 92 | 1199220 | 1303809 | 104589.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good and functional.
7557 | Administration, Planning and Support Services | construction of Tuyobei Ketit tea buying centre | To construct Tuyobei Ketit tea buying centre | Tuyobei Ketit tea buying centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
7558 | Crop Development and Management | Establishment of a fish hatchery in Lakeview | To implement establishment of a fish hatchery in lakeview for agricultural development and food production | Establishment of a fish hatchery in Lakeview completed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.742104, 36.432755 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 3215636 | 64.3 | 3215636 | 1784364 | 1784364 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Submerged.
7559 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks in lakeview ward | To implement procure and supply of one (1) month old improved kienyenji chicks in lakeview ward for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks in lakeview ward completed | 4130299 | N/A | NAIVASHA | LAKEVIEW | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995000 | 99.8 | 1995000 | 0 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7560 | Crop Development and Management | Renovation of slaughterhouse at Nguriga | To rehabilitate slaughterhouse at Nguriga to restore functionality | Slaughterhouse at Nguriga rehabilitated | 4130299 | N/A | NJORO | LARE | -0.446195, 36.013001 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Promax General Supplies. Assessor remarks: No renovation yet and not operational and the area need to be secured with a concrete fence.
7561 | Construction of a milk cooling plants at Ndabibi and Maiella | Construction of a milk cooling plants at Ndabibi and Maiella | To construct a milk cooling plants at Ndabibi and Maiella | A milk cooling plants at Ndabibi and Maiella constructed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.730135, 36.230433 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6998825 | 100 | 6998825 | 1500000 | 1175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in use.
7562 | Crop Development and Management | Purchase of KCC fish ponds | To procure KCC fish ponds | KCC fish ponds procured | 4130299 | N/A | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 493000 | 98.6 | 493000 | 0 | 7000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need continuous improvement.
7563 | Crop Development and Management | Repair of fish ponds - Tarabete landing beach | To rehabilitate fish ponds - Tarabete landing beach to restore functionality | Fish ponds - Tarabete landing beach rehabilitated | 4130299 | N/A | GILGIL | MALEWA WEST | -0.684685 36.471073 0 2000 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999203 | 100 | 1999203 | 1200000 | 797 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yea. Assessor remarks: Has been maintained over years.
7564 | Crop Development and Management | Construction and completion of Milk cooler plant | To construct and completion of Milk cooler plant | And completion of Milk cooler plant constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.168207 35.999097 1886.9 728.802001953125 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | EQUITABLE | 3500000 | 0 | 1766448 | 50.5 | 1766448 | 1773421 | 1733552 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped as in the description.
7565 | Crop Development and Management | Purchase of chicks incubators | To procure chicks incubators | Chicks incubators procured | 4130299 | N/A | Rongai | Menengai West | -0.177776, 35.995233 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 1199900 | 100 | 1199900 | 2000000 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7566 | Crop Development and Management | Construction and completion of Milk cooler plant | To construct and completion of Milk cooler plant | And completion of Milk cooler plant constructed | 4130299 | N/A | Rongai | Menengai West | -0.168207 35.999097 1886.9 728.802001953125 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 1773421.2 | 1773421.2 | Equitable | EQUITABLE | 1773421.2 | 0 | 1766448 | 99.6 | 1766448 | 1773421 | 6973.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped as in the description.
7567 | Crop Development and Management | Livestock breeding stock/materials(incubators and fertilised eggs) | To implement livestock breeding stock/materials(incubators and fertilised eggs) for agricultural development and food production | Livestock breeding stock/materials(incubators and fertilised eggs) completed | 4130299 | N/A | Gilgil | Murindat | -0.506488, 36.365923 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2895984 | 96.5 | 2895984 | 0 | 104016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Cubango E.A Limited. Assessor remarks: The project is not viable.
7568 | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision | To implement naivasha east fish project - purchase and distribution of dam liners for kimunyu, maraigushu and sision for agricultural development and food production | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision completed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.850102, 36.535011 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2018-19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1935450 | 96.8 | 1935450 | 0 | 64550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7569 | Crop Development and Management | purchase of incubator for women groups | To procure incubator for women groups | Incubator for women groups procured | 4130299 | N/A | NJORO | NJORO | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998800 | 99.9 | 998800 | 0 | 1200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7570 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 4130299 | N/A | Njoro | Njoro | N/A | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | EQUITABLE | 2500000 | 0 | 2386250 | 95.5 | 2386250 | 0 | 113750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7571 | Crop Development and Management | Purchase of eggs incubators | To procure eggs incubators | Eggs incubators procured | 4130299 | N/A | Njoro | Njoro | -0.329135 35.95168 2146.10009765625 72.9000015258789 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 999910 | 100 | 999910 | 0 | 90 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sincere Electricals Ltd. Assessor remarks: Well done work.
7572 | Crop Development and Management | Purchase of incubators and generators for the youth and women groups | To procure incubators and generators for the youth and women groups | Incubators and generators for the youth and women groups procured | 4130299 | N/A | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2969200 | 99 | 2969200 | 978500 | 30800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
7573 | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip | To implement soin ward cattle dips - construction of a cattle dip at lobisil cattle dip, banita cattle dip for agricultural development and food production | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip completed | 4130299 | N/A | RONGAI | SOIN | -0.065365 36.063149 1637 9.5 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 1400001.8 | 1400001.8 | Equitable | N/A | 1400001.8 | 0 | 1400000 | 100 | 1400000 | 0 | 1.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require renovation.
7574 | Construction of Tuiyomoi Cattle Dip | Construction of Tuiyomoi Cattle Dip | To construct Tuiyomoi Cattle Dip | Tuiyomoi Cattle Dip constructed | 4130299 | N/A | RONGAI | SOLAI | 0.096274, 36.173405 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2018 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1990000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project broke down and is not in use.
7575 | Crop Development and Management | Renovation of Limuru Cattle Dip | To rehabilitate Limuru Cattle Dip to restore functionality | Limuru Cattle Dip rehabilitated | 4130299 | N/A | RONGAI | SOLAI | 0.151221 36.195465 1713.139404296875 7.593999862670898 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 1940216 | 323.4 | 1940216 | 597667 | -1340216 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7576 | Rehabilitation of Nairobi cattle dip in Arutani | Rehabilitation of Nairobi cattle dip in Arutani | To rehabilitate Nairobi cattle dip in Arutani to restore functionality | Nairobi cattle dip in Arutani rehabilitated | 4130299 | N/A | RONGAI | SOLAI | -0.039489, 36.122165 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799472 | 99.9 | 799472 | 597667 | 528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7577 | Crop Development and Management | Renovation of Limuru Cattle Dip | To rehabilitate Limuru Cattle Dip to restore functionality | Limuru Cattle Dip rehabilitated | 4130299 | N/A | Rongai | Solai | 0.151221 36.195465 1713.139404296875 7.593999862670898 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 600000 | 597666.8 | 597666.8 | Equitable | EQUITABLE | 597666.8 | 0 | 1940216 | 324.6 | 1940216 | 597667 | -1342549.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7578 | Crop Development and Management | Procure and supply of one (1) month old improved kienyenji chicks | To implement procure and supply of one (1) month old improved kienyenji chicks for agricultural development and food production | Procure and supply of one (1) month old improved kienyenji chicks completed | 4130299 | N/A | Subukia | Subukia | 0.002518 36.230234 1991.4000244140625 33.17599868774414 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 989919 | 989919 | 989919 | Equitable | EQUITABLE | 989919 | 0 | 944525 | 95.4 | 944525 | 0 | 45394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Residents, patients and staff now have interrupted power supply.. Viable: Yes. Power outages have since been resolved.. Assessor remarks: The power generator was a donation from Gilgil Sub county hospital. The funds initially allocated to the purchase of a new power generator were reallocated via public participation to other uses within the same facility, particularly the renovation works for Subukia sub County hospital old wing..
7579 | Administration, Planning and Support Services | purchase and supply of goats | To procure and supply goats | Goats procured and supplied | 4130299 | N/A | Subukia | Subukia | 0.002518 36.230234 1991.4000244140625 33.17599868774414 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 997800 | 99.8 | 997800 | 997800 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Residents, patients and staff now have interrupted power supply.. Viable: Yes. Power outages have since been resolved.. Assessor remarks: The power generator was a donation from Gilgil Sub county hospital. The funds initially allocated to the purchase of a new power generator were reallocated via public participation to other uses within the same facility, particularly the renovation works for Subukia sub County hospital old wing..
7580 | Construction of Olmanyatta Cattle Dip | Construction of Olmanyatta Cattle Dip | To construct Olmanyatta Cattle Dip | Olmanyatta Cattle Dip constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.166288, 36.231724 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498950 | 99.8 | 498950 | 499066 | 1050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Ye. Assessor remarks: Needs to be operationalize.
7581 | Crop Development and Management | Purchase of land for construction of Farm input Centre at Wei Centre | To acquire land for construction of Farm input Centre at Wei Centre | Land for construction of Farm input Centre at Wei Centre acquired | 4130299 | N/A | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
7582 | Administration, Planning and Support Services | Purchase of land for milk coolers, Water and Electricity at Wei Centre | To acquire land for milk coolers, Water and Electricity at Wei Centre | Land for milk coolers, Water and Electricity at Wei Centre acquired | 4130299 | N/A | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1200000 | 60 | 1200000 | 800000 | 800000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
7583 | Rehabilitation of KT Cattle Dip | Rehabilitation of KT Cattle Dip | To rehabilitate KT Cattle Dip to restore functionality | KT Cattle Dip rehabilitated | 4130299 | N/A | SUBUKIA | WASEGES | 0.111637, 36.241873 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498950 | 99.8 | 498950 | 499066 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Should operational and rehabilitate.
7584 | Construction of Olmanyatta Cattle Dip | Construction of Olmanyatta Cattle Dip | To construct Olmanyatta Cattle Dip | Olmanyatta Cattle Dip constructed | 4130299 | N/A | Subukia | Waseges | 0.166288, 36.231724 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 499066 | 499066 | Equitable | N/A | 499066 | 0 | 498950 | 100 | 498950 | 499066 | 116 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Ye. Assessor remarks: Needs to be operationalize.
7585 | Crop Development and Management | Purchase of land for construction of Farm input Centre at Wei Centre | To acquire land for construction of Farm input Centre at Wei Centre | Land for construction of Farm input Centre at Wei Centre acquired | 4130299 | N/A | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
7586 | Administration, Planning and Support Services | Purchase of land for milk coolers, Water and Electricity at Wei Centre | To acquire land for milk coolers, Water and Electricity at Wei Centre | Land for milk coolers, Water and Electricity at Wei Centre acquired | 4130299 | N/A | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4569 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1200000 | 60 | 1200000 | 800000 | 800000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
7587 | Consultancy services to carry out environmental and social impact for KUSP (Nakuru UDG) | Consultancy services to carry out environmental and social impact for KUSP (Nakuru UDG) | To provide professional services for carry out environmental and social impact for KUSP (Nakuru UDG) | Professional services for carry out environmental and social impact for KUSP (Nakuru UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 3070514 | 0 | Equitable | N/A | 0 | 3070514 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7588 | Supervision of roads and drainage works in Naivasha Municipality (Naivasha UDG) | Supervision of roads and drainage works in Naivasha Municipality (Naivasha UDG) | To provide professional services for of roads and drainage works in Naivasha Municipality (Naivasha UDG) | Professional services for of roads and drainage works in Naivasha Municipality (Naivasha UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 748202 | 0 | Equitable | N/A | 0 | 748202 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7589 | Supervision of roads and drainage works in Nakuru Municipality (Nakuru UDG) | Supervision of roads and drainage works in Nakuru Municipality (Nakuru UDG) | To provide professional services for of roads and drainage works in Nakuru Municipality (Nakuru UDG) | Professional services for of roads and drainage works in Nakuru Municipality (Nakuru UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 1246521.4 | 0 | Equitable | N/A | 0 | 1246521.4 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7590 | Surveying of trading centres | Surveying of trading centres | To survey trading centres for planning and development | Trading centres surveyed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 18895710 | 13395710 | 18895710 | Equitable | N/A | 18895710 | 0 | 2710014 | 20.2 | 2710014 | 16185696 | 10685696 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7591 | Construction of Alternative Building Materials and Training Centres | Construction of Alternative Building Materials and Training Centres | To construct Alternative Building Materials and Training Centres | Alternative Building Materials and Training Centres constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 19042735 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7592 | Construction of Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | Construction of Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | To construct Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) constructed | 3110401 | Major Roads | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 188075500 | 100067851.9 | 0 | N/A | N/A | 0 | 100067851.9 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7593 | Reroofing of flamingo estate | Reroofing of flamingo estate | To implement reroofing of flamingo estate for orderly land use and housing provision | Reroofing of flamingo estate completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Flamingo | -0.302283, 36.079495 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2022/23 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 959740 | 0 | 959740 | 2696440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kempy.
7594 | Baharini 1 Estate Re-roofing | Baharini 1 Estate Re-roofing | To implement baharini 1 estate re-roofing for orderly land use and housing provision | Baharini 1 Estate Re-roofing completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Kivumbini | -0.300896, 36.086453 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2023 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 0 | 1500000 | 106286 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
7595 | survey,valuation, mapping and conveyancing cost | survey,valuation, mapping and conveyancing cost | To implement survey,valuation, mapping and conveyancing cost for orderly land use and housing provision | survey,valuation, mapping and conveyancing cost completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.176836 36.132331 1982.8623046875 15.597999572753906 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1580000 | 1580000 | 1580000 | Equitable | N/A | 1580000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is good.
7596 | construction of a wall at kambi somali and installation of two gates | construction of a wall at kambi somali and installation of two gates | To construct a wall at kambi somali and installation of two gates | A wall at kambi somali and installation of two gates constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7597 | Re-roofing of flamingo estate county houses(section 3) | Re-roofing of flamingo estate county houses(section 3) | To implement re-roofing of flamingo estate county houses(section 3) for orderly land use and housing provision | Re-roofing of flamingo estate county houses(section 3) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.302383, 36.07953 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 850000 | 85 | 850000 | 2696440 | 150000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mammeny.
7598 | Re-roofing of kimathi estate county houses | Re-roofing of kimathi estate county houses | To implement re-roofing of kimathi estate county houses for orderly land use and housing provision | Re-roofing of kimathi estate county houses completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.302237, 36.072567 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 950000 | 95 | 950000 | 2696440 | 50000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
7599 | Construction of 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | Construction of 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | To construct 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 169000000 | 89211284.5 | 0 | Equitable | N/A | 0 | 89211284.5 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7600 | Construction of a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | Construction of a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | To construct a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | A new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 303924500 | 303924500 | 0 | Equitable | N/A | 0 | 303924500 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Status: Complete. Recommendation: Retain and archive.
7601 | Construction of fire station at Nakuru Old Town Hall (Nakuru UDG) | Construction of fire station at Nakuru Old Town Hall (Nakuru UDG) | To construct fire station at Nakuru Old Town Hall (Nakuru UDG) | Fire station at Nakuru Old Town Hall (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 164843300 | 121036109 | 0 | Equitable | N/A | 0 | 121036109 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7602 | Partial construction of Naivasha market (Naivasha UDG) | Partial construction of Naivasha market (Naivasha UDG) | To implement partial construction of naivasha market (naivasha udg) for orderly land use and housing provision | Partial construction of Naivasha market (Naivasha UDG) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 150000000 | 128620348.7 | 0 | Equitable | N/A | 0 | 128620348.7 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7603 | Renovation of County Houses | Renovation of County Houses | To rehabilitate County Houses to restore functionality | County Houses rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 20000000 | 15651890.05 | 15651890.05 | Equitable | N/A | 15651890.05 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7604 | Fencing of muwa community land | Fencing of muwa community land | To secure muwa community land through fencing | Muwa community land fenced and secured | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.280343, 36.158548 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but not done.
7605 | Purchase of Fire Engines for Disaster Management | Purchase of Fire Engines for Disaster Management | To procure Fire Engines for Disaster Management | Fire Engines for Disaster Management procured | 3110705 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 93000000 | 93000000 | 0 | N/A | N/A | 0 | 93000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7606 | Fencing of pipeline county land | Fencing of pipeline county land | To secure pipeline county land through fencing | Pipeline county land fenced and secured | 3111112 | Purchase of Software | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7607 | Purchase of land for Kapsoyo ECDE | Purchase of land for Kapsoyo ECDE | To acquire land for Kapsoyo ECDE | Land for Kapsoyo ECDE acquired | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.641135 35.623433 2440 6.199999809265137 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7608 | Purchase of land for Water project at Pangani Network | Purchase of land for Water project at Pangani Network | To acquire land for Water project at Pangani Network | Land for Water project at Pangani Network acquired | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.641135 35.623433 2440 6.199999809265137 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 578966 | 578966 | 578966 | Equitable | N/A | 578966 | 0 | 0 | 0 | 0 | 578966 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7609 | Purchase of land for Ahero Market | Purchase of land for Ahero Market | To acquire land for Ahero Market | Land for Ahero Market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.187336, 36.124786 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 5200000 | 5200000 | Equitable | N/A | 5200000 | 0 | 5200000 | 100 | 5200000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
7610 | Purchase of Land for Maili Kumi Trade Market | Purchase of Land for Maili Kumi Trade Market | To acquire land for Maili Kumi Trade Market | Land for Maili Kumi Trade Market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.16885, 36.123548 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 5400000 | 5400000 | 5400000 | Equitable | N/A | 5400000 | 0 | 5400000 | 100 | 5400000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7611 | purchase of land for Wanyororo market | purchase of land for Wanyororo market | To acquire land for Wanyororo market | Land for Wanyororo market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.187336, 36.124786 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 5200000 | 5200000 | 5200000 | Equitable | N/A | 5200000 | 0 | 5200000 | 100 | 5200000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
7612 | Purchase of land for kelelwet borehole land | Purchase of land for kelelwet borehole land | To acquire land for kelelwet borehole land | Land for kelelwet borehole land acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.3425 36.042 0 2000 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 750000 | 125 | 750000 | 3000000 | -150000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: No land has been purchased for soimet ecd.
7613 | Purchase of land for githioro hospital staffs and other offices | Purchase of land for githioro hospital staffs and other offices | To acquire land for githioro hospital staffs and other offices | Land for githioro hospital staffs and other offices acquired | 3130101 | Acquisition of Land | Bahati | Dundori | -0.2523 36.18779 2039.2 19.399999618530273 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Metro EDD company. Assessor remarks: Good.
7614 | Purchase land for Karunga ECDE | Purchase land for Karunga ECDE | To procure land for Karunga ECDE | Land for Karunga ECDE procured | 3130101 | Acquisition of Land | Molo | Elburgon | -0.26052 35.863608 0 6199.9990234375 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4000000 | 400 | 4000000 | 1000000 | -3000000 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7615 | Purchase land for Saptet tagat road | Purchase land for Saptet tagat road | To procure land for Saptet tagat road | Land for Saptet tagat road procured | 3130101 | Acquisition of Land | Molo | Elburgon | -0.293257 35.80205 2488.1 15.399999618530273 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
7616 | Purchase of public slaughter house land. | Purchase of public slaughter house land. | To procure public slaughter house land | Public slaughter house land procured | 3130101 | Acquisition of Land | Gilgil | Gilgil | -0.552511 36.151373 0 100 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Contractor: Unspecified. Assessor remarks: No such project under the code.
7617 | Purchase of land for a Market in Kamara | Purchase of land for a Market in Kamara | To acquire land for a Market in Kamara | Land for a Market in Kamara acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 25000000 | 12500000 | 12500000 | N/A | N/A | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7618 | purchase of land for Ndungiri hospital | purchase of land for Ndungiri hospital | To acquire land for Ndungiri hospital | Land for Ndungiri hospital acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.08223 36.16987 0 1381 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 4000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
7619 | Purchase of Ndungiri market land | Purchase of Ndungiri market land | To procure Ndungiri market land | Ndungiri market land procured | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.118145, 36.052432 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated.
7620 | Purchase of additional land for construction of Vocational Training Centre | Purchase of additional land for construction of Vocational Training Centre | To procure additional land for construction of Vocational Training Centre | Additional land for construction of Vocational Training Centre procured | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.30479 36.055153 1791.5 14.612000465393066 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 10000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable, it has helped the youths Very much,but defective toilets and urinals. Contractor: ZIBO COMPANY. Assessor remarks: Complete.
7621 | Purchase of land for public use in upper kaptembwo | Purchase of land for public use in upper kaptembwo | To acquire land for public use in upper kaptembwo | Land for public use in upper kaptembwo acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
7622 | Purchase of land for installation of water tank | Purchase of land for installation of water tank | To acquire land for installation of water tank | Land for installation of water tank acquired | 3130101 | Acquisition of Land | Njoro | Kihingo | -0.48105, 35.990172 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 485000 | 97 | 485000 | 0 | 15000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7623 | Purchase of land for milk cooling plant in kiptagich | Purchase of land for milk cooling plant in kiptagich | To acquire land for milk cooling plant in kiptagich | Land for milk cooling plant in kiptagich acquired | 3130101 | Acquisition of Land | Kuresoi South | Kiptagich | -0.572761 35.614001 2486.500244140625 8.199999809265137 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 735956 | 735956 | 735956 | Equitable | N/A | 735956 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but for now it doesn't meet the needs of the residents. Contractor: Don't know. Assessor remarks: The market is complete but not operational because a new market is under construction on the same site.
7624 | purchase of land for lanet umoa health centre | purchase of land for lanet umoa health centre | To acquire land for lanet umoa health centre | Land for lanet umoa health centre acquired | 3130101 | Acquisition of Land | Bahati | Lanet/Umoja | -0.267792, 36.171793 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2021/22 | 96500000 | 23015405 | 23015405 | Equitable | N/A | 23015405 | 0 | 30000000 | 130.3 | 30000000 | 1000000 | -6984595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
7625 | Purchase of land for Tarembeta borehole | Purchase of land for Tarembeta borehole | To acquire land for Tarembeta borehole | Land for Tarembeta borehole acquired | 3130101 | Acquisition of Land | Gilgil | Malewa West | -0.702703, 36.291018 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2500000 | 0 | 2500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
7626 | Acquisition of land for ECD Centre-kahuho mwisho | Acquisition of land for ECD Centre-kahuho mwisho | To acquire land for ECD Centre-kahuho mwisho | Land for ECD Centre-kahuho mwisho acquired | 3130101 | Acquisition of Land | Njoro | Mau Narok | -0.597728 35.995954 0 20 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2520000 | 100 | 2520000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
7627 | Purchase of land for Kiratina ECDE | Purchase of land for Kiratina ECDE | To acquire land for Kiratina ECDE | Land for Kiratina ECDE acquired | 3130101 | Acquisition of Land | Nakuru East | Menengai | -0.273152 36.107904 1867.699951171875 10.253000259399414 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The school doesn't have a special needs unit. The items were never supplied.
7628 | Purchase of market land at Mang'u | Purchase of market land at Mang'u | To procure market land at Mang'u | Market land at Mang'u procured | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.144718 36.010936 0 92.9000015258789 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
7629 | Completion of Land purchase for access road at sumeek atebwo road | Completion of Land purchase for access road at sumeek atebwo road | To complete Land purchase for access road at sumeek atebwo road | Land purchase for access road at sumeek atebwo road completed | 3130101 | Acquisition of Land | Rongai | Mosop | -0.266003 35.881008 2093.4 16.5 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
7630 | Purchase of land for water tank project in lelechwet | Purchase of land for water tank project in lelechwet | To acquire land for water tank project in lelechwet | Land for water tank project in lelechwet acquired | 3130101 | Acquisition of Land | Rongai | Mosop | -0.28556 35.892287 2148.4 11.699999809265137 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 5800000 | 1160 | 5800000 | 0 | -5300000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Gamak enterprise. Assessor remarks: Good work.
7631 | Buying of land for naivasha east value additional factory | Buying of land for naivasha east value additional factory | To procure land for naivasha east value additional factory | Land for naivasha east value additional factory procured | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.82546, 36.532327 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2023 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3200000 | 91.4 | 3200000 | 0 | 300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7632 | Purchase of Land (1 acre) for Sossion ECD | Purchase of Land (1 acre) for Sossion ECD | To acquire land for (1 acre) for Sossion ECD | Land for (1 acre) for Sossion ECD acquired | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.87416 36.540758 2116.800048828125 3.299999952316284 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing to mark boundary.
7633 | Buying of land for the construction of a tank in lower piave | Buying of land for the construction of a tank in lower piave | To procure land for the construction of a tank in lower piave | Land for the construction of a tank in lower piave procured | 3130101 | Acquisition of Land | Njoro | Njoro | -0.324494 35.975425 2064.329345703125 10.163999557495117 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 696000 | 87 | 696000 | 0 | 104000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
7634 | Purchase of land at mulwang | Purchase of land at mulwang | To acquire land for mulwang | Land for mulwang acquired | 3130101 | Acquisition of Land | Rongai | Soin | -0.069327 35.957573 1636 5.400000095367432 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs regular maintenance.
7635 | Buying of arus dispensary land | Buying of arus dispensary land | To procure arus dispensary land | Arus dispensary land procured | 3130101 | Acquisition of Land | Rongai | Solai | 0.02989, 36.161615 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 800000 | 80 | 800000 | 800000 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
7636 | Purchase of land for Arus Dispensary | Purchase of land for Arus Dispensary | To acquire land for Arus Dispensary | Land for Arus Dispensary acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.013051 36.159552 1574.0458984375 4.935999870300293 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 900000 | 75 | 900000 | 800000 | 300000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purchased.
7637 | Purchase of land for a Road connecting tetu and KijabeTetu | Purchase of land for a Road connecting tetu and KijabeTetu | To acquire land for a Road connecting tetu and KijabeTetu | Land for a Road connecting tetu and KijabeTetu acquired | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900000 | 90 | 900000 | 750000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7638 | purchase of Land for Road connecting miroreni and subukia valley | purchase of Land for Road connecting miroreni and subukia valley | To acquire land for Road connecting miroreni and subukia valley | Land for Road connecting miroreni and subukia valley acquired | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 550000 | 550000 | 550000 | Equitable | N/A | 550000 | 0 | 430000 | 78.2 | 430000 | 750000 | 120000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7639 | Purchase of one plot of land for construction of a tank for tetu kirima borehole | Purchase of one plot of land for construction of a tank for tetu kirima borehole | To procure one plot of land for construction of a tank for tetu kirima borehole | One plot of land for construction of a tank for tetu kirima borehole procured | 3130101 | Acquisition of Land | Subukia | Subukia | -0.006188, 36.235553 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2021/2022 | 650000 | 650000 | 650000 | Equitable | N/A | 650000 | 0 | 900000 | 138.5 | 900000 | 1600000 | -250000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Community blocked accessing the water till the matter of payment for the landis resolved. Viable: Yes. Contractor: Details not availed.
7640 | Purchase of plot for Araki water projects | Purchase of plot for Araki water projects | To procure plot for Araki water projects | Plot for Araki water projects procured | 3130101 | Acquisition of Land | Subukia | Subukia | -0.025971, 36.229397 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 12/12/2019 | 650000 | 650000 | 650000 | Equitable | N/A | 650000 | 0 | 500000 | 76.9 | 500000 | 2000000 | 150000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The plot has tanks used for water reticulation. Contractor: Information not known.
7641 | Purchase of land for road bypass turi center | Purchase of land for road bypass turi center | To acquire land for road bypass turi center | Land for road bypass turi center acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 2900000 | 725 | 2900000 | 3000000 | -2500000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7642 | Purchase of land for road network at kiagwaci | Purchase of land for road network at kiagwaci | To acquire land for road network at kiagwaci | Land for road network at kiagwaci acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2900000 | 580 | 2900000 | 500000 | -2400000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7643 | Purchase of land for Gicheha community borehole | Purchase of land for Gicheha community borehole | To acquire land for Gicheha community borehole | Land for Gicheha community borehole acquired | 4130299 | N/A | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 700000 | 87.5 | 700000 | 1000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7644 | Purchase of land for Kahuruko community borehole | Purchase of land for Kahuruko community borehole | To acquire land for Kahuruko community borehole | Land for Kahuruko community borehole acquired | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.728632, 36.50234 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2022 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fastracking of title deed by county government..
7645 | Purchase of land for Mbombo ECDE | Purchase of land for Mbombo ECDE | To acquire land for Mbombo ECDE | Land for Mbombo ECDE acquired | 4130299 | N/A | Gilgil | Elementaita | -0.556018 36.104887 1961.0999755859375 18.899999618530273 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 5500000 | 5000000 | 5500000 | Equitable | N/A | 5500000 | 0 | 4490000 | 89.8 | 4490000 | 4200000 | 510000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Owners are yet to be paid..
7646 | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | To acquire land for - Slaughter House land in Gilgil (additional Funding) | Land for - Slaughter House land in Gilgil (additional Funding) acquired | 4130299 | N/A | Gilgil | Gilgil | -0.508071 36.319004 2000.9000244140625 87.68000030517578 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 994874 | 994874 | Equitable | N/A | 994874 | 0 | 2000000 | 201 | 2000000 | 0 | -1005126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
7647 | Development of housing infrastructure | Development of housing infrastructure | To develop housing infrastructure | Housing infrastructure developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 8009185.75 | 8009185.75 | Equitable | N/A | 8009185.75 | 0 | 19500000 | 243.5 | 19500000 | 23103900 | -11490814.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7648 | Development of Urban centres | Development of Urban centres | To develop Urban centres | Urban centres developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 77500000 | 15000000 | 19500000 | Equitable | N/A | 19500000 | 0 | 19500000 | 130 | 19500000 | 23103900 | -4500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7649 | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2014/15 | 2014/15 | N/A | 16977976 | 4244494.5 | 4244494.5 | Equitable | N/A | 4244494.5 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7650 | Housing Technology Transfer | Housing Technology Transfer | To implement housing technology transfer for orderly land use and housing provision | Housing Technology Transfer completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2015/16 | 2095464.6 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 904098 | 90.4 | 904098 | 0 | 95902 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7651 | Kihingo market - Purchase of market land for Kihingo Community | Kihingo market - Purchase of market land for Kihingo Community | To implement kihingo market - purchase of market land for kihingo community for orderly land use and housing provision | Kihingo market - Purchase of market land for Kihingo Community completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | N/A | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7652 | planning of urban centres | planning of urban centres | To develop of urban centres | Of urban centres developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 20428585 | 20428585 | Equitable | N/A | 20428585 | 0 | 1688125 | 8.3 | 1688125 | 2156959 | 18740460 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7653 | Survey and mapping (titling of land) | Survey and mapping (titling of land) | To survey and mapping (titling of land) for planning and development | And mapping (titling of land) surveyed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 25000000 | 17654700 | 17654700 | Equitable | N/A | 17654700 | 0 | 2250750 | 12.7 | 2250750 | 10740580 | 15403950 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7654 | Purchase of land for Kapkures ECD | Purchase of land for Kapkures ECD | To acquire land for Kapkures ECD | Land for Kapkures ECD acquired | 4130299 | N/A | Nakuru West | Kapkures | -0.306306 36.036551 0 2000 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5000000 | 83.3 | 5000000 | 1000000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Class was never done. No land available.
7655 | Purchase of land for Tachasis market | Purchase of land for Tachasis market | To acquire land for Tachasis market | Land for Tachasis market acquired | 4130299 | N/A | Nakuru West | Kapkures | -0.306306, 36.036551 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. The place is not ideal for market due to poor accessibility and low population.
7656 | Purchase of land for public utility - Resource Centre - at sewage village (additional) | Purchase of land for public utility - Resource Centre - at sewage village (additional) | To acquire land for public utility - Resource Centre - at sewage village (additional) | Land for public utility - Resource Centre - at sewage village (additional) acquired | 4130299 | N/A | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
7657 | Purchase of land for a public playground at Kihingo Centre | Purchase of land for a public playground at Kihingo Centre | To acquire land for a public playground at Kihingo Centre | Land for a public playground at Kihingo Centre acquired | 4130299 | N/A | Njoro | Kihingo | -0.44293, 35.969328 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4000000 | 88.9 | 4000000 | 0 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
7658 | Kaloleni 'A' estate re-roofing | Kaloleni 'A' estate re-roofing | To implement kaloleni 'a' estate re-roofing for orderly land use and housing provision | Kaloleni 'A' estate re-roofing completed | 4130299 | N/A | Nakuru East | Kivumbini | -0.300759, 36.086506 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 1995084 | 1995084 | 1995084 | Equitable | N/A | 1995084 | 0 | 1982368 | 99.4 | 1982368 | 106286 | 12716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
7659 | Reroofing of Baharini 1 estate | Reroofing of Baharini 1 estate | To implement reroofing of baharini 1 estate for orderly land use and housing provision | Reroofing of Baharini 1 estate completed | 4130299 | N/A | Nakuru East | Kivumbini | -0.300577, 36.0869 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1200000 | 80 | 1200000 | 3000000 | 300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7660 | Reroofing of Baharini 2 estate | Reroofing of Baharini 2 estate | To implement reroofing of baharini 2 estate for orderly land use and housing provision | Reroofing of Baharini 2 estate completed | 4130299 | N/A | Nakuru East | Kivumbini | -0.300646 36.086514 1777 28.100000381469727 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1200000 | 80 | 1200000 | 3000000 | 300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: roof still intact.
7661 | Reroofing of Baharini I &II estate | Reroofing of Baharini I &II estate | To implement reroofing of baharini i &ii estate for orderly land use and housing provision | Reroofing of Baharini I &II estate completed | 4130299 | N/A | Nakuru East | Kivumbini | -0.300255, 36.087205 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 3993570 | 3793570 | 3793570 | Equitable | N/A | 3793570 | 0 | 3688258 | 97.2 | 3688258 | 3000000 | 105312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7662 | Reroofing of Kaloleni A estate | Reroofing of Kaloleni A estate | To implement reroofing of kaloleni a estate for orderly land use and housing provision | Reroofing of Kaloleni A estate completed | 4130299 | N/A | Nakuru East | Kivumbini | -0.30025, 36.087202 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1925746 | 96.3 | 1925746 | 50000 | 74254 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: tes.
7663 | Purchase of land for Longonot water project | Purchase of land for Longonot water project | To acquire land for Longonot water project | Land for Longonot water project acquired | 4130299 | N/A | Naivasha | Maai Mahiu | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7664 | Purchase of borehole land in Ngecha | Purchase of borehole land in Ngecha | To procure borehole land in Ngecha | Borehole land in Ngecha procured | 4130299 | N/A | Rongai | Mosop | -0.308665 35.93839 2141.6 5 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 770000 | 77 | 770000 | 0 | 230000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: La-mac. Assessor remarks: Good work.
7665 | Naivasha East Ward water works - Purchase of land for sisioni water project | Naivasha East Ward water works - Purchase of land for sisioni water project | To implement naivasha east ward water works - purchase of land for sisioni water project for orderly land use and housing provision | Naivasha East Ward water works - Purchase of land for sisioni water project completed | 4130299 | N/A | Naivasha | Naivasha East | -0.88167, 36.566296 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1800000 | 90 | 1800000 | 0 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7666 | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | To procure Public Utility Land for Livestock and Chepkinoiyo Retail Market | Public Utility Land for Livestock and Chepkinoiyo Retail Market procured | 4130299 | N/A | Kuresoi North | Nyota | -0.362015, 35.598653 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
7667 | Purchase of land for establishment of a Dispensary in Rhonda | Purchase of land for establishment of a Dispensary in Rhonda | To acquire land for establishment of a Dispensary in Rhonda | Land for establishment of a Dispensary in Rhonda acquired | 4130299 | N/A | Nakuru West | Rhonda | N/A | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2019/20 | N/A | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7668 | Kirengero Water borehole - plot compensation | Kirengero Water borehole - plot compensation | To implement kirengero water borehole - plot compensation for orderly land use and housing provision | Kirengero Water borehole - plot compensation completed | 4130299 | N/A | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
7669 | Purchase of land for Public use in Lucia Moraa Arash | Purchase of land for Public use in Lucia Moraa Arash | To acquire land for Public use in Lucia Moraa Arash | Land for Public use in Lucia Moraa Arash acquired | 4130299 | N/A | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1200000 | 85.7 | 1200000 | 2400000 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7670 | purchase of land for Turi Health Center (Land Buying) | purchase of land for Turi Health Center (Land Buying) | To acquire land for Turi Health Center (Land Buying) | Land for Turi Health Center (Land Buying) acquired | 4130299 | N/A | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2900000 | 96.7 | 2900000 | 3000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7671 | purchase of land for Kware kapkwen borehole | purchase of land for Kware kapkwen borehole | To acquire land for Kware kapkwen borehole | Land for Kware kapkwen borehole acquired | 4130299 | N/A | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7672 | Purchase of land for Igwamiti ECD | Purchase of land for Igwamiti ECD | To acquire land for Igwamiti ECD | Land for Igwamiti ECD acquired | 4130299 | N/A | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4570 | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
7673 | Surveying of trading centres | Surveying of trading centres | To survey trading centres for planning and development | Trading centres surveyed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 16895710 | 6895710 | 6895710 | Equitable | N/A | 6895710 | 0 | 2710014 | 39.3 | 2710014 | 16185696 | 4185696 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7674 | Conditional Fund -Kenya Urban Support Project (KUSP) | Conditional Fund -Kenya Urban Support Project (KUSP) | To implement conditional fund -kenya urban support project (kusp) for orderly land use and housing provision | Conditional Fund -Kenya Urban Support Project (KUSP) completed | 2640503 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 1084843300 | 0 | 0 | KUSP | N/A | 0 | 1084843300 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7675 | Kenya Urban Support Programme - urban institutional grants | Kenya Urban Support Programme - urban institutional grants | To implement kenya urban support programme - urban institutional grants for orderly land use and housing provision | Kenya Urban Support Programme - urban institutional grants completed | 2640503 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 41200000 | 0 | 0 | N/A | N/A | 0 | 9527096 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7676 | Purchase of land for water tank project in lelechwet | Purchase of land for water tank project in lelechwet | To acquire land for water tank project in lelechwet | Land for water tank project in lelechwet acquired | 3110101 | N/A | RONGAI | MOSOP | -0.28556 35.892287 2148.4 11.699999809265137 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 5800000 | 1160 | 5800000 | 0 | -5300000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Gamak enterprise. Assessor remarks: Good work.
7677 | Re-roofing of Flamingo estate County houses | Re-roofing of Flamingo estate County houses | To implement re-roofing of flamingo estate county houses for orderly land use and housing provision | Re-roofing of Flamingo estate County houses completed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.302183, 36.079475 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2024/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2996976 | 99.9 | 2996976 | 2696440 | 3024 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: ECRAT merchants ltd.
7678 | Implementation of Physical Development Plans | Implementation of Physical Development Plans | To implement implementation of physical development plans for orderly land use and housing provision | Implementation of Physical Development Plans completed | 3111112 | Purchase of Software | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 28000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7679 | Planning of Urban Centres | Planning of Urban Centres | To develop of Urban Centres | Of Urban Centres developed | 3111112 | Purchase of Software | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 11985871 | 11985871 | Equitable | N/A | 11985871 | 0 | 1688125 | 14.1 | 1688125 | 2156959 | 10297746 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7680 | Purchase of survey equipment | Purchase of survey equipment | To procure survey equipment | Survey equipment procured | 3111114 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 7955350 | 7955350.02 | 7955350.02 | N/A | N/A | 7955350.02 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7681 | Purchase of land for Kapsoyo ECDE | Purchase of land for Kapsoyo ECDE | To acquire land for Kapsoyo ECDE | Land for Kapsoyo ECDE acquired | 3130101 | Acquisition of Land | KURESOI SOUTH | AMALO | -0.641135 35.623433 2440 6.199999809265137 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7682 | Purchase of land for Water project at Pangani Network | Purchase of land for Water project at Pangani Network | To acquire land for Water project at Pangani Network | Land for Water project at Pangani Network acquired | 3130101 | Acquisition of Land | KURESOI SOUTH | AMALO | -0.641135 35.623433 2440 6.199999809265137 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 578966 | 578966 | 578966 | Equitable | N/A | 578966 | 0 | 0 | 0 | 0 | 578966 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7683 | Purchase of land for Ahero Market | Purchase of land for Ahero Market | To acquire land for Ahero Market | Land for Ahero Market acquired | 3130101 | Acquisition of Land | BAHATI | BAHATI | -0.187336, 36.124786 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 3440461 | 3440461 | 3440461 | Equitable | N/A | 3440461 | 0 | 5200000 | 151.1 | 5200000 | 3440461 | -1759539 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
7684 | Purchase of land for Wanyororo B Market | Purchase of land for Wanyororo B Market | To acquire land for Wanyororo B Market | Land for Wanyororo B Market acquired | 3130101 | Acquisition of Land | BAHATI | BAHATI | -0.187336, 36.124786 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 3440461 | 3440461 | 3440461 | Equitable | N/A | 3440461 | 0 | 5200000 | 151.1 | 5200000 | 3440461 | -1759539 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
7685 | Purchase land for Saptet tagat road | Purchase land for Saptet tagat road | To procure land for Saptet tagat road | Land for Saptet tagat road procured | 3130101 | Acquisition of Land | MOLO | ELBURGON | -0.293257 35.80205 2488.1 15.399999618530273 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
7686 | Purchase of Land at Mwatu market | Purchase of Land at Mwatu market | To acquire land for Mwatu market | Land for Mwatu market acquired | 3130101 | Acquisition of Land | MOLO | ELBURGON | -0.293257 35.80205 2488.1 15.399999618530273 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
7687 | Purchase of public slaughter house land. | Purchase of public slaughter house land. | To procure public slaughter house land | Public slaughter house land procured | 3130101 | Acquisition of Land | GILGIL | GILGIL | -0.552511 36.151373 0 100 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Contractor: Unspecified. Assessor remarks: No such project under the code.
7688 | Purchase of land for a Market in Kamara | Purchase of land for a Market in Kamara | To acquire land for a Market in Kamara | Land for a Market in Kamara acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 25000000 | 12500000 | 12500000 | N/A | N/A | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7689 | Purchase of land in Karagita - Naivasha | Purchase of land in Karagita - Naivasha | To acquire land for in Karagita - Naivasha | Land for in Karagita - Naivasha acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 50000000 | 30000000 | 30000000 | N/A | N/A | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7690 | Purchase of land for public use in upper kaptembwo | Purchase of land for public use in upper kaptembwo | To acquire land for public use in upper kaptembwo | Land for public use in upper kaptembwo acquired | 3130101 | Acquisition of Land | NAKURU WEST | KAPTEMBWO | -0.315776 36.052811 0 0 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
7691 | Purchase of land for installation of water tank | Purchase of land for installation of water tank | To acquire land for installation of water tank | Land for installation of water tank acquired | 3130101 | Acquisition of Land | NJORO | KIHINGO | -0.48105, 35.990172 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 485000 | 97 | 485000 | 0 | 15000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7692 | purchase of land for lanet umoa health centre | purchase of land for lanet umoa health centre | To acquire land for lanet umoa health centre | Land for lanet umoa health centre acquired | 3130101 | Acquisition of Land | BAHATI | LANET/UMOJA | -0.267792, 36.171793 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2021/22 | 96500000 | 23015405 | 23015405 | Equitable | N/A | 23015405 | 0 | 30000000 | 130.3 | 30000000 | 1000000 | -6984595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
7693 | Acquisition of land for ECD Centre-kahuho mwisho | Acquisition of land for ECD Centre-kahuho mwisho | To acquire land for ECD Centre-kahuho mwisho | Land for ECD Centre-kahuho mwisho acquired | 3130101 | Acquisition of Land | NJORO | MAU NAROK | -0.597728 35.995954 0 20 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2520000 | 100 | 2520000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
7694 | purchase of land for cemetry mau narok ward | purchase of land for cemetry mau narok ward | To acquire land for cemetry mau narok ward | Land for cemetry mau narok ward acquired | 3130101 | Acquisition of Land | NJORO | MAU NAROK | -0.600012 36.007202 0 212 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 3760317 | 3760317 | 3760317 | Equitable | N/A | 3760317 | 0 | 0 | 0 | 0 | 3760317 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: ok.
7695 | Purchase of market land at mangu | Purchase of market land at mangu | To procure market land at mangu | Market land at mangu procured | 3130101 | Acquisition of Land | RONGAI | MENENGAI WEST | -0.144718 36.010936 0 92.9000015258789 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
7696 | Purchase of public land at Mercy Njeri | Purchase of public land at Mercy Njeri | To procure public land at Mercy Njeri | Public land at Mercy Njeri procured | 3130101 | Acquisition of Land | RONGAI | MENENGAI WEST | -0.144718 36.010936 0 92.9000015258789 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
7697 | Buying of land for the construction of a tank in lower piave | Buying of land for the construction of a tank in lower piave | To procure land for the construction of a tank in lower piave | Land for the construction of a tank in lower piave procured | 3130101 | Acquisition of Land | NJORO | NJORO | -0.324494 35.975425 2064.329345703125 10.163999557495117 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 696000 | 87 | 696000 | 0 | 104000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
7698 | purchase of land for a Road connecting piave-ronda | purchase of land for a Road connecting piave-ronda | To acquire land for a Road connecting piave-ronda | Land for a Road connecting piave-ronda acquired | 3130101 | Acquisition of Land | NJORO | NJORO | -0.340825 35.994282 2020.162841796875 20 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 0 | 0 | 0 | 3400000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Not available. Assessor remarks: Nothing done yet on the ground.
7699 | Purchase of land in Jordan Estate for construction of reservoir tank | Purchase of land in Jordan Estate for construction of reservoir tank | To acquire land for in Jordan Estate for construction of reservoir tank | Land for in Jordan Estate for construction of reservoir tank acquired | 3130101 | Acquisition of Land | NJORO | NJORO | -0.336778 35.952613 1044.5999755859375 10.923999786376953 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Well done work.
7700 | Purchase of land and Tarakwa Water works | Purchase of land and Tarakwa Water works | To acquire land for and Tarakwa Water works | Land for and Tarakwa Water works acquired | 3130101 | Acquisition of Land | KURESOI NORTH | NYOTA | -0.309268 35.575838 2618.7000000000003 10.600000381469727 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 4000000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7701 | Purchase of land, Drilling, equipping and piping of Seguton/Langenda Water Project | Purchase of land, Drilling, equipping and piping of Seguton/Langenda Water Project | To procure land, Drilling, equipping and piping of Seguton/Langenda Water Project | Land, Drilling, equipping and piping of Seguton/Langenda Water Project procured | 3130101 | Acquisition of Land | KURESOI NORTH | NYOTA | -0.37308 35.677892 2768.6 5.099999904632568 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
7702 | Purchases of land for Grading and Murraming of Chesingele-Omari Road | Purchases of land for Grading and Murraming of Chesingele-Omari Road | To implement purchases of land for grading and murraming of chesingele-omari road for orderly land use and housing provision | Purchases of land for Grading and Murraming of Chesingele-Omari Road completed | 3130101 | Acquisition of Land | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 0 | 0 | 0 | 250000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
7703 | Purchase of land at mulwang | Purchase of land at mulwang | To acquire land for mulwang | Land for mulwang acquired | 3130101 | Acquisition of Land | RONGAI | SOIN | -0.069327 35.957573 1636 5.400000095367432 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs regular maintenance.
7704 | Purchase of land for Arus Dispensary | Purchase of land for Arus Dispensary | To acquire land for Arus Dispensary | Land for Arus Dispensary acquired | 3130101 | Acquisition of Land | RONGAI | SOLAI | 0.013051 36.159552 1574.0458984375 4.935999870300293 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 900000 | 75 | 900000 | 800000 | 300000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purchased.
7705 | Purchase of 2 plots of land for tetu kirima borehole | Purchase of 2 plots of land for tetu kirima borehole | To procure 2 plots of land for tetu kirima borehole | 2 plots of land for tetu kirima borehole procured | 3130101 | Acquisition of Land | SUBUKIA | SUBUKIA | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900000 | 90 | 900000 | 2000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7706 | Purchase of land for a Road connecting tetu and KijabeTetu | Purchase of land for a Road connecting tetu and KijabeTetu | To acquire land for a Road connecting tetu and KijabeTetu | Land for a Road connecting tetu and KijabeTetu acquired | 3130101 | Acquisition of Land | SUBUKIA | SUBUKIA | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900000 | 90 | 900000 | 750000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7707 | purchase of Land for Road connecting miroreni and subukia valley | purchase of Land for Road connecting miroreni and subukia valley | To acquire land for Road connecting miroreni and subukia valley | Land for Road connecting miroreni and subukia valley acquired | 3130101 | Acquisition of Land | SUBUKIA | SUBUKIA | 0.002545 36.22944 2004.1999999999998 1 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 430000 | 122.9 | 430000 | 750000 | -80000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
7708 | Purchase of plot for Araki water project | Purchase of plot for Araki water project | To procure plot for Araki water project | Plot for Araki water project procured | 3130101 | Acquisition of Land | SUBUKIA | SUBUKIA | -0.025971, 36.229397 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 12/12/2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The plot has tanks used for water reticulation. Contractor: Information not known.
7709 | Purchase of land for road bypass turi center | Purchase of land for road bypass turi center | To acquire land for road bypass turi center | Land for road bypass turi center acquired | 3130101 | Acquisition of Land | MOLO | TURI | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 2900000 | 725 | 2900000 | 3000000 | -2500000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7710 | Purchase of land for road network at kiagwaci | Purchase of land for road network at kiagwaci | To acquire land for road network at kiagwaci | Land for road network at kiagwaci acquired | 3130101 | Acquisition of Land | MOLO | TURI | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2900000 | 580 | 2900000 | 500000 | -2400000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7711 | Purchase of Land for Soimet ECD | Purchase of Land for Soimet ECD | To acquire land for Soimet ECD | Land for Soimet ECD acquired | 4130299 | N/A | NAKURU WEST | BARUT | -0.3425 36.042 0 2000 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 750000 | 37.5 | 750000 | 3000000 | 1250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: No land has been purchased for soimet ecd.
7712 | Purchase of land for Gicheha community borehole | Purchase of land for Gicheha community borehole | To acquire land for Gicheha community borehole | Land for Gicheha community borehole acquired | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 700000 | 87.5 | 700000 | 1000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7713 | Purchase of land for Kahuruko community borehole | Purchase of land for Kahuruko community borehole | To acquire land for Kahuruko community borehole | Land for Kahuruko community borehole acquired | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.728632, 36.50234 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2022 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fastracking of title deed by county government..
7714 | purchase of land for Mbombo ECDE | purchase of land for Mbombo ECDE | To acquire land for Mbombo ECDE | Land for Mbombo ECDE acquired | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.556018 36.104887 1961.0999755859375 18.899999618530273 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 3500000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4490000 | 112.2 | 4490000 | 4200000 | -490000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Owners are yet to be paid..
7715 | rehabilitation of Kimathi Toilets | rehabilitation of Kimathi Toilets | To rehabilitate Kimathi Toilets to restore functionality | Kimathi Toilets rehabilitated | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.303539, 36.078562 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2017/18 | 5195712 | 5195712 | 5195712 | Equitable | N/A | 5195712 | 0 | 4621115 | 88.9 | 4621115 | 3800000 | 574597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dame group Africa Ltd.
7716 | Flamingo ward Estate Project - Reroofing of Kimathi Estate | Flamingo ward Estate Project - Reroofing of Kimathi Estate | To implement flamingo ward estate project - reroofing of kimathi estate for orderly land use and housing provision | Flamingo ward Estate Project - Reroofing of Kimathi Estate completed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.304258, 36.077959 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1989052 | 49.7 | 1989052 | 4000000 | 2010948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Danveck construction ltd.
7717 | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | To acquire land for - Slaughter House land in Gilgil (additional Funding) | Land for - Slaughter House land in Gilgil (additional Funding) acquired | 4130299 | N/A | GILGIL | GILGIL | -0.508071 36.319004 2000.9000244140625 87.68000030517578 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 994874 | 994874 | Equitable | N/A | 994874 | 0 | 2000000 | 201 | 2000000 | 0 | -1005126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
7718 | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) | To implement county spatial plan - completion of contract price for the development of county spatial plan.(preparation of plans ,interpretation and localize strategic national and regional polices and procedure, production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic development) for orderly land use and housing provision | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 121182048 | 1532016 | 1532016 | Equitable | N/A | 1532016 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7719 | Development of housing infrastructure | Development of housing infrastructure | To develop housing infrastructure | Housing infrastructure developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 19500000 | 97.5 | 19500000 | 23103900 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7720 | Development of Urban centres | Development of Urban centres | To develop Urban centres | Urban centres developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 77500000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 19500000 | 130 | 19500000 | 23103900 | -4500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7721 | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2014/15 | 2014/15 | N/A | 16977976 | 4244494.5 | 4244494.5 | Equitable | N/A | 4244494.5 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7722 | Establishment of Survey and Mapping Centres | Establishment of Survey and Mapping Centres | To implement establishment of survey and mapping centres for orderly land use and housing provision | Establishment of Survey and Mapping Centres completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 19500000 | 130 | 19500000 | 23103900 | -4500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7723 | Housing Technology Transfer | Housing Technology Transfer | To implement housing technology transfer for orderly land use and housing provision | Housing Technology Transfer completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2015/16 | 2095464.6 | 2095464.6 | 2095464.6 | Equitable | N/A | 2095464.6 | 0 | 904098 | 43.1 | 904098 | 0 | 1191366.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7724 | Kihingo market - Purchase of market land for Kihingo Community | Kihingo market - Purchase of market land for Kihingo Community | To implement kihingo market - purchase of market land for kihingo community for orderly land use and housing provision | Kihingo market - Purchase of market land for Kihingo Community completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | N/A | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7725 | planning of urban centres | planning of urban centres | To develop of urban centres | Of urban centres developed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 1688125 | 8.4 | 1688125 | 2156959 | 18311875 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7726 | Rehabilitation of County Estates | Rehabilitation of County Estates | To rehabilitate County Estates to restore functionality | County Estates rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 40200000 | 25200000 | 25200000 | Equitable | N/A | 25200000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7727 | Survey and mapping (titling of land) | Survey and mapping (titling of land) | To survey and mapping (titling of land) for planning and development | And mapping (titling of land) surveyed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 25000000 | 25000000 | 25000000 | Equitable | N/A | 25000000 | 0 | 2250750 | 9 | 2250750 | 10740580 | 22749250 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7728 | Survey and Mapping | Survey and Mapping | To survey and Mapping for planning and development | And Mapping surveyed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2250750 | 45 | 2250750 | 5000000 | 2749250 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7729 | Survey, mapping and Planning for Bahati Centre | Survey, mapping and Planning for Bahati Centre | To implement survey, mapping and planning for bahati centre for orderly land use and housing provision | Survey, mapping and Planning for Bahati Centre completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2250750 | 150 | 2250750 | 10740580 | -750750 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7730 | Purchase of land for the ECD | Purchase of land for the ECD | To acquire land for the ECD | Land for the ECD acquired | 4130299 | N/A | BAHATI | KABATINI | -0.233983 36.154465 1965.599609375 11.258999824523926 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes by then. Viable: Yes. Assessor remarks: Road needs routine maintenance (bulk project).
7731 | Purchase of land for Kabianga dispensary | Purchase of land for Kabianga dispensary | To acquire land for Kabianga dispensary | Land for Kabianga dispensary acquired | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.168763 35.689192 2508 7.900000095367432 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 9800000 | 653.3 | 9800000 | 1500000 | -8300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Land not bought.
7732 | Purchase of land for Kapkures ECD | Purchase of land for Kapkures ECD | To acquire land for Kapkures ECD | Land for Kapkures ECD acquired | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.306306 36.036551 0 2000 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5000000 | 83.3 | 5000000 | 1000000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Class was never done. No land available.
7733 | Purchase of land for Tachasis market | Purchase of land for Tachasis market | To acquire land for Tachasis market | Land for Tachasis market acquired | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.306306, 36.036551 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. The place is not ideal for market due to poor accessibility and low population.
7734 | Purchase of land for public utility - Resource Centre - at sewage village (additional) | Purchase of land for public utility - Resource Centre - at sewage village (additional) | To acquire land for public utility - Resource Centre - at sewage village (additional) | Land for public utility - Resource Centre - at sewage village (additional) acquired | 4130299 | N/A | NAKURU WEST | KAPTEMBWO | -0.315776 36.052811 0 0 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
7735 | Purchase of land for a public playground at Kihingo Centre | Purchase of land for a public playground at Kihingo Centre | To acquire land for a public playground at Kihingo Centre | Land for a public playground at Kihingo Centre acquired | 4130299 | N/A | NJORO | KIHINGO | -0.44293, 35.969328 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4000000 | 88.9 | 4000000 | 0 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
7736 | Baharini I & II estate re-roofing | Baharini I & II estate re-roofing | To implement baharini i & ii estate re-roofing for orderly land use and housing provision | Baharini I & II estate re-roofing completed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.299839, 36.085466 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3893714 | 97.3 | 3893714 | 106286 | 106286 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
7737 | Kaloleni 'A' estate re-roofing | Kaloleni 'A' estate re-roofing | To implement kaloleni 'a' estate re-roofing for orderly land use and housing provision | Kaloleni 'A' estate re-roofing completed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.300759, 36.086506 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 1995084 | 1995084 | 1995084 | Equitable | N/A | 1995084 | 0 | 1982368 | 99.4 | 1982368 | 106286 | 12716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
7738 | Development of Housing Technology - purchase of interlocking bricks making machine | Development of Housing Technology - purchase of interlocking bricks making machine | To develop Housing Technology - purchase of interlocking bricks making machine | Housing Technology - purchase of interlocking bricks making machine developed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.752033, 36.458625 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
7739 | Purchase of land for Longonot water project | Purchase of land for Longonot water project | To acquire land for Longonot water project | Land for Longonot water project acquired | 4130299 | N/A | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7740 | Purchase of borehole land in Ngecha | Purchase of borehole land in Ngecha | To procure borehole land in Ngecha | Borehole land in Ngecha procured | 4130299 | N/A | RONGAI | MOSOP | -0.308665 35.93839 2141.6 5 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 770000 | 77 | 770000 | 0 | 230000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: La-mac. Assessor remarks: Good work.
7741 | Naivasha East Ward water works - Purchase of land for sisioni water project | Naivasha East Ward water works - Purchase of land for sisioni water project | To implement naivasha east ward water works - purchase of land for sisioni water project for orderly land use and housing provision | Naivasha East Ward water works - Purchase of land for sisioni water project completed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.88167, 36.566296 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1800000 | 90 | 1800000 | 0 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7742 | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | To procure Public Utility Land for Livestock and Chepkinoiyo Retail Market | Public Utility Land for Livestock and Chepkinoiyo Retail Market procured | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.362015, 35.598653 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
7743 | Purchase of land for establishment of a Dispensary in Rhonda | Purchase of land for establishment of a Dispensary in Rhonda | To acquire land for establishment of a Dispensary in Rhonda | Land for establishment of a Dispensary in Rhonda acquired | 4130299 | N/A | NAKURU WEST | RHONDA | N/A | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2019/20 | N/A | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7744 | Kirengero Water borehole - plot compensation | Kirengero Water borehole - plot compensation | To implement kirengero water borehole - plot compensation for orderly land use and housing provision | Kirengero Water borehole - plot compensation completed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.041156 36.220377 2150.7001953125 56.099998474121094 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
7745 | Purchase of land for Public use in Subukia ward - Kamundia Tetu | Purchase of land for Public use in Subukia ward - Kamundia Tetu | To acquire land for Public use in Subukia ward - Kamundia Tetu | Land for Public use in Subukia ward - Kamundia Tetu acquired | 4130299 | N/A | SUBUKIA | SUBUKIA | 0.006195 36.23787 1991 20 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1200000 | 50 | 1200000 | 2400000 | 1200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.. Local farmers have increased investment in dairy, more milk marketed , increased income. Contractor: Not availed. Assessor remarks: The cooperative has grown in production and value added to various products.
7746 | purchase of land for Turi Health Center (Land Buying) | purchase of land for Turi Health Center (Land Buying) | To acquire land for Turi Health Center (Land Buying) | Land for Turi Health Center (Land Buying) acquired | 4130299 | N/A | MOLO | TURI | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2900000 | 96.7 | 2900000 | 3000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
7747 | purchase of land for Kware kapkwen borehole | purchase of land for Kware kapkwen borehole | To acquire land for Kware kapkwen borehole | Land for Kware kapkwen borehole acquired | 4130299 | N/A | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7748 | Purchase of land for Igwamiti ECD | Purchase of land for Igwamiti ECD | To acquire land for Igwamiti ECD | Land for Igwamiti ECD acquired | 4130299 | N/A | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4570 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
7749 | Refurbishment of Offices (HQs) WEENR) | Refurbishment of Offices (HQs) WEENR) | To implement refurbishment of offices (hqs) weenr) for access to clean water and environmental sustainability | Refurbishment of Offices (HQs) WEENR) completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2456688 | 2456688 | 2456688 | N/A | N/A | 2456688 | 0 | 2456688 | 100 | 2456688 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7750 | Water and Sewerage Management | Construction of community Water tank at Kitoben Primary School | To construct community Water tank at Kitoben Primary School | Community Water tank at Kitoben Primary School constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.635722, 35.67651 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999881 | 100 | 999881 | 119 | 119 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: complete.
7751 | Water and Sewerage Management | Construction of community water tank at pangani network | To construct community water tank at pangani network | Community water tank at pangani network constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.493175, 35.716723 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999881 | 100 | 999881 | 1000000 | 119 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working due to pump failure.
7752 | Water and Sewerage Management | Construction of Lelaitich water project | To construct Lelaitich water project | Lelaitich water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.615343 35.656623 2472.1 55.29999923706055 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7753 | Water and Sewerage Management | Construction of water tank at sinerindet | To construct water tank at sinerindet | Water tank at sinerindet constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.632512 35.664773 2513.7 10.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 960712 | 96.1 | 960712 | 39288 | 39288 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet in use. Viable: yet to start. Assessor remarks: project ongoing.
7754 | Water and Sewerage Management | Drilling of borehole at ndashata | To provide access to clean water through borehole drilling at ndashata | Borehole drilled at ndashata | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.638882 35.658625 2494.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997376 | 99.9 | 2997376 | 2997376 | 2624 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesllà. Assessor remarks: Complete.
7755 | Water and Sewerage Management | Drilling of Borehole at network | To provide access to clean water through borehole drilling at network | Borehole drilled at network | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.638882 35.658625 2494.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2636630 | 87.9 | 2636630 | 363370 | 363370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesllà. Assessor remarks: Complete.
7756 | Water and Sewerage Management | Construction of Bondeni Water intake | To construct Bondeni Water intake | Bondeni Water intake constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.590476 35.686102 2581.1123046875 9.741999626159668 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599824 | 100 | 599824 | 1000000 | 176 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: yes. Viable: yes. Contractor: m/s koros. Assessor remarks: works going on well.
7757 | Water and Sewerage Management | Completion of lelaitich water project | To complete lelaitich water project | Lelaitich water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.63578 35.67659 2498.5 10.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially. Assessor remarks: requires completion of piping.
7758 | Water and Sewerage Management | Construction of community Water tank at Kitoben Primary School | To construct community Water tank at Kitoben Primary School | Community Water tank at Kitoben Primary School constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.635722, 35.67651 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999881 | 100 | 999881 | 119 | 119 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: complete.
7759 | Water and Sewerage Management | Construction of community water tank at pangani network | To construct community water tank at pangani network | Community water tank at pangani network constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.493175, 35.716723 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999881 | 100 | 999881 | 1000000 | 119 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working due to pump failure.
7760 | Water and Sewerage Management | Construction of Lelaitich water project | To construct Lelaitich water project | Lelaitich water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.615343 35.656623 2472.1 55.29999923706055 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7761 | Water and Sewerage Management | Construction of water tank at sinerindet | To construct water tank at sinerindet | Water tank at sinerindet constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.632512 35.664773 2513.7 10.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 960712 | 96.1 | 960712 | 39288 | 39288 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet in use. Viable: yet to start. Assessor remarks: project ongoing.
7762 | Water and Sewerage Management | Drilling of borehole at ndashata | To provide access to clean water through borehole drilling at ndashata | Borehole drilled at ndashata | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.638882 35.658625 2494.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2997376 | 2997376 | Equitable | N/A | 2997376 | 0 | 2997376 | 100 | 2997376 | 2997376 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesllà. Assessor remarks: Complete.
7763 | Water and Sewerage Management | Drilling of Borehole at network | To provide access to clean water through borehole drilling at network | Borehole drilled at network | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.638882 35.658625 2494.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2636630 | 87.9 | 2636630 | 363370 | 363370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesllà. Assessor remarks: Complete.
7764 | Water and Sewerage Management | Drilling of kitoben borehole | To implement drilling of kitoben borehole for access to clean water and environmental sustainability | Drilling of kitoben borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.633461, 35.677897 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2619477 | 87.3 | 2619477 | 3000000 | 380523 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: operational.
7765 | Water and Sewerage Management | Equipping and solarisation of ndashata water project | To equip and solarisation of ndashata water project with necessary facilities and equipment | And solarisation of ndashata water project equipped | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.63908, 35.658645 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2277278 | 91.1 | 2277278 | 222722 | 222722 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: done.
7766 | Water and Sewerage Management | Piping and distribution at ndashata water project | To provide water distribution infrastructure at ndashata water project | Water piping at ndashata water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.639807 35.658602 2502.2 9.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: completed.
7767 | Water and Sewerage Management | Bahati water works project | To implement bahati water works project for access to clean water and environmental sustainability | Bahati water works project completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.174193, 36.135371 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 6000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1197584 | 24 | 1197584 | 1197584 | 3802416 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes it did. Assessor remarks: Nicely done.
7768 | Water and Sewerage Management | construction of a water tank at Old Bahati dispensary | To construct a water tank at Old Bahati dispensary | A water tank at Old Bahati dispensary constructed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.161366 36.11427 1838.094970703125 88.09379577636719 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable. Assessor remarks: Good.
7769 | Water and Sewerage Management | construction of water tank for Karunga DCC borehole | To construct water tank for Karunga DCC borehole | Water tank for Karunga DCC borehole constructed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.161802 36.114986 0 800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 100000 | 5 | 100000 | 2000000 | 1900000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work on progress.
7770 | Water and Sewerage Management | Drilling of borehole at Karunga DCC area | To provide access to clean water through borehole drilling at Karunga DCC area | Borehole drilled at Karunga DCC area | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.170071 36.121778 0 2400 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7771 | Water and Sewerage Management | drilling of borehole at old Bahati dispensary | To provide access to clean water through borehole drilling at old Bahati dispensary | Borehole drilled at old Bahati dispensary | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.170071 36.121778 0 2400 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7772 | Water and Sewerage Management | Piping at Bibilioni | To provide water distribution infrastructure at Bibilioni | Water piping at Bibilioni completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.17427 36.123558 1921.699951171875 76.52400207519531 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In use but broken Chambers.
7773 | Water And Sewerage Management | Piping at Rumathi Water project | To provide water distribution infrastructure at Rumathi Water project | Water piping at Rumathi Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.127386, 36.178531 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 999589.25 | 999589.25 | 999589.25 | Equitable | N/A | 999589.25 | 0 | 998968 | 99.9 | 998968 | 621 | 621.25 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water is in use.
7774 | Water and Sewerage Management | Piping at Wanyororo | To provide water distribution infrastructure at Wanyororo | Water piping at Wanyororo completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.162521, 36.110571 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 998968 | 199.8 | 998968 | 500000 | -498968 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7775 | Water and Sewerage Management | piping Karunga DCC area to St. John Secondary - phase I | To provide water distribution infrastructure at Karunga DCC area to St. John Secondary - phase I | Water piping at Karunga DCC area to St. John Secondary - phase I completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.127321 36.178713 2275.578125 5.429999828338623 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1183988 | 1183988 | Equitable | N/A | 1183988 | 0 | 0 | 0 | 0 | 1183988 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is working well.
7776 | Water And Sewerage Management | piping Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto | To provide water distribution infrastructure at Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto | Water piping at Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.154823 36.152876 2079.1091818588393 7.083000183105469 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3483328 | 99.5 | 3483328 | 0 | 16672 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable. Assessor remarks: The tank is there but there is no water also pipes are there.
7777 | Water and Sewerage Management | purchase and installation of solar panel at Old Bahati dispensary | To procure and install solar panel at Old Bahati dispensary | Solar panel at Old Bahati dispensary procured and installed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.154613, 36.157595 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 788916 | 78.9 | 788916 | 1000000 | 211084 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's working.
7778 | Water and Sewerage Management | purchase and installation of solar panels at Karunga DCC borehole | To procure and install solar panels at Karunga DCC borehole | Solar panels at Karunga DCC borehole procured and installed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.150455 36.146665 2036.32080078125 5.013999938964844 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 788916 | 78.9 | 788916 | 1000000 | 211084 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
7779 | Water and Sewerage Management | purchase of 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | To procure 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School procured | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.14783, 36.121778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499973 | 100 | 499973 | 27 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesb. Assessor remarks: Good.
7780 | Water and Sewerage Management | Renovation of 2 Gatangi tanks in Wanyororo | To rehabilitate 2 Gatangi tanks in Wanyororo to restore functionality | 2 Gatangi tanks in Wanyororo rehabilitated | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.160234 36.102195 1851.86962890625 30.295000076293945 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 1737845 | 99.3 | 1737845 | 1745951 | 12155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Nor started.
7781 | Water and Sewerage Management | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti | To implement water piping for bahati farmer water, bahati trading centre, jomokenyatta area maili kumi and wanyororo gatangi to ngoti for access to clean water and environmental sustainability | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.160193, 36.102193 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499926 | 100 | 499926 | 500000 | 74 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes. Assessor remarks: The projects is on use.
7782 | Water and Sewerage Management | Drilling of a borehole and intallation of piping and electricity at mlima ugali | To implement drilling of a borehole and intallation of piping and electricity at mlima ugali for access to clean water and environmental sustainability | Drilling of a borehole and intallation of piping and electricity at mlima ugali completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.353373, 36.049497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 1865558 | 49.1 | 1865558 | 3800000 | 1934442 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GREAT RIFT GENERAL MERCHANTS. Assessor remarks: The project is complete and operational.
7783 | Water and Sewerage Management | Drilling of borehole for kelelwet water project | To provide access to clean water through borehole drilling at for kelelwet water project | Borehole drilled at for kelelwet water project | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | 0.3533, 36.049 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1987776 | 99.4 | 1987776 | 12224 | 12224 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no drilling which has been done.
7784 | Water and Sewerage Management | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol | To implement soimet water borehole - piping to kapkwen village,soimet village and kiptenden village and kipsimbol for access to clean water and environmental sustainability | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.342342, 36.036679 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797921 | 99.9 | 1797921 | 2079 | 2079 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: CIDER COLLECTIONS. Assessor remarks: There was no project done.
7785 | Water and Sewerage Management | Water works at barut | To implement water works at barut for access to clean water and environmental sustainability | Water works at barut completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.342342, 36.054698 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1455000 | 103.9 | 1455000 | 1500000 | -55000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: The project are still ongoing.
7786 | Water and Sewerage Management | Water works at kelelwet | To implement water works at kelelwet for access to clean water and environmental sustainability | Water works at kelelwet completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.342342, 36.054698 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1455000 | 97 | 1455000 | 1500000 | 45000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: The project are still ongoing.
7787 | Water and Sewerage Management | Water works in Mwariki health | To implement water works in mwariki health for access to clean water and environmental sustainability | Water works in Mwariki health completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | 0.353373, 36.049497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999197 | 99.9 | 999197 | 803 | 803 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No water works which has been done.
7788 | Water and Sewerage Management | Drilling borehole in Mwariki area and piping | To implement drilling borehole in mwariki area and piping for access to clean water and environmental sustainability | Drilling borehole in Mwariki area and piping completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | 0.324324, 36.054632 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 1921 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1463150 | 48.8 | 1463150 | 1473237 | 1536850 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7789 | Water and Sewerage Management | Completion of milimani tower tank | To complete milimani tower tank | Milimani tower tank completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2797826 | 99.9 | 2797826 | 1979714 | 2174 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7790 | Water and Sewerage Management | drilling of Gicheha community borehole | To implement drilling of gicheha community borehole for access to clean water and environmental sustainability | drilling of Gicheha community borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 2961397 | 92.5 | 2961397 | 238604 | 238603 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7791 | Water and Sewerage Management | Drilling of Gituamba borehole | To implement drilling of gituamba borehole for access to clean water and environmental sustainability | Drilling of Gituamba borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2588981.6 | 2588981.6 | 2588981.6 | Equitable | N/A | 2588981.6 | 0 | 2586423 | 99.9 | 2586423 | 2559 | 2558.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7792 | Water and Sewerage Management | Drilling of Kambi Ndoro borehole | To implement drilling of kambi ndoro borehole for access to clean water and environmental sustainability | Drilling of Kambi Ndoro borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | -0.728758, 36.502177 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 2516508 | 2516508 | 2516508 | Equitable | N/A | 2516508 | 0 | 2510298 | 99.8 | 2510298 | 55145 | 6210 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project is ongoing ,solarisation and pumbing ,tower..and tanks.
7793 | Water and Sewerage Management | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house | To implement kambi ndoro borehole - purchase of pumps and construction of pump house for access to clean water and environmental sustainability | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | -0.701617, 36.532842 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998664 | 99.9 | 1998664 | 1336 | 1336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
7794 | Water and Sewerage Management | Kamurugu borehole pump - purchase of pump for kamurugu borehole | To implement kamurugu borehole pump - purchase of pump for kamurugu borehole for access to clean water and environmental sustainability | Kamurugu borehole pump - purchase of pump for kamurugu borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1469109.14 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7795 | Water and Sewerage Management | Muteithia Borehole - Drilling of Muteithia borehole | To implement muteithia borehole - drilling of muteithia borehole for access to clean water and environmental sustainability | Muteithia Borehole - Drilling of Muteithia borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798082 | 99.9 | 2798082 | 1918 | 1918 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7796 | Water and Sewerage Management | Muteithia Borehole Drilling(additional Funding) | To implement muteithia borehole drilling(additional funding) for access to clean water and environmental sustainability | Muteithia Borehole Drilling(additional Funding) completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7797 | Water and Sewerage Management | Piping in Kirima Water Project | To provide water distribution infrastructure at in Kirima Water Project | Water piping at in Kirima Water Project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499366 | 100 | 2499366 | 800 | 634 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7798 | Water and Sewerage Management | Piping in Mununga Water Project | To provide water distribution infrastructure at in Mununga Water Project | Water piping at in Mununga Water Project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999200 | 100 | 1999200 | 800 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7799 | Water and Sewerage Management | Piping of Kamurugu water project | To provide water distribution infrastructure at Kamurugu water project | Water piping at Kamurugu water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2900000 | 2900000 | 2900000 | Equitable | N/A | 2900000 | 0 | 2897000 | 99.9 | 2897000 | 800 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7800 | Water and Sewerage Management | purchase and installation of water pump for Kamurugu borehole project | To procure and install water pump for Kamurugu borehole project | Water pump for Kamurugu borehole project procured and installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991160 | 99.6 | 1991160 | 2500000 | 8840 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7801 | Water and Sewerage Management | Bahati water works project | To implement bahati water works project for access to clean water and environmental sustainability | Bahati water works project completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174193, 36.135371 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 6000000 | 14124449 | 14124449 | Equitable | N/A | 14124449 | 0 | 1197584 | 8.5 | 1197584 | 1197584 | 12926865 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes it did. Assessor remarks: Nicely done.
7802 | Water and Sewerage Management | Bahati water works | To implement bahati water works for access to clean water and environmental sustainability | Bahati water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2991652 | 59.8 | 2991652 | 2008348 | 2008348 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
7803 | Water And Sewerage Management | Piping at Rumathi Water project | To provide water distribution infrastructure at Rumathi Water project | Water piping at Rumathi Water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.127386, 36.178531 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 999589.25 | 999589.25 | 999589.25 | Equitable | N/A | 999589.25 | 0 | 998968 | 99.9 | 998968 | 621 | 621.25 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water is in use.
7804 | Water and Sewerage Management | purchase and supply of 10,000 litres water tanks at Osembo primary school and St. John secondary school | To procure and supply 10,000 litres water tanks at Osembo primary school and St. John secondary school | 10,000 litres water tanks at Osembo primary school and St. John secondary school procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.173854 36.132917 0 87.5999984741211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is well in use.
7805 | Water and Sewerage Management | purchase and supply of 10,000 litres water tanks for public toilet at Maili Kumi level 4 hospital | To procure and supply 10,000 litres water tanks for public toilet at Maili Kumi level 4 hospital | 10,000 litres water tanks for public toilet at Maili Kumi level 4 hospital procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.170023 36.123607 1924.5 53.448001861572266 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 150000 | 150000 | 150000 | Equitable | N/A | 150000 | 0 | 89377 | 59.6 | 89377 | 150000 | 60623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7806 | Water and Sewerage Management | purchase of 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | To procure 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School procured | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.14783, 36.121778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499973 | 100 | 499973 | 27 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesb. Assessor remarks: Good.
7807 | Water and Sewerage Management | Purchase of water tank at Jakaranda primary school | To procure water tank at Jakaranda primary school | Water tank at Jakaranda primary school procured | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.150455 36.146665 2036.32080078125 5.013999938964844 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 100000 | 100 | 100000 | 100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
7808 | Water and Sewerage Management | Renovation of 2 Gatangi tanks in Wanyororo | To rehabilitate 2 Gatangi tanks in Wanyororo to restore functionality | 2 Gatangi tanks in Wanyororo rehabilitated | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.160234 36.102195 1851.86962890625 30.295000076293945 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1750000 | 1745951.45 | 1745951.45 | Equitable | N/A | 1745951.45 | 0 | 1737845 | 99.5 | 1737845 | 1745951 | 8106.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Nor started.
7809 | Water and Sewerage Management | Supply of pipes(1,2 and 3.5 inches) in Bahati ward | To implement supply of pipes(1,2 and 3.5 inches) in bahati ward for access to clean water and environmental sustainability | Supply of pipes(1,2 and 3.5 inches) in Bahati ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.154613 36.157595 2094.000244140625 6.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 496000 | 99.2 | 496000 | 500000 | 4000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
7810 | Water and Sewerage Management | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti | To implement water piping for bahati farmer water, bahati trading centre, jomokenyatta area maili kumi and wanyororo gatangi to ngoti for access to clean water and environmental sustainability | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.160193, 36.102193 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499926 | 100 | 499926 | 500000 | 74 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes. Assessor remarks: The projects is on use.
7811 | Water and Sewerage Management | Drilling of a borehole and intallation of piping and electricity at mlima ugali | To implement drilling of a borehole and intallation of piping and electricity at mlima ugali for access to clean water and environmental sustainability | Drilling of a borehole and intallation of piping and electricity at mlima ugali completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.353373, 36.049497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 1865558 | 49.1 | 1865558 | 3800000 | 1934442 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GREAT RIFT GENERAL MERCHANTS. Assessor remarks: The project is complete and operational.
7812 | Water and Sewerage Management | Drilling of borehole for kelelwet water project | To provide access to clean water through borehole drilling at for kelelwet water project | Borehole drilled at for kelelwet water project | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.3533, 36.049 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1987776 | 99.4 | 1987776 | 12224 | 12224 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no drilling which has been done.
7813 | Water and Sewerage Management | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol | To implement soimet water borehole - piping to kapkwen village,soimet village and kiptenden village and kipsimbol for access to clean water and environmental sustainability | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.342342, 36.036679 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797921 | 99.9 | 1797921 | 2079 | 2079 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: CIDER COLLECTIONS. Assessor remarks: There was no project done.
7814 | Water and Sewerage Management | supply of water pipes to Barut community borehole | To implement supply of water pipes to barut community borehole for access to clean water and environmental sustainability | supply of water pipes to Barut community borehole completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.324324, 36.054632 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1422856 | 94.9 | 1422856 | 1500000 | 77144 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: NDIRANCHI GROUP LTD. Assessor remarks: The pipes were bought.
7815 | Water and Sewerage Management | Water works at Barut | To implement water works at barut for access to clean water and environmental sustainability | Water works at Barut completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.342342, 36.054698 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1455000 | 0 | 1455000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: The project are still ongoing.
7816 | Water and Sewerage Management | Water works in Mwariki health | To implement water works in mwariki health for access to clean water and environmental sustainability | Water works in Mwariki health completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.353373, 36.049497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999197 | 99.9 | 999197 | 803 | 803 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No water works which has been done.
7817 | Water and Sewerage Management | Drilling borehole in Mwariki area and piping | To implement drilling borehole in mwariki area and piping for access to clean water and environmental sustainability | Drilling borehole in Mwariki area and piping completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.324324, 36.054632 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 1921 | 3000000 | 1473237 | 1473237 | Equitable | N/A | 1473237 | 0 | 1463150 | 99.3 | 1463150 | 1473237 | 10087 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
7818 | Water and Sewerage Management | drilling of Gicheha community borehole | To implement drilling of gicheha community borehole for access to clean water and environmental sustainability | drilling of Gicheha community borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 2961397 | 92.5 | 2961397 | 238604 | 238603 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7819 | Water and Sewerage Management | Drilling of Gituamba borehole | To implement drilling of gituamba borehole for access to clean water and environmental sustainability | Drilling of Gituamba borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2588981.6 | 2588981.6 | 2588981.6 | Equitable | N/A | 2588981.6 | 0 | 2586423 | 99.9 | 2586423 | 2559 | 2558.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7820 | Water and Sewerage Management | installation of solar and fencing of Kirima borehole | To install solar and fencing of Kirima borehole | Solar and fencing of Kirima borehole installed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2300355 | 92 | 2300355 | 199645 | 199645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7821 | Water and Sewerage Management | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house | To implement kambi ndoro borehole - purchase of pumps and construction of pump house for access to clean water and environmental sustainability | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.701617, 36.532842 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998664 | 99.9 | 1998664 | 1336 | 1336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
7822 | Water and Sewerage Management | Muteithia Borehole - Drilling of Muteithia borehole | To implement muteithia borehole - drilling of muteithia borehole for access to clean water and environmental sustainability | Muteithia Borehole - Drilling of Muteithia borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798082 | 99.9 | 2798082 | 1918 | 1918 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7823 | Water and Sewerage Management | Muteithia Borehole Drilling(additional Funding) | To implement muteithia borehole drilling(additional funding) for access to clean water and environmental sustainability | Muteithia Borehole Drilling(additional Funding) completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7824 | Water and Sewerage Management | Piping in Kirima Water Project | To provide water distribution infrastructure at in Kirima Water Project | Water piping at in Kirima Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2499366 | 2499366 | Equitable | N/A | 2499366 | 0 | 2499366 | 100 | 2499366 | 800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7825 | Water and Sewerage Management | Piping in Mununga Water Project | To provide water distribution infrastructure at in Mununga Water Project | Water piping at in Mununga Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999200 | 100 | 1999200 | 800 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7826 | Water and Sewerage Management | Piping of Kamurugu water project | To provide water distribution infrastructure at Kamurugu water project | Water piping at Kamurugu water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2900000 | 2897000 | 2897000 | Equitable | N/A | 2897000 | 0 | 2897000 | 100 | 2897000 | 800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7827 | Water and Sewerage Management | purchase and installation of pump at Gicheha borehole | To procure and install pump at Gicheha borehole | Pump at Gicheha borehole procured and installed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1991160 | 79.6 | 1991160 | 2500000 | 508840 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7828 | Water and Sewerage Management | Bavuni borehole power connection and water works | To implement bavuni borehole power connection and water works for access to clean water and environmental sustainability | Bavuni borehole power connection and water works completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.252415, 36.187695 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 449019 | 89.8 | 449019 | 449019 | 50981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
7829 | Water and Sewerage Management | Construction of intake and piping at Kanyiriri Water project | To construct intake and piping at Kanyiriri Water project | Intake and piping at Kanyiriri Water project constructed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.251523, 36.24046 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Intake needs protection and fencing.
7830 | Water and Sewerage Management | construction of kiamunyeki B water project tank | To construct kiamunyeki B water project tank | Kiamunyeki B water project tank constructed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.22522, 36.184739 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Gichamba holding. Assessor remarks: Good.
7831 | Water and Sewerage Management | Construction of Water tank at Faari Area(wanyoro water project) | To construct Water tank at Faari Area(wanyoro water project) | Water tank at Faari Area(wanyoro water project) constructed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.251917, 36.187728 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Gichamba holdings Ltd. Assessor remarks: Good.
7832 | Water and Sewerage Management | Drilling and purchase of water pump for Wanyororo water project | To implement drilling and purchase of water pump for wanyororo water project for access to clean water and environmental sustainability | Drilling and purchase of water pump for Wanyororo water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.252388, 36.187673 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1369685 | 34.2 | 1369685 | 1369685 | 2630315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Naxxy limited. Assessor remarks: Ongoing project.
7833 | Water and Sewerage Management | Dundori polytechnic water works water works Construction of an intake, Piping and construction of water tank | To implement dundori polytechnic water works water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Dundori polytechnic water works water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/2017 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1078369 | 98 | 1078369 | 0 | 21631 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
7834 | Water and Sewerage Management | Dundori water project water works Construction of an intake, Piping and construction of water tank | To implement dundori water project water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Dundori water project water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/2017 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494853 | 99 | 494853 | 0 | 5147 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
7835 | Water and Sewerage Management | Dundori Water works | To implement dundori water works for access to clean water and environmental sustainability | Dundori Water works completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.239802 36.241437 2324.000244140625 5.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1559761 | 78 | 1559761 | 140239 | 440239 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7836 | Water and Sewerage Management | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump | To implement mugwathi dundori water project - drilling of mugwathi dundori borehole and purchase of pump for access to clean water and environmental sustainability | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.235918, 36.182103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/2018 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7837 | Water and Sewerage Management | Nyumba Kumi water project water works Construction of an intake, Piping and construction of water tank | To implement nyumba kumi water project water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Nyumba Kumi water project water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/2017 | 3000000 | 2257142 | 2257142 | Equitable | N/A | 2257142 | 0 | 2191959 | 97.1 | 2191959 | 0 | 65183 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
7838 | Water and Sewerage Management | Piping and construction of intake Kimae Water project | To provide water distribution infrastructure at and construction of intake Kimae Water project | Water piping at and construction of intake Kimae Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.23988, 36.241492 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1500000 | 150 | 1500000 | 1000000 | -500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational needs upgrade and maintenance and fencing.
7839 | Water and Sewerage Management | Piping of Kamburi Water project | To provide water distribution infrastructure at Kamburi Water project | Water piping at Kamburi Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.261988 36.17999 1980.9000244140625 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 795445 | 79.5 | 795445 | 1000000 | 204555 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7840 | Water and Sewerage Management | Piping of Tabuga Water project | To provide water distribution infrastructure at Tabuga Water project | Water piping at Tabuga Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.261988 36.17999 1980.9000244140625 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 795445 | 99.4 | 795445 | 1000000 | 4555 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7841 | Water and Sewerage Management | Purchase of water pump for Menengai water project | To procure water pump for Menengai water project | Water pump for Menengai water project procured | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.271495, 36.206253 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2261527 | 98.3 | 2261527 | 1369685 | 38473 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jawap general contractors ltd. Assessor remarks: Not functioning.
7842 | Water and Sewerage Management | Supply of water tanks to elderly widowed women group in Dundori ward | To implement supply of water tanks to elderly widowed women group in dundori ward for access to clean water and environmental sustainability | Supply of water tanks to elderly widowed women group in Dundori ward completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.263061, 36.187479 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996816 | 99.7 | 996816 | 996816 | 3184 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward hard to track.
7843 | Water and Sewerage Management | Wanyoro borehole power connection and water works | To implement wanyoro borehole power connection and water works for access to clean water and environmental sustainability | Wanyoro borehole power connection and water works completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.252415, 36.187695 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 542370 | 542370 | 542370 | Equitable | N/A | 542370 | 0 | 541279 | 99.8 | 541279 | 542370 | 1091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
7844 | Water and Sewerage Management | Bavuni borehole power connection and water works | To implement bavuni borehole power connection and water works for access to clean water and environmental sustainability | Bavuni borehole power connection and water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.252415, 36.187695 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 449019 | 89.8 | 449019 | 449019 | 50981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
7845 | Water and Sewerage Management | construction of Dundori water tank | To construct Dundori water tank | Dundori water tank constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.236015 36.182315 2054.3999999999996 8.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1417143 | 94.5 | 1417143 | 1500000 | 82857 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kewaska company. Assessor remarks: Good.
7846 | Water and Sewerage Management | construction of kiamunyeki B water project tank | To construct kiamunyeki B water project tank | Kiamunyeki B water project tank constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.22522, 36.184739 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Gichamba holding. Assessor remarks: Good.
7847 | Water and Sewerage Management | Construction of Water tank at Faari Area(wanyoro water project) | To construct Water tank at Faari Area(wanyoro water project) | Water tank at Faari Area(wanyoro water project) constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.251917, 36.187728 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Gichamba holdings Ltd. Assessor remarks: Good.
7848 | Water and Sewerage Management | Drilling and purchase of water pump for Wanyororo water project | To implement drilling and purchase of water pump for wanyororo water project for access to clean water and environmental sustainability | Drilling and purchase of water pump for Wanyororo water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.252388, 36.187673 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 1526377.2 | 1526377.2 | Equitable | N/A | 1526377.2 | 0 | 1369685 | 89.7 | 1369685 | 1369685 | 156692.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Naxxy limited. Assessor remarks: Ongoing project.
7849 | Water and Sewerage Management | drilling, equipping and water works at Dundori water projects | To implement drilling, equipping and water works at dundori water projects for access to clean water and environmental sustainability | drilling, equipping and water works at Dundori water projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.24679, 36.2379 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 621700 | 17.8 | 621700 | 621700 | 2878300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nemoca enterprise. Assessor remarks: In good state.
7850 | Water and Sewerage Management | Dundori water power connection | To implement dundori water power connection for access to clean water and environmental sustainability | Dundori water power connection completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.239802 36.241437 2324.000244140625 5.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 448311 | 448311 | 448311 | Equitable | N/A | 448311 | 0 | 448311 | 100 | 448311 | 448311 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7851 | Water and Sewerage Management | Dundori Water works | To implement dundori water works for access to clean water and environmental sustainability | Dundori Water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.239802 36.241437 2324.000244140625 5.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1559761 | 78 | 1559761 | 140239 | 440239 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7852 | Water and Sewerage Management | Installation of solar panel and water works at bavuni water borehole | To install solar panel and water works at bavuni water borehole | Solar panel and water works at bavuni water borehole installed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.235943, 36.182293 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 383127 | 15.3 | 383127 | 1000000 | 2116873 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Metro EDD company. Assessor remarks: Good.
7853 | Water and Sewerage Management | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump | To implement mugwathi dundori water project - drilling of mugwathi dundori borehole and purchase of pump for access to clean water and environmental sustainability | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.235918, 36.182103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/2018 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7854 | Water and Sewerage Management | supply of pipess to water projects | To implement supply of pipess to water projects for access to clean water and environmental sustainability | supply of pipess to water projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246448, 36.238052 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 650205 | 92.9 | 650205 | 49795 | 49795 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Endorse ventures. Assessor remarks: Good.
7855 | Water and Sewerage Management | Supply of water tanks to elderly widowed women group in Dundori ward | To implement supply of water tanks to elderly widowed women group in dundori ward for access to clean water and environmental sustainability | Supply of water tanks to elderly widowed women group in Dundori ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.263061, 36.187479 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1000000 | 996816 | 996816 | Equitable | N/A | 996816 | 0 | 996816 | 100 | 996816 | 996816 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward hard to track.
7856 | Water and Sewerage Management | supply of water tanks to vulnerable women | To implement supply of water tanks to vulnerable women for access to clean water and environmental sustainability | supply of water tanks to vulnerable women completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.2631, 36.187452 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 637724 | 79.7 | 637724 | 162276 | 162276 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward.
7857 | Water and Sewerage Management | Wanyoro borehole power connection and water works | To implement wanyoro borehole power connection and water works for access to clean water and environmental sustainability | Wanyoro borehole power connection and water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.252415, 36.187695 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 542370 | 542370 | 542370 | Equitable | N/A | 542370 | 0 | 541279 | 99.8 | 541279 | 542370 | 1091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
7858 | Water and Sewerage Management | Eburru/Mbaruk Water Works | To implement eburru/mbaruk water works for access to clean water and environmental sustainability | Eburru/Mbaruk Water Works completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | -0.488148, 36.156876 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 22-23 | 20500000 | 20500000 | 20500000 | Equitable | N/A | 20500000 | 0 | 2491100 | 12.2 | 2491100 | 2686526 | 18008900 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Value for money. Viable: Yes. Contractor: Online movers ltd box 16147-Nakuru. Assessor remarks: Well done.
7859 | Water and Sewerage Management | Mbaruk / Eburru ward water project - water works - piping and tank renovations for Sogonoi, borehole and solar panel for Morop, borehole and solar for Echariria, piping in Ngorika ndogo, pema piping, piping meleleshwa, piping Oljorai, piping Gema water, Kiungururia East gate main piping, Thome dam repair and desilting, Jaika dam repair and desilting | To implement mbaruk / eburru ward water project - water works - piping and tank renovations for sogonoi, borehole and solar panel for morop, borehole and solar for echariria, piping in ngorika ndogo, pema piping, piping meleleshwa, piping oljorai, piping gema water, kiungururia east gate main piping, thome dam repair and desilting, jaika dam repair and desilting for access to clean water and environmental sustainability | Mbaruk / Eburru ward water project - water works - piping and tank renovations for Sogonoi, borehole and solar panel for Morop, borehole and solar for Echariria, piping in Ngorika ndogo, pema piping, piping meleleshwa, piping Oljorai, piping Gema water, Kiungururia East gate main piping, Thome dam repair and desilting, Jaika dam repair and desilting completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 18000000 | 11588481 | 11588481 | Equitable | N/A | 11588481 | 0 | 11588481 | 100 | 11588481 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7860 | Water and Sewerage Management | Nagum piping | To implement nagum piping for access to clean water and environmental sustainability | Nagum piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2831499.91 | 2831499.91 | 2831499.91 | Equitable | N/A | 2831499.91 | 0 | 2831500 | 100 | 2831500 | 444810 | -0.09 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7861 | Water and Sewerage Management | Piping of water from Gilgil through Gema to Kamathatha | To provide water distribution infrastructure at water from Gilgil through Gema to Kamathatha | Water piping at water from Gilgil through Gema to Kamathatha completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998048 | 99.9 | 1998048 | 1000000 | 1952 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7862 | Water and Sewerage Management | Piping of water in Barnabas area | To provide water distribution infrastructure at water in Barnabas area | Water piping at water in Barnabas area completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 1200000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7863 | Water and Sewerage Management | Purchase of land for Kirima water project | To acquire land for Kirima water project | Land for Kirima water project acquired | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2529000 | 2529000 | 2529000 | Equitable | N/A | 2529000 | 0 | 0 | 0 | 0 | 2529000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7864 | University -Ngorika ndogo piping | University -Ngorika ndogo piping | To implement university -ngorika ndogo piping for access to clean water and environmental sustainability | University -Ngorika ndogo piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU-MBARUK | -0.361044, 36.19708 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | 17/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 489725 | 97.9 | 489725 | 0 | 10275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Water connected to few people.
7865 | Water and Sewerage Management | Completion of Milimani water project/satewa | To complete Milimani water project/satewa | Milimani water project/satewa completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999788 | 100 | 1999788 | 212 | 212 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7866 | Water and Sewerage Management | Completion of ndimu water project | To complete ndimu water project | Ndimu water project completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7867 | Water and Sewerage Management | Completion of Nyariche water project | To complete Nyariche water project | Nyariche water project completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2235974 | 74.5 | 2235974 | 264026 | 764026 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7868 | Water and Sewerage Management | Construction of water tank and installation of pump at Cheponde/Ribotfarm Water project | To construct water tank and installation of pump at Cheponde/Ribotfarm Water project | Water tank and installation of pump at Cheponde/Ribotfarm Water project constructed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.165752 35.696828 0 2299.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2756113 | 2756113 | 2756113 | Equitable | N/A | 2756113 | 0 | 2756113 | 100 | 2756113 | 264026 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
7869 | Water and Sewerage Management | Green estate water works | To implement green estate water works for access to clean water and environmental sustainability | Green estate water works completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.305135 35.798927 2498.4 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2500001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187550 | 99 | 1187550 | 1000000 | 12450 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet connected to borehole.
7870 | Water and Sewerage Management | Ndimu borehole | To implement ndimu borehole for access to clean water and environmental sustainability | Ndimu borehole completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.292714 35.791345 0 2700 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2799698 | 100 | 2799698 | 989608 | 302 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
7871 | Water and Sewerage Management | Nyakiambi/Karunga Borehole Completion | To implement nyakiambi/karunga borehole completion for access to clean water and environmental sustainability | Nyakiambi/Karunga Borehole Completion completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.264914, 35.831575 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
7872 | Water and Sewerage Management | Nyariche community water projects- purchase of water pipes to supply water to Nyakiambi, Arimi and Ribot areas | To implement nyariche community water projects- purchase of water pipes to supply water to nyakiambi, arimi and ribot areas for access to clean water and environmental sustainability | Nyariche community water projects- purchase of water pipes to supply water to Nyakiambi, Arimi and Ribot areas completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.284884 35.845889 0 1399.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499965 | 100 | 2499965 | 0 | 35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
7873 | Water and Sewerage Management | Piping of Mwangi -Michuki-Mukinyai water project | To provide water distribution infrastructure at Mwangi -Michuki-Mukinyai water project | Water piping at Mwangi -Michuki-Mukinyai water project completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.238303, 35.786763 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project is functional.
7874 | Water and Sewerage Management | Piping on nyariche Nyakiambi-karuga water project | To provide water distribution infrastructure at on nyariche Nyakiambi-karuga water project | Water piping at on nyariche Nyakiambi-karuga water project completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.294954 35.766447 0 2799.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995056 | 99.5 | 995056 | 1000000 | 4944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GILECHAM KENYA SUPPLIES. Assessor remarks: Good.
7875 | Water and Sewerage Management | Ndimu water project completion | To implement ndimu water project completion for access to clean water and environmental sustainability | Ndimu water project completion completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.294145, 35.7941 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | - | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2698749 | 100 | 2698749 | 3500000 | 1251 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Only solarization was done by county government,borehole was done by NG-CDF.
7876 | Water and Sewerage Management | Council Tank to Mbombo piping - purchase of water pipes for Council Tank to Mbombo | To implement council tank to mbombo piping - purchase of water pipes for council tank to mbombo for access to clean water and environmental sustainability | Council Tank to Mbombo piping - purchase of water pipes for Council Tank to Mbombo completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.569973, 36.108448 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995525 | 99.6 | 995525 | 0 | 4475 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipes laid from kiptawanyi to aMakongo.
7877 | Water and Sewerage Management | Gituamba / Kamugunda water project - purchase of water pipes for Gituamba / Kamugunda water project | To implement gituamba / kamugunda water project - purchase of water pipes for gituamba / kamugunda water project for access to clean water and environmental sustainability | Gituamba / Kamugunda water project - purchase of water pipes for Gituamba / Kamugunda water project completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799343 | 99.9 | 799343 | 0 | 657 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7878 | Water and Sewerage Management | installation of submiersible water pump and solar panel at Nyarienda borehole | To install submiersible water pump and solar panel at Nyarienda borehole | Submiersible water pump and solar panel at Nyarienda borehole installed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.63272, 36.115741 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3758989 | 96.4 | 3758989 | 1000000 | 141011 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs security enhancement.
7879 | Water and Sewerage Management | Kahuho west Water Tank - Construction of water tank | To implement kahuho west water tank - construction of water tank for access to clean water and environmental sustainability | Kahuho west Water Tank - Construction of water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.640563, 36.145693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995672 | 99.6 | 995672 | 4328 | 4328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
7880 | Water and Sewerage Management | Makongo Tank - Construction of Water tank and Piping | To implement makongo tank - construction of water tank and piping for access to clean water and environmental sustainability | Makongo Tank - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1480515 | 98.7 | 1480515 | 19485 | 19485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7881 | Water and Sewerage Management | Miti Miti centre - competion of water piping | To implement miti miti centre - competion of water piping for access to clean water and environmental sustainability | Miti Miti centre - competion of water piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.526958, 36.073972 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691497 | 99.5 | 1691497 | 1700000 | 8503 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
7882 | Mugaa Water Tank | Mugaa Water Tank | To implement mugaa water tank for access to clean water and environmental sustainability | Mugaa Water Tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.558901, 36.076289 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 998812 | 998812 | 998812 | Equitable | N/A | 998812 | 0 | 1979879 | 198.2 | 1979879 | 998812 | -981067 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
7883 | Water and Sewerage Management | Munanda police water tank - Construction of tank police water tank | To implement munanda police water tank - construction of tank police water tank for access to clean water and environmental sustainability | Munanda police water tank - Construction of tank police water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.597591, 36.111653 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998341 | 99.8 | 998341 | 1000000 | 1659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
7884 | Water and Sewerage Management | Muririgua Tan - Construction of Water tank and Piping | To implement muririgua tan - construction of water tank and piping for access to clean water and environmental sustainability | Muririgua Tan - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1500000 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7885 | Water and Sewerage Management | Ndamu Tank - competion of piping works | To implement ndamu tank - competion of piping works for access to clean water and environmental sustainability | Ndamu Tank - competion of piping works completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.55338 36.112845 1929.4 12.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 790909 | 39.5 | 790909 | 13029 | 1209091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Ues. Viable: Yes. Assessor remarks: Operational.
7886 | Water and Sewerage Management | Ndibai village - completion of water tank and water piping | To implement ndibai village - completion of water tank and water piping for access to clean water and environmental sustainability | Ndibai village - completion of water tank and water piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.553445 36.112768 2020.2 15 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 1588887 | 58.8 | 1588887 | 6113 | 1111113 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7887 | Water And Sewerage Management | Ngesha A water tank | To implement ngesha a water tank for access to clean water and environmental sustainability | Ngesha A water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.582928, 36.115417 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1979879.08 | 1979879.08 | 1979879.08 | Equitable | N/A | 1979879.08 | 0 | 1979879 | 100 | 1979879 | 998812 | 0.08 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7888 | Water and Sewerage Management | Njeru water tank | To implement njeru water tank for access to clean water and environmental sustainability | Njeru water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.558886, 36.07641 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1998598 | 1998598 | 1998598 | Equitable | N/A | 1998598 | 0 | 1979879 | 99.1 | 1979879 | 1998598 | 18719 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
7889 | Water and Sewerage Management | Nyarienda - Kanorero water works | To implement nyarienda - kanorero water works for access to clean water and environmental sustainability | Nyarienda - Kanorero water works completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.633168 36.115234 2504.494 4.165999889373779 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2100000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2699650 | 100 | 2699650 | 3300000 | 350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs renovation.
7890 | Rerechua Borehole - Instalation of Solar Panel and Booster Pump | Rerechua Borehole - Instalation of Solar Panel and Booster Pump | To implement rerechua borehole - instalation of solar panel and booster pump for access to clean water and environmental sustainability | Rerechua Borehole - Instalation of Solar Panel and Booster Pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.563339 36.117975 1961.0999755859375 1.0069999694824219 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3697674 | 99.9 | 3697674 | 1480 | 2326 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7891 | Water and Sewerage Management | Rerechua Water Project - Purchase of PPI pipes(3 inches) | To implement rerechua water project - purchase of ppi pipes(3 inches) for access to clean water and environmental sustainability | Rerechua Water Project - Purchase of PPI pipes(3 inches) completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.563372, 36.117994 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996788 | 99.8 | 1996788 | 0 | 3212 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7892 | Water And Sewerage Management | Settlement Borehole - installation of solar panel and purchase of submersible water pump | To implement settlement borehole - installation of solar panel and purchase of submersible water pump for access to clean water and environmental sustainability | Settlement Borehole - installation of solar panel and purchase of submersible water pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.529775, 36.090549 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3398520 | 100 | 3398520 | 1480 | 1480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Function.
7893 | Water and Sewerage Management | Eburru/Mbaruk Water Works | To implement eburru/mbaruk water works for access to clean water and environmental sustainability | Eburru/Mbaruk Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.488148, 36.156876 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 22-23 | 20500000 | 14832983.85 | 14832983.85 | Equitable | N/A | 14832983.85 | 0 | 2491100 | 16.8 | 2491100 | 2686526 | 12341883.85 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Value for money. Viable: Yes. Contractor: Online movers ltd box 16147-Nakuru. Assessor remarks: Well done.
7894 | Water and Sewerage Management | Equipping of kasambara borehole | To equip kasambara borehole with necessary facilities and equipment | Kasambara borehole equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.36445, 36.239523 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | No information | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 4699964 | 97.9 | 4699964 | 4800000 | 100036 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara. Assessor remarks: Successful project.
7895 | Water and Sewerage Management | Equipping of workers borehole | To equip workers borehole with necessary facilities and equipment | Workers borehole equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.342227, 36.151336 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021/22 | 4900000 | 4900000 | 4900000 | Equitable | N/A | 4900000 | 0 | 4895816 | 99.9 | 4895816 | 4900000 | 4184 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Mwea construction. Assessor remarks: Low usability/ low utilization rate.
7896 | Water and Sewerage Management | Equipping ,solarisation and fencing of nderit borehole | To equip ,solarisation and fencing of nderit borehole with necessary facilities and equipment | ,solarisation and fencing of nderit borehole equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5991939 | 99.9 | 5991939 | 6000000 | 8061 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7897 | Water and Sewerage Management | Fencing of kasambara borehole | To secure kasambara borehole through fencing | Kasambara borehole fenced and secured | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.36445, 36.239523 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | No information | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 394446 | 98.6 | 394446 | 400000 | 5554 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara. Assessor remarks: Successful project.
7898 | Water and Sewerage Management | Piping and water point from Echariria to Kirima | To provide water distribution infrastructure at and water point from Echariria to Kirima | Water piping at and water point from Echariria to Kirima completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.336579, 36.169605 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2492315 | 99.7 | 2492315 | 2500000 | 7685 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: The project was fairly done but it's not operational at this moment because of political issues..
7899 | Water and Sewerage Management | Piping at miti mingi to kiwanja ndege | To provide water distribution infrastructure at miti mingi to kiwanja ndege | Water piping at miti mingi to kiwanja ndege completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.346735, 36.167249 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Not yet completed. Contractor: Unkworn. Assessor remarks: Done Fair work.
7900 | Water and Sewerage Management | Piping of water from Kirimato to Miririshwa | To provide water distribution infrastructure at water from Kirimato to Miririshwa | Water piping at water from Kirimato to Miririshwa completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru-Mbaruk | -0.336579, 36.169605 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 998101 | 0 | 998101 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: The project was fairly done but it's not operational at this moment because of political issues..
7901 | Water and Sewerage Management | Completion of Milimani water project/satewa | To complete Milimani water project/satewa | Milimani water project/satewa completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999788 | 100 | 1999788 | 212 | 212 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7902 | Water and Sewerage Management | Completion of ndimu water project | To complete ndimu water project | Ndimu water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7903 | Water and Sewerage Management | Completion of Nyariche water project | To complete Nyariche water project | Nyariche water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3000000 | 2998991 | 2998991 | Equitable | N/A | 2998991 | 0 | 2235974 | 74.6 | 2235974 | 264026 | 763017 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7904 | Water and Sewerage Management | Equipping of mwangi michuki borehole | To equip mwangi michuki borehole with necessary facilities and equipment | Mwangi michuki borehole equipped | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.210282 35.784866 0 899.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2199518 | 73.3 | 2199518 | 800482 | 800482 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good use.
7905 | Water and Sewerage Management | equipping of ndimu water project | To equip ndimu water project with necessary facilities and equipment | Ndimu water project equipped | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
7906 | Water and Sewerage Management | Nyakiambi/Karunga Borehole Completion | To implement nyakiambi/karunga borehole completion for access to clean water and environmental sustainability | Nyakiambi/Karunga Borehole Completion completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
7907 | Water and Sewerage Management | Pipe laying for Ndimu borehole water | To implement pipe laying for ndimu borehole water for access to clean water and environmental sustainability | Pipe laying for Ndimu borehole water completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1484191 | 98.9 | 1484191 | 1500000 | 15809 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
7908 | Water and Sewerage Management | Piping of Mwangi -Michuki-Mukinyai water project | To provide water distribution infrastructure at Mwangi -Michuki-Mukinyai water project | Water piping at Mwangi -Michuki-Mukinyai water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.238303, 35.786763 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project is functional.
7909 | Water and Sewerage Management | Piping on nyariche Nyakiambi-karuga water project | To provide water distribution infrastructure at on nyariche Nyakiambi-karuga water project | Water piping at on nyariche Nyakiambi-karuga water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995056 | 99.5 | 995056 | 1000000 | 4944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GILECHAM KENYA SUPPLIES. Assessor remarks: Good.
7910 | Water and Sewerage Management | Repair of intake at Ndimu primary water project | To rehabilitate intake at Ndimu primary water project to restore functionality | Intake at Ndimu primary water project rehabilitated | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 989422 | 98.9 | 989422 | 1000000 | 10578 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Euro Enterprises company limited. Assessor remarks: Complete and functional.
7911 | Water and Sewerage Management | Water piping at Arimi chieponde nyariche | To implement water piping at arimi chieponde nyariche for access to clean water and environmental sustainability | Water piping at Arimi chieponde nyariche completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.290391 35.774293 0 2900 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to make followup on ownership documents.
7912 | Water and Sewerage Management | construction of Rerechua tank | To construct Rerechua tank | Rerechua tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.563348, 36.118021 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187473 | 99 | 1187473 | 1200000 | 12527 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
7913 | Water and Sewerage Management | construction of upper Kanorero water tank | To construct upper Kanorero water tank | Upper Kanorero water tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.602644, 36.117023 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1272660 | 97.9 | 1272660 | 1300000 | 27340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
7914 | Water and Sewerage Management | drilling of Meli borehole | To implement drilling of meli borehole for access to clean water and environmental sustainability | drilling of Meli borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.601384, 36.106642 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 3619344 | 80.4 | 3619344 | 880656 | 880656 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not equipped.
7915 | Water and Sewerage Management | Hawaziporrah cattle dip eleveted tank and pipes | To implement hawaziporrah cattle dip eleveted tank and pipes for access to clean water and environmental sustainability | Hawaziporrah cattle dip eleveted tank and pipes completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.565733 36.116574 1961.0999755859375 92.9000015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 4303743 | 4303743 | 4303743 | Equitable | N/A | 4303743 | 0 | 4210834 | 97.8 | 4210834 | 4303743 | 92909 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Stalled.
7916 | Water and Sewerage Management | Kahuho west Water Tank - Construction of water tank | To implement kahuho west water tank - construction of water tank for access to clean water and environmental sustainability | Kahuho west Water Tank - Construction of water tank completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.640563, 36.145693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995672 | 99.6 | 995672 | 4328 | 4328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
7917 | Water and Sewerage Management | Makongo Tank - Construction of Water tank and Piping | To implement makongo tank - construction of water tank and piping for access to clean water and environmental sustainability | Makongo Tank - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1480515 | 98.7 | 1480515 | 19485 | 19485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7918 | Water and Sewerage Management | Miti Miti centre - completion of water piping | To implement miti miti centre - completion of water piping for access to clean water and environmental sustainability | Miti Miti centre - completion of water piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.526958, 36.073972 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691497 | 99.5 | 1691497 | 8503 | 8503 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
7919 | Water and Sewerage Management | Mitimingi settlement borehole pipes | To implement mitimingi settlement borehole pipes for access to clean water and environmental sustainability | Mitimingi settlement borehole pipes completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.664198 36.110342 2290.6 14.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 1700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
7920 | Water and Sewerage Management | Mugaa Water Tank and piping | To implement mugaa water tank and piping for access to clean water and environmental sustainability | Mugaa Water Tank and piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.558886, 36.07641 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1998812 | 1998812 | 1998812 | Equitable | N/A | 1998812 | 0 | 1903550 | 95.2 | 1903550 | 1998812 | 95262 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
7921 | Water and Sewerage Management | Munanda police water tank - Construction of tank police water tank | To implement munanda police water tank - construction of tank police water tank for access to clean water and environmental sustainability | Munanda police water tank - Construction of tank police water tank completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.597591, 36.111653 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998341 | 99.8 | 998341 | 1000000 | 1659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
7922 | Water and Sewerage Management | Muririgua Tan - Construction of Water tank and Piping | To implement muririgua tan - construction of water tank and piping for access to clean water and environmental sustainability | Muririgua Tan - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1500000 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7923 | Water and Sewerage Management | Ndamu Tank - competion of piping works | To implement ndamu tank - competion of piping works for access to clean water and environmental sustainability | Ndamu Tank - competion of piping works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.55338 36.112845 1929.4 12.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 803938.3 | 803938.3 | Equitable | N/A | 803938.3 | 0 | 790909 | 98.4 | 790909 | 13029 | 13029.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Ues. Viable: Yes. Assessor remarks: Operational.
7924 | Water and Sewerage Management | Ndibai village - completion of water tank and water piping | To implement ndibai village - completion of water tank and water piping for access to clean water and environmental sustainability | Ndibai village - completion of water tank and water piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.553445 36.112768 2020.2 15 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1595000 | 1595000 | Equitable | N/A | 1595000 | 0 | 1588887 | 99.6 | 1588887 | 6113 | 6113 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7925 | Water And Sewerage Management | Settlement Borehole - installation of solar panel and purchase of submersible water pump | To implement settlement borehole - installation of solar panel and purchase of submersible water pump for access to clean water and environmental sustainability | Settlement Borehole - installation of solar panel and purchase of submersible water pump completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.529775, 36.090549 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3398520 | 100 | 3398520 | 1480 | 1480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Function.
7926 | Water and Sewerage Management | Sinking a borehole and pump of installation at Gilgil sub county Hospital | To implement sinking a borehole and pump of installation at gilgil sub county hospital for access to clean water and environmental sustainability | Sinking a borehole and pump of installation at Gilgil sub county Hospital completed | 3110502 | Water Supplies and Sewerage | GILGIL | GILGIL | -0.503559, 36.321536 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996302 | 99.8 | 1996302 | 3228677 | 3698 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: KASCOM ENTERPRISE. Assessor remarks: Functional but required piping to other areas within the hospital and the borehole was drilled by a donor the county did equipping..
7927 | Water and Sewerage Management | Construction of Kikopey water tank | To construct Kikopey water tank | Kikopey water tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.335397 36.14884 0 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1083163 | 1083163 | 1083163 | Equitable | N/A | 1083163 | 0 | 981857 | 90.6 | 981857 | 1083163 | 101306 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: Fairly done.
7928 | Water and Sewerage Management | Completion of Mirera borehole | To complete Mirera borehole | Mirera borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.78226, 36.446978 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999431 | 99.9 | 999431 | 999431 | 569 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 999,431.
7929 | Water and Sewerage Management | Desilting Kameno Dam | To implement desilting kameno dam for access to clean water and environmental sustainability | Desilting Kameno Dam completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.804589, 36.475493 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998356 | 100 | 3998356 | 1644 | 1644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 4,000,000.
7930 | Water and Sewerage Management | Karai water project and piping | To implement karai water project and piping for access to clean water and environmental sustainability | Karai water project and piping completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.770277, 36.487133 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198920 | 99.9 | 1198920 | 0 | 1080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project costed 1,200,000.
7931 | Water And Sewerage Management | Mountain view water project drilling of borehole and installation of pump and piping | To implement mountain view water project drilling of borehole and installation of pump and piping for access to clean water and environmental sustainability | Mountain view water project drilling of borehole and installation of pump and piping completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.777377, 36.456881 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 873268 | 873268 | Equitable | N/A | 873268 | 0 | 2321284 | 265.8 | 2321284 | 873268 | -1448016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole is still in use, few repairs from then have been made.
7932 | Water and Sewerage Management | Mountain view Water project (piping, Water tanks, installation of solar pumps) | To implement mountain view water project (piping, water tanks, installation of solar pumps) for access to clean water and environmental sustainability | Mountain view Water project (piping, Water tanks, installation of solar pumps) completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.777464, 36.456934 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 2321284 | 15.5 | 2321284 | 118064 | 12678716 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is going on well , few challenges here and there.
7933 | Water and Sewerage Management | Drilling of borehole at Mirera focus water project water project | To provide access to clean water through borehole drilling at Mirera focus water project water project | Borehole drilled at Mirera focus water project water project | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.837765, 36.55962 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2950064 | 98.3 | 2950064 | 3000000 | 49936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project cost 3,000,000.
7934 | Water and Sewerage Management | Installation of water pumps and repair of existing wells at Mirera suswa | To install water pumps and repair of existing wells at Mirera suswa | Water pumps and repair of existing wells at Mirera suswa installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.782138, 36.447091 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997737 | 99.9 | 2997737 | 1821159 | 2263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 3,000,000.
7935 | Water and Sewerage Management | Bore hole drilling and equipping | To implement bore hole drilling and equipping for access to clean water and environmental sustainability | Bore hole drilling and equipping completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 1496859 | 29.9 | 1496859 | 1496859 | 3503141 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7936 | Water and Sewerage Management | Borehole Works | To implement borehole works for access to clean water and environmental sustainability | Borehole Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000001 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 146709 | 2.9 | 146709 | 163337 | 4853291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7937 | Water and Sewerage Management | Construction of small dams and water pans | To construct small dams and water pans | Small dams and water pans constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 1436265 | 23.9 | 1436265 | 3183456 | 4563735 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7938 | Water and Sewerage Management | Construction of water projects | To construct water projects | Water projects constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 100000000 | 11620812 | 30381095.4 | Equitable | N/A | 30381095.4 | 0 | 1936626 | 16.7 | 1936626 | 1936626 | 9684186 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7939 | Water and Sewerage Management | County Water Works | To implement county water works for access to clean water and environmental sustainability | County Water Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 7143492.61 | 5687803.61 | 5687803.61 | N/A | N/A | 5687803.61 | 0 | 941663 | 16.6 | 941663 | 1696992 | 4746140.61 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7940 | Water and Sewerage Management | Grogon Water Works | To implement grogon water works for access to clean water and environmental sustainability | Grogon Water Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1253078.2 | 1253078.2 | 1253078.2 | N/A | N/A | 1253078.2 | 0 | 1253078 | 100 | 1253078 | 1253078 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7941 | Water and Sewerage Management | Laying of water pipes in Kiamunyi / ngata bridge | To implement laying of water pipes in kiamunyi / ngata bridge for access to clean water and environmental sustainability | Laying of water pipes in Kiamunyi / ngata bridge completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 19985041 | 99.9 | 19985041 | 14959 | 14959 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7942 | Water and Sewerage Management | Laying of water pipes in Maiella Ward | To implement laying of water pipes in maiella ward for access to clean water and environmental sustainability | Laying of water pipes in Maiella Ward completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 25000000 | 9000000 | 9000000 | N/A | N/A | 9000000 | 0 | 6471683 | 71.9 | 6471683 | 2528317 | 2528317 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7943 | Water and Sewerage Management | Litawa water project | To implement litawa water project for access to clean water and environmental sustainability | Litawa water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 8200000 | 5354143 | 5354143 | N/A | N/A | 5354143 | 0 | 4855031 | 90.7 | 4855031 | 499112 | 499112 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7944 | Water and Sewerage Management | Mawalebo Water Project | To implement mawalebo water project for access to clean water and environmental sustainability | Mawalebo Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 1116806 | 22.3 | 1116806 | 916219 | 3883194 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7945 | Water and Sewerage Management | Morop Dam desilting | To implement morop dam desilting for access to clean water and environmental sustainability | Morop Dam desilting completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7946 | Water and Sewerage Management | Naivawass Works | To implement naivawass works for access to clean water and environmental sustainability | Naivawass Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 1750000 | 1750000 | N/A | N/A | 1750000 | 0 | 1750000 | 100 | 1750000 | 1750000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7947 | Water and Sewerage Management | Naruwasco Works | To implement naruwasco works for access to clean water and environmental sustainability | Naruwasco Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 1750000 | 70 | 1750000 | 2500000 | 750000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7948 | Water and Sewerage Management | Nyondia water project | To implement nyondia water project for access to clean water and environmental sustainability | Nyondia water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 5161292 | 4675825.95 | 4675825.95 | N/A | N/A | 4675825.95 | 0 | 485466 | 10.4 | 485466 | 4675826 | 4190359.95 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7949 | Water and Sewerage Management | Other Developments | To implement other developments for access to clean water and environmental sustainability | Other Developments completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3135512 | 3135512 | 3135512 | N/A | N/A | 3135512 | 0 | 3115644 | 99.4 | 3115644 | 3728738 | 19868 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7950 | Provision Of Water And Sewerage Services (Mawalebo Water Project) | Provision Of Water And Sewerage Services (Mawalebo Water Project) | To implement provision of water and sewerage services (mawalebo water project) for access to clean water and environmental sustainability | Provision Of Water And Sewerage Services (Mawalebo Water Project) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 4160283.4 | 4160283.4 | 4160283.4 | N/A | N/A | 4160283.4 | 0 | 0 | 0 | 0 | 4160283 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
7951 | purchase of water tanks | purchase of water tanks | To procure water tanks | Water tanks procured | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 3021214.55 | 3021214.55 | N/A | N/A | 3021214.55 | 0 | 2994169 | 99.1 | 2994169 | 27046 | 27045.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7952 | Water and Sewerage Management | Rehabilitation Of Naruwassco Water Works | To rehabilitate Naruwassco Water Works to restore functionality | Naruwassco Water Works rehabilitated | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 945567.85 | 945567.85 | 945567.85 | N/A | N/A | 945567.85 | 0 | 2994378 | 316.7 | 2994378 | 945568 | -2048810.15 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
7953 | Water and Sewerage Management | Rehabilitation of water supplies (existing system) | To rehabilitate water supplies (existing system) to restore functionality | Water supplies (existing system) rehabilitated | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.695026, 36.480933 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/22 | 6000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 2994378 | 99.8 | 2994378 | 5622 | 5622 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
7954 | Water and Sewerage Management | Sanitation Projects | To implement sanitation projects for access to clean water and environmental sustainability | Sanitation Projects completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 1936626 | 19.4 | 1936626 | 10000000 | 8063374 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
7955 | Water and Sewerage Management | solarization of water boreholes | To implement solarization of water boreholes for access to clean water and environmental sustainability | solarization of water boreholes completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7956 | Water and Sewerage Management | Water Works (Proposed Rerouting From Ngosur Intake And Mariru Storage Tank) | To implement water works (proposed rerouting from ngosur intake and mariru storage tank) for access to clean water and environmental sustainability | Water Works (Proposed Rerouting From Ngosur Intake And Mariru Storage Tank) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | 2015/16 | 3794728.05 | 689594 | 689594 | N/A | N/A | 689594 | 0 | 689594 | 100 | 689594 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7957 | Water and Sewerage Management | Completion of Mirera borehole | To complete Mirera borehole | Mirera borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.78226, 36.446978 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999431 | 999431 | Equitable | N/A | 999431 | 0 | 999431 | 100 | 999431 | 999431 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 999,431.
7958 | Water and Sewerage Management | Desilting Kameno Dam | To implement desilting kameno dam for access to clean water and environmental sustainability | Desilting Kameno Dam completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.804589, 36.475493 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998356 | 100 | 3998356 | 1644 | 1644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 4,000,000.
7959 | Water And Sewerage Management | Mountain view water project drilling of borehole and installation of pump and piping | To implement mountain view water project drilling of borehole and installation of pump and piping for access to clean water and environmental sustainability | Mountain view water project drilling of borehole and installation of pump and piping completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.777377, 36.456881 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 873268 | 873268 | Equitable | N/A | 873268 | 0 | 2321284 | 265.8 | 2321284 | 873268 | -1448016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole is still in use, few repairs from then have been made.
7960 | Water and Sewerage Management | Mountain view Water project (piping, Water tanks, installation of solar pumps) | To implement mountain view water project (piping, water tanks, installation of solar pumps) for access to clean water and environmental sustainability | Mountain view Water project (piping, Water tanks, installation of solar pumps) completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.777464, 36.456934 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 2321284 | 15.5 | 2321284 | 118064 | 12678716 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is going on well , few challenges here and there.
7961 | Water and Sewerage Management | Drilling of borehole at Mirera focus water project water project | To provide access to clean water through borehole drilling at Mirera focus water project water project | Borehole drilled at Mirera focus water project water project | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.837765, 36.55962 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2950064 | 98.3 | 2950064 | 3000000 | 49936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project cost 3,000,000.
7962 | Water and Sewerage Management | Construction of 2 tanks and piping at Kangata and Mama Mbushe | To construct 2 tanks and piping at Kangata and Mama Mbushe | 2 tanks and piping at Kangata and Mama Mbushe constructed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.196066, 36.197552 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999983 | 100 | 2999983 | 17 | 17 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
7963 | Water and Sewerage Management | Construction of water tank of 100m3 diameter and piping of water at Thayu | To construct water tank of 100m3 diameter and piping of water at Thayu | Water tank of 100m3 diameter and piping of water at Thayu constructed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.188492, 36.170466 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 28 August 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1494013 | 99.6 | 1494013 | 1000000 | 5987 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Ms ridgerock enterprise. Assessor remarks: Initially the piping was to go up to thayu sublocation,the tank intake pipe is small it doesn't sustain their consumption.
7964 | Water and Sewerage Management | Expansion and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende | To expand and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende to increase capacity | And distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende expanded | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.230755, 36.163102 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 10880000 | 8880000 | 8880000 | Equitable | N/A | 8880000 | 0 | 6661068 | 75 | 6661068 | 141927 | 2218932 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
7965 | Water and Sewerage Management | Piping at Kabatini kwa Pastor to Moi Ndeffo Heroes | To provide water distribution infrastructure at Kabatini kwa Pastor to Moi Ndeffo Heroes | Water piping at Kabatini kwa Pastor to Moi Ndeffo Heroes completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.216169 36.164536 2031.300048828125 72.9000015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991256 | 99.6 | 1991256 | 8744 | 8744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No it's not done. Viable: No. Contractor: Bitro construction. Assessor remarks: The fund were reallocated to piping at ngosur dam.
7966 | Water and Sewerage Management | Piping at Kwa Muchina | To provide water distribution infrastructure at Kwa Muchina | Water piping at Kwa Muchina completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.214959 36.16585 2031.300048828125 39.106998443603516 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1256428 | 1256428 | 1256428 | Equitable | N/A | 1256428 | 0 | 1176286 | 93.6 | 1176286 | 1256428 | 80142 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Currently the borehole has a court case however nawasco is not able to do management it's done by residents.
7967 | Water and Sewerage Management | Piping from Bahati Boys to JC centre | To provide water distribution infrastructure at from Bahati Boys to JC centre | Water piping at from Bahati Boys to JC centre completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998359 | 99.9 | 1998359 | 1641 | 1641 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
7968 | Water and Sewerage Management | piping of water from Thayu tank | To provide water distribution infrastructure at water from Thayu tank | Water piping at water from Thayu tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996394 | 99.8 | 1996394 | 1996394 | 3606 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
7969 | Water and Sewerage Management | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward | To implement kabazi ward greening and beautitification - tree planting and beautification of kabazi ward for access to clean water and environmental sustainability | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 485500 | 48.5 | 485500 | 501021 | 514500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
7970 | Water and Sewerage Management | Kabazi Ward water works - design and piping of Jumuia water project, construction of water tank and piping of Kabazi Rugongo water projects, water tanks at mutukanio A and Ime | To implement kabazi ward water works - design and piping of jumuia water project, construction of water tank and piping of kabazi rugongo water projects, water tanks at mutukanio a and ime for access to clean water and environmental sustainability | Kabazi Ward water works - design and piping of Jumuia water project, construction of water tank and piping of Kabazi Rugongo water projects, water tanks at mutukanio A and Ime completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.09011 36.16711 0 2117 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 9000000 | 2006739 | 2006739 | Equitable | N/A | 2006739 | 0 | 2006739 | 100 | 2006739 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated.
7971 | Water and Sewerage Management | Kabazi water works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 14800000 | 15400000 | 15400000 | Equitable | N/A | 15400000 | 0 | 2547005 | 16.5 | 2547005 | 1165035 | 12852995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
7972 | Water and Sewerage Management | Renovation of Kingochoch water tank | To rehabilitate Kingochoch water tank to restore functionality | Kingochoch water tank rehabilitated | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.158008 36.079218 1887.2 9 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 499210.64 | 499210.64 | 499210.64 | Equitable | N/A | 499210.64 | 0 | 2718933 | 544.6 | 2718933 | 499211 | -2219722.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
7973 | Water and Sewerage Management | construction of Kiawairi water project (intake. Storage tank and piping) | To construct Kiawairi water project (intake. Storage tank and piping) | Kiawairi water project (intake. Storage tank and piping) constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.09011 36.16711 0 2117 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997398 | 99.9 | 1997398 | 2000000 | 2602 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated.
7974 | Water and Sewerage Management | Kabazi water works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 6300000 | 6300000 | Equitable | N/A | 6300000 | 0 | 2547005 | 40.4 | 2547005 | 1165035 | 3752995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
7975 | Water and Sewerage Management | Completion of Kamara water project | To complete Kamara water project | Kamara water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149131, 35.715047 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999697 | 100 | 1999697 | 1376603 | 303 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
7976 | Water and Sewerage Management | Completion of Mlima water project | To complete Mlima water project | Mlima water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149131, 35.715047 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 1376602.6 | 1376602.6 | 1376602.6 | Equitable | N/A | 1376602.6 | 0 | 1999697 | 145.3 | 1999697 | 1376603 | -623094.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
7977 | Water and Sewerage Management | Haraka / kipseret water project - drilling and solar equiping kipseret water project | To implement haraka / kipseret water project - drilling and solar equiping kipseret water project for access to clean water and environmental sustainability | Haraka / kipseret water project - drilling and solar equiping kipseret water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.16308, 35.684305 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2399771 | 120 | 2399771 | 2000000 | -399771 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
7978 | Water and Sewerage Management | Kamara location waterworks | To implement kamara location waterworks for access to clean water and environmental sustainability | Kamara location waterworks completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.08778 35.67402 2487.6 4.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1993257 | 99.7 | 1993257 | 6743 | 6743 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: VESTA ENTERPRISES LTD. Assessor remarks: Project constructed in Kamara secondary instead of Kamara primary. It's being used as a classroom for secondary.
7979 | Water and Sewerage Management | Kamara / Tarakwet water project - piping and construction of water tank | To implement kamara / tarakwet water project - piping and construction of water tank for access to clean water and environmental sustainability | Kamara / Tarakwet water project - piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.21323 35.661657 2695.9 4.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3732679 | 93.3 | 3732679 | 1000000 | 267321 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
7980 | Water and Sewerage Management | Mau Summit Location water works | To implement mau summit location water works for access to clean water and environmental sustainability | Mau Summit Location water works completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995084 | 99.8 | 1995084 | 4916 | 4916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
7981 | Water and Sewerage Management | mlima water project - piping of mlima water project | To implement mlima water project - piping of mlima water project for access to clean water and environmental sustainability | mlima water project - piping of mlima water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149078, 35.715007 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 2500000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399771 | 100 | 2399771 | 1376603 | 229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
7982 | Water and Sewerage Management | Piping and installation of a tank at Mau | To provide water distribution infrastructure at and installation of a tank at Mau | Water piping at and installation of a tank at Mau completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.160328 35.694146 2529.500244140625 64.0999984741211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999077 | 100 | 2999077 | 429568 | 923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
7983 | Water and Sewerage Management | Protection and piping of Koige spring | To implement protection and piping of koige spring for access to clean water and environmental sustainability | Protection and piping of Koige spring completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149078, 35.715007 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498201 | 99.9 | 1498201 | 2999995 | 1799 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
7984 | Water and Sewerage Management | Protection and piping of Sarambei spring | To implement protection and piping of sarambei spring for access to clean water and environmental sustainability | Protection and piping of Sarambei spring completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.097643, 35.68589 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 31/06/2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999995 | 100 | 2999995 | 2999995 | 5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
7985 | Water and Sewerage Management | Installation of solar panel at Kapnandi borehole | To install solar panel at Kapnandi borehole | Solar panel at Kapnandi borehole installed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2917562 | 97.3 | 2917562 | 2917562 | 82438 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
7986 | Water and Sewerage Management | Purchase of land and drilling of new Ingobor borehole and equipping | To acquire land for and drilling of new Ingobor borehole and equipping | Land for and drilling of new Ingobor borehole and equipping acquired | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 5000000 | 2437096.6 | 2437096.6 | Equitable | N/A | 2437096.6 | 0 | 2431841 | 99.8 | 2431841 | 5256 | 5255.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operational.
7987 | Water and Sewerage Management | Water works at Ingobor water project | To implement water works at ingobor water project for access to clean water and environmental sustainability | Water works at Ingobor water project completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.324324, 36.036613 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1791264 | 99.5 | 1791264 | 8736 | 8736 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Pipe laying complete and in use.
7988 | Water and Sewerage Management | Drilling of borehole and piping at Tulwet | To provide access to clean water through borehole drilling at and piping at Tulwet | Borehole drilled at and piping at Tulwet | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.324324, 36.036613 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 1998494 | 57.1 | 1998494 | 1501506 | 1501506 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Collapsed during drilling.
7989 | Water and Sewerage Management | fencing of Tulwet borehole land | To secure Tulwet borehole land through fencing | Tulwet borehole land fenced and secured | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 2924609 | 417.8 | 2924609 | 700000 | -2224609 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Security enhanced. Assessor remarks: Stone fencing done.
7990 | Water and Sewerage Management | Installation of pipes and water tank at Tachasis (Kapkures borehole) | To install pipes and water tank at Tachasis (Kapkures borehole) | Pipes and water tank at Tachasis (Kapkures borehole) installed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1898510 | 94.9 | 1898510 | 2000000 | 101490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
7991 | Water and Sewerage Management | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks | To implement purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across kaptembwo ward, painting and branding of the kiosks for access to clean water and environmental sustainability | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPTEMBWO | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 601180 | 12 | 601180 | 2398820 | 4398820 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
7992 | Water and Sewerage Management | Construction of 4 water kiosks across Kaptembwo Ward | To construct 4 water kiosks across Kaptembwo Ward | 4 water kiosks across Kaptembwo Ward constructed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPTEMBWO | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
7993 | Water and Sewerage Management | Drilling of Borehole at Baraka/Bararget | To provide access to clean water through borehole drilling at Baraka/Bararget | Borehole drilled at Baraka/Bararget | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.417612, 35.723675 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2720156 | 90.7 | 2720156 | 279844 | 279844 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Initially the project was to be done at bararget but later changed to baseline.
7994 | Water and Sewerage Management | Keringet Water works | To implement keringet water works for access to clean water and environmental sustainability | Keringet Water works completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.417722, 35.723717 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
7995 | Water and Sewerage Management | Piping Water at Keringet from kapkores | To provide water distribution infrastructure at Water at Keringet from kapkores | Water piping at Water at Keringet from kapkores completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.515075 35.718312 2624.1 4.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997191 | 99.9 | 1997191 | 2809 | 2809 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
7996 | Water and Sewerage Management | Piping Water at Tulwet | To provide water distribution infrastructure at Water at Tulwet | Water piping at Water at Tulwet completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499188 | 99.9 | 1499188 | 813 | 812 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
7997 | Water and Sewerage Management | Plumbing and piping Water at Silibwet | To implement plumbing and piping water at silibwet for access to clean water and environmental sustainability | Plumbing and piping Water at Silibwet completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995467 | 99.5 | 995467 | 4534 | 4533 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
7998 | Water and Sewerage Management | purchase and installation of water tanks and piping of Saptet water project | To procure and install water tanks and piping of Saptet water project | Water tanks and piping of Saptet water project procured and installed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.501323 35.714485 2647.8 6.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998967 | 99.9 | 1998967 | 1033 | 1033 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pu. P failure.
7999 | Water and Sewerage Management | purchase of pump,Storage tank and piping Water at Soitaran | To procure pump,Storage tank and piping Water at Soitaran | Pump,Storage tank and piping Water at Soitaran procured | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999867 | 100 | 2999867 | 2999867 | 133 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8000 | Water and Sewerage Management | purchase of pump,tank and piping of Water at Tendwet | To procure pump,tank and piping of Water at Tendwet | Pump,tank and piping of Water at Tendwet procured | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 3000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2320356 | 92.8 | 2320356 | 2500000 | 179644 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8001 | Water and Sewerage Management | Purchase of water pump and piping of water at kapseger | To procure water pump and piping of water at kapseger | Water pump and piping of water at kapseger procured | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1793334 | 99.6 | 1793334 | 1793334 | 6666 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8002 | Water and Sewerage Management | Water piping at Siwot | To implement water piping at siwot for access to clean water and environmental sustainability | Water piping at Siwot completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.41027, 35.681303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997658 | 99.9 | 1997658 | 1 | 2342 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2020. Assessor remarks: Working.
8003 | Water and Sewerage Management | water works - chelangat maritim water project | To implement water works - chelangat maritim water project for access to clean water and environmental sustainability | water works - chelangat maritim water project completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.506215 35.697313 0 34.400001525878906 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1838120 | 183.8 | 1838120 | 1000000 | -838120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8004 | Water and Sewerage Management | Construction of water tank at Chebara | To construct water tank at Chebara | Water tank at Chebara constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.471803, 35.68375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799008 | 99.9 | 799008 | 992 | 992 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8005 | Water and Sewerage Management | Drilling of borehole at Silibwet | To provide access to clean water through borehole drilling at Silibwet | Borehole drilled at Silibwet | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.515322, 35.718285 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 627823 | 20.9 | 627823 | 627823 | 2372177 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pump failure.
8006 | Water and Sewerage Management | Extension of piping / Pump at Kapseger Borehole | To expand piping / Pump at Kapseger Borehole to increase capacity | Piping / Pump at Kapseger Borehole expanded | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.500082, 35.714228 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998665 | 99.9 | 1998665 | 500000 | 1335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8007 | Water and Sewerage Management | Gituamba Water works and piping | To implement gituamba water works and piping for access to clean water and environmental sustainability | Gituamba Water works and piping completed | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.24371, 36.130752 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797636 | 99.9 | 1797636 | 2364 | 2364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was piped to community.
8008 | Water and Sewerage Management | Kiamaina Sub-location Water works and piping | To implement kiamaina sub-location water works and piping for access to clean water and environmental sustainability | Kiamaina Sub-location Water works and piping completed | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.234697, 36.104025 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1989238 | 99.5 | 1989238 | 1989238 | 10762 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water on the pipeline.
8009 | Water and Sewerage Management | Menengai Sub-location Water works and piping | To implement menengai sub-location water works and piping for access to clean water and environmental sustainability | Menengai Sub-location Water works and piping completed | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.234697, 36.104025 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3797190 | 99.9 | 3797190 | 2810 | 2810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water on the pipeline.
8010 | Piping extension at Menengai Water Project and St. Peters Primary Water Project | Piping extension at Menengai Water Project and St. Peters Primary Water Project | To provide water distribution infrastructure at extension at Menengai Water Project and St. Peters Primary Water Project | Water piping at extension at Menengai Water Project and St. Peters Primary Water Project completed | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.241438 36.138958 0 45.599998474121094 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000112 | 2000112 | 2000112 | Equitable | N/A | 2000112 | 0 | 1999596 | 100 | 1999596 | 516 | 516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Not operating because of lack of water pump.
8011 | Water and Sewerage Management | Purchase of solar pumps, piping, equipment for water projects at Kiamaina ward | To procure solar pumps, piping, equipment for water projects at Kiamaina ward | Solar pumps, piping, equipment for water projects at Kiamaina ward procured | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.234598 36.103832 1939 3.4000000953674316 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9981591 | 99.8 | 9981591 | 0 | 18409 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete but no water on site.
8012 | Water and Sewerage Management | Construction of a Water tank at Kihingo Centre and piping | To construct a Water tank at Kihingo Centre and piping | A Water tank at Kihingo Centre and piping constructed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.433912 35.972216 2278.2001953125 35.13199996948242 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2299949 | 100 | 2299949 | 134 | 51 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Market construction has stalled.
8013 | Water and Sewerage Management | Mugumoini Water Project-Equipping and piping in ndeffo | To implement mugumoini water project-equipping and piping in ndeffo for access to clean water and environmental sustainability | Mugumoini Water Project-Equipping and piping in ndeffo completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.479294, 35.97843 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499961 | 100 | 2499961 | 39 | 39 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance required.
8014 | Water and Sewerage Management | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project | To implement mutito a water project - drilling of borehole , construction of water tank and water kiosk and piping mutito a water project for access to clean water and environmental sustainability | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.433157, 35.959162 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3145607 | 52.4 | 3145607 | 2854393 | 2854393 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires fencing.
8015 | Water and Sewerage Management | Piping of water at kihingo and store mbili villages | To provide water distribution infrastructure at water at kihingo and store mbili villages | Water piping at water at kihingo and store mbili villages completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1383270 | 1383270 | 1383270 | Equitable | N/A | 1383270 | 0 | 1383136 | 100 | 1383136 | 134 | 134 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
8016 | Water and Sewerage Management | Subuku Water Project Drilling and Equipping borehole and water tank | To implement subuku water project drilling and equipping borehole and water tank for access to clean water and environmental sustainability | Subuku Water Project Drilling and Equipping borehole and water tank completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.42206 35.969528 2213.5 11.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 2701604 | 45 | 2701604 | 3075582 | 3298396 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
8017 | Water and Sewerage Management | Lusiru water project - water priping for Lusiru water project | To implement lusiru water project - water priping for lusiru water project for access to clean water and environmental sustainability | Lusiru water project - water priping for Lusiru water project completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.498868 35.997912 2387.8 4.099999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2986993 | 99.6 | 2986993 | 188846 | 13007 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8018 | Water and Sewerage Management | Water works at stoo mbili | To implement water works at stoo mbili for access to clean water and environmental sustainability | Water works at stoo mbili completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.456623 35.981843 2308.8999999999996 6.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 151400 | 2.5 | 151400 | 151401 | 5848600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: More piping and connection.
8019 | Water and Sewerage Management | Construction of Chebotoi water project | To construct Chebotoi water project | Chebotoi water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.56174, 35.630252 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995987 | 99.8 | 1995987 | 4013 | 4013 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
8020 | Water and Sewerage Management | Construction of Kiptagich water project | To construct Kiptagich water project | Kiptagich water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.56174, 35.630252 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999508 | 100 | 3999508 | 4000000 | 492 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
8021 | Water and Sewerage Management | Construction of weir , water Tank and piping at Cheptuech - Irongo water project | To construct weir , water Tank and piping at Cheptuech - Irongo water project | Weir , water Tank and piping at Cheptuech - Irongo water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998496 | 100 | 3998496 | 4000000 | 1504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8022 | Water and Sewerage Management | Gikamba water projects, piping and supply of water | To implement gikamba water projects, piping and supply of water for access to clean water and environmental sustainability | Gikamba water projects, piping and supply of water completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.658612, 35.604138 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1314709 | 87.6 | 1314709 | 185291 | 185291 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has stalled.
8023 | Water and Sewerage Management | Oromoit water project construction of generator house | To implement oromoit water project construction of generator house for access to clean water and environmental sustainability | Oromoit water project construction of generator house completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.590645 35.59291 2486.400146484375 50.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 90 | N/A | Land Dispute | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functions.
8024 | Water and Sewerage Management | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project | To implement simatwet water project - design and construction of water tank, perimeter fence and piping of simatwet water project for access to clean water and environmental sustainability | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8025 | Water and Sewerage Management | Construction of a water collection point at Kuresoi Centre | To construct a water collection point at Kuresoi Centre | A water collection point at Kuresoi Centre constructed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KIPTORORO | -0.300932, 35.531763 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 2950807 | 1475.4 | 2950807 | 200000 | -2750807 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Due to stolen solar panel it's making it non functional.
8026 | Water and Sewerage Management | Drilling of borehole and piping at Kio | To provide access to clean water through borehole drilling at and piping at Kio | Borehole drilled at and piping at Kio | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KIPTORORO | -0.294178, 35.491267 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 2545376 | 46.3 | 2545376 | 2668729 | 2954624 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
8027 | Water and Sewerage Management | Drilling of borehole and piping at Kuresoi centre | To provide access to clean water through borehole drilling at and piping at Kuresoi centre | Borehole drilled at and piping at Kuresoi centre | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KIPTORORO | -0.294178, 35.491267 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4881121 | 4881121 | 4881121 | Equitable | N/A | 4881121 | 0 | 2545376 | 52.1 | 2545376 | 4881121 | 2335745 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
8028 | Water and Sewerage Management | Drilling of borehole, construction of water tank and piping Kongoi centre | To implement drilling of borehole, construction of water tank and piping kongoi centre for access to clean water and environmental sustainability | Drilling of borehole, construction of water tank and piping Kongoi centre completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KIPTORORO | -0.30261, 35.529464 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2500000 | 55.6 | 2500000 | 2500000 | 2000000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Completed but solar was stolen. Viable: Partially, its serving the health center and not the public. Assessor remarks: The borehole is functional but two solar s belongs to dakuki contractor.
8029 | Water and Sewerage Management | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks | To implement nakuru press estate - rehabilitation of kivumbini estate sewerage networks for access to clean water and environmental sustainability | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | KIVUMBINI | -0.300433, 36.082496 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
8030 | Water and Sewerage Management | Rehabilitation of sewer line at Shauri Yako | To rehabilitate sewer line at Shauri Yako to restore functionality | Sewer line at Shauri Yako rehabilitated | 3110502 | Water Supplies and Sewerage | NAKURU EAST | KIVUMBINI | -0.298813, 36.081315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3031776 | 75.8 | 3031776 | 4000000 | 968224 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sewerline.
8031 | Water and Sewerage Management | Construction of 2 tanks and piping at Kangata and Mama Mbushe | To construct 2 tanks and piping at Kangata and Mama Mbushe | 2 tanks and piping at Kangata and Mama Mbushe constructed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999983 | 100 | 2999983 | 17 | 17 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
8032 | Water and Sewerage Management | Expansion and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende | To expand and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende to increase capacity | And distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende expanded | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.230755, 36.163102 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 10880000 | 6802994.55 | 6802994.55 | Equitable | N/A | 6802994.55 | 0 | 6661068 | 97.9 | 6661068 | 141927 | 141926.55 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8033 | Water and Sewerage Management | Installation of Solar System at Kwa Amos Borehole | To install Solar System at Kwa Amos Borehole | Solar System at Kwa Amos Borehole installed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.231931, 36.147504 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1881520 | 94.1 | 1881520 | 118480 | 118480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
8034 | Water and Sewerage Management | Limuko borehole solar installation | To implement limuko borehole solar installation for access to clean water and environmental sustainability | Limuko borehole solar installation completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.245966 36.145761 1928.199951171875 9.814000129699707 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yed. Contractor: Gee-el construction works ltd. Assessor remarks: Operational but it only serves the school ( heroes technical, heroes girls and boys) it doesn't serve the community.
8035 | Water and Sewerage Management | Piping at Kabatini kwa Pastor to Moi Ndeffo Heroes | To provide water distribution infrastructure at Kabatini kwa Pastor to Moi Ndeffo Heroes | Water piping at Kabatini kwa Pastor to Moi Ndeffo Heroes completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.216169 36.164536 2031.300048828125 72.9000015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991256 | 99.6 | 1991256 | 8744 | 8744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No it's not done. Viable: No. Contractor: Bitro construction. Assessor remarks: The fund were reallocated to piping at ngosur dam.
8036 | Water and Sewerage Management | Piping from Bahati Boys to JC centre | To provide water distribution infrastructure at from Bahati Boys to JC centre | Water piping at from Bahati Boys to JC centre completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998359 | 99.9 | 1998359 | 1641 | 1641 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
8037 | Water and Sewerage Management | Piping of kwa muchina water project | To provide water distribution infrastructure at kwa muchina water project | Water piping at kwa muchina water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1176286 | 98 | 1176286 | 1200000 | 23714 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
8038 | Water and Sewerage Management | piping of water from Thayu tank | To provide water distribution infrastructure at water from Thayu tank | Water piping at water from Thayu tank completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1996394 | 1996394 | Equitable | N/A | 1996394 | 0 | 1996394 | 100 | 1996394 | 1996394 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
8039 | Water and Sewerage Management | Purchase and supply of 3000L water tank | To procure and supply 3000L water tank | 3000L water tank procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.214433 36.162776 2030.4000244140625 10.21500015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998796 | 99.9 | 1998796 | 1204 | 1204 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Willis samwa suppliers limited. Assessor remarks: Operational.
8040 | Water and Sewerage Management | Additional fund to Kabazi water works | To implement additional fund to kabazi water works for access to clean water and environmental sustainability | Additional fund to Kabazi water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 4416057 | 4416057 | 4416057 | Equitable | N/A | 4416057 | 0 | 640770 | 14.5 | 640770 | 3775288 | 3775287 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
8041 | Water and Sewerage Management | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward | To implement kabazi ward greening and beautitification - tree planting and beautification of kabazi ward for access to clean water and environmental sustainability | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 485500 | 32.4 | 485500 | 501021 | 1014500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8042 | Water and Sewerage Management | Kabazi water works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2019/20 | N/A | 14800000 | 15400000 | 15400000 | Equitable | N/A | 15400000 | 0 | 2547005 | 16.5 | 2547005 | 1165035 | 12852995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
8043 | Water and Sewerage Management | Renovation of Kingochoch water tank | To rehabilitate Kingochoch water tank to restore functionality | Kingochoch water tank rehabilitated | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.158008 36.079218 1887.2 9 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 499210.64 | 499210.64 | 499210.64 | Equitable | N/A | 499210.64 | 0 | 2718933 | 544.6 | 2718933 | 499211 | -2219722.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
8044 | Water and Sewerage Management | Kabazi water works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 584535 | 584535 | Equitable | N/A | 584535 | 0 | 2547005 | 435.7 | 2547005 | 1165035 | -1962470 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
8045 | Water and Sewerage Management | Completion of Mlima water project | To complete Mlima water project | Mlima water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149131, 35.715047 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 1376602.6 | 1376602.6 | 1376602.6 | Equitable | N/A | 1376602.6 | 0 | 1999697 | 145.3 | 1999697 | 1376603 | -623094.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
8046 | Water and Sewerage Management | Kamara location waterworks | To implement kamara location waterworks for access to clean water and environmental sustainability | Kamara location waterworks completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.08778 35.67402 2487.6 4.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1993257 | 99.7 | 1993257 | 6743 | 6743 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: VESTA ENTERPRISES LTD. Assessor remarks: Project constructed in Kamara secondary instead of Kamara primary. It's being used as a classroom for secondary.
8047 | Water and Sewerage Management | Kamara ward water works | To implement kamara ward water works for access to clean water and environmental sustainability | Kamara ward water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149157 35.715017 2708.8 2.700000047683716 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2033665 | 2033665 | 2033665 | Equitable | N/A | 2033665 | 0 | 1950540 | 95.9 | 1950540 | 1950540 | 83125 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Project done.
8048 | Water and Sewerage Management | Kiptenden mau water works | To implement kiptenden mau water works for access to clean water and environmental sustainability | Kiptenden mau water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149157 35.715017 2708.8 2.700000047683716 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1992240 | 99.6 | 1992240 | 1992240 | 7760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Project done.
8049 | Water and Sewerage Management | Mau Summit Location water works | To implement mau summit location water works for access to clean water and environmental sustainability | Mau Summit Location water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995084 | 99.8 | 1995084 | 4916 | 4916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
8050 | Water and Sewerage Management | Protection and piping of Sarambei spring | To implement protection and piping of sarambei spring for access to clean water and environmental sustainability | Protection and piping of Sarambei spring completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.097643, 35.68589 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 31/06/2025 | 3000000 | 2999994.9 | 2999994.9 | Equitable | N/A | 2999994.9 | 0 | 2999995 | 100 | 2999995 | 2999995 | -0.1 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
8051 | Water and Sewerage Management | Installation of solar panel at Kapnandi borehole | To install solar panel at Kapnandi borehole | Solar panel at Kapnandi borehole installed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2018/19 | 3000000 | 2917562 | 2917562 | Equitable | N/A | 2917562 | 0 | 2917562 | 100 | 2917562 | 2917562 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
8052 | Water and Sewerage Management | Water works at Ingobor water project | To implement water works at ingobor water project for access to clean water and environmental sustainability | Water works at Ingobor water project completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1791264 | 99.5 | 1791264 | 8736 | 8736 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Pipe laying complete and in use.
8053 | Water and Sewerage Management | Drilling of borehole and piping at Tulwet | To provide access to clean water through borehole drilling at and piping at Tulwet | Borehole drilled at and piping at Tulwet | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 1501505.6 | 1501505.6 | Equitable | N/A | 1501505.6 | 0 | 1998494 | 133.1 | 1998494 | 1501506 | -496988.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Collapsed during drilling.
8054 | Water and Sewerage Management | Installation of pipes and water tank at Tachasis (Kapkures borehole) | To install pipes and water tank at Tachasis (Kapkures borehole) | Pipes and water tank at Tachasis (Kapkures borehole) installed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1898510 | 94.9 | 1898510 | 2000000 | 101490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
8055 | Water and Sewerage Management | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks | To implement purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across kaptembwo ward, painting and branding of the kiosks for access to clean water and environmental sustainability | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 4398820 | 4398820 | Equitable | N/A | 4398820 | 0 | 601180 | 13.7 | 601180 | 2398820 | 3797640 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
8056 | Water and Sewerage Management | Additional fund for tendwet water project | To implement additional fund for tendwet water project for access to clean water and environmental sustainability | Additional fund for tendwet water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506215 35.697313 0 34.400001525878906 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8057 | Water and Sewerage Management | construction of water tank at saptet water project | To construct water tank at saptet water project | Water tank at saptet water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.482883 35.707903 2706.2 10.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1838120 | 91.9 | 1838120 | 2000000 | 161880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8058 | Water and Sewerage Management | Drilling of Borehole at Baraka/Bararget | To provide access to clean water through borehole drilling at Baraka/Bararget | Borehole drilled at Baraka/Bararget | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417612, 35.723675 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2720156 | 90.7 | 2720156 | 279844 | 279844 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Initially the project was to be done at bararget but later changed to baseline.
8059 | Water and Sewerage Management | Installation of water tank and piping at Tuiyobei | To install water tank and piping at Tuiyobei | Water tank and piping at Tuiyobei installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.437227, 35.703787 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1277612 | 425.9 | 1277612 | 293202 | -977612 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8060 | Water and Sewerage Management | Installation of water tank,fencing and piping at silibwet water project | To install water tank,fencing and piping at silibwet water project | Water tank,fencing and piping at silibwet water project installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471103 35.6416 2687.900146484375 5.099999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1277612 | 319.4 | 1277612 | 400000 | -877612 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8061 | Water and Sewerage Management | piping and installation of water kiosk (10,000l water tank at Kpakwen primary school | To provide water distribution infrastructure at and installation of water kiosk (10,000l water tank at Kpakwen primary school | Water piping at and installation of water kiosk (10,000l water tank at Kpakwen primary school completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463277, 35.709932 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | N/A | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
8062 | Water and Sewerage Management | Piping Water at Keringet from kapkores | To provide water distribution infrastructure at Water at Keringet from kapkores | Water piping at Water at Keringet from kapkores completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997191 | 99.9 | 1997191 | 2809 | 2809 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
8063 | Water and Sewerage Management | Piping Water at Tulwet | To provide water distribution infrastructure at Water at Tulwet | Water piping at Water at Tulwet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499188 | 99.9 | 1499188 | 813 | 812 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8064 | Water and Sewerage Management | piping water from silibwet to pombo | To provide water distribution infrastructure at water from silibwet to pombo | Water piping at water from silibwet to pombo completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.483387, 35.707437 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 950161 | 95 | 950161 | 1000000 | 49839 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8065 | Water and Sewerage Management | piping water from Soitaran to Lelaibei Primary school and installation of water kiosk (10,000 litres water tank | To provide water distribution infrastructure at water from Soitaran to Lelaibei Primary school and installation of water kiosk (10,000 litres water tank | Water piping at water from Soitaran to Lelaibei Primary school and installation of water kiosk (10,000 litres water tank completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463277, 35.709932 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | N/A | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1164175 | 97 | 1164175 | 1185427 | 35825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
8066 | Water and Sewerage Management | Plumbing and piping Water at Silibwet | To implement plumbing and piping water at silibwet for access to clean water and environmental sustainability | Plumbing and piping Water at Silibwet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995467 | 99.5 | 995467 | 4534 | 4533 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8067 | Water and Sewerage Management | purchase and installation of water tanks and piping of Saptet water project | To procure and install water tanks and piping of Saptet water project | Water tanks and piping of Saptet water project procured and installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.501323 35.714485 2647.8 6.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998967 | 99.9 | 1998967 | 1033 | 1033 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pu. P failure.
8068 | Water and Sewerage Management | Purchase of a skips (waste collection unit) | To procure a skips (waste collection unit) | A skips (waste collection unit) procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.426622, 35.692727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 700000 | 140 | 700000 | 500000 | -200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
8069 | Water and Sewerage Management | purchase of pump,Storage tank and piping Water at Soitaran | To procure pump,Storage tank and piping Water at Soitaran | Pump,Storage tank and piping Water at Soitaran procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 4000000 | 2999867.01 | 2999867.01 | Equitable | N/A | 2999867.01 | 0 | 2999867 | 100 | 2999867 | 2999867 | 0.01 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8070 | Water and Sewerage Management | purchase of pump,tank and piping of Water at Tendwet | To procure pump,tank and piping of Water at Tendwet | Pump,tank and piping of Water at Tendwet procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 3000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2320356 | 92.8 | 2320356 | 2500000 | 179644 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8071 | Water and Sewerage Management | Purchase of water pump and piping of water at kapseger | To procure water pump and piping of water at kapseger | Water pump and piping of water at kapseger procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 1793334.48 | 1793334.48 | Equitable | N/A | 1793334.48 | 0 | 1793334 | 100 | 1793334 | 1793334 | 0.48 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
8072 | Water and Sewerage Management | Renovation of water tank and piping at kapseger water project | To rehabilitate water tank and piping at kapseger water project to restore functionality | Water tank and piping at kapseger water project rehabilitated | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.501323 35.714485 2647.8 6.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pu. P failure.
8073 | Water and Sewerage Management | Water piping at Siwot | To implement water piping at siwot for access to clean water and environmental sustainability | Water piping at Siwot completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.41027, 35.681303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019 | 2000000 | 1997659 | 1997659 | Equitable | N/A | 1997659 | 0 | 1997658 | 100 | 1997658 | 1 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2020. Assessor remarks: Working.
8074 | Water and Sewerage Management | Water piping from bararget to kiptulwa primary school | To implement water piping from bararget to kiptulwa primary school for access to clean water and environmental sustainability | Water piping from bararget to kiptulwa primary school completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417828, 35.723693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1288830 | 99.1 | 1288830 | 1300000 | 11170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8075 | Water and Sewerage Management | Water piping from saptet to soimet | To implement water piping from saptet to soimet for access to clean water and environmental sustainability | Water piping from saptet to soimet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.483387, 35.707437 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8076 | Water and Sewerage Management | Water piping from tulwet to ndabibit primary school | To implement water piping from tulwet to ndabibit primary school for access to clean water and environmental sustainability | Water piping from tulwet to ndabibit primary school completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.447195, 35.704157 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8077 | Water and Sewerage Management | Construction of water tank at Chebara | To construct water tank at Chebara | Water tank at Chebara constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471803, 35.68375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799008 | 99.9 | 799008 | 992 | 992 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
8078 | Water and Sewerage Management | Drilling of borehole at Silibwet | To provide access to clean water through borehole drilling at Silibwet | Borehole drilled at Silibwet | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515322, 35.718285 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 627823.2 | 627823.2 | Equitable | N/A | 627823.2 | 0 | 627823 | 100 | 627823 | 627823 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pump failure.
8079 | Water and Sewerage Management | Gituamba Water works and piping | To implement gituamba water works and piping for access to clean water and environmental sustainability | Gituamba Water works and piping completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.24371, 36.130752 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797636 | 99.9 | 1797636 | 2364 | 2364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was piped to community.
8080 | Water and Sewerage Management | Kiamaina Sub-location Water works and piping | To implement kiamaina sub-location water works and piping for access to clean water and environmental sustainability | Kiamaina Sub-location Water works and piping completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.234697, 36.104025 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1989238 | 1989238 | Equitable | N/A | 1989238 | 0 | 1989238 | 100 | 1989238 | 1989238 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water on the pipeline.
8081 | Water and Sewerage Management | Kiamaina ward water works | To implement kiamaina ward water works for access to clean water and environmental sustainability | Kiamaina ward water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.241345 36.138941 0 52.400001525878906 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999000 | 100 | 1999000 | 2000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: No water on the pipeline.
8082 | Water and Sewerage Management | Menengai Sub-location Water works and piping | To implement menengai sub-location water works and piping for access to clean water and environmental sustainability | Menengai Sub-location Water works and piping completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.234697, 36.104025 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3797190 | 99.9 | 3797190 | 2810 | 2810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water on the pipeline.
8083 | Piping extension at Menengai Water Project and St. Peters Primary Water Project | Piping extension at Menengai Water Project and St. Peters Primary Water Project | To provide water distribution infrastructure at extension at Menengai Water Project and St. Peters Primary Water Project | Water piping at extension at Menengai Water Project and St. Peters Primary Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.241438 36.138958 0 45.599998474121094 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000112 | 2000112 | 2000112 | Equitable | N/A | 2000112 | 0 | 1999596 | 100 | 1999596 | 516 | 516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Not operating because of lack of water pump.
8084 | Water and Sewerage Management | Construction of a Water tank at Kihingo Centre and piping | To construct a Water tank at Kihingo Centre and piping | A Water tank at Kihingo Centre and piping constructed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.433912 35.972216 2278.2001953125 35.13199996948242 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2299949 | 100 | 2299949 | 134 | 51 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Market construction has stalled.
8085 | Water and Sewerage Management | Mugumoini Water Project-Equipping and piping in ndeffo | To implement mugumoini water project-equipping and piping in ndeffo for access to clean water and environmental sustainability | Mugumoini Water Project-Equipping and piping in ndeffo completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.479294, 35.97843 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499961 | 100 | 2499961 | 39 | 39 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance required.
8086 | Water and Sewerage Management | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project | To implement mutito a water project - drilling of borehole , construction of water tank and water kiosk and piping mutito a water project for access to clean water and environmental sustainability | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.433157, 35.959162 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3145607 | 52.4 | 3145607 | 2854393 | 2854393 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires fencing.
8087 | Water and Sewerage Management | Piping of water at kihingo and store mbili villages | To provide water distribution infrastructure at water at kihingo and store mbili villages | Water piping at water at kihingo and store mbili villages completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1383270 | 1383270 | 1383270 | Equitable | N/A | 1383270 | 0 | 1383136 | 100 | 1383136 | 134 | 134 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
8088 | Water and Sewerage Management | Subuku Water Project Drilling and Equipping borehole and water tank | To implement subuku water project drilling and equipping borehole and water tank for access to clean water and environmental sustainability | Subuku Water Project Drilling and Equipping borehole and water tank completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.42206 35.969528 2213.5 11.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 6000000 | 3075582 | 3075582 | Equitable | N/A | 3075582 | 0 | 2701604 | 87.8 | 2701604 | 3075582 | 373978 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
8089 | Water and Sewerage Management | Water works at Mutito water project | To implement water works at mutito water project for access to clean water and environmental sustainability | Water works at Mutito water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1472000 | 98.1 | 1472000 | 1500000 | 28000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
8090 | Water and Sewerage Management | Water works at subuku water project | To implement water works at subuku water project for access to clean water and environmental sustainability | Water works at subuku water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1886844 | 94.3 | 1886844 | 2000000 | 113156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
8091 | Water and Sewerage Management | Water works at stoo mbili | To implement water works at stoo mbili for access to clean water and environmental sustainability | Water works at stoo mbili completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.456623 35.981843 2308.8999999999996 6.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 3350496.75 | 3350496.75 | Equitable | N/A | 3350496.75 | 0 | 151400 | 4.5 | 151400 | 151401 | 3199096.75 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: More piping and connection.
8092 | Water and Sewerage Management | Construction of Chebotoi water project | To construct Chebotoi water project | Chebotoi water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.56174, 35.630252 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995987 | 99.8 | 1995987 | 4013 | 4013 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
8093 | Water and Sewerage Management | Construction of Kiptagich water project | To construct Kiptagich water project | Kiptagich water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.56174, 35.630252 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999508 | 100 | 3999508 | 4000000 | 492 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
8094 | Water and Sewerage Management | Construction of weir , water Tank and piping at Cheptuech - Irongo water project | To construct weir , water Tank and piping at Cheptuech - Irongo water project | Weir , water Tank and piping at Cheptuech - Irongo water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998496 | 100 | 3998496 | 4000000 | 1504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8095 | Water and Sewerage Management | Gikamba water projects, piping and supply of water | To implement gikamba water projects, piping and supply of water for access to clean water and environmental sustainability | Gikamba water projects, piping and supply of water completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.658612, 35.604138 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1314709 | 87.6 | 1314709 | 185291 | 185291 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has stalled.
8096 | Water and Sewerage Management | Oromoit water project construction of generator house | To implement oromoit water project construction of generator house for access to clean water and environmental sustainability | Oromoit water project construction of generator house completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.590645 35.59291 2486.400146484375 50.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 90 | N/A | Land Dispute | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functions.
8097 | Water and Sewerage Management | Piping and water tank at ainamoi water project | To provide water distribution infrastructure at and water tank at ainamoi water project | Water piping at and water tank at ainamoi water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797444 | 99.9 | 1797444 | 1800000 | 2556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8098 | Water and Sewerage Management | Piping and water tank at kiptagich water project | To provide water distribution infrastructure at and water tank at kiptagich water project | Water piping at and water tank at kiptagich water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 608700 | 76.1 | 608700 | 800000 | 191300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8099 | Water and Sewerage Management | Piping and water tank at oromoit water project | To provide water distribution infrastructure at and water tank at oromoit water project | Water piping at and water tank at oromoit water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1797444 | 449.4 | 1797444 | 400000 | -1397444 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8100 | Water and Sewerage Management | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project | To implement simatwet water project - design and construction of water tank, perimeter fence and piping of simatwet water project for access to clean water and environmental sustainability | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
8101 | Water and Sewerage Management | Water works at chapsikwet water project | To implement water works at chapsikwet water project for access to clean water and environmental sustainability | Water works at chapsikwet water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1797444 | 89.9 | 1797444 | 2000000 | 202556 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
8102 | Water and Sewerage Management | Construction of a water collection point at Kuresoi Centre | To construct a water collection point at Kuresoi Centre | A water collection point at Kuresoi Centre constructed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.300932, 35.531763 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 2950807 | 1475.4 | 2950807 | 200000 | -2750807 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Due to stolen solar panel it's making it non functional.
8103 | Water and Sewerage Management | Drilling of borehole and piping at Kio | To provide access to clean water through borehole drilling at and piping at Kio | Borehole drilled at and piping at Kio | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.294178, 35.491267 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 2545376 | 46.3 | 2545376 | 2668729 | 2954624 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
8104 | Water and Sewerage Management | Drilling of borehole, construction of water tank and piping Kongoi centre | To implement drilling of borehole, construction of water tank and piping kongoi centre for access to clean water and environmental sustainability | Drilling of borehole, construction of water tank and piping Kongoi centre completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.30261, 35.529464 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2500000 | 55.6 | 2500000 | 2500000 | 2000000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Completed but solar was stolen. Viable: Partially, its serving the health center and not the public. Assessor remarks: The borehole is functional but two solar s belongs to dakuki contractor.
8105 | Water and Sewerage Management | Kio water works | To implement kio water works for access to clean water and environmental sustainability | Kio water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.295213, 35.490188 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 0 | 0 | 0 | 2700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
8106 | Water and Sewerage Management | piping and repairing of water tank at Kuresoi centre | To provide water distribution infrastructure at and repairing of water tank at Kuresoi centre | Water piping at and repairing of water tank at Kuresoi centre completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.30261, 35.529464 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3881121 | 3881121 | 3881121 | Equitable | N/A | 3881121 | 0 | 2950807 | 76 | 2950807 | 3688509 | 930314 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Completed but solar was stolen. Viable: Partially, its serving the health center and not the public. Assessor remarks: The borehole is functional but two solar s belongs to dakuki contractor.
8107 | Water and Sewerage Management | Rehabilitation of sewer line at Shauri Yako | To rehabilitate sewer line at Shauri Yako to restore functionality | Sewer line at Shauri Yako rehabilitated | 3110502 | Water Supplies and Sewerage | Nakuru East | Kivumbini | -0.298813, 36.081315 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3031776 | 75.8 | 3031776 | 4000000 | 968224 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sewerline.
8108 | Water and Sewerage Management | Drilling and equipping boreholes at Milimani and Unity primary school | To implement drilling and equipping boreholes at milimani and unity primary school for access to clean water and environmental sustainability | Drilling and equipping boreholes at Milimani and Unity primary school completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | LAKEVIEW | -0.720739, 36.43967 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 10000000 | 10360765 | 10360765 | Equitable | N/A | 10360765 | 0 | 796146 | 7.7 | 796146 | 873778 | 9564619 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: High flouride levels, water not safe for drinking.
8109 | Water and Sewerage Management | Drilling of borehole murunyu water project | To provide access to clean water through borehole drilling at murunyu water project | Borehole drilled at murunyu water project | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.247859, 36.151991 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 844287 | 21.1 | 844287 | 894392 | 3155713 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
8110 | Water and Sewerage Management | Drilling of Borehole, pump and piping Lamnyondeki | To implement drilling of borehole, pump and piping lamnyondeki for access to clean water and environmental sustainability | Drilling of Borehole, pump and piping Lamnyondeki completed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.265977, 36.16637 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1579317 | 39.5 | 1579317 | 1615034 | 2420683 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , very viable. Contractor: Njegwa investment limited. Assessor remarks: Functional.
8111 | Water and Sewerage Management | Installation of pump and purchase of 10000 litres of water tank at baraka | To install pump and purchase of 10000 litres of water tank at baraka | Pump and purchase of 10000 litres of water tank at baraka installed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.282202, 36.155693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3993388 | 99.8 | 3993388 | 340755 | 6612 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8112 | Water and Sewerage Management | Installation of pump and purchase of 10000 litres water tank at modern | To install pump and purchase of 10000 litres water tank at modern | Pump and purchase of 10000 litres water tank at modern installed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.282202, 36.155693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1529199 | 38.2 | 1529199 | 340755 | 2470801 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8113 | Water and Sewerage Management | Lanet Umoja Water Works | To implement lanet umoja water works for access to clean water and environmental sustainability | Lanet Umoja Water Works completed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.235204, 36.165713 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/2017 | 1125737.92 | 1125737.92 | 1125737.92 | Equitable | N/A | 1125737.92 | 0 | 1113059 | 98.9 | 1113059 | 1500001 | 12678.92 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8114 | Water and Sewerage Management | Repair of 2 water tanks in Kiamunyeki | To rehabilitate 2 water tanks in Kiamunyeki to restore functionality | 2 water tanks in Kiamunyeki rehabilitated | 3110502 | Water Supplies and Sewerage | BAHATI | LANET/UMOJA | -0.283645, 36.150508 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995900 | 99.8 | 1995900 | 4100 | 4100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but the repaired tank is not functional due to leakages.
8115 | Water and Sewerage Management | Nganoini Naishi game water project - piping of water from Kihingo - mutiume to Nganoini naishi game | To implement nganoini naishi game water project - piping of water from kihingo - mutiume to nganoini naishi game for access to clean water and environmental sustainability | Nganoini Naishi game water project - piping of water from Kihingo - mutiume to Nganoini naishi game completed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.423142, 36.038682 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3374605 | 99.3 | 3374605 | 0 | 25395 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8116 | Water and Sewerage Management | Installation of pipes at Bagaria | To install pipes at Bagaria | Pipes at Bagaria installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.479368, 36.052937 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498845 | 100 | 2498845 | 54100 | 1155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need electricity connection and the project taken over NARUWASCO.
8117 | Water and Sewerage Management | Installation of pipes at Karogoe mugumo | To install pipes at Karogoe mugumo | Pipes at Karogoe mugumo installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.46423, 36.044957 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2445900 | 97.8 | 2445900 | 54100 | 54100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8118 | Water and Sewerage Management | Installation of pipes at lower zone block 3 | To install pipes at lower zone block 3 | Pipes at lower zone block 3 installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.46423, 36.044957 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499279 | 100 | 2499279 | 54100 | 721 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8119 | Water and Sewerage Management | Installation of water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk. | To install water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk | Water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497633 | 99.8 | 1497633 | 1500000 | 2367 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8120 | Water and Sewerage Management | Installation of water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3. | To install water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3 | Water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3 installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499137 | 99.9 | 1499137 | 863 | 863 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8121 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1629476 | 1629476 | 1629476 | Equitable | N/A | 1629476 | 0 | 1628847 | 100 | 1628847 | 629 | 629 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8122 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8123 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499990 | 100 | 1499990 | 10 | 10 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8124 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499834 | 100 | 1499834 | 166 | 166 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8125 | Water and Sewerage Management | Purchase of 10000L Plastic water tank and construction of water Kiosk at Naishi Game. | To procure 10000L Plastic water tank and construction of water Kiosk at Naishi Game | 10000L Plastic water tank and construction of water Kiosk at Naishi Game procured | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.435797, 36.044722 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499937 | 100 | 499937 | 63 | 63 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
8126 | Water and Sewerage Management | Construction of water tank and fencing at Guba | To construct water tank and fencing at Guba | Water tank and fencing at Guba constructed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | LONDON | -0.279623 36.031717 1873.699951171875 64.0999984741211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3548882 | 3548882 | 3548882 | Equitable | N/A | 3548882 | 0 | 337770 | 9.5 | 337770 | 337770 | 3211112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Kitchen and dinning complete.
8127 | Water and Sewerage Management | Extension piping network in London and milimani apartments | To expand piping network in London and milimani apartments to increase capacity | Piping network in London and milimani apartments expanded | 3110502 | Water Supplies and Sewerage | NAKURU WEST | LONDON | -0.274103 36.054114 1880.728105673961 24 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 5358649 | 5358649 | Equitable | N/A | 5358649 | 0 | 4770829 | 89 | 4770829 | 587820 | 587820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8128 | Water and Sewerage Management | Drilling and equipping boreholes at Milimani and Unity primary school | To implement drilling and equipping boreholes at milimani and unity primary school for access to clean water and environmental sustainability | Drilling and equipping boreholes at Milimani and Unity primary school completed | 3110502 | Water Supplies and Sewerage | Naivasha | Lakeview | -0.720739, 36.43967 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 10000000 | 7542800.15 | 7542800.15 | Equitable | N/A | 7542800.15 | 0 | 796146 | 10.6 | 796146 | 873778 | 6746654.15 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: High flouride levels, water not safe for drinking.
8129 | Water and Sewerage Management | purchase and supply of water pipes and fittings to Manera estate | To procure and supply water pipes and fittings to Manera estate | Water pipes and fittings to Manera estate procured and supplied | 3110502 | Water Supplies and Sewerage | Naivasha | Lakeview | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1266830 | 97.4 | 1266830 | 1300000 | 33170 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8130 | Water and Sewerage Management | Completion of murunyu water project(pump and solar) | To complete murunyu water project(pump and solar) | Murunyu water project(pump and solar) completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.281411, 36.155653 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8131 | Water and Sewerage Management | Drilling of borehole at ndege ndimu | To provide access to clean water through borehole drilling at ndege ndimu | Borehole drilled at ndege ndimu | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.301965, 36.172122 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
8132 | Water and Sewerage Management | Drilling of borehole murunyu water project | To provide access to clean water through borehole drilling at murunyu water project | Borehole drilled at murunyu water project | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.247859, 36.151991 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 4000000 | 894392 | 894392 | Equitable | N/A | 894392 | 0 | 844287 | 94.4 | 844287 | 894392 | 50105 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
8133 | Water and Sewerage Management | Drilling of Borehole, pump and piping Lamnyondeki | To implement drilling of borehole, pump and piping lamnyondeki for access to clean water and environmental sustainability | Drilling of Borehole, pump and piping Lamnyondeki completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.265977, 36.16637 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1579317 | 39.5 | 1579317 | 1615034 | 2420683 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , very viable. Contractor: Njegwa investment limited. Assessor remarks: Functional.
8134 | Water and Sewerage Management | Installation of pump and purchase of 10000 litres water tank at modern | To install pump and purchase of 10000 litres water tank at modern | Pump and purchase of 10000 litres water tank at modern installed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.282202, 36.155693 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 1869954 | 1869954 | Equitable | N/A | 1869954 | 0 | 1529199 | 81.8 | 1529199 | 340755 | 340755 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8135 | Water and Sewerage Management | Installation of Water Pumps and solar panel at Kiamunyeki Water Project | To install Water Pumps and solar panel at Kiamunyeki Water Project | Water Pumps and solar panel at Kiamunyeki Water Project installed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.276553, 36.144895 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1922411 | 1922411 | 1922411 | Equitable | N/A | 1922411 | 0 | 1845061 | 96 | 1845061 | 1922411 | 77350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not functioning.
8136 | Water and Sewerage Management | Piping at Murunyu water works | To provide water distribution infrastructure at Murunyu water works | Water piping at Murunyu water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.23528, 36.167166 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RIDGEROCK ENTERPRISES. Assessor remarks: Functional.
8137 | Water and Sewerage Management | Piping of Baraka Water Project | To provide water distribution infrastructure at Baraka Water Project | Water piping at Baraka Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.2625, 36.150548 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1304295 | 87 | 1304295 | 1500000 | 195705 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
8138 | Water and Sewerage Management | Piping of modern water project | To provide water distribution infrastructure at modern water project | Water piping at modern water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.2625, 36.150548 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 924462 | 92.4 | 924462 | 75538 | 75538 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
8139 | Water and Sewerage Management | Repair of 2 water tanks in Kiamunyeki | To rehabilitate 2 water tanks in Kiamunyeki to restore functionality | 2 water tanks in Kiamunyeki rehabilitated | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.283645, 36.150508 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995900 | 99.8 | 1995900 | 4100 | 4100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but the repaired tank is not functional due to leakages.
8140 | Water and Sewerage Management | Repairing of Kiamunyeki borehole | To implement repairing of kiamunyeki borehole for access to clean water and environmental sustainability | Repairing of Kiamunyeki borehole completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.280414, 36.158421 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes ,but has land disputes. Assessor remarks: Has land dispute, borehole covered with sand.
8141 | Water and Sewerage Management | construction of intake structures for Ndurumoro water project | To construct intake structures for Ndurumoro water project | Intake structures for Ndurumoro water project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.446785 36.008917 2071.900146484375 87.5999984741211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 484996 | 97 | 484996 | 500000 | 15004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
8142 | Water and Sewerage Management | Installation of pipes at Karogoe mugumo | To install pipes at Karogoe mugumo | Pipes at Karogoe mugumo installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.46423, 36.044957 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2445900 | 97.8 | 2445900 | 54100 | 54100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8143 | Water and Sewerage Management | Installation of water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk. | To install water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk | Water pipes from Elimu ECDE. Purchase of 10000L Plastic water tank and construction of water Kiosk installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497633 | 99.8 | 1497633 | 1500000 | 2367 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8144 | Water and Sewerage Management | Installation of water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3. | To install water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3 | Water pipes from Kariaini Water, Purchase of 10000L Plastic water tank and construction of water Kiosk at Block 3 installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499137 | 99.9 | 1499137 | 863 | 863 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8145 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Bagaria - Kirima areas installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1629476 | 1629476 | 1629476 | Equitable | N/A | 1629476 | 0 | 1628847 | 100 | 1628847 | 629 | 629 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8146 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Muthiga installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8147 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk at Nganoini/Mugumo areas installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499990 | 100 | 1499990 | 10 | 10 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8148 | Water and Sewerage Management | Installation of water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House. | To install water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House | Water pipes, Purchase of 10000L Plastic water tank and construction of water Kiosk from Nguriga Slaughter House installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499834 | 100 | 1499834 | 166 | 166 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8149 | Water and Sewerage Management | Purchase of 10000L Plastic water tank and construction of water Kiosk at Naishi Game. | To procure 10000L Plastic water tank and construction of water Kiosk at Naishi Game | 10000L Plastic water tank and construction of water Kiosk at Naishi Game procured | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.435797, 36.044722 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499937 | 100 | 499937 | 63 | 63 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
8150 | Water and Sewerage Management | Installation of water pipes, purchase of 10,000L plastic water tank and construction of a water kiosk at Bagaria | To install water pipes, purchase of 10,000L plastic water tank and construction of a water kiosk at Bagaria | Water pipes, purchase of 10,000L plastic water tank and construction of a water kiosk at Bagaria installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024 | 1133898 | 1133898 | 1133898 | Equitable | N/A | 1133898 | 0 | 1010009 | 89.1 | 1010009 | 112223 | 123889 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
8151 | Water and Sewerage Management | Construction of water tank and fencing at Guba | To construct water tank and fencing at Guba | Water tank and fencing at Guba constructed | 3110502 | Water Supplies and Sewerage | Nakuru West | London | -0.279623 36.031717 1873.699951171875 64.0999984741211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3548882 | 337769.9 | 337769.9 | Equitable | N/A | 337769.9 | 0 | 337770 | 100 | 337770 | 337770 | -0.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Kitchen and dinning complete.
8152 | Water and Sewerage Management | Extension piping network in London and milimani apartments | To expand piping network in London and milimani apartments to increase capacity | Piping network in London and milimani apartments expanded | 3110502 | Water Supplies and Sewerage | Nakuru West | London | -0.274103 36.054114 1880.728105673961 24 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 5358649 | 5358649 | Equitable | N/A | 5358649 | 0 | 4770829 | 89 | 4770829 | 587820 | 587820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8153 | Water and Sewerage Management | design and construction of Kijabe water intake ( monkey conrner) | To design and construct Kijabe water intake ( monkey conrner) | Kijabe water intake ( monkey conrner) designed and constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000001 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8154 | Water and Sewerage Management | Maai Mahiu and longonot Water Works-Construction of Water tanks, drilling and Piping | To implement maai mahiu and longonot water works-construction of water tanks, drilling and piping for access to clean water and environmental sustainability | Maai Mahiu and longonot Water Works-Construction of Water tanks, drilling and Piping completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 14000000 | 14000000 | 14000000 | Equitable | N/A | 14000000 | 0 | 13454643 | 96.1 | 13454643 | 14000000 | 545357 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8155 | Water and Sewerage Management | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project | To implement maai mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; karima water project, githima water project, longonot water project, gichungu water project, satelite water project, vumilia camp water project, ruiru water project and car wash association water project for access to clean water and environmental sustainability | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | -1.007345, 36.534153 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 11000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 889299 | 8.9 | 889299 | 1203066 | 9110701 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: Needs to be made operational.
8156 | Water and Sewerage Management | Longonot water works | To implement longonot water works for access to clean water and environmental sustainability | Longonot water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | -0.890168, 36.496111 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 9000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3279350 | 54.7 | 3279350 | 6000000 | 2720650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete/water at tap.
8157 | Water and Sewerage Management | Maai Mahiu water works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2176522 | 54.4 | 2176522 | 8318914 | 1823478 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8158 | Water and Sewerage Management | Installation of water pump at Tangi Tatu Water Project | To install water pump at Tangi Tatu Water Project | Water pump at Tangi Tatu Water Project installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.796872 36.250812 1882.2 6.900000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 695072 | 695072 | 695072 | Equitable | N/A | 695072 | 0 | 657778 | 94.6 | 657778 | 695072 | 37294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
8159 | Water and Sewerage Management | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi | To implement maella ward water works - drilling, construction and piping of adc manyatta jikaze borehole: installation of a water tank at ngondi for access to clean water and environmental sustainability | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 9300000 | 9300000 | 9300000 | Equitable | N/A | 9300000 | 0 | 4959574 | 53.3 | 4959574 | 22738 | 4340426 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8160 | Water and Sewerage Management | MAIELLA ward water works | To implement maiella ward water works for access to clean water and environmental sustainability | MAIELLA ward water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.893724 36.198464 2353.60009765625 26.42799949645996 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 6239116 | 6239116 | 6239116 | Equitable | N/A | 6239116 | 0 | 3115340 | 49.9 | 3115340 | 79703 | 3123776 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
8161 | Water and Sewerage Management | NDABIBI water works | To implement ndabibi water works for access to clean water and environmental sustainability | NDABIBI water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.817397, 36.223778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2229403 | 89.2 | 2229403 | 270597 | 270597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
8162 | Water and Sewerage Management | Construction of a water reservoir and pipe work in Upper Maiella | To construct a water reservoir and pipe work in Upper Maiella | A water reservoir and pipe work in Upper Maiella constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.889533, 36.198517 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 313361 | 6.3 | 313361 | 313361 | 4686639 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Not Operation...Defunct project.
8163 | Water and Sewerage Management | completion and equipping of Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John | To complete and equip Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John | Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John completed and equipped | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.612613, 36.380458 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020/21 | 14100000 | 14250000 | 14250000 | Equitable | N/A | 14250000 | 0 | 5699962 | 40 | 5699962 | 6201314 | 8550038 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8164 | Water and Sewerage Management | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump | To implement malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of gatamaiyu, kwa njonjo, nyondia and karati centre boreholes and kasarani solar water pump for access to clean water and environmental sustainability | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 3099636 | 15.5 | 3099636 | 459053 | 16900364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well maintained.
8165 | Water and Sewerage Management | Piping and purchase of 3 water tank for Gathengera water project | To provide water distribution infrastructure at and purchase of 3 water tank for Gathengera water project | Water piping at and purchase of 3 water tank for Gathengera water project completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.774775 36.417744 0 5099.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199987 | 100 | 1199987 | 417 | 13 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8166 | Water and Sewerage Management | Proposed fencing of the proposed Kasarani Forest / Arboretum | To undertake the proposed fencing of the proposed Kasarani Forest / Arboretum | Proposed fencing of the proposed Kasarani Forest / Arboretum implemented | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done entirely need reinforcement.
8167 | Water and Sewerage Management | Purchase of 10000 litres water tank for Corner Nyondia water project and Construction of tank stand | To procure 10000 litres water tank for Corner Nyondia water project and Construction of tank stand | 10000 litres water tank for Corner Nyondia water project and Construction of tank stand procured | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.774775 36.417744 0 5099.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 288660 | 82.5 | 288660 | 417 | 61340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8168 | Water and Sewerage Management | Mugumoini Bore Hole(Pipe network) | To implement mugumoini bore hole(pipe network) for access to clean water and environmental sustainability | Mugumoini Bore Hole(Pipe network) completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703 36.471211 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2014/15 | 2014/15 | 2014/15 | 4620000 | 4607332 | 4607332 | Equitable | N/A | 4607332 | 0 | 2990874 | 64.9 | 2990874 | 3308420 | 1616458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8169 | Water and Sewerage Management | Completion of Kiplelmui water project | To complete Kiplelmui water project | Kiplelmui water project completed | 3110502 | Water Supplies and Sewerage | MOLO | MARIASHONI | -0.344047, 35.846218 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999802 | 100 | 2999802 | 198 | 198 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Water quality wanting.
8170 | Water and Sewerage Management | construction of water tank of oinoptich Centre | To construct water tank of oinoptich Centre | Water tank of oinoptich Centre constructed | 3110502 | Water Supplies and Sewerage | MOLO | MARIASHONI | -0.315941 35.844828 2322.209591306301 14 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2497033 | 99.9 | 2497033 | 2497033 | 2967 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8171 | Water and Sewerage Management | Drilling of Borehole at Digital Village | To provide access to clean water through borehole drilling at Digital Village | Borehole drilled at Digital Village | 3110502 | Water Supplies and Sewerage | MOLO | MARIASHONI | -0.358225, 35.815535 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4485480 | 89.7 | 4485480 | 514520 | 514520 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water ok.
8172 | Water and Sewerage Management | Kiplelmoi water project - laying of pipes and repairing of water intake | To implement kiplelmoi water project - laying of pipes and repairing of water intake for access to clean water and environmental sustainability | Kiplelmoi water project - laying of pipes and repairing of water intake completed | 3110502 | Water Supplies and Sewerage | MOLO | MARIASHONI | -0.342099, 35.849298 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 0 | 18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Water supply okay.
8173 | Water and Sewerage Management | Drilling and equipping of borehole, at Majimingi | To implement drilling and equipping of borehole, at majimingi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Majimingi completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
8174 | Water and Sewerage Management | Drilling and equipping of borehole, at Mukungugu | To implement drilling and equipping of borehole, at mukungugu for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Mukungugu completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
8175 | Water and Sewerage Management | Drilling and equipping of borehole, at Nyakiambi | To implement drilling and equipping of borehole, at nyakiambi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Nyakiambi completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2144654 | 85.8 | 2144654 | 354073 | 355346 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
8176 | Water And Sewerage Management | Drilling of borehole at Mutukanio B | To provide access to clean water through borehole drilling at Mutukanio B | Borehole drilled at Mutukanio B | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.60628, 36.008692 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 799565 | 40 | 799565 | 1894 | 1200435 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need solar.
8177 | Water and Sewerage Management | Equipping Gatimu Borehole | To equip Gatimu Borehole with necessary facilities and equipment | Gatimu Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -1.2841 36.8155 0 85955 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 1261440 | 1261440 | Equitable | N/A | 1261440 | 0 | 944834 | 74.9 | 944834 | 316606 | 316606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
8178 | Water and Sewerage Management | Installation of pipes at Segutiet Borehole | To install pipes at Segutiet Borehole | Pipes at Segutiet Borehole installed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -1.2841 36.8155 0 83800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998959 | 99.9 | 998959 | 1041 | 1041 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
8179 | Water and Sewerage Management | Kianjoya Dam - Construction of dam | To implement kianjoya dam - construction of dam for access to clean water and environmental sustainability | Kianjoya Dam - Construction of dam completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.544487, 36.059952 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070378 | 97.3 | 1070378 | 29622 | 29622 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not in use.
8180 | Water and Sewerage Management | Likia borehole equipping - equipping, installation of water pump and replacing of pipes for Likia borehole | To implement likia borehole equipping - equipping, installation of water pump and replacing of pipes for likia borehole for access to clean water and environmental sustainability | Likia borehole equipping - equipping, installation of water pump and replacing of pipes for Likia borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -1.2841 36.8155 0 85955 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990000 | 99.5 | 1990000 | 0 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
8181 | Water and Sewerage Management | Mahiga Water works | To implement mahiga water works for access to clean water and environmental sustainability | Mahiga Water works completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.503987, 36.053999 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499236 | 99.9 | 1499236 | 764 | 764 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Yes.
8182 | Water and Sewerage Management | Metta Water Project - Construction/completion/operationalization | To implement metta water project - construction/completion/operationalization for access to clean water and environmental sustainability | Metta Water Project - Construction/completion/operationalization completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.580995, 36.032157 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2861816 | 95.4 | 2861816 | 138183 | 138184 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need extra piping.
8183 | Water and Sewerage Management | Mukungugu Water Works | To implement mukungugu water works for access to clean water and environmental sustainability | Mukungugu Water Works completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601831, 36.011598 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 1261440 | 1261440 | Equitable | N/A | 1261440 | 0 | 1499236 | 118.9 | 1499236 | 1261440 | -237796 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: in good state of repair.
8184 | Water and Sewerage Management | Mutukanio B borehole Drilling | To implement mutukanio b borehole drilling for access to clean water and environmental sustainability | Mutukanio B borehole Drilling completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.59713, 35.996263 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 670248 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Assessor remarks: Projected stalled.
8185 | Water and Sewerage Management | Mutukanio Dam - desilting and Construction of Mutukanio Dam | To implement mutukanio dam - desilting and construction of mutukanio dam for access to clean water and environmental sustainability | Mutukanio Dam - desilting and Construction of Mutukanio Dam completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.597373, 35.998823 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499353 | 99.9 | 499353 | 499353 | 647 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need fencing.
8186 | Water and Sewerage Management | Nyakiambi Borehole Drilling | To implement nyakiambi borehole drilling for access to clean water and environmental sustainability | Nyakiambi Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.597155 35.996343 2588.8999999999996 5.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1329752 | 66.5 | 1329752 | 670248 | 670248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Assessor remarks: Project stalled.
8187 | Water and Sewerage Management | Nyandimu Water works | To implement nyandimu water works for access to clean water and environmental sustainability | Nyandimu Water works completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -1.2841, 36.8155 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 5260317 | 350.7 | 5260317 | 5260317 | -3760317 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: not viable. Assessor remarks: site handed over.
8188 | Water and Sewerage Management | Building of Tank and piping at Kaptich water project | To implement building of tank and piping at kaptich water project for access to clean water and environmental sustainability | Building of Tank and piping at Kaptich water project completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.565457, 36.036751 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019 | 2848617 | 2848617 | 2848617 | Equitable | N/A | 2848617 | 0 | 3436946 | 120.7 | 3436946 | 2848617 | -588329 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not. Assessor remarks: Needs improvement.
8189 | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | To construct a weir wall for gravity water flow and buying of pipes at Teret sub location water project | A weir wall for gravity water flow and buying of pipes at Teret sub location water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.465378, 35.952084 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 1939139.97 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999993 | 100 | 1999993 | 7 | 7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
8190 | Water and Sewerage Management | Construction of water tank and installation of pipes at Kamungei water project | To construct water tank and installation of pipes at Kamungei water project | Water tank and installation of pipes at Kamungei water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.553985, 36.044817 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1199077 | 40 | 1199077 | 896167 | 1800923 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8191 | Water and Sewerage Management | Construction of water tank at Kapsir | To construct water tank at Kapsir | Water tank at Kapsir constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.501888 35.980393 2406.1000000000004 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998470 | 99.9 | 1998470 | 1998470 | 1530 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8192 | Water and Sewerage Management | Drilling of borehole, purchase of water pump and installation of pipes at Toplife stock theft water project | To implement drilling of borehole, purchase of water pump and installation of pipes at toplife stock theft water project for access to clean water and environmental sustainability | Drilling of borehole, purchase of water pump and installation of pipes at Toplife stock theft water project completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1810593 | 36.2 | 1810593 | 1810593 | 3189407 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8193 | Water and Sewerage Management | Installation of pipes and construction of water kiosks at Kosimbei Water Project | To install pipes and construction of water kiosks at Kosimbei Water Project | Pipes and construction of water kiosks at Kosimbei Water Project installed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3798997 | 100 | 3798997 | 1003 | 1003 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8194 | Water and Sewerage Management | Purchase of solar panel at Tachasis water project | To procure solar panel at Tachasis water project | Solar panel at Tachasis water project procured | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.5304, 35.949238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 2719822 | 2719822 | 2719822 | Equitable | N/A | 2719822 | 0 | 4881268 | 179.5 | 4881268 | 2719822 | -2161446 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8195 | Water and Sewerage Management | Tachasis community water project - design and Construction of Tachasis community water project- piping | To implement tachasis community water project - design and construction of tachasis community water project- piping for access to clean water and environmental sustainability | Tachasis community water project - design and Construction of Tachasis community water project- piping completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.530473, 35.949265 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2014 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8196 | Tegunot / Siryat water project piping of water | Tegunot / Siryat water project piping of water | To implement tegunot / siryat water project piping of water for access to clean water and environmental sustainability | Tegunot / Siryat water project piping of water completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.501963 35.980358 2388.7999999999997 13.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 499937 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8197 | Water and Sewerage Management | construction of water tank and piping work at Kaptich water project | To construct water tank and piping work at Kaptich water project | Water tank and piping work at Kaptich water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.539043, 36.016872 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3436946 | 85.9 | 3436946 | 563054 | 563054 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8198 | Water and Sewerage Management | construction of water tank and piping work at Tulyotich community water project | To construct water tank and piping work at Tulyotich community water project | Water tank and piping work at Tulyotich community water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.539043, 36.016872 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3436946 | 85.9 | 3436946 | 4000000 | 563054 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8199 | Water and Sewerage Management | drilling of borehole at kamunget | To provide access to clean water through borehole drilling at kamunget | Borehole drilled at kamunget | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.568588, 36.034408 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs piping.
8200 | Water and Sewerage Management | Drilling of borehole at Kiratina | To provide access to clean water through borehole drilling at Kiratina | Borehole drilled at Kiratina | 3110502 | Water Supplies and Sewerage | NAKURU EAST | MENENGAI | -0.271879 36.103026 1889.5 18.309999465942383 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2306428 | 76.9 | 2306428 | 685285 | 693572 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8201 | Water and Sewerage Management | Drilling of borehole at Teachers Hyrax | To provide access to clean water through borehole drilling at Teachers Hyrax | Borehole drilled at Teachers Hyrax | 3110502 | Water Supplies and Sewerage | NAKURU EAST | MENENGAI | -0.275792, 36.114935 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2767296 | 92.2 | 2767296 | 232704 | 232704 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8202 | Water and Sewerage Management | Menengai ward water piping and sewer - piping of Kiratina, Teachers, Nyamarutu and Nguta / Mireri estate in Menengai Ward and sewer at Bismack | To implement menengai ward water piping and sewer - piping of kiratina, teachers, nyamarutu and nguta / mireri estate in menengai ward and sewer at bismack for access to clean water and environmental sustainability | Menengai ward water piping and sewer - piping of Kiratina, Teachers, Nyamarutu and Nguta / Mireri estate in Menengai Ward and sewer at Bismack completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | MENENGAI | -0.274763 36.113326 1858.4000244140625 8.986000061035156 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2432541 | 97.3 | 2432541 | 0 | 67459 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8203 | Water and Sewerage Management | Kaptich water works | To implement kaptich water works for access to clean water and environmental sustainability | Kaptich water works completed | 3110502 | Water Supplies and Sewerage | RONGAI | MENENGAI WEST | -0.144718 36.010936 0 92.9000015258789 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
8204 | Water and Sewerage Management | Ol Rongai water works and piping - piping of Ol Rongai water project | To implement ol rongai water works and piping - piping of ol rongai water project for access to clean water and environmental sustainability | Ol Rongai water works and piping - piping of Ol Rongai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MENENGAI WEST | -0.146435 36.009523 1826 13.850000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999709 | 100 | 3999709 | 3999709 | 291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8205 | Water and Sewerage Management | Rehabilitation Mercy Njeri tank | To rehabilitate Mercy Njeri tank to restore functionality | Mercy Njeri tank rehabilitated | 3110502 | Water Supplies and Sewerage | RONGAI | MENENGAI WEST | -0.150263 36.010846 1900.199951171875 123.6719970703125 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1858667 | 103.3 | 1858667 | 1800000 | -58667 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8206 | Water and Sewerage Management | Construction of Green garden water tank | To construct Green garden water tank | Green garden water tank constructed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3999000 | 3999000 | 3999000 | Equitable | N/A | 3999000 | 0 | 1436265 | 35.9 | 1436265 | 3183456 | 2562735 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8207 | Water and Sewerage Management | Construction of Milimani water tank | To construct Milimani water tank | Milimani water tank constructed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 1436265 | 55.2 | 1436265 | 3183456 | 1163735 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8208 | Water and Sewerage Management | Distilling of Chesoin Dam and piping | To implement distilling of chesoin dam and piping for access to clean water and environmental sustainability | Distilling of Chesoin Dam and piping completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2910000 | 2910000 | 2910000 | Equitable | N/A | 2910000 | 0 | 14592200 | 501.5 | 14592200 | 0 | -11682200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8209 | Water and Sewerage Management | Kenyatta borehole drilling | To implement kenyatta borehole drilling for access to clean water and environmental sustainability | Kenyatta borehole drilling completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1496859 | 29.9 | 1496859 | 1496859 | 3503141 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8210 | Water and Sewerage Management | Molo Dumping site | To implement molo dumping site for access to clean water and environmental sustainability | Molo Dumping site completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8211 | Water and Sewerage Management | Piping of Matumani/mugeremukia water project | To provide water distribution infrastructure at Matumani/mugeremukia water project | Water piping at Matumani/mugeremukia water project completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 485466 | 16.2 | 485466 | 5000000 | 2514534 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8212 | Water and Sewerage Management | Rehabilitation of Tekek water intake and tank | To rehabilitate Tekek water intake and tank to restore functionality | Tekek water intake and tank rehabilitated | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2994378 | 99.8 | 2994378 | 945568 | 5622 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8213 | Water and Sewerage Management | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project | To implement rehabiltation works at maishani area and mutiruthia; extension of piping at tayari water project and kiambogo water project for access to clean water and environmental sustainability | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2601108.39 | 2601108.39 | 2601108.39 | Equitable | N/A | 2601108.39 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
8214 | Water and Sewerage Management | Boror Nairobi water projects - purchase and laying of water pipes | To implement boror nairobi water projects - purchase and laying of water pipes for access to clean water and environmental sustainability | Boror Nairobi water projects - purchase and laying of water pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2002493 | 80.1 | 2002493 | 2002493 | 497507 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8215 | Water and Sewerage Management | Chelele water project - construction of 50m3 tank and laying of pipes | To implement chelele water project - construction of 50m3 tank and laying of pipes for access to clean water and environmental sustainability | Chelele water project - construction of 50m3 tank and laying of pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.215495 35.822015 1909.6000000000001 23.200000762939453 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 14000003 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3900000 | 100 | 3900000 | 55200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kina investment. Assessor remarks: Good work.
8216 | Water and Sewerage Management | Chepseon water project- laying of pipes | To implement chepseon water project- laying of pipes for access to clean water and environmental sustainability | Chepseon water project- laying of pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.236822 35.826233 1903.300048828125 5.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 14000004 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 2997208 | 96.7 | 2997208 | 55200 | 102792 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8217 | Water and Sewerage Management | completion of keriko water project | To complete keriko water project | Keriko water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998043 | 99.9 | 1998043 | 1998043 | 1957 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8218 | Water and Sewerage Management | Construction of tank, and laying of pipes at Sumeek,rigogo water project | To construct tank, and laying of pipes at Sumeek,rigogo water project | Tank, and laying of pipes at Sumeek,rigogo water project constructed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2571987 | 98.9 | 2571987 | 28013 | 28013 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
8219 | Water and Sewerage Management | Ex magret water tank and piping | To implement ex magret water tank and piping for access to clean water and environmental sustainability | Ex magret water tank and piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.28556 35.892287 2148.4 11.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998975 | 99.9 | 1998975 | 1998975 | 1025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Gamak enterprise. Assessor remarks: Good work.
8220 | Water and Sewerage Management | Keriko water project - purchase and laying of water pipes | To implement keriko water project - purchase and laying of water pipes for access to clean water and environmental sustainability | Keriko water project - purchase and laying of water pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 625000 | 625000 | 625000 | Equitable | N/A | 625000 | 0 | 624344 | 99.9 | 624344 | 2002493 | 656 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8221 | Water and Sewerage Management | Kerma borehole - purchase and installation of pump and water piping | To implement kerma borehole - purchase and installation of pump and water piping for access to clean water and environmental sustainability | Kerma borehole - purchase and installation of pump and water piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.314718, 35.970947 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2479575 | 99.2 | 2479575 | 2500000 | 20425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Marileon. Assessor remarks: Good.
8222 | Water and Sewerage Management | Laying of pipes lelechwet, chepseon water project | To implement laying of pipes lelechwet, chepseon water project for access to clean water and environmental sustainability | Laying of pipes lelechwet, chepseon water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.212327, 35.820707 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1155282 | 1155282 | 1155282 | Equitable | N/A | 1155282 | 0 | 1152021 | 99.7 | 1152021 | 3261 | 3261 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Jitahidi enterprise. Assessor remarks: Stalled.
8223 | Water and Sewerage Management | laying of water pipes Lelechwet kapkures | To implement laying of water pipes lelechwet kapkures for access to clean water and environmental sustainability | laying of water pipes Lelechwet kapkures completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.216828, 35.824175 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996178 | 99.6 | 996178 | 3822 | 3822 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Mathioya. Assessor remarks: Stalled project.
8224 | Water and Sewerage Management | Lelechwet water tank - construction of 200m3 water tank and pipes | To implement lelechwet water tank - construction of 200m3 water tank and pipes for access to clean water and environmental sustainability | Lelechwet water tank - construction of 200m3 water tank and pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2024 | 14000002 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 1231519 | 31.6 | 1231519 | 1231519 | 2668481 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8225 | Water and Sewerage Management | Mbama Intake project - intake works | To implement mbama intake project - intake works for access to clean water and environmental sustainability | Mbama Intake project - intake works completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.21216, 35.816242 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 14000001 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 1356326 | 43.8 | 1356326 | 30825 | 1743674 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Contractor: Roy n alvis. Assessor remarks: Stalled.
8226 | Water and Sewerage Management | Moyaset piping | To implement moyaset piping for access to clean water and environmental sustainability | Moyaset piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.218702, 35.837082 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 500000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 798967 | 99.9 | 798967 | 1033 | 1033 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/ s samues. Assessor remarks: Good.
8227 | Water and Sewerage Management | Ndusu / Rigogo / Sumeek - construction of intake and piping | To implement ndusu / rigogo / sumeek - construction of intake and piping for access to clean water and environmental sustainability | Ndusu / Rigogo / Sumeek - construction of intake and piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | 2024 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3663643 | 91.6 | 3663643 | 0 | 336357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8228 | Water and Sewerage Management | Ngecha Water Project | To implement ngecha water project for access to clean water and environmental sustainability | Ngecha Water Project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 371075 | 12.4 | 371075 | 374966 | 2628925 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8229 | Water and Sewerage Management | Ngondu Water project piping | To implement ngondu water project piping for access to clean water and environmental sustainability | Ngondu Water project piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8230 | Water and Sewerage Management | Waldai water projects works - intake and pipes | To implement waldai water projects works - intake and pipes for access to clean water and environmental sustainability | Waldai water projects works - intake and pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 0 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498800 | 99.9 | 1498800 | 2002493 | 1200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8231 | Water and Sewerage Management | Construction of Ngondu Water tank | To construct Ngondu Water tank | Ngondu Water tank constructed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1202617 | 80.2 | 1202617 | 1998043 | 297383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8232 | Water and Sewerage Management | Piping of Sumeek water project | To provide water distribution infrastructure at Sumeek water project | Water piping at Sumeek water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | To be vired | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495931 | 99.8 | 2495931 | 4069 | 4069 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8233 | Water and Sewerage Management | Murindat water works | To implement murindat water works for access to clean water and environmental sustainability | Murindat water works completed | 3110502 | Water Supplies and Sewerage | GILGIL | MURINDAT | -0.411137, 36.311427 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 584640 | 11.7 | 584640 | 597406 | 4415360 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not done. Viable: Yet to start. Assessor remarks: Not done.
8234 | Water and Sewerage Management | design and construction of Kijabe water intake (monkey corner) | To design and construct Kijabe water intake (monkey corner) | Kijabe water intake (monkey corner) designed and constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000001 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8235 | Water and Sewerage Management | Maai Mahiu and longonot Water Works-Construction of Water tanks, drilling and Piping | To implement maai mahiu and longonot water works-construction of water tanks, drilling and piping for access to clean water and environmental sustainability | Maai Mahiu and longonot Water Works-Construction of Water tanks, drilling and Piping completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 14000000 | 14000000 | 14000000 | Equitable | N/A | 14000000 | 0 | 13454643 | 96.1 | 13454643 | 14000000 | 545357 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8236 | Water and Sewerage Management | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project | To implement maai mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; karima water project, githima water project, longonot water project, gichungu water project, satelite water project, vumilia camp water project, ruiru water project and car wash association water project for access to clean water and environmental sustainability | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -1.007345, 36.534153 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 11000000 | 3983769 | 3983769 | Equitable | N/A | 3983769 | 0 | 889299 | 22.3 | 889299 | 1203066 | 3094470 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: Needs to be made operational.
8237 | Water and Sewerage Management | Water works-purchase of pipes and pipe laying in maai mahiu/longonot | To implement water works-purchase of pipes and pipe laying in maai mahiu/longonot for access to clean water and environmental sustainability | Water works-purchase of pipes and pipe laying in maai mahiu/longonot completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8238 | Water and Sewerage Management | Longonot water works | To implement longonot water works for access to clean water and environmental sustainability | Longonot water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -0.890168, 36.496111 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 9000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3279350 | 54.7 | 3279350 | 6000000 | 2720650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete/water at tap.
8239 | Water and Sewerage Management | Maai Mahiu water works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 1432516.9 | 1432516.9 | Equitable | N/A | 1432516.9 | 0 | 2176522 | 151.9 | 2176522 | 8318914 | -744005.1 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8240 | Water and Sewerage Management | Construction of a water reservoir and pipe work in Upper Maiella | To construct a water reservoir and pipe work in Upper Maiella | A water reservoir and pipe work in Upper Maiella constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.889533, 36.198517 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 313361 | 6.3 | 313361 | 313361 | 4686639 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Not Operation...Defunct project.
8241 | Water and Sewerage Management | Drilling of borehole at Natooli water project | To provide access to clean water through borehole drilling at Natooli water project | Borehole drilled at Natooli water project | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.824917 36.203913 0 400 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 584820 | 17.2 | 584820 | 2400000 | 2815180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
8242 | Water and Sewerage Management | Equipping of borehole at Natooli water project | To equip borehole at Natooli water project with necessary facilities and equipment | Borehole at Natooli water project equipped | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.824917 36.203913 0 400 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 584820 | 19.5 | 584820 | 3000000 | 2415180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
8243 | Water and Sewerage Management | Fly over-tumaini water works | To implement fly over-tumaini water works for access to clean water and environmental sustainability | Fly over-tumaini water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1113636 | 1113636 | 1113636 | Equitable | N/A | 1113636 | 0 | 1018608 | 91.5 | 1018608 | 1018608 | 95028 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
8244 | Water and Sewerage Management | Installation of water pump at Tangi Tatu Water Project | To install water pump at Tangi Tatu Water Project | Water pump at Tangi Tatu Water Project installed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 695072 | 695072 | 695072 | Equitable | N/A | 695072 | 0 | 657778 | 94.6 | 657778 | 695072 | 37294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
8245 | Water and Sewerage Management | Kiburuti water works | To implement kiburuti water works for access to clean water and environmental sustainability | Kiburuti water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 477444 | 95.5 | 477444 | 500000 | 22556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8246 | Water and Sewerage Management | Kirima water works | To implement kirima water works for access to clean water and environmental sustainability | Kirima water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
8247 | Water and Sewerage Management | Maeilla water works | To implement maeilla water works for access to clean water and environmental sustainability | Maeilla water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1331984 | 1331984 | 1331984 | Equitable | N/A | 1331984 | 0 | 1305170 | 98 | 1305170 | 1331984 | 26814 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
8248 | Water and Sewerage Management | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi | To implement maella ward water works - drilling, construction and piping of adc manyatta jikaze borehole: installation of a water tank at ngondi for access to clean water and environmental sustainability | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 9300000 | 4982312 | 4982312 | Equitable | N/A | 4982312 | 0 | 4959574 | 99.5 | 4959574 | 22738 | 22738 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8249 | Water and Sewerage Management | Maiella ward water works | To implement maiella ward water works for access to clean water and environmental sustainability | Maiella ward water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 6239116 | 3195042 | 3195042 | Equitable | N/A | 3195042 | 0 | 3115340 | 97.5 | 3115340 | 79703 | 79702 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
8250 | Water and Sewerage Management | Moindabi water works | To implement moindabi water works for access to clean water and environmental sustainability | Moindabi water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
8251 | Water and Sewerage Management | Ndabibi water works | To implement ndabibi water works for access to clean water and environmental sustainability | Ndabibi water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2229403 | 89.2 | 2229403 | 270597 | 270597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
8252 | Water and Sewerage Management | Solar panel installation at Natooli water project | To implement solar panel installation at natooli water project for access to clean water and environmental sustainability | Solar panel installation at Natooli water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 657778 | 18.3 | 657778 | 1600000 | 2942222 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
8253 | Water and Sewerage Management | completion and equipping of Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John | To complete and equip Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John | Gwashare borehole, kasarani borehole,Milimani Borehole and purchase of land at St John completed and equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.612613, 36.380458 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020/21 | 14100000 | 11167851 | 11167851 | Equitable | N/A | 11167851 | 0 | 5699962 | 51 | 5699962 | 6201314 | 5467889 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8254 | Water and Sewerage Management | Equipping of mlimani borehole and solarisation | To equip mlimani borehole and solarisation with necessary facilities and equipment | Mlimani borehole and solarisation equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.630631, 36.488697 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8255 | Water and Sewerage Management | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump | To implement malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of gatamaiyu, kwa njonjo, nyondia and karati centre boreholes and kasarani solar water pump for access to clean water and environmental sustainability | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.471211 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 20000000 | 4229322 | 4229322 | Equitable | N/A | 4229322 | 0 | 3099636 | 73.3 | 3099636 | 459053 | 1129686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well maintained.
8256 | Water and Sewerage Management | Piping and purchase of 2 no. 10,000 L water tank at green valley water project | To provide water distribution infrastructure at and purchase of 2 no. 10,000 L water tank at green valley water project | Water piping at and purchase of 2 no. 10,000 L water tank at green valley water project completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.774775 36.417744 0 5099.9990234375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699583 | 99.9 | 699583 | 417 | 417 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8257 | Water and Sewerage Management | Piping at nyondia water works | To provide water distribution infrastructure at nyondia water works | Water piping at nyondia water works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.612613, 36.398477 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021-22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8258 | Water and Sewerage Management | Mugumoini Bore Hole(Pipe network) | To implement mugumoini bore hole(pipe network) for access to clean water and environmental sustainability | Mugumoini Bore Hole(Pipe network) completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2014/15 | 2014/15 | 2014/15 | 4620000 | 4607332 | 4607332 | Equitable | N/A | 4607332 | 0 | 2990874 | 64.9 | 2990874 | 3308420 | 1616458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8259 | Water and Sewerage Management | Completion of Kiplelmui water project | To complete Kiplelmui water project | Kiplelmui water project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.344047, 35.846218 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999802 | 100 | 2999802 | 198 | 198 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Water quality wanting.
8260 | Water and Sewerage Management | construction of water tank of oinoptich Centre | To construct water tank of oinoptich Centre | Water tank of oinoptich Centre constructed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.315941 35.844828 2322.209591306301 14 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2497033 | 2497033 | Equitable | N/A | 2497033 | 0 | 2497033 | 100 | 2497033 | 2497033 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8261 | Water and Sewerage Management | Drilling of Borehole at Digital Village | To provide access to clean water through borehole drilling at Digital Village | Borehole drilled at Digital Village | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.358225, 35.815535 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4485480 | 89.7 | 4485480 | 514520 | 514520 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water ok.
8262 | Water and Sewerage Management | Piping lawina water project | To provide water distribution infrastructure at lawina water project | Water piping at lawina water project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.343994, 35.846228 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 921890 | 92.2 | 921890 | 78110 | 78110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational thus no water supply.
8263 | Water and Sewerage Management | Piping of oinoptich water project | To provide water distribution infrastructure at oinoptich water project | Water piping at oinoptich water project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.336516 35.875599 2348 27.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499938 | 100 | 1499938 | 1500000 | 62 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Pipes are not working thus no supply of water.
8264 | Water and Sewerage Management | Construction of Nyakiambi water tank and piping | To construct Nyakiambi water tank and piping | Nyakiambi water tank and piping constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.600012 36.007202 0 141 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 2100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs upgrading.
8265 | Water and Sewerage Management | Drilling and equipping of borehole, at Majimingi | To implement drilling and equipping of borehole, at majimingi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Majimingi completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601445, 36.011229 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
8266 | Water and Sewerage Management | Drilling and equipping of borehole, at Nyakiambi | To implement drilling and equipping of borehole, at nyakiambi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Nyakiambi completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601445, 36.011229 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019/20 | 2500000 | 2498727 | 2498727 | Equitable | N/A | 2498727 | 0 | 2144654 | 85.8 | 2144654 | 354073 | 354073 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
8267 | Water And Sewerage Management | Drilling of borehole at Mutukanio B | To provide access to clean water through borehole drilling at Mutukanio B | Borehole drilled at Mutukanio B | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.60628, 36.008692 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 801459 | 801459 | Equitable | N/A | 801459 | 0 | 799565 | 99.8 | 799565 | 1894 | 1894 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need solar.
8268 | Water and Sewerage Management | Equipping Gatimu Borehole | To equip Gatimu Borehole with necessary facilities and equipment | Gatimu Borehole equipped | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 1261440 | 1261440 | Equitable | N/A | 1261440 | 0 | 944834 | 74.9 | 944834 | 316606 | 316606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
8269 | Water and Sewerage Management | Installation of pipes at Segutiet Borehole | To install pipes at Segutiet Borehole | Pipes at Segutiet Borehole installed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841 36.8155 0 83800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998959 | 99.9 | 998959 | 1041 | 1041 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
8270 | Water and Sewerage Management | Kianjoya Dam - Construction of dam | To implement kianjoya dam - construction of dam for access to clean water and environmental sustainability | Kianjoya Dam - Construction of dam completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.544487, 36.059952 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070378 | 97.3 | 1070378 | 29622 | 29622 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not in use.
8271 | Water and Sewerage Management | Mahiga Water works | To implement mahiga water works for access to clean water and environmental sustainability | Mahiga Water works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.503987, 36.053999 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499236 | 99.9 | 1499236 | 764 | 764 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Yes.
8272 | Water and Sewerage Management | Metta Water Project - Construction/completion/operationalization | To implement metta water project - construction/completion/operationalization for access to clean water and environmental sustainability | Metta Water Project - Construction/completion/operationalization completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.580995, 36.032157 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 2999999 | 2999999 | Equitable | N/A | 2999999 | 0 | 2861816 | 95.4 | 2861816 | 138183 | 138183 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need extra piping.
8273 | Water and Sewerage Management | Mukungugu Water Works | To implement mukungugu water works for access to clean water and environmental sustainability | Mukungugu Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601831, 36.011598 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 1261440 | 1261440 | Equitable | N/A | 1261440 | 0 | 1499236 | 118.9 | 1499236 | 1261440 | -237796 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: in good state of repair.
8274 | Water and Sewerage Management | Mutukanio Dam - desilting and Construction of Mutukanio Dam | To implement mutukanio dam - desilting and construction of mutukanio dam for access to clean water and environmental sustainability | Mutukanio Dam - desilting and Construction of Mutukanio Dam completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.597373, 35.998823 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 499353 | 499353 | Equitable | N/A | 499353 | 0 | 499353 | 100 | 499353 | 499353 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need fencing.
8275 | Water and Sewerage Management | Nyakiambi Borehole Drilling | To implement nyakiambi borehole drilling for access to clean water and environmental sustainability | Nyakiambi Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.597155 35.996343 2588.8999999999996 5.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 670247.9 | 670247.9 | Equitable | N/A | 670247.9 | 0 | 1329752 | 198.4 | 1329752 | 670248 | -659504.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Assessor remarks: Project stalled.
8276 | Water and Sewerage Management | Nyandimu Water works | To implement nyandimu water works for access to clean water and environmental sustainability | Nyandimu Water works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841, 36.8155 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5260317 | 5260317 | 5260317 | Equitable | N/A | 5260317 | 0 | 5260317 | 100 | 5260317 | 5260317 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: not viable. Assessor remarks: site handed over.
8277 | Water and Sewerage Management | Mau Narok Water Works (Mahiga Water Project; Mukeu Water Project; Block 9/Obwaka Water Project; Maji Mingi Water Project; Solarisation of Mutikanio B Borehole) | To implement mau narok water works (mahiga water project; mukeu water project; block 9/obwaka water project; maji mingi water project; solarisation of mutikanio b borehole) for access to clean water and environmental sustainability | Mau Narok Water Works (Mahiga Water Project; Mukeu Water Project; Block 9/Obwaka Water Project; Maji Mingi Water Project; Solarisation of Mutikanio B Borehole) completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.50398, 36.05382 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 7398052 | 7398052 | 7398052 | Equitable | N/A | 7398052 | 0 | 5764574 | 77.9 | 5764574 | 1633478 | 1633478 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8278 | Water and Sewerage Management | Building of Tank and piping at Kaptich water project | To implement building of tank and piping at kaptich water project for access to clean water and environmental sustainability | Building of Tank and piping at Kaptich water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.565457, 36.036751 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019 | 2848617 | 2848617 | 2848617 | Equitable | N/A | 2848617 | 0 | 3436946 | 120.7 | 3436946 | 2848617 | -588329 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not. Assessor remarks: Needs improvement.
8279 | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | To construct a weir wall for gravity water flow and buying of pipes at Teret sub location water project | A weir wall for gravity water flow and buying of pipes at Teret sub location water project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.465378, 35.952084 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 1939139.97 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999993 | 100 | 1999993 | 7 | 7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
8280 | Water and Sewerage Management | Construction of water tank and installation of pipes at Kamungei water project | To construct water tank and installation of pipes at Kamungei water project | Water tank and installation of pipes at Kamungei water project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.553985, 36.044817 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 2495244 | 2495244 | Equitable | N/A | 2495244 | 0 | 1199077 | 48.1 | 1199077 | 896167 | 1296167 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8281 | Water and Sewerage Management | Construction of water tank at Kapsir | To construct water tank at Kapsir | Water tank at Kapsir constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.501888 35.980393 2406.1000000000004 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 1998470 | 1998470 | Equitable | N/A | 1998470 | 0 | 1998470 | 100 | 1998470 | 1998470 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8282 | Water and Sewerage Management | drilling of a borehole at Kusumek water projects | To implement drilling of a borehole at kusumek water projects for access to clean water and environmental sustainability | drilling of a borehole at Kusumek water projects completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.517562 35.973678 2471 8.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2431685 | 81.1 | 2431685 | 3000000 | 568315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good.
8283 | Water and Sewerage Management | Drilling of borehole, purchase of water pump and installation of pipes at Toplife stock theft water project | To implement drilling of borehole, purchase of water pump and installation of pipes at toplife stock theft water project for access to clean water and environmental sustainability | Drilling of borehole, purchase of water pump and installation of pipes at Toplife stock theft water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1810593 | 36.2 | 1810593 | 1810593 | 3189407 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8284 | Water and Sewerage Management | Installation of pipes and construction of water kiosks at Kosimbei Water Project | To install pipes and construction of water kiosks at Kosimbei Water Project | Pipes and construction of water kiosks at Kosimbei Water Project installed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3798997 | 100 | 3798997 | 1003 | 1003 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8285 | Water and Sewerage Management | Installation of solar panels at kamungei water project | To install solar panels at kamungei water project | Solar panels at kamungei water project installed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.55395, 36.044742 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 4881268 | 212.2 | 4881268 | 1300000 | -2581268 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8286 | Water and Sewerage Management | Installation of solar panels at Top life water project | To install solar panels at Top life water project | Solar panels at Top life water project installed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.532137 35.995515 2400 7.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2300000 | 5300000 | 5300000 | Equitable | N/A | 5300000 | 0 | 4881268 | 92.1 | 4881268 | 418732 | 418732 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8287 | Tegunot / Siryat water project piping of water | Tegunot / Siryat water project piping of water | To implement tegunot / siryat water project piping of water for access to clean water and environmental sustainability | Tegunot / Siryat water project piping of water completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.501963 35.980358 2388.7999999999997 13.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 499937.25 | 499937.25 | Equitable | N/A | 499937.25 | 0 | 0 | 0 | 0 | 499937 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8288 | Water and Sewerage Management | construction of water tank and piping work at Kaptich water project | To construct water tank and piping work at Kaptich water project | Water tank and piping work at Kaptich water project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.539043, 36.016872 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 4000000 | 563053.7 | 563053.7 | Equitable | N/A | 563053.7 | 0 | 3436946 | 610.4 | 3436946 | 563054 | -2873892.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
8289 | Water and Sewerage Management | drilling of borehole at kamunget | To provide access to clean water through borehole drilling at kamunget | Borehole drilled at kamunget | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.568588, 36.034408 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs piping.
8290 | Water and Sewerage Management | Drilling of borehole at Kiratina | To provide access to clean water through borehole drilling at Kiratina | Borehole drilled at Kiratina | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.271879 36.103026 1889.5 18.309999465942383 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 685285 | 685285 | Equitable | N/A | 685285 | 0 | 2306428 | 336.6 | 2306428 | 685285 | -1621143 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8291 | Water and Sewerage Management | Drilling of borehole at Teachers Hyrax | To provide access to clean water through borehole drilling at Teachers Hyrax | Borehole drilled at Teachers Hyrax | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.275792, 36.114935 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2767296 | 92.2 | 2767296 | 232704 | 232704 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8292 | Water and Sewerage Management | piping of water for Shiners borehole to Neylan tank | To provide water distribution infrastructure at water for Shiners borehole to Neylan tank | Water piping at water for Shiners borehole to Neylan tank completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.266251 36.100627 1913.5 20 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1294850 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Nop. Viable: Nop. Assessor remarks: It's good for muhoro road to be upgraded to tarmac.
8293 | Water and Sewerage Management | Ol Rongai water works and piping - piping of Ol Rongai water project | To implement ol rongai water works and piping - piping of ol rongai water project for access to clean water and environmental sustainability | Ol Rongai water works and piping - piping of Ol Rongai water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.146435 36.009523 1826 13.850000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 3999709 | 3999709 | Equitable | N/A | 3999709 | 0 | 3999709 | 100 | 3999709 | 3999709 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8294 | Water and Sewerage Management | Construction of Green garden water tank | To construct Green garden water tank | Green garden water tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3999000 | 3899403 | 3899403 | Equitable | N/A | 3899403 | 0 | 1436265 | 36.8 | 1436265 | 3183456 | 2463138 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8295 | Water and Sewerage Management | Construction of Milimani water tank | To construct Milimani water tank | Milimani water tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 1436265 | 55.2 | 1436265 | 3183456 | 1163735 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8296 | Water and Sewerage Management | Distilling of Chesoin Dam and piping | To implement distilling of chesoin dam and piping for access to clean water and environmental sustainability | Distilling of Chesoin Dam and piping completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2910000 | 2910000 | 2910000 | Equitable | N/A | 2910000 | 0 | 14592200 | 501.5 | 14592200 | 0 | -11682200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8297 | Water and Sewerage Management | Kenyatta borehole drilling | To implement kenyatta borehole drilling for access to clean water and environmental sustainability | Kenyatta borehole drilling completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 2796333.5 | 2796333.5 | Equitable | N/A | 2796333.5 | 0 | 1496859 | 53.5 | 1496859 | 1496859 | 1299474.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8298 | Water and Sewerage Management | Piping of Matumani/mugeremukia water project | To provide water distribution infrastructure at Matumani/mugeremukia water project | Water piping at Matumani/mugeremukia water project completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 485466 | 16.2 | 485466 | 5000000 | 2514534 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8299 | Water and Sewerage Management | Rehabilitation of Tekek water intake and tank | To rehabilitate Tekek water intake and tank to restore functionality | Tekek water intake and tank rehabilitated | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 2997023 | 2997023 | Equitable | N/A | 2997023 | 0 | 2994378 | 99.9 | 2994378 | 945568 | 2645 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8300 | Water and Sewerage Management | Boror Nairobi water projects - purchase and laying of water pipes | To implement boror nairobi water projects - purchase and laying of water pipes for access to clean water and environmental sustainability | Boror Nairobi water projects - purchase and laying of water pipes completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.23233, 35.837018 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 2500000 | 2002493 | 2002493 | Equitable | N/A | 2002493 | 0 | 2002493 | 100 | 2002493 | 2002493 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8301 | Water and Sewerage Management | Chelele water project - construction of 50m3 tank and laying of pipes | To implement chelele water project - construction of 50m3 tank and laying of pipes for access to clean water and environmental sustainability | Chelele water project - construction of 50m3 tank and laying of pipes completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.215495 35.822015 1909.6000000000001 23.200000762939453 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 14000003 | 3955200 | 3955200 | Equitable | N/A | 3955200 | 0 | 3900000 | 98.6 | 3900000 | 55200 | 55200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kina investment. Assessor remarks: Good work.
8302 | Water and Sewerage Management | completion of keriko water project | To complete keriko water project | Keriko water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 2000000 | 1998043 | 1998043 | Equitable | N/A | 1998043 | 0 | 1998043 | 100 | 1998043 | 1998043 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8303 | Water and Sewerage Management | Construction of tank, and laying of pipes at Sumeek,rigogo water project | To construct tank, and laying of pipes at Sumeek,rigogo water project | Tank, and laying of pipes at Sumeek,rigogo water project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2571987 | 98.9 | 2571987 | 28013 | 28013 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
8304 | Water and Sewerage Management | Ex magret water tank and piping | To implement ex magret water tank and piping for access to clean water and environmental sustainability | Ex magret water tank and piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.28556 35.892287 2148.4 11.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1998974.78 | 1998974.78 | Equitable | N/A | 1998974.78 | 0 | 1998975 | 100 | 1998975 | 1998975 | -0.22 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Gamak enterprise. Assessor remarks: Good work.
8305 | Water and Sewerage Management | Kerma borehole - purchase and installation of pump and water piping | To implement kerma borehole - purchase and installation of pump and water piping for access to clean water and environmental sustainability | Kerma borehole - purchase and installation of pump and water piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.314718, 35.970947 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2479575 | 99.2 | 2479575 | 2500000 | 20425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Marileon. Assessor remarks: Good.
8306 | Water and Sewerage Management | Laying of pipes lelechwet, chepseon water project | To implement laying of pipes lelechwet, chepseon water project for access to clean water and environmental sustainability | Laying of pipes lelechwet, chepseon water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.212327, 35.820707 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1155282 | 1155282 | 1155282 | Equitable | N/A | 1155282 | 0 | 1152021 | 99.7 | 1152021 | 3261 | 3261 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Jitahidi enterprise. Assessor remarks: Stalled.
8307 | Water and Sewerage Management | laying of water pipes Lelechwet kapkures | To implement laying of water pipes lelechwet kapkures for access to clean water and environmental sustainability | laying of water pipes Lelechwet kapkures completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.216828, 35.824175 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996178 | 99.6 | 996178 | 3822 | 3822 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Mathioya. Assessor remarks: Stalled project.
8308 | Water and Sewerage Management | Lelechwet water tank - construction of 200m3 water tank and pipes | To implement lelechwet water tank - construction of 200m3 water tank and pipes for access to clean water and environmental sustainability | Lelechwet water tank - construction of 200m3 water tank and pipes completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.248192, 35.808833 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2024 | 14000002 | 3897641.41 | 3897641.41 | Equitable | N/A | 3897641.41 | 0 | 1231519 | 31.6 | 1231519 | 1231519 | 2666122.41 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8309 | Water and Sewerage Management | Mbama Intake project - intake works | To implement mbama intake project - intake works for access to clean water and environmental sustainability | Mbama Intake project - intake works completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.21216, 35.816242 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 14000001 | 3093894 | 3093894 | Equitable | N/A | 3093894 | 0 | 1356326 | 43.8 | 1356326 | 30825 | 1737568 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Contractor: Roy n alvis. Assessor remarks: Stalled.
8310 | Water and Sewerage Management | Moyaset piping | To implement moyaset piping for access to clean water and environmental sustainability | Moyaset piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.218702, 35.837082 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 500000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 798967 | 99.9 | 798967 | 1033 | 1033 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/ s samues. Assessor remarks: Good.
8311 | Water and Sewerage Management | Ngata location water works(purchase and laying of pipes) | To implement ngata location water works(purchase and laying of pipes) for access to clean water and environmental sustainability | Ngata location water works(purchase and laying of pipes) completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.23233, 35.837018 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995860 | 99.6 | 995860 | 1000000 | 4140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
8312 | Water and Sewerage Management | Ngecha Water Project | To implement ngecha water project for access to clean water and environmental sustainability | Ngecha Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 371075 | 12.4 | 371075 | 374966 | 2628925 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8313 | Water and Sewerage Management | Ngondu Water project piping | To implement ngondu water project piping for access to clean water and environmental sustainability | Ngondu Water project piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8314 | Water and Sewerage Management | Piping and water tank at Boror Nairobi water project | To provide water distribution infrastructure at and water tank at Boror Nairobi water project | Water piping at and water tank at Boror Nairobi water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.25239, 35.833605 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1468319 | 73.4 | 1468319 | 1502917 | 531681 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Jitahidi enterprise. Assessor remarks: Good work.
8315 | Water and Sewerage Management | Pumps and piping at Ngecha B water project | To implement pumps and piping at ngecha b water project for access to clean water and environmental sustainability | Pumps and piping at Ngecha B water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | To be vired | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8316 | Water and Sewerage Management | Piping of Sumeek water project | To provide water distribution infrastructure at Sumeek water project | Water piping at Sumeek water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | To be vired | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495931 | 99.8 | 2495931 | 4069 | 4069 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
8317 | Water and Sewerage Management | Murindat water works | To implement murindat water works for access to clean water and environmental sustainability | Murindat water works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Murindat | -0.411137, 36.311427 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 584640 | 11.7 | 584640 | 597406 | 4415360 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not done. Viable: Yet to start. Assessor remarks: Not done.
8318 | Water and Sewerage Management | Upper Langa Langa extention water works | To implement upper langa langa extention water works for access to clean water and environmental sustainability | Upper Langa Langa extention water works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Murindat | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2001549 | 2001549 | 2001549 | Equitable | N/A | 2001549 | 0 | 1686296 | 84.2 | 1686296 | 2001549 | 315253 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8319 | Water and Sewerage Management | Construction of Kahuho water tank | To construct Kahuho water tank | Kahuho water tank constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.742074, 36.53051 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 208043 | 13.9 | 208043 | 208043 | 1291957 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
8320 | Water and Sewerage Management | Construction of Maraigushu water tank | To construct Maraigushu water tank | Maraigushu water tank constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.742074, 36.53051 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1364053 | 90.9 | 1364053 | 134595 | 135947 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
8321 | Water and Sewerage Management | Ihindu water project installation of solar panels | To implement ihindu water project installation of solar panels for access to clean water and environmental sustainability | Ihindu water project installation of solar panels completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.842147, 36.561961 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1522836 | 76.1 | 1522836 | 2000000 | 477164 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project was not done.
8322 | Water and Sewerage Management | piping of Sisioni water projects | To provide water distribution infrastructure at Sisioni water projects | Water piping at Sisioni water projects completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.883097, 36.565648 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 988356 | 988356 | 988356 | Equitable | N/A | 988356 | 0 | 972349 | 98.4 | 972349 | 988356 | 16007 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A Very good project with impact.
8323 | Water and Sewerage Management | Purchase of water tanks in kiambogo munyu area | To procure water tanks in kiambogo munyu area | Water tanks in kiambogo munyu area procured | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.867296, 36.535193 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996440 | 99.6 | 996440 | 1000000 | 3560 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
8324 | Water and Sewerage Management | Drilling of borehole for Sisioni water project | To provide access to clean water through borehole drilling at for Sisioni water project | Borehole drilled at for Sisioni water project | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.802878, 36.531191 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2022-23 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 319308 | 10 | 319308 | 319308 | 2880692 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: After drilling the water was not obtained.
8325 | Water and Sewerage Management | purchase and installation of pipes for Sisioni water project | To procure and install pipes for Sisioni water project | Pipes for Sisioni water project procured and installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.862662, 36.540468 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Require more funding for rericulation of pipes.
8326 | Water and Sewerage Management | Muguga Water Project-Piping at barnabas | To implement muguga water project-piping at barnabas for access to clean water and environmental sustainability | Muguga Water Project-Piping at barnabas completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | NAKURU EAST | -0.310242, 36.145721 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3493650 | 99.8 | 3493650 | 6350 | 6350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bonca investment⁷. Assessor remarks: Complete.
8327 | Water and Sewerage Management | Mzee Wanyama Water Project-Piping and distribution | To implement mzee wanyama water project-piping and distribution for access to clean water and environmental sustainability | Mzee Wanyama Water Project-Piping and distribution completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | NAKURU EAST | -0.36965, 36.149532 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3600343 | 3600343 | 3600343 | Equitable | N/A | 3600343 | 0 | 3575539 | 99.3 | 3575539 | 6350 | 24804 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dermerc ventures. Assessor remarks: Project ok.
8328 | Water and Sewerage Management | Borehole Testing | To implement borehole testing for access to clean water and environmental sustainability | Borehole Testing completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.433936 35.919127 2591.218994140625 3.7899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1339800 | 89.3 | 1339800 | 0 | 160200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds drilled borehole, constructed control panel, 100,000 litre water tank and water kiosk..
8329 | Water And Sewerage Management | Cheptoroi borehole installation of pump and construction of water tank and piping | To implement cheptoroi borehole installation of pump and construction of water tank and piping for access to clean water and environmental sustainability | Cheptoroi borehole installation of pump and construction of water tank and piping completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.368773, 35.897801 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1851471 | 92.6 | 1851471 | 148529 | 148529 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Pump has never been installed.
8330 | Water and Sewerage Management | construction of weir and piping of water from river kipkogo and construction of water tank at sigaon | To construct weir and piping of water from river kipkogo and construction of water tank at sigaon | Weir and piping of water from river kipkogo and construction of water tank at sigaon constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.402693 35.886069 2460.500244140625 6.163000106811523 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2624984 | 2624984 | 2624984 | Equitable | N/A | 2624984 | 0 | 2346377 | 89.4 | 2346377 | 278607 | 278607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project was vandalized and doesn't serve the residents as required. Fence not available.
8331 | Water and Sewerage Management | Construction of weir intake and fencing of Kware springs and Tarakwet spring | To construct weir intake and fencing of Kware springs and Tarakwet spring | Weir intake and fencing of Kware springs and Tarakwet spring constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.37894, 35.898381 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499867 | 100 | 499867 | 133 | 133 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was vandalized and human encroachment led to cutting of trees and volume of water has reduced..
8332 | Water and Sewerage Management | Drilling of Borehole at Tuei | To provide access to clean water through borehole drilling at Tuei | Borehole drilled at Tuei | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.362196, 35.871931 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2900000 | 2900000 | Equitable | N/A | 2900000 | 0 | 2567544 | 88.5 | 2567544 | 2900000 | 332456 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No, the volume of water is low. Assessor remarks: Water volume is low.
8333 | Water and Sewerage Management | Installation of pipes and construction of a water tank at Sigotik | To install pipes and construction of a water tank at Sigotik | Pipes and construction of a water tank at Sigotik installed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.357531 35.895056 2383.815673828125 5.058000087738037 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2499739 | 92.6 | 2499739 | 2700000 | 200261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
8334 | Water and Sewerage Management | Installation of pipes and construction of water kiosks Cheptoroi | To install pipes and construction of water kiosks Cheptoroi | Pipes and construction of water kiosks Cheptoroi installed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.357531 35.895056 2383.815673828125 5.058000087738037 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499739 | 100 | 2499739 | 262 | 261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
8335 | Water and Sewerage Management | Takitech borehole piping and construction of water kiosks | To implement takitech borehole piping and construction of water kiosks for access to clean water and environmental sustainability | Takitech borehole piping and construction of water kiosks completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.424694, 35.92853 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1878095 | 93.9 | 1878095 | 2000000 | 121905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds were used to construct 50M³ masonry water tank at Ruto's residence and piping done from the borehole to the water tank.
8336 | Water and Sewerage Management | Takitech borehole | To implement takitech borehole for access to clean water and environmental sustainability | Takitech borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.433936 35.919127 2591.218994140625 3.7899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5913775 | 98.6 | 5913775 | 4021803 | 86225 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds drilled borehole, constructed control panel, 100,000 litre water tank and water kiosk..
8337 | Water and Sewerage Management | design and construction of Tagitech water kiosk and piping | To design and construct Tagitech water kiosk and piping | Tagitech water kiosk and piping designed and constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4600000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1851471 | 168.3 | 1851471 | 1100000 | -751471 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
8338 | Water and Sewerage Management | construction of Rumwe tank | To construct Rumwe tank | Rumwe tank constructed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.33297, 35.946161 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1921270 | 96.1 | 1921270 | 78730 | 78730 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Slink supplier. Assessor remarks: Good work done.
8339 | Water and Sewerage Management | Construction of storage water tank in upper piane | To construct storage water tank in upper piane | Storage water tank in upper piane constructed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.337804, 35.993675 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998917 | 99.9 | 1998917 | 1000000 | 1083 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8340 | Water and Sewerage Management | Construction of water tank in njawatho | To construct water tank in njawatho | Water tank in njawatho constructed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.33297, 35.946161 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998917 | 99.9 | 1998917 | 2000000 | 1083 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Slink supplier. Assessor remarks: Good work done.
8341 | Water and Sewerage Management | Drilling and equipping of Jordan borehole | To implement drilling and equipping of jordan borehole for access to clean water and environmental sustainability | Drilling and equipping of Jordan borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.288202, 35.87854 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2025 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1843027 | 41 | 1843027 | 1872774 | 2656973 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Not available. Assessor remarks: Only drilling and lining done.
8342 | Water and Sewerage Management | Drilling and equipping of Njoro police post borehole | To implement drilling and equipping of njoro police post borehole for access to clean water and environmental sustainability | Drilling and equipping of Njoro police post borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.331744, 35.945973 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2649576 | 53 | 2649576 | 1350424 | 2350424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprise. Assessor remarks: Complete awaiting Jewathu piping.
8343 | Water and Sewerage Management | Drilling and equipping of rumwe farm borehole | To implement drilling and equipping of rumwe farm borehole for access to clean water and environmental sustainability | Drilling and equipping of rumwe farm borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.341093, 35.951532 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1843027 | 36.9 | 1843027 | 5000000 | 3156973 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sagit global Ltd. Assessor remarks: Good work.
8344 | Water and Sewerage Management | Drilling of borehole in kamwango/kenana | To provide access to clean water through borehole drilling at kamwango/kenana | Borehole drilled at kamwango/kenana | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998170 | 99.9 | 2998170 | 3000000 | 1830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8345 | Water and Sewerage Management | Drilling of Eriithia water borehole | To implement drilling of eriithia water borehole for access to clean water and environmental sustainability | Drilling of Eriithia water borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999690 | 100 | 2999690 | 2999690 | 310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8346 | Water and Sewerage Management | Equipping and piping of Njokerio Borehole | To equip and piping of Njokerio Borehole with necessary facilities and equipment | And piping of Njokerio Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 611390 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
8347 | Water and Sewerage Management | Equipping of Natu Borehole | To equip Natu Borehole with necessary facilities and equipment | Natu Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.338884, 36.004589 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 305611 | 23.5 | 305611 | 305611 | 994389 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Trizah logistics. Assessor remarks: In good state.
8348 | Water and Sewerage Management | Equipping of Piave Borehole | To equip Piave Borehole with necessary facilities and equipment | Piave Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.336684, 35.995746 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1298950 | 99.9 | 1298950 | 1298950 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprises. Assessor remarks: Good work.
8349 | Water and Sewerage Management | Kamwayo Water Project - Piping of kamwayo water project | To implement kamwayo water project - piping of kamwayo water project for access to clean water and environmental sustainability | Kamwayo Water Project - Piping of kamwayo water project completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998568 | 99.9 | 1998568 | 1433 | 1432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8350 | Water and Sewerage Management | Kosoa water projects in kamwaura | To implement kosoa water projects in kamwaura for access to clean water and environmental sustainability | Kosoa water projects in kamwaura completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.286075, 35.861546 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 4677917 | 4677917 | 4677917 | Equitable | N/A | 4677917 | 0 | 4650499 | 99.4 | 4650499 | 27418 | 27418 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8351 | Water and Sewerage Management | Piave water project | To implement piave water project for access to clean water and environmental sustainability | Piave water project completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.332133, 35.945717 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999325 | 100 | 2999325 | 1000000 | 675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Live World Enterprise. Assessor remarks: Work incomplete.
8352 | Water and Sewerage Management | piping of Jawatho water project | To provide water distribution infrastructure at Jawatho water project | Water piping at Jawatho water project completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.332133, 35.945717 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990000 | 99 | 990000 | 1000000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Live World Enterprise. Assessor remarks: Work incomplete.
8353 | Water and Sewerage Management | Water piping at Eriithia borehole, Mwigito , Njokerio water projects | To implement water piping at eriithia borehole, mwigito , njokerio water projects for access to clean water and environmental sustainability | Water piping at Eriithia borehole, Mwigito , Njokerio water projects completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.394635, 35.922432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2014 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Fair work.
8354 | Water and Sewerage Management | Water works for Njoro ward | To implement water works for njoro ward for access to clean water and environmental sustainability | Water works for Njoro ward completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.32681 35.940695 2151.900146484375 5.441999912261963 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Samues merchants. Assessor remarks: In good state.
8355 | Water and Sewerage Management | Additional funding for Borehole Drilling and Piping at Lulukwet Water Project | To implement additional funding for borehole drilling and piping at lulukwet water project for access to clean water and environmental sustainability | Additional funding for Borehole Drilling and Piping at Lulukwet Water Project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.37308 35.677892 2768.6 5.099999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 600044 | 30 | 600044 | 2000000 | 1399956 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
8356 | Water and Sewerage Management | Chesirikwa Water works | To implement chesirikwa water works for access to clean water and environmental sustainability | Chesirikwa Water works completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 947630 | 94.8 | 947630 | 52370 | 52370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
8357 | Water and Sewerage Management | Drilling, equipping and piping of Seguton/Langwenda water project | To implement drilling, equipping and piping of seguton/langwenda water project for access to clean water and environmental sustainability | Drilling, equipping and piping of Seguton/Langwenda water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.37308 35.677892 2768.6 5.099999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4250000 | 4250000 | 4250000 | Equitable | N/A | 4250000 | 0 | 1250794 | 29.4 | 1250794 | 1250794 | 2999206 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
8358 | Water and Sewerage Management | Kuresoi Water Project - Drilling of Borehole | To implement kuresoi water project - drilling of borehole for access to clean water and environmental sustainability | Kuresoi Water Project - Drilling of Borehole completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.41092 35.65578 2673.7 19 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 2235726 | 203.2 | 2235726 | 1100000 | -1135726 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good. Pump needs repairs..
8359 | Water and Sewerage Management | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) | To implement ongoing temoyotta water project pumping unit, pump house, tank renovation piping and power connection) for access to clean water and environmental sustainability | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2479793.48 | 2479793.48 | 2479793.48 | Equitable | N/A | 2479793.48 | 0 | 0 | 0 | 0 | 2479793 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8360 | Water and Sewerage Management | Tarakwa Water Works | To implement tarakwa water works for access to clean water and environmental sustainability | Tarakwa Water Works completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3750000 | 3750000 | 3750000 | Equitable | N/A | 3750000 | 0 | 1307423 | 34.9 | 1307423 | 1307423 | 2442577 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
8361 | Water and Sewerage Management | Construction of Kahuho water tank | To construct Kahuho water tank | Kahuho water tank constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.742074, 36.53051 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 208043 | 13.9 | 208043 | 208043 | 1291957 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
8362 | Water and Sewerage Management | Construction of Maraigushu water tank | To construct Maraigushu water tank | Maraigushu water tank constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.742074, 36.53051 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1500000 | 1499866 | 1499866 | Equitable | N/A | 1499866 | 0 | 1364053 | 90.9 | 1364053 | 134595 | 135813 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
8363 | Water and Sewerage Management | Ihindu water project installation of pump and solar panels | To implement ihindu water project installation of pump and solar panels for access to clean water and environmental sustainability | Ihindu water project installation of pump and solar panels completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.842147, 36.561961 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1522836 | 76.1 | 1522836 | 2000000 | 477164 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project was not done.
8364 | Water and Sewerage Management | piping of Sisioni water projects | To provide water distribution infrastructure at Sisioni water projects | Water piping at Sisioni water projects completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.883097, 36.565648 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 988356 | 988356 | 988356 | Equitable | N/A | 988356 | 0 | 972349 | 98.4 | 972349 | 988356 | 16007 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A Very good project with impact.
8365 | Water and Sewerage Management | Purchase of 4" and 2.5" water pipes for kiambogo munyu area | To procure 4" and 2.5" water pipes for kiambogo munyu area | 4" and 2.5" water pipes for kiambogo munyu area procured | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.844545 36.545487 2469.2000000000003 5.400000095367432 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996440 | 99.6 | 996440 | 1000000 | 3560 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2023. Assessor remarks: Supplied 1 inch pipes.
8366 | Water and Sewerage Management | Supply of 2.5 inch pipes for sision water | To implement supply of 2.5 inch pipes for sision water for access to clean water and environmental sustainability | Supply of 2.5 inch pipes for sision water completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.867345 36.535489 2460 5.611999988555908 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 479590 | 95.9 | 479590 | 500000 | 20410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project combine with another project to construct mateenity.
8367 | Water and Sewerage Management | Supply of 4 inch HDPE pipes for maraigushu water project | To implement supply of 4 inch hdpe pipes for maraigushu water project for access to clean water and environmental sustainability | Supply of 4 inch HDPE pipes for maraigushu water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.791159, 36.542467 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 334725 | 66.9 | 334725 | 500000 | 165275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8368 | Water and Sewerage Management | Drilling of borehole for Sisioni water project | To provide access to clean water through borehole drilling at for Sisioni water project | Borehole drilled at for Sisioni water project | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.802878, 36.531191 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2022-23 | 3200000 | 319308 | 319308 | Equitable | N/A | 319308 | 0 | 319308 | 100 | 319308 | 319308 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: After drilling the water was not obtained.
8369 | Water and Sewerage Management | purchase and installation of pipes for Sisioni water project | To procure and install pipes for Sisioni water project | Pipes for Sisioni water project procured and installed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.862662, 36.540468 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Require more funding for rericulation of pipes.
8370 | Water and Sewerage Management | Muguga Water Project-Piping at barnabas | To implement muguga water project-piping at barnabas for access to clean water and environmental sustainability | Muguga Water Project-Piping at barnabas completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Nakuru East | -0.310242, 36.145721 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3493650 | 99.8 | 3493650 | 6350 | 6350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bonca investment⁷. Assessor remarks: Complete.
8371 | Water And Sewerage Management | Cheptoroi borehole installation of pump and construction of water tank and piping | To implement cheptoroi borehole installation of pump and construction of water tank and piping for access to clean water and environmental sustainability | Cheptoroi borehole installation of pump and construction of water tank and piping completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.368773, 35.897801 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1851471 | 92.6 | 1851471 | 148529 | 148529 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Pump has never been installed.
8372 | Water and Sewerage Management | construction of weir and piping of water from river kipkogo and construction of water tank at sigaon | To construct weir and piping of water from river kipkogo and construction of water tank at sigaon | Weir and piping of water from river kipkogo and construction of water tank at sigaon constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.402693 35.886069 2460.500244140625 6.163000106811523 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2624984 | 2624984 | 2624984 | Equitable | N/A | 2624984 | 0 | 2346377 | 89.4 | 2346377 | 278607 | 278607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project was vandalized and doesn't serve the residents as required. Fence not available.
8373 | Water and Sewerage Management | Construction of weir intake and fencing of Kware springs and Tarakwet spring | To construct weir intake and fencing of Kware springs and Tarakwet spring | Weir intake and fencing of Kware springs and Tarakwet spring constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.37894, 35.898381 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499867 | 100 | 499867 | 133 | 133 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was vandalized and human encroachment led to cutting of trees and volume of water has reduced..
8374 | Water and Sewerage Management | Drilling of Borehole at Tuei | To provide access to clean water through borehole drilling at Tuei | Borehole drilled at Tuei | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.362196, 35.871931 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2900000 | 2900000 | Equitable | N/A | 2900000 | 0 | 2567544 | 88.5 | 2567544 | 2900000 | 332456 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No, the volume of water is low. Assessor remarks: Water volume is low.
8375 | Water and Sewerage Management | Installation of pipes and construction of a water tank at Sigotik | To install pipes and construction of a water tank at Sigotik | Pipes and construction of a water tank at Sigotik installed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2499739 | 92.6 | 2499739 | 2700000 | 200261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
8376 | Water and Sewerage Management | Installation of pipes and construction of water kiosks Cheptoroi | To install pipes and construction of water kiosks Cheptoroi | Pipes and construction of water kiosks Cheptoroi installed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499739 | 100 | 2499739 | 262 | 261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
8377 | Water and Sewerage Management | Piping and construction of a tank at Amani and Majimoto | To provide water distribution infrastructure at and construction of a tank at Amani and Majimoto | Water piping at and construction of a tank at Amani and Majimoto completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1775816 | 1775816 | 1775816 | Equitable | N/A | 1775816 | 0 | 3692602 | 207.9 | 3692602 | 1775816 | -1916786 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
8378 | Water and Sewerage Management | Piping, construction of water kiosk and tank at Sigotik | To implement piping, construction of water kiosk and tank at sigotik for access to clean water and environmental sustainability | Piping, construction of water kiosk and tank at Sigotik completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1272459 | 1272459 | 1272459 | Equitable | N/A | 1272459 | 0 | 1878095 | 147.6 | 1878095 | 1272459 | -605636 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
8379 | Water and Sewerage Management | Takitech borehole piping and construction of water kiosks | To implement takitech borehole piping and construction of water kiosks for access to clean water and environmental sustainability | Takitech borehole piping and construction of water kiosks completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.424694, 35.92853 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1878095 | 93.9 | 1878095 | 2000000 | 121905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds were used to construct 50M³ masonry water tank at Ruto's residence and piping done from the borehole to the water tank.
8380 | Water and Sewerage Management | design and construction of Tagitech water kiosk and piping | To design and construct Tagitech water kiosk and piping | Tagitech water kiosk and piping designed and constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4600000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1851471 | 168.3 | 1851471 | 1100000 | -751471 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
8381 | Water and Sewerage Management | construction of Rumwe tank | To construct Rumwe tank | Rumwe tank constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.33297, 35.946161 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1921270 | 96.1 | 1921270 | 78730 | 78730 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Slink supplier. Assessor remarks: Good work done.
8382 | Water and Sewerage Management | Construction of storage water tank in upper piane | To construct storage water tank in upper piane | Storage water tank in upper piane constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.337804, 35.993675 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998917 | 99.9 | 1998917 | 1000000 | 1083 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8383 | Water and Sewerage Management | distillation and expansion of Piave dams | To implement distillation and expansion of piave dams for access to clean water and environmental sustainability | distillation and expansion of Piave dams completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.332084 35.954071 2142.400146484375 15.730999946594238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3388870 | 99.7 | 3388870 | 3400000 | 11130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch designers. Assessor remarks: Well done understaking.
8384 | Water and Sewerage Management | Drilling and equipping of Jordan borehole | To implement drilling and equipping of jordan borehole for access to clean water and environmental sustainability | Drilling and equipping of Jordan borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.288202, 35.87854 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2025 | 4500000 | 1872774 | 1872774 | Equitable | N/A | 1872774 | 0 | 1843027 | 98.4 | 1843027 | 1872774 | 29747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Not available. Assessor remarks: Only drilling and lining done.
8385 | Water and Sewerage Management | Drilling and equipping of Njoro police post borehole | To implement drilling and equipping of njoro police post borehole for access to clean water and environmental sustainability | Drilling and equipping of Njoro police post borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.331744, 35.945973 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 2350423.7 | 2350423.7 | Equitable | N/A | 2350423.7 | 0 | 2649576 | 112.7 | 2649576 | 1350424 | -299152.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprise. Assessor remarks: Complete awaiting Jewathu piping.
8386 | Water and Sewerage Management | drilling of borehole at Piave / Kahuho sub location | To provide access to clean water through borehole drilling at Piave / Kahuho sub location | Borehole drilled at Piave / Kahuho sub location | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.340825 35.994282 2020.162841796875 20 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Not available. Assessor remarks: Nothing done yet on the ground.
8387 | Water and Sewerage Management | Drilling of borehole in kamwango/kenana | To provide access to clean water through borehole drilling at kamwango/kenana | Borehole drilled at kamwango/kenana | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998170 | 99.9 | 2998170 | 3000000 | 1830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8388 | Water and Sewerage Management | Drilling of Eriithia water borehole | To implement drilling of eriithia water borehole for access to clean water and environmental sustainability | Drilling of Eriithia water borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2999690 | 2999690 | Equitable | N/A | 2999690 | 0 | 2999690 | 100 | 2999690 | 2999690 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8389 | Water and Sewerage Management | Equipping of Natu Borehole | To equip Natu Borehole with necessary facilities and equipment | Natu Borehole equipped | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.338884, 36.004589 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 305611 | 23.5 | 305611 | 305611 | 994389 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Trizah logistics. Assessor remarks: In good state.
8390 | Water and Sewerage Management | Equipping of Piave Borehole | To equip Piave Borehole with necessary facilities and equipment | Piave Borehole equipped | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.336684, 35.995746 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1298950 | 1298950 | Equitable | N/A | 1298950 | 0 | 1298950 | 100 | 1298950 | 1298950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprises. Assessor remarks: Good work.
8391 | Water and Sewerage Management | Kamwayo Water Project - Piping of kamwayo water project | To implement kamwayo water project - piping of kamwayo water project for access to clean water and environmental sustainability | Kamwayo Water Project - Piping of kamwayo water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998568 | 99.9 | 1998568 | 1433 | 1432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8392 | Water and Sewerage Management | Kosoa water projects in kamwaura | To implement kosoa water projects in kamwaura for access to clean water and environmental sustainability | Kosoa water projects in kamwaura completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.286075, 35.861546 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 4677917 | 4677917 | 4677917 | Equitable | N/A | 4677917 | 0 | 4650499 | 99.4 | 4650499 | 27418 | 27418 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8393 | Water and Sewerage Management | Njoro water works | To implement njoro water works for access to clean water and environmental sustainability | Njoro water works completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.367753 35.97066 2090.9 9.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2494389 | 49.9 | 2494389 | 2500000 | 2505611 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: yes but has issues. Contractor: na. Assessor remarks: work done.
8394 | Water and Sewerage Management | piping of Jawatho water project | To provide water distribution infrastructure at Jawatho water project | Water piping at Jawatho water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.332133, 35.945717 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990000 | 99 | 990000 | 1000000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Live World Enterprise. Assessor remarks: Work incomplete.
8395 | Water and Sewerage Management | supply of pipes to Piave borehole | To implement supply of pipes to piave borehole for access to clean water and environmental sustainability | supply of pipes to Piave borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.336684, 35.995746 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprises. Assessor remarks: Good work.
8396 | Water and Sewerage Management | Supply of water pipes in sociot | To implement supply of water pipes in sociot for access to clean water and environmental sustainability | Supply of water pipes in sociot completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990098 | 99 | 990098 | 1000000 | 9902 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
8397 | Water and Sewerage Management | Additional fund for Nyota water works | To implement additional fund for nyota water works for access to clean water and environmental sustainability | Additional fund for Nyota water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.355807 35.688607 2814.6 13.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1141646 | 1141646 | 1141646 | Equitable | N/A | 1141646 | 0 | 1141646 | 100 | 1141646 | 1141646 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: CEDER RED INVESTMENTS LTD.. Assessor remarks: Done to Completion.
8398 | Water and Sewerage Management | Chesirikwa Water works | To implement chesirikwa water works for access to clean water and environmental sustainability | Chesirikwa Water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 947630 | 94.8 | 947630 | 52370 | 52370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
8399 | Water and Sewerage Management | Drilling, equipping and piping of Seguton/Langwenda water project | To implement drilling, equipping and piping of seguton/langwenda water project for access to clean water and environmental sustainability | Drilling, equipping and piping of Seguton/Langwenda water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.37308 35.677892 2768.6 5.099999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4250000 | 4250000 | 4250000 | Equitable | N/A | 4250000 | 0 | 1250794 | 29.4 | 1250794 | 1250794 | 2999206 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
8400 | Water and Sewerage Management | Drilling of borehole at Lulukwet Water Project | To provide access to clean water through borehole drilling at Lulukwet Water Project | Borehole drilled at Lulukwet Water Project | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.301275, 35.542787 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 850089 | 27.4 | 850089 | 850089 | 2249911 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, well done.
8401 | Water and Sewerage Management | Nyota ward water works | To implement nyota ward water works for access to clean water and environmental sustainability | Nyota ward water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 4200000 | 4200000 | 4200000 | Equitable | N/A | 4200000 | 0 | 539914 | 12.9 | 539914 | 653853 | 3660086 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
8402 | Water and Sewerage Management | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) | To implement ongoing temoyotta water project pumping unit, pump house, tank renovation piping and power connection) for access to clean water and environmental sustainability | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2479793.48 | 2479793.48 | 2479793.48 | Equitable | N/A | 2479793.48 | 0 | 0 | 0 | 0 | 2479793 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8403 | Water and Sewerage Management | Tarakwa Water Works | To implement tarakwa water works for access to clean water and environmental sustainability | Tarakwa Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3750000 | 3750000 | 3750000 | Equitable | N/A | 3750000 | 0 | 1307423 | 34.9 | 1307423 | 1307423 | 2442577 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
8404 | Water and Sewerage Management | Drilling of borehole and casing at Sher Moi ECDE | To provide access to clean water through borehole drilling at and casing at Sher Moi ECDE | Borehole drilled at and casing at Sher Moi ECDE | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | -0.817132 36.32586 1922.199951171875 24.67099952697754 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
8405 | Water and Sewerage Management | piping and installation of tank at kamere beach | To provide water distribution infrastructure at and installation of tank at kamere beach | Water piping at and installation of tank at kamere beach completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1899987 | 63.3 | 1899987 | 3000000 | 1100013 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
8406 | Water and Sewerage Management | Sher academy water tank - installation of a water tank at sher academy | To implement sher academy water tank - installation of a water tank at sher academy for access to clean water and environmental sustainability | Sher academy water tank - installation of a water tank at sher academy completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | 0.837016, 36.366272 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2410512 | 80.4 | 2410512 | 2988940 | 589488 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Ni it was not done. Assessor remarks: Yet to start.
8407 | Water and Sewerage Management | piping and installation of tank at kamere beach | To provide water distribution infrastructure at and installation of tank at kamere beach | Water piping at and installation of tank at kamere beach completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1899987 | 63.3 | 1899987 | 3000000 | 1100013 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
8408 | Water and Sewerage Management | Purchase and installation of water gutters for water harvesting | To procure and install water gutters for water harvesting | Water gutters for water harvesting procured and installed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 828280 | 828280 | 828280 | Equitable | N/A | 828280 | 0 | 0 | 0 | 0 | 828280 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
8409 | Water and Sewerage Management | Sher academy water tank - installation of a water tank at sher academy | To implement sher academy water tank - installation of a water tank at sher academy for access to clean water and environmental sustainability | Sher academy water tank - installation of a water tank at sher academy completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.837016, 36.366272 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2988940 | 2988940 | Equitable | N/A | 2988940 | 0 | 2410512 | 80.6 | 2410512 | 2988940 | 578428 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Ni it was not done. Assessor remarks: Yet to start.
8410 | Water and Sewerage Management | Rhonda Sewage Construction - Construction at Mwariki, Pembe mbili | To implement rhonda sewage construction - construction at mwariki, pembe mbili for access to clean water and environmental sustainability | Rhonda Sewage Construction - Construction at Mwariki, Pembe mbili completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | RHONDA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3963197 | 99.1 | 3963197 | 0 | 36803 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8411 | Water and Sewerage Management | Piping and distribution of water in Sirikwa | To provide water distribution infrastructure at water in Sirikwa | Water piping at water in Sirikwa completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | SIRIKWA | -0.283492, 35.673157 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997851 | 99.9 | 2997851 | 3000000 | 2149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank needs fencing, enhance distribution to all the villages.
8412 | Water and Sewerage Management | Sirikwa water works | To implement sirikwa water works for access to clean water and environmental sustainability | Sirikwa water works completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | SIRIKWA | -0.278173, 35.660898 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 119848 | 1.2 | 119848 | 119848 | 9880152 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use and members of the public get their water here, more piping needed to reach more households.
8413 | Water and Sewerage Management | Sirikwa water project - Design and construction of tank, Piping and distribution | To implement sirikwa water project - design and construction of tank, piping and distribution for access to clean water and environmental sustainability | Sirikwa water project - Design and construction of tank, Piping and distribution completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | SIRIKWA | -0.297153, 35.629421 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 3262001 | 32.6 | 3262001 | 592903 | 6737999 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,but it has not meet the needs of the residents, money needs to be allocated for water source. Assessor remarks: Project is not operational the source has high water turbidity,the tank nèeds to be fenced to secure it,,.
8414 | Water and Sewerage Management | Construction of Lomolo Borehole and piping | To construct Lomolo Borehole and piping | Lomolo Borehole and piping constructed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | 0.018446, 36.032083 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2671062 | 2671062 | 2671062 | Equitable | N/A | 2671062 | 0 | 0 | 0 | 0 | 2671062 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working q.
8415 | Water and Sewerage Management | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita | To implement soin ward water projects - drilling of morop borehole and kokwomoi borehole and water works at testai / banita for access to clean water and environmental sustainability | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | -0.062307, 36.062092 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 11400000 | 3185550 | 3185550 | Equitable | N/A | 3185550 | 0 | 2851216 | 89.5 | 2851216 | 334334 | 334334 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water in use.
8416 | Water and Sewerage Management | Soin water works - Kabarnet farm Water Works, Kipsyenan Water Works, Athinai sub location water works, Morop water works | To implement soin water works - kabarnet farm water works, kipsyenan water works, athinai sub location water works, morop water works for access to clean water and environmental sustainability | Soin water works - Kabarnet farm Water Works, Kipsyenan Water Works, Athinai sub location water works, Morop water works completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | -0.097772 35.930847 1669.8000000000002 3.5999999046325684 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 12247823 | 9847823 | 9847823 | Equitable | N/A | 9847823 | 0 | 1890733 | 19.2 | 1890733 | 2010266 | 7957090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bikon Engineering. Assessor remarks: Residents are grateful.
8417 | Water and Sewerage Management | Barafu Water Project - Expansion of Intake and piping | To implement barafu water project - expansion of intake and piping for access to clean water and environmental sustainability | Barafu Water Project - Expansion of Intake and piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.044788, 36.171572 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | September 2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194431 | 99.5 | 1194431 | 2298889 | 5569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ekay contractors and General supplies. Assessor remarks: Functional.
8418 | Water and Sewerage Management | Construction of Chemarmar Water trough | To construct Chemarmar Water trough | Chemarmar Water trough constructed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.069247, 36.177572 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 449948 | 90 | 449948 | 500000 | 50052 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
8419 | Water and Sewerage Management | Construction of Ewani Water tank and piping | To construct Ewani Water tank and piping | Ewani Water tank and piping constructed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.069247, 36.177572 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999760 | 100 | 2999760 | 2999760 | 240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
8420 | Water and Sewerage Management | Drilling and capping of Arutani Borehole | To implement drilling and capping of arutani borehole for access to clean water and environmental sustainability | Drilling and capping of Arutani Borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | -0.074664, 36.115103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499685 | 100 | 2499685 | 2500000 | 315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8421 | Water and Sewerage Management | Drilling and equipping of Chemassis Borehole | To implement drilling and equipping of chemassis borehole for access to clean water and environmental sustainability | Drilling and equipping of Chemassis Borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5471976 | 5471976 | 5471976 | Equitable | N/A | 5471976 | 0 | 2899355 | 53 | 2899355 | 2900291 | 2572621 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8422 | Water and Sewerage Management | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project | To implement lower solai water project - construction of water reservoir and piping of lower solai water project for access to clean water and environmental sustainability | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.097788, 36.178758 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 630663 | 9 | 630663 | 631107 | 6369337 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8423 | Water and Sewerage Management | Ngendaptich tuiyotich water project piping | To implement ngendaptich tuiyotich water project piping for access to clean water and environmental sustainability | Ngendaptich tuiyotich water project piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.04618, 36.140841 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1260630 | 63 | 1260630 | 739370 | 739370 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8424 | Water and Sewerage Management | Nyamamithi water project - Drilling of borehole and Installation of pump | To implement nyamamithi water project - drilling of borehole and installation of pump for access to clean water and environmental sustainability | Nyamamithi water project - Drilling of borehole and Installation of pump completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.113312, 36.222792 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2045996 | 51.1 | 2045996 | 2056072 | 1954004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8425 | Water and Sewerage Management | purchase and installation of water pipes of Ewani water project | To procure and install water pipes of Ewani water project | Water pipes of Ewani water project procured and installed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | -0.060176 36.104307 1695.93603515625 15.730999946594238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499801 | 100 | 3499801 | 3500000 | 199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Stalled.
8426 | Water and Sewerage Management | Sigito water project - piping | To implement sigito water project - piping for access to clean water and environmental sustainability | Sigito water project - piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.04618, 36.140841 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998215 | 99.8 | 998215 | 1000000 | 1785 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8427 | Water and Sewerage Management | Supply of Water pipes to KaMosop Water project | To implement supply of water pipes to kamosop water project for access to clean water and environmental sustainability | Supply of Water pipes to KaMosop Water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.161156, 36.165684 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499975 | 100 | 499975 | 2700 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Pipes have not been laid though they have been delivered.
8428 | Water and Sewerage Management | Supply of Water pipes to Sigito/Murram Water project | To implement supply of water pipes to sigito/murram water project for access to clean water and environmental sustainability | Supply of Water pipes to Sigito/Murram Water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.023174 36.146624 1550.736083984375 9.659000396728516 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497300 | 99.5 | 497300 | 2700 | 2700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8429 | Water and Sewerage Management | Completion of lower Solai water project | To complete lower Solai water project | Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.18324 36.184717 1648.8 7.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3491285 | 87.3 | 3491285 | 508715 | 508715 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8430 | Water and Sewerage Management | Piping of Sigito water project | To provide water distribution infrastructure at Sigito water project | Water piping at Sigito water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.11082 36.218 1789.6 15.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997984 | 99.9 | 1997984 | 1000000 | 2016 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8431 | Water and Sewerage Management | Rehabilitation of Chemasis water project | To rehabilitate Chemasis water project to restore functionality | Chemasis water project rehabilitated | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | -0.010666 36.166707 1752.446044921875 37.472999572753906 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1075924 | 1075924 | Equitable | N/A | 1075924 | 0 | 1069046 | 99.4 | 1069046 | 1000000 | 6878 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8432 | Water and Sewerage Management | construction of 2 water tanks at the Shrine | To construct 2 water tanks at the Shrine | 2 water tanks at the Shrine constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.024925 36.251015 2248.60009765625 4 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1253078 | 83.5 | 1253078 | 1253078 | 246922 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, community enjoying access to clean water.. Viable: Yes. Contractor: Details not provided. Assessor remarks: Water tanks constructed and piping done.
8433 | Water and Sewerage Management | Construction of Gituamba Kianoe (Nguba farm) water Tank | To construct Gituamba Kianoe (Nguba farm) water Tank | Gituamba Kianoe (Nguba farm) water Tank constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.004125 36.219987 1997.199951171875 8.61400032043457 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198895 | 99.9 | 1198895 | 1200000 | 1105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes.. Contractor: Information not available. Assessor remarks: Water tank in good condition.
8434 | Water and Sewerage Management | Construction of tank and piping of Araki water project | To construct tank and piping of Araki water project | Tank and piping of Araki water project constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.025943, 36.229345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2483954 | 99.4 | 2483954 | 2500000 | 16046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Yes.
8435 | Water and Sewerage Management | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project | To implement drilling of borehole, installation of pump and solar panels and piping of subukia valley water project for access to clean water and environmental sustainability | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.040933 36.220476 2150.7001953125 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 4245277 | 4245277 | Equitable | N/A | 4245277 | 0 | 1658854 | 39.1 | 1658854 | 1658854 | 2586423 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
8436 | Water and Sewerage Management | Drilling of Tetu Kirima Kibugi borehole | To implement drilling of tetu kirima kibugi borehole for access to clean water and environmental sustainability | Drilling of Tetu Kirima Kibugi borehole completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.04678 36.170557 2107.6 2.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3996217 | 2996217 | 2996217 | Equitable | N/A | 2996217 | 0 | 3661174 | 122.2 | 3661174 | 2000000 | -664957 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
8437 | Water and Sewerage Management | Gatundu water piping | To implement gatundu water piping for access to clean water and environmental sustainability | Gatundu water piping completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.02504, 36.175968 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 197095 | 98.5 | 197095 | 2905 | 2905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Completed and is in good working condition.
8438 | Water and Sewerage Management | Gawasu water project - purchase and installation of solar panels | To implement gawasu water project - purchase and installation of solar panels for access to clean water and environmental sustainability | Gawasu water project - purchase and installation of solar panels completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.040933 36.220476 2150.7001953125 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1999888 | 133.3 | 1999888 | 1500000 | -499888 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
8439 | Water and Sewerage Management | installation of water pipes at ACK Munanda water | To install water pipes at ACK Munanda water | Water pipes at ACK Munanda water installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.042368, 36.190708 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2918/2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494803 | 99 | 494803 | 500000 | 5197 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water Supply to the local community provided and functional.
8440 | Water and Sewerage Management | Miloreni water women | To implement miloreni water women for access to clean water and environmental sustainability | Miloreni water women completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.030765 36.234948 2103.5849609375 9.105999946594238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2993702 | 2993702 | 2993702 | Equitable | N/A | 2993702 | 0 | 0 | 0 | 0 | 2993702 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Sure the water serves the community.. Contractor: Information not available. Assessor remarks: Good work.
8441 | Water and Sewerage Management | Piping, purchase and installation of solar panels subukia valley borehole | To implement piping, purchase and installation of solar panels subukia valley borehole for access to clean water and environmental sustainability | Piping, purchase and installation of solar panels subukia valley borehole completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.040933 36.220476 2150.7001953125 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 643491 | 29.2 | 643491 | 1556509 | 1556509 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
8442 | Water and Sewerage Management | Purchase and installation of Edgewood Borehole Solar Panels | To procure and install Edgewood Borehole Solar Panels | Edgewood Borehole Solar Panels procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.017333, 36.198352 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 11/03/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996662 | 99.8 | 1996662 | 2000000 | 3338 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes the project was successful.. Contractor: Information not available. Assessor remarks: Good work with the panels.
8443 | Water and Sewerage Management | Purchase and installation of Morro borehole Solar Panels | To procure and install Morro borehole Solar Panels | Morro borehole Solar Panels procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | 0.007778, 36.223232 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999888 | 100 | 1999888 | 112 | 112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the borehole.
8444 | Water and Sewerage Management | purchase and installation of water pump, solar panels and construction of water tank for Arash B Kirima borehole | To procure and install water pump, solar panels and construction of water tank for Arash B Kirima borehole | Water pump, solar panels and construction of water tank for Arash B Kirima borehole procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 5245277 | 5245277 | Equitable | N/A | 5245277 | 0 | 2734410 | 52.1 | 2734410 | 2510867 | 2510867 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
8445 | Water and Sewerage Management | purchase and installation of water pump, solar pannels and piping for Arash A Mutito mumui water projects | To procure and install water pump, solar pannels and piping for Arash A Mutito mumui water projects | Water pump, solar pannels and piping for Arash A Mutito mumui water projects procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1999999 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966642 | 98.9 | 2966642 | 3000000 | 33358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
8446 | Water and Sewerage Management | purchase of Hydrum pump for Gatongu water project (GAWASU) | To procure Hydrum pump for Gatongu water project (GAWASU) | Hydrum pump for Gatongu water project (GAWASU) procured | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | 0.007568 36.223208 2011.8999999999999 7.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2997632 | 199.8 | 2997632 | 1500000 | -1497632 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the boreho.
8447 | Water and Sewerage Management | Quarry water project Subukia town | To implement quarry water project subukia town for access to clean water and environmental sustainability | Quarry water project Subukia town completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.006327, 36.23532 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2500000 | 62.5 | 2500000 | 4000000 | 1500000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further measures to be taken due to tank not having water.
8448 | Water and Sewerage Management | repair of tank at Gathima Kirengero | To rehabilitate tank at Gathima Kirengero to restore functionality | Tank at Gathima Kirengero rehabilitated | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.030926 36.197107 2206.2999999999997 30 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 299999 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The school has only one ECDE classroom, without a toilet. Toilet URGENTLY needed.
8449 | Water and Sewerage Management | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects | To implement subukia ward water works - construction of water intake, purchase of land and piping at kware subukia town water projects for access to clean water and environmental sustainability | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.006257, 36.23544 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 12/12/2019 | 4000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999876 | 100 | 1999876 | 1999876 | 124 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.. Contractor: Information not known. Assessor remarks: The water tank is in good condition.
8450 | Water and Sewerage Management | Piping and distribution of water in Sirikwa | To provide water distribution infrastructure at water in Sirikwa | Water piping at water in Sirikwa completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.283492, 35.673157 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997851 | 99.9 | 2997851 | 3000000 | 2149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank needs fencing, enhance distribution to all the villages.
8451 | Water and Sewerage Management | Sirikwa water works | To implement sirikwa water works for access to clean water and environmental sustainability | Sirikwa water works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.278173, 35.660898 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2019/20 | 2019/20 | 10000000 | 4193771 | 4193771 | Equitable | N/A | 4193771 | 0 | 119848 | 2.9 | 119848 | 119848 | 4073923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use and members of the public get their water here, more piping needed to reach more households.
8452 | Water and Sewerage Management | Sirikwa water project - Design and construction of tank, Piping and distribution | To implement sirikwa water project - design and construction of tank, piping and distribution for access to clean water and environmental sustainability | Sirikwa water project - Design and construction of tank, Piping and distribution completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.297153, 35.629421 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 10000000 | 7754897.1 | 7754897.1 | Equitable | N/A | 7754897.1 | 0 | 3262001 | 42.1 | 3262001 | 592903 | 4492896.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,but it has not meet the needs of the residents, money needs to be allocated for water source. Assessor remarks: Project is not operational the source has high water turbidity,the tank nèeds to be fenced to secure it,,.
8453 | Water and Sewerage Management | Athinai sub location water works | To implement athinai sub location water works for access to clean water and environmental sustainability | Athinai sub location water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.008958, 36.039238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | FY 2023 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1786812 | 99.3 | 1786812 | 1800000 | 13188 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping needs extension.
8454 | Water and Sewerage Management | Construction of Lomolo Borehole and piping | To construct Lomolo Borehole and piping | Lomolo Borehole and piping constructed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | 0.018446, 36.032083 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2671062 | 2671062 | 2671062 | Equitable | N/A | 2671062 | 0 | 0 | 0 | 0 | 2671062 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working q.
8455 | Water and Sewerage Management | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita | To implement soin ward water projects - drilling of morop borehole and kokwomoi borehole and water works at testai / banita for access to clean water and environmental sustainability | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.062307, 36.062092 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 11400000 | 334333.8 | 334333.8 | Equitable | N/A | 334333.8 | 0 | 2851216 | 852.8 | 2851216 | 334334 | -2516882.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water in use.
8456 | Water and Sewerage Management | Soin water works - Kabarnet farm Water Works, Kipsyenan Water Works, Athinai sub location water works, Morop water works | To implement soin water works - kabarnet farm water works, kipsyenan water works, athinai sub location water works, morop water works for access to clean water and environmental sustainability | Soin water works - Kabarnet farm Water Works, Kipsyenan Water Works, Athinai sub location water works, Morop water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.097772 35.930847 1669.8000000000002 3.5999999046325684 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 12247823 | 8336597 | 8336597 | Equitable | N/A | 8336597 | 0 | 1890733 | 22.7 | 1890733 | 2010266 | 6445864 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bikon Engineering. Assessor remarks: Residents are grateful.
8457 | Water and Sewerage Management | Soin water works | To implement soin water works for access to clean water and environmental sustainability | Soin water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.008958, 36.039238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | FY 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4204030 | 280.3 | 4204030 | 4430000 | -2704030 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping needs extension.
8458 | Water and Sewerage Management | Construction of Chemarmar Water trough | To construct Chemarmar Water trough | Chemarmar Water trough constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 449948 | 90 | 449948 | 500000 | 50052 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
8459 | Water and Sewerage Management | Construction of Ewani Water tank and piping | To construct Ewani Water tank and piping | Ewani Water tank and piping constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 3000000 | 2999760 | 2999760 | Equitable | N/A | 2999760 | 0 | 2999760 | 100 | 2999760 | 2999760 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
8460 | Water and Sewerage Management | Drilling and capping of Arutani Borehole | To implement drilling and capping of arutani borehole for access to clean water and environmental sustainability | Drilling and capping of Arutani Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.074664, 36.115103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499685 | 100 | 2499685 | 2500000 | 315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8461 | Water and Sewerage Management | Drilling and equipping of Chemassis Borehole | To implement drilling and equipping of chemassis borehole for access to clean water and environmental sustainability | Drilling and equipping of Chemassis Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5471976 | 5471976 | 5471976 | Equitable | N/A | 5471976 | 0 | 2899355 | 53 | 2899355 | 2900291 | 2572621 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8462 | Water and Sewerage Management | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project | To implement lower solai water project - construction of water reservoir and piping of lower solai water project for access to clean water and environmental sustainability | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.097788, 36.178758 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 7000000 | 631107 | 631107 | Equitable | N/A | 631107 | 0 | 630663 | 99.9 | 630663 | 631107 | 444 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8463 | Water and Sewerage Management | Ngendaptich tuiyotich water project piping | To implement ngendaptich tuiyotich water project piping for access to clean water and environmental sustainability | Ngendaptich tuiyotich water project piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.04618, 36.140841 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1260630 | 63 | 1260630 | 739370 | 739370 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8464 | Water and Sewerage Management | Nyamamithi water project - Drilling of borehole and Installation of pump | To implement nyamamithi water project - drilling of borehole and installation of pump for access to clean water and environmental sustainability | Nyamamithi water project - Drilling of borehole and Installation of pump completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.113312, 36.222792 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 4000000 | 2056072 | 2056072 | Equitable | N/A | 2056072 | 0 | 2045996 | 99.5 | 2045996 | 2056072 | 10076 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8465 | Water and Sewerage Management | purchase and installation of water pipes of Ewani water project | To procure and install water pipes of Ewani water project | Water pipes of Ewani water project procured and installed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.060176 36.104307 1695.93603515625 15.730999946594238 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499801 | 100 | 3499801 | 3500000 | 199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Stalled.
8466 | Water and Sewerage Management | Sigito water project - piping | To implement sigito water project - piping for access to clean water and environmental sustainability | Sigito water project - piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.04618, 36.140841 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998215 | 99.8 | 998215 | 1000000 | 1785 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8467 | Water and Sewerage Management | Supply of Water pipes to Sigito/Murram Water project | To implement supply of water pipes to sigito/murram water project for access to clean water and environmental sustainability | Supply of Water pipes to Sigito/Murram Water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.023174 36.146624 1550.736083984375 9.659000396728516 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497300 | 99.5 | 497300 | 2700 | 2700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8468 | Water and Sewerage Management | Supply of water pipes to solai ward water works | To implement supply of water pipes to solai ward water works for access to clean water and environmental sustainability | Supply of water pipes to solai ward water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.023174 36.146624 1550.736083984375 9.659000396728516 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1900596 | 95 | 1900596 | 2000000 | 99404 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8469 | Water and Sewerage Management | Completion of lower Solai water project | To complete lower Solai water project | Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.18324 36.184717 1648.8 7.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3491285 | 87.3 | 3491285 | 508715 | 508715 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8470 | Water and Sewerage Management | construction of 2 water tanks at the Shrine | To construct 2 water tanks at the Shrine | 2 water tanks at the Shrine constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.024925 36.251015 2248.60009765625 4 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1253078 | 1253078 | Equitable | N/A | 1253078 | 0 | 1253078 | 100 | 1253078 | 1253078 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, community enjoying access to clean water.. Viable: Yes. Contractor: Details not provided. Assessor remarks: Water tanks constructed and piping done.
8471 | Water and Sewerage Management | Construction of Gituamba Kianoe (Nguba farm) water Tank | To construct Gituamba Kianoe (Nguba farm) water Tank | Gituamba Kianoe (Nguba farm) water Tank constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.004125 36.219987 1997.199951171875 8.61400032043457 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198895 | 99.9 | 1198895 | 1200000 | 1105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes.. Contractor: Information not available. Assessor remarks: Water tank in good condition.
8472 | Water and Sewerage Management | Construction of tank and piping of Araki water project | To construct tank and piping of Araki water project | Tank and piping of Araki water project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.025943, 36.229345 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2483954 | 99.4 | 2483954 | 2500000 | 16046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Yes.
8473 | Water and Sewerage Management | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project | To implement drilling of borehole, installation of pump and solar panels and piping of subukia valley water project for access to clean water and environmental sustainability | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.040933 36.220476 2150.7001953125 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1658854 | 1658854 | Equitable | N/A | 1658854 | 0 | 1658854 | 100 | 1658854 | 1658854 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
8474 | Water and Sewerage Management | Drilling of Tetu Kirima Kibugi borehole | To implement drilling of tetu kirima kibugi borehole for access to clean water and environmental sustainability | Drilling of Tetu Kirima Kibugi borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3661174 | 183.1 | 3661174 | 2000000 | -1661174 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
8475 | Water and Sewerage Management | Gatundu water piping | To implement gatundu water piping for access to clean water and environmental sustainability | Gatundu water piping completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.02504, 36.175968 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 197095 | 98.5 | 197095 | 2905 | 2905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Completed and is in good working condition.
8476 | Water and Sewerage Management | installation of water pipes at ACK Munanda water | To install water pipes at ACK Munanda water | Water pipes at ACK Munanda water installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042368, 36.190708 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2918/2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494803 | 99 | 494803 | 500000 | 5197 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water Supply to the local community provided and functional.
8477 | Water and Sewerage Management | Piping, purchase and installation of solar panels subukia valley borehole | To implement piping, purchase and installation of solar panels subukia valley borehole for access to clean water and environmental sustainability | Piping, purchase and installation of solar panels subukia valley borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.040933 36.220476 2150.7001953125 100 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 643491 | 29.2 | 643491 | 1556509 | 1556509 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
8478 | Water and Sewerage Management | Purchase and installation of Hydrum pump, sola panels and piping at GAWASU water project | To procure and install Hydrum pump, sola panels and piping at GAWASU water project | Hydrum pump, sola panels and piping at GAWASU water project procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997632 | 99.9 | 2997632 | 3000000 | 2368 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
8479 | Water and Sewerage Management | Purchase and installation of Morro borehole Solar Panels | To procure and install Morro borehole Solar Panels | Morro borehole Solar Panels procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | 0.007778, 36.223232 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999888 | 100 | 1999888 | 112 | 112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the borehole.
8480 | Water and Sewerage Management | purchase and installation of water pump, solar panels and construction of water tank for Arash B Kirima borehole | To procure and install water pump, solar panels and construction of water tank for Arash B Kirima borehole | Water pump, solar panels and construction of water tank for Arash B Kirima borehole procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2510867 | 2510867 | Equitable | N/A | 2510867 | 0 | 2734410 | 108.9 | 2734410 | 2510867 | -223543 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
8481 | Water and Sewerage Management | purchase and installation of water pump, solar panels and piping for Arash A Mutito mumui water projects | To procure and install water pump, solar panels and piping for Arash A Mutito mumui water projects | Water pump, solar panels and piping for Arash A Mutito mumui water projects procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1999999 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966642 | 98.9 | 2966642 | 3000000 | 33358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
8482 | Water and Sewerage Management | Quarry water project Subukia town | To implement quarry water project subukia town for access to clean water and environmental sustainability | Quarry water project Subukia town completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.006327, 36.23532 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2500000 | 62.5 | 2500000 | 4000000 | 1500000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further measures to be taken due to tank not having water.
8483 | Water and Sewerage Management | Kware piping subukia water projects | To implement kware piping subukia water projects for access to clean water and environmental sustainability | Kware piping subukia water projects completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399639 | 100 | 2399639 | 2400000 | 361 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
8484 | Water and Sewerage Management | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects | To implement subukia ward water works - construction of water intake, purchase of land and piping at kware subukia town water projects for access to clean water and environmental sustainability | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.006257, 36.23544 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 12/12/2019 | 4000000 | 1999876 | 1999876 | Equitable | N/A | 1999876 | 0 | 1999876 | 100 | 1999876 | 1999876 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.. Contractor: Information not known. Assessor remarks: The water tank is in good condition.
8485 | Water and Sewerage Management | Construction of chagoror water project | To construct chagoror water project | Chagoror water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | TINET | -0.445126 35.609035 0 2200 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999183 | 99.9 | 999183 | 1000000 | 817 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
8486 | Water and Sewerage Management | Drilling of Chemaner Borehole | To implement drilling of chemaner borehole for access to clean water and environmental sustainability | Drilling of Chemaner Borehole completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | TINET | -0.445126, 35.609035 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2200000 | 100 | 2200000 | 2200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Complete but operational needs piping powerandtank.
8487 | Water and Sewerage Management | Kamwaura Sinking of Borehole | To implement kamwaura sinking of borehole for access to clean water and environmental sustainability | Kamwaura Sinking of Borehole completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | TINET | -0.538982 35.643548 0 2900 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2013/14 | 2013/14 | N/A | 828149 | 828149 | 828149 | Equitable | N/A | 828149 | 0 | 2200000 | 265.7 | 2200000 | 828149 | -1371851 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational use by Kapkeet secondary school.
8488 | Water and Sewerage Management | Construction of water tank at Turi | To construct water tank at Turi | Water tank at Turi constructed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.299733 35.69569 2705.4 9.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999941 | 100 | 999941 | 999941 | 59 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repainting is required. The facility is very dirty.
8489 | Water and Sewerage Management | Drilling of Borehole at Geteru water project | To provide access to clean water through borehole drilling at Geteru water project | Borehole drilled at Geteru water project | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.269092, 35.774998 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999956 | 100 | 1999956 | 1999956 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The water was drilled but was later sealed as the water was not safe for human consumption.
8490 | Water and Sewerage Management | Drilling of Borehole at Mitoni water project | To provide access to clean water through borehole drilling at Mitoni water project | Borehole drilled at Mitoni water project | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.269092, 35.774998 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1999956 | 200 | 1999956 | 1000000 | -999956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The water was drilled but was later sealed as the water was not safe for human consumption.
8491 | Water and Sewerage Management | Drilling of Borehole Valley water project | To provide access to clean water through borehole drilling at Valley water project | Borehole drilled at Valley water project | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.269092, 35.774998 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The water was drilled but was later sealed as the water was not safe for human consumption.
8492 | Water and Sewerage Management | Michatha water project - Piping of Michatha water project | To implement michatha water project - piping of michatha water project for access to clean water and environmental sustainability | Michatha water project - Piping of Michatha water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.27483, 35.724585 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998760 | 99.9 | 998760 | 500000 | 1240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
8493 | Water and Sewerage Management | Michatha water project Piping works | To implement michatha water project piping works for access to clean water and environmental sustainability | Michatha water project Piping works completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499923 | 100 | 499923 | 77 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
8494 | Water and Sewerage Management | Mona-michatha water project - Piping of Mona-michatha water project | To implement mona-michatha water project - piping of mona-michatha water project for access to clean water and environmental sustainability | Mona-michatha water project - Piping of Mona-michatha water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.27483, 35.724585 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
8495 | Water and Sewerage Management | Muchorwe water project - Piping of Muchorwa water project | To implement muchorwe water project - piping of muchorwa water project for access to clean water and environmental sustainability | Muchorwe water project - Piping of Muchorwa water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 796157 | 99.5 | 796157 | 77 | 3843 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
8496 | Water and Sewerage Management | Piping of water at Mona water project | To provide water distribution infrastructure at water at Mona water project | Water piping at water at Mona water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 797936 | 88.7 | 797936 | 499923 | 102064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
8497 | Water and Sewerage Management | Purchase of water pump kiambu | To procure water pump kiambu | Water pump kiambu procured | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
8498 | Water and Sewerage Management | Rehabilitation of Kwa Nyakundi water project | To rehabilitate Kwa Nyakundi water project to restore functionality | Kwa Nyakundi water project rehabilitated | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.301193 35.70907 2682 10.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497237 | 99.4 | 497237 | 500000 | 2763 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title is under some self help group and now an individual is claiming ownership. The county government of Nakuru needs to follow up.
8499 | Water and Sewerage Management | Segaitim water project - Piping of Segaitim water project | To implement segaitim water project - piping of segaitim water project for access to clean water and environmental sustainability | Segaitim water project - Piping of Segaitim water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 998760 | 66.6 | 998760 | 1500000 | 501240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
8500 | Water and Sewerage Management | Water projects at Ndenderu A | To implement water projects at ndenderu a for access to clean water and environmental sustainability | Water projects at Ndenderu A completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.310893, 35.743707 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499906 | 100 | 1499906 | 1499906 | 94 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Until the entire project is completed that's when it will meet the objective. Viable: Yes. Assessor remarks: The tank is complete but awaiting piping.
8501 | Water and Sewerage Management | Construction of water tank and piping at Mukorombo dispensary | To construct water tank and piping at Mukorombo dispensary | Water tank and piping at Mukorombo dispensary constructed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.330008 35.687633 2765.800048828125 39.599998474121094 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 999941 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Both the fence and the gate house were vandalised.
8502 | Water and Sewerage Management | Piping at Geteru borehole | To provide water distribution infrastructure at Geteru borehole | Water piping at Geteru borehole completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.268852, 35.77511 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999973 | 100 | 999973 | 499923 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project was completed but not in use. No water connection to the tank.
8503 | Water and Sewerage Management | Piping at Kiambu Water Project | To provide water distribution infrastructure at Kiambu Water Project | Water piping at Kiambu Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.330019 35.68764 2765.800048828125 42.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499752 | 100 | 499752 | 499923 | 248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Viable but it did not meet the needs of the residents. Assessor remarks: The project was abandoned and now vandalised.
8504 | Water and Sewerage Management | Piping at Michatha Water Project | To provide water distribution infrastructure at Michatha Water Project | Water piping at Michatha Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 900000 | 402366 | 402366 | Equitable | N/A | 402366 | 0 | 499923 | 124.2 | 499923 | 499923 | -97557 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
8505 | Water and Sewerage Management | Piping at water valley | To provide water distribution infrastructure at water valley | Water piping at water valley completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.270953, 35.756172 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999949 | 100 | 999949 | 499923 | 51 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well built.
8506 | Water and Sewerage Management | Renovation of borehole at Kapsita | To rehabilitate borehole at Kapsita to restore functionality | Borehole at Kapsita rehabilitated | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -1.281229 36.821402 0 291468.7964650597 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 898925 | 99.9 | 898925 | 2300000 | 1075 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: YES. Assessor remarks: THE TOILET INSIDE THE OPD IS NOT FUNCTIONAL. THE WORK WAS NOT DONE SATISFACTORY MANNER.
8507 | Water and Sewerage Management | Water tank renovation and piping at Sagaitim | To implement water tank renovation and piping at sagaitim for access to clean water and environmental sustainability | Water tank renovation and piping at Sagaitim completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.303666 35.690293 2745.8 23.200000762939453 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 700000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499918 | 100 | 499918 | 50067 | 82 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8508 | Water and Sewerage Management | Completion of Water Borehole at Chemaner | To complete Water Borehole at Chemaner | Water Borehole at Chemaner completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.435337, 35.605734 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 710717 | 39.5 | 710717 | 1089283 | 1089283 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Never started.
8509 | Water and Sewerage Management | Construction of chagoror water project | To construct chagoror water project | Chagoror water project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999183 | 99.9 | 999183 | 1000000 | 817 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
8510 | Water and Sewerage Management | Drilling of Chemaner Borehole | To implement drilling of chemaner borehole for access to clean water and environmental sustainability | Drilling of Chemaner Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.445126, 35.609035 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2200000 | 100 | 2200000 | 2200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Complete but operational needs piping powerandtank.
8511 | Water and Sewerage Management | Kamwaura Sinking of Borehole | To implement kamwaura sinking of borehole for access to clean water and environmental sustainability | Kamwaura Sinking of Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.538982 35.643548 0 2900 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2013/14 | 2013/14 | N/A | 828149 | 828149 | 828149 | Equitable | N/A | 828149 | 0 | 2200000 | 265.7 | 2200000 | 828149 | -1371851 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational use by Kapkeet secondary school.
8512 | Water and Sewerage Management | construcgion of a water tank at Mitoni water project | To implement construcgion of a water tank at mitoni water project for access to clean water and environmental sustainability | construcgion of a water tank at Mitoni water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.279945 35.774557 2458.800048828125 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999941 | 100 | 999941 | 1000000 | 59 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: The department to follow up to process the title. The water tank is not in use since the time it was constructed. No water connection. The residents are seeing it as a white elephant project.
8513 | Water and Sewerage Management | Construction of water tank at Turi | To construct water tank at Turi | Water tank at Turi constructed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.299733 35.69569 2705.4 9.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999941 | 999941 | Equitable | N/A | 999941 | 0 | 999941 | 100 | 999941 | 999941 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repainting is required. The facility is very dirty.
8514 | Water and Sewerage Management | Drilling of Borehole at Geteru water project | To provide access to clean water through borehole drilling at Geteru water project | Borehole drilled at Geteru water project | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.269092, 35.774998 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999956 | 1999956 | Equitable | N/A | 1999956 | 0 | 1999956 | 100 | 1999956 | 1999956 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The water was drilled but was later sealed as the water was not safe for human consumption.
8515 | Water and Sewerage Management | Drilling of Borehole Valley water project | To provide access to clean water through borehole drilling at Valley water project | Borehole drilled at Valley water project | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.269092, 35.774998 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The water was drilled but was later sealed as the water was not safe for human consumption.
8516 | Water and Sewerage Management | Michatha water project Piping works | To implement michatha water project piping works for access to clean water and environmental sustainability | Michatha water project Piping works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499923 | 100 | 499923 | 77 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
8517 | Water and Sewerage Management | Milima mitatu piping works | To implement milima mitatu piping works for access to clean water and environmental sustainability | Milima mitatu piping works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -1.281229 36.821402 0 291468.7964650597 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398718 | 99.7 | 398718 | 1282 | 1282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: the project is in use.
8518 | Water and Sewerage Management | Mona-michatha water project - Piping of Mona-michatha water project | To implement mona-michatha water project - piping of mona-michatha water project for access to clean water and environmental sustainability | Mona-michatha water project - Piping of Mona-michatha water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.27483, 35.724585 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
8519 | Water and Sewerage Management | Purchase of sakaitim water pump | To procure sakaitim water pump | Sakaitim water pump procured | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
8520 | Water and Sewerage Management | Purchase of water pump at kiambu | To procure water pump at kiambu | Water pump at kiambu procured | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
8521 | Water and Sewerage Management | Rehabilitation of Kwa Nyakundi water project | To rehabilitate Kwa Nyakundi water project to restore functionality | Kwa Nyakundi water project rehabilitated | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.301193 35.70907 2682 10.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497237 | 99.4 | 497237 | 500000 | 2763 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title is under some self help group and now an individual is claiming ownership. The county government of Nakuru needs to follow up.
8522 | Water and Sewerage Management | Water projects at Ndenderu A | To implement water projects at ndenderu a for access to clean water and environmental sustainability | Water projects at Ndenderu A completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.310893, 35.743707 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499906 | 1499906 | Equitable | N/A | 1499906 | 0 | 1499906 | 100 | 1499906 | 1499906 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Until the entire project is completed that's when it will meet the objective. Viable: Yes. Assessor remarks: The tank is complete but awaiting piping.
8523 | Water and Sewerage Management | Piping at Michatha Water Project | To provide water distribution infrastructure at Michatha Water Project | Water piping at Michatha Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 900000 | 499923 | 499923 | Equitable | N/A | 499923 | 0 | 499923 | 100 | 499923 | 499923 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
8524 | Water and Sewerage Management | Completion of kandutura borehole | To complete kandutura borehole | Kandutura borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.149943 35.881463 1841.6 9.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 364995 | 73 | 364995 | 57432 | 135005 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
8525 | Water and Sewerage Management | Completion of Rajuera Borehole | To complete Rajuera Borehole | Rajuera Borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1742568 | 96.8 | 1742568 | 57432 | 57432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
8526 | Water and Sewerage Management | Completion of Umoja borehole (Piping and Installation of Water tank) | To complete Umoja borehole (Piping and Installation of Water tank) | Umoja borehole (Piping and Installation of Water tank) completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.198778, 35.936028 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 3328973 | 151.3 | 3328973 | 3449399 | -1128973 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ms Tirus. Assessor remarks: Good.
8527 | Water and Sewerage Management | Drilling of borehole at lengenet Chiefs Office | To provide access to clean water through borehole drilling at lengenet Chiefs Office | Borehole drilled at lengenet Chiefs Office | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.112228 35.887368 1817.7 20.799999237060547 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8528 | Water and Sewerage Management | Installation of an elevated tank at Chergei Water Project | To install an elevated tank at Chergei Water Project | An elevated tank at Chergei Water Project installed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.13898 35.90486 1791.2 8.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 798152 | 99.8 | 798152 | 798152 | 1848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The conductor has broken down.
8529 | Water and Sewerage Management | Kware Kapkwen Borehole - Drilling of Borehole | To implement kware kapkwen borehole - drilling of borehole for access to clean water and environmental sustainability | Kware Kapkwen Borehole - Drilling of Borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2229709 | 96.9 | 2229709 | 0 | 70291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8530 | Water and Sewerage Management | Nafaka water works | To implement nafaka water works for access to clean water and environmental sustainability | Nafaka water works completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.137292 35.824637 1889.3 9.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1794996 | 99.7 | 1794996 | 2000000 | 5004 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment. Assessor remarks: Good.
8531 | Water and Sewerage Management | Piping and Purchase of 2 tank at Shalom B borehole | To provide water distribution infrastructure at and Purchase of 2 tank at Shalom B borehole | Water piping at and Purchase of 2 tank at Shalom B borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1477931 | 98.5 | 1477931 | 1477931 | 22069 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8532 | Water and Sewerage Management | Piping and Purchase of a tank at Shalom A borehole | To provide water distribution infrastructure at and Purchase of a tank at Shalom A borehole | Water piping at and Purchase of a tank at Shalom A borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1477931 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8533 | Water and Sewerage Management | Rehabilitation of Burgei Borehole | To rehabilitate Burgei Borehole to restore functionality | Burgei Borehole rehabilitated | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.149943 35.881463 1841.6 9.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1265104 | 90.4 | 1265104 | 1284290 | 134896 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
8534 | Water and Sewerage Management | Tabot/tuiyotich water project | To implement tabot/tuiyotich water project for access to clean water and environmental sustainability | Tabot/tuiyotich water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499199 | 99.9 | 1499199 | 801 | 801 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
8535 | Water and Sewerage Management | Visoi ward water works | To implement visoi ward water works for access to clean water and environmental sustainability | Visoi ward water works completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.137292 35.824637 1889.3 9.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 4385784.55 | 2335646.95 | 2335646.95 | Equitable | N/A | 2335646.95 | 0 | 2335647 | 100 | 2335647 | 2000000 | -0.05 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment. Assessor remarks: Good.
8536 | Water and Sewerage Management | Water Works - Piping of Water from Sobea to Deloraine | To implement water works - piping of water from sobea to deloraine for access to clean water and environmental sustainability | Water Works - Piping of Water from Sobea to Deloraine completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125166 35.938548 1742 21.430999755859375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1900000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199579 | 100 | 1199579 | 421 | 421 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8537 | Water and Sewerage Management | Completion of Belbur water project (Additional solar panels) | To complete Belbur water project (Additional solar panels) | Belbur water project (Additional solar panels) completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2298866 | 100 | 2298866 | 2298866 | 1134 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
8538 | Water and Sewerage Management | Completion of Rajuera water project (Piping and pump and water tank) | To complete Rajuera water project (Piping and pump and water tank) | Rajuera water project (Piping and pump and water tank) completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.113343 35.830298 1856.1000000000001 9.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1959594 | 98 | 1959594 | 3449399 | 40406 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: 2018/19. Assessor remarks: Good.
8539 | Water and Sewerage Management | Construction of Gogar water pan and digging of trench | To construct Gogar water pan and digging of trench | Gogar water pan and digging of trench constructed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.123667 35.824817 1897.9 9.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3550334 | 88.8 | 3550334 | 120000 | 449666 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: Not achieved. Viable: Yes. Assessor remarks: Poor.
8540 | Water and Sewerage Management | Drilling and completion of Umoja water borehole | To implement drilling and completion of umoja water borehole for access to clean water and environmental sustainability | Drilling and completion of Umoja water borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 4231790 | 4231790 | Equitable | N/A | 4231790 | 0 | 1342243 | 31.7 | 1342243 | 1342243 | 2889547 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8541 | Water and Sewerage Management | water piping, purchase of water tank and fencing for Lenginet dispensary | To implement water piping, purchase of water tank and fencing for lenginet dispensary for access to clean water and environmental sustainability | water piping, purchase of water tank and fencing for Lenginet dispensary completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125197 35.935737 1744.699951171875 6.599999904632568 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599659 | 99.9 | 599659 | 0 | 341 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8542 | Water and Sewerage Management | Connection of water to CCCR residential houses | To implement connection of water to cccr residential houses for access to clean water and environmental sustainability | Connection of water to CCCR residential houses completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | VIWANDANI | -0.71766 36.442854 1917.1319026947021 49.76555278365609 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
8543 | Water and Sewerage Management | Completion of drilling of burgei water works | To complete drilling of burgei water works | Drilling of burgei water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
8544 | Water and Sewerage Management | Completion of Rajuera Borehole | To complete Rajuera Borehole | Rajuera Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1742568 | 96.8 | 1742568 | 57432 | 57432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
8545 | Water and Sewerage Management | Completion of Umoja borehole (Piping and Installation of Water tank) | To complete Umoja borehole (Piping and Installation of Water tank) | Umoja borehole (Piping and Installation of Water tank) completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.198778, 35.936028 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2749399 | 3449399 | 3449399 | Equitable | N/A | 3449399 | 0 | 3328973 | 96.5 | 3328973 | 3449399 | 120426 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ms Tirus. Assessor remarks: Good.
8546 | Water and Sewerage Management | Installation of an elevated tank at Chergei Water Project | To install an elevated tank at Chergei Water Project | An elevated tank at Chergei Water Project installed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.13898 35.90486 1791.2 8.100000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 798152 | 798152 | Equitable | N/A | 798152 | 0 | 798152 | 100 | 798152 | 798152 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The conductor has broken down.
8547 | Water and Sewerage Management | Piping and Purchase of 2 tank at Shalom B borehole | To provide water distribution infrastructure at and Purchase of 2 tank at Shalom B borehole | Water piping at and Purchase of 2 tank at Shalom B borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1477930.5 | 1477930.5 | Equitable | N/A | 1477930.5 | 0 | 1477931 | 100 | 1477931 | 1477931 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8548 | Water and Sewerage Management | Rehabilitation of Burgei Borehole | To rehabilitate Burgei Borehole to restore functionality | Burgei Borehole rehabilitated | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1265104 | 90.4 | 1265104 | 1284290 | 134896 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
8549 | Water and Sewerage Management | Tabot/tuiyotich water project | To implement tabot/tuiyotich water project for access to clean water and environmental sustainability | Tabot/tuiyotich water project completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499199 | 99.9 | 1499199 | 801 | 801 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
8550 | Water and Sewerage Management | Water piping in kandutura,kimangu,mawe and jamii | To implement water piping in kandutura,kimangu,mawe and jamii for access to clean water and environmental sustainability | Water piping in kandutura,kimangu,mawe and jamii completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1846952 | 92.3 | 1846952 | 2000000 | 153048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8551 | Water and Sewerage Management | Water Works - Piping of Water from Sobea to Deloraine | To implement water works - piping of water from sobea to deloraine for access to clean water and environmental sustainability | Water Works - Piping of Water from Sobea to Deloraine completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125166 35.938548 1742 21.430999755859375 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1900000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199579 | 100 | 1199579 | 421 | 421 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8552 | Water and Sewerage Management | Completion of Belbur water project (Additional solar panels) | To complete Belbur water project (Additional solar panels) | Belbur water project (Additional solar panels) completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 2298865.55 | 2298865.55 | Equitable | N/A | 2298865.55 | 0 | 2298866 | 100 | 2298866 | 2298866 | -0.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
8553 | Water and Sewerage Management | Drilling and completion of Umoja water borehole | To implement drilling and completion of umoja water borehole for access to clean water and environmental sustainability | Drilling and completion of Umoja water borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1342243.3 | 1342243.3 | Equitable | N/A | 1342243.3 | 0 | 1342243 | 100 | 1342243 | 1342243 | 0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8554 | Water and Sewerage Management | Connection of water to CCCR residential houses | To implement connection of water to cccr residential houses for access to clean water and environmental sustainability | Connection of water to CCCR residential houses completed | 3110502 | Water Supplies and Sewerage | Naivasha | Viwandani | -0.71766 36.442854 1917.1319026947021 49.76555278365609 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
8555 | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | To implement akuiz borehole - drilling, equipping construction of water tank and installation of solar panels at akuiz borehole for access to clean water and environmental sustainability | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 394720 | 394720 | Equitable | N/A | 394720 | 0 | 394500 | 99.9 | 394500 | 394720 | 220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8556 | Chania Igana / Nganoini water works | Chania Igana / Nganoini water works | To implement chania igana / nganoini water works for access to clean water and environmental sustainability | Chania Igana / Nganoini water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 997931.01 | 997931.01 | 997931.01 | Equitable | N/A | 997931.01 | 0 | 912210 | 91.4 | 912210 | 997931 | 85721.01 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
8557 | Water and Sewerage Management | Construction of intake, pipeline and storage tank at upendo, Kianoe, kirima -water works | To construct intake, pipeline and storage tank at upendo, Kianoe, kirima -water works | Intake, pipeline and storage tank at upendo, Kianoe, kirima -water works constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.080873 36.244899 0 20.445999145507812 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499487 | 100 | 2499487 | 639 | 513 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
8558 | Water and Sewerage Management | Construction of intake,storage tank and piping of Sugutek water project | To construct intake,storage tank and piping of Sugutek water project | Intake,storage tank and piping of Sugutek water project constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.146943 36.2423 1696.7 18.299999237060547 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999045 | 100 | 1999045 | 639 | 955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
8559 | Water and Sewerage Management | Construction of storage tank and piping at wei borehole water project | To construct storage tank and piping at wei borehole water project | Storage tank and piping at wei borehole water project constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.146943 36.2423 1696.7 18.299999237060547 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499361 | 100 | 2499361 | 639 | 639 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
8560 | Water and Sewerage Management | Construction of storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project | To construct storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project | Storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499874 | 100 | 3499874 | 3500000 | 126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8561 | Water and Sewerage Management | Construction of storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project | To construct storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project | Storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499100 | 100 | 3499100 | 3499100 | 900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
8562 | Water and Sewerage Management | Design and construction of intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project | To design and construct intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project | Intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project designed and constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995163 | 99.8 | 1995163 | 1995163 | 4837 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
8563 | Water and Sewerage Management | Design, rehabilitation of intake,piping and construction of storage tank of Berur water project | To implement design, rehabilitation of intake,piping and construction of storage tank of berur water project for access to clean water and environmental sustainability | Design, rehabilitation of intake,piping and construction of storage tank of Berur water project completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494757 | 99.8 | 2494757 | 2500000 | 5243 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
8564 | Water and Sewerage Management | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well | To implement gathiini gustion shallow wells - excavation and digging of gathiini shallows well for access to clean water and environmental sustainability | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1198074 | 0 | Stalled | 0 | N/A | Residents Prefer Borehole instead of shallow wells and hence require Additional funding | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Residents Prefer Borehole instead of shallow wells and hence require Additional funding.
8565 | Water and Sewerage Management | Gathima water project (Marana water tank ) | To implement gathima water project (marana water tank ) for access to clean water and environmental sustainability | Gathima water project (Marana water tank ) completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1144051 | 1000000.05 | 1000000.05 | Equitable | N/A | 1000000.05 | 0 | 983544 | 98.4 | 983544 | 0 | 16456.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
8566 | Water and Sewerage Management | Installation of solar panel, equipping and pumping machiness at Wei borehole water project | To install solar panel, equipping and pumping machiness at Wei borehole water project | Solar panel, equipping and pumping machiness at Wei borehole water project installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499813 | 100 | 3499813 | 187 | 187 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8567 | Ngamini water works - drilling of borehole and equipping | Ngamini water works - drilling of borehole and equipping | To implement ngamini water works - drilling of borehole and equipping for access to clean water and environmental sustainability | Ngamini water works - drilling of borehole and equipping completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.027937 36.257645 2098.1 63.17599868774414 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000001 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998643 | 100 | 2998643 | 0 | 1357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
8568 | Water and Sewerage Management | Additional piping at Wei, Akuisi and Nganoini water works | To implement additional piping at wei, akuisi and nganoini water works for access to clean water and environmental sustainability | Additional piping at Wei, Akuisi and Nganoini water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.08815 36.229812 1777.6 13.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3446244 | 229.7 | 3446244 | 3500000 | -1946244 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets is in use.
8569 | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | To implement akuiz borehole - drilling, equipping construction of water tank and installation of solar panels at akuiz borehole for access to clean water and environmental sustainability | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 394720 | 394720 | Equitable | N/A | 394720 | 0 | 394500 | 99.9 | 394500 | 394720 | 220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8570 | Chania Igana / Nganoini water works | Chania Igana / Nganoini water works | To implement chania igana / nganoini water works for access to clean water and environmental sustainability | Chania Igana / Nganoini water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 997931.01 | 997931.01 | 997931.01 | Equitable | N/A | 997931.01 | 0 | 912210 | 91.4 | 912210 | 997931 | 85721.01 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
8571 | Water and Sewerage Management | Construction of intake, pipeline and storage tank at upendo, Kianoe, kirima -water works | To construct intake, pipeline and storage tank at upendo, Kianoe, kirima -water works | Intake, pipeline and storage tank at upendo, Kianoe, kirima -water works constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499487 | 100 | 2499487 | 639 | 513 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
8572 | Water and Sewerage Management | Construction of intake,storage tank and piping of Sugutek water project | To construct intake,storage tank and piping of Sugutek water project | Intake,storage tank and piping of Sugutek water project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999045 | 100 | 1999045 | 639 | 955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
8573 | Water and Sewerage Management | Construction of storage tank and piping at wei borehole water project | To construct storage tank and piping at wei borehole water project | Storage tank and piping at wei borehole water project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499361 | 100 | 2499361 | 639 | 639 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
8574 | Water and Sewerage Management | Construction of storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project | To construct storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project | Storage tank,piping, installation of solar panels and pumping machines at ngamini borehole water project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499874 | 100 | 3499874 | 3500000 | 126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8575 | Water and Sewerage Management | Construction of storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project | To construct storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project | Storage tank,piping, installation of solar panels, pumping machines and water kiosk at akuisi borehole water project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3499100 | 3499100 | Equitable | N/A | 3499100 | 0 | 3499100 | 100 | 3499100 | 3499100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
8576 | Water and Sewerage Management | Design and construction of intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project | To design and construct intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project | Intake pump, installation of solar panels, pumping machines, piping and repair of storage tank of Kasi water Project designed and constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1995163 | 1995163 | Equitable | N/A | 1995163 | 0 | 1995163 | 100 | 1995163 | 1995163 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
8577 | Water and Sewerage Management | Design, rehabilitation of intake,piping and construction of storage tank of Berur water project | To implement design, rehabilitation of intake,piping and construction of storage tank of berur water project for access to clean water and environmental sustainability | Design, rehabilitation of intake,piping and construction of storage tank of Berur water project completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494757 | 99.8 | 2494757 | 2500000 | 5243 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
8578 | Water and Sewerage Management | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well | To implement gathiini gustion shallow wells - excavation and digging of gathiini shallows well for access to clean water and environmental sustainability | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1198073.52 | 1198073.52 | Equitable | N/A | 1198073.52 | 0 | 0 | 0 | 0 | 1198074 | 0 | Stalled | 0 | N/A | Residents Prefer Borehole instead of shallow wells and hence require Additional funding | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Residents Prefer Borehole instead of shallow wells and hence require Additional funding.
8579 | Water and Sewerage Management | Installation of solar panel, equipping and pumping machiness at Wei borehole water project | To install solar panel, equipping and pumping machiness at Wei borehole water project | Solar panel, equipping and pumping machiness at Wei borehole water project installed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499813 | 100 | 3499813 | 187 | 187 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
8580 | Water and Sewerage Management | Shakika water works | To implement shakika water works for access to clean water and environmental sustainability | Shakika water works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 489000 | 97.8 | 489000 | 996926 | 11000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
8581 | Water and Sewerage Management | Kamurugu water project - installation of solar | To implement kamurugu water project - installation of solar for access to clean water and environmental sustainability | Kamurugu water project - installation of solar completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.725647, 36.486758 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2016 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2757088 | 0 | 2757088 | 242912 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Initial drilling delivered less water hence drilled deeper..
8582 | Water and Sewerage Management | Muteithia borehole - deepening , fencing and pump constructionmof pump house | To implement muteithia borehole - deepening , fencing and pump constructionmof pump house for access to clean water and environmental sustainability | Muteithia borehole - deepening , fencing and pump constructionmof pump house completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.721865, 36.520293 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498988 | 100 | 2498988 | 2500000 | 1012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional of storage tanks...
8583 | Water and Sewerage Management | construction of sewer line at Abongoloya area | To construct sewer line at Abongoloya area | Sewer line at Abongoloya area constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1329591 | 88.6 | 1329591 | 1500000 | 170409 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8584 | Water and Sewerage Management | Desalination of Wanyororo Dam | To implement desalination of wanyororo dam for access to clean water and environmental sustainability | Desalination of Wanyororo Dam completed | 3110504 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.256626, 36.185103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 935838 | 78 | 935838 | 261273 | 264162 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ardent logistics. Assessor remarks: Good require desalination.
8585 | Water and Sewerage Management | Desalination of Wanyororo Dam | To implement desalination of wanyororo dam for access to clean water and environmental sustainability | Desalination of Wanyororo Dam completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.256626, 36.185103 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1197111 | 1197111 | Equitable | N/A | 1197111 | 0 | 935838 | 78.2 | 935838 | 261273 | 261273 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ardent logistics. Assessor remarks: Good require desalination.
8586 | Water and Sewerage Management | Purchase and installation of solar panel in wanyororo water project | To procure and install solar panel in wanyororo water project | Solar panel in wanyororo water project procured and installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.2523 36.18779 2039.2 19.399999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2199894 | 100 | 2199894 | 2200000 | 106 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Metro EDD company. Assessor remarks: Good.
8587 | Water and Sewerage Management | Supply of water pipes to water projects in Dundori | To implement supply of water pipes to water projects in dundori for access to clean water and environmental sustainability | Supply of water pipes to water projects in Dundori completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.232046, 36.174856 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DMG holding. Assessor remarks: Good.
8588 | Water and Sewerage Management | Supply of water tanks to vulnerable women in Dundori | To implement supply of water tanks to vulnerable women in dundori for access to clean water and environmental sustainability | Supply of water tanks to vulnerable women in Dundori completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.263108 36.187457 1987.5999755859375 9.600000381469727 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8589 | Water and Sewerage Management | Fencing of Ainamoi dam | To secure Ainamoi dam through fencing | Ainamoi dam fenced and secured | 3110504 | Other Infrastructure and Civil Works | GILGIL | EBURRU-MBARUK | -0.551568, 36.152333 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 19-20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 394446 | 78.9 | 394446 | 500000 | 105554 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Partially. Contractor: Unspecified. Assessor remarks: Need rehabilitation.
8590 | Water and Sewerage Management | Extention of echariria water piping | To implement extention of echariria water piping for access to clean water and environmental sustainability | Extention of echariria water piping completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8591 | Water and Sewerage Management | Extention of piping from Gema -witemere road | To implement extention of piping from gema -witemere road for access to clean water and environmental sustainability | Extention of piping from Gema -witemere road completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8592 | Water and Sewerage Management | Extention of upper Baraka village | To implement extention of upper baraka village for access to clean water and environmental sustainability | Extention of upper Baraka village completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.355649, 36.194914 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 22/23 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 267937 | 67 | 267937 | 400000 | 132063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Residents have piped water.
8593 | Water and Sewerage Management | roofing and renovation of kahuho tank | To implement roofing and renovation of kahuho tank for access to clean water and environmental sustainability | roofing and renovation of kahuho tank completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.553538, 36.112757 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 1489746 | 212.8 | 1489746 | 700000 | -789746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8594 | Water and Sewerage Management | Rehabilitation of toilet and new sewer line system at Kimathi estate | To rehabilitate toilet and new sewer line system at Kimathi estate to restore functionality | Toilet and new sewer line system at Kimathi estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.30363, 36.078623 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020/21 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3485179 | 87.1 | 3485179 | 514821 | 514821 | Stalled | 75 | 87.1 | STALLED DUE TO INSUFFICIEN FUNDS | 2018 | N/A | 514821 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
8595 | Water and Sewerage Management | Rehabilitation of toilet and new sewer line system at Kimathi estate | To rehabilitate toilet and new sewer line system at Kimathi estate to restore functionality | Toilet and new sewer line system at Kimathi estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30363, 36.078623 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020/21 | 5000000 | 514820.55 | 514820.55 | Equitable | N/A | 514820.55 | 0 | 3485179 | 677 | 3485179 | 514821 | -2970358.45 | Stalled | 75 | 100 | STALLED DUE TO INSUFFICIEN FUNDS | 2018 | N/A | -2970358.45 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
8596 | Water and Sewerage Management | Beautification and rehabilitation of Nyayo Gardens | To implement beautification and rehabilitation of nyayo gardens for access to clean water and environmental sustainability | Beautification and rehabilitation of Nyayo Gardens completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 20000000 | 100 | 20000000 | 8000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8597 | Water and Sewerage Management | Bore Hole Drilling And Equipping (Siwot & Keringet) | To implement bore hole drilling and equipping (siwot & keringet) for access to clean water and environmental sustainability | Bore Hole Drilling And Equipping (Siwot & Keringet) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 15000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 7752314 | 96.9 | 7752314 | 8000000 | 247686 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8598 | Water and Sewerage Management | Climate Change Mitigation and Adaptation | To implement climate change mitigation and adaptation for access to clean water and environmental sustainability | Climate Change Mitigation and Adaptation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 4997450 | 50 | 4997450 | 10000000 | 5002550 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8599 | Water and Sewerage Management | Completion of desilting of Storm Water retention Pond at Old Town treatment Works | To complete desilting of Storm Water retention Pond at Old Town treatment Works | Desilting of Storm Water retention Pond at Old Town treatment Works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 5000000 | 15497054 | 15497054 | N/A | N/A | 15497054 | 0 | 4941252 | 31.9 | 4941252 | 497054 | 10555802 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8600 | Water and Sewerage Management | Construction of Office and Sanitary facility Eco-Toilets I (Gioto) | To construct Office and Sanitary facility Eco-Toilets I (Gioto) | Office and Sanitary facility Eco-Toilets I (Gioto) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 7025864 | 351.3 | 7025864 | 2000000 | -5025864 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8601 | Water and Sewerage Management | Construction/Rehabilitation of sanitation facilities | To implement construction/rehabilitation of sanitation facilities for access to clean water and environmental sustainability | Construction/Rehabilitation of sanitation facilities completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 3400000 | Equitable | N/A | 3400000 | 0 | 7025864 | 140.5 | 7025864 | 3400000 | -2025864 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8602 | Environmental Management | Fencing of Gioto Disposal Site | To secure Gioto Disposal Site through fencing | Gioto Disposal Site fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 3303249.45 | 3303249.45 | N/A | N/A | 3303249.45 | 0 | 4696751 | 142.2 | 4696751 | 3303249 | -1393501.55 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8603 | Environmental Management | Greening and Beautification | To implement greening and beautification for access to clean water and environmental sustainability | Greening and Beautification completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 11500000 | 11500000 | 11500000 | N/A | N/A | 11500000 | 0 | 0 | 0 | 0 | 11500000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
8604 | Water and Sewerage Management | Other County Development Projects | To implement other county development projects for access to clean water and environmental sustainability | Other County Development Projects completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 27963000 | 3728738 | 3728738 | N/A | N/A | 3728738 | 0 | 7089732 | 190.1 | 7089732 | 3728738 | -3360994 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8605 | Environmental Management | renovation / rehabilitation of Naivasha municipal park | To rehabilitate / rehabilitation of Naivasha municipal park to restore functionality | / rehabilitation of Naivasha municipal park rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 20000000 | 666.7 | 20000000 | 3000000 | -17000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8606 | Water and Sewerage Management | Installation of electicity at ingobor borehole (phase 11) | To install electicity at ingobor borehole (phase 11) | Electicity at ingobor borehole (phase 11) installed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 723963 | 723963 | 723963 | Equitable | N/A | 723963 | 0 | 723722 | 100 | 723722 | 723963 | 241 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operating..
8607 | Water and Sewerage Management | Purchase of sub massive pump at ingobor | To procure sub massive pump at ingobor | Sub massive pump at ingobor procured | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497653 | 99.8 | 1497653 | 2347 | 2347 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Done and in operation.
8608 | Water and Sewerage Management | Installation of electicity at ingobor borehole (Phase II) | To install electicity at ingobor borehole (Phase II) | Electicity at ingobor borehole (Phase II) installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 723963 | 723963 | 723963 | Equitable | N/A | 723963 | 0 | 723722 | 100 | 723722 | 723963 | 241 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operating..
8609 | Water and Sewerage Management | Purchase of sub massive pump at ingobor | To procure sub massive pump at ingobor | Sub massive pump at ingobor procured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497653 | 99.8 | 1497653 | 2347 | 2347 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Done and in operation.
8610 | Water and Sewerage Management | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks | To implement nakuru press estate - rehabilitation of kivumbini estate sewerage networks for access to clean water and environmental sustainability | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.300433, 36.082496 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
8611 | Water and Sewerage Management | purchase and installation of london gabbage bins - Street cleaning and garbage /refuse collection | To procure and install london gabbage bins - Street cleaning and garbage /refuse collection | London gabbage bins - Street cleaning and garbage /refuse collection procured and installed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274104, 36.05562 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999978 | 100 | 999978 | 0 | 22 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
8612 | Water and Sewerage Management | Construction of sewer line at Hilton | To construct sewer line at Hilton | Sewer line at Hilton constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.273485, 36.052403 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 337770 | 9.7 | 337770 | 3500000 | 3162230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The toilet and the office was vandalized. They are in a bad shape and not operational.
8613 | Water and Sewerage Management | Installation of Garbage bins | To install Garbage bins | Garbage bins installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MENENGAI WEST | -0.226135, 35.9752 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997040 | 99.7 | 997040 | 997040 | 2960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: Vandalised.
8614 | Water and Sewerage Management | Digging of borehole at Lower st John | To implement digging of borehole at lower st john for access to clean water and environmental sustainability | Digging of borehole at Lower st John completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1459354 | 1459354 | 1459354 | Equitable | N/A | 1459354 | 0 | 2500000 | 171.3 | 2500000 | 1459354 | -1040646 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8615 | Water and Sewerage Management | purchase and installation of water pumpmat mulimani borehole in gatamaiyu | To procure and install water pumpmat mulimani borehole in gatamaiyu | Water pumpmat mulimani borehole in gatamaiyu procured and installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.648649, 36.488825 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8616 | Water and Sewerage Management | Installation of Garbage bins | To install Garbage bins | Garbage bins installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.226135, 35.9752 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020/21 | 1000000 | 997040 | 997040 | Equitable | N/A | 997040 | 0 | 997040 | 100 | 997040 | 997040 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: Vandalised.
8617 | Environmental Management | purchase and distribution of waste litter bins | To procure and distribution of waste litter bins | And distribution of waste litter bins procured | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2020/21 | 2020/21 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2870026 | 136.7 | 2870026 | 27046 | -770026 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8618 | Water and Sewerage Management | Construction of water tank and laying of pipes at boror,nairobi and mbama | To construct water tank and laying of pipes at boror,nairobi and mbama | Water tank and laying of pipes at boror,nairobi and mbama constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1487442 | 74.4 | 1487442 | 2000000 | 512558 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
8619 | Water and Sewerage Management | Installation of a transformer and electricity | To install a transformer and electricity | A transformer and electricity installed | 3110504 | Other Infrastructure and Civil Works | NJORO | NESSUIT | -0.368755, 35.897744 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 3574510 | 446.8 | 3574510 | 800000 | -2774510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Transformer was never delivered from KPLC..
8620 | Water and Sewerage Management | Installation of a transformer and electricity | To install a transformer and electricity | A transformer and electricity installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.368755, 35.897744 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 3574510 | 446.8 | 3574510 | 800000 | -2774510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Transformer was never delivered from KPLC..
8621 | Water and Sewerage Management | Climate mitigation-tree planting | To implement climate mitigation-tree planting for access to clean water and environmental sustainability | Climate mitigation-tree planting completed | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | OLKARIA | -0.815759, 36.322371 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996728 | 99.8 | 1996728 | 0 | 3272 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: No. Contractor: Domestic enterprises and general supplies. Assessor remarks: The project needs more touch.
8622 | Water and Sewerage Management | Olkaria Waste Management Plan - Purchase and installation of waste disposal bins at Kwa muhia and Kamere beach | To implement olkaria waste management plan - purchase and installation of waste disposal bins at kwa muhia and kamere beach for access to clean water and environmental sustainability | Olkaria Waste Management Plan - Purchase and installation of waste disposal bins at Kwa muhia and Kamere beach completed | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | OLKARIA | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 5300000 | 5300000 | Equitable | N/A | 5300000 | 0 | 1999956 | 37.7 | 1999956 | 3300044 | 3300044 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
8623 | Water and Sewerage Management | Piping and tank installation at sher kasarani | To provide water distribution infrastructure at and tank installation at sher kasarani | Water piping at and tank installation at sher kasarani completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | 0.836945, 36.357213 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1988876 | 99.4 | 1988876 | 1988876 | 11124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
8624 | Water and Sewerage Management | piping and tanks installation at Narasha | To provide water distribution infrastructure at and tanks installation at Narasha | Water piping at and tanks installation at Narasha completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1899987 | 95 | 1899987 | 2000000 | 100013 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
8625 | Water and Sewerage Management | Purchase of dust bins to schools i.e Narasha,mvuke,mara and sher moi | To procure dust bins to schools i.e Narasha,mvuke,mara and sher moi | Dust bins to schools i.e Narasha,mvuke,mara and sher moi procured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.918139, 36.267024 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
8626 | Water and Sewerage Management | Construction of sewer line at public toilet in pondamali | To construct sewer line at public toilet in pondamali | Sewer line at public toilet in pondamali constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1248085 | 1248085 | 1248085 | Equitable | N/A | 1248085 | 0 | 0 | 0 | 0 | 1248085 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8627 | Water and Sewerage Management | Purchase and installation of plastic garbage bins in Subukia | To procure and install plastic garbage bins in Subukia | Plastic garbage bins in Subukia procured and installed | 3110504 | Other Infrastructure and Civil Works | SUBUKIA | SUBUKIA | 0.002948 36.229185 1993.0999755859375 52.52199935913086 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 637536 | 94.5 | 637536 | 674464 | 36928 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The business community and road users are enjoying the service. Security improved.s.
8628 | Water and Sewerage Management | Renovation of Chemasis water intake | To rehabilitate Chemasis water intake to restore functionality | Chemasis water intake rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.176262, 36.176939 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 995268 | 0 | 995268 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
8629 | Water and Sewerage Management | Purchase and installation of Edgewood Borehole Solar Panels | To procure and install Edgewood Borehole Solar Panels | Edgewood Borehole Solar Panels procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.017333, 36.198352 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 11/03/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996662 | 99.8 | 1996662 | 2000000 | 3338 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes the project was successful.. Contractor: Information not available. Assessor remarks: Good work with the panels.
8630 | Water and Sewerage Management | Purchase and installation of plastic garbage bins in Subukia | To procure and install plastic garbage bins in Subukia | Plastic garbage bins in Subukia procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.002948 36.229185 1993.0999755859375 52.52199935913086 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 637536 | 94.5 | 637536 | 674464 | 36928 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The business community and road users are enjoying the service. Security improved.s.
8631 | Water and Sewerage Management | repair of tank at Gathima Kirengero | To rehabilitate tank at Gathima Kirengero to restore functionality | Tank at Gathima Kirengero rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.030926 36.197107 2206.2999999999997 30 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 299999 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The school has only one ECDE classroom, without a toilet. Toilet URGENTLY needed.
8632 | Water and Sewerage Management | Construction of 50m3 tank at Mkorombosi | To construct 50m3 tank at Mkorombosi | 50m3 tank at Mkorombosi constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.330793, 35.753182 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 891023 | 99 | 891023 | 900000 | 8977 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: People are happy with the project.
8633 | Water and Sewerage Management | Supply of water pipes for Ndenderu A farm | To implement supply of water pipes for ndenderu a farm for access to clean water and environmental sustainability | Supply of water pipes for Ndenderu A farm completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.306118, 35.750638 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 480000 | 480000 | 480000 | Equitable | N/A | 480000 | 0 | 1499906 | 312.5 | 1499906 | 480000 | -1019906 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
8634 | Water and Sewerage Management | Rehabilitation of Municipal Park | To rehabilitate Municipal Park to restore functionality | Municipal Park rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.71433 36.434014 1901.0999755859375 0.5360000133514404 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3223399 | 3223399 | 3223399 | Equitable | N/A | 3223399 | 0 | 0 | 0 | 0 | 3223399 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Amount allocated not justifiable.
8635 | Environmental Management | Nyayo Gardens - Rehabilitation of Nyayo Gardens (Ongoing 2017/18) | To implement nyayo gardens - rehabilitation of nyayo gardens (ongoing 2017/18) for access to clean water and environmental sustainability | Nyayo Gardens - Rehabilitation of Nyayo Gardens (Ongoing 2017/18) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 6957806 | 6957806 | N/A | N/A | 6957806 | 0 | 20000000 | 287.4 | 20000000 | 8000000 | -13042194 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8636 | Water and Sewerage Management | Rehabilitation of Municipal Park | To rehabilitate Municipal Park to restore functionality | Municipal Park rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.71433 36.434014 1901.0999755859375 0.5360000133514404 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 3750000 | 3750000 | Equitable | N/A | 3750000 | 0 | 0 | 0 | 0 | 3223399 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Amount allocated not justifiable.
8637 | Water and Sewerage Management | Fabrication of waste skip loader | To implement fabrication of waste skip loader for access to clean water and environmental sustainability | Fabrication of waste skip loader completed | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 4970000 | 0 | 4970000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8638 | Environmental Management | Procurement of waste trolleys 100 No. | To procure and supply waste trolleys 100 No | Waste trolleys 100 No procured and supplied | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 999758 | 100 | 999758 | 1000000 | 242 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
8639 | Water and Sewerage Management | Purchase Of 2 No. Refuse Trucks for Naivasha And Bahati/Subukia | To procure 2 No. Refuse Trucks for Naivasha And Bahati/Subukia | 2 No. Refuse Trucks for Naivasha And Bahati/Subukia procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 8000000 | 100 | 8000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8640 | Water and Sewerage Management | Purchase of 5No. Skips | To procure 5No. Skips | 5No. Skips procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 3000000 | 10400000 | 10400000 | Equitable | N/A | 10400000 | 0 | 2494000 | 24 | 2494000 | 1900000 | 7906000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8641 | Water and Sewerage Management | Purchase of Skip Loader (Tractor) | To procure Skip Loader (Tractor) | Skip Loader (Tractor) procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 7849770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8642 | Water and Sewerage Management | Purchase of Skip Loader (Truck) | To procure Skip Loader (Truck) | Skip Loader (Truck) procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 7849770 | 7849770 | N/A | N/A | 7849770 | 0 | 7849770 | 100 | 7849770 | 7849770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8643 | Water and Sewerage Management | Electronic Theodolite (2 No.) | To implement electronic theodolite (2 no.) for access to clean water and environmental sustainability | Electronic Theodolite (2 No.) completed | 3111114 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 3000000 | 5000000 | N/A | N/A | 5000000 | 0 | 5000000 | 166.7 | 5000000 | 3000000 | -2000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8644 | Water and Sewerage Management | Purchase of Terrameter (1 No.) | To procure Terrameter (1 No.) | Terrameter (1 No.) procured | 3111114 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 13000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 5800000 | 72.5 | 5800000 | 1000000 | 2200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8645 | Water and Sewerage Management | Quantum GPS(2 No.) | To implement quantum gps(2 no.) for access to clean water and environmental sustainability | Quantum GPS(2 No.) completed | 3111114 | N/A | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8646 | Water and Sewerage Management | Servicing of tractor in Environment | To implement servicing of tractor in environment for access to clean water and environmental sustainability | Servicing of tractor in Environment completed | 3111201 | Overhaul of Plant, Machinery and Equipment | MOLO | ELBURGON | -0.308342 35.807555 2442.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398900 | 99.7 | 398900 | 1100 | 1100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
8647 | Water and Sewerage Management | Servicing of tractor in Environment | To implement servicing of tractor in environment for access to clean water and environmental sustainability | Servicing of tractor in Environment completed | 3111201 | Overhaul of Plant, Machinery and Equipment | Molo | Elburgon | -0.308342 35.807555 2442.7 11.300000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398900 | 99.7 | 398900 | 1100 | 1100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
8648 | Water and Sewerage Management | Beautification and rehabilitation of Naivasha Gardens | To implement beautification and rehabilitation of naivasha gardens for access to clean water and environmental sustainability | Beautification and rehabilitation of Naivasha Gardens completed | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 19000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 20000000 | 250 | 20000000 | 8000000 | -12000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8649 | Water and Sewerage Management | Tree nursery seedlings | To implement tree nursery seedlings for access to clean water and environmental sustainability | Tree nursery seedlings completed | 3111305 | Beautification and Tree Planting | Nakuru West | Barut | -0.3654 36.05454 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398300 | 99.6 | 398300 | 400000 | 1700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GREAT RIFT GENERAL MERCHANTS. Assessor remarks: Completed.
8650 | Environmental Management | Climate Change Mitigation and Adaptation (Tree Growing) | To implement climate change mitigation and adaptation (tree growing) for access to clean water and environmental sustainability | Climate Change Mitigation and Adaptation (Tree Growing) completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 20000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 4997450 | 99.9 | 4997450 | 2550 | 2550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8651 | Water and Sewerage Management | Tree planting in Kamara ward | To implement tree planting in kamara ward for access to clean water and environmental sustainability | Tree planting in Kamara ward completed | 3111305 | Beautification and Tree Planting | KURESOI NORTH | KAMARA | -0.17061 35.72264 2489.5 3.700000047683716 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998780 | 99.9 | 1998780 | 0 | 1220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
8652 | Water and Sewerage Management | Acquisition of tree seedlings in Kiptororo Ward | To procure tree seedlings in Kiptororo Ward | Tree seedlings in Kiptororo Ward procured | 3111305 | Beautification and Tree Planting | KURESOI NORTH | KIPTORORO | -0.377203 35.505747 0 800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2498886.7 | 2498886.7 | 2498886.7 | Equitable | N/A | 2498886.7 | 0 | 1139835 | 45.6 | 1139835 | 1052 | 1359051.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
8653 | Water and Sewerage Management | Planting trees to rehabilitate river ndarugu | To implement planting trees to rehabilitate river ndarugu for access to clean water and environmental sustainability | Planting trees to rehabilitate river ndarugu completed | 3111305 | Beautification and Tree Planting | Nakuru West | Kaptembwo | -0.311443 36.059645 1781.5999755859375 4.184999942779541 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1840507 | 92 | 1840507 | 159493 | 159493 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: U193. Assessor remarks: Not yet levellized.
8654 | Water and Sewerage Management | Tree seedlings for kihingo ward | To implement tree seedlings for kihingo ward for access to clean water and environmental sustainability | Tree seedlings for kihingo ward completed | 3111305 | Beautification and Tree Planting | Njoro | Kihingo | -0.443013 35.969212 2274.8 8.800000190734863 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997500 | 99.8 | 997500 | 2500 | 2500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Requires fencing, levelling and installation of goalposts.
8655 | Water and Sewerage Management | Acquisition of tree seedlings in Kiptororo Ward | To procure tree seedlings in Kiptororo Ward | Tree seedlings in Kiptororo Ward procured | 3111305 | Beautification and Tree Planting | Kuresoi North | Kiptororo | -0.377203 35.505747 0 800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2498886.7 | 1140886.7 | 1140886.7 | Equitable | N/A | 1140886.7 | 0 | 1139835 | 99.9 | 1139835 | 1052 | 1051.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
8656 | Water and Sewerage Management | Tree Planting at Kijabe water catchments | To implement tree planting at kijabe water catchments for access to clean water and environmental sustainability | Tree Planting at Kijabe water catchments completed | 3111305 | Beautification and Tree Planting | NAIVASHA | MAAI MAHIU | -1.062633, 36.549497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 970000 | 97 | 970000 | 970000 | 30000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
8657 | Water and Sewerage Management | Tree Planting at Namucha water catchments | To implement tree planting at namucha water catchments for access to clean water and environmental sustainability | Tree Planting at Namucha water catchments completed | 3111305 | Beautification and Tree Planting | NAIVASHA | MAAI MAHIU | -1.062633, 36.549497 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998176 | 99.8 | 998176 | 1000000 | 1824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
8658 | Water and Sewerage Management | Malewa west ward planting trees | To implement malewa west ward planting trees for access to clean water and environmental sustainability | Malewa west ward planting trees completed | 3111305 | Beautification and Tree Planting | GILGIL | MALEWA WEST | -0.720721 36.471354 0 2000 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8659 | Water and Sewerage Management | Purchase of tree seedlings | To procure tree seedlings | Tree seedlings procured | 3111305 | Beautification and Tree Planting | Njoro | Njoro | -0.305133 35.915642 2158.858642578125 27.304000854492188 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2356253 | 98.2 | 2356253 | 43747 | 43747 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mamenyi Solutions. Assessor remarks: In good state.
8660 | Water and Sewerage Management | climate Change Mitigation and Adaptation- planting / growing of trees | To implement climate change mitigation and adaptation- planting / growing of trees for access to clean water and environmental sustainability | climate Change Mitigation and Adaptation- planting / growing of trees completed | 3111305 | Beautification and Tree Planting | NAIVASHA | OLKARIA | -0.816383 36.324117 1932.699951171875 7.5 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999232 | 100 | 2999232 | 0 | 768 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been damaged by rain so requires maintenance.
8661 | Water and Sewerage Management | Climate change mitigation(planting trees) in 2 schools-Olkaria and Narasha Primary | To implement climate change mitigation(planting trees) in 2 schools-olkaria and narasha primary for access to clean water and environmental sustainability | Climate change mitigation(planting trees) in 2 schools-Olkaria and Narasha Primary completed | 3111305 | Beautification and Tree Planting | Naivasha | Olkaria | -0.918725, 36.267243 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499793 | 100 | 1499793 | 1500000 | 207 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The trees dried up due to harsh weather.
8662 | Water and Sewerage Management | Purchase of tree seedlings (public institutions) | To procure tree seedlings (public institutions) | Tree seedlings (public institutions) procured | 3111305 | Beautification and Tree Planting | KURESOI NORTH | SIRIKWA | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990800 | 99.5 | 1990800 | 0 | 9200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8663 | Water and Sewerage Management | supply of indigenous tree seedlings | To implement supply of indigenous tree seedlings for access to clean water and environmental sustainability | supply of indigenous tree seedlings completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Kiptororo | -0.406703 35.561853 0 800 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1896773 | 99.8 | 1896773 | 3228 | 3227 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
8664 | Water and Sewerage Management | Physical Planning relating to energy | To implement physical planning relating to energy for access to clean water and environmental sustainability | Physical Planning relating to energy completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8665 | Water and Sewerage Management | Purchase of land for Kirima water project | To acquire land for Kirima water project | Land for Kirima water project acquired | 3130101 | Acquisition of Land | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2529000 | 2529000 | 2529000 | Equitable | N/A | 2529000 | 0 | 0 | 0 | 0 | 2529000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8666 | Water and Sewerage Management | Purchase of Dumpsites | To procure Dumpsites | Dumpsites procured | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 14790000 | 14790000 | N/A | N/A | 14790000 | 0 | 14790000 | 100 | 14790000 | 14790000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8667 | Water and Sewerage Management | Purchase of Waste Disposal Sites(Waste Transfer Stations) | To procure Waste Disposal Sites(Waste Transfer Stations) | Waste Disposal Sites(Waste Transfer Stations) procured | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 13613000 | 90.8 | 13613000 | 1387000 | 1387000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8668 | Water and Sewerage Management | Purchase of land and drilling of new Ingobor borehole and equipping | To acquire land for and drilling of new Ingobor borehole and equipping | Land for and drilling of new Ingobor borehole and equipping acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.018533 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 5000000 | 2437096.6 | 2437096.6 | Equitable | N/A | 2437096.6 | 0 | 2431841 | 99.8 | 2431841 | 5256 | 5255.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operational.
8669 | Water and Sewerage Management | purchase of land for Green valley water project | To acquire land for Green valley water project | Land for Green valley water project acquired | 3130101 | Acquisition of Land | GILGIL | MALEWA WEST | -0.695009, 36.48094 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 599999 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 699583 | 58.3 | 699583 | 1200000 | 500417 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8670 | Water and Sewerage Management | purchase of land for Green valley water project | To acquire land for Green valley water project | Land for Green valley water project acquired | 3130101 | Acquisition of Land | Gilgil | Malewa West | -0.695009, 36.48094 | VOTE NO 4572 | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | MINISTRY OF WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 599999 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 699583 | 58.3 | 699583 | 1200000 | 500417 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8671 | Debt Management (outstanding legal fees) | Debt Management (outstanding legal fees) | To implement debt management (outstanding legal fees) for improved service delivery | Debt Management (outstanding legal fees) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 15853014 | 15853014 | 15853014 | N/A | N/A | 15853014 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8672 | KRA tax arrears | KRA tax arrears | To implement kra tax arrears for improved service delivery | KRA tax arrears completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 45000000 | 45000000 | 29523687 | N/A | N/A | 29523687 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8673 | Construction Of Speakers House | Construction Of Speakers House | To construct Speakers House | Speakers House constructed | 3110199 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/19 | 2018/19 | 60155707 | 30129553 | 23129553 | N/A | N/A | 23129553 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8674 | Construction of Speakers House | Construction of Speakers House | To construct Speakers House | Speakers House constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 24329683.6 | 24329683.6 | N/A | N/A | 24329683.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8675 | Completion Of The Office Block | Completion Of The Office Block | To complete The Office Block | The Office Block completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/19 | 2018/19 | 281822818 | 28716902.95 | 21207098.95 | N/A | N/A | 21207098.95 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8676 | Completion of Office Block | Completion of Office Block | To complete Office Block | Office Block completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 4173827.9 | 4173827.9 | N/A | N/A | 4173827.9 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8677 | Completion of the Phase II office Block | Completion of the Phase II office Block | To complete the Phase II office Block | The Phase II office Block completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 91700000 | 91700000 | 91700000 | N/A | N/A | 91700000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8678 | Construction of Phase II Block and Consultancy | Construction of Phase II Block and Consultancy | To construct Phase II Block and Consultancy | Phase II Block and Consultancy constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2019/20 | 2019/20 | 10025725 | 20051450 | 20051450 | N/A | N/A | 20051450 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8679 | Construction of Phase II Block | Construction of Phase II Block | To construct Phase II Block | Phase II Block constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2020/21 | 2020/21 | 2020/21 | 173030084 | 290847506.5 | 290847506.5 | N/A | N/A | 290847506.5 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8680 | Construction Of Phase II Office Block And Consultancy | Construction Of Phase II Office Block And Consultancy | To construct Phase II Office Block And Consultancy | Phase II Office Block And Consultancy constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/19 | 2018/19 | 62154769 | 35000000.15 | 35000000.15 | N/A | N/A | 35000000.15 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8681 | Construction Of Phase II Office Block | Construction Of Phase II Office Block | To construct Phase II Office Block | Phase II Office Block constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2019/20 | 2019/20 | 180282875 | 134833908 | 155833908 | N/A | N/A | 155833908 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8682 | Refurbishment Of Buildings | Refurbishment Of Buildings | To implement refurbishment of buildings for improved service delivery | Refurbishment Of Buildings completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/19 | 2018/19 | 47338255 | 15086946 | 5086946 | N/A | N/A | 5086946 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8683 | Refurbishment of Building | Refurbishment of Building | To implement refurbishment of building for improved service delivery | Refurbishment of Building completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2019/20 | 2019/20 | 4012500 | 5403534.15 | 4403534.15 | N/A | N/A | 4403534.15 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8684 | Refurbishment of Hansard Equipment | Refurbishment of Hansard Equipment | To implement refurbishment of hansard equipment for improved service delivery | Refurbishment of Hansard Equipment completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2019/20 | 2019/20 | 40028000 | 87390067.55 | 119376184.55 | N/A | N/A | 119376184.55 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8685 | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities | To implement refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities for improved service delivery | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 17300000 | 15300000 | 15300000 | N/A | N/A | 15300000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8686 | Completion of Public Gallery | Completion of Public Gallery | To complete Public Gallery | Public Gallery completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2019/20 | 2019/20 | 2080000 | 5197922.5 | 5197922.5 | N/A | N/A | 5197922.5 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8687 | Construction of Perimeter wall / security gate at the Rear | Construction of Perimeter wall / security gate at the Rear | To construct Perimeter wall / security gate at the Rear | Perimeter wall / security gate at the Rear constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8688 | Driveway / cabro paving | Driveway / cabro paving | To implement driveway / cabro paving for improved service delivery | Driveway / cabro paving completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8689 | Equipping and Configuration of the Chamber | Equipping and Configuration of the Chamber | To equip and Configuration of the Chamber with necessary facilities and equipment | And Configuration of the Chamber equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2019/20 | 2019/20 | 3012980.95 | 10528942.9 | 6528942.9 | N/A | N/A | 6528942.9 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8690 | Landscaping of Speakers House | Landscaping of Speakers House | To implement landscaping of speakers house for improved service delivery | Landscaping of Speakers House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8691 | Purchase and installation of a water treatment plant | Purchase and installation of a water treatment plant | To procure and install a water treatment plant | A water treatment plant procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 7123120 | 8123120 | N/A | N/A | 8123120 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8692 | Development of the Strategic Plan | Development of the Strategic Plan | To develop the Strategic Plan | The Strategic Plan developed | 3111403 | Research | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4573 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2019/20 | 2021/22 | 2021/22 | 3000000 | 12830720 | 16830720 | N/A | N/A | 16830720 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8693 | Administration, Planning and Support Services | Construction of Ward Offices in Gilgil Sub County | To construct Ward Offices in Gilgil Sub County | Ward Offices in Gilgil Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 4375390 | 4375390 | N/A | N/A | 4375390 | 0 | 1659800 | 37.9 | 1659800 | 1659800 | 2715590 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8694 | Administration, Planning and Support Services | Construction of Ward Offices in Lanet Umoja in Sub County | To construct Ward Offices in Lanet Umoja in Sub County | Ward Offices in Lanet Umoja in Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 4634142 | 4634142 | N/A | N/A | 4634142 | 0 | 1692600 | 36.5 | 1692600 | 1692600 | 2941542 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8695 | Administration, Planning and Support Services | Construction of Ward Offices in Molo Sub County | To construct Ward Offices in Molo Sub County | Ward Offices in Molo Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 4791960 | 4791960 | N/A | N/A | 4791960 | 0 | 2483870 | 51.8 | 2483870 | 2483870 | 2308090 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8696 | Administration, Planning and Support Services | Construction of Ward Offices in Nakuru West Sub County | To construct Ward Offices in Nakuru West Sub County | Ward Offices in Nakuru West Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 4538465 | 4538465 | N/A | N/A | 4538465 | 0 | 4629722 | 102 | 4629722 | 4629722 | -91257 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8697 | Administration, Planning and Support Services | Construction of Ward Offices in Njoro Sub County | To construct Ward Offices in Njoro Sub County | Ward Offices in Njoro Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 4720882 | 4720882 | N/A | N/A | 4720882 | 0 | 4533975 | 96 | 4533975 | 4484600 | 186907 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8698 | Administration, Planning and Support Services | Construction of Ward Offices in Rongai Sub County | To construct Ward Offices in Rongai Sub County | Ward Offices in Rongai Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 4500510 | 4500510 | N/A | N/A | 4500510 | 0 | 1569650 | 34.9 | 1569650 | 1569650 | 2930860 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8699 | Administration, Planning and Support Services | Construction of Ward Offices in Subukia Sub County | To construct Ward Offices in Subukia Sub County | Ward Offices in Subukia Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | N/A | 8700000 | 6700000 | 6700000 | N/A | N/A | 6700000 | 0 | 2843795 | 42.4 | 2843795 | 2844546 | 3856205 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8700 | County Coordination of Policy formulation | Construction of Kiptangwanyi ward administration block | To construct Kiptangwanyi ward administration block | Kiptangwanyi ward administration block constructed | 3110299 | Construction of Buildings - Ot | Gilgil | Elementaita | -0.567447, 36.114695 | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 14500000 | 21826940 | 14826940 | Equitable | N/A | 14826940 | 0 | 7315640 | 33.5 | 7315640 | 7326940 | 14511300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8701 | County Coordination of Policy formulation | Construction of a toilet in Mosop Ward, Kiamaina Ward, Gilgil Town Ward and Kabatini Ward | To construct a toilet in Mosop Ward, Kiamaina Ward, Gilgil Town Ward and Kabatini Ward | A toilet in Mosop Ward, Kiamaina Ward, Gilgil Town Ward and Kabatini Ward constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 2800000 | 2800000 | 2800000 | N/A | N/A | 2800000 | 0 | 2800000 | 100 | 2800000 | 2800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8702 | General Administration, Planning and Support Services | Fencing of ward admin block | To secure ward admin block through fencing | Ward admin block fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.313599, 36.067283 | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | 20/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1269272 | 84.6 | 1269272 | 1500000 | 230728 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Worksman international CO. LTD.
8703 | County Coordination of Policy formulation | Purchase of lorry (Canter) | To procure lorry (Canter) | Lorry (Canter) procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 5121000 | 85.4 | 5121000 | 0 | 879000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8704 | County Coordination of Policy formulation | Bahati Sub County offices | To implement bahati sub county offices for improved service delivery | Bahati Sub County offices completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 2420537.2 | 2420537.2 | 2420537.2 | N/A | N/A | 2420537.2 | 0 | 2420537 | 100 | 2420537 | 0 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8705 | County Coordination of Policy formulation | Gilgil Sub County Offices | To implement gilgil sub county offices for improved service delivery | Gilgil Sub County Offices completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 3643507.52 | 2922333.17 | 2922333.17 | N/A | N/A | 2922333.17 | 0 | 2922333 | 100 | 2922333 | 0 | 0.17 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8706 | County Coordination of Policy formulation | Naivasha sub county offices | To implement naivasha sub county offices for improved service delivery | Naivasha sub county offices completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 2497575 | 227606.95 | 227606.95 | N/A | N/A | 227606.95 | 0 | 227607 | 100 | 227607 | 0 | -0.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8707 | County Coordination of Policy formulation | Nakuru East Sub county Offices | To implement nakuru east sub county offices for improved service delivery | Nakuru East Sub county Offices completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 5012775.7 | 969861.4 | 969861.4 | N/A | N/A | 969861.4 | 0 | 969861 | 100 | 969861 | 0 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8708 | County Coordination of Policy formulation | Rongai Sub County offices | To implement rongai sub county offices for improved service delivery | Rongai Sub County offices completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4574 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/19 | 2018/19 | 1199915.6 | 685374.4 | 685374.4 | N/A | N/A | 685374.4 | 0 | 685374 | 100 | 685374 | 0 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8709 | Conditional Allocation for Rehabilitation of Youth Polytechnics | Conditional Allocation for Rehabilitation of Youth Polytechnics | To implement conditional allocation for rehabilitation of youth polytechnics for access to quality education and training | Conditional Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2020/21 | N/A | 66289894 | 75152126 | 0 | Equitable | N/A | 0 | 166187324 | 10193360 | 13.6 | 10193360 | 66289894 | 64958766 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8710 | Construction of 1 class and latrines at Subukia primary ECDE | Construction of 1 class and latrines at Subukia primary ECDE | To construct 1 class and latrines at Subukia primary ECDE | 1 class and latrines at Subukia primary ECDE constructed | 3110201 | Residential Buildings (including hostels) | SUBUKIA | SUBUKIA | 0.003143, 36.229305 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 04/03/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2892 | 0.2 | 2892 | 2892 | 1497108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: The project has many learning children. Viable: Yes.. Contractor: Information not available.
8711 | Construction and equipping ECDE class and pupils toilet at Lelaitich primary school | Construction and equipping ECDE class and pupils toilet at Lelaitich primary school | To construct and equip ECDE class and pupils toilet at Lelaitich primary school | ECDE class and pupils toilet at Lelaitich primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.676213, 35.657443 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 646075 | 35.9 | 646075 | 646075 | 1153925 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
8712 | Construction of ECDE classroom at Kabigeriet | Construction of ECDE classroom at Kabigeriet | To construct ECDE classroom at Kabigeriet | ECDE classroom at Kabigeriet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.570777, 35.664768 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2018 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 416194 | 34.7 | 416194 | 1349217 | 783806 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8713 | Construction of one ECD Classroom at Olenguruone D.B.B Primary | Construction of one ECD Classroom at Olenguruone D.B.B Primary | To construct one ECD Classroom at Olenguruone D.B.B Primary | One ECD Classroom at Olenguruone D.B.B Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.589005, 35.685668 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199956 | 100 | 1199956 | 1199956 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8714 | Construction of one ECDE classroom at Gorofa | Construction of one ECDE classroom at Gorofa | To construct one ECDE classroom at Gorofa | One ECDE classroom at Gorofa constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.652603, 35.651755 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199956 | 100 | 1199956 | 1349217 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8715 | Construction of an ECD Classroom at Ndashata ECDE | Construction of an ECD Classroom at Ndashata ECDE | To construct an ECD Classroom at Ndashata ECDE | An ECD Classroom at Ndashata ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.679731 35.639555 2433.82666015625 4.373000144958496 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 416194 | 34.7 | 416194 | 416194 | 783806 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: yes. Assessor remarks: not yet done.
8716 | Construction and equipping ECDE class and pupils toilet at Lelaitich primary school | Construction and equipping ECDE class and pupils toilet at Lelaitich primary school | To construct and equip ECDE class and pupils toilet at Lelaitich primary school | ECDE class and pupils toilet at Lelaitich primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676213, 35.657443 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 646075 | 35.9 | 646075 | 646075 | 1153925 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
8717 | Construction of ECDE classroom at Kabigeriet | Construction of ECDE classroom at Kabigeriet | To construct ECDE classroom at Kabigeriet | ECDE classroom at Kabigeriet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2018 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 416194 | 34.7 | 416194 | 1349217 | 783806 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8718 | Construction of one ECD Classroom at Olenguruone D.B.B Primary | Construction of one ECD Classroom at Olenguruone D.B.B Primary | To construct one ECD Classroom at Olenguruone D.B.B Primary | One ECD Classroom at Olenguruone D.B.B Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.589005, 35.685668 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1199956 | 1199956 | Equitable | Equitable | 1199956 | 0 | 1199956 | 100 | 1199956 | 1199956 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8719 | Construction of one ECDE classroom at Gorofa | Construction of one ECDE classroom at Gorofa | To construct one ECDE classroom at Gorofa | One ECDE classroom at Gorofa constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199956 | 100 | 1199956 | 1349217 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
8720 | Construction of an ECD Classroom at Ndashata ECDE | Construction of an ECD Classroom at Ndashata ECDE | To construct an ECD Classroom at Ndashata ECDE | An ECD Classroom at Ndashata ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.679731 35.639555 2433.82666015625 4.373000144958496 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 416193.8 | 416193.8 | Equitable | N/A | 416193.8 | 0 | 416194 | 100 | 416194 | 416194 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: yes. Assessor remarks: not yet done.
8721 | Construction of an ECDE class Water tank and sanitation facility at Barasta School | Construction of an ECDE class Water tank and sanitation facility at Barasta School | To construct an ECDE class Water tank and sanitation facility at Barasta School | An ECDE class Water tank and sanitation facility at Barasta School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.147818 36.090577 1844.547607421875 6.189000129699707 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
8722 | Construction of an ECDE class Water tank and sanitation facility at St Francis Primary | Construction of an ECDE class Water tank and sanitation facility at St Francis Primary | To construct an ECDE class Water tank and sanitation facility at St Francis Primary | An ECDE class Water tank and sanitation facility at St Francis Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.147818 36.090577 1844.547607421875 6.189000129699707 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 1997862 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
8723 | Construction of Gituru Polytechnic | Construction of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | BIASHARA-NAIVASHA | -0.725923, 36.486655 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019 | 8732944 | 8732944 | 8732944 | Equitable | N/A | 8732944 | 0 | 8683480 | 99.4 | 8683480 | 21997 | 49464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
8724 | Construction of Kinamba Polytechnic | Construction of Kinamba Polytechnic | To construct Kinamba Polytechnic | Kinamba Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | BIASHARA-NAIVASHA | -0.725923, 36.486655 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019 | 9000000 | 9000000 | 9000000 | Equitable | N/A | 9000000 | 0 | 10999070 | 122.2 | 10999070 | 11011771 | -1999070 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
8725 | Renovation of ECD classroom at ST. Joseph Primary school | Renovation of ECD classroom at ST. Joseph Primary school | To rehabilitate ECD classroom at ST. Joseph Primary school to restore functionality | ECD classroom at ST. Joseph Primary school rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | -0.293494, 36.069545 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799356 | 99.9 | 799356 | 0 | 644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Samue’s merchants.
8726 | Construction of an ECDE class Water tank and sanitation facility at Barasta School | Construction of an ECDE class Water tank and sanitation facility at Barasta School | To construct an ECDE class Water tank and sanitation facility at Barasta School | An ECDE class Water tank and sanitation facility at Barasta School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
8727 | Construction of an ECDE class Water tank and sanitation facility at St Francis Primary | Construction of an ECDE class Water tank and sanitation facility at St Francis Primary | To construct an ECDE class Water tank and sanitation facility at St Francis Primary | An ECDE class Water tank and sanitation facility at St Francis Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 1997862.2 | 1997862.2 | Equitable | N/A | 1997862.2 | 0 | 1997862 | 100 | 1997862 | 1997862 | 0.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
8728 | Renovation of bahati wanyororo polytechnic | Renovation of bahati wanyororo polytechnic | To rehabilitate bahati wanyororo polytechnic to restore functionality | Bahati wanyororo polytechnic rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.158496, 36.104997 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No.
8729 | Supply of paints at Jakaranda primary | Supply of paints at Jakaranda primary | To implement supply of paints at jakaranda primary for access to quality education and training | Supply of paints at Jakaranda primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.154613 36.157595 2094.000244140625 6.599999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
8730 | Construction of Gituru Polytechnic | Construction of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.725923, 36.486655 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019 | 8732944 | 8683480 | 8683480 | Equitable | N/A | 8683480 | 0 | 8683480 | 100 | 8683480 | 21997 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
8731 | Construction of Kinamba Polytechnic | Construction of Kinamba Polytechnic | To construct Kinamba Polytechnic | Kinamba Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.725923, 36.486655 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019 | 9000000 | 8970425 | 8970425 | Equitable | N/A | 8970425 | 0 | 10999070 | 122.6 | 10999070 | 11011771 | -2028645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
8732 | Construction of 1 classroom at Cider ECD | Construction of 1 classroom at Cider ECD | To construct 1 classroom at Cider ECD | 1 classroom at Cider ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU-MBARUK | -0.616508, 36.256504 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 6796 | 0.6 | 6796 | 1199996 | 1193204 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
8733 | Construction of 1 classroom at Kelelwa ECD | Construction of 1 classroom at Kelelwa ECD | To construct 1 classroom at Kelelwa ECD | 1 classroom at Kelelwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU-MBARUK | -0.616508, 36.256504 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 6796 | 0.6 | 6796 | 6796 | 1193204 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
8734 | Construction of additional classes at Elburgon Polytechnic | Construction of additional classes at Elburgon Polytechnic | To construct additional classes at Elburgon Polytechnic | Additional classes at Elburgon Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.306273, 35.808072 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8735 | Construction of Sokoro ECDE | Construction of Sokoro ECDE | To construct Sokoro ECDE | Sokoro ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.29731, 35.796388 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | - | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194994 | 99.6 | 1194994 | 1200000 | 5006 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8736 | purchase and construction of Karunga ECDE | purchase and construction of Karunga ECDE | To procure and construction of Karunga ECDE | And construction of Karunga ECDE procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.26052 35.863608 0 6199.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8737 | Construction of ECD classroom and Toilet at Mbombo Primary ECD | Construction of ECD classroom and Toilet at Mbombo Primary ECD | To construct ECD classroom and Toilet at Mbombo Primary ECD | ECD classroom and Toilet at Mbombo Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.566526 36.119802 1961.0999755859375 1.0700000524520874 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 80430 | 4.5 | 80430 | 1799870 | 1719570 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
8738 | Construction of 1 classroom at Cider ECD | Construction of 1 classroom at Cider ECD | To construct 1 classroom at Cider ECD | 1 classroom at Cider ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.616508, 36.256504 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 6796 | 0.6 | 6796 | 1199996 | 1193200 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
8739 | Construction of 1 classroom at Kelelwa ECD | Construction of 1 classroom at Kelelwa ECD | To construct 1 classroom at Kelelwa ECD | 1 classroom at Kelelwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.616508, 36.256504 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 6796 | 0.6 | 6796 | 6796 | 1193200 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
8740 | Construction of kasambara ECD toilets | Construction of kasambara ECD toilets | To construct kasambara ECD toilets | Kasambara ECD toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | -0.3633633062, 36.24275068 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | No information | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 490250 | 98 | 490250 | 500000 | 9750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes it was viable. Contractor: No details.
8741 | Construction of kiungururia toilets ECDE | Construction of kiungururia toilets ECDE | To construct kiungururia toilets ECDE | Kiungururia toilets ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru-Mbaruk | 0.347671, 36.185201 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | Not found | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 490250 | 98 | 490250 | 500000 | 9750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indcated.
8742 | Construction of I ECDE classroom at Kamirithu | Construction of I ECDE classroom at Kamirithu | To construct I ECDE classroom at Kamirithu | I ECDE classroom at Kamirithu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.309157 35.80994 2403.900146484375 10.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1202494.4 | 1202494.4 | Equitable | N/A | 1202494.4 | 0 | 1194994 | 99.4 | 1194994 | 1202494 | 7500.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Funtional.
8743 | Design and construction of mucharage ECDE | Design and construction of mucharage ECDE | To design and construct mucharage ECDE | Mucharage ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.307435 35.749389 0 2599.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repairs and maintainance.
8744 | Design and construction of Nyakiambi karunga ECDE | Design and construction of Nyakiambi karunga ECDE | To design and construct Nyakiambi karunga ECDE | Nyakiambi karunga ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.180252 35.704339 0 3299.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
8745 | Design and construction of Tegat ECDE | Design and construction of Tegat ECDE | To design and construct Tegat ECDE | Tegat ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.27156 35.816038 2145.7 13.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair and maintainance.
8746 | Construction of Matuiku ECDE classroom | Construction of Matuiku ECDE classroom | To construct Matuiku ECDE classroom | Matuiku ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.581133 36.06226 2358 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 80430 | 6.7 | 80430 | 1109905 | 1119570 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state of tepair.
8747 | Construction of ECD Administration block at Lake view ECD | Construction of ECD Administration block at Lake view ECD | To construct ECD Administration block at Lake view ECD | ECD Administration block at Lake view ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | FLAMINGO | -0.305502, 36.07834 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 3495558 | 3495558 | 3495558 | Equitable | N/A | 3495558 | 0 | 3449870 | 98.7 | 3449870 | 1068473 | 45688 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Nalah women company limited.
8748 | Design and construction of 2 no ECDE classes at lake view ECD | Design and construction of 2 no ECDE classes at lake view ECD | To design and construct 2 no ECDE classes at lake view ECD | 2 no ECDE classes at lake view ECD designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | FLAMINGO | -0.305357, 36.078337 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2390952 | 99.6 | 2390952 | 2390952 | 9048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s NaxxyLimited.
8749 | Construction of ECD Administration block at Lake view ECD | Construction of ECD Administration block at Lake view ECD | To construct ECD Administration block at Lake view ECD | ECD Administration block at Lake view ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.305502, 36.07834 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 3495558 | 3449870 | 3449870 | Equitable | N/A | 3449870 | 0 | 3449870 | 100 | 3449870 | 1068473 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Nalah women company limited.
8750 | Design and construction of 2 no ECDE classes at lake view ECD | Design and construction of 2 no ECDE classes at lake view ECD | To design and construct 2 no ECDE classes at lake view ECD | 2 no ECDE classes at lake view ECD designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.305357, 36.078337 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2390952 | 99.6 | 2390952 | 2390952 | 9048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s NaxxyLimited.
8751 | Construction of St. Patrick ECDE one classroom plus furniture | Construction of St. Patrick ECDE one classroom plus furniture | To construct St. Patrick ECDE one classroom plus furniture | St. Patrick ECDE one classroom plus furniture constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.506473, 36.327503 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 3509 | 0.2 | 3509 | 3509 | 1596491 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glasammur construction limited.
8752 | Construction of Teachers B ECDE classroom, toilet block and equipment. | Construction of Teachers B ECDE classroom, toilet block and equipment. | To construct Teachers B ECDE classroom, toilet block and equipment | Teachers B ECDE classroom, toilet block and equipment constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.486074, 36.340162 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1999794 | 100 | 1999794 | 1999794 | 206 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed. Contractor: M/s Mbuma Cintractors.
8753 | Construction of St. Patrick ECDE one classroom plus furniture | Construction of St. Patrick ECDE one classroom plus furniture | To construct St. Patrick ECDE one classroom plus furniture | St. Patrick ECDE one classroom plus furniture constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.506473, 36.327503 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1600000 | 1599994 | 1599994 | Equitable | N/A | 1599994 | 0 | 3509 | 0.2 | 3509 | 3509 | 1596485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glasammur construction limited.
8754 | Construction of Teachers B ECDE classroom, toilet block and equipment. | Construction of Teachers B ECDE classroom, toilet block and equipment. | To construct Teachers B ECDE classroom, toilet block and equipment | Teachers B ECDE classroom, toilet block and equipment constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.486074, 36.340162 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 1999794 | 1999794 | Equitable | Equitable | 1999794 | 0 | 1999794 | 100 | 1999794 | 1999794 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed. Contractor: M/s Mbuma Cintractors.
8755 | Design and construction of Kanyawa ECD classroom,tank,furnitures,swings and toilets | Design and construction of Kanyawa ECD classroom,tank,furnitures,swings and toilets | To design and construct Kanyawa ECD classroom,tank,furnitures,swings and toilets | Kanyawa ECD classroom,tank,furnitures,swings and toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.507742, 36.323612 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1797480 | 89.9 | 1797480 | 2000000 | 202520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8756 | Construction of 1 ECD classrooms at Rubiri Primary ECD and Equipping | Construction of 1 ECD classrooms at Rubiri Primary ECD and Equipping | To construct 1 ECD classrooms at Rubiri Primary ECD and Equipping | 1 ECD classrooms at Rubiri Primary ECD and Equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.805435 36.443733 1926.5 9.605999946594238 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1199658 | 60 | 1199658 | 1199658 | 800342 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class is in good condition.
8757 | Construction of a Rehabilitation Centre at YMCA | Construction of a Rehabilitation Centre at YMCA | To construct a Rehabilitation Centre at YMCA | A Rehabilitation Centre at YMCA constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.778267, 36.429562 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998000 | 99.9 | 2998000 | 2988000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8758 | Construction of 1 ECD classrooms at Rubiri Primary ECD and Equipping | Construction of 1 ECD classrooms at Rubiri Primary ECD and Equipping | To construct 1 ECD classrooms at Rubiri Primary ECD and Equipping | 1 ECD classrooms at Rubiri Primary ECD and Equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.805435 36.443733 1926.5 9.605999946594238 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1199658 | 1199658 | Equitable | Equitable | 1199658 | 0 | 1199658 | 100 | 1199658 | 1199658 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class is in good condition.
8759 | completion of murungaru ECD | completion of murungaru ECD | To complete murungaru ECD | Murungaru ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.185964 36.168814 2112.656005859375 15.793000221252441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1070 | 0.1 | 1070 | 1070 | 998930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
8760 | completion of st john ECD | completion of st john ECD | To complete st john ECD | St john ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.185964 36.168814 2112.656005859375 15.793000221252441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5 | 0 | 5 | 5 | 999995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
8761 | Construction of 1 ECD classroom at Banita ECD | Construction of 1 ECD classroom at Banita ECD | To construct 1 ECD classroom at Banita ECD | 1 ECD classroom at Banita ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.118417, 36.073703 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 37 | 0 | 37 | 37 | 1199963 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
8762 | Construction of 1 ECD classroom Ndungiri ECD | Construction of 1 ECD classroom Ndungiri ECD | To construct 1 ECD classroom Ndungiri ECD | 1 ECD classroom Ndungiri ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.118417, 36.073703 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 37 | 0 | 37 | 40 | 1199963 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
8763 | Construction of 1 Jumatatu ECDE | Construction of 1 Jumatatu ECDE | To construct 1 Jumatatu ECDE | 1 Jumatatu ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.09353 36.13189 0 1787 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 682652 | 56.9 | 682652 | 758890 | 517348 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works ltd. Assessor remarks: Requires water tank and toilets.