8764 | Construction of ECDE class at Kaproret | Construction of ECDE class at Kaproret | To construct ECDE class at Kaproret | ECDE class at Kaproret constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1199975 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8765 | Construction of ECDE class at Kiptenden | Construction of ECDE class at Kiptenden | To construct ECDE class at Kiptenden | ECDE class at Kiptenden constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8766 | Construction of ECDE class at muchorwei | Construction of ECDE class at muchorwei | To construct ECDE class at muchorwei | ECDE class at muchorwei constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8767 | Construction of ECDE class at Tabora | Construction of ECDE class at Tabora | To construct ECDE class at Tabora | ECDE class at Tabora constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1131185 | 94.3 | 1131185 | 1131185 | 68815 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8768 | Construction of a classroom at Tulwet ECD | Construction of a classroom at Tulwet ECD | To construct a classroom at Tulwet ECD | A classroom at Tulwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.32933, 36.034112 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1478771 | 1478771 | 1478771 | Equitable | N/A | 1478771 | 0 | 279231 | 18.9 | 279231 | 279231 | 1199540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ngambo Hardware.
8769 | Construction of administration block at tulwet | Construction of administration block at tulwet | To construct administration block at tulwet | Administration block at tulwet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.288288 36.05451 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 800 | 0.1 | 800 | 1500000 | 1499200 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But not done. Assessor remarks: Not done on the ground.
8770 | Construction of ECD at Kapkures | Construction of ECD at Kapkures | To construct ECD at Kapkures | ECD at Kapkures constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.306306, 36.036551 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 279231 | 8 | 279231 | 3499700 | 3220769 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But class not done.
8771 | Construction of ECD classroom and 2 door pupil toilet at Eleein ngochoch | Construction of ECD classroom and 2 door pupil toilet at Eleein ngochoch | To construct ECD classroom and 2 door pupil toilet at Eleein ngochoch | ECD classroom and 2 door pupil toilet at Eleein ngochoch constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPTEMBWO | -0.321969, 36.057196 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2023 | 1700000 | 1700000 | 1700000 | Equitable | Equitable | 1700000 | 0 | 1699997 | 100 | 1699997 | 1699997 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: CYRUS BOIT.
8772 | Construction and Equipping kiamaina ECDE | Construction and Equipping kiamaina ECDE | To construct and equip kiamaina ECDE | Kiamaina ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.268282 36.11517 1863.800048828125 4.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1798168 | 99.9 | 1798168 | 0 | 1832 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
8773 | Construction of 1 ECD classroom at Mutitu B | Construction of 1 ECD classroom at Mutitu B | To construct 1 ECD classroom at Mutitu B | 1 ECD classroom at Mutitu B constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.433837 35.96382 2225.1000000000004 12.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 219716 | 18.3 | 219716 | 1200000 | 980284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
8774 | Construction of 1 ECD classroom at Njuguini Primary school | Construction of 1 ECD classroom at Njuguini Primary school | To construct 1 ECD classroom at Njuguini Primary school | 1 ECD classroom at Njuguini Primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.426573 35.973733 2247.5 5.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
8775 | Construction of Kipkebei ECD class | Construction of Kipkebei ECD class | To construct Kipkebei ECD class | Kipkebei ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1199995 | 109.1 | 1199995 | 1047500 | -99995 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
8776 | Construction of Lelpanga ECD class | Construction of Lelpanga ECD class | To construct Lelpanga ECD class | Lelpanga ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1800000 | 52340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
8777 | Construction of Ole Tachasis ECD class | Construction of Ole Tachasis ECD class | To construct Ole Tachasis ECD class | Ole Tachasis ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
8778 | Construction of classroom at Kio ECD | Construction of classroom at Kio ECD | To construct classroom at Kio ECD | Classroom at Kio ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199980 | 100 | 1199980 | 1199980 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8779 | Construction of classroom at Kipkewa ECD | Construction of classroom at Kipkewa ECD | To construct classroom at Kipkewa ECD | Classroom at Kipkewa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8780 | Construction of classroom at Kipkoris ECD | Construction of classroom at Kipkoris ECD | To construct classroom at Kipkoris ECD | Classroom at Kipkoris ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199980 | 100 | 1199980 | 1200000 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8781 | Construction of classroom at Kongoi ECD | Construction of classroom at Kongoi ECD | To construct classroom at Kongoi ECD | Classroom at Kongoi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198898 | 99.9 | 1198898 | 1199898 | 1102 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8782 | Construction of classroom at Seguton ECD | Construction of classroom at Seguton ECD | To construct classroom at Seguton ECD | Classroom at Seguton ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199830 | 100 | 1199830 | 1199830 | 170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8783 | Construction of classroom at Taragonik ECD | Construction of classroom at Taragonik ECD | To construct classroom at Taragonik ECD | Classroom at Taragonik ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8784 | Construction of one ECD Classroom at Kaloleni Primary | Construction of one ECD Classroom at Kaloleni Primary | To construct one ECD Classroom at Kaloleni Primary | One ECD Classroom at Kaloleni Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.302534, 36.086781 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
8785 | completion of murungaru ECD | completion of murungaru ECD | To complete murungaru ECD | Murungaru ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.185964 36.168814 2112.656005859375 15.793000221252441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1070 | 0.1 | 1070 | 1070 | 998930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
8786 | completion of st john ECD | completion of st john ECD | To complete st john ECD | St john ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.185964 36.168814 2112.656005859375 15.793000221252441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5 | 0 | 5 | 5 | 999995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
8787 | Construction of 1 ECD classroom at Banita ECD | Construction of 1 ECD classroom at Banita ECD | To construct 1 ECD classroom at Banita ECD | 1 ECD classroom at Banita ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.118417, 36.073703 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1199999 | 1199999 | Equitable | N/A | 1199999 | 0 | 37 | 0 | 37 | 37 | 1199962 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
8788 | Construction of 1 ECD classroom Ndungiri ECD | Construction of 1 ECD classroom Ndungiri ECD | To construct 1 ECD classroom Ndungiri ECD | 1 ECD classroom Ndungiri ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.118417, 36.073703 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 37 | 0 | 37 | 40 | 1199959 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
8789 | Construction of 1 Jumatatu ECDE | Construction of 1 Jumatatu ECDE | To construct 1 Jumatatu ECDE | 1 Jumatatu ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.09353 36.13189 0 1787 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 682652 | 56.9 | 682652 | 758890 | 517348 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works ltd. Assessor remarks: Requires water tank and toilets.
8790 | Construction of ampiva ECD and toilets and completion of Ruiru ECD plus toilets | Construction of ampiva ECD and toilets and completion of Ruiru ECD plus toilets | To construct ampiva ECD and toilets and completion of Ruiru ECD plus toilets | Ampiva ECD and toilets and completion of Ruiru ECD plus toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.12904 36.15429 0 220 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 699162 | 35 | 699162 | 2000000 | 1300838 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
8791 | Construction of ECDE class at Kaproret | Construction of ECDE class at Kaproret | To construct ECDE class at Kaproret | ECDE class at Kaproret constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kamara | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1199999 | 1199999 | Equitable | N/A | 1199999 | 0 | 1199975 | 100 | 1199975 | 1199975 | 24 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8792 | Construction of ECDE class at Tabora | Construction of ECDE class at Tabora | To construct ECDE class at Tabora | ECDE class at Tabora constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kamara | -0.176655, 35.698202 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1131185 | 1131185 | Equitable | N/A | 1131185 | 0 | 1131185 | 100 | 1131185 | 1131185 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
8793 | Construction and equipping of two ECDE classrooms at Kapnandi ECDE | Construction and equipping of two ECDE classrooms at Kapnandi ECDE | To construct and equip two ECDE classrooms at Kapnandi ECDE | Two ECDE classrooms at Kapnandi ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.319488, 36.02239 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3499700 | 3499700 | Equitable | N/A | 3499700 | 0 | 279231 | 8 | 279231 | 3499700 | 3220469 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mugima Enterprises LTD.
8794 | Construction of a classroom at Tulwet ECD | Construction of a classroom at Tulwet ECD | To construct a classroom at Tulwet ECD | A classroom at Tulwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.32933, 36.034112 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1478771 | 1478771 | 1478771 | Equitable | N/A | 1478771 | 0 | 279231 | 18.9 | 279231 | 279231 | 1199540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ngambo Hardware.
8795 | Construction of an administration Block at Ingobor | Construction of an administration Block at Ingobor | To construct an administration Block at Ingobor | An administration Block at Ingobor constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 800 | 0 | 800 | 2500000 | 2499200 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Not constructed. Viable: Viable but has not been implemented. Assessor remarks: Not done.
8796 | Construction of and equipping of a classroom at Tulwet | Construction of and equipping of a classroom at Tulwet | To construct and equipping of a classroom at Tulwet | And equipping of a classroom at Tulwet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 279231 | 18.6 | 279231 | 1500000 | 1220769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved learning environment.
8797 | Construction of ECD classroom and 2 door pupil toilet at Eleein ngochoch | Construction of ECD classroom and 2 door pupil toilet at Eleein ngochoch | To construct ECD classroom and 2 door pupil toilet at Eleein ngochoch | ECD classroom and 2 door pupil toilet at Eleein ngochoch constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.321969, 36.057196 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2023 | 1700000 | 1699997 | 1699997 | Equitable | Equitable | 1699997 | 0 | 1699997 | 100 | 1699997 | 1699997 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: CYRUS BOIT.
8798 | Construction of 1 ECD classroom at Njuguini Primary school | Construction of 1 ECD classroom at Njuguini Primary school | To construct 1 ECD classroom at Njuguini Primary school | 1 ECD classroom at Njuguini Primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Kihingo | -0.426573 35.973733 2247.5 5.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199994 | 1199994 | Equitable | Equitable | 1199994 | 0 | 1199994 | 100 | 1199994 | 1199994 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
8799 | Construction of Kipkebei ECD class | Construction of Kipkebei ECD class | To construct Kipkebei ECD class | Kipkebei ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1199995 | 109.1 | 1199995 | 1047500 | -99995 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
8800 | Construction of Lelpanga ECD class | Construction of Lelpanga ECD class | To construct Lelpanga ECD class | Lelpanga ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1800000 | 52340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
8801 | Construction of Ole Tachasis ECD class | Construction of Ole Tachasis ECD class | To construct Ole Tachasis ECD class | Ole Tachasis ECD class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
8802 | Construction of classroom at Kio ECD | Construction of classroom at Kio ECD | To construct classroom at Kio ECD | Classroom at Kio ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199980 | 1199980 | Equitable | N/A | 1199980 | 0 | 1199980 | 100 | 1199980 | 1199980 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8803 | Construction of classroom at Kipkewa ECD | Construction of classroom at Kipkewa ECD | To construct classroom at Kipkewa ECD | Classroom at Kipkewa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8804 | Construction of classroom at Kongoi ECD | Construction of classroom at Kongoi ECD | To construct classroom at Kongoi ECD | Classroom at Kongoi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199898.2 | 1199898.2 | Equitable | N/A | 1199898.2 | 0 | 1198898 | 99.9 | 1198898 | 1199898 | 1000.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8805 | Construction of classroom at Seguton ECD | Construction of classroom at Seguton ECD | To construct classroom at Seguton ECD | Classroom at Seguton ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199830 | 1199830 | Equitable | N/A | 1199830 | 0 | 1199830 | 100 | 1199830 | 1199830 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8806 | Construction of classroom at Taragonik ECD | Construction of classroom at Taragonik ECD | To construct classroom at Taragonik ECD | Classroom at Taragonik ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
8807 | Construction of one ECD Classroom at Kaloleni Primary | Construction of one ECD Classroom at Kaloleni Primary | To construct one ECD Classroom at Kaloleni Primary | One ECD Classroom at Kaloleni Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Kivumbini | -0.302534, 36.086781 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199994 | 1199994 | Equitable | Equitable | 1199994 | 0 | 1199994 | 100 | 1199994 | 1199994 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
8808 | Construction of a daycare centre at Kihoto | Construction of a daycare centre at Kihoto | To construct a daycare centre at Kihoto | A daycare centre at Kihoto constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.734134, 36.436222 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 3430230 | 3430230 | 3430230 | Equitable | N/A | 3430230 | 0 | 7157555 | 208.7 | 7157555 | 3396260 | -3727325 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: The project is construction of 5 day care classrooms. Viable: No.
8809 | Construction of classroom at Prison ECD | Construction of classroom at Prison ECD | To construct classroom at Prison ECD | Classroom at Prison ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.273641, 36.058444 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 221 | 0 | 221 | 221 | 1199779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8810 | Construction of classroom at Uhuru primary ECD | Construction of classroom at Uhuru primary ECD | To construct classroom at Uhuru primary ECD | Classroom at Uhuru primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.273641, 36.058444 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 221 | 0 | 221 | 1480 | 1199779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8811 | Design and construction ECD Classroom and Equipping at Umoja Primary School | Design and construction ECD Classroom and Equipping at Umoja Primary School | To design and construct ECD Classroom and Equipping at Umoja Primary School | ECD Classroom and Equipping at Umoja Primary School designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Lanet/Umoja | -0.269832, 36.164046 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/2021 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1695002 | 94.2 | 1695002 | 1800000 | 104998 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
8812 | Construction of classroom at Prison ECD | Construction of classroom at Prison ECD | To construct classroom at Prison ECD | Classroom at Prison ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.273641, 36.058444 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 221 | 0 | 221 | 221 | 1199779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8813 | Construction of classroom at Uhuru primary ECD | Construction of classroom at Uhuru primary ECD | To construct classroom at Uhuru primary ECD | Classroom at Uhuru primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.273641, 36.058444 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 221 | 0 | 221 | 1480 | 1199779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8814 | 1 ECD class at Ngeya primary | 1 ECD class at Ngeya primary | To implement 1 ecd class at ngeya primary for access to quality education and training | 1 ECD class at Ngeya primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAAI MAHIU | -0.979769, 36.583913 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 955540 | 79.6 | 955540 | 1200000 | 244460 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8815 | Completion of a polytechnic at Kipkonyo | Completion of a polytechnic at Kipkonyo | To complete a polytechnic at Kipkonyo | A polytechnic at Kipkonyo completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3894092 | 97.4 | 3894092 | 577071 | 105908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
8816 | Completion of a Polytechnic at Ndabibi | Completion of a Polytechnic at Ndabibi | To complete a Polytechnic at Ndabibi | A Polytechnic at Ndabibi completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.804803 36.246244 0 22.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3894092 | 97.4 | 3894092 | 105908 | 105908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
8817 | Completion of a Polytechnic in Maiella | Completion of a Polytechnic in Maiella | To complete a Polytechnic in Maiella | A Polytechnic in Maiella completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 826780 | 82.7 | 826780 | 172500 | 173220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
8818 | Construction of 2 ECD classes at Tumaini | Construction of 2 ECD classes at Tumaini | To construct 2 ECD classes at Tumaini | 2 ECD classes at Tumaini constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.831127 36.203445 2035.699951171875 87.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2499394 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
8819 | Construction of ECDE classroom at Block Ten | Construction of ECDE classroom at Block Ten | To construct ECDE classroom at Block Ten | ECDE classroom at Block Ten constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIASHONI | -0.396822, 35.792966 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 801480 | 66.8 | 801480 | 1177200 | 398520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8820 | Construction of ECDE classroom at Kapmungei | Construction of ECDE classroom at Kapmungei | To construct ECDE classroom at Kapmungei | ECDE classroom at Kapmungei constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIASHONI | -0.396822, 35.792966 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 260 | 0 | 260 | 260 | 1399740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8821 | Construction of Kalyet ECDE classroom | Construction of Kalyet ECDE classroom | To construct Kalyet ECDE classroom | Kalyet ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIASHONI | -0.353608 35.870252 2418.508656566576 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1177200 | 98.1 | 1177200 | 1177200 | 22800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Poor flooring therefore not functioning.
8822 | construction of 2 ECDE classrooms for Ngwataninro primary school | construction of 2 ECDE classrooms for Ngwataninro primary school | To construct 2 ECDE classrooms for Ngwataninro primary school | 2 ECDE classrooms for Ngwataninro primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.597728 35.995954 0 20 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2381998 | 99.2 | 2381998 | 2400000 | 18002 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
8823 | Construction of an ECD classroom at Gatimu, Mukungugu | Construction of an ECD classroom at Gatimu, Mukungugu | To construct an ECD classroom at Gatimu, Mukungugu | An ECD classroom at Gatimu, Mukungugu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.633, 36.027475 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399998 | 100 | 2399998 | 1500000 | 2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8824 | Construction of a classroom at Bondet ECD | Construction of a classroom at Bondet ECD | To construct a classroom at Bondet ECD | A classroom at Bondet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.46968, 35.968475 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199994 | 100 | 1199994 | 1200000 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8825 | Construction of 2 ECD classrooms and toilets at Kiratina primary school and fencing | Construction of 2 ECD classrooms and toilets at Kiratina primary school and fencing | To construct 2 ECD classrooms and toilets at Kiratina primary school and fencing | 2 ECD classrooms and toilets at Kiratina primary school and fencing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | MENENGAI | -0.290028, 36.121309 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499981 | 100 | 3499981 | 3499975 | 19 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
8826 | Construction of ol rongai polytechnic | Construction of ol rongai polytechnic | To construct ol rongai polytechnic | Ol rongai polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.16156 36.002493 0 1100 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 999240 | 33.3 | 999240 | 3000000 | 2000760 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
8827 | Construction of Kabunia Highway ECD classroom | Construction of Kabunia Highway ECD classroom | To construct Kabunia Highway ECD classroom | Kabunia Highway ECD classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
8828 | Construction of KERMA ECDE Classroom | Construction of KERMA ECDE Classroom | To construct KERMA ECDE Classroom | KERMA ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.279457 35.88394 2110.2 6.099999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
8829 | Renovation of Kerma primary ECD toilets | Renovation of Kerma primary ECD toilets | To rehabilitate Kerma primary ECD toilets to restore functionality | Kerma primary ECD toilets rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.3179 35.967392 2041.9999999999998 18.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497999 | 99.6 | 497999 | 600000 | 2001 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good workmanship.
8830 | Construction of Cura ECD | Construction of Cura ECD | To construct Cura ECD | Cura ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MURINDAT | -0.381786, 36.298667 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Vertex General supplies & supplies construction enterprises ltd.
8831 | 1 ECD class at Ngeya primary | 1 ECD class at Ngeya primary | To implement 1 ecd class at ngeya primary for access to quality education and training | 1 ECD class at Ngeya primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.979769, 36.583913 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 955540 | 79.6 | 955540 | 1200000 | 244460 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8832 | Completion of a polytechnic at Kipkonyo | Completion of a polytechnic at Kipkonyo | To complete a polytechnic at Kipkonyo | A polytechnic at Kipkonyo completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 577071 | 577071 | Equitable | N/A | 577071 | 0 | 3894092 | 674.8 | 3894092 | 577071 | -3317021 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
8833 | Completion of a Polytechnic at Ndabibi | Completion of a Polytechnic at Ndabibi | To complete a Polytechnic at Ndabibi | A Polytechnic at Ndabibi completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 3894092 | 3894092 | Equitable | N/A | 3894092 | 0 | 3894092 | 100 | 3894092 | 105908 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
8834 | Completion of a Polytechnic in Maiella | Completion of a Polytechnic in Maiella | To complete a Polytechnic in Maiella | A Polytechnic in Maiella completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999280 | 999280 | Equitable | N/A | 999280 | 0 | 826780 | 82.7 | 826780 | 172500 | 172500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
8835 | Construction of 2 ECD classes at Tumaini | Construction of 2 ECD classes at Tumaini | To construct 2 ECD classes at Tumaini | 2 ECD classes at Tumaini constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2499394 | 2499394 | Equitable | N/A | 2499394 | 0 | 2499394 | 100 | 2499394 | 2499394 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
8836 | Design and construction of ECD classroom at Natooli | Design and construction of ECD classroom at Natooli | To design and construct ECD classroom at Natooli | ECD classroom at Natooli designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
8837 | Design and construction of ECD classroom at Ndabibi central | Design and construction of ECD classroom at Ndabibi central | To design and construct ECD classroom at Ndabibi central | ECD classroom at Ndabibi central designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2739065 | 2739065 | 2739065 | Equitable | N/A | 2739065 | 0 | 2499394 | 91.2 | 2499394 | 2739065 | 239671 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
8838 | Design and construction of ECD classroom at Ngondi | Design and construction of ECD classroom at Ngondi | To design and construct ECD classroom at Ngondi | ECD classroom at Ngondi designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
8839 | Purchase and supply of school uniforms to Lodia primary,marula primary and gatamayu primary | Purchase and supply of school uniforms to Lodia primary,marula primary and gatamayu primary | To procure and supply school uniforms to Lodia primary,marula primary and gatamayu primary | School uniforms to Lodia primary,marula primary and gatamayu primary procured and supplied | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Equitable | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
8840 | Construction of ECDE classroom at Block Ten | Construction of ECDE classroom at Block Ten | To construct ECDE classroom at Block Ten | ECDE classroom at Block Ten constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.396822, 35.792966 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 801480 | 66.8 | 801480 | 1177200 | 398516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8841 | Construction of ECDE classroom at Kapmungei | Construction of ECDE classroom at Kapmungei | To construct ECDE classroom at Kapmungei | ECDE classroom at Kapmungei constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.396822, 35.792966 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 260 | 0 | 260 | 260 | 1399740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8842 | Construction of Kalyet ECDE classroom | Construction of Kalyet ECDE classroom | To construct Kalyet ECDE classroom | Kalyet ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.353608 35.870252 2418.508656566576 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1177200 | 98.1 | 1177200 | 1177200 | 22800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Poor flooring therefore not functioning.
8843 | Design and construction of classroom at Lawina ECDE and toilets | Design and construction of classroom at Lawina ECDE and toilets | To design and construct classroom at Lawina ECDE and toilets | Classroom at Lawina ECDE and toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.341599 35.822118 2558.0320406425963 6.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1900000 | 95 | 1900000 | 2000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8844 | levelling of playground at Lawina primary school | levelling of playground at Lawina primary school | To implement levelling of playground at lawina primary school for access to quality education and training | levelling of playground at Lawina primary school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.327859, 35.86732 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8845 | construction of 2 ECDE classrooms for Ngwataninro primary school | construction of 2 ECDE classrooms for Ngwataninro primary school | To construct 2 ECDE classrooms for Ngwataninro primary school | 2 ECDE classrooms for Ngwataninro primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.597728 35.995954 0 20 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2381998 | 99.2 | 2381998 | 2400000 | 18002 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
8846 | Design and construction Classroom at Chesoen ECDE | Design and construction Classroom at Chesoen ECDE | To design and construct Classroom at Chesoen ECDE | Classroom at Chesoen ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.543632, 36.030652 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1099992 | 91.7 | 1099992 | 1200000 | 100008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8847 | Completion of stalled classes and rehabilitation of existing classes at ol rongai polytechnic | Completion of stalled classes and rehabilitation of existing classes at ol rongai polytechnic | To complete stalled classes and rehabilitation of existing classes at ol rongai polytechnic | Stalled classes and rehabilitation of existing classes at ol rongai polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.168652, 36.0002 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995421 | 99.8 | 2995421 | 3000000 | 4579 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8848 | Construction of Kabunia Highway ECD classroom | Construction of Kabunia Highway ECD classroom | To construct Kabunia Highway ECD classroom | Kabunia Highway ECD classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
8849 | Design and construction of mugaa ECDE toilets at sachangwan | Design and construction of mugaa ECDE toilets at sachangwan | To design and construct mugaa ECDE toilets at sachangwan | Mugaa ECDE toilets at sachangwan designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
8850 | Construction of baraka youth polytechnic toilets | Construction of baraka youth polytechnic toilets | To construct baraka youth polytechnic toilets | Baraka youth polytechnic toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499994 | 100 | 499994 | 500000 | 6 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
8851 | Construction of KERMA ECDE Classroom | Construction of KERMA ECDE Classroom | To construct KERMA ECDE Classroom | KERMA ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.279457 35.88394 2110.2 6.099999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
8852 | Equipping of baraka youth polytechnic | Equipping of baraka youth polytechnic | To equip baraka youth polytechnic with necessary facilities and equipment | Baraka youth polytechnic equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
8853 | Equipping of Ogilgei youth polytechnic | Equipping of Ogilgei youth polytechnic | To equip Ogilgei youth polytechnic with necessary facilities and equipment | Ogilgei youth polytechnic equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.284455, 35.96628 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1499996 | 300 | 1499996 | 500000 | -999996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable. Contractor: Not awarded.
8854 | Construction of Cura ECD | Construction of Cura ECD | To construct Cura ECD | Cura ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.381786, 36.298667 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Vertex General supplies & supplies construction enterprises ltd.
8855 | Completion of ECD class at Karai | Completion of ECD class at Karai | To complete ECD class at Karai | ECD class at Karai completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.760113, 36.49383 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2017-18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 999352 | 199.9 | 999352 | 500000 | -499352 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8856 | Construction of Vocational Polytechnic at Free area | Construction of Vocational Polytechnic at Free area | To construct Vocational Polytechnic at Free area | Vocational Polytechnic at Free area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | NAKURU EAST | -0.293514 36.118728 1839.199951171875 37.99700164794922 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 5025850 | 50.3 | 5025850 | 4344590 | 4974150 | Stalled | 75 | 50.3 | Stalled — reasons to be confirmed by department | 2019 | N/A | 4974150 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Belistra enterprises ltd. Assessor remarks: No occupation certificate issued.
8857 | Design and construction of Kimugui ECDE classroom | Design and construction of Kimugui ECDE classroom | To design and construct Kimugui ECDE classroom | Kimugui ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.433627 35.887802 2581.822998046875 4.065000057220459 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 569 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The ECDE is a stand alone school. The classroom construction did not meet the standards and therefore the amount allocated didn't meet the required scope of work..
8858 | Construction of ECD classes in mwigito village | Construction of ECD classes in mwigito village | To construct ECD classes in mwigito village | ECD classes in mwigito village constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.385759 35.95324 2212.000244140625 9.197999954223633 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1197000 | 99.8 | 1197000 | 1200000 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Floor completely worn.
8859 | Construction of ECD in njokerio | Construction of ECD in njokerio | To construct ECD in njokerio | ECD in njokerio constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.384841 35.935522 2275.121826171875 4.958000183105469 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2996 | 0.2 | 2996 | 1199996 | 1197004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8860 | Construction of ECD in njoro township primary | Construction of ECD in njoro township primary | To construct ECD in njoro township primary | ECD in njoro township primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.326462, 35.954217 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 3396 | 0.3 | 3396 | 3396 | 1196604 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Contractor: Weigh road Ltd.
8861 | Construction of ECD in sosiot farm | Construction of ECD in sosiot farm | To construct ECD in sosiot farm | ECD in sosiot farm constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.384685 35.935928 2293.6 10.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1798168 | 99.9 | 1798168 | 1798168 | 1832 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
8862 | Completion of Songo ECDE Classroom | Completion of Songo ECDE Classroom | To complete Songo ECDE Classroom | Songo ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.404183 35.662365 2637 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 261174 | 26.1 | 261174 | 998985 | 738826 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sumcott Enterprises. Assessor remarks: Needs urgent painting.
8863 | Construction of Silibonik ECDE Classroom | Construction of Silibonik ECDE Classroom | To construct Silibonik ECDE Classroom | Silibonik ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.346288, 35.588013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021-2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8864 | Construction of Tonongoi ECDE Classroom | Construction of Tonongoi ECDE Classroom | To construct Tonongoi ECDE Classroom | Tonongoi ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.346288, 35.588013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021-2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 261174 | 21.8 | 261174 | 261174 | 938826 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8865 | construction of ECD class at Karai | construction of ECD class at Karai | To construct ECD class at Karai | ECD class at Karai constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.760113, 36.49383 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2017-18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999352 | 99.9 | 999352 | 1000000 | 648 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8866 | Construction of toilet at Sision ECDE | Construction of toilet at Sision ECDE | To construct toilet at Sision ECDE | Toilet at Sision ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.867345 36.535489 2460 5.611999988555908 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 999352 | 199.9 | 999352 | 500000 | -499352 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project combine with another project to construct mateenity.
8867 | Fencing and construction of toilet for kariokor kinungi ECDE | Fencing and construction of toilet for kariokor kinungi ECDE | To secure and construction of toilet for kariokor kinungi ECDE through fencing | And construction of toilet for kariokor kinungi ECDE fenced and secured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.807484, 36.528971 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 359377 | 359377 | 359377 | Equitable | Equitable | 359377 | 0 | 3600022 | 1001.7 | 3600022 | 359377 | -3240645 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
8868 | Repairing of Maraigushu ECDE | Repairing of Maraigushu ECDE | To implement repairing of maraigushu ecde for access to quality education and training | Repairing of Maraigushu ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.75252, 36.527393 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
8869 | Construction of Vocational Polytechnic at Free area | Construction of Vocational Polytechnic at Free area | To construct Vocational Polytechnic at Free area | Vocational Polytechnic at Free area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.293514 36.118728 1839.199951171875 37.99700164794922 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 9370440 | 9370440 | Equitable | N/A | 9370440 | 0 | 5025850 | 53.6 | 5025850 | 4344590 | 4344590 | Stalled | 75 | 53.6 | Stalled — reasons to be confirmed by department | 2019 | N/A | 4344590 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Belistra enterprises ltd. Assessor remarks: No occupation certificate issued.
8870 | Construction of one classroom at James Mwaniki Primary school | Construction of one classroom at James Mwaniki Primary school | To construct one classroom at James Mwaniki Primary school | One classroom at James Mwaniki Primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.445208, 36.146617 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/2021 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 0 | 2715032 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
8871 | Design and construction of 1 ECDE classroom at Naka primary | Design and construction of 1 ECDE classroom at Naka primary | To design and construct 1 ECDE classroom at Naka primary | 1 ECDE classroom at Naka primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.289113 36.103626 1817.699951171875 6.599999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 226.3 | 2715032 | 1200000 | -1515032 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require funds more funds for completion.
8872 | Design and construction of Kimugui ECDE classroom | Design and construction of Kimugui ECDE classroom | To design and construct Kimugui ECDE classroom | Kimugui ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.433627 35.887802 2581.822998046875 4.065000057220459 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 569 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The ECDE is a stand alone school. The classroom construction did not meet the standards and therefore the amount allocated didn't meet the required scope of work..
8873 | Construction of ECD classes in mwigito village | Construction of ECD classes in mwigito village | To construct ECD classes in mwigito village | ECD classes in mwigito village constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.385759 35.95324 2212.000244140625 9.197999954223633 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1197000 | 99.8 | 1197000 | 1200000 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Floor completely worn.
8874 | Construction of ECD in njokerio | Construction of ECD in njokerio | To construct ECD in njokerio | ECD in njokerio constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.384841 35.935522 2275.121826171875 4.958000183105469 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 2996 | 0.2 | 2996 | 1199996 | 1197000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
8875 | Construction of ECD in njoro township primary | Construction of ECD in njoro township primary | To construct ECD in njoro township primary | ECD in njoro township primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.326462, 35.954217 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 3396 | 0.3 | 3396 | 3396 | 1196600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Contractor: Weigh road Ltd.
8876 | Construction of ECD in sosiot farm | Construction of ECD in sosiot farm | To construct ECD in sosiot farm | ECD in sosiot farm constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.384685 35.935928 2293.6 10.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1798168.2 | 1798168.2 | Equitable | N/A | 1798168.2 | 0 | 1798168 | 100 | 1798168 | 1798168 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
8877 | construction of two ECDE classrooms and fixing playing equipments at Sosoit | construction of two ECDE classrooms and fixing playing equipments at Sosoit | To construct two ECDE classrooms and fixing playing equipments at Sosoit | Two ECDE classrooms and fixing playing equipments at Sosoit constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.385759 35.95324 2212.000244140625 9.197999954223633 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2492711 | 2492710 | 2492710 | Equitable | N/A | 2492710 | 0 | 0 | 0 | 0 | 2492710 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Floor completely worn.
8878 | Completion of Songo ECDE Classroom | Completion of Songo ECDE Classroom | To complete Songo ECDE Classroom | Songo ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.404183 35.662365 2637 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 261174 | 26.1 | 261174 | 998985 | 738826 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sumcott Enterprises. Assessor remarks: Needs urgent painting.
8879 | Construction of Silibonik ECDE Classroom | Construction of Silibonik ECDE Classroom | To construct Silibonik ECDE Classroom | Silibonik ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.346288, 35.588013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021-2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8880 | Construction of Tonongoi ECDE Classroom | Construction of Tonongoi ECDE Classroom | To construct Tonongoi ECDE Classroom | Tonongoi ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.346288, 35.588013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021-2022 | 1200000 | 261174.2 | 261174.2 | Equitable | N/A | 261174.2 | 0 | 261174 | 100 | 261174 | 261174 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8881 | Design and construction of kondamet ECDE classroom | Design and construction of kondamet ECDE classroom | To design and construct kondamet ECDE classroom | Kondamet ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.347828, 35.59568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8882 | Design and construction of Teregena ECDE | Design and construction of Teregena ECDE | To design and construct Teregena ECDE | Teregena ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.401607, 35.706659 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8883 | Design and construction of Umoja ECDE classroom | Design and construction of Umoja ECDE classroom | To design and construct Umoja ECDE classroom | Umoja ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.347828, 35.59568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8884 | Construction of two ECDE and toilets at Muslim Primary | Construction of two ECDE and toilets at Muslim Primary | To construct two ECDE and toilets at Muslim Primary | Two ECDE and toilets at Muslim Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAB | -0.293563, 36.051321 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | Equitable | 3000000 | 0 | 2998542 | 100 | 2998542 | 2998542 | 1458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
8885 | Construction of kaptembwo ECD | Construction of kaptembwo ECD | To construct kaptembwo ECD | Kaptembwo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.249117, 35.6819 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187070 | 98.9 | 1187070 | 1200000 | 12930 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not met. Viable: No.
8886 | Construction of kiptenden sirikwa ECD | Construction of kiptenden sirikwa ECD | To construct kiptenden sirikwa ECD | Kiptenden sirikwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.278465 35.661547 2738.7 13.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187070 | 98.9 | 1187070 | 1200000 | 12930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
8887 | 71 ECD class construction | 71 ECD class construction | To implement 71 ecd class construction for access to quality education and training | 71 ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199540 | 100 | 1199540 | 1199540 | 460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8888 | Classroom and workshop construction at Rongai polytechnic | Classroom and workshop construction at Rongai polytechnic | To implement classroom and workshop construction at rongai polytechnic for access to quality education and training | Classroom and workshop construction at Rongai polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.099944, 35.936673 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1455 | 0.1 | 1455 | 1455 | 2498545 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8889 | Kapsetek ECD construction | Kapsetek ECD construction | To implement kapsetek ecd construction for access to quality education and training | Kapsetek ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199898 | 100 | 1199898 | 1199898 | 102 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8890 | Kimamoi ECD class construction | Kimamoi ECD class construction | To implement kimamoi ecd class construction for access to quality education and training | Kimamoi ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 200 | 0 | 200 | 200 | 1199800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8891 | Kimugul ECD class construction | Kimugul ECD class construction | To implement kimugul ecd class construction for access to quality education and training | Kimugul ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 200 | 0 | 200 | 1199540 | 1199800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8892 | Majani mingi 2 ECD Classes construction | Majani mingi 2 ECD Classes construction | To implement majani mingi 2 ecd classes construction for access to quality education and training | Majani mingi 2 ECD Classes construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2398880 | 100 | 2398880 | 2400000 | 1120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8893 | Majani mingi polytechnic class construction (2 classes) | Majani mingi polytechnic class construction (2 classes) | To implement majani mingi polytechnic class construction (2 classes) for access to quality education and training | Majani mingi polytechnic class construction (2 classes) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.041913, 36.024447 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2400000 | 2400000 | 2400000 | Equitable | Equitable | 2400000 | 0 | 2399924 | 100 | 2399924 | 2399924 | 76 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: It was viable but hasn't met the needs.
8894 | Sawaiti ECD construction | Sawaiti ECD construction | To implement sawaiti ecd construction for access to quality education and training | Sawaiti ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1132000 | 94.3 | 1132000 | 1200000 | 68000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8895 | Sinendet ECD class construction | Sinendet ECD class construction | To implement sinendet ecd class construction for access to quality education and training | Sinendet ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199895 | 100 | 1199895 | 1199895 | 105 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8896 | Testai ECD construction | Testai ECD construction | To implement testai ecd construction for access to quality education and training | Testai ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194400 | 99.5 | 1194400 | 1194400 | 5600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8897 | Construction of 1 class at Kamemo primary ECDE | Construction of 1 class at Kamemo primary ECDE | To construct 1 class at Kamemo primary ECDE | 1 class at Kamemo primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.030872, 36.196235 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2892 | 0.2 | 2892 | 1183015 | 1197108 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8898 | Design and construction of Kianyoro primary ECDE classroom | Design and construction of Kianyoro primary ECDE classroom | To design and construct Kianyoro primary ECDE classroom | Kianyoro primary ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.022576, 36.239011 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 13/01/2020 | 1500000 | 1505000 | 1505000 | Equitable | N/A | 1505000 | 0 | 1183015 | 78.6 | 1183015 | 1505000 | 321985 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: No.. Viable: The class was condemed. Contractor: Information not available.
8899 | Construction of two ECDE and toilets at Muslim Primary | Construction of two ECDE and toilets at Muslim Primary | To construct two ECDE and toilets at Muslim Primary | Two ECDE and toilets at Muslim Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | -0.293563, 36.051321 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2998542 | 2998542 | Equitable | Equitable | 2998542 | 0 | 2998542 | 100 | 2998542 | 2998542 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
8900 | Design and construction of ECDE classroom, toilet and water tank at Koinange Primary | Design and construction of ECDE classroom, toilet and water tank at Koinange Primary | To design and construct ECDE classroom, toilet and water tank at Koinange Primary | ECDE classroom, toilet and water tank at Koinange Primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | -0.29293, 36.054277 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 744068 | 41.3 | 744068 | 746875 | 1055932 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8901 | Construction of kiptenden sirikwa ECD | Construction of kiptenden sirikwa ECD | To construct kiptenden sirikwa ECD | Kiptenden sirikwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.278465 35.661547 2738.7 13.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187070 | 98.9 | 1187070 | 1200000 | 12930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
8902 | 71 ECD class construction | 71 ECD class construction | To implement 71 ecd class construction for access to quality education and training | 71 ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199540 | 1199540 | Equitable | N/A | 1199540 | 0 | 1199540 | 100 | 1199540 | 1199540 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8903 | Classroom and workshop construction at Rongai polytechnic | Classroom and workshop construction at Rongai polytechnic | To implement classroom and workshop construction at rongai polytechnic for access to quality education and training | Classroom and workshop construction at Rongai polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.099944, 35.936673 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1455 | 0.1 | 1455 | 1455 | 2498545 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8904 | construction and equipping of Kabarnet farm ECDE classroom | construction and equipping of Kabarnet farm ECDE classroom | To construct and equip Kabarnet farm ECDE classroom | Kabarnet farm ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.10065 35.988127 1680.5 4.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1511226 | 1511226 | 1511226 | Equitable | N/A | 1511226 | 0 | 1163660 | 77 | 1163660 | 1511226 | 347566 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installation of Terrazo, construction of a new classroom and installation of plastic Water Tank, installation of gutters, Construction of Learners and staff Toilets, Construction of a modern kitchen,Outdoor play materials and furniture.
8905 | Design and construction of classroom at Koisamo ECDE | Design and construction of classroom at Koisamo ECDE | To design and construct classroom at Koisamo ECDE | Classroom at Koisamo ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199997 | 100 | 1199997 | 1200000 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8906 | Design and construction of classroom at Lomolo ECDE | Design and construction of classroom at Lomolo ECDE | To design and construct classroom at Lomolo ECDE | Classroom at Lomolo ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199997 | 100 | 1199997 | 1199997 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8907 | Design and construction of classroom at Losibil ECDE | Design and construction of classroom at Losibil ECDE | To design and construct classroom at Losibil ECDE | Classroom at Losibil ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1132000 | 94.3 | 1132000 | 1200000 | 68000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8908 | Design and construction of classroom at Molok ECDE | Design and construction of classroom at Molok ECDE | To design and construct classroom at Molok ECDE | Classroom at Molok ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1132000 | 94.3 | 1132000 | 1200000 | 68000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8909 | Design and construction of classroom at Testai ECDE | Design and construction of classroom at Testai ECDE | To design and construct classroom at Testai ECDE | Classroom at Testai ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199997 | 100 | 1199997 | 1200000 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8910 | Kapsetek ECD construction | Kapsetek ECD construction | To implement kapsetek ecd construction for access to quality education and training | Kapsetek ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199898.2 | 1199898.2 | Equitable | Equitable | 1199898.2 | 0 | 1199898 | 100 | 1199898 | 1199898 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8911 | Kimamoi ECD class construction | Kimamoi ECD class construction | To implement kimamoi ecd class construction for access to quality education and training | Kimamoi ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199980 | 1199980 | Equitable | N/A | 1199980 | 0 | 200 | 0 | 200 | 200 | 1199780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8912 | Kimugul ECD class construction | Kimugul ECD class construction | To implement kimugul ecd class construction for access to quality education and training | Kimugul ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199540 | 1199540 | Equitable | N/A | 1199540 | 0 | 200 | 0 | 200 | 1199540 | 1199340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8913 | Majani mingi 2 ECD Classes construction | Majani mingi 2 ECD Classes construction | To implement majani mingi 2 ecd classes construction for access to quality education and training | Majani mingi 2 ECD Classes construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2398880 | 100 | 2398880 | 2400000 | 1120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8914 | Majani mingi polytechnic class construction (2 classes) | Majani mingi polytechnic class construction (2 classes) | To implement majani mingi polytechnic class construction (2 classes) for access to quality education and training | Majani mingi polytechnic class construction (2 classes) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.041913, 36.024447 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2400000 | 2399924 | 2399924 | Equitable | Equitable | 2399924 | 0 | 2399924 | 100 | 2399924 | 2399924 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: It was viable but hasn't met the needs.
8915 | Sawaiti ECD construction | Sawaiti ECD construction | To implement sawaiti ecd construction for access to quality education and training | Sawaiti ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1132000 | 94.3 | 1132000 | 1200000 | 68000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8916 | Sinendet ECD class construction | Sinendet ECD class construction | To implement sinendet ecd class construction for access to quality education and training | Sinendet ECD class construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199895 | 1199895 | Equitable | N/A | 1199895 | 0 | 1199895 | 100 | 1199895 | 1199895 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8917 | Testai ECD construction | Testai ECD construction | To implement testai ecd construction for access to quality education and training | Testai ECD construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1194400 | 1194400 | Equitable | N/A | 1194400 | 0 | 1194400 | 100 | 1194400 | 1194400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
8918 | Construction of 1 class at Kamemo primary ECDE | Construction of 1 class at Kamemo primary ECDE | To construct 1 class at Kamemo primary ECDE | 1 class at Kamemo primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.030872, 36.196235 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2892 | 0.2 | 2892 | 1183015 | 1197108 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8919 | Design and construction of Kianyoro primary ECDE classroom | Design and construction of Kianyoro primary ECDE classroom | To design and construct Kianyoro primary ECDE classroom | Kianyoro primary ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.022576, 36.239011 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 13/01/2020 | 1500000 | 1505000 | 1505000 | Equitable | N/A | 1505000 | 0 | 1183015 | 78.6 | 1183015 | 1505000 | 321985 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: No.. Viable: The class was condemed. Contractor: Information not available.
8920 | Construction of ECDE classroom at Barao | Construction of ECDE classroom at Barao | To construct ECDE classroom at Barao | ECDE classroom at Barao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1319 | 0.1 | 1319 | 1319 | 1198681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8921 | Construction of ECDE classroom at Busienkiruk | Construction of ECDE classroom at Busienkiruk | To construct ECDE classroom at Busienkiruk | ECDE classroom at Busienkiruk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8922 | Construction of ECDE classroom at Chenugu | Construction of ECDE classroom at Chenugu | To construct ECDE classroom at Chenugu | ECDE classroom at Chenugu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199960 | 100 | 1199960 | 1199960 | 40 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8923 | Construction of ECDE classroom at Geticha | Construction of ECDE classroom at Geticha | To construct ECDE classroom at Geticha | ECDE classroom at Geticha constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1199730 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8924 | Construction of ECDE classroom at Kabonqoi | Construction of ECDE classroom at Kabonqoi | To construct ECDE classroom at Kabonqoi | ECDE classroom at Kabonqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 690090 | 57.5 | 690090 | 690090 | 509910 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8925 | Construction of ECDE classroom at Kapkoi | Construction of ECDE classroom at Kapkoi | To construct ECDE classroom at Kapkoi | ECDE classroom at Kapkoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8926 | Construction of ECDE classroom at Kapnandi | Construction of ECDE classroom at Kapnandi | To construct ECDE classroom at Kapnandi | ECDE classroom at Kapnandi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 1200000 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8927 | Construction of ECDE classroom at Kapno | Construction of ECDE classroom at Kapno | To construct ECDE classroom at Kapno | ECDE classroom at Kapno constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8928 | Construction of ECDE classroom at Korao | Construction of ECDE classroom at Korao | To construct ECDE classroom at Korao | ECDE classroom at Korao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1319 | 0.1 | 1319 | 1138490 | 1198681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8929 | Construction of ECDE classroom at Ogiek | Construction of ECDE classroom at Ogiek | To construct ECDE classroom at Ogiek | ECDE classroom at Ogiek constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1199730 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8930 | Construction of ECDE classroom at Tach Asis | Construction of ECDE classroom at Tach Asis | To construct ECDE classroom at Tach Asis | ECDE classroom at Tach Asis constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8931 | Construction of ECDE classroom at Tilindi | Construction of ECDE classroom at Tilindi | To construct ECDE classroom at Tilindi | ECDE classroom at Tilindi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199930 | 100 | 1199930 | 1199930 | 70 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8932 | Construction of ECDE classroom at Tiriiqoi | Construction of ECDE classroom at Tiriiqoi | To construct ECDE classroom at Tiriiqoi | ECDE classroom at Tiriiqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8933 | Construction of Magicheit ECD | Construction of Magicheit ECD | To construct Magicheit ECD | Magicheit ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.511222 35.692048 0 1200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2099 | 0.2 | 2099 | 2099 | 1197901 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
8934 | Construction of ECDE classroom at Mianzini | Construction of ECDE classroom at Mianzini | To construct ECDE classroom at Mianzini | ECDE classroom at Mianzini constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -1.284506 36.827955 0 256022.35698292882 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199997 | 100 | 1199997 | 1199997 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: THE CLASS IS IN USE BUT DOES NOT HAVE A TOILET. AN ADDITIONAL CLASS IS NEEDED AS PUPIL POPULATION IS VERY HIGH.
8935 | Construction of ECDE classroom at Saqaitim | Construction of ECDE classroom at Saqaitim | To construct ECDE classroom at Saqaitim | ECDE classroom at Saqaitim constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.34223 35.745215 2732.1 99.69999694824219 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199940 | 100 | 1199940 | 1199996 | 60 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs renovations.
8936 | Construction of ECDE classroom at Turi Farmers | Construction of ECDE classroom at Turi Farmers | To construct ECDE classroom at Turi Farmers | ECDE classroom at Turi Farmers constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.29662 35.755398 2422.2001953125 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 6 | 0 | 6 | 6 | 1199994 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs to be equipped. The water gutters needs to be replaced. They are broken.
8937 | Construction of polytechnic administration block at muchorwe | Construction of polytechnic administration block at muchorwe | To construct polytechnic administration block at muchorwe | Polytechnic administration block at muchorwe constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.29399 35.745263 2473.500244140625 8.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
8938 | Construction of a classroom at ogiek polytechnic | Construction of a classroom at ogiek polytechnic | To construct a classroom at ogiek polytechnic | A classroom at ogiek polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.478177, 35.670193 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1199900 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8939 | Construction of chebalungu ECDE | Construction of chebalungu ECDE | To construct chebalungu ECDE | Chebalungu ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199220 | 99.9 | 1199220 | 1200000 | 780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
8940 | Construction of ECDE classroom at Araret ECDE | Construction of ECDE classroom at Araret ECDE | To construct ECDE classroom at Araret ECDE | ECDE classroom at Araret ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1319 | 0.1 | 1319 | 1200000 | 1198681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8941 | Construction of ECDE classroom at Barao | Construction of ECDE classroom at Barao | To construct ECDE classroom at Barao | ECDE classroom at Barao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 580300 | 580300 | Equitable | N/A | 580300 | 0 | 1319 | 0.2 | 1319 | 1319 | 578981 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8942 | Construction of ECDE classroom at Busienkiruk | Construction of ECDE classroom at Busienkiruk | To construct ECDE classroom at Busienkiruk | ECDE classroom at Busienkiruk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8943 | Construction of ECDE classroom at Chenugu | Construction of ECDE classroom at Chenugu | To construct ECDE classroom at Chenugu | ECDE classroom at Chenugu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199960 | 1199960 | Equitable | N/A | 1199960 | 0 | 1199960 | 100 | 1199960 | 1199960 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8944 | Construction of ECDE classroom at Geticha | Construction of ECDE classroom at Geticha | To construct ECDE classroom at Geticha | ECDE classroom at Geticha constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199730 | 1199730 | Equitable | N/A | 1199730 | 0 | 1151750 | 96 | 1151750 | 1199730 | 47980 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8945 | Construction of ECDE classroom at Kabonqoi | Construction of ECDE classroom at Kabonqoi | To construct ECDE classroom at Kabonqoi | ECDE classroom at Kabonqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 690090 | 57.5 | 690090 | 690090 | 509910 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8946 | Construction of ECDE classroom at Kapkoi | Construction of ECDE classroom at Kapkoi | To construct ECDE classroom at Kapkoi | ECDE classroom at Kapkoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8947 | Construction of ECDE classroom at Kapno | Construction of ECDE classroom at Kapno | To construct ECDE classroom at Kapno | ECDE classroom at Kapno constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8948 | Construction of ECDE classroom at Korao | Construction of ECDE classroom at Korao | To construct ECDE classroom at Korao | ECDE classroom at Korao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1319 | 0.1 | 1319 | 1138490 | 1198681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8949 | Construction of ECDE classroom at Ogiek | Construction of ECDE classroom at Ogiek | To construct ECDE classroom at Ogiek | ECDE classroom at Ogiek constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1193336 | 1193336 | Equitable | N/A | 1193336 | 0 | 1151750 | 96.5 | 1151750 | 1199730 | 41586 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8950 | Construction of ECDE classroom at Tach Asis | Construction of ECDE classroom at Tach Asis | To construct ECDE classroom at Tach Asis | ECDE classroom at Tach Asis constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1151750 | 96 | 1151750 | 1151750 | 48250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8951 | Construction of ECDE classroom at Tilindi | Construction of ECDE classroom at Tilindi | To construct ECDE classroom at Tilindi | ECDE classroom at Tilindi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199930 | 1199930 | Equitable | N/A | 1199930 | 0 | 1199930 | 100 | 1199930 | 1199930 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
8952 | Construction of ECDE classroom at Tiriiqoi | Construction of ECDE classroom at Tiriiqoi | To construct ECDE classroom at Tiriiqoi | ECDE classroom at Tiriiqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 590910 | 49.2 | 590910 | 590910 | 609090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8953 | Construction of Magicheit ECD | Construction of Magicheit ECD | To construct Magicheit ECD | Magicheit ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2099 | 0.2 | 2099 | 2099 | 1197901 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
8954 | Design and construction of 2 no ECDE Classroom at marwa | Design and construction of 2 no ECDE Classroom at marwa | To design and construct 2 no ECDE Classroom at marwa | 2 no ECDE Classroom at marwa designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2316400 | 96.5 | 2316400 | 2400000 | 83600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
8955 | Equipping of ogiek polytechnic | Equipping of ogiek polytechnic | To equip ogiek polytechnic with necessary facilities and equipment | Ogiek polytechnic equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.478177, 35.670193 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1040698 | 1040698 | 1040698 | Equitable | N/A | 1040698 | 0 | 0 | 0 | 0 | 1040698 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8956 | Construction of ECDE classroom at Mianzini | Construction of ECDE classroom at Mianzini | To construct ECDE classroom at Mianzini | ECDE classroom at Mianzini constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -1.284506 36.827955 0 256022.35698292882 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199997 | 1199997 | Equitable | N/A | 1199997 | 0 | 1199997 | 100 | 1199997 | 1199997 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: THE CLASS IS IN USE BUT DOES NOT HAVE A TOILET. AN ADDITIONAL CLASS IS NEEDED AS PUPIL POPULATION IS VERY HIGH.
8957 | Construction of ECDE classroom at Saqaitim | Construction of ECDE classroom at Saqaitim | To construct ECDE classroom at Saqaitim | ECDE classroom at Saqaitim constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.34223 35.745215 2732.1 99.69999694824219 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 1199940 | 100 | 1199940 | 1199996 | 56 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs renovations.
8958 | Construction of ECDE classroom at Turi Farmers | Construction of ECDE classroom at Turi Farmers | To construct ECDE classroom at Turi Farmers | ECDE classroom at Turi Farmers constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.29662 35.755398 2422.2001953125 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 6 | 0 | 6 | 6 | 1199994 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs to be equipped. The water gutters needs to be replaced. They are broken.
8959 | Completion of Burgei ECD Classroom | Completion of Burgei ECD Classroom | To complete Burgei ECD Classroom | Burgei ECD Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.17174 35.922497 1749.5 8.645999908447266 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1798100 | 299.7 | 1798100 | 600000 | -1198100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8960 | Construction of Belbur ECD and toilets | Construction of Belbur ECD and toilets | To construct Belbur ECD and toilets | Belbur ECD and toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1798100 | 99.9 | 1798100 | 600000 | 1900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
8961 | Completion of Burgei ECD Classroom | Completion of Burgei ECD Classroom | To complete Burgei ECD Classroom | Burgei ECD Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1798100 | 299.7 | 1798100 | 600000 | -1198100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8962 | Construction of toilet,fencing and equipping of classroom at waka ECDE | Construction of toilet,fencing and equipping of classroom at waka ECDE | To construct toilet,fencing and equipping of classroom at waka ECDE | Toilet,fencing and equipping of classroom at waka ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 970000 | 121.2 | 970000 | 800000 | -170000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
8963 | Construction of Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | Construction of Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | To construct Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.0104, 36.23452 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: No.
8964 | Construction of Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | Construction of Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | To construct Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors | Loremetta ECDE 1 no block toilet for both teachers and pupils with double doors constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.0104, 36.23452 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: No.
8965 | Design and construction of one classroom and a toilet at Gitundaga B, wiyumirire, chania and kavillila ECDEs | Design and construction of one classroom and a toilet at Gitundaga B, wiyumirire, chania and kavillila ECDEs | To design and construct one classroom and a toilet at Gitundaga B, wiyumirire, chania and kavillila ECDEs | One classroom and a toilet at Gitundaga B, wiyumirire, chania and kavillila ECDEs designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.188668, 36.235863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5761409 | 96 | 5761409 | 5763165 | 238591 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8966 | Purchase of ECDE furniture for Wei ECDE,Kaptarakwa ECDE,Nairobi ares ECDE,Wiyumiririe ECDE,Kiriko ECDE,Kavillila ECDE,Gitundaga B ECDE,Lari ECDE and Simboyon ECDE plus teachers chair and table for each ECDE(each ECDE to consist of 4 wooden tables and 24 small wooden chairs ,for teachers 1 wooden chair and a locker,samples to be seen at kamumo ECDE) | Purchase of ECDE furniture for Wei ECDE,Kaptarakwa ECDE,Nairobi ares ECDE,Wiyumiririe ECDE,Kiriko ECDE,Kavillila ECDE,Gitundaga B ECDE,Lari ECDE and Simboyon ECDE plus teachers chair and table for each ECDE(each ECDE to consist of 4 wooden tables and 24 small wooden chairs ,for teachers 1 wooden chair and a locker,samples to be seen at kamumo ECDE) | To procure ECDE furniture for Wei ECDE,Kaptarakwa ECDE,Nairobi ares ECDE,Wiyumiririe ECDE,Kiriko ECDE,Kavillila ECDE,Gitundaga B ECDE,Lari ECDE and Simboyon ECDE plus teachers chair and table for each ECDE(each ECDE to consist of 4 wooden tables and 24 small wooden chairs ,for teachers 1 wooden chair and a locker,samples to be seen at kamumo ECDE) | ECDE furniture for Wei ECDE,Kaptarakwa ECDE,Nairobi ares ECDE,Wiyumiririe ECDE,Kiriko ECDE,Kavillila ECDE,Gitundaga B ECDE,Lari ECDE and Simboyon ECDE plus teachers chair and table for each ECDE(each ECDE to consist of 4 wooden tables and 24 small wooden chairs ,for teachers 1 wooden chair and a locker,samples to be seen at kamumo ECDE) procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.033498, 36.226888 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8967 | Construction of ECD Centre of Excellence | Construction of ECD Centre of Excellence | To construct ECD Centre of Excellence | ECD Centre of Excellence constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 23466338.86 | 23466338.86 | 23466338.86 | Equitable | N/A | 23466338.86 | 0 | 19900008 | 84.8 | 19900008 | 3566331 | 3566330.86 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8968 | Establishment of a Data Centre at the County HQ | Establishment of a Data Centre at the County HQ | To implement establishment of a data centre at the county hq for access to quality education and training | Establishment of a Data Centre at the County HQ completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 10000000 | 10000000 | Equitable | Equitable | 10000000 | 0 | 8735600 | 87.4 | 8735600 | 1264400 | 1264400 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8969 | Mirera VTC twin workshop | Mirera VTC twin workshop | To implement mirera vtc twin workshop for access to quality education and training | Mirera VTC twin workshop completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 12000000 | 12000000 | 12000000 | Equitable | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
8970 | Revitalization of Youth Polytechnics | Revitalization of Youth Polytechnics | To implement revitalization of youth polytechnics for access to quality education and training | Revitalization of Youth Polytechnics completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 22572419 | 11000000 | 11000000 | Equitable | N/A | 11000000 | 0 | 10193360 | 92.7 | 10193360 | 11000000 | 806640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8971 | Set Up of digital centres | Set Up of digital centres | To implement set up of digital centres for access to quality education and training | Set Up of digital centres completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 9505494 | 9505494 | Equitable | N/A | 9505494 | 0 | 1897400 | 20 | 1897400 | 2813994 | 7608094 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8972 | Twin workshop in Cheptuech VTC | Twin workshop in Cheptuech VTC | To implement twin workshop in cheptuech vtc for access to quality education and training | Twin workshop in Cheptuech VTC completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 12000000 | 12000000 | 12000000 | Equitable | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8973 | Completion of Mororbei ECD | Completion of Mororbei ECD | To complete Mororbei ECD | Mororbei ECD completed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | KIPTORORO | -0.302609 35.529459 2587.10009765625 48.900001525878906 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project was completed but demolished afterwards.
8974 | Design and construction of Limuko ECDE | Design and construction of Limuko ECDE | To design and construct Limuko ECDE | Limuko ECDE designed and constructed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.214235 36.163212 2030.4000244140625 10.031000137329102 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1950470 | 97.5 | 1950470 | 2000000 | 49530 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s wakasi enterprise. Assessor remarks: Operational but the floor needs renovation.
8975 | Construction of a sanitary facility for ECDE at Our Lady of Mercy primary school | Construction of a sanitary facility for ECDE at Our Lady of Mercy primary school | To construct a sanitary facility for ECDE at Our Lady of Mercy primary school | A sanitary facility for ECDE at Our Lady of Mercy primary school constructed | 3110504 | Other Infrastructure and Civil Works | BAHATI | BAHATI | -0.172187, 36.125967 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1815981 | 1815981 | 1815981 | Equitable | N/A | 1815981 | 0 | 1997862 | 110 | 1997862 | 1815981 | -181881 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
8976 | Construction of perimeter wall at Barut Polytechnic | Construction of perimeter wall at Barut Polytechnic | To construct perimeter wall at Barut Polytechnic | Perimeter wall at Barut Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | -0.342342, 36.054698 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2023 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1194400 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: KITALF ENTERPRISES.
8977 | Construction of toilets at Ngala Special School | Construction of toilets at Ngala Special School | To construct toilets at Ngala Special School | Toilets at Ngala Special School constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | -0.293169, 36.075539 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024/25 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799590 | 99.9 | 799590 | 10 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Merlinz keys enterprise ltd.
8978 | Construction of toilets at St. Paul Primary School | Construction of toilets at St. Paul Primary School | To construct toilets at St. Paul Primary School | Toilets at St. Paul Primary School constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | -0.296043, 36.079196 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 10 | 0 | 10 | 10 | 799990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8979 | Construction of a sanitary facility, ECDE class and water tank at Kahawa nursery | Construction of a sanitary facility, ECDE class and water tank at Kahawa nursery | To construct a sanitary facility, ECDE class and water tank at Kahawa nursery | A sanitary facility, ECDE class and water tank at Kahawa nursery constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
8980 | Gituru polytechnic fencing, latrines and other works | Gituru polytechnic fencing, latrines and other works | To implement gituru polytechnic fencing, latrines and other works for access to quality education and training | Gituru polytechnic fencing, latrines and other works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.7255, 36.486383 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 7300000 | 7300000 | 7300000 | Equitable | N/A | 7300000 | 0 | 7300000 | 100 | 7300000 | 7300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8981 | Kinamba Polytechnic fencing, latrines and other works | Kinamba Polytechnic fencing, latrines and other works | To implement kinamba polytechnic fencing, latrines and other works for access to quality education and training | Kinamba Polytechnic fencing, latrines and other works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.7255, 36.486383 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 3099310 | 100 | 3099310 | 3100000 | 690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
8982 | Construction of toilets at St. Paul Primary School | Construction of toilets at St. Paul Primary School | To construct toilets at St. Paul Primary School | Toilets at St. Paul Primary School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.296043, 36.079196 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 10 | 0 | 10 | 10 | 799990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8983 | Hardware and Software Platforms | Hardware and Software Platforms | To implement hardware and software platforms for access to quality education and training | Hardware and Software Platforms completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 4066066 | 2649566 | 2649566 | Equitable | N/A | 2649566 | 0 | 1528500 | 57.7 | 1528500 | 1121066 | 1121066 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
8984 | Installation of Local Area Network (LANs) at Old Town Hall and Njoro Youth Polytechnic | Installation of Local Area Network (LANs) at Old Town Hall and Njoro Youth Polytechnic | To install Local Area Network (LANs) at Old Town Hall and Njoro Youth Polytechnic | Local Area Network (LANs) at Old Town Hall and Njoro Youth Polytechnic installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8985 | Revitalization of Vocational Training Centres of Excellence | Revitalization of Vocational Training Centres of Excellence | To implement revitalization of vocational training centres of excellence for access to quality education and training | Revitalization of Vocational Training Centres of Excellence completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 24000000 | 24000000 | 23000648 | Equitable | N/A | 23000648 | 0 | 3535000 | 14.7 | 3535000 | 11157648 | 20465000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
8986 | Construction of a Rehabilitation Centre at YMCA | Construction of a Rehabilitation Centre at YMCA | To construct a Rehabilitation Centre at YMCA | A Rehabilitation Centre at YMCA constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.778267, 36.429562 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998000 | 99.9 | 2998000 | 2988000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8987 | Construction and equipping of a workshop at Wendo Polytechnic | Construction and equipping of a workshop at Wendo Polytechnic | To construct and equip a workshop at Wendo Polytechnic | A workshop at Wendo Polytechnic constructed and equipped | 3110504 | Other Infrastructure and Civil Works | BAHATI | KABATINI | -0.18076 36.180676 1937.9000244140625 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 300000 | 12 | 300000 | 300000 | 2200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s tripple general supplies. Assessor remarks: Operational but the roof need to be redone.
8988 | Fencing/landscaping of mau summit polytechnic | Fencing/landscaping of mau summit polytechnic | To implement fencing/landscaping of mau summit polytechnic for access to quality education and training | Fencing/landscaping of mau summit polytechnic completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.167892 35.676188 2607 2643.741943359375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 995800 | 99.6 | 995800 | 995800 | 4200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Needs renovation. Viable: Yes. Assessor remarks: Needs renovation.
8989 | Construction of Administration block at kapkures Tulwet ECDE | Construction of Administration block at kapkures Tulwet ECDE | To construct Administration block at kapkures Tulwet ECDE | Administration block at kapkures Tulwet ECDE constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.324324, 36.036613 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 800 | 0 | 800 | 800 | 2499200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. But has not been operational. Contractor: Ng'ambo hardware Ltd.
8990 | Installation of solar panel at Heshima ECD | Installation of solar panel at Heshima ECD | To install solar panel at Heshima ECD | Solar panel at Heshima ECD installed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.299576 36.052178 1803.5999755859375 8.61400032043457 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s cider collection limited. Assessor remarks: It's a very viable.
8991 | Installation of Solar panel at Kaptembwo ECD | Installation of Solar panel at Kaptembwo ECD | To install Solar panel at Kaptembwo ECD | Solar panel at Kaptembwo ECD installed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.29789 36.052599 1812.199951171875 82.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 9999900 | 2000 | 9999900 | 500000 | -9499900 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
8992 | Completion of Githima ECD toilet blocks | Completion of Githima ECD toilet blocks | To complete Githima ECD toilet blocks | Githima ECD toilet blocks completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KIPTORORO | -0.303273, 35.490462 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8993 | Construction of ECD perimeter wall at St Theresa Primary School | Construction of ECD perimeter wall at St Theresa Primary School | To construct ECD perimeter wall at St Theresa Primary School | ECD perimeter wall at St Theresa Primary School constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.298332, 36.08463 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 1000000 | 25.6 | 1000000 | 3793570 | 2900000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
8994 | Construction and equipping of a workshop at Wendo Polytechnic | Construction and equipping of a workshop at Wendo Polytechnic | To construct and equip a workshop at Wendo Polytechnic | A workshop at Wendo Polytechnic constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.18076 36.180676 1937.9000244140625 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2499935 | 2499935 | Equitable | N/A | 2499935 | 0 | 300000 | 12 | 300000 | 300000 | 2199935 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s tripple general supplies. Assessor remarks: Operational but the roof need to be redone.
8995 | Fencing/landscaping of mau summit polytechnic | Fencing/landscaping of mau summit polytechnic | To implement fencing/landscaping of mau summit polytechnic for access to quality education and training | Fencing/landscaping of mau summit polytechnic completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.167892 35.676188 2607 2643.741943359375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 995800 | 995800 | Equitable | Equitable | 995800 | 0 | 995800 | 100 | 995800 | 995800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Needs renovation. Viable: Yes. Assessor remarks: Needs renovation.
8996 | Construction of Administration block at kapkures Tulwet ECDE | Construction of Administration block at kapkures Tulwet ECDE | To construct Administration block at kapkures Tulwet ECDE | Administration block at kapkures Tulwet ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 800 | 0 | 800 | 800 | 2499200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. But has not been operational. Contractor: Ng'ambo hardware Ltd.
8997 | Installation of solar panel at Heshima ECD | Installation of solar panel at Heshima ECD | To install solar panel at Heshima ECD | Solar panel at Heshima ECD installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.299576 36.052178 1803.5999755859375 8.61400032043457 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s cider collection limited. Assessor remarks: It's a very viable.
8998 | Installation of Solar panel at Kaptembwo ECD | Installation of Solar panel at Kaptembwo ECD | To install Solar panel at Kaptembwo ECD | Solar panel at Kaptembwo ECD installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29789 36.052599 1812.199951171875 82.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 9999900 | 2000 | 9999900 | 500000 | -9499900 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
8999 | Construction of Nyondia annex ECD toilet | Construction of Nyondia annex ECD toilet | To construct Nyondia annex ECD toilet | Nyondia annex ECD toilet constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703 36.471211 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need repair and renovation.
9000 | Construction of Lawina ECDE toilets | Construction of Lawina ECDE toilets | To construct Lawina ECDE toilets | Lawina ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIASHONI | -0.328205 35.867922 2352.2693772589882 11 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 499952 | 100 | 499952 | 499952 | 48 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No toilet was built during classroom construction.
9001 | Construction of kamungei ECDE toilets | Construction of kamungei ECDE toilets | To construct kamungei ECDE toilets | Kamungei ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MENENGAI WEST | -0.122242, 36.008073 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999200 | 99.9 | 999200 | 999200 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
9002 | Construction of kichwa ECDE toilets | Construction of kichwa ECDE toilets | To construct kichwa ECDE toilets | Kichwa ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MENENGAI WEST | -0.122242, 36.008073 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999844 | 100 | 999844 | 999844 | 156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
9003 | Construction of Ex Magret ECDE toilet | Construction of Ex Magret ECDE toilet | To construct Ex Magret ECDE toilet | Ex Magret ECDE toilet constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.260493, 35.933902 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Not indicated | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 694 | 0.1 | 694 | 694 | 499306 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
9004 | Construction of Matuiku ECDE Toilets | Construction of Matuiku ECDE Toilets | To construct Matuiku ECDE Toilets | Matuiku ECDE Toilets constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.260493, 35.933902 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Not indicated | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499994 | 100 | 499994 | 499994 | 6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
9005 | Construction San marco ECDE toilet | Construction San marco ECDE toilet | To construct San marco ECDE toilet | San marco ECDE toilet constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.235414, 35.898561 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 694 | 0.1 | 694 | 498974 | 499306 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: M/s Bekeli.
9006 | Construction of Gatundu ECD (Equipping,fencing,toilets and water tanks) | Construction of Gatundu ECD (Equipping,fencing,toilets and water tanks) | To construct Gatundu ECD (Equipping,fencing,toilets and water tanks) | Gatundu ECD (Equipping,fencing,toilets and water tanks) constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | MURINDAT | -0.502893, 36.390597 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2396460 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not done. Viable: Not done.
9007 | Construction of Lawina ECDE toilets | Construction of Lawina ECDE toilets | To construct Lawina ECDE toilets | Lawina ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.328205 35.867922 2352.2693772589882 11 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 499952 | 499952 | Equitable | Equitable | 499952 | 0 | 499952 | 100 | 499952 | 499952 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No toilet was built during classroom construction.
9008 | Construction of kamungei ECDE toilets | Construction of kamungei ECDE toilets | To construct kamungei ECDE toilets | Kamungei ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.122242, 36.008073 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999200 | 999200 | Equitable | N/A | 999200 | 0 | 999200 | 100 | 999200 | 999200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
9009 | Construction of kichwa ECDE toilets | Construction of kichwa ECDE toilets | To construct kichwa ECDE toilets | Kichwa ECDE toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.122242, 36.008073 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999844 | 999844 | Equitable | N/A | 999844 | 0 | 999844 | 100 | 999844 | 999844 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
9010 | Construction of Ex Magret ECDE toilet | Construction of Ex Magret ECDE toilet | To construct Ex Magret ECDE toilet | Ex Magret ECDE toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Not indicated | 500000 | 499994 | 499994 | Equitable | N/A | 499994 | 0 | 694 | 0.1 | 694 | 694 | 499300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
9011 | Construction of Matuiku ECDE Toilets | Construction of Matuiku ECDE Toilets | To construct Matuiku ECDE Toilets | Matuiku ECDE Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Not indicated | 500000 | 499994.4 | 499994.4 | Equitable | N/A | 499994.4 | 0 | 499994 | 100 | 499994 | 499994 | 0.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
9012 | Construction San marco ECDE toilet | Construction San marco ECDE toilet | To construct San marco ECDE toilet | San marco ECDE toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.235414, 35.898561 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 500000 | 498974 | 498974 | Equitable | N/A | 498974 | 0 | 694 | 0.1 | 694 | 498974 | 498280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: M/s Bekeli.
9013 | Construction of toilets in Utafiti ECD | Construction of toilets in Utafiti ECD | To construct toilets in Utafiti ECD | Toilets in Utafiti ECD constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | NJORO | -0.338219, 35.944823 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 600000 | 600000 | 600000 | Equitable | Equitable | 600000 | 0 | 599640 | 99.9 | 599640 | 599640 | 360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
9014 | Construction of muoroto polytechnic toilets | Construction of muoroto polytechnic toilets | To construct muoroto polytechnic toilets | Muoroto polytechnic toilets constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | NYOTA | -0.344545, 35.629493 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2016 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 498400 | 99.7 | 498400 | 498400 | 1600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Yah enterprises ltd.
9015 | Construction of toilets in Utafiti ECD | Construction of toilets in Utafiti ECD | To construct toilets in Utafiti ECD | Toilets in Utafiti ECD constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.338219, 35.944823 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 600000 | 599640.4 | 599640.4 | Equitable | Equitable | 599640.4 | 0 | 599640 | 100 | 599640 | 599640 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
9016 | Construction of muoroto polytechnic toilets | Construction of muoroto polytechnic toilets | To construct muoroto polytechnic toilets | Muoroto polytechnic toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.344545, 35.629493 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2016 | 500000 | 498400 | 498400 | Equitable | Equitable | 498400 | 0 | 498400 | 100 | 498400 | 498400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Yah enterprises ltd.
9017 | construction of toilet at koilitit ECD school | construction of toilet at koilitit ECD school | To construct toilet at koilitit ECD school | Toilet at koilitit ECD school constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.046432 36.033078 1632.3999999999999 9.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 348930 | 99.7 | 348930 | 350000 | 1070 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
9018 | Design and construction of Koyumtich ECDE toilet | Design and construction of Koyumtich ECDE toilet | To design and construct Koyumtich ECDE toilet | Koyumtich ECDE toilet designed and constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.110025 35.94125 0 1700 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 396354 | 99.1 | 396354 | 400000 | 3646 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs alot of repair,Needs more toilets for staffs.
9019 | Partitioning and equipping of Special needs classroom at Koinange Primary school | Partitioning and equipping of Special needs classroom at Koinange Primary school | To implement partitioning and equipping of special needs classroom at koinange primary school for access to quality education and training | Partitioning and equipping of Special needs classroom at Koinange Primary school completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.293948, 36.055144 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 744068 | 37.2 | 744068 | 2000000 | 1255932 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9020 | construction of toilet at koilitit ECD school | construction of toilet at koilitit ECD school | To construct toilet at koilitit ECD school | Toilet at koilitit ECD school constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.046432 36.033078 1632.3999999999999 9.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 348930 | 99.7 | 348930 | 350000 | 1070 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
9021 | Design and construction of 4-door toilets at Kokwomoi ECDE | Design and construction of 4-door toilets at Kokwomoi ECDE | To design and construct 4-door toilets at Kokwomoi ECDE | 4-door toilets at Kokwomoi ECDE designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.045687 36.049197 1618.2 7.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1199997 | 400 | 1199997 | 300000 | -899997 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The teacher needs an ablution block.
9022 | Design and construction of 4-door toilets at Ruyobei ECDE | Design and construction of 4-door toilets at Ruyobei ECDE | To design and construct 4-door toilets at Ruyobei ECDE | 4-door toilets at Ruyobei ECDE designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.045687 36.049197 1618.2 7.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1132000 | 377.3 | 1132000 | 300000 | -832000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The teacher needs an ablution block.
9023 | Design and construction of Koyumtich ECDE toilet | Design and construction of Koyumtich ECDE toilet | To design and construct Koyumtich ECDE toilet | Koyumtich ECDE toilet designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.110025 35.94125 0 1700 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 396354 | 99.1 | 396354 | 400000 | 3646 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs alot of repair,Needs more toilets for staffs.
9024 | Construction of 1 class and latrines at Subukia primary ECDE | Construction of 1 class and latrines at Subukia primary ECDE | To construct 1 class and latrines at Subukia primary ECDE | 1 class and latrines at Subukia primary ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.003143, 36.229305 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 04/03/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2892 | 0.2 | 2892 | 2892 | 1497108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: The project has many learning children. Viable: Yes.. Contractor: Information not available.
9025 | Construction of Ogiek polytechnic toilets | Construction of Ogiek polytechnic toilets | To construct Ogiek polytechnic toilets | Ogiek polytechnic toilets constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | TINET | -0.403875 35.693755 0 899.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 644401 | 644401 | 644401 | Equitable | N/A | 644401 | 0 | 2099 | 0.3 | 2099 | 644401 | 642302 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational and good condition.
9026 | Fencing and toilet construction at Chandera Polytechnic | Fencing and toilet construction at Chandera Polytechnic | To secure and toilet construction at Chandera Polytechnic through fencing | And toilet construction at Chandera Polytechnic fenced and secured | 3110504 | Other Infrastructure and Civil Works | MOLO | TURI | -0.311474 35.734196 2602.8 14.149999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1499500 | 100 | 1499500 | 1499500 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Excellent work.
9027 | Construction of Ogiek polytechnic toilets | Construction of Ogiek polytechnic toilets | To construct Ogiek polytechnic toilets | Ogiek polytechnic toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.403875 35.693755 0 899.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 644401 | 644401 | 644401 | Equitable | N/A | 644401 | 0 | 2099 | 0.3 | 2099 | 644401 | 642302 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational and good condition.
9028 | Fencing and toilet construction at Chandera Polytechnic | Fencing and toilet construction at Chandera Polytechnic | To secure and toilet construction at Chandera Polytechnic through fencing | And toilet construction at Chandera Polytechnic fenced and secured | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.311474 35.734196 2602.8 14.149999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499500 | 1499500 | Equitable | Equitable | 1499500 | 0 | 1499500 | 100 | 1499500 | 1499500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Excellent work.
9029 | Construction and equipping of ICT Hub Facility/hub estate | Construction and equipping of ICT Hub Facility/hub estate | To construct and equip ICT Hub Facility/hub estate | ICT Hub Facility/hub estate constructed and equipped | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.714882 36.432885 0 200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1499845 | 30 | 1499845 | 5000000 | 3500155 | Stalled | 90 | 30 | Stalled — reasons to be confirmed by department | 2019 | N/A | 3500155 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Effective.
9030 | Design and construction of Kayanet ECD toilets | Design and construction of Kayanet ECD toilets | To design and construct Kayanet ECD toilets | Kayanet ECD toilets designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.112228 35.887368 1817.7 20.799999237060547 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 598560 | 99.8 | 598560 | 600000 | 1440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9031 | Construction and equipping of ICT Hub Facility/hub estate | Construction and equipping of ICT Hub Facility/hub estate | To construct and equip ICT Hub Facility/hub estate | ICT Hub Facility/hub estate constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714882 36.432885 0 200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1499845 | 30 | 1499845 | 5000000 | 3500155 | Stalled | 90 | 30 | Stalled — reasons to be confirmed by department | 2019 | N/A | 3500155 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Effective.
9032 | Design and construction and equipping of 2 no special need classrooms at DEB school | Design and construction and equipping of 2 no special need classrooms at DEB school | To design and construct and equipping of 2 no special need classrooms at DEB school | And equipping of 2 no special need classrooms at DEB school designed and constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.711536 36.435973 1906.69 0.621999979019165 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 3990000 | 3990000 | 3990000 | Equitable | N/A | 3990000 | 0 | 3542890 | 88.8 | 3542890 | 3990000 | 447110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Has met minimum health requirements.
9033 | equipping of Gituru Polytechnic | equipping of Gituru Polytechnic | To equip Gituru Polytechnic with necessary facilities and equipment | Gituru Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Biashara-Naivasha | -0.725835, 36.486833 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2483000 | 99.3 | 2483000 | 2500000 | 17000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: N/a.
9034 | equipping of Kinamba Polytechnic | equipping of Kinamba Polytechnic | To equip Kinamba Polytechnic with necessary facilities and equipment | Kinamba Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Biashara-Naivasha | -0.725835, 36.486833 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2474525 | 99 | 2474525 | 2498730 | 25475 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: N/a.
9035 | Equipping of Kongasis Polytechnic | Equipping of Kongasis Polytechnic | To equip Kongasis Polytechnic with necessary facilities and equipment | Kongasis Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | GILGIL | EBURRU-MBARUK | -0.554731, 36.153036 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 985800 | 98.6 | 985800 | 2000000 | 14200 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
9036 | Equipping of Elburgon polytechnic | Equipping of Elburgon polytechnic | To equip Elburgon polytechnic with necessary facilities and equipment | Elburgon polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | MOLO | ELBURGON | -0.308342 35.807555 2442.7 11.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 995299 | 99.5 | 995299 | 995299 | 4701 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
9037 | Equipping of Kongasis Polytechnic | Equipping of Kongasis Polytechnic | To equip Kongasis Polytechnic with necessary facilities and equipment | Kongasis Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru-Mbaruk | -0.554731, 36.153036 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 985800 | 98.6 | 985800 | 2000000 | 14200 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
9038 | Equipping of Elburgon polytechnic | Equipping of Elburgon polytechnic | To equip Elburgon polytechnic with necessary facilities and equipment | Elburgon polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Molo | Elburgon | -0.308342 35.807555 2442.7 11.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 995299 | 995299 | Equitable | Equitable | 995299 | 0 | 995299 | 100 | 995299 | 995299 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
9039 | Equipping of ECDE classes | Equipping of ECDE classes | To equip ECDE classes with necessary facilities and equipment | ECDE classes equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 9201198 | 9201198 | Equitable | N/A | 9201198 | 0 | 1561000 | 17 | 1561000 | 4043398 | 7640198 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9040 | Equipping of ECD's | Equipping of ECD's | To equip ECD's with necessary facilities and equipment | ECD's equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9787000 | 97.9 | 9787000 | 5502637 | 213000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9041 | Equipping of Baby Care Centre at Kihoto | Equipping of Baby Care Centre at Kihoto | To equip Baby Care Centre at Kihoto with necessary facilities and equipment | Baby Care Centre at Kihoto equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | LAKEVIEW | -0.73409, 36.436208 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9042 | Equipping of ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws | Equipping of ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws | To equip ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws with necessary facilities and equipment | ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | OLKARIA | 0.833651, 36.341813 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1746200 | 145.5 | 1746200 | 253800 | -546200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9043 | Equipping of ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws | Equipping of ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws | To equip ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws with necessary facilities and equipment | ECDE in Maua , Sher moi , Oserian , Mvuke olkaria primary and Naivasha with the following slides, swings and see saws equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.833651, 36.341813 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1746200 | 145.5 | 1746200 | 253800 | -546200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9044 | Purchase and supply of playing equipments at mwariki ECDE | Purchase and supply of playing equipments at mwariki ECDE | To procure and supply playing equipments at mwariki ECDE | Playing equipments at mwariki ECDE procured and supplied | 3111120 | Purchase of Specialized Plant. - | Nakuru West | Rhonda | -0.3162, 36.06627 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 20/21 | 710352 | 710352 | 710352 | Equitable | N/A | 710352 | 0 | 0 | 0 | 0 | 710352 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
9045 | Purchase of 1acre Land for Kimugul ECDE | Purchase of 1acre Land for Kimugul ECDE | To procure 1acre Land for Kimugul ECDE | 1acre Land for Kimugul ECDE procured | 3130101 | Acquisition of Land | KURESOI SOUTH | AMALO | -0.640943, 35.623492 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 75 | N/A | STALLED. TO BE SUPPLEMENTED | 2018 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9046 | Purchase of 1acre Land for Kimugul ECDE | Purchase of 1acre Land for Kimugul ECDE | To procure 1acre Land for Kimugul ECDE | 1acre Land for Kimugul ECDE procured | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.640943, 35.623492 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 75 | N/A | STALLED. TO BE SUPPLEMENTED | 2018 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9047 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.570653, 35.664722 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499996 | 100 | 1499996 | 4 | 4 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
9048 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.570768, 35.664825 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1499996 | 150 | 1499996 | 992345 | -499996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
9049 | Construction of the administration block and Toilets at Kaplamai Polytechnic | Construction of the administration block and Toilets at Kaplamai Polytechnic | To construct the administration block and Toilets at Kaplamai Polytechnic | The administration block and Toilets at Kaplamai Polytechnic constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.658488, 35.639393 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996557 | 99.8 | 1996557 | 2000000 | 3443 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
9050 | construction of Toilet and fencing at Pangani ECD | construction of Toilet and fencing at Pangani ECD | To construct Toilet and fencing at Pangani ECD | Toilet and fencing at Pangani ECD constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.589148, 35.674193 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 499500 | 99.9 | 499500 | 500000 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
9051 | Kaplamboi Ecd - Construction of a toilet and Furniture | Kaplamboi Ecd - Construction of a toilet and Furniture | To implement kaplamboi ecd - construction of a toilet and furniture for access to quality education and training | Kaplamboi Ecd - Construction of a toilet and Furniture completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.660928, 35.617525 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
9052 | Pangani Ecd | Pangani Ecd | To implement pangani ecd for access to quality education and training | Pangani Ecd completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.589155, 35.674233 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 499380 | 49.9 | 499380 | 0 | 500620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes.
9053 | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point | To implement saptet ecd - design and construction of 1 no ecd classroom, pupils toilet and watering point for access to quality education and training | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point completed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.63516 35.678194 2480.126708984375 6.038000106811523 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499858 | 100 | 1499858 | 992345 | 142 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: done well ,but teacher and pupils toilet ..
9054 | Construction of latrines and guttering of ECDE class Kiptenden | Construction of latrines and guttering of ECDE class Kiptenden | To construct latrines and guttering of ECDE class Kiptenden | Latrines and guttering of ECDE class Kiptenden constructed | 4130299 | N/A | KURESOI SOUTH | AMALO | -0.565397, 35.697377 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 1240000 | 1240000 | 1240000 | Equitable | N/A | 1240000 | 0 | 416194 | 33.6 | 416194 | 1240000 | 823806 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: no. Viable: not yet.
9055 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.570653, 35.664722 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1500000 | 4 | 4 | Equitable | N/A | 4 | 0 | 1499996 | 37499900 | 1499996 | 4 | -1499992 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
9056 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.570768, 35.664825 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1499996 | 150 | 1499996 | 992345 | -499996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
9057 | Construction of the administration block and Toilets at Kaplamai Polytechnic | Construction of the administration block and Toilets at Kaplamai Polytechnic | To construct the administration block and Toilets at Kaplamai Polytechnic | The administration block and Toilets at Kaplamai Polytechnic constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.658488, 35.639393 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996557 | 99.8 | 1996557 | 2000000 | 3443 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
9058 | construction of Toilet and fencing at Pangani ECD | construction of Toilet and fencing at Pangani ECD | To construct Toilet and fencing at Pangani ECD | Toilet and fencing at Pangani ECD constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.589148, 35.674193 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 499500 | 99.9 | 499500 | 500000 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
9059 | Construction of 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | Construction of 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | To construct 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD constructed | 4130299 | N/A | NAKURU WEST | BARUT | 0.353373 36.049497 1834.1 503.205993652 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999051 | 1999051 | 1999051 | Equitable | N/A | 1999051 | 0 | 1999051 | 100 | 1999051 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Yet to be completed.good progress seen..
9060 | Soimmet ECD - Fencing of Land and Construction of ECD | Soimmet ECD - Fencing of Land and Construction of ECD | To implement soimmet ecd - fencing of land and construction of ecd for access to quality education and training | Soimmet ECD - Fencing of Land and Construction of ECD completed | 4130299 | N/A | NAKURU WEST | BARUT | -0.3656, 36.05254 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: PIRAKIL COMPANY LIMITED.
9061 | Fencing of Parkview ECD field | Fencing of Parkview ECD field | To secure Parkview ECD field through fencing | Parkview ECD field fenced and secured | 4130299 | N/A | NAKURU WEST | BARUT | 0.353373, 36.049 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499380 | 99.9 | 499380 | 0 | 620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alfary supplies.
9062 | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic | To implement purchasing of masonry, textile design and hair dressing equipment for barut polytechnic for access to quality education and training | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic completed | 4130299 | N/A | NAKURU WEST | BARUT | -0.342342, 36.054698 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9063 | Construction of 1.No ECD classroom at Nyonjoro ECD | Construction of 1.No ECD classroom at Nyonjoro ECD | To construct 1.No ECD classroom at Nyonjoro ECD | 1.No ECD classroom at Nyonjoro ECD constructed | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199406.36 | 1199406.36 | 1199406.36 | Equitable | N/A | 1199406.36 | 0 | 1199406 | 100 | 1199406 | 2389990 | 0.36 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9064 | Construction of 2 ECDE classroom at Kinamba ECDE | Construction of 2 ECDE classroom at Kinamba ECDE | To construct 2 ECDE classroom at Kinamba ECDE | 2 ECDE classroom at Kinamba ECDE constructed | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.718757, 36.483535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2021 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2389990 | 99.6 | 2389990 | 2389990 | 10010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
9065 | Construction of Gituru Polytechnic | Construction of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 4130299 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.661007, 36.50238 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2020 | 16000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 8683480 | 124 | 8683480 | 21997 | -1683480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Dakuki.
9066 | Construction of ECD classroom at Freehold Primary school | Construction of ECD classroom at Freehold Primary school | To construct ECD classroom at Freehold Primary school | ECD classroom at Freehold Primary school constructed | 4130299 | N/A | NAKURU EAST | BIASHARA-NAKURU | -0.297456, 36.066859 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1190650 | 99.2 | 1190650 | 700000 | 9350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9067 | Construction of ECD classroom at Harambee Khalsa primary | Construction of ECD classroom at Harambee Khalsa primary | To construct ECD classroom at Harambee Khalsa primary | ECD classroom at Harambee Khalsa primary constructed | 4130299 | N/A | NAKURU EAST | BIASHARA-NAKURU | -0.297456, 36.066859 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1190650 | 99.2 | 1190650 | 700000 | 9350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9068 | Construction of ECD classroom at Menengai Primary | Construction of ECD classroom at Menengai Primary | To construct ECD classroom at Menengai Primary | ECD classroom at Menengai Primary constructed | 4130299 | N/A | NAKURU EAST | BIASHARA-NAKURU | -0.297456, 36.066859 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199771 | 100 | 1199771 | 2000000 | 229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9069 | Construction of 2 ECDE classroom at Kinamba ECDE | Construction of 2 ECDE classroom at Kinamba ECDE | To construct 2 ECDE classroom at Kinamba ECDE | 2 ECDE classroom at Kinamba ECDE constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.718757, 36.483535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2021 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2389990 | 99.6 | 2389990 | 2389990 | 10010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
9070 | Construction of Gituru Polytechnic | Construction of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.661007, 36.50238 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2020 | 16000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 8683480 | 124 | 8683480 | 21997 | -1683480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Dakuki.
9071 | Construction of 1No ECD Classrooms at ,Kianda Ecd, | Construction of 1No ECD Classrooms at ,Kianda Ecd, | To construct 1No ECD Classrooms at ,Kianda Ecd, | 1No ECD Classrooms at ,Kianda Ecd, constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.233853, 36.179481 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/2017 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 22 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company Ltd.
9072 | Construction of 1.No ECD Classrooms Bavuni ECD, | Construction of 1.No ECD Classrooms Bavuni ECD, | To construct 1.No ECD Classrooms Bavuni ECD, | 1.No ECD Classrooms Bavuni ECD, constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.233853, 36.179481 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/2017 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company Ltd.
9073 | Construction of 1.No ECD Classrooms Tabuga ECD | Construction of 1.No ECD Classrooms Tabuga ECD | To construct 1.No ECD Classrooms Tabuga ECD | 1.No ECD Classrooms Tabuga ECD constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.233853, 36.179481 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/2017 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company Ltd.
9074 | Construction of 1.No ECD Classrooms Wanyororo ECD | Construction of 1.No ECD Classrooms Wanyororo ECD | To construct 1.No ECD Classrooms Wanyororo ECD | 1.No ECD Classrooms Wanyororo ECD constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.233853, 36.179481 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/2017 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 22 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company Ltd.
9075 | Construction of an ECD classroom at Dundori primary school | Construction of an ECD classroom at Dundori primary school | To construct an ECD classroom at Dundori primary school | An ECD classroom at Dundori primary school constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.25394, 36.238355 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199978 | 100 | 1199978 | 22 | 22 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms Top Notch.
9076 | construction of Mikeu ECDE classroom | construction of Mikeu ECDE classroom | To construct Mikeu ECDE classroom | Mikeu ECDE classroom constructed | 4130299 | N/A | BAHATI | DUNDORI | -0.249596 36.231481 2331.10009765625 20 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done under NKU/CITY/222/2013-2014 no septic tank constructed.
9077 | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic | To implement dundori polytechnic - design and construction of 1 dormitory at dundori polytechnic for access to quality education and training | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic completed | 4130299 | N/A | BAHATI | DUNDORI | -0.2496, 36.231092 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/2018 | 4000000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3487282 | 99.6 | 3487282 | 0 | 12718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wilkin ventures.
9078 | Kaburi ECDE - Construction of I classroom | Kaburi ECDE - Construction of I classroom | To implement kaburi ecde - construction of i classroom for access to quality education and training | Kaburi ECDE - Construction of I classroom completed | 4130299 | N/A | BAHATI | DUNDORI | -0.237247 36.23572 2418 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
9079 | Construction of an ECD classroom at Dundori primary school | Construction of an ECD classroom at Dundori primary school | To construct an ECD classroom at Dundori primary school | An ECD classroom at Dundori primary school constructed | 4130299 | N/A | Bahati | Dundori | -0.25394, 36.238355 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199978 | 100 | 1199978 | 22 | 22 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms Top Notch.
9080 | construction of Mikeu ECDE classroom | construction of Mikeu ECDE classroom | To construct Mikeu ECDE classroom | Mikeu ECDE classroom constructed | 4130299 | N/A | Bahati | Dundori | -0.249596 36.231481 2331.10009765625 20 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done under NKU/CITY/222/2013-2014 no septic tank constructed.
9081 | Kaburi ECDE - Construction of I classroom | Kaburi ECDE - Construction of I classroom | To implement kaburi ecde - construction of i classroom for access to quality education and training | Kaburi ECDE - Construction of I classroom completed | 4130299 | N/A | Bahati | Dundori | -0.237247 36.23572 2418 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
9082 | Completion of Kongasis Polytechnic | Completion of Kongasis Polytechnic | To complete Kongasis Polytechnic | Kongasis Polytechnic completed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9083 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD constructed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1197000 | 99.8 | 1197000 | 156146 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9084 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD constructed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1195536 | 99.6 | 1195536 | 156146 | 4464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9085 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD constructed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 156146 | 156146 | Equitable | N/A | 156146 | 0 | 1195536 | 765.7 | 1195536 | 156146 | -1039390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9086 | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | To construct 3 ECD classroom at Morop Primary and Kiungururia primary | 3 ECD classroom at Morop Primary and Kiungururia primary constructed | 4130299 | N/A | GILGIL | EBURRU-MBARUK | -0.605373, 36.164023 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Unspecified | 3600000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2160890 | 90 | 2160890 | 239110 | 239110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unspecified.
9087 | Construction of ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | Construction of ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | To construct ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations constructed | 4130299 | N/A | MOLO | ELBURGON | -0.303254, 35.816855 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | - | 7200001 | 5364161 | 5364161 | Equitable | N/A | 5364161 | 0 | 3961667 | 73.9 | 3961667 | 1402494 | 1402494 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
9088 | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) | To implement constuction of 3 ecd classrom in (mukinyai ecd, st. stephen ecd and mutate primary ecd) for access to quality education and training | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) completed | 4130299 | N/A | MOLO | ELBURGON | -0.203536, 35.817258 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | - | 3600000 | 2414990 | 2414990 | Equitable | N/A | 2414990 | 0 | 1192608 | 49.4 | 1192608 | 1222382 | 1222382 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9089 | Construction of 1No. Classroom at Ebenezer ECD and Toilets | Construction of 1No. Classroom at Ebenezer ECD and Toilets | To construct 1No. Classroom at Ebenezer ECD and Toilets | 1No. Classroom at Ebenezer ECD and Toilets constructed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.5412 36.07037 2057.4 10.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199700 | 100 | 1199700 | 1200000 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9090 | Construction of 1No. Classroom at Kiambogo Township ECD | Construction of 1No. Classroom at Kiambogo Township ECD | To construct 1No. Classroom at Kiambogo Township ECD | 1No. Classroom at Kiambogo Township ECD constructed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.595422 36.130154 0 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1166090 | 97.2 | 1166090 | 1200000 | 33910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
9091 | Construction of 1No. Classroom at Muriricua Primary ECD | Construction of 1No. Classroom at Muriricua Primary ECD | To construct 1No. Classroom at Muriricua Primary ECD | 1No. Classroom at Muriricua Primary ECD constructed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.566243 36.119887 1951.9 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198280 | 409770 | 409770 | Equitable | N/A | 409770 | 0 | 1166090 | 284.6 | 1166090 | 409770 | -756320 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9092 | Construction of a classroom at Gwachati ECD | Construction of a classroom at Gwachati ECD | To construct a classroom at Gwachati ECD | A classroom at Gwachati ECD constructed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.616893 36.148898 2042.8999999999999 16.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 80430 | 8 | 80430 | 81930 | 919570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
9093 | Installation of lightning arresters at Elementaita ECD | Installation of lightning arresters at Elementaita ECD | To install lightning arresters at Elementaita ECD | Lightning arresters at Elementaita ECD installed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.616691, 36.125577 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9094 | Munanda pry ecd | Munanda pry ecd | To implement munanda pry ecd for access to quality education and training | Munanda pry ecd completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.594733, 36.109841 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199923 | 100 | 1199923 | 0 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9095 | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | To implement njeru ecde - construction of one classrooms at njeru ecde for access to quality education and training | Njeru ECDE - Construction of one Classrooms at Njeru ECDE completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.585127 36.13751 2039.304 5.4679999351501465 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 119 | 0 | 119 | 119 | 1199881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9096 | Ole Sultan polytechnic administration blocks and toilets | Ole Sultan polytechnic administration blocks and toilets | To implement ole sultan polytechnic administration blocks and toilets for access to quality education and training | Ole Sultan polytechnic administration blocks and toilets completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.567384 36.1137 1948.66 1.1130000352859497 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 3799982.4 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3799733 | 100 | 3799733 | 3800000 | 267 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9097 | Tangi tano ecd | Tangi tano ecd | To implement tangi tano ecd for access to quality education and training | Tangi tano ecd completed | 4130299 | N/A | GILGIL | ELEMENTAITA | -0.64194, 36.11936 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1299784 | 100 | 1299784 | 0 | 216 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9098 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD constructed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 156146 | 156146 | Equitable | N/A | 156146 | 0 | 1195536 | 765.7 | 1195536 | 156146 | -1039390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9099 | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | To construct 3 ECD classroom at Morop Primary and Kiungururia primary | 3 ECD classroom at Morop Primary and Kiungururia primary constructed | 4130299 | N/A | Gilgil | Eburru-Mbaruk | -0.605373, 36.164023 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Unspecified | 3600000 | 239110 | 239110 | Equitable | N/A | 239110 | 0 | 2160890 | 903.7 | 2160890 | 239110 | -1921780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unspecified.
9100 | Construction of Elburgon ECDE classroom | Construction of Elburgon ECDE classroom | To construct Elburgon ECDE classroom | Elburgon ECDE classroom constructed | 4130299 | N/A | Molo | Elburgon | -0.292714, 35.791345 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | - | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194994 | 99.6 | 1194994 | 1200000 | 5006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9101 | Constuction of Mutate Primary ECDE classroom | Constuction of Mutate Primary ECDE classroom | To implement constuction of mutate primary ecde classroom for access to quality education and training | Constuction of Mutate Primary ECDE classroom completed | 4130299 | N/A | Molo | Elburgon | -0.294954, 35.766447 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | - | 1222382 | 1222382 | 1222382 | Equitable | N/A | 1222382 | 0 | 1194994 | 97.8 | 1194994 | 1222382 | 27388 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9102 | Construction of 1No. Classroom at Kiambogo Township ECD | Construction of 1No. Classroom at Kiambogo Township ECD | To construct 1No. Classroom at Kiambogo Township ECD | 1No. Classroom at Kiambogo Township ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.595422 36.130154 0 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1166090 | 97.2 | 1166090 | 1200000 | 33910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
9103 | Construction of 1No. Classroom at Muriricua Primary ECD | Construction of 1No. Classroom at Muriricua Primary ECD | To construct 1No. Classroom at Muriricua Primary ECD | 1No. Classroom at Muriricua Primary ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.566243 36.119887 1951.9 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198280 | 409770 | 409770 | Equitable | N/A | 409770 | 0 | 1166090 | 284.6 | 1166090 | 409770 | -756320 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9104 | Construction of a classroom at Gwachati ECD | Construction of a classroom at Gwachati ECD | To construct a classroom at Gwachati ECD | A classroom at Gwachati ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.616893 36.148898 2042.8999999999999 16.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 80430 | 8 | 80430 | 81930 | 919570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
9105 | equipping Ole Sultan polytechnic and connection of electricity | equipping Ole Sultan polytechnic and connection of electricity | To equip Ole Sultan polytechnic and connection of electricity with necessary facilities and equipment | Ole Sultan polytechnic and connection of electricity equipped | 4130299 | N/A | Gilgil | Elementaita | -0.567565 36.114003 1993.429 1.6779999732971191 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2800000 | 100 | 2800000 | 2800000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not Functional.
9106 | Installation of lightning arresters at Elementaita ECD | Installation of lightning arresters at Elementaita ECD | To install lightning arresters at Elementaita ECD | Lightning arresters at Elementaita ECD installed | 4130299 | N/A | Gilgil | Elementaita | -0.616691, 36.125577 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9107 | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | To implement njeru ecde - construction of one classrooms at njeru ecde for access to quality education and training | Njeru ECDE - Construction of one Classrooms at Njeru ECDE completed | 4130299 | N/A | Gilgil | Elementaita | -0.585127 36.13751 2039.304 5.4679999351501465 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 119 | 0 | 119 | 119 | 1199881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9108 | Ole Sultan polytechnic administration blocks and toilets | Ole Sultan polytechnic administration blocks and toilets | To implement ole sultan polytechnic administration blocks and toilets for access to quality education and training | Ole Sultan polytechnic administration blocks and toilets completed | 4130299 | N/A | Gilgil | Elementaita | -0.567384 36.1137 1948.66 1.1130000352859497 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 3799982.4 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3799733 | 100 | 3799733 | 3800000 | 267 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9109 | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | To implement lakeview ecde center - construction of a perimetre wall and gate for access to quality education and training | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate completed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.30524, 36.078817 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | fy2017/2018 | 5000000 | 135987 | 135987 | Equitable | N/A | 135987 | 0 | 135987 | 100 | 135987 | 135987 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Peshmac Enteprises.
9110 | Rehabilitation of Langalanga Pri and Lakeview pry. | Rehabilitation of Langalanga Pri and Lakeview pry. | To rehabilitate Langalanga Pri and Lakeview pry to restore functionality | Langalanga Pri and Lakeview pry rehabilitated | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.305426, 36.078777 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | Fy/2016/2017 | 2902087.8 | 2084531.8 | 2084531.8 | Equitable | N/A | 2084531.8 | 0 | 2084532 | 100 | 2084532 | 0 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Contractor: Steadfast international Limited.
9111 | Design and construction of 2 ECDE classes at Lake view primary school | Design and construction of 2 ECDE classes at Lake view primary school | To design and construct 2 ECDE classes at Lake view primary school | 2 ECDE classes at Lake view primary school designed and constructed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.312617, 36.069464 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Fy2018-2019 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2385216 | 99.4 | 2385216 | 360243 | 14784 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Almaio Holdings.
9112 | Design and construction of 2 ECDE classes at Race track primary school | Design and construction of 2 ECDE classes at Race track primary school | To design and construct 2 ECDE classes at Race track primary school | 2 ECDE classes at Race track primary school designed and constructed | 4130299 | N/A | NAKURU EAST | FLAMINGO | -0.312617, 36.069464 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Fy2018-2019 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 352009 | 14.7 | 352009 | 360243 | 2047991 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Almaio Holdings.
9113 | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | To implement lakeview ecde center - construction of a perimetre wall and gate for access to quality education and training | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate completed | 4130299 | N/A | Nakuru East | Flamingo | -0.30524, 36.078817 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | fy2017/2018 | 5000000 | 135987 | 135987 | Equitable | N/A | 135987 | 0 | 135987 | 100 | 135987 | 135987 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Peshmac Enteprises.
9114 | Design and construction of 2 ECDE classes at Race track primary school | Design and construction of 2 ECDE classes at Race track primary school | To design and construct 2 ECDE classes at Race track primary school | 2 ECDE classes at Race track primary school designed and constructed | 4130299 | N/A | Nakuru East | Flamingo | -0.312617, 36.069464 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Fy2018-2019 | 2400000 | 360243 | 360243 | Equitable | N/A | 360243 | 0 | 352009 | 97.7 | 352009 | 360243 | 8234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Almaio Holdings.
9115 | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | To construct 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point constructed | 4130299 | N/A | GILGIL | GILGIL | -0.484536 36.336413 2011.800048828125 9.114999771118164 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999840 | 100 | 1999840 | 160 | 160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: One ECDE classroom constructed.
9116 | Construction of ECD classroom, equipping and construction of toilet at View point ECD centre | Construction of ECD classroom, equipping and construction of toilet at View point ECD centre | To construct ECD classroom, equipping and construction of toilet at View point ECD centre | ECD classroom, equipping and construction of toilet at View point ECD centre constructed | 4130299 | N/A | GILGIL | GILGIL | -0.507431 36.327348 1989.199951171875 12.510000228881836 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 1079308 | 1079308 | Equitable | N/A | 1079308 | 0 | 1079308 | 100 | 1079308 | 1682085 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project description does not match whats on the ground.
9117 | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | To construct 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point constructed | 4130299 | N/A | Gilgil | Gilgil | -0.484536 36.336413 2011.800048828125 9.114999771118164 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 160 | 160 | Equitable | N/A | 160 | 0 | 1999840 | 1249900 | 1999840 | 160 | -1999680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: One ECDE classroom constructed.
9118 | Airstrip ECDE - Construction of One Classroom and Equiping | Airstrip ECDE - Construction of One Classroom and Equiping | To implement airstrip ecde - construction of one classroom and equiping for access to quality education and training | Airstrip ECDE - Construction of One Classroom and Equiping completed | 4130299 | N/A | NAIVASHA | HELLS GATE | -0.778059, 36.42951 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1171977 | 58.6 | 1171977 | 1173036 | 828023 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Somewhat. Viable: Yes.
9119 | Karagita ECDE - Construction of One Classroom and Equiping | Karagita ECDE - Construction of One Classroom and Equiping | To implement karagita ecde - construction of one classroom and equiping for access to quality education and training | Karagita ECDE - Construction of One Classroom and Equiping completed | 4130299 | N/A | NAIVASHA | HELLS GATE | -0.776669, 36.433058 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998654 | 99.9 | 1998654 | 1998654 | 1346 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
9120 | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | To implement longonot deb pri school ecde - construction of two classrooms and equiping for access to quality education and training | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping completed | 4130299 | N/A | NAIVASHA | HELLS GATE | -0.814865, 36.399555 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2600000 | 86.7 | 2600000 | 3000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9121 | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) | To implement puchase of sport uniforms and equipments (hells gate youth empowerment) for access to quality education and training | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) completed | 4130299 | N/A | NAIVASHA | HELLS GATE | -0.778058 36.450916 1944.048828125 5.145999908447266 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999700 | 1999700 | 1999700 | Equitable | N/A | 1999700 | 0 | 1999700 | 100 | 1999700 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project cost is not indicated.
9122 | Construction of 1 ECD class and toilet at Mirera Primary | Construction of 1 ECD class and toilet at Mirera Primary | To construct 1 ECD class and toilet at Mirera Primary | 1 ECD class and toilet at Mirera Primary constructed | 4130299 | N/A | NAIVASHA | HELLS GATE | -0.78239, 36.445743 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1487282 | 99.2 | 1487282 | 1199658 | 12718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: If it was done would be more viable because the population of the school is so high.
9123 | Construction of Resource and Training centre-Nakuru VTC. | Construction of Resource and Training centre-Nakuru VTC. | To construct Resource and Training centre-Nakuru VTC | Resource and Training centre-Nakuru VTC constructed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 14000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 19900008 | 199 | 19900008 | 4986452 | -9900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9124 | Construction of workshops- Njoro VTC | Construction of workshops- Njoro VTC | To construct workshops- Njoro VTC | Workshops- Njoro VTC constructed | 4130299 | N/A | HQ | HQ | -0.337502, 35.952445 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 6000000 | 3386755 | 3386755 | Equitable | Equitable | 3386755 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Yes. Contractor: Fabrica Building and construction company Ltd.
9125 | Digital Centres internet setup | Digital Centres internet setup | To implement digital centres internet setup for access to quality education and training | Digital Centres internet setup completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4672484 | 233.6 | 4672484 | 4942144 | -2672484 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9126 | Equiping youth polytechnics | Equiping youth polytechnics | To implement equiping youth polytechnics for access to quality education and training | Equiping youth polytechnics completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 8800000 | 8800000 | Equitable | N/A | 8800000 | 0 | 4123683 | 46.9 | 4123683 | 8800000 | 4676317 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9127 | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto | To implement establishment of wi-fi hotspots at county hq- nyayo gardens, naivasha recreational park, kuresoi south digital centres, subukia digital centre, rongai - kampi ya moto for access to quality education and training | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 18750000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5747366 | 95.8 | 5747366 | 0 | 252634 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Status: Complete. Recommendation: Retain and archive.
9128 | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties | To implement improvement of learning environment through equipping of ecde centres in all sub counties for access to quality education and training | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 20597085 | 3064542 | 3064542 | Equitable | N/A | 3064542 | 0 | 1744000 | 56.9 | 1744000 | 1745742 | 1320542 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9129 | Pangani special school | Pangani special school | To implement pangani special school for access to quality education and training | Pangani special school completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | Equitable | 4000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9130 | Rehabilitation Of Nakuru Polytechnic PHASE2 | Rehabilitation Of Nakuru Polytechnic PHASE2 | To rehabilitate Nakuru Polytechnic PHASE2 to restore functionality | Nakuru Polytechnic PHASE2 rehabilitated | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999984 | 3999984 | 3999984 | Equitable | N/A | 3999984 | 0 | 3905534 | 97.6 | 3905534 | 11000000 | 94450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9131 | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties | To implement reinforcement of county server rooms and digital centres in all sub counties for access to quality education and training | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 2631780 | 2631780 | Equitable | N/A | 2631780 | 0 | 2217197 | 84.2 | 2217197 | 414583 | 414583 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9132 | Revitalization Of youth Polytechnic | Revitalization Of youth Polytechnic | To implement revitalization of youth polytechnic for access to quality education and training | Revitalization Of youth Polytechnic completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 20000000 | 3796433 | 3796433 | Equitable | N/A | 3796433 | 0 | 623800 | 16.4 | 623800 | 659133 | 3172633 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9133 | Software development - Email solution, Bursary and feeding programme management software | Software development - Email solution, Bursary and feeding programme management software | To implement software development - email solution, bursary and feeding programme management software for access to quality education and training | Software development - Email solution, Bursary and feeding programme management software completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 1607903 | 1607903 | Equitable | N/A | 1607903 | 0 | 884500 | 55 | 884500 | 723403 | 723403 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9134 | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall | To implement wide area network (wan) connectivity at county hq, regional coordinator's complex, all sub-counties, department of infrastructure department of lands, housing & physical planning, subukia digital centre, kuresoi south digital centre, old town hall for access to quality education and training | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall completed | 4130299 | N/A | HQ | HQ | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 65000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5983283 | 99.7 | 5983283 | 0 | 16717 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9135 | Airstrip ECDE - Construction of One Classroom and Equiping | Airstrip ECDE - Construction of One Classroom and Equiping | To implement airstrip ecde - construction of one classroom and equiping for access to quality education and training | Airstrip ECDE - Construction of One Classroom and Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.778059, 36.42951 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1171977 | 58.6 | 1171977 | 1173036 | 828023 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Somewhat. Viable: Yes.
9136 | Karagita ECDE - Construction of One Classroom and Equiping | Karagita ECDE - Construction of One Classroom and Equiping | To implement karagita ecde - construction of one classroom and equiping for access to quality education and training | Karagita ECDE - Construction of One Classroom and Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.776669, 36.433058 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998654 | 99.9 | 1998654 | 1998654 | 1346 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
9137 | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | To implement longonot deb pri school ecde - construction of two classrooms and equiping for access to quality education and training | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.814865, 36.399555 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2600000 | 86.7 | 2600000 | 3000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9138 | Construction of Wendo polytechnic | Construction of Wendo polytechnic | To construct Wendo polytechnic | Wendo polytechnic constructed | 4130299 | N/A | BAHATI | KABATINI | -0.181071, 36.180736 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2135 | 0 | 2135 | 2135 | 4497865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers general supplies and company.
9139 | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, | To implement kabatini ward ecds - design and construction of 2 no. ecd classroom at wendo and kiugu, design and construction of teachers toilet, for access to quality education and training | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, completed | 4130299 | N/A | BAHATI | KABATINI | -0.232131 36.147748 1941.300048828125 37.290000915527344 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2400000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s max victor enterprise. Assessor remarks: Currently not operational,boda.-boda riders relocated because its in accessible requires installation of culvert.
9140 | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | To construct Mahinga ECDE toilet - construction of Mahinga ECDE toilet | Mahinga ECDE toilet - construction of Mahinga ECDE toilet constructed | 4130299 | N/A | SUBUKIA | KABAZI | -0.12904 36.15429 0 220 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699162 | 99.9 | 699162 | 699162 | 838 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
9141 | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | To construct 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms constructed | 4130299 | N/A | SUBUKIA | KABAZI | -0.08223 36.16987 0 1381 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2700000 | 2700000 | 2700000 | Equitable | Equitable | 2700000 | 0 | 2700000 | 100 | 2700000 | 2700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works Ltd. Assessor remarks: Requires equipping, toilets and kitchen.
9142 | Construction Of 3 ECD classroom at Kimochoch, Marigu B and Kihoto | Construction Of 3 ECD classroom at Kimochoch, Marigu B and Kihoto | To construct 3 ECD classroom at Kimochoch, Marigu B and Kihoto | 3 ECD classroom at Kimochoch, Marigu B and Kihoto constructed | 4130299 | N/A | SUBUKIA | KABAZI | -0.08223, 36.16987 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399056 | 100 | 2399056 | 37 | 944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
9143 | Construction of ECD class at Bureti ECD | Construction of ECD class at Bureti ECD | To construct ECD class at Bureti ECD | ECD class at Bureti ECD constructed | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.092833 35.682177 2536.4 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 830 | 0.1 | 830 | 830 | 1199170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs additional teachers, classrooms, furniture and pitlatrines.
9144 | Construction of ECD class at Choronok ECD | Construction of ECD class at Choronok ECD | To construct ECD class at Choronok ECD | ECD class at Choronok ECD constructed | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.210503 35.662043 2676.9 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1199975 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot Enterprises. Assessor remarks: Project needs more classrooms a pit latrines.
9145 | Construction of ECD class at Taban ECD | Construction of ECD class at Taban ECD | To construct ECD class at Taban ECD | ECD class at Taban ECD constructed | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.07866 35.672895 2565.1 2.9000000953674316 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2314 | 0.2 | 2314 | 2314 | 1197686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
9146 | Equipping of Kamara polytechnic | Equipping of Kamara polytechnic | To equip Kamara polytechnic with necessary facilities and equipment | Kamara polytechnic equipped | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.167952 35.675978 2630.6 10.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 987900 | 98.8 | 987900 | 1000000 | 12100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs more equipments.
9147 | Rironi ecd LAND | Rironi ecd LAND | To implement rironi ecd land for access to quality education and training | Rironi ecd LAND completed | 4130299 | N/A | KURESOI NORTH | KAMARA | -0.176747 35.712237 2487.6 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Land not purchased.
9148 | Construction of 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | Construction of 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | To construct 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD constructed | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.306306, 36.036551 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399998 | 2399998 | 2399998 | Equitable | N/A | 2399998 | 0 | 2399945 | 100 | 2399945 | 800 | 53 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving well.
9149 | Ingobor phase 2 | Ingobor phase 2 | To implement ingobor phase 2 for access to quality education and training | Ingobor phase 2 completed | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.288288 36.000456 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1352110 | 1352110 | 1352110 | Equitable | N/A | 1352110 | 0 | 1105828 | 81.8 | 1105828 | 246282 | 246282 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has improved work environment. Assessor remarks: Done and in use.
9150 | Lalwet ECD land | Lalwet ECD land | To implement lalwet ecd land for access to quality education and training | Lalwet ECD land completed | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving as school. Assessor remarks: About 1and quarter acreLand purchased and serving.
9151 | toilet desks,desk and washing point ingobor | toilet desks,desk and washing point ingobor | To implement toilet desks,desk and washing point ingobor for access to quality education and training | toilet desks,desk and washing point ingobor completed | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.306306 36.018533 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2949834.6 | 2949834.6 | 2949834.6 | Equitable | N/A | 2949834.6 | 0 | 1635 | 0.1 | 1635 | 1635 | 2948199.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. But did not meet needs. Assessor remarks: Stalled. Not completed.
9152 | Purchase of land for construction of a Polytechnic in Ingobor | Purchase of land for construction of a Polytechnic in Ingobor | To acquire land for construction of a Polytechnic in Ingobor | Land for construction of a Polytechnic in Ingobor acquired | 4130299 | N/A | NAKURU WEST | KAPKURES | -0.324324 36.018595 0 2591.7880859375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but has not been developed. Assessor remarks: Land was bought. Has not been developed.
9153 | Construction of 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | Construction of 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | To construct 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school constructed | 4130299 | N/A | NAKURU WEST | KAPTEMBWO | -0.310577 36.05279 1787.5 72.9000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 276605 | 276605 | Equitable | N/A | 276605 | 0 | 271440 | 98.1 | 271440 | 3800000 | 5165 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Contractor: PANASCOPE HOLDINGS LTD. Assessor remarks: Complete but it has chipped and pothole floors need renovation.
9154 | construction of 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | construction of 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | To construct 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school constructed | 4130299 | N/A | NAKURU WEST | KAPTEMBWO | -0.310577 36.05279 1787.5 72.9000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599994 | 100 | 1599994 | 3800000 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Contractor: PANASCOPE HOLDINGS LTD. Assessor remarks: Complete but it has chipped and pothole floors need renovation.
9155 | Bararget ukwala ecd | Bararget ukwala ecd | To implement bararget ukwala ecd for access to quality education and training | Bararget ukwala ecd completed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.391032, 35.7425 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 999532 | 999532 | 999532 | Equitable | N/A | 999532 | 0 | 0 | 0 | 0 | 999532 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9156 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 340868 | 28.4 | 340868 | 1199950 | 859082 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9157 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 156142.8 | 156142.8 | Equitable | N/A | 156142.8 | 0 | 156143 | 100 | 156143 | 156143 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9158 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9159 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 497952 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9160 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 497952 | 497952 | Equitable | N/A | 497952 | 0 | 340868 | 68.5 | 340868 | 497952 | 157084 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9161 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 1199997.8 | 1199997.8 | Equitable | N/A | 1199997.8 | 0 | 340868 | 28.4 | 340868 | 340868 | 859129.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9162 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199990 | 1199990 | 1199990 | Equitable | N/A | 1199990 | 0 | 1199990 | 100 | 1199990 | 1199990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9163 | Construction of 2 No classrooms at Upendo | Construction of 2 No classrooms at Upendo | To construct 2 No classrooms at Upendo | 2 No classrooms at Upendo constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.463932 35.69647 2646.3 6.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1693833 | 1693833 | 1693833 | Equitable | N/A | 1693833 | 0 | 667928 | 39.4 | 667928 | 1693833 | 1025905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9164 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 4130299 | N/A | KURESOI SOUTH | KERINGET | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9165 | Construction of Kapkwen ECD Classroom | Construction of Kapkwen ECD Classroom | To construct Kapkwen ECD Classroom | Kapkwen ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.463567 35.709915 2674.6 9.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 667928 | 55.7 | 667928 | 1200000 | 532072 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating.
9166 | construction of Lelaibei ECDE classroom | construction of Lelaibei ECDE classroom | To construct Lelaibei ECDE classroom | Lelaibei ECDE classroom constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.527932 35.73419 2592.6 50.099998474121094 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 312620 | 26.1 | 312620 | 1200000 | 887380 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9167 | Construction of Saptet ECD Classroom | Construction of Saptet ECD Classroom | To construct Saptet ECD Classroom | Saptet ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.485137 35.699573 2616.3 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 667928 | 50.2 | 667928 | 183305 | 662072 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need another classroom.
9168 | Construction of Tendwet ECD Classroom | Construction of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KERINGET | -0.50589, 35.698535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 312620 | 23.5 | 312620 | 538613 | 1017380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9169 | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD | To implement kiamaina ward ecds - purchase of land for ecd expansion for st peter primary ecd and central primary ecd for access to quality education and training | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD completed | 4130299 | N/A | BAHATI | KIAMAINA | -0.236625 36.133717 1909.5 3.200000047683716 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 0 | 0 | 0 | 3400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It's viable if can be purchased. Assessor remarks: No land purchased.
9170 | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet | To implement workers primary ecd - design and construction of 1 ecd class room and pupils toilet for access to quality education and training | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet completed | 4130299 | N/A | BAHATI | KIAMAINA | -0.268707 36.114891 1863.5 48.20000076293945 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1782004 | 99 | 1782004 | 0 | 17996 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
9171 | 2 class Davishon ECD and Kariaini ECD | 2 class Davishon ECD and Kariaini ECD | To implement 2 class davishon ecd and kariaini ecd for access to quality education and training | 2 class Davishon ECD and Kariaini ECD completed | 4130299 | N/A | NJORO | KIHINGO | -0.476213 35.988603 2288 17.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1849000 | 1849000 | 1849000 | Equitable | N/A | 1849000 | 0 | 1849000 | 100 | 1849000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: At that time yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
9172 | Construction of 1 no ECD classroom at Davishon ECD | Construction of 1 no ECD classroom at Davishon ECD | To construct 1 no ECD classroom at Davishon ECD | 1 no ECD classroom at Davishon ECD constructed | 4130299 | N/A | NJORO | KIHINGO | -0.440443 35.983555 2278.2001953125 4.400000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199612 | 100 | 1199612 | 0 | 388 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation required.
9173 | Construction of 1 no ECD classroom at Mutitu B ECD | Construction of 1 no ECD classroom at Mutitu B ECD | To construct 1 no ECD classroom at Mutitu B ECD | 1 no ECD classroom at Mutitu B ECD constructed | 4130299 | N/A | NJORO | KIHINGO | -0.433837 35.96382 2225.1000000000004 12.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1185259 | 1185259 | 1185259 | Equitable | Equitable | 1185259 | 0 | 219716 | 18.5 | 219716 | 0 | 965543 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9174 | Construction of 1 no ECD classroom at Njugu ini ECD | Construction of 1 no ECD classroom at Njugu ini ECD | To construct 1 no ECD classroom at Njugu ini ECD | 1 no ECD classroom at Njugu ini ECD constructed | 4130299 | N/A | NJORO | KIHINGO | -0.440443 35.983555 2278.2001953125 4.400000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199612 | 100 | 1199612 | 0 | 388 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation required.
9175 | KARIAINI ECD | KARIAINI ECD | To implement kariaini ecd for access to quality education and training | KARIAINI ECD completed | 4130299 | N/A | NJORO | KIHINGO | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1080098 | 663236 | 663236 | Equitable | N/A | 663236 | 0 | 1080098 | 162.9 | 1080098 | 0 | -416862 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9176 | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom | To implement kio ecd classroom - construction of a ecde classroom kio ecd classroom for access to quality education and training | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom completed | 4130299 | N/A | NJORO | KIHINGO | -0.455877 35.985462 2286.60009765625 16.200000762939453 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199393 | 99.9 | 1199393 | 600000 | 607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
9177 | Toilet block njuguini | Toilet block njuguini | To implement toilet block njuguini for access to quality education and training | Toilet block njuguini completed | 4130299 | N/A | NJORO | KIHINGO | -0.440014 35.974624 2303.300048828125 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
9178 | Construction of ECD classroom at Mutarakwa Primary | Construction of ECD classroom at Mutarakwa Primary | To construct ECD classroom at Mutarakwa Primary | ECD classroom at Mutarakwa Primary constructed | 4130299 | N/A | NJORO | KIHINGO | -0.476557 35.987107 2230.1 12.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1148599 | 95.7 | 1148599 | 51401 | 51401 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation and ECDE toilets.
9179 | Construction of ECD Toilets at Mutito ECD Centre | Construction of ECD Toilets at Mutito ECD Centre | To construct ECD Toilets at Mutito ECD Centre | ECD Toilets at Mutito ECD Centre constructed | 4130299 | N/A | NJORO | KIHINGO | -0.426452 35.9737 2257.5 14.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 219716 | 36.6 | 219716 | 600000 | 380284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
9180 | Construction of ECD Toilets at Mutiume Primary | Construction of ECD Toilets at Mutiume Primary | To construct ECD Toilets at Mutiume Primary | ECD Toilets at Mutiume Primary constructed | 4130299 | N/A | NJORO | KIHINGO | -0.476557 35.987107 2230.1 12.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1148599 | 191.4 | 1148599 | 600000 | -548599 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation and ECDE toilets.
9181 | Cheptuech polytechnic | Cheptuech polytechnic | To implement cheptuech polytechnic for access to quality education and training | Cheptuech polytechnic completed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.59162 35.645365 2576.7 24.700000762939453 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road for a permanent solution.
9182 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1270177 | 84.7 | 1270177 | 229823 | 229823 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
9183 | Construction of Emitik ECD Classroom | Construction of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1799740 | 5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
9184 | Construction of Konoin ECD Classroom | Construction of Konoin ECD Classroom | To construct Konoin ECD Classroom | Konoin ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.57719, 35.57822 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1200000 | 5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
9185 | Construction of Sitotwet ECD Classroom | Construction of Sitotwet ECD Classroom | To construct Sitotwet ECD Classroom | Sitotwet ECD Classroom constructed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.598048 35.611248 2413 13.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 202597 | 202597 | Equitable | N/A | 202597 | 0 | 1199995 | 592.3 | 1199995 | 202597 | -997398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
9186 | ECD classes:-Sototwet | ECD classes:-Sototwet | To implement ecd classes:-sototwet for access to quality education and training | ECD classes:-Sototwet completed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.656443 35.6033 2446.4 5.599999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | N/A | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 0 | 0 | 0 | 999363 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional but there are no toilets..
9187 | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | To implement ketitui central ecde classroom - design and construction of ketitui ecde classroom for access to quality education and training | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom completed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
9188 | Seger ECDE classroom - design and construction of Seger ECDE classroom | Seger ECDE classroom - design and construction of Seger ECDE classroom | To implement seger ecde classroom - design and construction of seger ecde classroom for access to quality education and training | Seger ECDE classroom - design and construction of Seger ECDE classroom completed | 4130299 | N/A | KURESOI SOUTH | KIPTAGICH | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 519208 | 519208 | Equitable | N/A | 519208 | 0 | 519198 | 100 | 519198 | 1200000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
9189 | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | To implement chemare ecd - design and construction of 1. no ecd classroom at kipkoimet ecd for access to quality education and training | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 376428 | 376428 | Equitable | N/A | 376428 | 0 | 648869 | 172.4 | 648869 | 376428 | -272441 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
9190 | Chepkoburot AGPO(YOUTH) polytechnic | Chepkoburot AGPO(YOUTH) polytechnic | To implement chepkoburot agpo(youth) polytechnic for access to quality education and training | Chepkoburot AGPO(YOUTH) polytechnic completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.438436, 35.510129 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999994 | 100 | 1999994 | 0 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes.
9191 | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | To implement chorwa ecd - design and construction of 1. no ecd classroom at chorwa ecd for access to quality education and training | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1625 | 0.1 | 1625 | 1625 | 1198375 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
9192 | Construction and equipping of an ECD classroom at Kibara | Construction and equipping of an ECD classroom at Kibara | To construct and equip an ECD classroom at Kibara | An ECD classroom at Kibara constructed and equipped | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.356669 35.481787 0 2099.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1999909 | 100 | 1999909 | 91 | 91 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
9193 | Construction of an ECD classroom at Chebuiyot | Construction of an ECD classroom at Chebuiyot | To construct an ECD classroom at Chebuiyot | An ECD classroom at Chebuiyot constructed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.376802 35.529802 2495.7 15.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
9194 | Construction of an ECD classroom at Kapsongop | Construction of an ECD classroom at Kapsongop | To construct an ECD classroom at Kapsongop | An ECD classroom at Kapsongop constructed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.385457 35.486922 0 2900 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete requires minor repair and it requres permanent pit latrine.
9195 | Githima ECD | Githima ECD | To implement githima ecd for access to quality education and training | Githima ECD completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.302533, 35.5297 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1499913 | 1499913 | 1499913 | Equitable | N/A | 1499913 | 0 | 1499913 | 100 | 1499913 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
9196 | Lemechonik ECD | Lemechonik ECD | To implement lemechonik ecd for access to quality education and training | Lemechonik ECD completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.35001 35.567448 2687.8 8.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1495414 | 1495414 | 1495414 | Equitable | N/A | 1495414 | 0 | 1495414 | 100 | 1495414 | 1495414 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovations and painting of classrooms.
9197 | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD | To implement tiloa ecde - design and construction of 1. no ecd classroom at kipkewa ecd for access to quality education and training | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD completed | 4130299 | N/A | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 650253 | 650253 | Equitable | N/A | 650253 | 0 | 648869 | 99.8 | 648869 | 376428 | 1384 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
9198 | Baharini And Nakuru Primary ECD - Construction of I classroom Each | Baharini And Nakuru Primary ECD - Construction of I classroom Each | To implement baharini and nakuru primary ecd - construction of i classroom each for access to quality education and training | Baharini And Nakuru Primary ECD - Construction of I classroom Each completed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.298432, 36.080159 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2190474 | 91.3 | 2190474 | 0 | 209526 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
9199 | Baharini Primary ECD school - Completion of a toilet block | Baharini Primary ECD school - Completion of a toilet block | To implement baharini primary ecd school - completion of a toilet block for access to quality education and training | Baharini Primary ECD school - Completion of a toilet block completed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.298431, 36.080159 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 984109 | 98.4 | 984109 | 0 | 15891 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9200 | Refurbishment of ECD classrooms within the ward | Refurbishment of ECD classrooms within the ward | To implement refurbishment of ecd classrooms within the ward for access to quality education and training | Refurbishment of ECD classrooms within the ward completed | 4130299 | N/A | NAKURU EAST | KIVUMBINI | -0.297797 36.080779 1790.699951171875 56.099998474121094 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997681 | 99.8 | 997681 | 0 | 2319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance required.
9201 | construction of ECDE classroom, toilets and water point at Cedar lodge | construction of ECDE classroom, toilets and water point at Cedar lodge | To construct ECDE classroom, toilets and water point at Cedar lodge | ECDE classroom, toilets and water point at Cedar lodge constructed | 4130299 | N/A | Bahati | Kabatini | -0.186813 36.177893 2119.520263671875 21.0049991607666 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1650000 | 97.1 | 1650000 | 1700000 | 50000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/a EDROSE ventures limited. Assessor remarks: Project is complete and in use.
9202 | Construction of Wendo polytechnic | Construction of Wendo polytechnic | To construct Wendo polytechnic | Wendo polytechnic constructed | 4130299 | N/A | Bahati | Kabatini | -0.181071, 36.180736 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2500021 | 2500021 | Equitable | N/A | 2500021 | 0 | 2135 | 0.1 | 2135 | 2135 | 2497886 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers general supplies and company.
9203 | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | To construct Mahinga ECDE toilet - construction of Mahinga ECDE toilet | Mahinga ECDE toilet - construction of Mahinga ECDE toilet constructed | 4130299 | N/A | Subukia | Kabazi | -0.12904 36.15429 0 220 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 700000 | 699162.14 | 699162.14 | Equitable | N/A | 699162.14 | 0 | 699162 | 100 | 699162 | 699162 | 0.14 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
9204 | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | To construct 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms constructed | 4130299 | N/A | Subukia | Kabazi | -0.08223 36.16987 0 1381 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2700000 | 2700000 | 2700000 | Equitable | Equitable | 2700000 | 0 | 2700000 | 100 | 2700000 | 2700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works Ltd. Assessor remarks: Requires equipping, toilets and kitchen.
9205 | Construction of ECD class at Bureti ECD | Construction of ECD class at Bureti ECD | To construct ECD class at Bureti ECD | ECD class at Bureti ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.092833 35.682177 2536.4 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 830 | 0.1 | 830 | 830 | 1199170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs additional teachers, classrooms, furniture and pitlatrines.
9206 | Construction of ECD class at Choronok ECD | Construction of ECD class at Choronok ECD | To construct ECD class at Choronok ECD | ECD class at Choronok ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.210503 35.662043 2676.9 3.0999999046325684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1199975 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot Enterprises. Assessor remarks: Project needs more classrooms a pit latrines.
9207 | Construction of ECD class at Taban ECD | Construction of ECD class at Taban ECD | To construct ECD class at Taban ECD | ECD class at Taban ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.07866 35.672895 2565.1 2.9000000953674316 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2314 | 0.2 | 2314 | 2314 | 1197686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
9208 | Equipping of Kamara polytechnic | Equipping of Kamara polytechnic | To equip Kamara polytechnic with necessary facilities and equipment | Kamara polytechnic equipped | 4130299 | N/A | Kuresoi North | Kamara | -0.167952 35.675978 2630.6 10.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 987900 | 98.8 | 987900 | 1000000 | 12100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs more equipments.
9209 | Ingobor phase 2 | Ingobor phase 2 | To implement ingobor phase 2 for access to quality education and training | Ingobor phase 2 completed | 4130299 | N/A | Nakuru West | Kapkures | -0.288288 36.000456 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1352110 | 246282 | 246282 | Equitable | N/A | 246282 | 0 | 1105828 | 449 | 1105828 | 246282 | -859546 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has improved work environment. Assessor remarks: Done and in use.
9210 | Lalwet ECD land | Lalwet ECD land | To implement lalwet ecd land for access to quality education and training | Lalwet ECD land completed | 4130299 | N/A | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving as school. Assessor remarks: About 1and quarter acreLand purchased and serving.
9211 | toilet desks,desk and washing point ingobor | toilet desks,desk and washing point ingobor | To implement toilet desks,desk and washing point ingobor for access to quality education and training | toilet desks,desk and washing point ingobor completed | 4130299 | N/A | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2949834.6 | 2949834.6 | 2949834.6 | Equitable | N/A | 2949834.6 | 0 | 1635 | 0.1 | 1635 | 1635 | 2948199.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. But did not meet needs. Assessor remarks: Stalled. Not completed.
9212 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 156142.8 | 156142.8 | Equitable | N/A | 156142.8 | 0 | 156143 | 100 | 156143 | 156143 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9213 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9214 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 497952 | 497952 | Equitable | N/A | 497952 | 0 | 340868 | 68.5 | 340868 | 497952 | 157084 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9215 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 340868.16 | 340868.16 | Equitable | N/A | 340868.16 | 0 | 340868 | 100 | 340868 | 340868 | 0.16 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9216 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199990 | 1199990 | 1199990 | Equitable | N/A | 1199990 | 0 | 1199990 | 100 | 1199990 | 1199990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9217 | Construction of 2 No classrooms at Upendo | Construction of 2 No classrooms at Upendo | To construct 2 No classrooms at Upendo | 2 No classrooms at Upendo constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.463932 35.69647 2646.3 6.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1693833 | 1693833 | 1693833 | Equitable | N/A | 1693833 | 0 | 667928 | 39.4 | 667928 | 1693833 | 1025905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9218 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 4130299 | N/A | Kuresoi South | Keringet | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9219 | Construction of Saptet ECD Classroom | Construction of Saptet ECD Classroom | To construct Saptet ECD Classroom | Saptet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.485137 35.699573 2616.3 98.4000015258789 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 667928 | 50.2 | 667928 | 183305 | 662072 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need another classroom.
9220 | Construction of Tendwet ECD Classroom | Construction of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.50589, 35.698535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 312620 | 23.5 | 312620 | 538613 | 1017380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9221 | Construction of 1 no ECD classroom at Mutitu B ECD | Construction of 1 no ECD classroom at Mutitu B ECD | To construct 1 no ECD classroom at Mutitu B ECD | 1 no ECD classroom at Mutitu B ECD constructed | 4130299 | N/A | Njoro | Kihingo | -0.433837 35.96382 2225.1000000000004 12.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1185259 | 219716 | 219716 | Equitable | Equitable | 219716 | 0 | 219716 | 100 | 219716 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9222 | Construction of ECD classroom at Mutarakwa Primary | Construction of ECD classroom at Mutarakwa Primary | To construct ECD classroom at Mutarakwa Primary | ECD classroom at Mutarakwa Primary constructed | 4130299 | N/A | Njoro | Kihingo | -0.476557 35.987107 2230.1 12.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 51401 | 51401 | Equitable | N/A | 51401 | 0 | 1148599 | 2234.6 | 1148599 | 51401 | -1097198 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation and ECDE toilets.
9223 | Cheptuech polytechnic | Cheptuech polytechnic | To implement cheptuech polytechnic for access to quality education and training | Cheptuech polytechnic completed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.59162 35.645365 2576.7 24.700000762939453 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road for a permanent solution.
9224 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 229823.2 | 229823.2 | Equitable | N/A | 229823.2 | 0 | 1270177 | 552.7 | 1270177 | 229823 | -1040353.8 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
9225 | construction of Ekabugunot ECDE | construction of Ekabugunot ECDE | To construct Ekabugunot ECDE | Ekabugunot ECDE constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 1199995 | 120.1 | 1199995 | 999363 | -200632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
9226 | Construction of Emitik ECD Classroom | Construction of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1799740 | 5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
9227 | Construction of Konoin ECD Classroom | Construction of Konoin ECD Classroom | To construct Konoin ECD Classroom | Konoin ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.57719, 35.57822 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1200000 | 5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
9228 | Construction of Sitotwet ECD Classroom | Construction of Sitotwet ECD Classroom | To construct Sitotwet ECD Classroom | Sitotwet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.598048 35.611248 2413 13.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 202597 | 202597 | Equitable | N/A | 202597 | 0 | 1199995 | 592.3 | 1199995 | 202597 | -997398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
9229 | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | To implement ketitui central ecde classroom - design and construction of ketitui ecde classroom for access to quality education and training | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom completed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
9230 | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | To implement chemare ecd - design and construction of 1. no ecd classroom at kipkoimet ecd for access to quality education and training | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 376428 | 376428 | Equitable | N/A | 376428 | 0 | 648869 | 172.4 | 648869 | 376428 | -272441 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
9231 | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | To implement chorwa ecd - design and construction of 1. no ecd classroom at chorwa ecd for access to quality education and training | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1625 | 0.1 | 1625 | 1625 | 1198375 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
9232 | Construction and equipping of an ECD classroom at Kibara | Construction and equipping of an ECD classroom at Kibara | To construct and equip an ECD classroom at Kibara | An ECD classroom at Kibara constructed and equipped | 4130299 | N/A | Kuresoi North | Kiptororo | -0.356669 35.481787 0 2099.9990234375 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 91 | 91 | Equitable | Equitable | 91 | 0 | 1999909 | 2197702.2 | 1999909 | 91 | -1999818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
9233 | Construction of an ECD classroom at Chebuiyot | Construction of an ECD classroom at Chebuiyot | To construct an ECD classroom at Chebuiyot | An ECD classroom at Chebuiyot constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
9234 | Lemechonik ECD | Lemechonik ECD | To implement lemechonik ecd for access to quality education and training | Lemechonik ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.35001 35.567448 2687.8 8.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1495414 | 1495414 | 1495414 | Equitable | N/A | 1495414 | 0 | 1495414 | 100 | 1495414 | 1495414 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovations and painting of classrooms.
9235 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD constructed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.734177, 36.4362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2099948 | 1282392 | 1282392 | Equitable | N/A | 1282392 | 0 | 1282392 | 100 | 1282392 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Chipped floor. Viable: Yes.
9236 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD constructed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.734177, 36.4362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099890 | 100 | 2099890 | 0 | 110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Chipped floor. Viable: Yes.
9237 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD constructed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.734177, 36.4362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 908379 | 908379 | Equitable | N/A | 908379 | 0 | 906432 | 99.8 | 906432 | 0 | 1947 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Chipped floor. Viable: Yes.
9238 | Lakeview ECD Classrooms Construction of 4 ECD classrooms | Lakeview ECD Classrooms Construction of 4 ECD classrooms | To implement lakeview ecd classrooms construction of 4 ecd classrooms for access to quality education and training | Lakeview ECD Classrooms Construction of 4 ECD classrooms completed | 4130299 | N/A | NAIVASHA | LAKEVIEW | -0.734197, 36.435788 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 3199716 | 64 | 3199716 | 1800284 | 1800284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9239 | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | To construct perimeter wall, gate and toilet at Ndege Polytechnic | Perimeter wall, gate and toilet at Ndege Polytechnic constructed | 4130299 | N/A | BAHATI | LANET/UMOJA | -0.302095, 36.172122 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998040 | 99.9 | 1998040 | 2000000 | 1960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9240 | ECD classes completion Lanet umoja | ECD classes completion Lanet umoja | To implement ecd classes completion lanet umoja for access to quality education and training | ECD classes completion Lanet umoja completed | 4130299 | N/A | BAHATI | LANET/UMOJA | -0.269849, 36.163805 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/2016 | 999664.8 | 999664.8 | 999664.8 | Equitable | Equitable | 999664.8 | 0 | 999665 | 100 | 999665 | 999665 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes.
9241 | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | To implement kamoronyo primary ecdes - design and construction of 2no. ecdes classrooms at kamoronyo primary ecdes for access to quality education and training | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs completed | 4130299 | N/A | BAHATI | LANET/UMOJA | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1695002 | 339 | 1695002 | 500000 | -1195002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9242 | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | To implement ndege ndimu polytechnic - design and construction of of ndege ndimu polytechnic for access to quality education and training | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic completed | 4130299 | N/A | BAHATI | LANET/UMOJA | -0.299253, 36.17216 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 3163654 | 57.5 | 3163654 | 32853 | 2336346 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9243 | ECDs Kapyemit | ECDs Kapyemit | To implement ecds kapyemit for access to quality education and training | ECDs Kapyemit completed | 4130299 | N/A | NJORO | LARE | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199755 | 1199755 | 1199755 | Equitable | N/A | 1199755 | 0 | 1127 | 0.1 | 1127 | 1127 | 1198628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9244 | equipping of ECDE classroom at nguriga primary school | equipping of ECDE classroom at nguriga primary school | To equip ECDE classroom at nguriga primary school with necessary facilities and equipment | ECDE classroom at nguriga primary school equipped | 4130299 | N/A | NJORO | LARE | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 400000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
9245 | Mwenyere ECD | Mwenyere ECD | To implement mwenyere ecd for access to quality education and training | Mwenyere ECD completed | 4130299 | N/A | NJORO | LARE | -0.528065, 36.044693 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198372 | 99.9 | 1198372 | 1200000 | 1628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9246 | Renovation of 2 ECD classrooms and installation of electricity at Mugumo Primary | Renovation of 2 ECD classrooms and installation of electricity at Mugumo Primary | To rehabilitate 2 ECD classrooms and installation of electricity at Mugumo Primary to restore functionality | 2 ECD classrooms and installation of electricity at Mugumo Primary rehabilitated | 4130299 | N/A | NJORO | LARE | -0.446409 36.00843 2071.900146484375 12 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1199999 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
9247 | Renovation of 2 ECD classrooms and purchase of water tank for Naishi Game Primary | Renovation of 2 ECD classrooms and purchase of water tank for Naishi Game Primary | To rehabilitate 2 ECD classrooms and purchase of water tank for Naishi Game Primary to restore functionality | 2 ECD classrooms and purchase of water tank for Naishi Game Primary rehabilitated | 4130299 | N/A | NJORO | LARE | -0.446409 36.00843 2071.900146484375 12 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1199999 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
9248 | Build Classes & Prov. Moi ECD | Build Classes & Prov. Moi ECD | To implement build classes & prov. moi ecd for access to quality education and training | Build Classes & Prov. Moi ECD completed | 4130299 | N/A | NAKURU WEST | LONDON | -0.277192, 36.067441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2773951 | 2773951 | 2773951 | Equitable | Equitable | 2773951 | 0 | 2773951 | 100 | 2773951 | 2773951 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9249 | Milimani With Teachers Tools | Milimani With Teachers Tools | To implement milimani with teachers tools for access to quality education and training | Milimani With Teachers Tools completed | 4130299 | N/A | NAKURU WEST | LONDON | -0.275947, 36.056465 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3558649 | 3558649 | 3558649 | Equitable | N/A | 3558649 | 0 | 2807500 | 78.9 | 2807500 | 0 | 751149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9250 | Lakeview ECD Classrooms Construction of 4 ECD classrooms | Lakeview ECD Classrooms Construction of 4 ECD classrooms | To implement lakeview ecd classrooms construction of 4 ecd classrooms for access to quality education and training | Lakeview ECD Classrooms Construction of 4 ECD classrooms completed | 4130299 | N/A | Naivasha | Lakeview | -0.734197, 36.435788 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 1800284 | 1800284 | Equitable | N/A | 1800284 | 0 | 3199716 | 177.7 | 3199716 | 1800284 | -1399432 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9251 | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | To construct perimeter wall, gate and toilet at Ndege Polytechnic | Perimeter wall, gate and toilet at Ndege Polytechnic constructed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.302095, 36.172122 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998040 | 99.9 | 1998040 | 2000000 | 1960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9252 | ECD classes completion Lanet umoja | ECD classes completion Lanet umoja | To implement ecd classes completion lanet umoja for access to quality education and training | ECD classes completion Lanet umoja completed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.269849, 36.163805 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/2016 | 999664.8 | 999664.8 | 999664.8 | Equitable | Equitable | 999664.8 | 0 | 999665 | 100 | 999665 | 999665 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes.
9253 | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | To implement kamoronyo primary ecdes - design and construction of 2no. ecdes classrooms at kamoronyo primary ecdes for access to quality education and training | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs completed | 4130299 | N/A | Bahati | Lanet/Umoja | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1695002 | 339 | 1695002 | 500000 | -1195002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9254 | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | To implement ndege ndimu polytechnic - design and construction of of ndege ndimu polytechnic for access to quality education and training | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic completed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.299253, 36.17216 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5500000 | 3196507 | 3196507 | Equitable | N/A | 3196507 | 0 | 3163654 | 99 | 3163654 | 32853 | 32853 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9255 | ECDs Kapyemit | ECDs Kapyemit | To implement ecds kapyemit for access to quality education and training | ECDs Kapyemit completed | 4130299 | N/A | Njoro | Lare | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199755 | 1199755 | 1199755 | Equitable | N/A | 1199755 | 0 | 1127 | 0.1 | 1127 | 1127 | 1198628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9256 | Mwenyere ECD | Mwenyere ECD | To implement mwenyere ecd for access to quality education and training | Mwenyere ECD completed | 4130299 | N/A | Njoro | Lare | -0.528065, 36.044693 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198372 | 99.9 | 1198372 | 1200000 | 1628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9257 | Build Classes & Prov. Moi ECD | Build Classes & Prov. Moi ECD | To implement build classes & prov. moi ecd for access to quality education and training | Build Classes & Prov. Moi ECD completed | 4130299 | N/A | Nakuru West | London | -0.277192, 36.067441 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2773951 | 2773951 | 2773951 | Equitable | Equitable | 2773951 | 0 | 2773951 | 100 | 2773951 | 2773951 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9258 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD constructed | 4130299 | N/A | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9259 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD constructed | 4130299 | N/A | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9260 | ECD, Namuncha primary school | ECD, Namuncha primary school | To implement ecd, namuncha primary school for access to quality education and training | ECD, Namuncha primary school completed | 4130299 | N/A | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9261 | Oiti ecd | Oiti ecd | To implement oiti ecd for access to quality education and training | Oiti ecd completed | 4130299 | N/A | NAIVASHA | MAAI MAHIU | -1.102478, 36.48795 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1195682 | 1195682 | 1195682 | Equitable | Equitable | 1195682 | 0 | 1195682 | 100 | 1195682 | 1195682 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9262 | Completion of Crater nursery school | Completion of Crater nursery school | To complete Crater nursery school | Crater nursery school completed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.83119 36.203515 0 156.89999389648438 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3894092 | 649 | 3894092 | 600000 | -3294092 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
9263 | Equipping with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs | Equipping with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs | To equip with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs with necessary facilities and equipment | With chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs equipped | 4130299 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999800 | 1999800 | 1999800 | Equitable | N/A | 1999800 | 0 | 1999800 | 100 | 1999800 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9264 | Maiella Township Nursery | Maiella Township Nursery | To implement maiella township nursery for access to quality education and training | Maiella Township Nursery completed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.901682 36.201828 2295.2 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance f the classroom needed.
9265 | Ndabibi polytechnic | Ndabibi polytechnic | To implement ndabibi polytechnic for access to quality education and training | Ndabibi polytechnic completed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1335596 | 1335596 | 1335596 | Equitable | N/A | 1335596 | 0 | 996500 | 74.6 | 996500 | 1335596 | 339096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
9266 | Nkampani nursery school | Nkampani nursery school | To implement nkampani nursery school for access to quality education and training | Nkampani nursery school completed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.920628 36.204578 2270.4 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
9267 | Construction of classrooms at Ndabibi and Kipkonyo Polytechnics | Construction of classrooms at Ndabibi and Kipkonyo Polytechnics | To construct classrooms at Ndabibi and Kipkonyo Polytechnics | Classrooms at Ndabibi and Kipkonyo Polytechnics constructed | 4130299 | N/A | NAIVASHA | MAIELLA | -0.804803 36.246244 0 22.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 497700 | 10 | 497700 | 5000000 | 4502300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
9268 | Construction of 2 ECD classrooms at Marula primary School | Construction of 2 ECD classrooms at Marula primary School | To construct 2 ECD classrooms at Marula primary School | 2 ECD classrooms at Marula primary School constructed | 4130299 | N/A | GILGIL | MALEWA WEST | -0.612613, 36.380458 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024/×5 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1197794 | 54.4 | 1197794 | 2200000 | 1002206 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9269 | Construction of ECD classroom at North Karate primary and 2 toilets | Construction of ECD classroom at North Karate primary and 2 toilets | To construct ECD classroom at North Karate primary and 2 toilets | ECD classroom at North Karate primary and 2 toilets constructed | 4130299 | N/A | GILGIL | MALEWA WEST | -0.684685 36.489092 0 2000 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1197794 | 79.9 | 1197794 | 302206 | 302206 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovations.
9270 | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | To construct and equip Tuiyobei ECD classrooms, toilets and water tank | Tuiyobei ECD classrooms, toilets and water tank constructed and equipped | 4130299 | N/A | MOLO | MARIASHONI | -0.349579, 35.801559 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1914000 | 95.7 | 1914000 | 2000000 | 86000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9271 | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | To construct 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank constructed | 4130299 | N/A | MOLO | MARIASHONI | -0.343994, 35.846228 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996707 | 99.8 | 1996707 | 1999952 | 3293 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9272 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE constructed | 4130299 | N/A | MOLO | MARIASHONI | -0.336003, 35.790239 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 269135 | 269135 | Equitable | N/A | 269135 | 0 | 269135 | 100 | 269135 | 381278 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9273 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE constructed | 4130299 | N/A | MOLO | MARIASHONI | -0.336003, 35.790239 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996708 | 99.8 | 1996708 | 381278 | 3292 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9274 | purchase of furniture, water tank and construction of toilets for Marioshoni ECDE | purchase of furniture, water tank and construction of toilets for Marioshoni ECDE | To procure furniture, water tank and construction of toilets for Marioshoni ECDE | Furniture, water tank and construction of toilets for Marioshoni ECDE procured | 4130299 | N/A | MOLO | MARIASHONI | -0.355511 35.814109 2664 6.25 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999757 | 100 | 999757 | 0 | 243 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: High populace school.
9275 | Constructon of ECD Classroom at Gacembe Primary | Constructon of ECD Classroom at Gacembe Primary | To implement constructon of ecd classroom at gacembe primary for access to quality education and training | Constructon of ECD Classroom at Gacembe Primary completed | 4130299 | N/A | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1643 | 0.1 | 1643 | 1643 | 1198357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9276 | Constructon of ECD Classroom at IKinu Primary | Constructon of ECD Classroom at IKinu Primary | To implement constructon of ecd classroom at ikinu primary for access to quality education and training | Constructon of ECD Classroom at IKinu Primary completed | 4130299 | N/A | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199920 | 100 | 1199920 | 1643 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9277 | Constructon of ECD Classroom at Kianjoya Primary | Constructon of ECD Classroom at Kianjoya Primary | To implement constructon of ecd classroom at kianjoya primary for access to quality education and training | Constructon of ECD Classroom at Kianjoya Primary completed | 4130299 | N/A | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198408 | 99.9 | 1198408 | 1643 | 1592 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9278 | Constructon of ECD Classroom at Makutano Primary | Constructon of ECD Classroom at Makutano Primary | To implement constructon of ecd classroom at makutano primary for access to quality education and training | Constructon of ECD Classroom at Makutano Primary completed | 4130299 | N/A | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198555 | 99.9 | 1198555 | 1643 | 1445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9279 | Constructon of ECD Classroom at Utalii Primary | Constructon of ECD Classroom at Utalii Primary | To implement constructon of ecd classroom at utalii primary for access to quality education and training | Constructon of ECD Classroom at Utalii Primary completed | 4130299 | N/A | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198407 | 99.9 | 1198407 | 1643 | 1593 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9280 | Mahiga ECD - design and Construction of 1 ECDE classroom | Mahiga ECD - design and Construction of 1 ECDE classroom | To implement mahiga ecd - design and construction of 1 ecde classroom for access to quality education and training | Mahiga ECD - design and Construction of 1 ECDE classroom completed | 4130299 | N/A | NJORO | MAU NAROK | -0.506468, 36.054437 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 19/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499490 | 100 | 1499490 | 1500000 | 510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9281 | Maji mingi ECD | Maji mingi ECD | To implement maji mingi ecd for access to quality education and training | Maji mingi ECD completed | 4130299 | N/A | NJORO | MAU NAROK | -0.624862 36.00766 2749.6 4.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: In bad condition.
9282 | Ngwataniro ECD | Ngwataniro ECD | To implement ngwataniro ecd for access to quality education and training | Ngwataniro ECD completed | 4130299 | N/A | NJORO | MAU NAROK | -1.2841, 36.8155 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2020/21 | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | Stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes.
9283 | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet | To implement chorwet primary ecde toilet construction - design and construction of chorwet primary ecde toilet for access to quality education and training | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet completed | 4130299 | N/A | NJORO | MAUCHE | -0.527215, 35.981072 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2015 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599970 | 100 | 599970 | 0 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know.
9284 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE constructed | 4130299 | N/A | NJORO | MAUCHE | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 70 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9285 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE constructed | 4130299 | N/A | NJORO | MAUCHE | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 567777 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9286 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE constructed | 4130299 | N/A | NJORO | MAUCHE | -0.49448 35.97722 2413 13.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 567777 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: No water tank & toilet for pupils & teachers & watering point needed.
9287 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE constructed | 4130299 | N/A | NJORO | MAUCHE | -0.527288 35.981027 2478.8999999999996 15.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 4221 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Good.
9288 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE constructed | 4130299 | N/A | NJORO | MAUCHE | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 70 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9289 | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | To implement koilonget ecde - design and construction of 1 no ecd classroom - koilonget ecde for access to quality education and training | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE completed | 4130299 | N/A | NJORO | MAUCHE | -0.481008 35.963225 2456.5 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 5542 | 0.5 | 5542 | 5542 | 1194458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9290 | Sigor ECDE | Sigor ECDE | To implement sigor ecde for access to quality education and training | Sigor ECDE completed | 4130299 | N/A | NJORO | MAUCHE | -0.547055 36.008958 2457 12.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: A fresh construction.
9291 | Construction of 1.No classroom at St Johns Primary ECD | Construction of 1.No classroom at St Johns Primary ECD | To construct 1.No classroom at St Johns Primary ECD | 1.No classroom at St Johns Primary ECD constructed | 4130299 | N/A | NAKURU EAST | MENENGAI | -0.266241, 36.100621 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499981 | 100 | 3499981 | 1700000 | 19 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Leskar enterprises limited.
9292 | Construction of 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | Construction of 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | To construct 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 1144900 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9293 | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | To construct 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399880 | 100 | 2399880 | 1144900 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9294 | Construction of 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | Construction of 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | To construct 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2399500.6 | 2399500.6 | 2399500.6 | Equitable | N/A | 2399500.6 | 0 | 2399500 | 100 | 2399500 | 1144900 | 0.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9295 | Kiamunyi High School 3 ECD | Kiamunyi High School 3 ECD | To implement kiamunyi high school 3 ecd for access to quality education and training | Kiamunyi High School 3 ECD completed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.2466 36.013657 2010.9 9.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1329170.8 | 1329170.8 | 1329170.8 | Equitable | N/A | 1329170.8 | 0 | 0 | 0 | 0 | 1329171 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9296 | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | To implement menengai polytechnic equipments - purchase of menengai polytechnic equipments and construction of the gate for access to quality education and training | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate completed | 4130299 | N/A | RONGAI | MENENGAI WEST | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998374 | 99.9 | 1998374 | 1626 | 1626 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9297 | Menengai polytechnic | Menengai polytechnic | To implement menengai polytechnic for access to quality education and training | Menengai polytechnic completed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.168667 36.000048 1898 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1987858.4 | 1987858.4 | 1987858.4 | Equitable | N/A | 1987858.4 | 0 | 1797768 | 90.4 | 1797768 | 1987858 | 190090.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
9298 | Olrongai polytechnic - Design and Construction of an administration block and equipping | Olrongai polytechnic - Design and Construction of an administration block and equipping | To implement olrongai polytechnic - design and construction of an administration block and equipping for access to quality education and training | Olrongai polytechnic - Design and Construction of an administration block and equipping completed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.168873, 36.000358 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2453665 | 98.1 | 2453665 | 46335 | 46335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9299 | Construction of 2 classrooms at Kichwa ECD and a water tank | Construction of 2 classrooms at Kichwa ECD and a water tank | To construct 2 classrooms at Kichwa ECD and a water tank | 2 classrooms at Kichwa ECD and a water tank constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.122357, 36.008043 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019/20 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399998 | 100 | 2399998 | 999844 | 2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s mburu.
9300 | construction of Toilet at Ol-Rongai Polytechnic | construction of Toilet at Ol-Rongai Polytechnic | To construct Toilet at Ol-Rongai Polytechnic | Toilet at Ol-Rongai Polytechnic constructed | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.168652, 36.000173 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999240 | 99.9 | 999240 | 1000000 | 760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9301 | fencing of Ol Rongai polytechnic | fencing of Ol Rongai polytechnic | To secure Ol Rongai polytechnic through fencing | Ol Rongai polytechnic fenced and secured | 4130299 | N/A | RONGAI | MENENGAI WEST | -0.168667 36.000048 1898 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797768 | 99.9 | 1797768 | 3000000 | 2232 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
9302 | Completion and equipping of Molo Youth Polytechnic | Completion and equipping of Molo Youth Polytechnic | To complete and equip Molo Youth Polytechnic | Molo Youth Polytechnic completed and equipped | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4123683 | 82.5 | 4123683 | 8800000 | 876317 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9303 | construction of Kapcholola ECD Centre & toilet | construction of Kapcholola ECD Centre & toilet | To construct Kapcholola ECD Centre & toilet | Kapcholola ECD Centre & toilet constructed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1195000 | 1195000 | 1195000 | Equitable | N/A | 1195000 | 0 | 19900008 | 1665.3 | 19900008 | 3566331 | -18705008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9304 | Construction of Kirandich ECD Centre | Construction of Kirandich ECD Centre | To construct Kirandich ECD Centre | Kirandich ECD Centre constructed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 19900008 | 1658.3 | 19900008 | 3566331 | -18700008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9305 | Construction of migaa ECD centre | Construction of migaa ECD centre | To construct migaa ECD centre | Migaa ECD centre constructed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 19900008 | 1658.3 | 19900008 | 3566331 | -18700008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9306 | Molo youth Polytechnic - Equiping of Youth Polytechnic | Molo youth Polytechnic - Equiping of Youth Polytechnic | To implement molo youth polytechnic - equiping of youth polytechnic for access to quality education and training | Molo youth Polytechnic - Equiping of Youth Polytechnic completed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9307 | Sachangwan ECD | Sachangwan ECD | To implement sachangwan ecd for access to quality education and training | Sachangwan ECD completed | 4130299 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9308 | Baraka Youth polytechnic | Baraka Youth polytechnic | To implement baraka youth polytechnic for access to quality education and training | Baraka Youth polytechnic completed | 4130299 | N/A | RONGAI | MOSOP | -0.213302 35.819547 1904.4000244140625 15.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1379950 | 1379950 | 1379950 | Equitable | N/A | 1379950 | 0 | 0 | 0 | 0 | 1379950 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9309 | Chepseon ecd - Renovations and toilets | Chepseon ecd - Renovations and toilets | To implement chepseon ecd - renovations and toilets for access to quality education and training | Chepseon ecd - Renovations and toilets completed | 4130299 | N/A | RONGAI | MOSOP | -0.265783 35.881283 2093.3 12.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 497999 | 35.6 | 497999 | 1400000 | 902001 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
9310 | construction and equipping of 1 Muthiga ECDE Classroom | construction and equipping of 1 Muthiga ECDE Classroom | To construct and equip 1 Muthiga ECDE Classroom | 1 Muthiga ECDE Classroom constructed and equipped | 4130299 | N/A | RONGAI | MOSOP | -0.279457 35.88394 2110.2 6.099999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1198000 | 85.6 | 1198000 | 1400000 | 202000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9311 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD constructed | 4130299 | N/A | RONGAI | MOSOP | -0.291287 35.98659 2132.2999999999997 16.799999237060547 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099576 | 100 | 2099576 | 464606 | 424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9312 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD constructed | 4130299 | N/A | RONGAI | MOSOP | -0.266003 35.881008 2093.4 16.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099576 | 100 | 2099576 | 464606 | 424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
9313 | Design and Construction of 3 No classrooms at Ogilgei polytechnic | Design and Construction of 3 No classrooms at Ogilgei polytechnic | To design and construct 3 No classrooms at Ogilgei polytechnic | 3 No classrooms at Ogilgei polytechnic designed and constructed | 4130299 | N/A | RONGAI | MOSOP | -0.211275 35.852425 1887.3999999999999 15.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 968873 | 968873 | Equitable | N/A | 968873 | 0 | 1499996 | 154.8 | 1499996 | 968873 | -531123 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Stalled.
9314 | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | To implement ngata primary ecd - design and construction of 1 no. classroom, pupils toilet and water point for access to quality education and training | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point completed | 4130299 | N/A | RONGAI | MOSOP | -0.24922 35.83006 2174.3999999999996 7 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2100000 | 464606 | 464606 | Equitable | Equitable | 464606 | 0 | 464606 | 100 | 464606 | 464606 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Chapakaz. Assessor remarks: Good work.
9315 | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic | To implement fencing, construction of a toilet and equipping of ogilgei polytechnic for access to quality education and training | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic completed | 4130299 | N/A | RONGAI | MOSOP | -0.28415, 35.966517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499996 | 100 | 1499996 | 968873 | 4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated.
9316 | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | To construct 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD constructed | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9317 | Construction of Toilets and Fencing of Ngeteti ECD | Construction of Toilets and Fencing of Ngeteti ECD | To construct Toilets and Fencing of Ngeteti ECD | Toilets and Fencing of Ngeteti ECD constructed | 4130299 | N/A | GILGIL | MURINDAT | -0.418758, 36.372043 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999456 | 99.9 | 999456 | 1200000 | 544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Murmur sobs and fabricators.
9318 | Equipping of Mbegi polytechnic | Equipping of Mbegi polytechnic | To equip Mbegi polytechnic with necessary facilities and equipment | Mbegi polytechnic equipped | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2830 | 0.3 | 2830 | 2830 | 997170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9319 | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms | To implement nganoini ecde classroom - design and construction of nganoini 2 classrooms for access to quality education and training | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms completed | 4130299 | N/A | GILGIL | MURINDAT | -0.410535, 36.358684 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1194649 | 59.7 | 1194649 | 805351 | 805351 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partly. Viable: Yes. Contractor: Murmur sobs and fabricators.
9320 | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | To implement wanguhu ecde classroom - design and construction of wanguhu ecde 1 classroom for access to quality education and training | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom completed | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1210000 | 80.7 | 1210000 | 290000 | 290000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9321 | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | To construct 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD constructed | 4130299 | N/A | GILGIL | MURINDAT | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 112 | 0 | 112 | 112 | 2399888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9322 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD constructed | 4130299 | N/A | Naivasha | Maai Mahiu | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9323 | ECD, Namuncha primary school | ECD, Namuncha primary school | To implement ecd, namuncha primary school for access to quality education and training | ECD, Namuncha primary school completed | 4130299 | N/A | Naivasha | Maai Mahiu | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9324 | Oiti ecd | Oiti ecd | To implement oiti ecd for access to quality education and training | Oiti ecd completed | 4130299 | N/A | Naivasha | Maai Mahiu | -1.102478, 36.48795 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1195682 | 1195682 | 1195682 | Equitable | Equitable | 1195682 | 0 | 1195682 | 100 | 1195682 | 1195682 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9325 | Completion of Crater nursery school | Completion of Crater nursery school | To complete Crater nursery school | Crater nursery school completed | 4130299 | N/A | Naivasha | Maiella | -0.83119 36.203515 0 156.89999389648438 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3894092 | 649 | 3894092 | 600000 | -3294092 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
9326 | construction of Toilets at Kipkonyo polytechnics | construction of Toilets at Kipkonyo polytechnics | To construct Toilets at Kipkonyo polytechnics | Toilets at Kipkonyo polytechnics constructed | 4130299 | N/A | Naivasha | Maiella | -0.781462, 36.223325 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497700 | 99.5 | 497700 | 500000 | 2300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Building Construction.
9327 | equipping of Kipkonyo Polytechnics | equipping of Kipkonyo Polytechnics | To equip Kipkonyo Polytechnics with necessary facilities and equipment | Kipkonyo Polytechnics equipped | 4130299 | N/A | Naivasha | Maiella | -0.782163, 36.223265 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2799119 | 279.9 | 2799119 | 1000000 | -1799119 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9328 | equipping of Ndabibi Polytechnics | equipping of Ndabibi Polytechnics | To equip Ndabibi Polytechnics with necessary facilities and equipment | Ndabibi Polytechnics equipped | 4130299 | N/A | Naivasha | Maiella | -0.782163, 36.223265 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996500 | 99.7 | 996500 | 1000000 | 3500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9329 | Maiella Township Nursery | Maiella Township Nursery | To implement maiella township nursery for access to quality education and training | Maiella Township Nursery completed | 4130299 | N/A | Naivasha | Maiella | -0.901682 36.201828 2295.2 12.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance f the classroom needed.
9330 | Ndabibi polytechnic | Ndabibi polytechnic | To implement ndabibi polytechnic for access to quality education and training | Ndabibi polytechnic completed | 4130299 | N/A | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1335596 | 1335596 | 1335596 | Equitable | N/A | 1335596 | 0 | 996500 | 74.6 | 996500 | 1335596 | 339096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
9331 | Nkampani nursery school | Nkampani nursery school | To implement nkampani nursery school for access to quality education and training | Nkampani nursery school completed | 4130299 | N/A | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
9332 | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | To construct and equip Tuiyobei ECD classrooms, toilets and water tank | Tuiyobei ECD classrooms, toilets and water tank constructed and equipped | 4130299 | N/A | Molo | Mariashoni | -0.349579, 35.801559 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1914000 | 95.7 | 1914000 | 2000000 | 86000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9333 | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | To construct 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank constructed | 4130299 | N/A | Molo | Mariashoni | -0.343994, 35.846228 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996707 | 99.8 | 1996707 | 1999952 | 3293 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9334 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE constructed | 4130299 | N/A | Molo | Mariashoni | -0.336003, 35.790239 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996708 | 99.8 | 1996708 | 381278 | 3292 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9335 | Constructon of ECD Classroom at Gacembe Primary | Constructon of ECD Classroom at Gacembe Primary | To implement constructon of ecd classroom at gacembe primary for access to quality education and training | Constructon of ECD Classroom at Gacembe Primary completed | 4130299 | N/A | Njoro | Mau Narok | -0.674452, 35.969013 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 426551 | 426551 | Equitable | N/A | 426551 | 0 | 1643 | 0.4 | 1643 | 1643 | 424908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9336 | Maji mingi ECD | Maji mingi ECD | To implement maji mingi ecd for access to quality education and training | Maji mingi ECD completed | 4130299 | N/A | Njoro | Mau Narok | -0.624862 36.00766 2749.6 4.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: In bad condition.
9337 | Ngwataniro ECD | Ngwataniro ECD | To implement ngwataniro ecd for access to quality education and training | Ngwataniro ECD completed | 4130299 | N/A | Njoro | Mau Narok | -1.2841, 36.8155 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2020/21 | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | Stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes.
9338 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 70 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9339 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.49448 35.97722 2413 13.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 567776.8 | 567776.8 | Equitable | N/A | 567776.8 | 0 | 70 | 0 | 70 | 567777 | 567706.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: No water tank & toilet for pupils & teachers & watering point needed.
9340 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.527288 35.981027 2478.8999999999996 15.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 4221 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Good.
9341 | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | To implement koilonget ecde - design and construction of 1 no ecd classroom - koilonget ecde for access to quality education and training | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE completed | 4130299 | N/A | Njoro | Mauche | -0.481008 35.963225 2456.5 10 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 5542 | 0.5 | 5542 | 5542 | 1194458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9342 | Sigor ECDE | Sigor ECDE | To implement sigor ecde for access to quality education and training | Sigor ECDE completed | 4130299 | N/A | Njoro | Mauche | -0.547055 36.008958 2457 12.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: A fresh construction.
9343 | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | To construct 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD constructed | 4130299 | N/A | Rongai | Menengai West | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399880 | 100 | 2399880 | 1144900 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9344 | equipping of ECDE ( purchase of desks) | equipping of ECDE ( purchase of desks) | To equip ECDE ( purchase of desks) with necessary facilities and equipment | ECDE ( purchase of desks) equipped | 4130299 | N/A | Rongai | Menengai West | -0.213115, 35.952208 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017/18 | 1329170.8 | 3000000.2 | 3000000.2 | Equitable | N/A | 3000000.2 | 0 | 0 | 0 | 0 | 3000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9345 | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | To implement menengai polytechnic equipments - purchase of menengai polytechnic equipments and construction of the gate for access to quality education and training | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate completed | 4130299 | N/A | Rongai | Menengai West | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 1626 | 1626 | Equitable | N/A | 1626 | 0 | 1998374 | 122901.2 | 1998374 | 1626 | -1996748 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9346 | Olrongai polytechnic - Design and Construction of an administration block and equipping | Olrongai polytechnic - Design and Construction of an administration block and equipping | To implement olrongai polytechnic - design and construction of an administration block and equipping for access to quality education and training | Olrongai polytechnic - Design and Construction of an administration block and equipping completed | 4130299 | N/A | Rongai | Menengai West | -0.168873, 36.000358 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2453665 | 98.1 | 2453665 | 46335 | 46335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9347 | construction of Toilet at Ol-Rongai Polytechnic | construction of Toilet at Ol-Rongai Polytechnic | To construct Toilet at Ol-Rongai Polytechnic | Toilet at Ol-Rongai Polytechnic constructed | 4130299 | N/A | Rongai | Menengai West | -0.168652, 36.000173 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999240 | 99.9 | 999240 | 1000000 | 760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9348 | construction of Kapcholola ECD Centre & toilet | construction of Kapcholola ECD Centre & toilet | To construct Kapcholola ECD Centre & toilet | Kapcholola ECD Centre & toilet constructed | 4130299 | N/A | Molo | Molo Central | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1195000 | 1195000 | 1195000 | Equitable | N/A | 1195000 | 0 | 19900008 | 1665.3 | 19900008 | 3566331 | -18705008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9349 | construction of modern toilets, septic tank, completion of administration block at Molo polytechnic | construction of modern toilets, septic tank, completion of administration block at Molo polytechnic | To construct modern toilets, septic tank, completion of administration block at Molo polytechnic | Modern toilets, septic tank, completion of administration block at Molo polytechnic constructed | 4130299 | N/A | Molo | Molo Central | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5318447.4 | 5318447.4 | 5318447.4 | Equitable | N/A | 5318447.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9350 | Baraka Youth polytechnic | Baraka Youth polytechnic | To implement baraka youth polytechnic for access to quality education and training | Baraka Youth polytechnic completed | 4130299 | N/A | Rongai | Mosop | -0.213302 35.819547 1904.4000244140625 15.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1379950 | 1379950 | 1379950 | Equitable | N/A | 1379950 | 0 | 0 | 0 | 0 | 1379950 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9351 | Chepseon ecd - Renovations and toilets | Chepseon ecd - Renovations and toilets | To implement chepseon ecd - renovations and toilets for access to quality education and training | Chepseon ecd - Renovations and toilets completed | 4130299 | N/A | Rongai | Mosop | -0.265783 35.881283 2093.3 12.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 497999 | 35.6 | 497999 | 1400000 | 902001 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
9352 | construction and equipping of 1 Muthiga ECDE Classroom | construction and equipping of 1 Muthiga ECDE Classroom | To construct and equip 1 Muthiga ECDE Classroom | 1 Muthiga ECDE Classroom constructed and equipped | 4130299 | N/A | Rongai | Mosop | -0.279457 35.88394 2110.2 6.099999904632568 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1198000 | 85.6 | 1198000 | 1400000 | 202000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9353 | Design and Construction of 3 No classrooms at Ogilgei polytechnic | Design and Construction of 3 No classrooms at Ogilgei polytechnic | To design and construct 3 No classrooms at Ogilgei polytechnic | 3 No classrooms at Ogilgei polytechnic designed and constructed | 4130299 | N/A | Rongai | Mosop | -0.211275 35.852425 1887.3999999999999 15.899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 968873 | 968873 | Equitable | N/A | 968873 | 0 | 1499996 | 154.8 | 1499996 | 968873 | -531123 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Stalled.
9354 | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | To implement ngata primary ecd - design and construction of 1 no. classroom, pupils toilet and water point for access to quality education and training | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point completed | 4130299 | N/A | Rongai | Mosop | -0.24922 35.83006 2174.3999999999996 7 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2100000 | 464606 | 464606 | Equitable | Equitable | 464606 | 0 | 464606 | 100 | 464606 | 464606 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Chapakaz. Assessor remarks: Good work.
9355 | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | To construct 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD constructed | 4130299 | N/A | Gilgil | Murindat | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9356 | Equipping of Mbegi polytechnic | Equipping of Mbegi polytechnic | To equip Mbegi polytechnic with necessary facilities and equipment | Mbegi polytechnic equipped | 4130299 | N/A | Gilgil | Murindat | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2830 | 0.3 | 2830 | 2830 | 997170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9357 | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | To implement wanguhu ecde classroom - design and construction of wanguhu ecde 1 classroom for access to quality education and training | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom completed | 4130299 | N/A | Gilgil | Murindat | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1210000 | 80.7 | 1210000 | 290000 | 290000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9358 | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | To construct 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD constructed | 4130299 | N/A | Gilgil | Murindat | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 112 | 0 | 112 | 112 | 2399888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9359 | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | To construct 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD constructed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.841832, 36.557322 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199939 | 100 | 1199939 | 0 | 61 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9360 | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | To construct 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD constructed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.841832, 36.557322 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199766 | 100 | 1199766 | 0 | 234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9361 | Construction of Mwega Polytechnic | Construction of Mwega Polytechnic | To construct Mwega Polytechnic | Mwega Polytechnic constructed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.790247, 36.546362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 936 | 0 | 936 | 936 | 2999064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: No.
9362 | construction and equipping of Mwega polytechnic | construction and equipping of Mwega polytechnic | To construct and equip Mwega polytechnic | Mwega polytechnic constructed and equipped | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.826406 36.536507 2471.60009765625 5.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999064 | 100 | 2999064 | 3000000 | 936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
9363 | Construction of ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | Construction of ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | To construct ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs constructed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.868073 36.520145 2307.2000000000003 4.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 4800000 | 3600022 | 3600022 | Equitable | N/A | 3600022 | 0 | 3600022 | 100 | 3600022 | 359377 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Ecd was constructed but later coneveeted to be a dispensary which non fuctional.
9364 | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | To implement naivasha east ward ecds - design and construction of 2 no ecd classroom, at nyakairu and mweega primary for access to quality education and training | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary completed | 4130299 | N/A | NAIVASHA | NAIVASHA EAST | -0.782198, 36.533643 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | Not done | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 4260 | 0.2 | 4260 | 4260 | 2395740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9365 | Construction of 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | Construction of 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | To construct 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools constructed | 4130299 | N/A | NAKURU EAST | NAKURU EAST | -0.301508, 36.127579 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/2017 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5998775 | 100 | 5998775 | 284968 | 1225 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes constrution Dakuki comstruction,Durhas construction.
9366 | Construction Of ECDEs:-Tagitech Primary School | Construction Of ECDEs:-Tagitech Primary School | To construct ECDEs:-Tagitech Primary School | ECDEs:-Tagitech Primary School constructed | 4130299 | N/A | NJORO | NESSUIT | -0.433359 35.91906 2583.1005859375 4.107999801635742 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1194730 | 1194730 | 1194730 | Equitable | N/A | 1194730 | 0 | 1194730 | 100 | 1194730 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs repairs and repainting. Furniture for pupils is also required. Due to the huge population of pupils in ECDEs ,they were relocated to use temporary classrooms..
9367 | Nginye ECD | Nginye ECD | To implement nginye ecd for access to quality education and training | Nginye ECD completed | 4130299 | N/A | NJORO | NESSUIT | -0.401883 35.907934 2429.297805547889 4.23799991607666 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
9368 | Tiritagoi ECD - Construction of 1 classroom | Tiritagoi ECD - Construction of 1 classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction of 1 classroom completed | 4130299 | N/A | NJORO | NESSUIT | -0.417516 35.906162 2476.5755676023055 30 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
9369 | design and construction of Korovio ECDE classroom | design and construction of Korovio ECDE classroom | To design and construct Korovio ECDE classroom | Korovio ECDE classroom designed and constructed | 4130299 | N/A | NJORO | NESSUIT | -0.410761 35.899338 2463.547607421875 10.36299991607666 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
9370 | design and construction of Masaita ECDE classroom and Toilets | design and construction of Masaita ECDE classroom and Toilets | To design and construct Masaita ECDE classroom and Toilets | Masaita ECDE classroom and Toilets designed and constructed | 4130299 | N/A | NJORO | NESSUIT | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
9371 | design and construction of Missipei ECDE classroom and Toilets | design and construction of Missipei ECDE classroom and Toilets | To design and construct Missipei ECDE classroom and Toilets | Missipei ECDE classroom and Toilets designed and constructed | 4130299 | N/A | NJORO | NESSUIT | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
9372 | ECD Tengecha | ECD Tengecha | To implement ecd tengecha for access to quality education and training | ECD Tengecha completed | 4130299 | N/A | NJORO | NJORO | -0.369383 35.901138 1512.2 77.69999694824219 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799960.4 | 1799960.4 | 1799960.4 | Equitable | N/A | 1799960.4 | 0 | 0 | 0 | 0 | 1799960 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: working well.
9373 | Njokerio ECD - Construction of Toilet and equiping | Njokerio ECD - Construction of Toilet and equiping | To implement njokerio ecd - construction of toilet and equiping for access to quality education and training | Njokerio ECD - Construction of Toilet and equiping completed | 4130299 | N/A | NJORO | NJORO | -0.384924, 35.935535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1800000 | 489154 | 489154 | Equitable | N/A | 489154 | 0 | 110660 | 22.6 | 110660 | 110660 | 378494 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
9374 | purchase of land for construction of sosiot ECDE | purchase of land for construction of sosiot ECDE | To acquire land for construction of sosiot ECDE | Land for construction of sosiot ECDE acquired | 4130299 | N/A | NJORO | NJORO | -0.32681 35.940695 2151.900146484375 5.441999912261963 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2492710 | 2492710 | 2492710 | Equitable | N/A | 2492710 | 0 | 1197000 | 48 | 1197000 | 2492710 | 1295710 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Samues merchants. Assessor remarks: In good state.
9375 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD constructed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.395862, 35.616267 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2023-2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199970 | 100 | 1199970 | 800002 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9376 | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | To construct Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic constructed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.38946, 35.568755 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
9377 | Langwenda youth polytechnic | Langwenda youth polytechnic | To implement langwenda youth polytechnic for access to quality education and training | Langwenda youth polytechnic completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 800200 | 800200 | Equitable | N/A | 800200 | 0 | 689140 | 86.1 | 689140 | 800200 | 111060 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9378 | Mawingu youth polytechnic | Mawingu youth polytechnic | To implement mawingu youth polytechnic for access to quality education and training | Mawingu youth polytechnic completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 800200 | 800200 | Equitable | N/A | 800200 | 0 | 689140 | 86.1 | 689140 | 800200 | 111060 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9379 | Mworoto youth polytechnic | Mworoto youth polytechnic | To implement mworoto youth polytechnic for access to quality education and training | Mworoto youth polytechnic completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 1374262 | 1374262 | Equitable | N/A | 1374262 | 0 | 689140 | 50.1 | 689140 | 1374262 | 685122 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9380 | Tachasis ECD | Tachasis ECD | To implement tachasis ecd for access to quality education and training | Tachasis ECD completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.364898, 35.697293 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015-2016 | 2170000 | 2170000 | 2170000 | Equitable | Equitable | 2170000 | 0 | 2172100 | 100.1 | 2172100 | 2172100 | -2100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S NEO TECHNICS LIMITED.
9381 | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | To implement nyota ward ecds - design and construction of 1.no ecd classrooms, teachers toilet, pupils toilet and watering point at chemorut, mawingu, masasita for access to quality education and training | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita completed | 4130299 | N/A | KURESOI NORTH | NYOTA | -0.3756, 35.726818 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018-2019 | 4800000 | 2000001 | 2000001 | Equitable | N/A | 2000001 | 0 | 1199999 | 60 | 1199999 | 800002 | 800002 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S WESJOY GENERAL SUPPLIES..
9382 | Construction of Kinungi Primary school ECDE | Construction of Kinungi Primary school ECDE | To construct Kinungi Primary school ECDE | Kinungi Primary school ECDE constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.807496, 36.52903 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018-19 | 999352 | 0 | 999352 | Equitable | N/A | 999352 | 0 | 999352 | 0 | 999352 | 999352 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9383 | Construction of Mwega Polytechnic | Construction of Mwega Polytechnic | To construct Mwega Polytechnic | Mwega Polytechnic constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.790247, 36.546362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 936 | 0 | 936 | 936 | 2999064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: No.
9384 | construction and equipping of Mwega polytechnic | construction and equipping of Mwega polytechnic | To construct and equip Mwega polytechnic | Mwega polytechnic constructed and equipped | 4130299 | N/A | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999064 | 100 | 2999064 | 3000000 | 936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
9385 | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | To implement naivasha east ward ecds - design and construction of 2 no ecd classroom, at nyakairu and mweega primary for access to quality education and training | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary completed | 4130299 | N/A | Naivasha | Naivasha East | -0.782198, 36.533643 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | Not done | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 4260 | 0.2 | 4260 | 4260 | 2395740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9386 | Nginye ECD | Nginye ECD | To implement nginye ecd for access to quality education and training | Nginye ECD completed | 4130299 | N/A | Njoro | Nessuit | -0.401883 35.907934 2429.297805547889 4.23799991607666 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
9387 | Tiritagoi ECD - Construction of 1 classroom | Tiritagoi ECD - Construction of 1 classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction of 1 classroom completed | 4130299 | N/A | Njoro | Nessuit | -0.417516 35.906162 2476.5755676023055 30 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
9388 | design and construction of Korovio ECDE classroom | design and construction of Korovio ECDE classroom | To design and construct Korovio ECDE classroom | Korovio ECDE classroom designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.410761 35.899338 2463.547607421875 10.36299991607666 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
9389 | design and construction of Masaita ECDE classroom and Toilets | design and construction of Masaita ECDE classroom and Toilets | To design and construct Masaita ECDE classroom and Toilets | Masaita ECDE classroom and Toilets designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
9390 | design and construction of Missipei ECDE classroom and Toilets | design and construction of Missipei ECDE classroom and Toilets | To design and construct Missipei ECDE classroom and Toilets | Missipei ECDE classroom and Toilets designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
9391 | ECD Tengecha | ECD Tengecha | To implement ecd tengecha for access to quality education and training | ECD Tengecha completed | 4130299 | N/A | Njoro | Njoro | -0.369383 35.901138 1512.2 77.69999694824219 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799960.4 | 1799960.4 | 1799960.4 | Equitable | N/A | 1799960.4 | 0 | 0 | 0 | 0 | 1799960 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: working well.
9392 | Njokerio ECD - Construction of Toilet and equiping | Njokerio ECD - Construction of Toilet and equiping | To implement njokerio ecd - construction of toilet and equiping for access to quality education and training | Njokerio ECD - Construction of Toilet and equiping completed | 4130299 | N/A | Njoro | Njoro | -0.384924, 35.935535 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1800000 | 489154 | 489154 | Equitable | N/A | 489154 | 0 | 110660 | 22.6 | 110660 | 110660 | 378494 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
9393 | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | To construct Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic constructed | 4130299 | N/A | Kuresoi North | Nyota | -0.38946, 35.568755 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
9394 | Langwenda youth polytechnic | Langwenda youth polytechnic | To implement langwenda youth polytechnic for access to quality education and training | Langwenda youth polytechnic completed | 4130299 | N/A | Kuresoi North | Nyota | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 800200 | 800200 | Equitable | N/A | 800200 | 0 | 689140 | 86.1 | 689140 | 800200 | 111060 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9395 | Mawingu youth polytechnic | Mawingu youth polytechnic | To implement mawingu youth polytechnic for access to quality education and training | Mawingu youth polytechnic completed | 4130299 | N/A | Kuresoi North | Nyota | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 800200 | 800200 | Equitable | N/A | 800200 | 0 | 689140 | 86.1 | 689140 | 800200 | 111060 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9396 | Mworoto youth polytechnic | Mworoto youth polytechnic | To implement mworoto youth polytechnic for access to quality education and training | Mworoto youth polytechnic completed | 4130299 | N/A | Kuresoi North | Nyota | -0.30101, 35.590975 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 1374262 | 1374262 | Equitable | N/A | 1374262 | 0 | 689140 | 50.1 | 689140 | 1374262 | 685122 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
9397 | Tachasis ECD | Tachasis ECD | To implement tachasis ecd for access to quality education and training | Tachasis ECD completed | 4130299 | N/A | Kuresoi North | Nyota | -0.364898, 35.697293 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015-2016 | 2170000 | 2172100 | 2172100 | Equitable | Equitable | 2172100 | 0 | 2172100 | 100 | 2172100 | 2172100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S NEO TECHNICS LIMITED.
9398 | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | To implement nyota ward ecds - design and construction of 1.no ecd classrooms, teachers toilet, pupils toilet and watering point at chemorut, mawingu, masasita for access to quality education and training | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita completed | 4130299 | N/A | Kuresoi North | Nyota | -0.3756, 35.726818 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018-2019 | 4800000 | 2000001 | 2000001 | Equitable | N/A | 2000001 | 0 | 1199999 | 60 | 1199999 | 800002 | 800002 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S WESJOY GENERAL SUPPLIES..
9399 | Mvuke ecd | Mvuke ecd | To implement mvuke ecd for access to quality education and training | Mvuke ecd completed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197887.77 | 1197887.77 | Equitable | N/A | 1197887.77 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46127.77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
9400 | Narasha ECD | Narasha ECD | To implement narasha ecd for access to quality education and training | Narasha ECD completed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.917012, 36.266132 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1195717 | 1195717 | 1195717 | Equitable | N/A | 1195717 | 0 | 0 | 0 | 0 | 1195717 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: No since the class room is not operational because of clarks.
9401 | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | To implement olkaria ward ecde classroom refurbishments - refurbishments of olkaria ecdes at narasha, mvuke, oserian, maua, sher primary for access to quality education and training | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary completed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.836891 36.366302 1881.9000244140625 12.005999565124512 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 192163 | 9.6 | 192163 | 192163 | 1807837 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No not done. Assessor remarks: At sher moi not done.
9402 | Olkaria ward | Olkaria ward | To implement olkaria ward for access to quality education and training | Olkaria ward completed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.832364 36.337064 1936.300048828125 6.109000205993652 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1296000 | 1296000 | 1296000 | Equitable | N/A | 1296000 | 0 | 0 | 0 | 0 | 1296000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The place needs more drainages.
9403 | Purchase of sport equipment for youths (Youth empowerment programme) | Purchase of sport equipment for youths (Youth empowerment programme) | To procure sport equipment for youths (Youth empowerment programme) | Sport equipment for youths (Youth empowerment programme) procured | 4130299 | N/A | NAIVASHA | OLKARIA | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999700 | 1999700 | 1999700 | Equitable | N/A | 1999700 | 0 | 1999700 | 100 | 1999700 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
9404 | Sher Moi ECD | Sher Moi ECD | To implement sher moi ecd for access to quality education and training | Sher Moi ECD completed | 4130299 | N/A | NAIVASHA | OLKARIA | -0.835686, 36.366152 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1136734 | 1136734 | 1136734 | Equitable | N/A | 1136734 | 0 | 0 | 0 | 0 | 1136734 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: It was not good.
9405 | equipping of ECDE centres | equipping of ECDE centres | To equip ECDE centres with necessary facilities and equipment | ECDE centres equipped | 4130299 | N/A | NAIVASHA | OLKARIA | 0.833976, 36.342019 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2410640 | 80.4 | 2410640 | 0 | 589360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9406 | Construction of olemayana Kubwa ECDE class, toilet blocks and equipping | Construction of olemayana Kubwa ECDE class, toilet blocks and equipping | To construct olemayana Kubwa ECDE class, toilet blocks and equipping | Olemayana Kubwa ECDE class, toilet blocks and equipping constructed | 4130299 | N/A | Naivasha | Olkaria | -0.914466, 36.304362 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195717 | 2491717 | 2491717 | Equitable | N/A | 2491717 | 0 | 2206597 | 88.6 | 2206597 | 285120 | 285120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9407 | Mvuke ecd | Mvuke ecd | To implement mvuke ecd for access to quality education and training | Mvuke ecd completed | 4130299 | N/A | Naivasha | Olkaria | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197887.77 | 1197887.77 | Equitable | N/A | 1197887.77 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46127.77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
9408 | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | To implement olkaria ward ecde classroom refurbishments - refurbishments of olkaria ecdes at narasha, mvuke, oserian, maua, sher primary for access to quality education and training | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary completed | 4130299 | N/A | Naivasha | Olkaria | -0.836891 36.366302 1881.9000244140625 12.005999565124512 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 192162.8 | 192162.8 | Equitable | N/A | 192162.8 | 0 | 192163 | 100 | 192163 | 192163 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No not done. Assessor remarks: At sher moi not done.
9409 | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | To design and construct administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Administration block, polytechnic, and equipping of classrooms at Rhonda resource centre designed and constructed | 4130299 | N/A | NAKURU WEST | RHONDA | -0.31321, 36.069056 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 16/17 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 9139 | 0.1 | 9139 | 9139 | 6990861 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers General Supplies and Construction.
9410 | Mwariki ECD - Construction of Administration Block and Equiping | Mwariki ECD - Construction of Administration Block and Equiping | To implement mwariki ecd - construction of administration block and equiping for access to quality education and training | Mwariki ECD - Construction of Administration Block and Equiping completed | 4130299 | N/A | NAKURU WEST | RHONDA | -0.316418, 36.06582 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 17/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4978558 | 99.6 | 4978558 | 1200000 | 21442 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Arlington company limited.
9411 | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | To construct an ECD classroom, toilet and tank at Mwariki Primary ECD | An ECD classroom, toilet and tank at Mwariki Primary ECD constructed | 4130299 | N/A | NAKURU WEST | RHONDA | -0.752322, 36.527363 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996330 | 99.8 | 1996330 | 2000000 | 3670 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.
9412 | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | To design and construct administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Administration block, polytechnic, and equipping of classrooms at Rhonda resource centre designed and constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.31321, 36.069056 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 16/17 | 7000000 | 9138.6 | 9138.6 | Equitable | N/A | 9138.6 | 0 | 9139 | 100 | 9139 | 9139 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers General Supplies and Construction.
9413 | completion of Mwariki vocational training | completion of Mwariki vocational training | To complete Mwariki vocational training | Mwariki vocational training completed | 4130299 | N/A | Nakuru West | Rhonda | -0.314109, 36.067322 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 23/24 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 2100000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9414 | construction of additional classroom and toilets at Hadassa vocational training | construction of additional classroom and toilets at Hadassa vocational training | To construct additional classroom and toilets at Hadassa vocational training | Additional classroom and toilets at Hadassa vocational training constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.313815, 36.068027 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 6988412 | 179.2 | 6988412 | 3900000 | -3088412 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
9415 | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | To construct an ECD classroom, toilet and tank at Mwariki Primary ECD | An ECD classroom, toilet and tank at Mwariki Primary ECD constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.752322, 36.527363 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996330 | 99.8 | 1996330 | 2000000 | 3670 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.
9416 | Construction of a PWD classroom at Koinange | Construction of a PWD classroom at Koinange | To construct a PWD classroom at Koinange | A PWD classroom at Koinange constructed | 4130299 | N/A | NAKURU WEST | SHABAB | -0.294043, 36.054678 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498895 | 100 | 2498895 | 746875 | 1105 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Partially.
9417 | Construction of an ICT Resource Centre in Shabab | Construction of an ICT Resource Centre in Shabab | To construct an ICT Resource Centre in Shabab | An ICT Resource Centre in Shabab constructed | 4130299 | N/A | NAKURU WEST | SHABAB | -0.294834, 36.058927 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499850 | 100 | 3499850 | 0 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9418 | Baringo ECD, | Baringo ECD, | To implement baringo ecd, for access to quality education and training | Baringo ECD, completed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.289637 35.642573 2687.6 9.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199442 | 480625 | 480625 | Equitable | N/A | 480625 | 0 | 407000 | 84.7 | 407000 | 73625 | 73625 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and in use, however the school needs another classroom to accommodate pp1 and pp2. The roof needs repair as its leaking, blackboard needs repainting, it also electricity, gutters and tank for water collection needed, they also require a pit latrine, seats and tables needs maintenance.
9419 | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | To complete Upendo ECD, Kadenye ECD, and Ngenia ECD | Upendo ECD, Kadenye ECD, and Ngenia ECD completed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.289225 35.684677 2731.4 4.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 28737 | 2.4 | 28737 | 28737 | 1171263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good and in use, however the ceiling needs some repairs, one classroom doesn't have ceiling.
9420 | Construction of 1. No ECD classrooms at Set Kotes ECD | Construction of 1. No ECD classrooms at Set Kotes ECD | To construct 1. No ECD classrooms at Set Kotes ECD | 1. No ECD classrooms at Set Kotes ECD constructed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 539491 | 539491 | Equitable | N/A | 539491 | 0 | 539491 | 100 | 539491 | 539491 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9421 | Construction of ECD classrooms at Kiletten | Construction of ECD classrooms at Kiletten | To construct ECD classrooms at Kiletten | ECD classrooms at Kiletten constructed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 402405 | 33.5 | 402405 | 402691 | 797595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9422 | Construction of ECD classrooms at Silibwet | Construction of ECD classrooms at Silibwet | To construct ECD classrooms at Silibwet | ECD classrooms at Silibwet constructed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1196609 | 99.7 | 1196609 | 3391 | 3391 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9423 | purchase of land for Tombo / Kaptembwo ECDE | purchase of land for Tombo / Kaptembwo ECDE | To acquire land for Tombo / Kaptembwo ECDE | Land for Tombo / Kaptembwo ECDE acquired | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.249192 35.682062 2664.4 19.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No land purchased.
9424 | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | To implement sirikwa ward ecds - design and construction of 2 no ecd classroom, teachers toilet, pupils toilet and watering point set kotes and sirikwa for access to quality education and training | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa completed | 4130299 | N/A | KURESOI NORTH | SIRIKWA | -0.257757, 35.666868 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3600000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9425 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD constructed | 4130299 | N/A | RONGAI | SOIN | -0.09054, 35.873892 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499555 | 100 | 1499555 | 0 | 445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes but the school needs additional toilets for the students,the ceiling needs repair it's sinking.
9426 | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | To construct 2 No classrooms and equpping of Majani Mingi Polytechnic | 2 No classrooms and equpping of Majani Mingi Polytechnic constructed | 4130299 | N/A | RONGAI | SOIN | -0.041969 36.024345 1647 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999796 | 2346341 | 2346341 | Equitable | N/A | 2346341 | 0 | 2230341 | 95.1 | 2230341 | 116000 | 116000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Equipment transferred to Kipsyenan Polytechnic because Majani Mingi Polytechnic is hosting Athinai IDPs.
9427 | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | To implement kipsyenan polytechnic - design and construction of 2 no. classrooms for access to quality education and training | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms completed | 4130299 | N/A | RONGAI | SOIN | -0.061705 36.062868 1618.2 9.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 994184 | 994184 | Equitable | N/A | 994184 | 0 | 540 | 0.1 | 540 | 540 | 993644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class needs repairs, installation Terrazo,furniture's,ECDE Toilet, Electricity installation,Purchase of outdoor equipments and painting.
9428 | Construction of ECDE classrooms at Ruyobei, Koyumtich, | Construction of ECDE classrooms at Ruyobei, Koyumtich, | To construct ECDE classrooms at Ruyobei, Koyumtich, | ECDE classrooms at Ruyobei, Koyumtich, constructed | 4130299 | N/A | RONGAI | SOIN | -0.056816 35.963252 1604 8.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 2400000 | 2400000 | Equitable | Equitable | 2400000 | 0 | 423576 | 17.6 | 423576 | 423576 | 1976424 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require an overhaul repair,including installation of terrazzo, furniture, outdoor activities. Additional modern kitchen also needed.
9429 | Chemachei ECD | Chemachei ECD | To implement chemachei ecd for access to quality education and training | Chemachei ECD completed | 4130299 | N/A | RONGAI | SOLAI | -0.005736, 36.138072 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1799299.6 | 1799299.6 | 1799299.6 | Equitable | N/A | 1799299.6 | 0 | 699162 | 38.9 | 699162 | 1799300 | 1100137.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9430 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD constructed | 4130299 | N/A | RONGAI | SOLAI | -0.025981 36.130112 1649.16064453125 25.464000701904297 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 102253 | 5.7 | 102253 | 1800000 | 1697747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9431 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD constructed | 4130299 | N/A | RONGAI | SOLAI | 0.099233, 36.173895 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 538822 | 538822 | Equitable | N/A | 538822 | 0 | 102253 | 19 | 102253 | 436569 | 436569 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9432 | Equipping of Ruiyobei polytechnic equipment | Equipping of Ruiyobei polytechnic equipment | To equip Ruiyobei polytechnic equipment with necessary facilities and equipment | Ruiyobei polytechnic equipment equipped | 4130299 | N/A | RONGAI | SOLAI | 0.045811 36.125512 1547.9873046875 17.819000244140625 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 748942 | 93.6 | 748942 | 21580 | 51058 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Non functional.
9433 | Kapndege ECD | Kapndege ECD | To implement kapndege ecd for access to quality education and training | Kapndege ECD completed | 4130299 | N/A | RONGAI | SOLAI | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9434 | Mahinga ECD | Mahinga ECD | To implement mahinga ecd for access to quality education and training | Mahinga ECD completed | 4130299 | N/A | RONGAI | SOLAI | 0.023445, 36.146794 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2022 | 1799542.8 | 1799542.8 | 1799542.8 | Equitable | N/A | 1799542.8 | 0 | 699162 | 38.9 | 699162 | 1100381 | 1100380.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9435 | Sigito ECD | Sigito ECD | To implement sigito ecd for access to quality education and training | Sigito ECD completed | 4130299 | N/A | RONGAI | SOLAI | 0.078648 36.19437 1940.5 6 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Solo m general enterprise. Assessor remarks: Good.
9436 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE constructed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.018283 36.216618 2016.9000244140625 6.940000057220459 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1650000 | 1650000 | 1650000 | Equitable | N/A | 1650000 | 0 | 1646614 | 99.8 | 1646614 | 0 | 3386 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: The class serves learners. Contractor: Information not available. Assessor remarks: Yes..
9437 | Construction of ECD classroom and toilet at Morro Hill | Construction of ECD classroom and toilet at Morro Hill | To construct ECD classroom and toilet at Morro Hill | ECD classroom and toilet at Morro Hill constructed | 4130299 | N/A | SUBUKIA | SUBUKIA | 0.003134, 36.229214 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 12/05/2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499984 | 100 | 1499984 | 2892 | 16 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure the class looks good.. Contractor: Information not known.
9438 | Construction of Staff toilet at Subukia Polytechnic | Construction of Staff toilet at Subukia Polytechnic | To construct Staff toilet at Subukia Polytechnic | Staff toilet at Subukia Polytechnic constructed | 4130299 | N/A | SUBUKIA | SUBUKIA | 0.003135 36.229308 1992.0999755859375 23.988000869750977 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 350000 | 100 | 350000 | 2892 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the staff have been using this toilet since it was constructed.. Contractor: No information available. Assessor remarks: The toilet is still in good standing.
9439 | Construction of toilet and fencing at Munanda ECDE Umoja | Construction of toilet and fencing at Munanda ECDE Umoja | To construct toilet and fencing at Munanda ECDE Umoja | Toilet and fencing at Munanda ECDE Umoja constructed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.031217, 36.202857 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999980 | 100 | 999980 | 1500000 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
9440 | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | To implement arash primary school-ecd - design and construction of 2 no. ecd classroom for access to quality education and training | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom completed | 4130299 | N/A | SUBUKIA | SUBUKIA | -0.016571, 36.209792 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 13/01/2018 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1994000 | 83.1 | 1994000 | 406000 | 406000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The class is in a good state.. Contractor: Information not available.
9441 | Baringo ECD, | Baringo ECD, | To implement baringo ecd, for access to quality education and training | Baringo ECD, completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.289637 35.642573 2687.6 9.300000190734863 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199442 | 73624.6 | 73624.6 | Equitable | N/A | 73624.6 | 0 | 407000 | 552.8 | 407000 | 73625 | -333375.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and in use, however the school needs another classroom to accommodate pp1 and pp2. The roof needs repair as its leaking, blackboard needs repainting, it also electricity, gutters and tank for water collection needed, they also require a pit latrine, seats and tables needs maintenance.
9442 | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | To complete Upendo ECD, Kadenye ECD, and Ngenia ECD | Upendo ECD, Kadenye ECD, and Ngenia ECD completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.289225 35.684677 2731.4 4.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 28737 | 2.4 | 28737 | 28737 | 1171263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good and in use, however the ceiling needs some repairs, one classroom doesn't have ceiling.
9443 | Construction of 1. No ECD classrooms at Set Kotes ECD | Construction of 1. No ECD classrooms at Set Kotes ECD | To construct 1. No ECD classrooms at Set Kotes ECD | 1. No ECD classrooms at Set Kotes ECD constructed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 539491 | 539491 | Equitable | N/A | 539491 | 0 | 539491 | 100 | 539491 | 539491 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9444 | Construction of ECD classrooms at Kiletten | Construction of ECD classrooms at Kiletten | To construct ECD classrooms at Kiletten | ECD classrooms at Kiletten constructed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 402691 | 402691 | Equitable | N/A | 402691 | 0 | 402405 | 99.9 | 402405 | 402691 | 286 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9445 | Construction of ECD classrooms at Silibwet | Construction of ECD classrooms at Silibwet | To construct ECD classrooms at Silibwet | ECD classrooms at Silibwet constructed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.235118, 35.662517 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 3391 | 3391 | Equitable | N/A | 3391 | 0 | 1196609 | 35287.8 | 1196609 | 3391 | -1193218 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9446 | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | To implement sirikwa ward ecds - design and construction of 2 no ecd classroom, teachers toilet, pupils toilet and watering point set kotes and sirikwa for access to quality education and training | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.257757, 35.666868 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3600000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9447 | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | To construct 2 No classrooms and equpping of Majani Mingi Polytechnic | 2 No classrooms and equpping of Majani Mingi Polytechnic constructed | 4130299 | N/A | Rongai | Soin | -0.041969 36.024345 1647 8 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999796 | 116000 | 116000 | Equitable | N/A | 116000 | 0 | 2230341 | 1922.7 | 2230341 | 116000 | -2114341 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Equipment transferred to Kipsyenan Polytechnic because Majani Mingi Polytechnic is hosting Athinai IDPs.
9448 | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | To implement kipsyenan polytechnic - design and construction of 2 no. classrooms for access to quality education and training | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms completed | 4130299 | N/A | Rongai | Soin | -0.061705 36.062868 1618.2 9.399999618530273 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 994184 | 994184 | Equitable | N/A | 994184 | 0 | 540 | 0.1 | 540 | 540 | 993644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class needs repairs, installation Terrazo,furniture's,ECDE Toilet, Electricity installation,Purchase of outdoor equipments and painting.
9449 | Construction of ECDE classrooms at Ruyobei, Koyumtich, | Construction of ECDE classrooms at Ruyobei, Koyumtich, | To construct ECDE classrooms at Ruyobei, Koyumtich, | ECDE classrooms at Ruyobei, Koyumtich, constructed | 4130299 | N/A | Rongai | Soin | -0.056816 35.963252 1604 8.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 423576 | 423576 | Equitable | Equitable | 423576 | 0 | 423576 | 100 | 423576 | 423576 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require an overhaul repair,including installation of terrazzo, furniture, outdoor activities. Additional modern kitchen also needed.
9450 | Chemachei ECD | Chemachei ECD | To implement chemachei ecd for access to quality education and training | Chemachei ECD completed | 4130299 | N/A | Rongai | Solai | -0.005736, 36.138072 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1799299.6 | 1799299.6 | 1799299.6 | Equitable | N/A | 1799299.6 | 0 | 699162 | 38.9 | 699162 | 1799300 | 1100137.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9451 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD constructed | 4130299 | N/A | Rongai | Solai | -0.025981 36.130112 1649.16064453125 25.464000701904297 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 102253 | 5.7 | 102253 | 1800000 | 1697747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9452 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD constructed | 4130299 | N/A | Rongai | Solai | 0.099233, 36.173895 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 538822 | 538822 | Equitable | N/A | 538822 | 0 | 102253 | 19 | 102253 | 436569 | 436569 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9453 | Kapndege ECD | Kapndege ECD | To implement kapndege ecd for access to quality education and training | Kapndege ECD completed | 4130299 | N/A | Rongai | Solai | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9454 | Mahinga ECD | Mahinga ECD | To implement mahinga ecd for access to quality education and training | Mahinga ECD completed | 4130299 | N/A | Rongai | Solai | 0.023445, 36.146794 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2022 | 1799542.8 | 1799542.8 | 1799542.8 | Equitable | N/A | 1799542.8 | 0 | 699162 | 38.9 | 699162 | 1100381 | 1100380.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9455 | Sigito ECD | Sigito ECD | To implement sigito ecd for access to quality education and training | Sigito ECD completed | 4130299 | N/A | Rongai | Solai | 0.078648 36.19437 1940.5 6 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Solo m general enterprise. Assessor remarks: Good.
9456 | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | To implement arash primary school-ecd - design and construction of 2 no. ecd classroom for access to quality education and training | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom completed | 4130299 | N/A | Subukia | Subukia | -0.016571, 36.209792 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 13/01/2018 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1994000 | 83.1 | 1994000 | 406000 | 406000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The class is in a good state.. Contractor: Information not available.
9457 | Aon ECD | Aon ECD | To implement aon ecd for access to quality education and training | Aon ECD completed | 4130299 | N/A | KURESOI SOUTH | TINET | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844.4 | 1190844.4 | 1190844.4 | Equitable | N/A | 1190844.4 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9458 | Banana ECD | Banana ECD | To implement banana ecd for access to quality education and training | Banana ECD completed | 4130299 | N/A | KURESOI SOUTH | TINET | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9459 | Chepkosigen ecd | Chepkosigen ecd | To implement chepkosigen ecd for access to quality education and training | Chepkosigen ecd completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.547198, 35.674974 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1195682 | 119.6 | 1195682 | 0 | -195682 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
9460 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 296998 | 296998 | Equitable | N/A | 296998 | 0 | 296992 | 100 | 296992 | 296998 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9461 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 690911 | 690911 | Equitable | N/A | 690911 | 0 | 689454 | 99.8 | 689454 | 1200000 | 1457 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9462 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199220 | 99.9 | 1199220 | 1200000 | 780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9463 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399500.6 | 2399500.6 | 2399500.6 | Equitable | N/A | 2399500.6 | 0 | 2399500 | 100 | 2399500 | 1200000 | 0.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9464 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1186982 | 98.9 | 1186982 | 1200000 | 13018 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9465 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 803509 | 67 | 803509 | 803564 | 396491 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9466 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999950 | 1999950 | 1999950 | Equitable | N/A | 1999950 | 0 | 800000 | 40 | 800000 | 800000 | 1199950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9467 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9468 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 712063 | 712063 | Equitable | N/A | 712063 | 0 | 708583 | 99.5 | 708583 | 1200000 | 3480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9469 | Construction of 2 No ECD classrooms at Kimomoroch | Construction of 2 No ECD classrooms at Kimomoroch | To construct 2 No ECD classrooms at Kimomoroch | 2 No ECD classrooms at Kimomoroch constructed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.558447, 35.616554 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1269806.15 | 1269806.15 | 1269806.15 | Equitable | N/A | 1269806.15 | 0 | 1151750 | 90.7 | 1151750 | 1269806 | 118056.15 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9470 | Finishing of 2. No ECD classrooms at Kipleljin ECD | Finishing of 2. No ECD classrooms at Kipleljin ECD | To implement finishing of 2. no ecd classrooms at kipleljin ecd for access to quality education and training | Finishing of 2. No ECD classrooms at Kipleljin ECD completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.509537 35.634567 2510.2 5.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 998516.4 | 998516.4 | 998516.4 | Equitable | N/A | 998516.4 | 0 | 1199930 | 120.2 | 1199930 | 998516 | -201413.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
9471 | Tinet ECD | Tinet ECD | To implement tinet ecd for access to quality education and training | Tinet ECD completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.497564 35.684194 0 1600 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1180063.3 | 1180063.3 | 1180063.3 | Equitable | N/A | 1180063.3 | 0 | 1180063 | 100 | 1180063 | 0 | 0.3 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition but leaking roof and cracked floor.
9472 | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | To implement tinet ward ecds -constrruction of 1 ecd classroom at buchechet, cheram, kipsirat, rwaget,maluo, kapnanda,kamwaura and kapnandi. for access to quality education and training | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. completed | 4130299 | N/A | KURESOI SOUTH | TINET | -0.513813 35.683561 2568.666 3.1989998817443848 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 8400000 | 3628986 | 3628986 | Equitable | N/A | 3628986 | 0 | 2750018 | 75.8 | 2750018 | 878968 | 878968 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
9473 | Chandera polytechnic 2 classrooms | Chandera polytechnic 2 classrooms | To implement chandera polytechnic 2 classrooms for access to quality education and training | Chandera polytechnic 2 classrooms completed | 4130299 | N/A | MOLO | TURI | -0.30802, 35.729738 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399724 | 2399724 | 2399724 | Equitable | N/A | 2399724 | 0 | 2399600 | 100 | 2399600 | 0 | 124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9474 | Chandora ecd | Chandora ecd | To implement chandora ecd for access to quality education and training | Chandora ecd completed | 4130299 | N/A | MOLO | TURI | -0.311867, 35.731635 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199940 | 100 | 1199940 | 30 | 60 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9475 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD constructed | 4130299 | N/A | MOLO | TURI | -0.248077 35.730962 2517.6 200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199996.8 | 1199996.8 | 1199996.8 | Equitable | N/A | 1199996.8 | 0 | 1199994 | 100 | 1199994 | 1199997 | 2.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
9476 | Gwataniro ECD | Gwataniro ECD | To implement gwataniro ecd for access to quality education and training | Gwataniro ECD completed | 4130299 | N/A | MOLO | TURI | -0.329513 35.694993 2755.300048828125 86.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199986 | 1199986 | 1199986 | Equitable | N/A | 1199986 | 0 | 1199986 | 100 | 1199986 | 30 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Very Good. Objective met: No. Viable: No. Assessor remarks: The project was drilled at someone's land. The owner of the land owns the project.
9477 | Migaa ECD | Migaa ECD | To implement migaa ecd for access to quality education and training | Migaa ECD completed | 4130299 | N/A | MOLO | TURI | -0.273188 35.732858 2517.6 18 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1186662.6 | 1186662.6 | 1186662.6 | Equitable | N/A | 1186662.6 | 0 | 30 | 0 | 30 | 30 | 1186632.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is in dilapidated condition..
9478 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 4130299 | N/A | MOLO | TURI | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9479 | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | To construct ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School constructed | 4130299 | N/A | MOLO | TURI | -0.32942 35.686729 2755.300048828125 96.13099670410156 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1199994 | 50 | 1199994 | 1200006 | 1200006 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is under the Chesingele, Gathigi and Mwangaza ECDs.
9480 | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | To construct Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD constructed | 4130299 | N/A | MOLO | TURI | -0.319855 35.739007 2667.3 8.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1095771 | 99.6 | 1095771 | 4229 | 4229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been painted afresh.
9481 | Renovation of existing ECD classroom at Rafiki ECD | Renovation of existing ECD classroom at Rafiki ECD | To rehabilitate existing ECD classroom at Rafiki ECD to restore functionality | Existing ECD classroom at Rafiki ECD rehabilitated | 4130299 | N/A | MOLO | TURI | -0.303263 35.728955 2630.6 8.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 1199940 | 600 | 1199940 | 199960 | -999940 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
9482 | Aon ECD | Aon ECD | To implement aon ecd for access to quality education and training | Aon ECD completed | 4130299 | N/A | Kuresoi South | Tinet | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844.4 | 1190844.4 | 1190844.4 | Equitable | N/A | 1190844.4 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9483 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 296998 | 296998 | Equitable | N/A | 296998 | 0 | 296992 | 100 | 296992 | 296998 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9484 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199220 | 99.9 | 1199220 | 1200000 | 780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9485 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1186982 | 98.9 | 1186982 | 1200000 | 13018 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9486 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 803509 | 67 | 803509 | 803564 | 396491 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9487 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999950 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9488 | Construction of 2 No ECD classrooms at Kimomoroch | Construction of 2 No ECD classrooms at Kimomoroch | To construct 2 No ECD classrooms at Kimomoroch | 2 No ECD classrooms at Kimomoroch constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.558447, 35.616554 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1269806.15 | 1269806.15 | 1269806.15 | Equitable | N/A | 1269806.15 | 0 | 1151750 | 90.7 | 1151750 | 1269806 | 118056.15 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9489 | Finishing of 2. No ECD classrooms at Kipleljin ECD | Finishing of 2. No ECD classrooms at Kipleljin ECD | To implement finishing of 2. no ecd classrooms at kipleljin ecd for access to quality education and training | Finishing of 2. No ECD classrooms at Kipleljin ECD completed | 4130299 | N/A | Kuresoi South | Tinet | -0.509537 35.634567 2510.2 5.699999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 998516.4 | 998516.4 | 998516.4 | Equitable | N/A | 998516.4 | 0 | 1199930 | 120.2 | 1199930 | 998516 | -201413.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
9490 | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | To implement tinet ward ecds -constrruction of 1 ecd classroom at buchechet, cheram, kipsirat, rwaget,maluo, kapnanda,kamwaura and kapnandi. for access to quality education and training | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. completed | 4130299 | N/A | Kuresoi South | Tinet | -0.513813 35.683561 2568.666 3.1989998817443848 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 8400000 | 878968.2 | 878968.2 | Equitable | N/A | 878968.2 | 0 | 2750018 | 312.9 | 2750018 | 878968 | -1871049.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
9491 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD constructed | 4130299 | N/A | Molo | Turi | -0.248077 35.730962 2517.6 200 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199996.8 | 1199996.8 | 1199996.8 | Equitable | N/A | 1199996.8 | 0 | 1199994 | 100 | 1199994 | 1199997 | 2.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
9492 | Migaa ECD | Migaa ECD | To implement migaa ecd for access to quality education and training | Migaa ECD completed | 4130299 | N/A | Molo | Turi | -0.273188 35.732858 2517.6 18 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1186662.6 | 1186662.6 | 1186662.6 | Equitable | N/A | 1186662.6 | 0 | 30 | 0 | 30 | 30 | 1186632.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is in dilapidated condition..
9493 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 4130299 | N/A | Molo | Turi | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9494 | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | To construct ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School constructed | 4130299 | N/A | Molo | Turi | -0.32942 35.686729 2755.300048828125 96.13099670410156 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1199994 | 50 | 1199994 | 1200006 | 1200006 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is under the Chesingele, Gathigi and Mwangaza ECDs.
9495 | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | To construct Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD constructed | 4130299 | N/A | Molo | Turi | -0.319855 35.739007 2667.3 8.600000381469727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1095771 | 99.6 | 1095771 | 4229 | 4229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been painted afresh.
9496 | Renovation of existing ECD classroom at Rafiki ECD | Renovation of existing ECD classroom at Rafiki ECD | To rehabilitate existing ECD classroom at Rafiki ECD to restore functionality | Existing ECD classroom at Rafiki ECD rehabilitated | 4130299 | N/A | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 1199940 | 600 | 1199940 | 199960 | -999940 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
9497 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD constructed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9498 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD constructed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199643 | 379239 | 379239 | Equitable | N/A | 379239 | 0 | 379239 | 100 | 379239 | 379239 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9499 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD constructed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1114636 | 92.9 | 1114636 | 85364 | 85364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9500 | Legetio ECD | Legetio ECD | To implement legetio ecd for access to quality education and training | Legetio ECD completed | 4130299 | N/A | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1199162 | 178052 | 178052 | Equitable | N/A | 178052 | 0 | 178052 | 100 | 178052 | 547290 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
9501 | Lengenet ECD | Lengenet ECD | To implement lengenet ecd for access to quality education and training | Lengenet ECD completed | 4130299 | N/A | RONGAI | VISOI | -0.136537, 35.896727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2016/17 | 1183447.66 | 1183447.66 | 1183447.66 | Equitable | N/A | 1183447.66 | 0 | 547290 | 46.2 | 547290 | 547290 | 636157.66 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Menengai TUMAINI 4.
9502 | Munanda tuyoitich ECDE - Construction of I classroom and Toilets | Munanda tuyoitich ECDE - Construction of I classroom and Toilets | To implement munanda tuyoitich ecde - construction of i classroom and toilets for access to quality education and training | Munanda tuyoitich ECDE - Construction of I classroom and Toilets completed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799914 | 100 | 1799914 | 600000 | 86 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9503 | Naiswet ECDE -Construction of Toilets | Naiswet ECDE -Construction of Toilets | To implement naiswet ecde -construction of toilets for access to quality education and training | Naiswet ECDE -Construction of Toilets completed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599592 | 99.9 | 599592 | 600000 | 408 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9504 | Shalom ECD | Shalom ECD | To implement shalom ecd for access to quality education and training | Shalom ECD completed | 4130299 | N/A | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1160093.96 | 1160093.96 | 1160093.96 | Equitable | N/A | 1160093.96 | 0 | 178052 | 15.3 | 178052 | 1160094 | 982041.96 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
9505 | Umoja ECDE - Construction of Toilets | Umoja ECDE - Construction of Toilets | To implement umoja ecde - construction of toilets for access to quality education and training | Umoja ECDE - Construction of Toilets completed | 4130299 | N/A | RONGAI | VISOI | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 593502 | 98.9 | 593502 | 600000 | 6498 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9506 | Construction of a classroom at Kipsaos ECD | Construction of a classroom at Kipsaos ECD | To construct a classroom at Kipsaos ECD | A classroom at Kipsaos ECD constructed | 4130299 | N/A | RONGAI | VISOI | -0.101903, 35.857515 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9507 | Construction of Thirandu ECD toilet | Construction of Thirandu ECD toilet | To construct Thirandu ECD toilet | Thirandu ECD toilet constructed | 4130299 | N/A | RONGAI | VISOI | -0.112228 35.887368 1817.7 20.799999237060547 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399446 | 99.9 | 399446 | 600000 | 554 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9508 | central pry viwandani | central pry viwandani | To implement central pry viwandani for access to quality education and training | central pry viwandani completed | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.710843 36.433726 1903.699951171875 7.052999973297119 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 77 | 0 | 77 | 77 | 1199923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Standard.
9509 | Construction and equipping of 1.No ECD classroom at Kabati Highway Primary ECD | Construction and equipping of 1.No ECD classroom at Kabati Highway Primary ECD | To construct and equip 1.No ECD classroom at Kabati Highway Primary ECD | 1.No ECD classroom at Kabati Highway Primary ECD constructed and equipped | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.721695 36.44449 1940.699951171875 77.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499439 | 100 | 1499439 | 1500000 | 561 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes The project objective met. Viable: Yes. Assessor remarks: Complete.
9510 | Construction and equipping of 1.No ECD classroom at Mithuri ECD | Construction and equipping of 1.No ECD classroom at Mithuri ECD | To construct and equip 1.No ECD classroom at Mithuri ECD | 1.No ECD classroom at Mithuri ECD constructed and equipped | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.721695 36.44449 1940.699951171875 77.5999984741211 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499845 | 100 | 1499845 | 1500000 | 155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes The project objective met. Viable: Yes. Assessor remarks: Complete.
9511 | Kabati Highway Primary ECD | Kabati Highway Primary ECD | To implement kabati highway primary ecd for access to quality education and training | Kabati Highway Primary ECD completed | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.720522 36.445398 1940.199951171875 100 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199922 | 100 | 1199922 | 0 | 78 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yet to start. Assessor remarks: Yet to start.
9512 | Mithuri ECD | Mithuri ECD | To implement mithuri ecd for access to quality education and training | Mithuri ECD completed | 4130299 | N/A | NAIVASHA | VIWANDANI | -0.711189, 36.436021 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
9513 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9514 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199643 | 379239 | 379239 | Equitable | N/A | 379239 | 0 | 379239 | 100 | 379239 | 379239 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9515 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 85364 | 85364 | Equitable | N/A | 85364 | 0 | 1114636 | 1305.7 | 1114636 | 85364 | -1029272 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9516 | Lengenet ECD | Lengenet ECD | To implement lengenet ecd for access to quality education and training | Lengenet ECD completed | 4130299 | N/A | Rongai | Visoi | -0.136537, 35.896727 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2016/17 | 1183447.66 | 547289.5 | 547289.5 | Equitable | N/A | 547289.5 | 0 | 547290 | 100 | 547290 | 547290 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Menengai TUMAINI 4.
9517 | Naiswet ECDE -Construction of Toilets | Naiswet ECDE -Construction of Toilets | To implement naiswet ecde -construction of toilets for access to quality education and training | Naiswet ECDE -Construction of Toilets completed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599592 | 99.9 | 599592 | 600000 | 408 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9518 | Shalom ECD | Shalom ECD | To implement shalom ecd for access to quality education and training | Shalom ECD completed | 4130299 | N/A | Rongai | Visoi | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1160093.96 | 1160093.96 | 1160093.96 | Equitable | N/A | 1160093.96 | 0 | 178052 | 15.3 | 178052 | 1160094 | 982041.96 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
9519 | Construction of a classroom at Kipsaos ECD | Construction of a classroom at Kipsaos ECD | To construct a classroom at Kipsaos ECD | A classroom at Kipsaos ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.101903, 35.857515 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9520 | central pry viwandani | central pry viwandani | To implement central pry viwandani for access to quality education and training | central pry viwandani completed | 4130299 | N/A | Naivasha | Viwandani | -0.710843 36.433726 1903.699951171875 7.052999973297119 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 77 | 0 | 77 | 77 | 1199923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Standard.
9521 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.168615 36.250903 1712.4 9 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 401975 | 33.5 | 401975 | 798025 | 798025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Teacher Toilet and Pupils Not Constructed.
9522 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 916423 | 76.4 | 916423 | 283577 | 283577 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
9523 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.09978 36.263945 1824.8 12 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 137 | 0 | 137 | 137 | 1199863 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
9524 | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | To construct 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs constructed | 4130299 | N/A | SUBUKIA | WASEGES | 0.08177, 36.226511 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2364444 | 98.5 | 2364444 | 35496 | 35556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9525 | Equipping of Gakingi polytechnic | Equipping of Gakingi polytechnic | To equip Gakingi polytechnic with necessary facilities and equipment | Gakingi polytechnic equipped | 4130299 | N/A | SUBUKIA | WASEGES | 0.116708, 36.224264 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910200 | 91 | 910200 | 89800 | 89800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes.
9526 | Gitudaga ECDEs | Gitudaga ECDEs | To implement gitudaga ecdes for access to quality education and training | Gitudaga ECDEs completed | 4130299 | N/A | SUBUKIA | WASEGES | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1149769.96 | 1149769.96 | 1149769.96 | Equitable | N/A | 1149769.96 | 0 | 0 | 0 | 0 | 1149770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9527 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.168615 36.250903 1712.4 9 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 401975 | 33.5 | 401975 | 798025 | 798025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Teacher Toilet and Pupils Not Constructed.
9528 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 283577 | 283577 | Equitable | N/A | 283577 | 0 | 916423 | 323.2 | 916423 | 283577 | -632846 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
9529 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.09978 36.263945 1824.8 12 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 137 | 0 | 137 | 137 | 1199863 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
9530 | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | To construct 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs constructed | 4130299 | N/A | Subukia | Waseges | 0.08177, 36.226511 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 35556 | 35556 | Equitable | N/A | 35556 | 0 | 2364444 | 6649.9 | 2364444 | 35496 | -2328888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9531 | Equipping of Gakingi polytechnic | Equipping of Gakingi polytechnic | To equip Gakingi polytechnic with necessary facilities and equipment | Gakingi polytechnic equipped | 4130299 | N/A | Subukia | Waseges | 0.116708, 36.224264 | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910200 | 91 | 910200 | 89800 | 89800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes.
9532 | Gitudaga ECDEs | Gitudaga ECDEs | To implement gitudaga ecdes for access to quality education and training | Gitudaga ECDEs completed | 4130299 | N/A | Subukia | Waseges | N/A | VOTE NO 4575 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1149769.96 | 1149769.96 | 1149769.96 | Equitable | N/A | 1149769.96 | 0 | 0 | 0 | 0 | 1149770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9533 | construction of a kitchen, caretaker house, laundry, expansion of rooms | construction of a kitchen, caretaker house, laundry, expansion of rooms | To construct a kitchen, caretaker house, laundry, expansion of rooms | A kitchen, caretaker house, laundry, expansion of rooms constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 6506105 | 6506105 | N/A | N/A | 6506105 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9534 | Construction Of Chain Link Fence Bahati Stadium | Construction Of Chain Link Fence Bahati Stadium | To construct Chain Link Fence Bahati Stadium | Chain Link Fence Bahati Stadium constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9535 | Construction Of Changing Room At Bahati Stadium | Construction Of Changing Room At Bahati Stadium | To construct Changing Room At Bahati Stadium | Changing Room At Bahati Stadium constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9536 | Construction Of Kamukunji Ground Perimetre Wall | Construction Of Kamukunji Ground Perimetre Wall | To construct Kamukunji Ground Perimetre Wall | Kamukunji Ground Perimetre Wall constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9537 | Construction Perimetre Waii Rongai Stadium | Construction Perimetre Waii Rongai Stadium | To construct Perimetre Waii Rongai Stadium | Perimetre Waii Rongai Stadium constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | N/A | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9538 | Constructionof Changing Room & General Renovation | Constructionof Changing Room & General Renovation | To implement constructionof changing room & general renovation for youth empowerment and social inclusion | Constructionof Changing Room & General Renovation completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | N/A | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9539 | Establishing and equipping of a GBV Centre | Establishing and equipping of a GBV Centre | To implement establishing and equipping of a gbv centre for youth empowerment and social inclusion | Establishing and equipping of a GBV Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 10000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9540 | Establishing and equipping of cultural facilities | Establishing and equipping of cultural facilities | To implement establishing and equipping of cultural facilities for youth empowerment and social inclusion | Establishing and equipping of cultural facilities completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 10000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9541 | Establishment of Sports Centre at Keringet (Phase I) | Establishment of Sports Centre at Keringet (Phase I) | To implement establishment of sports centre at keringet (phase i) for youth empowerment and social inclusion | Establishment of Sports Centre at Keringet (Phase I) completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 50000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9542 | Kamukunji Ground Changing Rooms | Kamukunji Ground Changing Rooms | To implement kamukunji ground changing rooms for youth empowerment and social inclusion | Kamukunji Ground Changing Rooms completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 1437453.9 | 1437453.9 | 1437453.9 | N/A | N/A | 1437453.9 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9543 | Partial Completion of a GBV Centre | Partial Completion of a GBV Centre | To implement partial completion of a gbv centre for youth empowerment and social inclusion | Partial Completion of a GBV Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 30000000 | 7714075 | 7714075 | N/A | N/A | 7714075 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9544 | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation | To implement partial fence, reroofing, electrical works , plumbing, general repairs and renovation for youth empowerment and social inclusion | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9545 | Renovation and equipping and refurbishment of Menengai social complex | Renovation and equipping and refurbishment of Menengai social complex | To rehabilitate equipping and refurbishment of Menengai social complex to restore functionality | Equipping and refurbishment of Menengai social complex rehabilitated | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9546 | Storm Water Drainge & Levelling Playfield At Molo Stadium | Storm Water Drainge & Levelling Playfield At Molo Stadium | To implement storm water drainge & levelling playfield at molo stadium for youth empowerment and social inclusion | Storm Water Drainge & Levelling Playfield At Molo Stadium completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9547 | Administration, Planning and support services | Construction of social hall at mwaki Mugi Chief ground | To construct social hall at mwaki Mugi Chief ground | Social hall at mwaki Mugi Chief ground constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.232477 36.147302 1941.300048828125 51.319000244140625 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | 4,780,076 | 5000000 | 0 | 0 | 0 | 0 | 11803 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational,but need installation of electricity.
9548 | Administration, Planning and support services | Construction and equipping of a Resource Centre at Mogoon Centre | To construct and equip a Resource Centre at Mogoon Centre | A Resource Centre at Mogoon Centre constructed and equipped | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPKURES | -0.306306 36.000514 0 2000 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | 2,973,420 | 3000000 | 0 | 0 | 0 | 0 | 316 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Was bought but about quarter has been privatised..
9549 | Administration, Planning and support services | Construction and equipping of a Resource Centre at Mogoon Centre | To construct and equip a Resource Centre at Mogoon Centre | A Resource Centre at Mogoon Centre constructed and equipped | 3110299 | Construction of Buildings - Ot | Nakuru West | Kapkures | -0.306306 36.000514 0 2000 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 2973420 | 2973420 | Equitable | 2,973,420 | 2973420 | 0 | 0 | 0 | 0 | 316 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Was bought but about quarter has been privatised..
9550 | Administration, Planning and support services | Completion of Kayole Social Hall | To complete Kayole Social Hall | Kayole Social Hall completed | 3110299 | Construction of Buildings - Ot | NAIVASHA | LAKEVIEW | -0.757177, 36.463784 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | 999,999 | 1000000 | 0 | 669 | 0.1 | 669 | 322 | 999331 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Pro max general supplies LTD.
9551 | Administration, Planning and support services | Completion of Kayole Social Hall | To complete Kayole Social Hall | Kayole Social Hall completed | 3110299 | Construction of Buildings - Ot | Naivasha | Lakeview | -0.757177, 36.463784 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | 999,999 | 1000000 | 0 | 669 | 0.1 | 669 | 322 | 999331 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Pro max general supplies LTD.
9552 | Administration, Planning and support services | Completion of mariashoni social hall | To complete mariashoni social hall | Mariashoni social hall completed | 3110299 | Construction of Buildings - Ot | MOLO | MARIASHONI | -0.36843 35.821484 2651.938503211059 8 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | - | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Does not exist.
9553 | Administration, Planning and support services | Completion of Teacher social Hall | To complete Teacher social Hall | Teacher social Hall completed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | MENENGAI | -0.27578, 36.115322 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2019/20 | 6498843 | 4000000 | 4000000 | Equitable | - | 4000000 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9554 | Administration, Planning and support services | Fencing of teachers playing field near full gospel | To secure teachers playing field near full gospel through fencing | Teachers playing field near full gospel fenced and secured | 3110299 | Construction of Buildings - Ot | NAKURU EAST | MENENGAI | -0.279579 36.122334 1856.4000244140625 64.94400024414062 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | 999,600 | 1000000 | 0 | 0 | 0 | 0 | 331 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9555 | Administration, Planning and support services | Fencing of Teachers social hall | To secure Teachers social hall through fencing | Teachers social hall fenced and secured | 3110299 | Construction of Buildings - Ot | NAKURU EAST | MENENGAI | -0.275812, 36.115291 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | 999,999 | 1000000 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9556 | Administration, Planning and support services | Construction of Social hall at Mercy Njeri | To construct Social hall at Mercy Njeri | Social hall at Mercy Njeri constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.242492 36.006959 2007.199951171875 47.21500015258789 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need mainenance.
9557 | Construction of library Molo Town | Construction of library Molo Town | To construct library Molo Town | Library Molo Town constructed | 3110299 | Construction of Buildings - Ot | MOLO | MOLO CENTRAL | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | 2014/15 | 1036883.2 | 1036883.2 | 1036883.2 | Equitable | N/A | 1036883.2 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9558 | Administration, Planning and Support Services | Construction of Jua Kali Social Hall | To construct Jua Kali Social Hall | Jua Kali Social Hall constructed | 3110299 | Construction of Buildings - Ot | Njoro | Mau Narok | -0.574654, 35.693519 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2017 | 2000000 | 2000000 | 2000000 | Equitable | 1,971,270 | 2000000 | 0 | 0 | 0 | 0 | 1306 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9559 | Administration, Planning and Support Services | Construction of youth centre at Kiamunyi | To construct youth centre at Kiamunyi | Youth centre at Kiamunyi constructed | 3110299 | Construction of Buildings - Ot | Rongai | Menengai West | -0.2466 36.013657 2010.9 9.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | 1,725,210 | 3500000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9560 | Construction of library Molo Town | Construction of library Molo Town | To construct library Molo Town | Library Molo Town constructed | 3110299 | Construction of Buildings - Ot | Molo | Molo Central | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | 2014/15 | 1036883.2 | 1036883 | 1036883 | Equitable | N/A | 1036883 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9561 | Administration, Planning and Support Services | construction of perimeter wall in Rongai Stadium | To construct perimeter wall in Rongai Stadium | Perimeter wall in Rongai Stadium constructed | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.173526 35.860517 1868.199951171875 54.09400177001953 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1910435 | 1910435 | 1910435 | Equitable | 286,567 | 1910435 | 0 | 0 | 0 | 0 | 314 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
9562 | Completion of London social hall | Completion of London social hall | To complete London social hall | London social hall completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 2700000 | 2700000 | 2700000 | N/A | N/A | 2700000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9563 | Administration, Planning and support services | Rehabilitation and equipping of Milimani social hall | To rehabilitate equipping of Milimani social hall to restore functionality | Equipping of Milimani social hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | NAKURU WEST | LONDON | -0.275133 36.049587 1857.5 9.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 3500000 | 3500000 | 3500000 | Equitable | - | 3500000 | 0 | 0 | 0 | 0 | 41 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting and provide an alternative access road from the one at gioto direct to the hall.
9564 | Administration, Planning and Support Services | Rehabilitation of London social hall | To rehabilitate London social hall to restore functionality | London social hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | NAKURU WEST | LONDON | -0.275133 36.049587 1857.5 9.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 3500000 | 3500000 | 3500000 | Equitable | 3,400,000 | 3500000 | 0 | 0 | 0 | 0 | 1318 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting and provide an alternative access road from the one at gioto direct to the hall.
9565 | Administration, Planning and Support Services | Rehabilitation of London social hall | To rehabilitate London social hall to restore functionality | London social hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.275133 36.049587 1857.5 9.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 3500000 | 6800000 | 6800000 | Equitable | 3,400,000 | 6800000 | 0 | 0 | 0 | 0 | 1318 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting and provide an alternative access road from the one at gioto direct to the hall.
9566 | Enhanced care and support of the elderly through expansion of new rooms at Alms house | Enhanced care and support of the elderly through expansion of new rooms at Alms house | To implement enhanced care and support of the elderly through expansion of new rooms at alms house for youth empowerment and social inclusion | Enhanced care and support of the elderly through expansion of new rooms at Alms house completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 2351783.6 | 2351783.6 | N/A | N/A | 2351783.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9567 | Administration, Planning and support services | Leveling and compacting of Menengai West field and goal post | To implement leveling and compacting of menengai west field and goal post for youth empowerment and social inclusion | Leveling and compacting of Menengai West field and goal post completed | 3110499 | Construction of Roads - Other | RONGAI | MENENGAI WEST | -0.255223 35.990582 1983.5 2.700000047683716 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | 498,972 | 500000 | 0 | 0 | 0 | 0 | 11898 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9568 | Administration, Planning and support services | Rehabilitation of Bahati Stadium i.e. levelling, fencing and new goal posts | To rehabilitate Bahati Stadium i.e. levelling, fencing and new goal posts to restore functionality | Bahati Stadium i.e. levelling, fencing and new goal posts rehabilitated | 3110504 | Other Infrastructure and Civil Works | BAHATI | BAHATI | -0.183297 36.123632 1931 9.64799976348877 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | 498,995 | 500000 | 0 | 0 | 0 | 0 | 11805 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
9569 | Administration, Planning and support services | Youth empowerment projects in dundori ward | To implement youth empowerment projects in dundori ward for youth empowerment and social inclusion | Youth empowerment projects in dundori ward completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.275225 36.190557 1965.9000244140625 4.900000095367432 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 909162 | 909162 | 909162 | Equitable | 895,000 | 909162 | 0 | 0 | 0 | 0 | 41772 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Holy son. Assessor remarks: Good.
9570 | Administration, Planning and support services | Supply of (wahl) shaving machines for barber shops in flamingo ward | To implement supply of (wahl) shaving machines for barber shops in flamingo ward for youth empowerment and social inclusion | Supply of (wahl) shaving machines for barber shops in flamingo ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308232 36.079252 1789.4000244140625 38.18600082397461 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 570185 | 570185 | 570185 | Equitable | 569,400 | 570185 | 0 | 0 | 0 | 0 | 37895 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well done. Operational.
9571 | Administration, Planning and support services | Construction of perimeter wall and metallic gate at Bondeni Social hall | To construct perimeter wall and metallic gate at Bondeni Social hall | Perimeter wall and metallic gate at Bondeni Social hall constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | GILGIL | -0.504943, 36.326059 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | 1,999,999 | 2000000 | 0 | 0 | 0 | 0 | 333 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
9572 | Administration, Planning and support services | Construction of perimeter wall and metallic gate at Bondeni Social hall | To construct perimeter wall and metallic gate at Bondeni Social hall | Perimeter wall and metallic gate at Bondeni Social hall constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504943, 36.326059 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1999999 | 1999999 | Equitable | 1,999,999 | 1999999 | 0 | 0 | 0 | 0 | 333 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
9573 | Administration, Planning and support services | Fencing of YMCA grounds | To secure YMCA grounds through fencing | YMCA grounds fenced and secured | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | HELLS GATE | -0.77689 36.431733 1913.300048828125 10.196999549865723 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 946472 | 946472 | 946472 | Equitable | 945,516 | 946472 | 0 | 0 | 0 | 0 | 317 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
9574 | Completion of Kamukunji Stadium | Completion of Kamukunji Stadium | To complete Kamukunji Stadium | Kamukunji Stadium completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9575 | Construction Perimetre Waii Rongai Stadium | Construction Perimetre Waii Rongai Stadium | To construct Perimetre Waii Rongai Stadium | Perimetre Waii Rongai Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3480711.08 | 3480711.08 | N/A | N/A | 3480711.08 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9576 | Establishment of Sports Centre at Keringet (Phase 2) | Establishment of Sports Centre at Keringet (Phase 2) | To implement establishment of sports centre at keringet (phase 2) for youth empowerment and social inclusion | Establishment of Sports Centre at Keringet (Phase 2) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 100000000 | 35000000 | 35000000 | N/A | N/A | 35000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9577 | Establishment of Sports Centre at Keringet (Phase I) | Establishment of Sports Centre at Keringet (Phase I) | To implement establishment of sports centre at keringet (phase i) for youth empowerment and social inclusion | Establishment of Sports Centre at Keringet (Phase I) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 50000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9578 | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation | To implement partial fence, reroofing, electrical works , plumbing, general repairs and renovation for youth empowerment and social inclusion | Partial fence, reroofing, electrical works , plumbing, general repairs and renovation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 9503720 | 9503720 | N/A | N/A | 9503720 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9579 | Renovation and equipping and refurbishment of Menengai social complex | Renovation and equipping and refurbishment of Menengai social complex | To rehabilitate equipping and refurbishment of Menengai social complex to restore functionality | Equipping and refurbishment of Menengai social complex rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 6000000 | 5900000 | N/A | N/A | 5900000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9580 | Renovation of perimeter water and installation of three (3) gates at Molo Stadium | Renovation of perimeter water and installation of three (3) gates at Molo Stadium | To rehabilitate perimeter water and installation of three (3) gates at Molo Stadium to restore functionality | Perimeter water and installation of three (3) gates at Molo Stadium rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | N/A | N/A | 3000000 | 2995460 | 2995460 | N/A | N/A | 2995460 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9581 | Administration, Planning and support services | Fencing of YMCA grounds | To secure YMCA grounds through fencing | YMCA grounds fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.77689 36.431733 1913.300048828125 10.196999549865723 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 946472 | 945516 | 945516 | Equitable | 945,516 | 945516 | 0 | 0 | 0 | 0 | 317 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
9582 | Administration, Planning and Support Services | fencing and land levelling of resource centre at sewage village | To secure and land levelling of resource centre at sewage village through fencing | And land levelling of resource centre at sewage village fenced and secured | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.318516 36.05296 1768.8572483399244 12.072999954223633 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 2999999 | 3000000 | 3000000 | Equitable | 2,750,000 | 3000000 | 0 | 0 | 0 | 0 | 1311 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but the gate was in wrong position. Contractor: U40. Assessor remarks: the gate was not well positioned hence it was relocated to an accessible place.
9583 | Administration, Planning and Support Services | land levelling of resource centre at sewage village | To implement land levelling of resource centre at sewage village for youth empowerment and social inclusion | land levelling of resource centre at sewage village completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.318516 36.05296 1768.8572483399244 12.072999954223633 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 2999999 | 3000000 | 3000000 | Equitable | 2,750,000 | 3000000 | 0 | 0 | 0 | 0 | 1311 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but the gate was in wrong position. Contractor: U40. Assessor remarks: the gate was not well positioned hence it was relocated to an accessible place.
9584 | Administration, Planning and Support Services | women and youth groups empowerment | To implement women and youth groups empowerment for youth empowerment and social inclusion | women and youth groups empowerment completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 4000000 | 5000000 | 5000000 | Equitable | 820,700 | 5000000 | 0 | 0 | 0 | 0 | 42289 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9585 | Administration, Planning and Support Services | Construction of Modern washrooms, water point, football and volleyball posts, security light and installation of WiFi at Kirathimo Grounds | To construct Modern washrooms, water point, football and volleyball posts, security light and installation of WiFi at Kirathimo Grounds | Modern washrooms, water point, football and volleyball posts, security light and installation of WiFi at Kirathimo Grounds constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.236885, 36.123922 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | 1,999,900 | 2000000 | 0 | 0 | 0 | 0 | 1317 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes.
9586 | Administration, Planning and Support Services | Fencing of maai mahiu social hall | To secure maai mahiu social hall through fencing | Maai mahiu social hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.978956, 36.585812 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | 1,660,750 | 1000000 | 0 | 789 | 0.1 | 789 | 0 | 999211 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
9587 | Administration, Planning and support services | Fencing of teachers playing field near full gospel | To secure teachers playing field near full gospel through fencing | Teachers playing field near full gospel fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.279579 36.122334 1856.4000244140625 64.94400024414062 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 999600 | 999600 | Equitable | 999,600 | 999600 | 0 | 0 | 0 | 0 | 331 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9588 | Administration, Planning and support services | Fencing of Teachers social hall | To secure Teachers social hall through fencing | Teachers social hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275812, 36.115291 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2020/21 | 1000000 | 999999 | 999999 | Equitable | 999,999 | 999999 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9589 | Administration, Planning and support services | Youth empowerment - Motor cycle | To implement youth empowerment - motor cycle for youth empowerment and social inclusion | Youth empowerment - Motor cycle completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.41097 35.942462 2349.6004424690186 4.385000228881836 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,968,750 | 2000000 | 0 | 0 | 0 | 0 | 41777 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and requires regular maintenance.
9590 | Administration, Planning and support services | Youth/Women empowerment at mwariki | To implement youth/women empowerment at mwariki for youth empowerment and social inclusion | Youth/Women empowerment at mwariki completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 1,485,600 | 1500000 | 0 | 0 | 0 | 0 | 37900 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9591 | Administration, Planning and Support Services | construction of perimeter wall in Rongai Stadium | To construct perimeter wall in Rongai Stadium | Perimeter wall in Rongai Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.173526 35.860517 1868.199951171875 54.09400177001953 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1910435 | 1899318 | 1899318 | Equitable | 286,567 | 1899318 | 0 | 0 | 0 | 0 | 314 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
9592 | Administration, Planning and Support Services | Equipping of ICT hub | To equip ICT hub with necessary facilities and equipment | ICT hub equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.715125 36.432547 0 300 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 42640 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
9593 | Administration, Planning and Support Services | Equipping of studio and amphitheatre in Industrial Are | To equip studio and amphitheatre in Industrial Are with necessary facilities and equipment | Studio and amphitheatre in Industrial Are equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71298 36.435601 1906.300048828125 20.15399932861328 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 3500000 | 3500000 | 3500000 | Equitable | - | 3500000 | 0 | 0 | 0 | 0 | 1329 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Complete.
9594 | Administration, Planning and Support Services | Renovation of studio and amphitheatre in Industrial Area | To rehabilitate studio and amphitheatre in Industrial Area to restore functionality | Studio and amphitheatre in Industrial Area rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71298 36.435601 1906.300048828125 20.15399932861328 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | - | 1500000 | 0 | 0 | 0 | 0 | 1329 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Complete.
9595 | Administration, Planning and support services | Youth empowerment - Motor cycle | To implement youth empowerment - motor cycle for youth empowerment and social inclusion | Youth empowerment - Motor cycle completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 1,495,968 | 1500000 | 0 | 0 | 0 | 0 | 37899 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9596 | Administration, Planning and support services | Construction of recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" | To construct recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" | Recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | -0.326886, 36.044487 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2019 | 3300000 | 3300000 | 3300000 | Equitable | 3,295,000 | 3300000 | 0 | 0 | 0 | 0 | 11888 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Cider collect.
9597 | Administration, Planning and support services | Equipping and fencing of Elburgon social hall | To equip and fencing of Elburgon social hall with necessary facilities and equipment | And fencing of Elburgon social hall equipped | 3110599 | Other Infrastructure and Civil Works | MOLO | ELBURGON | -0.307065 35.810187 2407.60009765625 27.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 16 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: PETMAT LTD. Assessor remarks: Ongoing.
9598 | Administration, Planning and support services | construction of Kiptangwanyi social hall | To construct Kiptangwanyi social hall | Kiptangwanyi social hall constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | ELEMENTAITA | -0.563416 36.116992 1960.699951171875 0.6940000057220459 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9599 | Administration, Planning and Support Services | Completion of Kimathi football dressing room | To complete Kimathi football dressing room | Kimathi football dressing room completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303692 36.07859 1814.5 4.699999809265137 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 1,485,500 | 1500000 | 0 | 0 | 0 | 0 | 1320 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Callbest logistics. Assessor remarks: Complete.
9600 | Administration, Planning and support services | AGPO youth development | To implement agpo youth development for youth empowerment and social inclusion | AGPO youth development completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | HELLS GATE | -0.77815 36.429658 1909.5999755859375 16.07900047302246 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: At a cost of 1,000,000.
9601 | Administration, Planning and Support Services | Construction of 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center | To construct 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center | 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | 2,439,980 | 2500000 | 0 | 0 | 0 | 0 | 1838 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
9602 | Administration, Planning and Support Services | Construction of social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center | To construct social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center | Social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 3645259 | 8145259 | 8145259 | Equitable | - | 8145259 | 0 | 788 | 0 | 788 | 1311 | 8144471 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
9603 | Administration, Planning and support services | equipping of Kiptangich Social Hall | To equip Kiptangich Social Hall with necessary facilities and equipment | Kiptangich Social Hall equipped | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.572849, 35.613061 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | Not yet started | 999944 | 999943 | 999943 | Equitable | 999,300 | 999943 | 0 | 0 | 0 | 0 | 29036 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started. Contractor: Don't know.
9604 | Administration, Planning and Support Services | construction of a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | To construct a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | A sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.29986, 36.084106 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 0 | 10500000 | 10500000 | Equitable | 252,416 | 10500000 | 0 | 0 | 0 | 0 | 11803 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9605 | Administration, Planning and Support Services | Construction of 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center | To construct 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center | 6 door stardard toilet disabilities friendly and construction of underground water tank 100,000 litres and installation of raised water tanlk 10,000 litres in kaptembwo resourse center constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | 2,439,980 | 2500000 | 0 | 0 | 0 | 0 | 1838 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
9606 | Administration, Planning and Support Services | Construction of social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center | To construct social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center | Social hall capacity minimum 500 people,innovative hub and music recording studio room, Construction of perimeter wall with razor wire and installation of standard gate and Equipping of social hall in kaptembwo resourse center constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 3645259 | 8145259 | 8145259 | Equitable | - | 8145259 | 0 | 788 | 0 | 788 | 1311 | 8144471 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
9607 | Administration, Planning and Support Services | installation of Chain link fence and gate in the resource center at sewage village | To install Chain link fence and gate in the resource center at sewage village | Chain link fence and gate in the resource center at sewage village installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.319271, 36.052208 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | Dec2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 13330 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Loscatoh.
9608 | Administration, Planning and Support Services | Construction of kuresoi social hall | To construct kuresoi social hall | Kuresoi social hall constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.300887, 35.53313 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | 2,908,870 | 3000000 | 0 | 0 | 0 | 0 | 1329 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9609 | Administration, Planning and Support Services | construction of a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | To construct a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | A sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.29986, 36.084106 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 8133044 | 8133044 | 8133044 | Equitable | 252,416 | 8133044 | 0 | 0 | 0 | 0 | 11803 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
9610 | Administration, Planning and support services | Kasarani social hall | To implement kasarani social hall for youth empowerment and social inclusion | Kasarani social hall completed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703 36.309037 0 2000 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2015/16 | 2015/16 | N/A | 1500000 | 2500000 | 2500000 | Equitable | 2,499,720 | 2500000 | 0 | 0 | 0 | 0 | 335 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
9611 | Renovation of Molo Social Hall, Electricity Connection and equipping | Renovation of Molo Social Hall, Electricity Connection and equipping | To rehabilitate Molo Social Hall, Electricity Connection and equipping to restore functionality | Molo Social Hall, Electricity Connection and equipping rehabilitated | 3110599 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9612 | Administration, Planning and Support Services | Completion of Fencing of maai mahiu social hall | To complete Fencing of maai mahiu social hall | Fencing of maai mahiu social hall completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | - | 1500000 | 0 | 789 | 0.1 | 789 | 0 | 1499211 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9613 | Administration, Planning and support services | Equipping of kasarani social hall and shade extention for darts,pool table and chess | To equip kasarani social hall and shade extention for darts,pool table and chess with necessary facilities and equipment | Kasarani social hall and shade extention for darts,pool table and chess equipped | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The equipping is to go on.
9614 | Administration, Planning and support services | Kasarani social hall | To implement kasarani social hall for youth empowerment and social inclusion | Kasarani social hall completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.309037 0 2000 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2015/16 | 2015/16 | N/A | 1500000 | 2500000 | 2500000 | Equitable | 2,499,720 | 2500000 | 0 | 0 | 0 | 0 | 335 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
9615 | Administration, Planning and support services | Youth empowerment projects in Mariashoni ward | To implement youth empowerment projects in mariashoni ward for youth empowerment and social inclusion | Youth empowerment projects in Mariashoni ward completed | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | 999,999 | 1000000 | 0 | 0 | 0 | 0 | 42286 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
9616 | Administration, Planning and support services | Purchase and supply of a 100 seater tent and 100 chairs | To procure and supply a 100 seater tent and 100 chairs | A 100 seater tent and 100 chairs procured and supplied | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.497747 35.960893 2477.6000000000004 12.399999618530273 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 291357 | 291357 | 291357 | Equitable | 290,995 | 291357 | 0 | 0 | 0 | 0 | 42281 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9617 | Administration, Planning and support services | Supply of indoor games equipment at menengai social hall and supply of outside sitting benches | To implement supply of indoor games equipment at menengai social hall and supply of outside sitting benches for youth empowerment and social inclusion | Supply of indoor games equipment at menengai social hall and supply of outside sitting benches completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275602 36.11133 1860.199951171875 20 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 467090 | 467090 | 467090 | Equitable | 1,499,856 | 467090 | 0 | 0 | 0 | 0 | 42281 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9618 | Administration, Planning and support services | youth empowerment ( supply of motor bikes for menengai boda boda | To implement youth empowerment ( supply of motor bikes for menengai boda boda for youth empowerment and social inclusion | youth empowerment ( supply of motor bikes for menengai boda boda completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.271411 36.111322 1863.5 14.951000213623047 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 1,499,856 | 1500000 | 0 | 0 | 0 | 0 | 42281 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9619 | Administration, Planning and Support Services | Completion of youths center at kiamunyi | To complete youths center at kiamunyi | Youths center at kiamunyi completed | 3110599 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.166762 36.007934 0 600 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,725,210 | 2000000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
9620 | Administration, Planning and support services | Completion of a Resource Centre at hadassa in mwariki | To complete a Resource Centre at hadassa in mwariki | A Resource Centre at hadassa in mwariki completed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.313656, 36.067306 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 19/20 | 6000000 | 6000000 | 6000000 | Equitable | - | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
9621 | Administration, Planning and Support Services | Construction of Toilet ,changing room and shade at mwariki playing ground | To construct Toilet ,changing room and shade at mwariki playing ground | Toilet ,changing room and shade at mwariki playing ground constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.315828, 36.063965 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 19/20 | 2000000 | 2000000 | 2000000 | Equitable | 1,999,900 | 2000000 | 0 | 0 | 0 | 0 | 1319 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N/a. Viable: N/a. Contractor: N/a.
9622 | Administration, Planning and support services | Equipping of Kwa amos Social Hall | To equip Kwa amos Social Hall with necessary facilities and equipment | Kwa amos Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Bahati | Kabatini | -0.232118, 36.147754 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2021 | 500000 | 500000 | 500000 | Equitable | 500,000 | 500000 | 0 | 0 | 0 | 0 | 41790 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9623 | Administration, Planning and support services | purchase of sport equipment - Sports uniforms,balls,nets in kiptororo ward | To procure sport equipment - Sports uniforms,balls,nets in kiptororo ward | Sport equipment - Sports uniforms,balls,nets in kiptororo ward procured | 3111109 | Purchase of Educational Aids and Related Equipment | Kuresoi North | Kiptororo | -0.381148 35.503821 2529.1 12.100000381469727 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,999,800 | 2000000 | 0 | 0 | 0 | 0 | 37896 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Stalled, captured in fy 2016/17 was also captured in the FY 2015/16.
9624 | Administration, Planning and support services | Maai mahiu Art and culture - purchase of studio / theatre equipments for maai mahiu social hall | To implement maai mahiu art and culture - purchase of studio / theatre equipments for maai mahiu social hall for youth empowerment and social inclusion | Maai mahiu Art and culture - purchase of studio / theatre equipments for maai mahiu social hall completed | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | MAAI MAHIU | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,970,000 | 2000000 | 0 | 0 | 0 | 0 | 29037 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9625 | Administration, Planning and Support Services | Equipping of Menengai Social Hall | To equip Menengai Social Hall with necessary facilities and equipment | Menengai Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAKURU EAST | MENENGAI | -0.275724, 36.115352 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9626 | Administration, Planning and support services | Sports Enhancement - Purchase of Sports Equipment for the Olive Inn Mercy Njeri football and Volley Ball teams | To implement sports enhancement - purchase of sports equipment for the olive inn mercy njeri football and volley ball teams for youth empowerment and social inclusion | Sports Enhancement - Purchase of Sports Equipment for the Olive Inn Mercy Njeri football and Volley Ball teams completed | 3111109 | Purchase of Educational Aids and Related Equipment | RONGAI | MENENGAI WEST | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 500000 | 500000 | 500000 | Equitable | 499,650 | 500000 | 0 | 0 | 0 | 0 | 29411 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9627 | Administration, Planning and Support Services | Equipping of Menengai Social Hall | To equip Menengai Social Hall with necessary facilities and equipment | Menengai Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Menengai | -0.275724, 36.115352 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9628 | Administration, Planning and support services | Constuction of toilet at piave center market | To implement constuction of toilet at piave center market for youth empowerment and social inclusion | Constuction of toilet at piave center market completed | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Njoro | -0.338683, 35.994005 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | 995,970 | 1000000 | 0 | 0 | 0 | 0 | 1303 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Contractor: great rift merchants.
9629 | Administration, Planning and support services | purchase of sports equipments | To procure sports equipments | Sports equipments procured | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Njoro | -0.332084 35.954071 2142.400146484375 15.730999946594238 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1018462 | 1018462 | 1018462 | Equitable | 1,002,000 | 1018462 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch designers. Assessor remarks: Well done understaking.
9630 | Administration, Planning and support services | Purchase of sport equipment for youths (Youth empowerment programme) | To procure sport equipment for youths (Youth empowerment programme) | Sport equipment for youths (Youth empowerment programme) procured | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | OLKARIA | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,998,890 | 2000000 | 0 | 0 | 0 | 0 | 90 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
9631 | Administration, Planning and support services | Purchase of sport equipment for youths (Youth empowerment programme) | To procure sport equipment for youths (Youth empowerment programme) | Sport equipment for youths (Youth empowerment programme) procured | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 1998890 | 1998890 | Equitable | 1,998,890 | 1998890 | 0 | 0 | 0 | 0 | 90 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
9632 | Administration, Planning and Support Services | Purchase of sports equipment | To procure sports equipment | Sports equipment procured | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 90 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
9633 | Administration, Planning and support services | Equipping of Rongai social hall | To equip Rongai social hall with necessary facilities and equipment | Rongai social hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | RONGAI | VISOI | -0.173053 35.86075 1861.5999755859375 10.399999618530273 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 300000 | 300000 | 300000 | Equitable | 300,000 | 300000 | 0 | 0 | 0 | 0 | 332 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9634 | Administration, Planning and support services | Equipping of Rongai social hall | To equip Rongai social hall with necessary facilities and equipment | Rongai social hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Visoi | -0.173053 35.86075 1861.5999755859375 10.399999618530273 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 300000 | 300000 | 300000 | Equitable | 300,000 | 300000 | 0 | 0 | 0 | 0 | 332 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9635 | Administration, Planning and support services | Youth empowerment (car wash machines and tanks) | To implement youth empowerment (car wash machines and tanks) for youth empowerment and social inclusion | Youth empowerment (car wash machines and tanks) completed | 3111120 | Purchase of Specialized Plant. - | Gilgil | Eburru-Mbaruk | N/A | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 727717 | 727717 | 727717 | Equitable | 678,000 | 727717 | 0 | 0 | 0 | 0 | 41789 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9636 | Administration, Planning and support services | Gilgil youth empowerment car wash machines | To implement gilgil youth empowerment car wash machines for youth empowerment and social inclusion | Gilgil youth empowerment car wash machines completed | 3111120 | Purchase of Specialized Plant. - | GILGIL | GILGIL | -0.503893 36.327129 1989.300048828125 76.23400115966797 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | 599,900 | 600000 | 0 | 0 | 0 | 0 | 300 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dumack enterprises. Assessor remarks: In good state.
9637 | Administration, Planning and support services | Purchase and supply of car wash machines with tanks | To procure and supply car wash machines with tanks | Car wash machines with tanks procured and supplied | 3111120 | Purchase of Specialized Plant. - | Gilgil | Gilgil | -0.509335 36.317226 2005.0999755859375 5.428999900817871 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | 996,800 | 1000000 | 0 | 0 | 0 | 0 | 37886 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Elias company limited. Assessor remarks: Road needs maintainance.
9638 | Administration, Planning and support services | Purchase and installation of car wash machines (Youth Empowerment) | To procure and install car wash machines (Youth Empowerment) | Car wash machines (Youth Empowerment) procured and installed | 3111120 | Purchase of Specialized Plant. - | BAHATI | KABATINI | -0.231538 36.148472 1944.5 44.513999938964844 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | 998,000 | 1000000 | 0 | 0 | 0 | 0 | 301 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9639 | Administration, Planning and support services | Purchase and supply of boda boda umbrellas | To procure and supply boda boda umbrellas | Boda boda umbrellas procured and supplied | 3111120 | Purchase of Specialized Plant. - | Molo | Mariashoni | -0.394087 35.76988 2911.0147396230864 11.5 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | 499,750 | 500000 | 0 | 0 | 0 | 0 | 37895 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9640 | Administration, Planning and support services | Empowerment of youths (car wash machines and tanks) | To implement empowerment of youths (car wash machines and tanks) for youth empowerment and social inclusion | Empowerment of youths (car wash machines and tanks) completed | 3111120 | Purchase of Specialized Plant. - | Rongai | Menengai West | -0.167583 36.011952 1897.699951171875 24.195999145507812 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1044597 | 1044597 | 1044597 | Equitable | 980,000 | 1044597 | 0 | 0 | 0 | 0 | 41772 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Not started.
9641 | Administration, Planning and support services | Youth empowerment(purchase of car washing machines and water tanks) | To implement youth empowerment(purchase of car washing machines and water tanks) for youth empowerment and social inclusion | Youth empowerment(purchase of car washing machines and water tanks) completed | 3111120 | Purchase of Specialized Plant. - | Molo | Turi | -0.330008 35.687633 2765.800048828125 39.599998474121094 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 610066 | 610066 | 610066 | Equitable | 610,000 | 610066 | 0 | 0 | 0 | 0 | 41790 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Both the fence and the gate house were vandalised.
9642 | Administration, Planning and support services | Viwandani social hall completion - completion of Viwandani social hall and construction of a toilet | To implement viwandani social hall completion - completion of viwandani social hall and construction of a toilet for youth empowerment and social inclusion | Viwandani social hall completion - completion of Viwandani social hall and construction of a toilet completed | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.708377, 36.432697 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | 2,999,000 | 3000000 | 0 | 0 | 0 | 0 | 11886 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
9643 | Administration, Planning and Support Services | Purchase of Land for social hall in Barut Ward | To acquire land for social hall in Barut Ward | Land for social hall in Barut Ward acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.324324, 36.054632 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2017 | 2000000 | 2000000 | 2000000 | Equitable | 2,000,000 | 2000000 | 0 | 0 | 0 | 0 | 836 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No.
9644 | Administration, Planning and Support Services | Purchase of manyere football pitch | To procure manyere football pitch | Manyere football pitch procured | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.34908, 36.056053 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 4000000 | 7200000 | 7200000 | Equitable | - | 7200000 | 0 | 0 | 0 | 0 | 837 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: RODI OREGE AND CO ADVOCATES.
9645 | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet | To implement athletes complex - purchase of 30 acres of land for establishing a sports centre at keringet for youth empowerment and social inclusion | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet completed | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2017/18 | 15000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9646 | Administration, Planning and support services | Kamara social hall - purchase of land for kamara social hall | To implement kamara social hall - purchase of land for kamara social hall for youth empowerment and social inclusion | Kamara social hall - purchase of land for kamara social hall completed | 3130101 | Acquisition of Land | KURESOI NORTH | KAMARA | -0.168763 35.689192 2508 7.900000095367432 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Land not bought.
9647 | Completion of London social hall | Completion of London social hall | To complete London social hall | London social hall completed | 4130299 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO 4576 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 6800000 | 0 | 100000 | N/A | N/A | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9648 | Naivasha Municipal Services | Conditional Fund -Kenya Urban Support Project (KUSP) | To implement conditional fund -kenya urban support project (kusp) for improved service delivery | Conditional Fund -Kenya Urban Support Project (KUSP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 740767800 | 529825868 | 0 | Conditional Grant | Conditional Grant | 0 | 639223993.36 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9649 | Naivasha Municipal Services | Conditional Fund -Kenya Urban Support Project (KUSP) | To implement conditional fund -kenya urban support project (kusp) for improved service delivery | Conditional Fund -Kenya Urban Support Project (KUSP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO 4578 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 344075500 | 246096144.98 | 0 | Conditional Grant | Conditional Grant | 0 | 296909861.22 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9650 | Transfers to County Emergency Fund Account as Per Section 110 of the Public Finance Management Act 2012 | Transfers to County Emergency Fund Account as Per Section 110 of the Public Finance Management Act 2012 | To implement transfers to county emergency fund account as per section 110 of the public finance management act 2012 for improved service delivery | Transfers to County Emergency Fund Account as Per Section 110 of the Public Finance Management Act 2012 completed | 2810205 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO D 01 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2018/19 | 2018/2019 | 2018/2019 | 57250000 | 57250000 | 35000000 | N/A | N/A | 35000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9651 | Administration, Planning and Support Services | Construction of official residence for the Deputy Governor | To construct official residence for the Deputy Governor | Official residence for the Deputy Governor constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | N/A | VOTE NO D 01 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2018/19 | 2018/2019 | N/A | 30000000 | 30000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 20000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9652 | Administration, Planning and Support Services | Construction of Sub County's Office | To construct Sub County's Office | Sub County's Office constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO D 01 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2018/19 | 2018/2019 | 2018/2019 | 16605318 | 16605318 | 16605318 | Equitable | N/A | 16605318 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9653 | Completion of renovations to Board offices at the Public Works building | Completion of renovations to Board offices at the Public Works building | To complete renovations to Board offices at the Public Works building | Renovations to Board offices at the Public Works building completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO D 03 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2017/18 | 2017/18 | 2017/18 | 3497152 | 3497152 | 3497152 | N/A | N/A | 3497152 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9654 | Partition and rehabilitate two additional board offices at the Provincial Public Works Building | Partition and rehabilitate two additional board offices at the Provincial Public Works Building | To implement partition and rehabilitate two additional board offices at the provincial public works building for improved service delivery | Partition and rehabilitate two additional board offices at the Provincial Public Works Building completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO D 03 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2018/19 | 2018/2019 | 2018/2019 | 908376 | 908376 | 908376 | N/A | N/A | 908376 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9655 | County Coordination of Policy formulation | Construction of Kiptangwanyi ward administration block | To construct Kiptangwanyi ward administration block | Kiptangwanyi ward administration block constructed | 3110299 | Construction of Buildings - Ot | GILGIL | ELEMENTAITA | -0.567447, 36.114695 | VOTE NO D 04 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/2019 | 2018/2019 | 2000000 | 2000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 7315640 | 365.8 | 7315640 | 7326940 | -5315640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9656 | County Coordination of Policy formulation | Construction of Sub County Offices | To construct Sub County Offices | Sub County Offices constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO D 04 | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | MINISTRY OF PUBLIC SERVICE, TRAINING AND DEVOLUTION | N/A | 2018/19 | 2018/2019 | 2018/2019 | 40000000 | 25000000 | 25000000 | N/A | N/A | 25000000 | 0 | 685374 | 2.7 | 685374 | 2941084 | 24314626 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9657 | Valuation of Assets | Valuation of Assets | To implement valuation of assets for improved service delivery | Valuation of Assets completed | 2211310 | Contracted Professional Services | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2018/2019 | 2018/2019 | 50000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9658 | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | To implement county debt management (as per the county medium term debt management strategy paper) for improved service delivery | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2018/2019 | 2018/2019 | 400000000 | 189730000 | 188453842 | N/A | N/A | 188453842 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9659 | Construction of County Treasury | Construction of County Treasury | To construct County Treasury | County Treasury constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2020/2021 | 2020/2021 | 150000000 | 40000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9660 | Purchase of an automatic generator for County HQ | Purchase of an automatic generator for County HQ | To procure an automatic generator for County HQ | An automatic generator for County HQ procured | 3111110 | Purchase of Generators | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2017/18 | 2017/19 | 2017/19 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9661 | 4.5% Admin Cost Of Revenue Administration System (ZIZI) | 4.5% Admin Cost Of Revenue Administration System (ZIZI) | To implement 4.5% admin cost of revenue administration system (zizi) for improved service delivery | 4.5% Admin Cost Of Revenue Administration System (ZIZI) completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2018/2019 | 2018/2019 | 50000000 | 0 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9662 | Development of Revenue Management System | Development of Revenue Management System | To develop Revenue Management System | Revenue Management System developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D 02 | MINISTRY OF FINANCE AND ECONOMIC PLANNING | MINISTRY OF FINANCE AND ECONOMIC PLANNING | N/A | 2018/19 | 2018/2019 | 2018/2019 | 100000000 | 40000000 | 40000000 | N/A | N/A | 40000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9663 | Preventive and Promotive Health Services | Capital Transfers to Health Centres and Dispensaries | To implement capital transfers to health centres and dispensaries for access to quality healthcare services | Capital Transfers to Health Centres and Dispensaries completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 36322032 | 14141275 | 0 | Grant | Grant | 0 | 14141275 | 20068710 | 141.9 | 20068710 | 19115250 | -5927435 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9664 | Health Curative and Rehabilitative Services | Conditional Fund for Leasing of Medical Equipment | To implement conditional fund for leasing of medical equipment for access to quality healthcare services | Conditional Fund for Leasing of Medical Equipment completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 200000000 | 200000000 | 0 | Grant | Grant | 0 | 200000000 | 124723404 | 62.4 | 124723404 | 0 | 75276596 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9665 | Preventive and Promotive Health Services | DANIDA Capital Transfers to Health Centres and Dispensaries | To implement danida capital transfers to health centres and dispensaries for access to quality healthcare services | DANIDA Capital Transfers to Health Centres and Dispensaries completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 31083750 | 31083750 | 0 | Grant | Grant | 0 | 31083750 | 20068710 | 64.6 | 20068710 | 19115250 | 11015040 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9666 | Health Curative and Rehabilitative Services | Other Developments (Facility Improvement Fund) | To implement other developments (facility improvement fund) for access to quality healthcare services | Other Developments (Facility Improvement Fund) completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 0 | Equitable | N/A | 0 | 5000000 | 10122860 | 202.5 | 10122860 | 70000000 | -5122860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9667 | Preventive and Promotive Health Services | World Bank Transforming Health Systems for Universal Care (THS-UC) | To implement development programme activities under World Bank Transforming Health Systems for Universal Care (THS-UC) | Programme activities completed | 2630201 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 95036351 | 95036351 | 0 | Grant | Grant | 0 | 95036351 | 79342370 | 83.5 | 79342370 | 62835 | 15693981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9668 | Preventive and Promotive Health Services | Completion and equipping of Sinendet dispensary | To complete and equip Sinendet dispensary | Sinendet dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.676255 35.657373 2458.322998046875 8.564000129699707 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999770 | 100 | 999770 | 230 | 230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: done.
9669 | Preventive and Promotive Health Services | Construction of staff houses at Kaplambai Dispensary | To construct staff houses at Kaplambai Dispensary | Staff houses at Kaplambai Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 999073 | 66.6 | 999073 | 927 | 500927 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
9670 | Preventive and Promotive Health Services | Construction of toilets at Kaplambai Dispensary | To construct toilets at Kaplambai Dispensary | Toilets at Kaplambai Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999073 | 99.9 | 999073 | 927 | 927 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
9671 | Preventive and Promotive Health Services | Design and Construction of out patient department at Wangu Dispensary | To design and construct out patient department at Wangu Dispensary | Out patient department at Wangu Dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000004 | 100 | 3000004 | 0 | -4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9672 | Preventive and Promotive Health Services | renovation and re- roofing of mithonge clinic ( Mithonge clinic) | To rehabilitate re- roofing of mithonge clinic ( Mithonge clinic) to restore functionality | Re- roofing of mithonge clinic ( Mithonge clinic) rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | -0.290679, 36.081191 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dopelight company. Assessor remarks: Needs renovation once more.
9673 | Preventive and Promotive Health Services | Construction of Githioro dispensary | To construct Githioro dispensary | Githioro dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.273677, 36.201615 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2017/2018 | 2017/2018 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 8096028 | 81 | 8096028 | 1751092 | 1903972 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
9674 | Preventive and Promotive Health Services | Construction of MCH at Kiwamu Health Centre | To construct MCH at Kiwamu Health Centre | MCH at Kiwamu Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.237345, 36.167237 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 4203337 | 210.2 | 4203337 | 1288168 | -2203337 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
9675 | Preventive and Promotive Health Services | fencing of Githioro dispensary | To secure Githioro dispensary through fencing | Githioro dispensary fenced and secured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.273677, 36.201615 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 10000001 | 0 | 2240000 | Equitable | N/A | 2240000 | 0 | 2199140 | 0 | 2199140 | 1751092 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
9676 | Preventive and Promotive Health Services | Kiwamu Health centre | To implement kiwamu health centre for access to quality healthcare services | Kiwamu Health centre completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.237045, 36.167621 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1156431.8 | 1156432 | 1156432 | Equitable | Ward Fund | 1156432 | 0 | 4203337 | 363.5 | 4203337 | 1000000 | -3046905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9677 | Preventive and Promotive Health Services | Construction of Orjorai Health Centre | To construct Orjorai Health Centre | Orjorai Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1199840 | 60 | 1199840 | 300000 | 800160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9678 | Preventive and Promotive Health Services | Completion of Kongasis Maternity | To complete Kongasis Maternity | Kongasis Maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURU-MBARUK | -0.554624, 36.153051 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 18-19 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: It was well done.
9679 | Preventive and Promotive Health Services | Completion of Arimi Dispensary | To complete Arimi Dispensary | Arimi Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.272217 35.816592 2382.3 13.600000381469727 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 515700 | 51.6 | 515700 | 1000000 | 484300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9680 | Preventive and Promotive Health Services | Construction of Kapsita Dispensary | To construct Kapsita Dispensary | Kapsita Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.294954 35.766447 0 2799.9990234375 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9681 | Preventive and Promotive Health Services | Completion of Satewa Dispensary | To complete Satewa Dispensary | Satewa Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.272217 35.816592 2382.3 13.600000381469727 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9682 | Preventive and Promotive Health Services | construction of toilets and fence and Completion and equipping of Mwangi Michuki Dispensary | To construct toilets and fence and Completion and equipping of Mwangi Michuki Dispensary | Toilets and fence and Completion and equipping of Mwangi Michuki Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.258464, 35.763718 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | - | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
9683 | Preventive and Promotive Health Services | Equipping of Mwangi Michuki (Mutamaiyu dispensary) | To equip Mwangi Michuki (Mutamaiyu dispensary) with necessary facilities and equipment | Mwangi Michuki (Mutamaiyu dispensary) equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.210282 35.784866 0 899.9990234375 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 800001 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 499980 | 0 | 499980 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good use.
9684 | Preventive and Promotive Health Services | Construction of Maternity Wing at Kiambogo dispensary | To construct Maternity Wing at Kiambogo dispensary | Maternity Wing at Kiambogo dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.591532, 36.127211 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4483308 | 4483308 | 4483308 | Equitable | N/A | 4483308 | 0 | 4483308 | 100 | 4483308 | 90 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maternity in use.
9685 | Preventive and Promotive Health Services | Construction of Miti Mingi dispensary | To construct Miti Mingi dispensary | Miti Mingi dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.516888, 36.112608 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | Ward Fund | 4000000 | 0 | 3991670 | 99.8 | 3991670 | 114973 | 8330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use..
9686 | Preventive and Promotive Health Services | Design and Construction of Munanda Dispensary | To design and construct Munanda Dispensary | Munanda Dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.596406, 36.111984 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 1041801.4 | 1041801.4 | Equitable | Ward Fund | 1041801.4 | 0 | 409863 | 39.3 | 409863 | 90 | 631938.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9687 | Preventive and Promotive Health Services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary | To implement kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary for access to quality healthcare services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.602163, 36.131095 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4500000 | 4500000 | 4500000 | Equitable | Ward Fund | 4500000 | 0 | 3272817 | 72.7 | 3272817 | 727214 | 1227183 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good working conditions..
9688 | Preventive and Promotive Health Services | Munanda Dispensary - Design and Construction of toilets | To implement munanda dispensary - design and construction of toilets for access to quality healthcare services | Munanda Dispensary - Design and Construction of toilets completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.596053, 36.112725 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499960 | 100 | 499960 | 0 | 40 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9689 | Preventive and Promotive Health Services | Equipping of Gilgil Sub-county hospital theater | To equip Gilgil Sub-county hospital theater with necessary facilities and equipment | Gilgil Sub-county hospital theater equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.504154, 36.32303 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 921158 | 46.1 | 921158 | 3206220 | 1078842 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9690 | Preventive and Promotive Health Services | Equipping of Karura dispensary | To equip Karura dispensary with necessary facilities and equipment | Karura dispensary equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.503966 36.32263 1991.4000244140625 20 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Needs additional equipment.
9691 | Preventive and Promotive Health Services | Construction of Maternity Edilong Hospital(Bondeni) | To construct Maternity Edilong Hospital(Bondeni) | Maternity Edilong Hospital(Bondeni) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 15000000 | 11015324 | 11015324 | Equitable | N/A | 11015324 | 0 | 750000 | 6.8 | 750000 | 9890259 | 10265324 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9692 | Preventive and Promotive Health Services | Construction and equipping of Muriundu Dispensary | To construct and equip Muriundu Dispensary | Muriundu Dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.231827, 36.15519 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2483264 | 99.3 | 2483264 | 2500000 | 16736 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomwaco limited. Assessor remarks: Operational.
9693 | Preventive and Promotive Health Services | Expansion and equipping of Muriundu Dispensary | To expand and equipping of Muriundu Dispensary to increase capacity | And equipping of Muriundu Dispensary expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.231827, 36.15519 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2018 | 1000126.4 | 1000126 | 1000126 | Equitable | Ward Fund | 1000126 | 0 | 1999991 | 200 | 1999991 | 2500000 | -999865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomwaco limited. Assessor remarks: Operational.
9694 | Preventive and Promotive Health Services | Expansion and equipping of Ruguru Dispensary | To expand and equipping of Ruguru Dispensary to increase capacity | And equipping of Ruguru Dispensary expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.165201, 36.177493 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1999991 | 100 | 1999991 | 2500000 | 9 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No yet. Viable: Yes. Assessor remarks: It's ongoing at 70% renovation done , Equipping not yet done.
9695 | Preventive and Promotive Health Services | construction of upper solai health centre - construction of upper solai health centre | To construct upper solai health centre - construction of upper solai health centre | Upper solai health centre - construction of upper solai health centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.077923 36.171018 0 215.28369140625 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vertex general supplies and construction enterprises ltd. Assessor remarks: Requires equipping.
9696 | Preventive and Promotive Health Services | Renovation of Kirima Dispensary | To rehabilitate Kirima Dispensary to restore functionality | Kirima Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.158043 36.079285 1879 4.699999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599540 | 99.9 | 599540 | 0 | 460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Njega investment ltd. Assessor remarks: To be operationalized.
9697 | Preventive and Promotive Health Services | completion of Kamara Health Centre | To complete Kamara Health Centre | Kamara Health Centre completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.096473 35.680083 2504.1 7.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 271597 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs re-painting.
9698 | Preventive and Promotive Health Services | Proposed Construction of Rironi Health centre | To undertake the proposed Construction of Rironi Health centre | Proposed Construction of Rironi Health centre implemented | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.1811, 35.712733 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 1766373 | 55.2 | 1766373 | 271597 | 1433627 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it didn't meet the needs. Contractor: Unknown. Assessor remarks: Project needs to be completed operationalised.
9699 | Preventive and Promotive Health Services | Completion and equiping of Kapkures Maternity wing | To complete and equiping of Kapkures Maternity wing | And equiping of Kapkures Maternity wing completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.310643, 36.038628 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2941998.6 | 2941999 | 2941999 | Equitable | N/A | 2941999 | 0 | 1798260 | 61.1 | 1798260 | 7680 | 1143739 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: Sageo investment. Assessor remarks: Well implimented.
9700 | Preventive and Promotive Health Services | design and Construction of the Ingobor health Centre | To design and construct the Ingobor health Centre | The Ingobor health Centre designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.305507, 36.017053 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 4500000 | 4500000 | 4500000 | Equitable | Ward Fund | 4500000 | 0 | 2499590 | 55.5 | 2499590 | 5 | 2000410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: well implemented and in use.
9701 | Preventive and Promotive Health Services | Construction of outpatient unit at Bararget dispensary | To construct outpatient unit at Bararget dispensary | Outpatient unit at Bararget dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.485712, 35.72451 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2023 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 432793 | 36.1 | 432793 | 250000 | 767207 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Incremental fund.
9702 | Preventive and Promotive Health Services | Construction of general ward and staff house at Keringet sub county hospital | To construct general ward and staff house at Keringet sub county hospital | General ward and staff house at Keringet sub county hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.426253, 35.68717 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 636411 | 31.8 | 636411 | 2000000 | 1363589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good and in use.
9703 | Preventive and Promotive Health Services | equipping of Mwangate dispensary | To equip Mwangate dispensary with necessary facilities and equipment | Mwangate dispensary equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.446063 35.637432 2561 11.199999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299850 | 100 | 299850 | 11099 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Yes.
9704 | Preventive and Promotive Health Services | Refurbishment of Chebara Dispensary | To implement refurbishment of chebara dispensary for access to quality healthcare services | Refurbishment of Chebara Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.47732, 35.679745 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2033 | 810000 | 810000 | 810000 | Equitable | N/A | 810000 | 0 | 798901 | 98.6 | 798901 | 11099 | 11099 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9705 | Preventive and Promotive Health Services | Refurbishment of Kapsimbeiywo Dispensary | To implement refurbishment of kapsimbeiywo dispensary for access to quality healthcare services | Refurbishment of Kapsimbeiywo Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.485835, 35.724327 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019 | 1330000 | 1330000 | 1330000 | Equitable | Ward Fund | 1330000 | 0 | 798901 | 60.1 | 798901 | 11099 | 531099 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work done.
9706 | Preventive and Promotive Health Services | Design and Construction of outpatient block | To design and construct outpatient block | Outpatient block designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.259097, 36.134247 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999132 | 100 | 1999132 | 0 | 868 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project requires renovation.
9707 | Preventive and Promotive Health Services | Renovation And Completion Of Menengai Dispensary | To rehabilitate Completion Of Menengai Dispensary to restore functionality | Completion Of Menengai Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.26831 36.107544 1876.699951171875 18.882999420166016 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 747896 | 747896 | 747896 | Equitable | Ward Fund | 747896 | 0 | 2000000 | 267.4 | 2000000 | 0 | -1252104 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project not in use.
9708 | Preventive and Promotive Health Services | Engashura Health Centre | To implement engashura health centre for access to quality healthcare services | Engashura Health Centre completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.258538 36.134637 1891.9000244140625 64.0999984741211 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | 2014/15 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Contractor on site.
9709 | Preventive and Promotive Health Services | Completion of a maternity Wing at Emitik Dispensary | To complete a maternity Wing at Emitik Dispensary | A maternity Wing at Emitik Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.623475, 35.603692 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2018 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1021185 | 51.1 | 1021185 | 899416 | 978815 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable and it meets the needs of the residents. Contractor: Spider. Assessor remarks: The project is complete and functional.
9710 | Preventive and Promotive Health Services | Construction of Kiplembeiyo Dispensary | To construct Kiplembeiyo Dispensary | Kiplembeiyo Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.534595 35.578933 2463.8 54.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1021185 | 34 | 1021185 | 3562 | 1978815 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: There is no electricity and gate..
9711 | Preventive and Promotive Health Services | design and construction of Chebotoi dispensary | To design and construct Chebotoi dispensary | Chebotoi dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.553555, 35.636309 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | It stalled | 4000000 | 4000000 | 3600000 | Equitable | Ward Fund | 3600000 | 0 | 2183050 | 54.6 | 2183050 | 1416950 | 1816950 | Stalled | 25 | 54.6 | More funds required to put up a new block | 2017 | N/A | 1816950 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but the needs of the residents are not met. Contractor: AI contrators. Assessor remarks: The project stalled and it is vandalized.
9712 | Preventive and Promotive Health Services | Construction of 3 no. Consultation room at Kongoi Dispensary | To construct 3 no. Consultation room at Kongoi Dispensary | 3 no. Consultation room at Kongoi Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.322344, 35.54414 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1554159 | 77.7 | 1554159 | 3000000 | 445841 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: It is not operational,there is no toilet at the facility ..
9713 | Preventive and Promotive Health Services | Construction Of Consultation Rooms In Kiptororo Dispensary | To construct Consultation Rooms In Kiptororo Dispensary | Consultation Rooms In Kiptororo Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.377203, 35.505747 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1554159 | 51.8 | 1554159 | 3000000 | 1445841 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The 3 rooms are incomplete,it requires good roofing plastering painting and fiting of window pane.
9714 | Preventive and Promotive Health Services | Construction Of Murinduko Dispensary | To construct Murinduko Dispensary | Murinduko Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.322428 35.543765 2615.219 3.438999891281128 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4084035 | 4084035 | 4084035 | Equitable | N/A | 4084035 | 0 | 1554159 | 38.1 | 1554159 | 352647 | 2529876 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Kongoi dispensary lacks sanitary facility ,fence and staff house.
9715 | Preventive and Promotive Health Services | Murinduko Dispensary-Maternity Wing - On Going | To implement murinduko dispensary-maternity wing - on going for access to quality healthcare services | Murinduko Dispensary-Maternity Wing - On Going completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.3246 35.498852 2546.3 22.100000381469727 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 3200000 | 3200000 | Equitable | Ward Fund | 3200000 | 0 | 948599 | 29.6 | 948599 | 0 | 2251401 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project is not functioning.
9716 | Preventive and Promotive Health Services | Construction of Health Centre | To construct Health Centre | Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.753474, 36.461966 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 860888.9 | 860889 | 860889 | Equitable | Ward Fund | 860889 | 0 | 467243 | 54.3 | 467243 | 2770 | 393646 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state of repair.
9717 | Preventive and Promotive Health Services | Design and construction of Umoja dispensary | To design and construct Umoja dispensary | Umoja dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | LANET UMOJA | -0.281344, 36.174332 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 2992156 | 99.7 | 2992156 | 0 | 7844 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes very viable. Assessor remarks: Renamed to Nyonjoro Health Center , functional.
9718 | Preventive and Promotive Health Services | Completion of Kapyemet Dispensary | To complete Kapyemet Dispensary | Kapyemet Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
9719 | Preventive and Promotive Health Services | Construction of Pwani maternity wing | To construct Pwani maternity wing | Pwani maternity wing constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.392153 36.025158 2016.2 25.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 6858950 | 342.9 | 6858950 | 6858950 | -4858950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not equipped.
9720 | Preventive and Promotive Health Services | Renovation of Lare Health Centre | To rehabilitate Lare Health Centre to restore functionality | Lare Health Centre rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.446784, 36.008922 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2024 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 6858950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
9721 | Preventive and Promotive Health Services | Construction of a waiting bay at FITC Dispensary | To construct a waiting bay at FITC Dispensary | A waiting bay at FITC Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.279623 36.031717 1873.699951171875 64.0999984741211 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999932 | 100 | 1999932 | 1000000 | 68 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Kitchen and dinning complete.
9722 | Preventive and Promotive Health Services | Expansion of moi Ndabi dispensary | To expand moi Ndabi dispensary to increase capacity | Moi Ndabi dispensary expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.832803 36.203925 1761.6 19.399999618530273 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 1399870 | 41.2 | 1399870 | 1400583 | 2000130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
9723 | Preventive and Promotive Health Services | Sero maternity | To implement sero maternity for access to quality healthcare services | Sero maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.824917 36.203913 0 400 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997670 | 99.9 | 1997670 | 2330 | 2330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
9724 | Preventive and Promotive Health Services | Renovation Of Maternity At Karati Dispensary | To rehabilitate Maternity At Karati Dispensary to restore functionality | Maternity At Karati Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MALEWA WEST | -0.684685, 36.471073 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2017/18 | 700000 | 700000 | 700000 | Equitable | Ward Fund | 700000 | 0 | 1997525 | 285.4 | 1997525 | 275 | -1297525 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was addition for renovation works that had started.
9725 | Preventive and Promotive Health Services | Gatamaiyo Dispensary Renovation & Staff Houses | To implement gatamaiyo dispensary renovation & staff houses for access to quality healthcare services | Gatamaiyo Dispensary Renovation & Staff Houses completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MALEWA WEST | -0.684685, 36.435034 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | Ward Fund | 2100000 | 0 | 1693992 | 80.7 | 1693992 | 29719 | 406008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not yet started.
9726 | Preventive and Promotive Health Services | Kasarani Dispensary completion and equipping | To implement kasarani dispensary completion and equipping for access to quality healthcare services | Kasarani Dispensary completion and equipping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MALEWA WEST | -0.684685, 36.435034 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2017/18 | 850000 | 850000 | 850000 | Equitable | Ward Fund | 850000 | 0 | 1693992 | 199.3 | 1693992 | 29719 | -843992 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
9727 | Preventive and Promotive Health Services | design and Construction of Kapsiwendet Dispensary | To design and construct Kapsiwendet Dispensary | Kapsiwendet Dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.381214, 35.795652 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 9890259 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank not operational.
9728 | Preventive and Promotive Health Services | design and construction of laboratory and drug store for Marioshoni health centre | To design and construct laboratory and drug store for Marioshoni health centre | Laboratory and drug store for Marioshoni health centre designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.368528, 35.821334 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9729 | Preventive and Promotive Health Services | purchase of equipment and furniture for Lawina dispensary | To procure equipment and furniture for Lawina dispensary | Equipment and furniture for Lawina dispensary procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.32707, 35.866401 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9730 | Preventive and Promotive Health Services | Construction of Maternity ward and Equipping of dispensary | To construct Maternity ward and Equipping of dispensary | Maternity ward and Equipping of dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5839587 | 97.3 | 5839587 | 1197370 | 160413 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9731 | Preventive and Promotive Health Services | Mau Narok Health Centre Maternity(0202) | To implement mau narok health centre maternity(0202) for access to quality healthcare services | Mau Narok Health Centre Maternity(0202) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1194600 | 1194600 | 1194600 | Equitable | Ward Fund | 1194600 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9732 | Preventive and Promotive Health Services | Mwisho Wa Lami - Construction Of Dispensary | To implement mwisho wa lami - construction of dispensary for access to quality healthcare services | Mwisho Wa Lami - Construction Of Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | -0.632973, 35.995962 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3498502 | 100 | 3498502 | 1498 | 1498 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: in good state of repair.
9733 | Preventive and Promotive Health Services | Completion of Mosop dispensary | To complete Mosop dispensary | Mosop dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.55248, 35.99102 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2019 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 504400 | 33.6 | 504400 | 100 | 995600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Lacks equipment.
9734 | Preventive and Promotive Health Services | Construction of Teret Dispensary | To construct Teret Dispensary | Teret Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.452938, 35.950194 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Requires renovation.
9735 | Preventive and Promotive Health Services | design and construction of Mosop health centre | To design and construct Mosop health centre | Mosop health centre designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.481008 35.963225 2456.5 10 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 504400 | 25.2 | 504400 | 10000000 | 1495600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
9736 | Preventive and Promotive Health Services | Construction and equipping of Taita dispensary | To construct and equip Taita dispensary | Taita dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.516652, 35.962658 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2022 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 5249461 | 52.5 | 5249461 | 506401 | 4750539 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Ongoing.
9737 | Preventive and Promotive Health Services | Completion and equipping of Menengai Health Centre | To complete and equip Menengai Health Centre | Menengai Health Centre completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | MENENGAI EAST | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9738 | Completion of a maternity wing and equipping | Completion of a maternity wing and equipping | To complete a maternity wing and equipping | A maternity wing and equipping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.140853, 36.017118 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 2000000 | 100 | 2000000 | 1999824 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and operational.
9739 | Preventive and Promotive Health Services | Construction Of Menengai Health Centre | To construct Menengai Health Centre | Menengai Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.2466 36.013657 2010.9 9.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1045897.8 | 1045898 | 1045898 | Equitable | N/A | 1045898 | 0 | 1000940 | 95.7 | 1000940 | 3614260 | 44958 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9740 | Preventive and Promotive Health Services | Equipping of maternity ward- Menengai west | To equip maternity ward- Menengai west with necessary facilities and equipment | Maternity ward- Menengai west equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.255223 35.990582 1983.5 2.700000047683716 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 999980 | 40 | 999980 | 1247916 | 1500020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9741 | Preventive and Promotive Health Services | Maternity Wards Menengai Dispensary - On Going | To implement maternity wards menengai dispensary - on going for access to quality healthcare services | Maternity Wards Menengai Dispensary - On Going completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.140657 36.017808 1906.8999999999999 11 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2247896 | 2247896 | 2247896 | Equitable | Ward Fund | 2247896 | 0 | 999980 | 44.5 | 999980 | 1247916 | 1247916 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
9742 | Preventive and Promotive Health Services | Completion and equipping of maternity wing at Mangu Dispensary | To complete and equip maternity wing at Mangu Dispensary | Maternity wing at Mangu Dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.139944 35.901417 0 699.9990234375 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2499870 | 100 | 2499870 | 2000000 | 130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
9743 | Health Curative and Rehabilitative Services | Completion of Women and Pediatric Wards at Molo District Hospital | To complete Women and Pediatric Wards at Molo District Hospital | Women and Pediatric Wards at Molo District Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9744 | Preventive and Promotive Health Services | Molo Sub County Hospital water tank | To implement molo sub county hospital water tank for access to quality healthcare services | Molo Sub County Hospital water tank completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9745 | Preventive and Promotive Health Services | Construction of Turi farmers health centre | To construct Turi farmers health centre | Turi farmers health centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.266003 35.881008 2093.4 16.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1600000 | 1600000 | 1600000 | Equitable | Ward Fund | 1600000 | 0 | 211969 | 13.2 | 211969 | 1400000 | 1388031 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
9746 | Preventive and Promotive Health Services | Equipping of Ogilgei Maternity Wing | To equip Ogilgei Maternity Wing with necessary facilities and equipment | Ogilgei Maternity Wing equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1499973 | 75 | 1499973 | 0 | 500027 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
9747 | Preventive and Promotive Health Services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine | To implement rongai turi health centre - renovation of staff houses, piping, and construction of a pit latrine for access to quality healthcare services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.252618 35.833533 2133.2999999999997 21 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 0 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1767712 | 0 | 1767712 | 232288 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra. Assessor remarks: Good.
9748 | Preventive and Promotive Health Services | Proposed Outpatient Block at Muguga Health Centre | To undertake the proposed Outpatient Block at Muguga Health Centre | Proposed Outpatient Block at Muguga Health Centre implemented | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | NAKURU EAST | -0.310143, 36.145533 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2375679.8 | 1500906.4 | 1500906.4 | Equitable | N/A | 1500906.4 | 0 | 953474 | 63.5 | 953474 | 547433 | 547432.4 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Euphemia general supplies. Assessor remarks: Project ok.
9749 | Preventive and Promotive Health Services | Rehabilitation and Equipping of Nessuit Maternity | To rehabilitate Equipping of Nessuit Maternity to restore functionality | Equipping of Nessuit Maternity rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.393429 35.899456 2477.7296299869195 52.435916900634766 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997290 | 99.7 | 997290 | 2710 | 2710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The maternity is operational.
9750 | Preventive and Promotive Health Services | Construction of Njoro Sub County Hospital | To construct Njoro Sub County Hospital | Njoro Sub County Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.335855 35.950051 2145.000244140625 8.836999893188477 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 1023508 | 1023508 | 1023508 | Equitable | N/A | 1023508 | 0 | 10563817 | 1032.1 | 10563817 | 30000000 | -9540309 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
9751 | Preventive and Promotive Health Services | Design and Construction of a Women's Ward in Njoro Sub District Hospital | To design and construct a Women's Ward in Njoro Sub District Hospital | A Women's Ward in Njoro Sub District Hospital designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.335855 35.950051 2145.000244140625 8.836999893188477 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 10563817 | 422.6 | 10563817 | 30000000 | -8063817 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
9752 | Preventive and Promotive Health Services | Njokerio Dispensary | To implement njokerio dispensary for access to quality healthcare services | Njokerio Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.38976, 35.931253 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2015 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999138 | 100 | 1999138 | 862 | 862 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
9753 | Preventive and Promotive Health Services | Completion of Chesirikwa dispensary | To complete Chesirikwa dispensary | Chesirikwa dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | 0.0299, 36.161619 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 442284 | 44.2 | 442284 | 57716 | 557716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete: Needs metal bars at the entrance. Grill doors..
9754 | Preventive and Promotive Health Services | Construction, Equipping And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) | To construct and equip And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) | And Offices At Olkaria Health Centre (Fabrication And Installation Of Container Container) constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.936641 36.369939 1908.19287109375 13.87600040435791 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 1923166 | 1923166 | 1923166 | Equitable | N/A | 1923166 | 0 | 0 | 0 | 0 | 8000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes.since the facility they are using is busy. Assessor remarks: The structure there was built by kengen.
9755 | Preventive and Promotive Health Services | Renovation of Mama Ngina clinic in Nakuru west | To rehabilitate Mama Ngina clinic in Nakuru west to restore functionality | Mama Ngina clinic in Nakuru west rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAAB | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
9756 | Health Curative and Rehabilitative Services | Design and construction and equipping of a laboratory | To design and construct and equipping of a laboratory | And equipping of a laboratory designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAB | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
9757 | Preventive and Promotive Health Services | completion of Sirikwa health centre toilet | To complete Sirikwa health centre toilet | Sirikwa health centre toilet completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.258163, 35.667396 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | 2018/19 | 2018/19 | 2018/19 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399142 | 99.8 | 399142 | 0 | 858 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project has visible cracks, the pit is almost full,.
9758 | Preventive and Promotive Health Services | Construction of Toilets at Gacharage Health Centre | To construct Toilets at Gacharage Health Centre | Toilets at Gacharage Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.288902, 35.636293 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 476394 | 39.7 | 476394 | 0 | 723606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not met the needs of the users and residents. Assessor remarks: The project is not in use,the workmanship was poor as result the project has cracks and it has shallow pit.
9759 | Preventive and Promotive Health Services | Construction Of 2no Rooms MCH At Kapsetek Maternity | To construct 2no Rooms MCH At Kapsetek Maternity | 2no Rooms MCH At Kapsetek Maternity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.08361 35.87401 1797.4 6.699999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 349972 | 23.3 | 349972 | 28 | 1150028 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was not constructed as budgeted.
9760 | Preventive and Promotive Health Services | Construction of Losbil dispensary | To construct Losbil dispensary | Losbil dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.10065 35.988127 1680.5 4.199999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | Ward Fund | 4000000 | 0 | 1185416 | 29.6 | 1185416 | 28 | 2814584 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installation of Terrazo, construction of a new classroom and installation of plastic Water Tank, installation of gutters, Construction of Learners and staff Toilets, Construction of a modern kitchen,Outdoor play materials and furniture.
9761 | Preventive and Promotive Health Services | Construction Of Losobil Dispensary | To construct Losobil Dispensary | Losobil Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.10065 35.988127 1680.5 4.199999809265137 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 970007.05 | 970007 | 970007 | Equitable | Ward Fund | 970007 | 0 | 1185416 | 122.2 | 1185416 | 28 | -215409 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installation of Terrazo, construction of a new classroom and installation of plastic Water Tank, installation of gutters, Construction of Learners and staff Toilets, Construction of a modern kitchen,Outdoor play materials and furniture.
9762 | Preventive and Promotive Health Services | construction of maternity ward at Kipsyenan Dispensary | To construct maternity ward at Kipsyenan Dispensary | Maternity ward at Kipsyenan Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.083928, 35.874083 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 30/12/3024 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 349972 | 11.7 | 349972 | 3900000 | 2650028 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: M/S Laron Investment. Assessor remarks: The project is ongoing.
9763 | Preventive and Promotive Health Services | Renovation And Repair Work At Majani Mingi Dispensary | To rehabilitate Repair Work At Majani Mingi Dispensary to restore functionality | Repair Work At Majani Mingi Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.04561 36.027826 1647 8 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 537556 | 53.8 | 537556 | 462444 | 462444 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fencing is ongoing.
9764 | Preventive and Promotive Health Services | Construction of a dispensary at Lomolo | To construct a dispensary at Lomolo | A dispensary at Lomolo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | 0.016382, 36.033423 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019/2020 | 3700000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 1185416 | 34.9 | 1185416 | 28 | 2214584 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require a maternity.
9765 | Preventive and Promotive Health Services | Fencing and installation of a gate at Losibil Dispensary | To secure and installation of a gate at Losibil Dispensary through fencing | And installation of a gate at Losibil Dispensary fenced and secured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.101619 35.990918 1694.5 4.400000095367432 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1223486 | 81.6 | 1223486 | 28 | 276514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Dispensary needs an extra Plastic Tank,.
9766 | Preventive and Promotive Health Services | Roofing of maternity wing at Kipsyenan Dispensary | To implement roofing of maternity wing at kipsyenan dispensary for access to quality healthcare services | Roofing of maternity wing at Kipsyenan Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.085275 35.944498 1671.6 11.399999618530273 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 439500 | 36.6 | 439500 | 3900000 | 760500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9767 | Preventive and Promotive Health Services | Design and Construction of the Maternity at Ngendaptich maternity | To design and construct the Maternity at Ngendaptich maternity | The Maternity at Ngendaptich maternity designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | 0.046135, 36.141027 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: There is no maternity unit on the ground only an OPD block constructed in year 2014.
9768 | Preventive and Promotive Health Services | Fencing of Set - Kobor dispensary | To secure Set - Kobor dispensary through fencing | Set - Kobor dispensary fenced and secured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | -0.027433 36.129588 0 1100 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 681540 | 68.2 | 681540 | 700000 | 318460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fence is in good condition.
9769 | Preventive and Promotive Health Services | Construction of Theatre at Subukia sub county Hospital | To construct Theatre at Subukia sub county Hospital | Theatre at Subukia sub county Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | 0.002605, 36.230324 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2019/20 | 05/03/2019 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2536538 | 63.4 | 2536538 | 10000000 | 1463462 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. At the time, the facility was in use untill it was changed use.. Viable: Yes. The complex was used as theatre until it was no longer in use as theatre. Contractor: Information not available. Assessor remarks: That's facility now used as a medical supplies store for the subcounty.
9770 | Preventive and Promotive Health Services | Edgewood dispensary | To implement edgewood dispensary for access to quality healthcare services | Edgewood dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | 0.004801, 36.207485 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 04/01/2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998346 | 99.9 | 1998346 | 1654 | 1654 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The facility serves the community. Contractor: Information not available. Assessor remarks: Good work.
9771 | Preventive and Promotive Health Services | Ongoing Project Miloreni Dispensary | To implement ongoing project miloreni dispensary for access to quality healthcare services | Ongoing Project Miloreni Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.027587 36.17731 2064.2 5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 0 | 0 | 0 | 674464 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Working.
9772 | Preventive and Promotive Health Services | Ongoing Project Munanda Dispensary | To implement ongoing project munanda dispensary for access to quality healthcare services | Ongoing Project Munanda Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.02697, 36.17742 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 674464 | 674464 | 674464 | Equitable | Ward Fund | 674464 | 0 | 0 | 0 | 0 | 674464 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The dispensary is providing basic health care services to local community. Ongoing construction of consultation room is yet to be completed since inception..
9773 | Preventive and Promotive Health Services | Dispensary-Chemnar, Kapket, Karao Dispensary - On Going | To implement dispensary-chemnar, kapket, karao dispensary - on going for access to quality healthcare services | Dispensary-Chemnar, Kapket, Karao Dispensary - On Going completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.47504 35.631932 0 2400 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4795796 | 4795796 | 4795796 | Equitable | Ward Fund | 4795796 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
9774 | Construction and renovation of Munyeshi dispensary | Construction and renovation of Munyeshi dispensary | To construct and renovation of Munyeshi dispensary | And renovation of Munyeshi dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.302072, 35.720327 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 499580 | 25 | 499580 | 420 | 1500420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title is still under muyeshi farm. The title has not yet been produced. The county to facilitate the process.
9775 | Preventive and Promotive Health Services | Construction of outpatient block at Kiambiriria health Centre | To construct outpatient block at Kiambiriria health Centre | Outpatient block at Kiambiriria health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.323608, 35.698085 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 998950 | 99.9 | 998950 | 1050 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The work was well done.
9776 | Preventive and Promotive Health Services | Renovation of Mona dispensary | To rehabilitate Mona dispensary to restore functionality | Mona dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.295452, 35.706082 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 499580 | 99.9 | 499580 | 420 | 420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title of the land still reads cattle dip there is need to follow up for change of user.
9777 | Preventive and Promotive Health Services | Renovation of Mukorombosi dispensary | To rehabilitate Mukorombosi dispensary to restore functionality | Mukorombosi dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.295452, 35.706082 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 499580 | 50 | 499580 | 420 | 500420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title of the land still reads cattle dip there is need to follow up for change of user.
9778 | Preventive and Promotive Health Services | Construction of Rajuela dispensary | To construct Rajuela dispensary | Rajuela dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.125197 35.935737 1744.699951171875 6.599999904632568 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2013/14 | 2013/14 | 2013/14 | 1797719 | 782943.5 | 782943.5 | Equitable | Ward Fund | 782943.5 | 0 | 999970 | 127.7 | 999970 | 30 | -217026.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9779 | Preventive and Promotive Health Services | Construction of Ngesumin-moricho dispensary Nurse station | To construct Ngesumin-moricho dispensary Nurse station | Ngesumin-moricho dispensary Nurse station constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.205477 35.849033 1900.9000244140625 56.099998474121094 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999970 | 100 | 999970 | 30 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition.
9780 | Preventive and Promotive Health Services | Construction of Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto | To construct Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto | Rajuera laboratory, toilets and gate and equipping of the dispensary at kambi ya moto constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1793557 | 99.6 | 1793557 | 0 | 6443 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
9781 | Preventive and Promotive Health Services | Construction and equipping of Kabati Dispensary | To construct and equip Kabati Dispensary | Kabati Dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.72189, 36.444124 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 105095 | 1.5 | 105095 | 105095 | 6894905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and functional.
9782 | Preventive and Promotive Health Services | Construction and equipping of laboratory and and connection to power Simboiyon health centre | To construct and equip laboratory and and connection to power Simboiyon health centre | Laboratory and and connection to power Simboiyon health centre constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.083666, 36.245626 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 700000 | 70135 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Laboratory Not Equipped.
9783 | Preventive and Promotive Health Services | Construction and equipping of laboratory and power at Olgilgei Dispensary | To construct and equip laboratory and power at Olgilgei Dispensary | Laboratory and power at Olgilgei Dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 699700 | 70135 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
9784 | Preventive and Promotive Health Services | purchase of Kasarani dispensary land | To procure Kasarani dispensary land | Kasarani dispensary land procured | 3110203 | N/A | MOLO | ELBURGON | -0.293257 35.80205 2488.1 15.399999618530273 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000001 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 515700 | 0 | 515700 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
9785 | Preventive and Promotive Health Services | Completion of Olenguruone public toilet | To complete Olenguruone public toilet | Olenguruone public toilet completed | 3110299 | Construction of Buildings - Ot | KURESOI SOUTH | AMALO | -0.589485, 35.685055 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2019 | 700000 | 700000 | 700000 | Equitable | Ward Fund | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: facility operational.
9786 | Preventive and Promotive Health Services | Construction of a maternity wing at Bahati Rural Health Centre | To construct a maternity wing at Bahati Rural Health Centre | A maternity wing at Bahati Rural Health Centre constructed | 3110299 | Construction of Buildings - Ot | BAHATI | BAHATI | -0.153829 36.145158 2044.5 32.861000061035156 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 3999583 | 133.3 | 3999583 | 5000000 | -999583 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Need replacement with a shade.
9787 | Preventive and Promotive Health Services | Construction of a public toilet at Bahati stage | To construct a public toilet at Bahati stage | A public toilet at Bahati stage constructed | 3110299 | Construction of Buildings - Ot | BAHATI | BAHATI | -0.159529 36.104999 1855.0999755859375 82.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997664 | 99.8 | 997664 | 382800 | 2336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
9788 | Preventive and Promotive Health Services | design and Construction of Bahati Eco public Toilets | To design and construct Bahati Eco public Toilets | Bahati Eco public Toilets designed and constructed | 3110299 | Construction of Buildings - Ot | BAHATI | BAHATI | -0.159529 36.104999 1855.0999755859375 82.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1180027 | 78.7 | 1180027 | 319973 | 319973 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice.
9789 | Preventive and Promotive Health Services | Design and Construction of septic tank, piping, toilet and laboratory, fencing of Mwariki Dispensary | To design and construct septic tank, piping, toilet and laboratory, fencing of Mwariki Dispensary | Septic tank, piping, toilet and laboratory, fencing of Mwariki Dispensary designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | BARUT | -0.324324, 36.036613 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Contractor: No contractor coming soon. Assessor remarks: No lab.
9790 | Preventive and Promotive Health Services | Construction of Toilet block, Septic Tank, Fencing and equipping of Mununga Dispensary | To construct Toilet block, Septic Tank, Fencing and equipping of Mununga Dispensary | Toilet block, Septic Tank, Fencing and equipping of Mununga Dispensary constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9791 | Preventive and Promotive Health Services | Construction of Songoloi public toilet | To construct Songoloi public toilet | Songoloi public toilet constructed | 3110299 | Construction of Buildings - Ot | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 600903 | 600903 | 600903 | Equitable | N/A | 600903 | 0 | 592609 | 98.6 | 592609 | 850000 | 8294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9792 | Preventive and Promotive Health Services | Construction of staff Quarters at Eburu health Centre | To construct staff Quarters at Eburu health Centre | Staff Quarters at Eburu health Centre constructed | 3110299 | Construction of Buildings - Ot | GILGIL | EBURU-MBARUK | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2533450 | 211.1 | 2533450 | 0 | -1333450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9793 | Preventive and Promotive Health Services | Design and Construction of Salama Trading Centre Public Toilet | To design and construct Salama Trading Centre Public Toilet | Salama Trading Centre Public Toilet designed and constructed | 3110299 | Construction of Buildings - Ot | MOLO | ELBURGON | -0.297461 35.796986 2452.800048828125 18.98200035095215 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 208798 | 13.9 | 208798 | 6202551 | 1291202 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not fit for use.
9794 | Preventive and Promotive Health Services | expanson of Arimi Dispensary ( maternity wing) | To implement expanson of arimi dispensary ( maternity wing) for access to quality healthcare services | expanson of Arimi Dispensary ( maternity wing) completed | 3110299 | Construction of Buildings - Ot | MOLO | ELBURGON | -0.284884, 35.845889 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | - | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 515700 | 20.6 | 515700 | 558067 | 1984300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No maternity wing.
9795 | Preventive and Promotive Health Services | Construction of staff quarters for Tangi Tano Dispensary | To construct staff quarters for Tangi Tano Dispensary | Staff quarters for Tangi Tano Dispensary constructed | 3110299 | Construction of Buildings - Ot | GILGIL | ELEMENTAITA | -0.618479 36.146866 2199.106 0.8889999985694885 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798133 | 99.9 | 2798133 | 90 | 1867 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9796 | Preventive and Promotive Health Services | Design and construction of sanitary block | To design and construct sanitary block | Sanitary block designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | FLAMINGO | -0.301265, 36.075843 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: It's in operation.
9797 | Preventive and Promotive Health Services | Design and construction of toilets | To design and construct toilets | Toilets designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | FLAMINGO | -0.301338, 36.076302 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 1400000 | 1400000 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Completed and in operation.
9798 | Preventive and Promotive Health Services | Sanitary (Blocks)Kimathi/Flamingo(1104) | To implement sanitary (blocks)kimathi/flamingo(1104) for access to quality healthcare services | Sanitary (Blocks)Kimathi/Flamingo(1104) completed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | FLAMINGO | -0.30256 36.072873 1823.9 19.100000381469727 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 1574965.38 | 1574965 | 1574965 | Equitable | Ward Fund | 1574965 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: It's in good status and in operation.
9799 | Preventive and Promotive Health Services | construction of a public toilet at the DCs office - Nakuru town | To construct a public toilet at the DCs office - Nakuru town | A public toilet at the DCs office - Nakuru town constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 2533450 | 126.7 | 2533450 | 9890259 | -533450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9800 | Construction of Maternity at Gilgil subcounty Hospital | Construction of Maternity at Gilgil subcounty Hospital | To construct Maternity at Gilgil subcounty Hospital | Maternity at Gilgil subcounty Hospital constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 200000000 | 0 | 0 | N/A | N/A | 0 | 40000000 | 750000 | 0 | 750000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9801 | Construction of OPD at Olenguruone Subcounty hospital | Construction of OPD at Olenguruone Subcounty hospital | To construct OPD at Olenguruone Subcounty hospital | OPD at Olenguruone Subcounty hospital constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 200000000 | 0 | 0 | N/A | N/A | 0 | 30000000 | 750000 | 0 | 750000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9802 | Design and Construction of outpatient block at Elburgon sub county hospital | Design and Construction of outpatient block at Elburgon sub county hospital | To design and construct outpatient block at Elburgon sub county hospital | Outpatient block at Elburgon sub county hospital designed and constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 200000000 | 0 | 0 | N/A | N/A | 0 | 29999999.45 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9803 | Preventive and Promotive Health Services | Construction of public toilet in Kabatini | To construct public toilet in Kabatini | Public toilet in Kabatini constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.213214 36.162865 2030 82.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
9804 | ECDs Toilets at (Engashura & St John) | ECDs Toilets at (Engashura & St John) | To implement ecds toilets at (engashura & st john) for access to quality healthcare services | ECDs Toilets at (Engashura & St John) completed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.241725, 36.152316 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | 28th October 2015 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but needs renovation.
9805 | Preventive and Promotive Health Services | Design and construction of doctors houses at Lalwet dispensary | To design and construct doctors houses at Lalwet dispensary | Doctors houses at Lalwet dispensary designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPKURES | -0.288288, 36.05451 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Was viable and serving purpose. Assessor remarks: Properly implemented.
9806 | Preventive and Promotive Health Services | Construction and equipping of new public toilet(disability friendly), raising of perimeter wall and installation of razor wire at Rhonda Health Centre Renovation of Dispensary wing at Rhonda Health Centre (ceiling, tiles, painting, renovation of waiting bay) | To construct and equip new public toilet(disability friendly), raising of perimeter wall and installation of razor wire at Rhonda Health Centre Renovation of Dispensary wing at Rhonda Health Centre (ceiling, tiles, painting, renovation of waiting bay) | New public toilet(disability friendly), raising of perimeter wall and installation of razor wire at Rhonda Health Centre Renovation of Dispensary wing at Rhonda Health Centre (ceiling, tiles, painting, renovation of waiting bay) constructed and equipped | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPTEMBWO | -0.305074, 36.055301 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 0 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes it really met the needs of the residents. Contractor: U23. Assessor remarks: Complete but needs renovation.
9807 | Preventive and Promotive Health Services | Construction of Youth Friendly Health Centre Unit | To construct Youth Friendly Health Centre Unit | Youth Friendly Health Centre Unit constructed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPTEMBWO | -0.30479 36.055153 1791.5 14.612000465393066 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 0 | 2234928 | Equitable | N/A | 2234928 | 0 | 1479928 | 0 | 1479928 | 1515728 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable, it has helped the youths Very much,but defective toilets and urinals. Contractor: ZIBO COMPANY. Assessor remarks: Complete.
9808 | Preventive and Promotive Health Services | Construction of Registry/ waiting bay, placenta pit and septic tank at Engashura health centre | To construct Registry/ waiting bay, placenta pit and septic tank at Engashura health centre | Registry/ waiting bay, placenta pit and septic tank at Engashura health centre constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KIAMAINA | -0.25936, 36.134108 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2018/2019 | 2000001 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 4800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The structure requires renovation.
9809 | Preventive and Promotive Health Services | Design and Construction of pharmacy and Registry block at Menengai dispensary | To design and construct pharmacy and Registry block at Menengai dispensary | Pharmacy and Registry block at Menengai dispensary designed and constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KIAMAINA | -0.259333, 36.134116 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2019/2020 | 2000001 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 0 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project requires renovation.
9810 | Preventive and Promotive Health Services | construction of Toilet blocks at Mutarakwa and kihingo dispensary | To construct Toilet blocks at Mutarakwa and kihingo dispensary | Toilet blocks at Mutarakwa and kihingo dispensary constructed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.475517 35.988007 2287.2999999999997 26.18600082397461 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation is required.
9811 | Preventive and Promotive Health Services | Completion and construction of toilet at Tulwet dispensary | To complete and construction of toilet at Tulwet dispensary | And construction of toilet at Tulwet dispensary completed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | KIPTORORO | -0.357906, 35.55465 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 543281 | 54.3 | 543281 | 93806 | 456719 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Tulwet. Assessor remarks: The toilet is complete but the pit was very shallow and its already full it requires exhaustion or construction of a septic tank and a soakage pit.
9812 | Preventive and Promotive Health Services | Construction of toilet blocks at Kivumbini II Estate | To construct toilet blocks at Kivumbini II Estate | Toilet blocks at Kivumbini II Estate constructed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | KIVUMBINI | -0.299841, 36.083603 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 3628118 | 181.4 | 3628118 | 1408217 | -1628118 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Emproved sanitation.
9813 | Preventive and Promotive Health Services | Design and construction of a sanitary block at the Estate | To design and construct a sanitary block at the Estate | A sanitary block at the Estate designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | KIVUMBINI | -0.299927, 36.083621 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 3628118 | 72.6 | 3628118 | 1408217 | 1371882 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: toilets funtional.
9814 | Preventive and Promotive Health Services | Construction of public toilet and fencing of Gichodo Dispensary | To construct public toilet and fencing of Gichodo Dispensary | Public toilet and fencing of Gichodo Dispensary constructed | 3110299 | Construction of Buildings - Ot | NJORO | LARE | -0.525252 36.044357 2325.000244140625 10 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Funds allocated was utilized for intended purpose.
9815 | Preventive and Promotive Health Services | Design and Construction of staff quarters; equipping of the Health Facility and Constrcution of Perimeter Fence for Maiella Mortuary | To design and construct staff quarters; equipping of the Health Facility and Constrcution of Perimeter Fence for Maiella Mortuary | Staff quarters; equipping of the Health Facility and Constrcution of Perimeter Fence for Maiella Mortuary designed and constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | MAIELLA | -0.832903, 36.204037 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2018 | 3300000 | 3300000 | 3300000 | Equitable | Ward Fund | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leakage and Paint.Rapairs and maintenance needed.
9816 | Preventive and Promotive Health Services | Construction of Kirima - Githima public toilet | To construct Kirima - Githima public toilet | Kirima - Githima public toilet constructed | 3110299 | Construction of Buildings - Ot | GILGIL | MALEWA WEST | -0.612613, 36.488572 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2017/18 | 600000 | 600000 | 600000 | Equitable | Ward Fund | 600000 | 0 | 499400 | 83.2 | 499400 | 0 | 100600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Condemned for demolition, not weĺ located.
9817 | Karati Dispensary Staff Houses | Karati Dispensary Staff Houses | To implement karati dispensary staff houses for access to quality healthcare services | Karati Dispensary Staff Houses completed | 3110299 | Construction of Buildings - Ot | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2014/15 | 2014/15 | 2016/17 | 657616 | 657616 | 657616 | Equitable | Ward Fund | 657616 | 0 | 1693992 | 257.6 | 1693992 | 29719 | -1036376 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
9818 | Preventive and Promotive Health Services | Design and Construction of toilet Block at Lawina Dispensary | To design and construct toilet Block at Lawina Dispensary | Toilet Block at Lawina Dispensary designed and constructed | 3110299 | Construction of Buildings - Ot | MOLO | MARIOSHONI | -0.327021, 35.866533 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | Ward Fund | 600000 | 0 | 2533450 | 422.2 | 2533450 | 9890259 | -1933450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9819 | Construction of toilets (2 blocks ) at Ol Rongai Dispensary | Construction of toilets (2 blocks ) at Ol Rongai Dispensary | To construct toilets (2 blocks ) at Ol Rongai Dispensary | Toilets (2 blocks ) at Ol Rongai Dispensary constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.140417, 36.017253 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 999920 | 100 | 999920 | 3614260 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kuria. Assessor remarks: Serves the purpose.
9820 | Preventive and Promotive Health Services | Construction of toilets, fencing and water tank at Nuthu Dispensary | To construct toilets, fencing and water tank at Nuthu Dispensary | Toilets, fencing and water tank at Nuthu Dispensary constructed | 3110299 | Construction of Buildings - Ot | GILGIL | MURINDAT | -0.408691, 36.310591 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1049950 | 52.5 | 1049950 | 1150960 | 950050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: NJASING ENTERPRISES. Assessor remarks: Good.
9821 | Preventive and Promotive Health Services | Design and Construction of Nessuit public toilet | To design and construct Nessuit public toilet | Nessuit public toilet designed and constructed | 3110299 | Construction of Buildings - Ot | NJORO | NESSUIT | -0.389554 35.895707 2419.01162878206 4.1620001792907715 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999300 | 99.9 | 999300 | 0 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The toilet was condemned immediately after construction due to underground water fill up making it difficult to use.
9822 | Preventive and Promotive Health Services | Construction of Toilets and fencing of Masaita Dispensary | To construct Toilets and fencing of Masaita Dispensary | Toilets and fencing of Masaita Dispensary constructed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | NYOTA | -0.379295 35.726667 2777 12 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699700 | 100 | 699700 | 41520 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: DREKS ENTERPRISES. Assessor remarks: Good.
9823 | Preventive and Promotive Health Services | Design and Construction of Kamere Public toilets | To design and construct Kamere Public toilets | Kamere Public toilets designed and constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | OLKARIA | -0.819094, 36.321451 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2499892 | 100 | 2499892 | 0 | 108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project lacks water tank and septic tank needs to be covered.
9824 | Preventive and Promotive Health Services | Design and Construction of Public Toilet at Kamere beach | To design and construct Public Toilet at Kamere beach | Public Toilet at Kamere beach designed and constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | OLKARIA | -0.819094, 36.321451 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 2499892 | 166.7 | 2499892 | 3000000 | -999892 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project lacks water tank and septic tank needs to be covered.
9825 | Preventive and Promotive Health Services | Design and construction of public toilets | To design and construct public toilets | Public toilets designed and constructed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | RHONDA | -0.306281, 36.063035 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 19/20 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Vandalized.
9826 | Preventive and Promotive Health Services | Design and Construction of two toilets at the town centre | To design and construct two toilets at the town centre | Two toilets at the town centre designed and constructed | 3110299 | Construction of Buildings - Ot | SUBUKIA | SUBUKIA | 0.001269 36.231898 1992.4000244140625 18.350000381469727 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1250000 | 50 | 1250000 | 1250000 | 1250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the project serves the boda boda riders in the area.. Contractor: Information not available. Assessor remarks: The boda boda shades are in use.
9827 | Preventive and Promotive Health Services | Rehabilitation of public toilet at Rongai Centre | To rehabilitate public toilet at Rongai Centre to restore functionality | Public toilet at Rongai Centre rehabilitated | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.174107, 35.861606 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 600000 | 600000 | Equitable | Ward Fund | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition,the toilet septic tank has collapsed.
9828 | Preventive and Promotive Health Services | Design and Construction of servant houses in Mbogoini | To design and construct servant houses in Mbogoini | Servant houses in Mbogoini designed and constructed | 3110299 | Construction of Buildings - Ot | SUBUKIA | WASEGES | 0.193542 36.215443 1698.1 11 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 985476 | 58 | 985476 | 0 | 714524 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and occupied.
9829 | Preventive and Promotive Health Services | Construction of 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary | To construct 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary | 4 doors toilet, septic tank, incinerator, purchase of 2 plastic tank 10m3, renovation of nurse house ( tiling and plinth), installatiion of 4 wooden doors at the dispensary, installation of dispensary gate and gutters for the nurse house at Ndoroto dispensary constructed | 3110302 | Refurbishment of Non-Residential Buildings | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/20 | 2019/21 | 2019/21 | 3500001 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999996 | 0 | 2999996 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9830 | Preventive and Promotive Health Services | Refurbishment of Health Buildings - Others | To implement refurbishment of health buildings - others for access to quality healthcare services | Refurbishment of Health Buildings - Others completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 50000000 | 40000000 | 40000000 | Equitable | N/A | 40000000 | 0 | 5400882 | 13.5 | 5400882 | 1657080 | 34599118 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9831 | Health Curative and Rehabilitative Services | Other Development (Conditional Fund for Level 5 Hospital (Nakuru PGH)) | To implement other development (conditional fund for level 5 hospital (nakuru pgh)) for access to quality healthcare services | Other Development (Conditional Fund for Level 5 Hospital (Nakuru PGH)) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 90000000 | 100000000 | 0 | N/A | N/A | 0 | 65500000 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
9832 | Preventive and Promotive Health Services | Fencing of Ngecha health Centre | To secure Ngecha health Centre through fencing | Ngecha health Centre fenced and secured | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.248426 35.939642 2052.10009765625 98.4000015258789 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 499990 | 100 | 499990 | 500000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes it was viable. Contractor: Not indicated. Assessor remarks: Good condition.
9833 | Preventive and Promotive Health Services | Rehabilitation and equipping of maternity ward and inpatient at Langa Langa sub county hospital | To rehabilitate equipping of maternity ward and inpatient at Langa Langa sub county hospital to restore functionality | Equipping of maternity ward and inpatient at Langa Langa sub county hospital rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.303564, 36.072862 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 11510664 | 287.8 | 11510664 | 134874 | -7510664 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
9834 | Preventive and Promotive Health Services | Construction of a perimeter fence around Industrial Area Health Centre | To construct a perimeter fence around Industrial Area Health Centre | A perimeter fence around Industrial Area Health Centre constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.283386, 36.043426 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494189 | 99.8 | 2494189 | 1100000 | 5811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
9835 | Preventive and Promotive Health Services | Other developments(Purchase Of Ambulances) | To implement other developments(purchase of ambulances) for access to quality healthcare services | Other developments(Purchase Of Ambulances) completed | 3110707 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 90000000 | 0 | 0 | Equitable | N/A | 0 | 34500000 | 59299908 | 100 | 59299908 | 70000000 | -59299908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9836 | Preventive and Promotive Health Services | Other developments | To implement other developments for access to quality healthcare services | Other developments completed | 3110707 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 52562897 | 18604117 | 1345250 | Equitable | N/A | 1345250 | 0 | 6308823 | 33.9 | 6308823 | 70000000 | 12295294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9837 | Preventive and Promotive Health Services | Purchase Of Ambulances | To procure Ambulances | Ambulances procured | 3110707 | N/A | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 5741133.05 | 5741133 | 23000000 | N/A | N/A | 23000000 | 0 | 59299908 | 1032.9 | 59299908 | 35324805 | -53558775 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9838 | Preventive and Promotive Health Services | Equipping and operationalization | To equip and operationalization with necessary facilities and equipment | And operationalization equipped | 3111101 | Purchase of Medical and Dental Equipment | NAKURU WEST | BARUT | -0.324324 36.036613 0 2000 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yee. Assessor remarks: It's operational....Good.
9839 | Preventive and Promotive Health Services | Equipping of Barut maternity | To equip Barut maternity with necessary facilities and equipment | Barut maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | NAKURU WEST | BARUT | -0.326993, 36.05629 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 16/10/2018 | 2400000 | 2400000 | 2400000 | Equitable | Ward Fund | 2400000 | 0 | 1496470 | 62.4 | 1496470 | 1500000 | 903530 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s mylers and billy investment. Assessor remarks: Most of the equipments are in use some in store awaiting usage.
9840 | Preventive and Promotive Health Services | Provision for purchase of medical equipment (Conditional Fund for Level 5 Hospital (Nakuru PGH)) | To implement provision for purchase of medical equipment (conditional fund for level 5 hospital (nakuru pgh)) for access to quality healthcare services | Provision for purchase of medical equipment (Conditional Fund for Level 5 Hospital (Nakuru PGH)) completed | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 70000000 | 70000000 | 0 | Equitable | N/A | 0 | 70000000 | 32239074 | 46.1 | 32239074 | 6109472 | 37760926 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9841 | Health Curative and Rehabilitative Services | Purchase Of Equipment Elementaita | To procure Equipment Elementaita | Equipment Elementaita procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 9093500 | 9093500 | 9093500 | FIF | FIF | 9093500 | 0 | 76381394 | 840 | 76381394 | 21343623 | -67287894 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9842 | Health Curative and Rehabilitative Services | Purchase of equipment (Facility Improvement Fund) | To procure equipment (Facility Improvement Fund) | Equipment (Facility Improvement Fund) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 35157500 | 35157500 | 0 | FIF | FIF | 0 | 35157500 | 692500 | 2 | 692500 | 35324805 | 34465000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9843 | Preventive and Promotive Health Services | Purchase of Medical Equipment s& dental Equipment for various new health centres(HQ) | To procure Medical Equipment s& dental Equipment for various new health centres(HQ) | Medical Equipment s& dental Equipment for various new health centres(HQ) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2015/16 | 2015/16 | N/A | 40000000 | 15593213.1 | 15593213.1 | Equitable | N/A | 15593213.1 | 0 | 2007688 | 12.9 | 2007688 | 6109472 | 13585525.1 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9844 | Preventive and Promotive Health Services | Purchase of Medical Equipments & dental Equipment for various new health centres(HQ) | To procure Medical Equipments & dental Equipment for various new health centres(HQ) | Medical Equipments & dental Equipment for various new health centres(HQ) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2007688 | 40.2 | 2007688 | 6109472 | 2992312 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9845 | Preventive and Promotive Health Services | Equipping of Ingobor Health Centre | To equip Ingobor Health Centre with necessary facilities and equipment | Ingobor Health Centre equipped | 3111101 | Purchase of Medical and Dental Equipment | NAKURU WEST | KAPKURES | -0.305507, 36.017052 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 2499590 | 100 | 2499590 | 5 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: All equipments available and in use.
9846 | Preventive and Promotive Health Services | equipping of Gichobo dispensary | To equip Gichobo dispensary with necessary facilities and equipment | Gichobo dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | NJORO | LARE | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
9847 | Preventive and Promotive Health Services | Equipping of Kapyemit Dispensary | To equip Kapyemit Dispensary with necessary facilities and equipment | Kapyemit Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | NJORO | LARE | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
9848 | Preventive and Promotive Health Services | Equipping of Gatamaiyu Dispensary | To equip Gatamaiyu Dispensary with necessary facilities and equipment | Gatamaiyu Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | GILGIL | MALEWA WEST | -0.702703, 36.291018 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more equipment.
9849 | Preventive and Promotive Health Services | Equipping of Kasarani Dispensary | To equip Kasarani Dispensary with necessary facilities and equipment | Kasarani Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | GILGIL | MALEWA WEST | -0.702703, 36.291018 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 499400 | 49.9 | 499400 | 0 | 500600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more equipment.
9850 | Health Curative and Rehabilitative Services | Construction of Maternity wing at Menengai Health Centre | To construct Maternity wing at Menengai Health Centre | Maternity wing at Menengai Health Centre constructed | 3111101 | Purchase of Medical and Dental Equipment | NAKURU EAST | MENENGAI EAST | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9851 | Health Curative and Rehabilitative Services | Purchase of plant machinery (Facility Improvement Fund) | To procure plant machinery (Facility Improvement Fund) | Plant machinery (Facility Improvement Fund) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | N/A | 16500000 | 16500000 | 0 | FIF | FIF | 0 | 16500000 | 692500 | 4.2 | 692500 | 35324805 | 15807500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9852 | Preventive and Promotive Health Services | Construction of Staff Quarters and fencing | To construct Staff Quarters and fencing | Staff Quarters and fencing constructed | 3111504 | N/A | NAKURU WEST | BARUT | -0.327006, 36.056342 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Contractor: M. Assessor remarks: Not habitable.
9853 | Preventive and Promotive Health Services | Naishi game dispensary fencing and dumpsite | To implement naishi game dispensary fencing and dumpsite for access to quality healthcare services | Naishi game dispensary fencing and dumpsite completed | 3111504 | N/A | NJORO | LARE | -0.396418 36.018132 2031.9 5.5 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999850 | 100 | 999850 | 0 | 150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
9854 | Preventive and Promotive Health Services | Refurbishment(re-roofing and ceiling, Construction perimeter wall; public toilets renovation,extension of waiting bay, Expansion water supply) of Lanet HEALTH Centre (Free Area) | To implement refurbishment(re-roofing and ceiling, construction perimeter wall; public toilets renovation,extension of waiting bay, expansion water supply) of lanet health centre (free area) for access to quality healthcare services | Refurbishment(re-roofing and ceiling, Construction perimeter wall; public toilets renovation,extension of waiting bay, Expansion water supply) of Lanet HEALTH Centre (Free Area) completed | 3111504 | N/A | NAKURU EAST | NAKURU EAST | -0.292729, 36.118408 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 5000000 | 5000000 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Plaster needed.
9855 | Preventive and Promotive Health Services | Purchase of Land for construction of Kiptenda Dispensary | To acquire land for construction of Kiptenda Dispensary | Land for construction of Kiptenda Dispensary acquired | 3130101 | Acquisition of Land | NAKURU WEST | BARUT | -0.338728 36.037972 1882.5 4.80000019073486 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 520384 | 34.7 | 520384 | 1500000 | 979616 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no kiptenden dispensary.
9856 | Preventive and Promotive Health Services | Purchase Of Cemetery Land | To procure Cemetery Land | Cemetery Land procured | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/2019 | 2018/2019 | 20000000 | 22032000 | 16032000 | Equitable | N/A | 16032000 | 0 | 59299908 | 269.2 | 59299908 | 35324805 | -37267908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9857 | Preventive and Promotive Health Services | Purchase of land for construction of a Dispensary at Kihoto | To acquire land for construction of a Dispensary at Kihoto | Land for construction of a Dispensary at Kihoto acquired | 3130101 | Acquisition of Land | NAIVASHA | LAKE VIEW | -0.728003, 36.43261 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no land that was purchased. No land on the ground.
9858 | Preventive and Promotive Health Services | Purchase of land and Construction of Arus Dispensary | To acquire land and construct Arus Dispensary | Land acquired and Arus Dispensary constructed | 3130101 | Acquisition of Land | RONGAI | SOLAI | 0.029958, 36.161542 | VOTE NO. D 05 | MINISTRY OF HEALTH SERVICES | MINISTRY OF HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2019 | 2800000 | 2800000 | 2800000 | Equitable | Ward Fund | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
9859 | Infrastructure, Development & Maintenance | Rehabilitation of bus park and other Parking bays | To rehabilitate bus park and other Parking bays to restore functionality | Bus park and other Parking bays rehabilitated | 2220299 | Routine Maintenance - Other As | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 44000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 1537405 | 15.4 | 1537405 | 1537405 | 8462595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9860 | Infrastructure, Development & Maintenance | Routine maintenance of roads, drainage ways and culverts | To maintain roads, drainage ways and culverts in serviceable condition | Roads, drainage ways and culverts maintained | 2220299 | Routine Maintenance - Other As | NAIVASHA | VIWANDANI | -0.714178 36.438707 1916.699951171875 3.816999912261963 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
9861 | Infrastructure, Development and Maintenance | Conditional Grant-Road Maintenance Levy Fund | To implement Road Maintenance Levy Fund as per conditional grant requirements | Road Maintenance Levy Fund implemented | 2640400 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 248847131 | 248847131 | 0 | RMLF | RMLF | 0 | 248847131 | 15258043 | 6.1 | 15258043 | 79595019 | 233589088 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9862 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Fire station) | To construct & Rehabilitation of buildings (Fire station) | & Rehabilitation of buildings (Fire station) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 20181765 | 201.8 | 20181765 | 7500000 | -10181765 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9863 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Water Reserviour) | To construct & Rehabilitation of buildings (Water Reserviour) | & Rehabilitation of buildings (Water Reserviour) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 20000000 | 400 | 20000000 | 4537500 | -15000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9864 | Rehabilitation Non Residential Buildings | Rehabilitation Non Residential Buildings | To rehabilitate Non Residential Buildings to restore functionality | Non Residential Buildings rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 4000000 | 40 | 4000000 | 10000000 | 6000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9865 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) | To construct & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) | & Rehabilitation of County Major Urban Roads (hire of Machinery & equipments) constructed | 3110401 | Major Roads | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 180000000 | 45000000 | 42300000 | Equitable | N/A | 42300000 | 0 | 27212000 | 60.5 | 27212000 | 7500000 | 17788000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9866 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) | To construct & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) | & Rehabilitation of County Major Urban Roads (purchase of gravel & murrams) constructed | 3110402 | Access Roads | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 180000001 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 6000000 | 0 | 6000000 | 7500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9867 | Infrastructure, Development and Maintenance | Grading and Murraming of Chesoen -Tuiyobei road | To improve road infrastructure by grading and murraming Chesoen -Tuiyobei road | Chesoen -Tuiyobei road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.603678 35.676035 2521 9.699999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 947399 | 94.7 | 947399 | 947400 | 52601 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
9868 | Infrastructure, Development & Maintenance | Grading and Murraming of Kapigeriet-Sigowet road | To improve road infrastructure by grading and murraming Kapigeriet-Sigowet road | Kapigeriet-Sigowet road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.638958, 35.653353 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1251901 | 89.4 | 1251901 | 80650 | 148099 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9869 | Infrastructure, Development and Maintenance | Grading and Murraming of Kiptaragon-Comboni road | To improve road infrastructure by grading and murraming Kiptaragon-Comboni road | Kiptaragon-Comboni road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.58684, 35.676332 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070680 | 97.3 | 1070680 | 1070680 | 29320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9870 | Infrastructure, Development and Maintenance | Grading and Murraming of Sachangwan -Ngeny road | To improve road infrastructure by grading and murraming Sachangwan -Ngeny road | Sachangwan -Ngeny road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.59666, 35.687903 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires grading and murraming.
9871 | Grading and Murraming of TTI- Bondet Church road | Grading and Murraming of TTI- Bondet Church road | To improve road infrastructure by grading and murraming TTI- Bondet Church road | TTI- Bondet Church road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.56301, 35.680885 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966126 | 98.9 | 2966126 | 2966126 | 33874 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires routine maintenance and spot gravelling.
9872 | Infrastructure, Development & Maintenance | Purchase of 1-Acre land to open Timoi-Kapkorio road | To procure 1-Acre land to open Timoi-Kapkorio road | 1-Acre land to open Timoi-Kapkorio road procured | 3110499 | Construction of Roads - Other | KURESOI SOUTH | AMALO | -0.573785, 35.697712 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: road yet to be graded. Viable: not yet. Assessor remarks: land has not been bought.
9873 | Infrastructure, Development & Maintenance | Laying of cabros at Ravine stage | To implement laying of cabros at ravine stage for road connectivity and accessibility | Laying of cabros at Ravine stage completed | 3110499 | Construction of Roads - Other | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997195 | 0 | 1997195 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9874 | Infrastructure, Development & Maintenance | Re-carpeting of Bargain Road | To upgrade Bargain Road through tarmacking for improved road connectivity | Bargain Road tarmacked and upgraded | 3110499 | Construction of Roads - Other | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 4458370 | 0 | 4458370 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9875 | Infrastructure, Development & Maintenance | Grading, murraming ang gravelling of roads in dundori | To implement grading, murraming ang gravelling of roads in dundori for road connectivity and accessibility | Grading, murraming ang gravelling of roads in dundori completed | 3110499 | Construction of Roads - Other | BAHATI | DUNDORI | -0.269, 36.182413 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 5700000 | 5300000 | 5300000 | Equitable | N/A | 5300000 | 0 | 2722767 | 51.4 | 2722767 | 2722767 | 2577233 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Daphy holdings Ltd. Assessor remarks: Require Maintenance.
9876 | Infrastructure, Development & Maintenance | purchase and installation of culverts in Githioro / Mugwathi access roads | To procure and install culverts in Githioro / Mugwathi access roads | Culverts in Githioro / Mugwathi access roads procured and installed | 3110499 | Construction of Roads - Other | BAHATI | DUNDORI | -0.237125, 36.167581 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 0 | 0 | 999800 | Equitable | N/A | 999800 | 0 | 106553 | 0 | 106553 | 106553 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance.
9877 | Infrastructure, Development & Maintenance | Grading and Gravelling of Losirwa road | To improve road infrastructure by grading and murraming Losirwa road | Losirwa road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | EBURU-MBARUK | -0.601504, 36.184973 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 18-19 | 2000000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Unspecified. Assessor remarks: Grading done but no murraming.
9878 | Infrastructure, Development & Maintenance | Grading and Murraming of Highway, Laikipia university, Mbaruk, Echariria road | To improve road infrastructure by grading and murraming Highway, Laikipia university, Mbaruk, Echariria road | Highway, Laikipia university, Mbaruk, Echariria road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | EBURU-MBARUK | -0.291385, 36.086452 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No value. Viable: No , No machinary used as per information gathered. Contractor: Unspecified. Assessor remarks: Poor work.
9879 | Infrastructure, Development & Maintenance | re-tarmacking of 350 metres othaya road racecourse estate | To implement re-tarmacking of 350 metres othaya road racecourse estate for road connectivity and accessibility | re-tarmacking of 350 metres othaya road racecourse estate completed | 3110499 | Construction of Roads - Other | NAKURU EAST | FLAMINGO | -0.273198, 36.105845 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2017/18 | 3000000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 2921344 | 91.3 | 2921344 | 8839 | 278656 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9880 | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge | To implement grading, gravelling and compacting of kariandusi primary school road and installation of culverts / foot bridge for road connectivity and accessibility | Grading, gravelling and compacting of Kariandusi primary school Road and installation of culverts / foot bridge completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.536368, 36.344783 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990000 | 99.5 | 1990000 | 1990000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Njasing enterprises Ltd. Assessor remarks: Maintainance.
9881 | Infrastructure, Development & Maintenance | Grading, gravelling, Installation of culverts compaction of maji moto - Kigogo road | To implement grading, gravelling, installation of culverts compaction of maji moto - kigogo road for road connectivity and accessibility | Grading, gravelling, Installation of culverts compaction of maji moto - Kigogo road completed | 3110499 | Construction of Roads - Other | GILGIL | GILGIL | -0.488406 36.329024 2004.300048828125 3.7899999618530273 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2929910 | 97.7 | 2929910 | 1410 | 70090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Maintainance.
9882 | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Grading and gravelling of Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | To improve road infrastructure by grading and murraming Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward | Nyamamitui Dispensary and routine maintenance of roads in Villa estate, Musaka and Kamuyu - Hells Gate Ward graded and murramed | 3110499 | Construction of Roads - Other | NAIVASHA | HELLS GATE | -0.778707 36.434856 1925.0999755859375 7.124000072479248 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5790256 | 96.5 | 5790256 | 4467177 | 209744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was at a cost of 2,802,096 some the road was later tarmarked.
9883 | Infrastructure, Development & Maintenance | Re-carpeting of roads in Kamara ward | To upgrade roads in Kamara ward through tarmacking for improved road connectivity | Roads in Kamara ward tarmacked and upgraded | 3110499 | Construction of Roads - Other | KURESOI NORTH | KAMARA | -0.097348 35.675729 2535.7001953125 49.63999938964844 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
9884 | Infrastructure, Development & Maintenance | Grading and gravelling of Kaporus-Kapkali Road | To improve road infrastructure by grading and murraming Kaporus-Kapkali Road | Kaporus-Kapkali Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KERINGET | -0.544877, 35.703545 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9885 | Infrastructure, Development & Maintenance | Grading and gravelling of Keringet - Ndabidit Road | To improve road infrastructure by grading and murraming Keringet - Ndabidit Road | Keringet - Ndabidit Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KERINGET | -0.43114, 35.688835 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 950681 | 55.9 | 950681 | 950681 | 749319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9886 | Infrastructure, Development and Maintenance | Grading and gravelling of Chebotoi- Kibirech road | To improve road infrastructure by grading and murraming Chebotoi- Kibirech road | Chebotoi- Kibirech road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.552683, 35.635952 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 980159 | 32.7 | 980159 | 980159 | 2019841 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
9887 | Infrastructure, Development & Maintenance | Grading and gravelling of Kipsongon Road | To improve road infrastructure by grading and murraming Kipsongon Road | Kipsongon Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | KIPTAGICH | -0.579112, 35.549627 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999983 | 100 | 1999983 | 999425 | 17 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable but needs not meet. Assessor remarks: Poor road,.
9888 | Infrastructure, Development & Maintenance | Graveling of 2km road at kongoi secondary-kongoi primary | To implement graveling of 2km road at kongoi secondary-kongoi primary for road connectivity and accessibility | Graveling of 2km road at kongoi secondary-kongoi primary completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.324475, 35.537975 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1962952 | 98.1 | 1962952 | 1962952 | 37048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.The uphill is slippery and muddy , It is impassable during raining season.
9889 | Infrastructure, Development & Maintenance | Gravelling of 1km Kongoi road | To implement gravelling of 1km kongoi road for road connectivity and accessibility | Gravelling of 1km Kongoi road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.177052 35.697812 2487.8 6.800000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1438000 | 143.8 | 1438000 | 1000000 | -438000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
9890 | Infrastructure, Development & Maintenance | Gravelling of factory lithia road | To implement gravelling of factory lithia road for road connectivity and accessibility | Gravelling of factory lithia road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.325895, 35.49856 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2989000 | 99.6 | 2989000 | 2989000 | 11000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.it is impassable during rainy season.
9891 | Infrastructure, Development & Maintenance | Gravelling of Franksways - Taragonik road | To implement gravelling of franksways - taragonik road for road connectivity and accessibility | Gravelling of Franksways - Taragonik road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.301405, 35.504565 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1438000 | 95.9 | 1438000 | 1438000 | 62000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement should be done,the road is very narrow,poor drainage.
9892 | Infrastructure, Development & Maintenance | Gravelling of Korabarret - Ogilgei corner 7Kms | To implement gravelling of korabarret - ogilgei corner 7kms for road connectivity and accessibility | Gravelling of Korabarret - Ogilgei corner 7Kms completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | KIPTORORO | -0.177052 35.697812 2487.8 6.800000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4191310 | 83.8 | 4191310 | 4191500 | 808690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
9893 | Infrastructure, Development & Maintenance | expansion of shuleni tarmac Road in kivumbini ward | To expand shuleni tarmac Road in kivumbini ward to increase capacity | Shuleni tarmac Road in kivumbini ward expanded | 3110499 | Construction of Roads - Other | NAKURU EAST | KIVUMBINI | -0.304157, 36.082921 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july 2022 | 5600001 | 0 | 5600000 | Equitable | N/A | 5600000 | 0 | 2132182 | 0 | 2132182 | 2133064 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes,. Viable: yes. Assessor remarks: chipped with potholes.
9894 | Infrastructure, Development & Maintenance | and bridge construction on Karimi-Kenyatta | To implement and bridge construction on karimi-kenyatta for road connectivity and accessibility | and bridge construction on Karimi-Kenyatta completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.45155 36.029847 2058.1 5.400000095367432 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5900000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3198850 | 100 | 3198850 | 0 | 1150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road need construction.
9895 | Infrastructure, Development & Maintenance | graging, Murraming on Karimi-Kenyatta road | To implement graging, murraming on karimi-kenyatta road for road connectivity and accessibility | graging, Murraming on Karimi-Kenyatta road completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.384527, 36.016745 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 5900000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2923687 | 97.5 | 2923687 | 2110574 | 76313 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
9896 | Infrastructure, Development & Maintenance | Murraming and culverting in Nguriga Centre roads | To implement murraming and culverting in nguriga centre roads for road connectivity and accessibility | Murraming and culverting in Nguriga Centre roads completed | 3110499 | Construction of Roads - Other | NJORO | LARE | -0.442215, 36.0103 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999144 | 100 | 1999144 | 1808250 | 856 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
9897 | Infrastructure, Development & Maintenance | Grading, murraming and compaction and drainage of NYS-Gatamaiyo-Nyakinyua road | To implement grading, murraming and compaction and drainage of nys-gatamaiyo-nyakinyua road for road connectivity and accessibility | Grading, murraming and compaction and drainage of NYS-Gatamaiyo-Nyakinyua road completed | 3110499 | Construction of Roads - Other | GILGIL | MALEWA WEST | -0.612613, 36.398477 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2882615 | 96.1 | 2882615 | 3000000 | 117385 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been consistently maintained.
9898 | Infrastructure, Development & Maintenance | Construction of drainage and culverts at Tayari farm road | To construct drainage and culverts at Tayari farm road | Drainage and culverts at Tayari farm road constructed | 3110499 | Construction of Roads - Other | MOLO | MOLO | -0.240857, 35.711253 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493907 | 99.6 | 1493907 | 1101 | 6093 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
9899 | Grading and gravelling of Kibunja Secondary school road | Grading and gravelling of Kibunja Secondary school road | To improve road infrastructure by grading and murraming Kibunja Secondary school road | Kibunja Secondary school road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO | -0.296743 35.713517 2682.1 8.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2019/20 | 3000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1488830 | 99.3 | 1488830 | 1488830 | 11170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
9900 | Infrastructure, Development & Maintenance | Grading and gravelling of Soin-Chesoen road | To improve road infrastructure by grading and murraming Soin-Chesoen road | Soin-Chesoen road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO | -0.205493, 35.796119 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2018/19 | 3000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499070 | 99.9 | 1499070 | 1499070 | 930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Status needs grading.
9901 | Infrastructure, Development & Maintenance | Grading and gravelling of Tayari-Moto road | To improve road infrastructure by grading and murraming Tayari-Moto road | Tayari-Moto road graded and murramed | 3110499 | Construction of Roads - Other | MOLO | MOLO | -0.245246, 35.719644 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2020/21 | 3000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 917055 | 91.7 | 917055 | 1000000 | 82945 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9902 | Infrastructure, Development & Maintenance | Grading and gravelling at Ha Nderitu-Kagumu primary Road | To improve road infrastructure by grading and murraming at Ha Nderitu-Kagumu primary Road | At Ha Nderitu-Kagumu primary Road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.402038, 36.293648 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 812223 | 73.8 | 812223 | 191977 | 287777 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ahnna Supplies Company Ltd. Assessor remarks: Good.
9903 | Infrastructure, Development & Maintenance | Grading and gravelling of Kahuho-Gitango road | To improve road infrastructure by grading and murraming Kahuho-Gitango road | Kahuho-Gitango road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1981343 | 132.1 | 1981343 | 1500000 | -481343 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
9904 | Grading and gravelling of Kangai- chemichemi road | Grading and gravelling of Kangai- chemichemi road | To improve road infrastructure by grading and murraming Kangai- chemichemi road | Kangai- chemichemi road graded and murramed | 3110499 | Construction of Roads - Other | GILGIL | MURINDAT | -0.50413, 36.381348 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1981343 | 99.1 | 1981343 | 17357 | 18657 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Durhas Construction. Assessor remarks: Good.
9905 | Infrastructure, Development & Maintenance | Roads maintenance within the ward | To implement roads maintenance within the ward for road connectivity and accessibility | Roads maintenance within the ward completed | 3110499 | Construction of Roads - Other | NAKURU EAST | NAKURU EAST | -0.291608, 36.114337 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3058340 | 76.5 | 3058340 | 946473 | 941660 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Glenwood construction limited. Assessor remarks: Project ok.
9906 | Infrastructure, Development & Maintenance | Grading and murraming of Soliat - Masaita dispensary Road | To improve road infrastructure by grading and murraming Soliat - Masaita dispensary Road | Soliat - Masaita dispensary Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1891670 | 94.6 | 1891670 | 88680 | 108330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
9907 | Infrastructure, Development & Maintenance | Grading and murraming of umoja secondary - Chepkinoyo Road | To improve road infrastructure by grading and murraming umoja secondary - Chepkinoyo Road | Umoja secondary - Chepkinoyo Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1994977 | 99.7 | 1994977 | 5023 | 5023 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
9908 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Kaplelach balozi masaita road | To implement gravelling and murraming of 3km of kaplelach balozi masaita road for road connectivity and accessibility | Gravelling and murraming of 3km of Kaplelach balozi masaita road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.390357, 35.690508 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018-2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2991943 | 99.7 | 2991943 | 2991944 | 8057 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
9909 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Mawingu Centre to lami juu road | To implement gravelling and murraming of 3km of mawingu centre to lami juu road for road connectivity and accessibility | Gravelling and murraming of 3km of Mawingu Centre to lami juu road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.301497 35.59234 2716 3.700000047683716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2962988 | 98.8 | 2962988 | 2962988 | 37012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
9910 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire | To implement gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire for road connectivity and accessibility | Gravelling and murraming of 3km of road at temoyetta secondary- ngarua bosire completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.352807, 35.604305 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018-2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2992550 | 99.8 | 2992550 | 2992551 | 7450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, just spot patches needed in some sections..
9911 | Infrastructure, Development & Maintenance | Gravelling and murraming of 6km road at Seguton to Langwenda road | To implement gravelling and murraming of 6km road at seguton to langwenda road for road connectivity and accessibility | Gravelling and murraming of 6km road at Seguton to Langwenda road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | NYOTA | -0.386155, 35.649127 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019-2020 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 4947850 | 82.5 | 4947850 | 4947850 | 1052150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Spot patches needed in some sections..
9912 | Infrastructure, Development & Maintenance | Grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | To improve road accessibility by grading and installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads | And installation of Culverts at Kaptembwo-Nyakinyua, Aeriol, Paulina Roads graded | 3110499 | Construction of Roads - Other | KURESOI NORTH | SIRIKWA | -0.253453, 35.671288 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3281000 | 82 | 3281000 | 715107 | 719000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bush clearing, culverting, drainage, murraming,, the residents have recently worked the road.
9913 | Infrastructure, Development & Maintenance | Grading, Gravelling and installation of culverts at Bygum-Set Kotes Road | To implement grading, gravelling and installation of culverts at bygum-set kotes road for road connectivity and accessibility | Grading, Gravelling and installation of culverts at Bygum-Set Kotes Road completed | 3110499 | Construction of Roads - Other | KURESOI NORTH | SIRIKWA | -0.311883, 35.68324 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997000 | 99.9 | 2997000 | 2997001 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Expansion of culvert and installation of guard rails.
9914 | Infrastructure, Development & Maintenance | Grading and murraming of Kapsetek centre-Kalasinga farm road | To improve road infrastructure by grading and murraming Kapsetek centre-Kalasinga farm road | Kapsetek centre-Kalasinga farm road graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOIN | -0.055935 36.076458 1641.2 3.200000047683716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1482680 | 98.8 | 1482680 | 119 | 17320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
9915 | Infrastructure, Development & Maintenance | Grading of peter chotara-sawaiti-Benita-border road | To improve road accessibility by grading peter chotara-sawaiti-Benita-border road | Peter chotara-sawaiti-Benita-border road graded | 3110499 | Construction of Roads - Other | RONGAI | SOIN | -0.118689 35.950928 1739 7.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 759300 | 94.9 | 759300 | 759300 | 40700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
9916 | Infrastructure, Development & Maintenance | Grading and murraming of Aruus-kwamusa-cherono roads | To improve road infrastructure by grading and murraming Aruus-kwamusa-cherono roads | Aruus-kwamusa-cherono roads graded and murramed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.015959 36.1597 1585.875 5.960999965667725 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991500 | 99.6 | 1991500 | 1000616 | 8500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
9917 | Infrastructure, Development and Maintenance | Grading, Murraming and construction of Gabion at white rock-Dip road | To implement grading, murraming and construction of gabion at white rock-dip road for road connectivity and accessibility | Grading, Murraming and construction of Gabion at white rock-Dip road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.159874 36.164702 1611.9619140625 8.440999984741211 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 252511 | 8.4 | 252511 | 252511 | 2747489 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is well maintained.
9918 | Infrastructure, Development & Maintenance | Murraming, construction of drift and light grading of Murram-Sigito road | To implement murraming, construction of drift and light grading of murram-sigito road for road connectivity and accessibility | Murraming, construction of drift and light grading of Murram-Sigito road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.046738 36.12905 1518.959228515625 3.7899999618530273 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2490729 | 99.6 | 2490729 | 2471 | 9271 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9919 | Infrastructure, Development & Maintenance | Spot Murraming and grading of Tuyotich-Chemasis road | To implement spot murraming and grading of tuyotich-chemasis road for road connectivity and accessibility | Spot Murraming and grading of Tuyotich-Chemasis road completed | 3110499 | Construction of Roads - Other | RONGAI | SOLAI | 0.023199, 36.126949 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 105750 | 5.3 | 105750 | 105750 | 1894250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
9920 | Grading and Gravelling of Chebalungu Road | Grading and Gravelling of Chebalungu Road | To improve road infrastructure by grading and murraming Chebalungu Road | Chebalungu Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999588 | 100 | 1999588 | 1999588 | 412 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
9921 | Infrastructure, Development & Maintenance | Grading and Gravelling of Sotiki Chepsoi Road | To improve road infrastructure by grading and murraming Sotiki Chepsoi Road | Sotiki Chepsoi Road graded and murramed | 3110499 | Construction of Roads - Other | KURESOI SOUTH | TINET | -0.547201, 35.674632 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2952403 | 98.4 | 2952403 | 43364 | 47597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage because of heavy rain.
9922 | Infrastructure, Development & Maintenance | Grading and gravelling of Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | To improve road infrastructure by grading and murraming Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads graded and murramed | 3110499 | Construction of Roads - Other | MOLO | TURI | -0.32764, 35.739845 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5200000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2524633 | 72.1 | 2524633 | 975367 | 975367 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Is good use.
9923 | Infrastructure, Development & Maintenance | Grading and Gravelling of Akuisi-kiriko road | To improve road infrastructure by grading and murraming Akuisi-kiriko road | Akuisi-kiriko road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1294500 | 99.6 | 1294500 | 1300000 | 5500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
9924 | Infrastructure, Development & Maintenance | Grading and Gravelling of baharini-Kericho road | To improve road infrastructure by grading and murraming baharini-Kericho road | Baharini-Kericho road graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 857463 | 42.9 | 857463 | 901112 | 1142537 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
9925 | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | Grading and gravelling of Wiyumiriria mbata moja -Ogilgei | To improve road infrastructure by grading and murraming Wiyumiriria mbata moja -Ogilgei | Wiyumiriria mbata moja -Ogilgei graded and murramed | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1979543 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
9926 | Infrastructure, Development & Maintenance | Grading of Mwiteithia-Suswa road (Kahuruko) | To improve road accessibility by grading Mwiteithia-Suswa road (Kahuruko) | Mwiteithia-Suswa road (Kahuruko) graded | 3110499 | Construction of Roads - Other | SUBUKIA | WASEGES | 0.16629, 36.249878 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 193044 | 14.8 | 193044 | 193044 | 1106956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
9927 | Infrastructure, Development and Maintenance | Construction of Njeru bridge | To construct Njeru bridge | Njeru bridge constructed | 3110501 | Bridges | GILGIL | ELEMENTAITA | -0.581721 36.082011 2049.59 0.9729999899864197 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3392375 | 169.6 | 3392375 | 3394694 | -1392375 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
9928 | Infrastructure, Development & Maintenance | Construction of bridges at Musaka, Kuiwait and Nyamathi | To construct bridges at Musaka, Kuiwait and Nyamathi | Bridges at Musaka, Kuiwait and Nyamathi constructed | 3110501 | Bridges | NAIVASHA | HELLS GATE | -0.777804, 36.45138 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1815785 | 90.8 | 1815785 | 139627 | 184215 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is passable but it needs reinforcement.
9929 | Infrastructure, Development & Maintenance | Construction of Motorable and Foot-Bridges | To construct Motorable and Foot-Bridges | Motorable and Foot-Bridges constructed | 3110501 | Bridges | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 70000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 6978545 | 100 | 6978545 | 15000000 | -6978545 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9930 | grading and murraming and culverts for access roads in kabazi ward | grading and murraming and culverts for access roads in kabazi ward | To improve road infrastructure by grading and murraming and culverts for access roads in kabazi ward | And culverts for access roads in kabazi ward graded and murramed | 3110501 | Bridges | SUBUKIA | KABAZI | -0.07772, 36.17076 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020/21 | 4989241 | 0 | 3989241 | Equitable | N/A | 3989241 | 0 | 3386875 | 0 | 3386875 | 3386875 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires additional drainages.
9931 | Infrastructure, Development & Maintenance | Construction bridges & drainages and installation of Culverts | To construct bridges & drainages and installation of Culverts | Bridges & drainages and installation of Culverts constructed | 3110501 | Bridges | KURESOI NORTH | KAMARA | -0.172682 35.679654 2519.9 36.900001525878906 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 499284 | 23.8 | 499284 | 499284 | 1600716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs renovation.
9932 | Infrastructure, Development & Maintenance | Construction of Kigomba bridge | To construct Kigomba bridge | Kigomba bridge constructed | 3110501 | Bridges | KURESOI SOUTH | KIPTAGICH | -0.590645 35.59291 2486.400146484375 50.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functions.
9933 | Infrastructure, Development & Maintenance | Construction of foot bridge at Kwa Muiruri - Kamuingi | To construct foot bridge at Kwa Muiruri - Kamuingi | Foot bridge at Kwa Muiruri - Kamuingi constructed | 3110501 | Bridges | KURESOI NORTH | KIPTORORO | -0.168805 35.689275 2517.4 3.799999952316284 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1272998 | 424.3 | 1272998 | 300000 | -972998 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete but needs tank and pit latrines.
9934 | Infrastructure, Development & Maintenance | Construction of the two foot bridge at Mutogi- Korabariet, Buchege - Ogilgei | To construct the two foot bridge at Mutogi- Korabariet, Buchege - Ogilgei | The two foot bridge at Mutogi- Korabariet, Buchege - Ogilgei constructed | 3110501 | Bridges | KURESOI NORTH | KIPTORORO | -0.377203 35.505747 0 800 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
9935 | Infrastructure, Development & Maintenance | drainage and culverts for Maai mahiu Roads | To implement drainage and culverts for maai mahiu roads for road connectivity and accessibility | drainage and culverts for Maai mahiu Roads completed | 3110501 | Bridges | NAIVASHA | MAAI MAHIU | -0.980223, 36.587151 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4817870 | 240.9 | 4817870 | 1932328 | -2817870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs unclogging and maintenance.
9936 | installation of high mast streetlights | installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110501 | Bridges | NAIVASHA | MAAI MAHIU | -0.979929, 36.578177 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933030 | 96.7 | 1933030 | 1933030 | 66970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Destroyed by flash floods.
9937 | Infrastructure, Development and Maintenance | Construction of bridge at Tayari- Molo | To construct bridge at Tayari- Molo | Bridge at Tayari- Molo constructed | 3110501 | Bridges | MOLO | MOLO | -0.801138, 36.513198 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3994693 | 99.9 | 3994693 | 5287 | 5307 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: It is very useful.
9938 | Infrastructure, Development & Maintenance | construction of Kallangat police post bridge | To construct Kallangat police post bridge | Kallangat police post bridge constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.378313, 35.9119 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2296800 | 255.2 | 2296800 | 900000 | -1396800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Non. Viable: No. Assessor remarks: The project never commenced due to insufficient funds on the scope of work needed. The money was reallocated to another project. The residents need a bride constructed for safety of the users.
9939 | Infrastructure, Development and Maintenance | construction of Kamugulet bridge | To construct Kamugulet bridge | Kamugulet bridge constructed | 3110501 | Bridges | NJORO | NESSUIT | -0.430448, 35.905942 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2296800 | 99.9 | 2296800 | 2296800 | 3200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: The bridge serves a big population especially school going children that use it to access school..
9940 | Construction of a footbridge at Kapsepeiywo | Construction of a footbridge at Kapsepeiywo | To construct a footbridge at Kapsepeiywo | A footbridge at Kapsepeiywo constructed | 3110501 | Bridges | RONGAI | SOIN | -0.068868, 36.044463 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499900 | 100 | 1499900 | 1500000 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repair.
9941 | Infrastructure, Development & Maintenance | Construction of a footbridge at Tuyomoi-Kiambogo | To construct a footbridge at Tuyomoi-Kiambogo | A footbridge at Tuyomoi-Kiambogo constructed | 3110501 | Bridges | RONGAI | SOLAI | 0.149031 36.196507 1685.18115234375 4.056000232696533 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
9942 | Infrastructure, Development and Maintenance | Construction of Taita Kapno Bridge | To construct Taita Kapno Bridge | Taita Kapno Bridge constructed | 3110501 | Bridges | KURESOI SOUTH | TINET | -0.445126 35.609035 0 2200 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2971834 | 99.1 | 2971834 | 20966 | 28166 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
9943 | Infrastructure, Development & Maintenance | Grading and Gravelling of Kamwaura- Angurwet Road | To improve road infrastructure by grading and murraming Kamwaura- Angurwet Road | Kamwaura- Angurwet Road graded and murramed | 3110501 | Bridges | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2979535 | 99.3 | 2979535 | 15586 | 20465 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
9944 | Infrastructure, Development & Maintenance | Construction of bridges at Nyeki and Kanyiriri (Ndenderu A) | To construct bridges at Nyeki and Kanyiriri (Ndenderu A) | Bridges at Nyeki and Kanyiriri (Ndenderu A) constructed | 3110501 | Bridges | MOLO | TURI | -0.289708, 35.738825 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1174638 | 97.9 | 1174638 | 186 | 25362 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is a movement of people from both sides of the valley.
9945 | Infrastructure, Development and Maintenance | Repair of bridges at kware, thirandu and kanga | To rehabilitate bridges at kware, thirandu and kanga to restore functionality | Bridges at kware, thirandu and kanga rehabilitated | 3110501 | Bridges | RONGAI | VISOI | -0.139406 35.905676 1808.19482421875 5.670000076293945 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1237905 | 88.4 | 1237905 | 1400000 | 162095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9946 | Construction of Wei cross bridge | Construction of Wei cross bridge | To construct Wei cross bridge | Wei cross bridge constructed | 3110501 | Bridges | SUBUKIA | WASEGES | 0.005697 36.25448 2085.5 13.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2019/20 | 3500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 941839 | 94.2 | 941839 | 1096 | 58161 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The is in use.
9947 | Infrastructure, Development and Maintenance | installation of highmast streetlights (mulika mwizi) in Bahati ward | To improve security lighting through high mast floodlight installation at streetlights (mulika mwizi) in Bahati ward | High mast floodlight installed at streetlights (mulika mwizi) in Bahati ward | 3110504 | Other Infrastructure and Civil Works | BAHATI | BAHATI | -0.194242, 36.133374 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 0 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
9948 | Infrastructure, Development & Maintenance | construction of a bridge between sewage and mwariki and St. Lukes | To construct a bridge between sewage and mwariki and St. Lukes | A bridge between sewage and mwariki and St. Lukes constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | 0.327123, 36.05335 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 4606400 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: M/s Jasmin construction limited. Assessor remarks: The project it was never done..
9949 | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Construction of Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | To construct Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael | Boda-boda sheds at Mwariki, Kwa Osborn, Tumaini School junction and Kwa Michael constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | 0.353373, 36.049497 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1193025 | 99.4 | 1193025 | 1200000 | 6975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Gibous Ventures. Assessor remarks: Complete and in use..
9950 | Infrastructure, Development & Maintenance | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.254746, 36.233905 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 871400 | 87.1 | 871400 | 1000000 | 128600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Holy sons. Assessor remarks: Good require maintenance.
9951 | Construction of drainage system at Eastleigh/ Jerusalem | Construction of drainage system at Eastleigh/ Jerusalem | To construct drainage system at Eastleigh/ Jerusalem | Drainage system at Eastleigh/ Jerusalem constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | ELBURGON | -0.288188 35.816137 2443.8 11.800000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999990 | 100 | 999990 | 77950 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9952 | Infrastructure, Development & Maintenance | Installation of 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | To install 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate | 10 (13m) highmast streetlights at Lake view estate (kipsigis road), langa langa estate and race course estate installed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.302653, 36.072775 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 2000000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1420750 | 78.9 | 1420750 | 1497250 | 379250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
9953 | Infrastructure, Development and Maintenance | Construction of Storm water Drains | To construct Storm water Drains | Storm water Drains constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 40000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 6978545 | 34.9 | 6978545 | 3021455 | 13021455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9954 | Infrastructure, Development & Maintenance | Installation of 4 sets of high mast security lights | To install 4 sets of high mast security lights | 4 sets of high mast security lights installed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.176363, 35.7124 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995000 | 99.8 | 1995000 | 1995000 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance. Some of them are not functional.
9955 | Infrastructure, Development & Maintenance | Rehabiltation of drainage system | To implement rehabiltation of drainage system for road connectivity and accessibility | Rehabiltation of drainage system completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.288288, 36.036492 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493907 | 99.6 | 1493907 | 0 | 6093 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved on water drainage. Assessor remarks: Done and serving well. Draining water efficiently.
9956 | maintenance of drainages and foot bridges | maintenance of drainages and foot bridges | To implement maintenance of drainages and foot bridges for road connectivity and accessibility | maintenance of drainages and foot bridges completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.302037 36.061704 1798.800048828125 52.400001525878906 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3399000 | 100 | 3399000 | 3400000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: M/S LEGIO GENERAL. Assessor remarks: Clogged, needs rehabilitation.
9957 | Infrastructure, Development & Maintenance | streetlighting maintenance | To implement streetlighting maintenance for road connectivity and accessibility | streetlighting maintenance completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.302265, 36.058547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It's a viable project, it's has met the needs of the residents. Contractor: Y72. Assessor remarks: It functional.
9958 | Infrastructure, Development & Maintenance | Construction of Storm water drains in Rurii, workers and Menengai | To construct Storm water drains in Rurii, workers and Menengai | Storm water drains in Rurii, workers and Menengai constructed | 3110504 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.268282 36.11517 1863.800048828125 4.699999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3302288 | 82.6 | 3302288 | 3302288 | 697712 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
9959 | Infrastructure, Development & Maintenance | Installation of streetlights In the ward | To improve lighting and safety through installation of solar streetlights at the ward | Solar streetlights installed at the ward | 3110504 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.231536 36.116876 1940.9000244140625 19.493999481201172 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4500000 | 5899024 | Equitable | N/A | 5899024 | 0 | 3613850 | 80.3 | 3613850 | 5899024 | 886150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The contractor is yet to begin the works.
9960 | Infrastructure, Development & Maintenance | Construction of drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages | To construct drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages | Drainage and culverts around Store mbili, Kihingo and Gachuhe and ndeffo villages constructed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.407653, 35.965057 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 5400000 | 5400000 | 5400000 | Equitable | N/A | 5400000 | 0 | 5108568 | 94.6 | 5108568 | 89624 | 291432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
9961 | Infrastructure, Development & Maintenance | Grading and murraming of Kihingo Centre, and Ndeffo centre roads | To improve road infrastructure by grading and murraming Kihingo Centre, and Ndeffo centre roads | Kihingo Centre, and Ndeffo centre roads graded and murramed | 3110504 | Other Infrastructure and Civil Works | NJORO | KIHINGO | -0.433545, 35.973563 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4284631 | 85.7 | 4284631 | 58361 | 715369 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance required.
9962 | Infrastructure, Development and Maintenance | Installation of security lights | To install security lights | Security lights installed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.296244, 36.084835 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497250 | 99.8 | 1497250 | 1500000 | 2750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
9963 | Infrastructure, Development & Maintenance | maintenance of Streetlights in kivumbini ward | To implement maintenance of streetlights in kivumbini ward for road connectivity and accessibility | maintenance of Streetlights in kivumbini ward completed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.298543, 36.086344 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
9964 | Infrastructure, Development & Maintenance | Installation of High mast streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | To improve security lighting through high mast floodlight installation at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | High mast floodlight installed at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, kichinjio road, remdic stop, Mtaa B and Ndege Ndimu | 3110504 | Other Infrastructure and Civil Works | BAHATI | LANET UMOJA | -0.275097, 36.174683 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 762100 | 23.8 | 762100 | 3198500 | 2437900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
9965 | Infrastructure, Development & Maintenance | Installation of streetlights in Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | To improve lighting and safety through installation of solar streetlights at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | Solar streetlights installed at Ndulele, Kapyemit, Sinendet, Muthiga,Miliimani and Kilo | 3110504 | Other Infrastructure and Civil Works | NJORO | LARE | -0.409943, 36.002193 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799920 | 100 | 1799920 | 1799920 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installed sub standard lights and need maintenance.
9966 | Infrastructure, Development & Maintenance | Construction of drainage and culverts in London Ward | To construct drainage and culverts in London Ward | Drainage and culverts in London Ward constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498125 | 99.9 | 2498125 | 4716 | 1875 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
9967 | Infrastructure, Development and Maintenance | Installation of high mast flood lights in London Ward | To improve security lighting through high mast floodlight installation at flood lights in London Ward | High mast floodlight installed at flood lights in London Ward | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274075, 36.058162 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2880600 | 82.3 | 2880600 | 3500000 | 619400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
9968 | Infrastructure, Development & Maintenance | Installation of Culverts at KK Quarry Road | To improve drainage and road access through culvert installation at KK Quarry Road | Culverts installed at KK Quarry Road | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more installation of culverts.
9969 | Infrastructure, Development & Maintenance | Installation of High mast Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | To improve security lighting through high mast floodlight installation at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | High mast floodlight installed at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | 3110504 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703, 36.489231 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999100 | 99.9 | 999100 | 999100 | 900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2019/20. Assessor remarks: Good work.
9970 | Infrastructure, Development & Maintenance | construction of Kamungei bridge | To construct Kamungei bridge | Kamungei bridge constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | -0.346125, 35.818593 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 30510811 | 1525.5 | 30510811 | 4000000 | -28510811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
9971 | Infrastructure, Development & Maintenance | grading and murraming of Rombei road- Tuiyobei road | To improve road infrastructure by grading and murraming Rombei road- Tuiyobei road | Rombei road- Tuiyobei road graded and murramed | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9972 | installation of culverts at Kondamet footbidge | installation of culverts at Kondamet footbidge | To improve drainage and road access through culvert installation at Kondamet footbidge | Culverts installed at Kondamet footbidge | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | -0.334026, 35.892891 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 9084220 | 908.4 | 9084220 | 15000000 | -8084220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bridge construction was done well.
9973 | installation of culverts at Marioshoni centre | installation of culverts at Marioshoni centre | To improve drainage and road access through culvert installation at Marioshoni centre | Culverts installed at Marioshoni centre | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | -0.370649, 35.824203 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 9084220 | 1816.8 | 9084220 | 11515780 | -8584220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor workmanship.
9974 | Infrastructure, Development & Maintenance | installation of culverts at Nduswa - Biston junction road | To improve drainage and road access through culvert installation at Nduswa - Biston junction road | Culverts installed at Nduswa - Biston junction road | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | -0.363089, 35.866439 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 34189000 | 6837.8 | 34189000 | 5811000 | -33689000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
9975 | Infrastructure, Development & Maintenance | installation of Kapkein culvert | To install Kapkein culvert | Kapkein culvert installed | 3110504 | Other Infrastructure and Civil Works | MOLO | MARIOSHONI | -0.34134, 35.886222 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1869923 | 1869923 | 1869923 | Equitable | N/A | 1869923 | 0 | 9084220 | 485.8 | 9084220 | 11515780 | -7214297 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
9976 | Infrastructure, Development & Maintenance | Installation of high mast lights at Mau Narok, metta AP Camp and utalii dam | To improve security lighting through high mast floodlight installation at lights at Mau Narok, metta AP Camp and utalii dam | High mast floodlight installed at lights at Mau Narok, metta AP Camp and utalii dam | 3110504 | Other Infrastructure and Civil Works | NJORO | MAU NAROK | -0.58119, 36.034068 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 512900 | 85.5 | 512900 | 87100 | 87100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
9977 | Construction of drainage system at Kiratina in Menengai East | Construction of drainage system at Kiratina in Menengai East | To construct drainage system at Kiratina in Menengai East | Drainage system at Kiratina in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI EAST | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000003 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2997950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9978 | Infrastructure, Development and Maintenance | Construction of drainage system at Lower teachers in Menengai East | To construct drainage system at Lower teachers in Menengai East | Drainage system at Lower teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI EAST | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000002 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2980455 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9979 | Infrastructure, Development and Maintenance | Construction of drainage system at upper teachers in Menengai East | To construct drainage system at upper teachers in Menengai East | Drainage system at upper teachers in Menengai East constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI EAST | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 14000001 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2997556 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
9980 | Infrastructure, Development & Maintenance | Construction of drainage and culverts at Kenyatta Estate | To construct drainage and culverts at Kenyatta Estate | Drainage and culverts at Kenyatta Estate constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO | -0.380641 35.796196 2793.679531111378 6 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 989607 | 99 | 989607 | 1000000 | 10393 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
9981 | Infrastructure, Development and Maintenance | Installation of floodlight at Tayari | To install floodlight at Tayari | Floodlight at Tayari installed | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO | -0.241711, 35.724926 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3887000 | 259.1 | 3887000 | 1500000 | -2387000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Faulty.
9982 | Infrastructure, Development and Maintenance | Installation of streetlights at Chazon and Gateiguru | To improve lighting and safety through installation of solar streetlights at Chazon and Gateiguru | Solar streetlights installed at Chazon and Gateiguru | 3110504 | Other Infrastructure and Civil Works | MOLO | MOLO | -0.232085, 35.705662 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1320450 | 220.1 | 1320450 | 600000 | -720450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
9983 | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | construction of drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | To construct drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road | Drainage and gabions culvert in Ngata , Kirobon, A.I.C Roret road constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.266963 36.0019 2029.9000244140625 20 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 0 | 1600000 | Equitable | N/A | 1600000 | 0 | 1199200 | 0 | 1199200 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
9984 | Infrastructure, Development & Maintenance | Construction of Salgaa drainage system | To construct Salgaa drainage system | Salgaa drainage system constructed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.207391, 35.847733 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3727314 | 93.2 | 3727314 | 1239800 | 272686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: No indicated. Assessor remarks: Good.
9985 | Infrastructure, Development & Maintenance | Installation of Culverts in various roads in the ward | To improve drainage and road access through culvert installation at in various roads in the ward | Culverts installed at in various roads in the ward | 3110504 | Other Infrastructure and Civil Works | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
9986 | Infrastructure, Development & Maintenance | Construction of Motorcycle sheds within the ward | To construct Motorcycle sheds within the ward | Motorcycle sheds within the ward constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | NAKURU EAST | -0.296102 36.128055 1847.4000244140625 4.599999904632568 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988358 | 99.7 | 3988358 | 4000000 | 11642 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cleafield contractors limited. Assessor remarks: Project ok.
9987 | Infrastructure, Development & Maintenance | Installation of high mast flood lights in Njoro ward | To improve security lighting through high mast floodlight installation at flood lights in Njoro ward | High mast floodlight installed at flood lights in Njoro ward | 3110504 | Other Infrastructure and Civil Works | NJORO | NJORO | -0.335004, 35.960373 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 765700 | 85.1 | 765700 | 133300 | 134300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rivtok contractors Ltd. Assessor remarks: In good state.
9988 | Construction of drainage system in Rhonda | Construction of drainage system in Rhonda | To construct drainage system in Rhonda | Drainage system in Rhonda constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.308484, 36.063407 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 18/20 | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4991500 | 99.8 | 4991500 | 5000000 | 8500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s biscon construction. Assessor remarks: Needs rehabilitation.
9989 | Infrastructure, Development and Maintenance | Construction of a drainage system at Githima | To construct a drainage system at Githima | A drainage system at Githima constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAAB | -0.290375, 36.043853 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
9990 | Infrastructure, Development & Maintenance | Installation of streetlights at Sondu Drive | To improve lighting and safety through installation of solar streetlights at Sondu Drive | Solar streetlights installed at Sondu Drive | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAAB | -0.294398, 36.055154 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3497000 | 99.9 | 3497000 | 3000 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Paid.
9991 | Infrastructure, Development & Maintenance | Unblocking of drainage system in Shabab Ward | To implement unblocking of drainage system in shabab ward for road connectivity and accessibility | Unblocking of drainage system in Shabab Ward completed | 3110504 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAAB | -0.297011, 36.057943 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
9992 | Installation of Culverts and grading of Sirikwa Access road | Installation of Culverts and grading of Sirikwa Access road | To improve drainage and road access through culvert installation at and grading of Sirikwa Access road | Culverts installed at and grading of Sirikwa Access road | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | SIRIKWA | -0.278465 35.661547 2738.7 13.399999618530273 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999000 | 100 | 3999000 | 4000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
9993 | Infrastructure, Development & Maintenance | Installation of 1 floodlights at Banita Goat auction ground | To install 1 floodlights at Banita Goat auction ground | 1 floodlights at Banita Goat auction ground installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.065528, 36.063015 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299700 | 99.9 | 299700 | 299700 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floodlight is ok.
9994 | Infrastructure, Development & Maintenance | Installation of 4 floodlights at rafiki area | To install 4 floodlights at rafiki area | 4 floodlights at rafiki area installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.150125, 35.958591 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1164900 | 97.1 | 1164900 | 1200000 | 35100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require repair and additional streetlight at the end of the street.
9995 | Infrastructure, Development & Maintenance | Installation of floodlights at Kamundu Centre | To install floodlights at Kamundu Centre | Floodlights at Kamundu Centre installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.082257 35.872951 1817 10 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 280000 | 93.3 | 280000 | 300000 | 20000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Two lights not working.
9996 | Installation of floodlights at majai mingy | Installation of floodlights at majai mingy | To install floodlights at majai mingy | Floodlights at majai mingy installed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOIN | -0.055765 36.026265 1647.0999755859375 6.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 299450 | 99.8 | 299450 | 299450 | 550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working in good condition.
9997 | Infrastructure, Development & Maintenance | Culverting and spot murraming at Majitamu Academy-Dairy road | To implement culverting and spot murraming at majitamu academy-dairy road for road connectivity and accessibility | Culverting and spot murraming at Majitamu Academy-Dairy road completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOLAI | 0.00759, 36.157721 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691724 | 99.5 | 1691724 | 1000616 | 8276 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
9998 | Infrastructure, Development & Maintenance | Construction of drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary | To construct drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary | Drainage at Rafiki, and Muchorwe and installation of Mulika mwizi at Mwangaza primary constructed | 3110504 | Other Infrastructure and Civil Works | MOLO | TURI | -0.248077 35.730962 2517.6 200 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
9999 | Infrastructure, Development & Maintenance | Construction of boda-boda sheds in Dundori ward | To construct boda-boda sheds in Dundori ward | Boda-boda sheds in Dundori ward constructed | 3110599 | Other Infrastructure and Civil Works | BAHATI | DUNDORI | -0.247407, 36.182378 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 498406 | 49.8 | 498406 | 896622 | 501594 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin construction ltd. Assessor remarks: Good three in number.
10000 | Infrastructure, Development & Maintenance | Construction of Lorry Park | To construct Lorry Park | Lorry Park constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 6978545 | 69.8 | 6978545 | 10000000 | 3021455 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10001 | Construction of four boda-boda sheds | Construction of four boda-boda sheds | To construct four boda-boda sheds | Four boda-boda sheds constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.181143 35.712828 2481.3 2.9000000953674316 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998600 | 99.9 | 998600 | 0 | 1400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs seats and painting.
10002 | Infrastructure, Development and Maintenance | Construction of one motorbike shade at high junction to Kasarani | To construct one motorbike shade at high junction to Kasarani | One motorbike shade at high junction to Kasarani constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.630631 36.398601 0 2000 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Vandalism common in the area. The project destroyed through vandalism.
10003 | Infrastructure, Development & Maintenance | construction of Boda boda sheds at Njoro | To construct Boda boda sheds at Njoro | Boda boda sheds at Njoro constructed | 3110599 | Other Infrastructure and Civil Works | NJORO | NJORO | -0.332853, 35.943837 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1296168 | 1296168 | 1296168 | Equitable | N/A | 1296168 | 0 | 1199768 | 92.6 | 1199768 | 1 | 96400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Solid Floor not provided.
10004 | Provision for Purchase of Telescopic Vehicle | Provision for Purchase of Telescopic Vehicle | To implement provision for purchase of telescopic vehicle for road connectivity and accessibility | Provision for Purchase of Telescopic Vehicle completed | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 0 | 0 | 0 | 5870000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10005 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of D8 dozer 1No) | To rehabilitate Rural Road(Provision for purchase of D8 dozer 1No) to restore functionality | Rural Road(Provision for purchase of D8 dozer 1No) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 21000000 | 21000000 | 21000000 | Equitable | N/A | 21000000 | 0 | 49500000 | 235.7 | 49500000 | 5870000 | -28500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10006 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Excavator 4No) | To rehabilitate Rural Road(Provision for purchase of Excavator 4No) to restore functionality | Rural Road(Provision for purchase of Excavator 4No) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 56000000 | 56000000 | 56000000 | Equitable | N/A | 56000000 | 0 | 49500000 | 88.4 | 49500000 | 5870000 | 6500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10007 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of grader 1 No.) | To rehabilitate Rural Road(Provision for purchase of grader 1 No.) to restore functionality | Rural Road(Provision for purchase of grader 1 No.) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 30000000 | 30000000 | 30000000 | Equitable | N/A | 30000000 | 0 | 49500000 | 165 | 49500000 | 5870000 | -19500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10008 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Low Loader lower Bed1No) | To rehabilitate Rural Road(Provision for purchase of Low Loader lower Bed1No) to restore functionality | Rural Road(Provision for purchase of Low Loader lower Bed1No) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 49500000 | 707.1 | 49500000 | 0 | -42500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10009 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Rollers 4No) | To rehabilitate Rural Road(Provision for purchase of Rollers 4No) to restore functionality | Rural Road(Provision for purchase of Rollers 4No) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 32000000 | 32000000 | 32000000 | Equitable | N/A | 32000000 | 0 | 49500000 | 154.7 | 49500000 | 5870000 | -17500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10010 | Infrastructure, Development & Maintenance | Rehabilitation of Rural Road(Provision for purchase of Tippers 8No) | To rehabilitate Rural Road(Provision for purchase of Tippers 8No) to restore functionality | Rural Road(Provision for purchase of Tippers 8No) rehabilitated | 3110799 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 64000000 | 64000000 | 64000000 | Equitable | N/A | 64000000 | 0 | 49500000 | 77.3 | 49500000 | 5870000 | 14500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10011 | Infrastructure, Development & Maintenance | Provision for Purchase of Fire Engine (1No) | To implement provision for purchase of fire engine (1no) for road connectivity and accessibility | Provision for Purchase of Fire Engine (1No) completed | 3111106 | Purchase of firefighting Vehicles and Equipment | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 100000000 | 50000000 | 50000000 | Equitable | N/A | 50000000 | 0 | 49500000 | 99 | 49500000 | 5870000 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10012 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts and compacting of teachers A - Ebenezar Road | To implement grading, gravelling, installation of culverts and compacting of teachers a - ebenezar road for road connectivity and accessibility | Grading, gravelling, installation of culverts and compacting of teachers A - Ebenezar Road completed | 3111499 | Research & Feasibility Studies | GILGIL | GILGIL | -0.488405, 36.32907 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1982774 | 99.1 | 1982774 | 168 | 17226 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: Needs maintainance and culverts.
10013 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts and compaction of Yu Mwema - Manyatta road | To implement grading, gravelling, installation of culverts and compaction of yu mwema - manyatta road for road connectivity and accessibility | Grading, gravelling, installation of culverts and compaction of Yu Mwema - Manyatta road completed | 3111499 | Research & Feasibility Studies | GILGIL | GILGIL | -0.479745, 36.298072 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1993400 | 99.7 | 1993400 | 1993400 | 6600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s phelmon limited. Assessor remarks: Requires maintainance.
10014 | Infrastructure, Development & Maintenance | Grading, gravelling, installation of culverts at Kekopey police line estate Road | To implement grading, gravelling, installation of culverts at kekopey police line estate road for road connectivity and accessibility | Grading, gravelling, installation of culverts at Kekopey police line estate Road completed | 3111499 | Research & Feasibility Studies | GILGIL | GILGIL | -0.474783, 36.289046 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1951377 | 97.6 | 1951377 | 3623 | 48623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Oriel General suppliers and contractors. Assessor remarks: Regular maintainance of other feeder roads at the estate.
10015 | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | Grading and Murraming of Lower Kapjorwa- Ketyenya Junction Road | To improve road infrastructure by grading and murraming Lower Kapjorwa- Ketyenya Junction Road | Lower Kapjorwa- Ketyenya Junction Road graded and murramed | 3111504 | N/A | KURESOI SOUTH | AMALO | -0.611516, 35.683798 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 404826 | 20.2 | 404826 | 404826 | 1595174 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: 2021.
10016 | Mzalendo - Kiptenden-Molit-Kiptenden-Kiptaragon foot bridges in Amalo Ward Kuresoi South Sub County : 1200mm ID -2 lines & 1800mm - 8m 1 line | Mzalendo - Kiptenden-Molit-Kiptenden-Kiptaragon foot bridges in Amalo Ward Kuresoi South Sub County : 1200mm ID -2 lines & 1800mm - 8m 1 line | To implement mzalendo - kiptenden-molit-kiptenden-kiptaragon foot bridges in amalo ward kuresoi south sub county : 1200mm id -2 lines & 1800mm - 8m 1 line for road connectivity and accessibility | Mzalendo - Kiptenden-Molit-Kiptenden-Kiptaragon foot bridges in Amalo Ward Kuresoi South Sub County : 1200mm ID -2 lines & 1800mm - 8m 1 line completed | 3111504 | N/A | KURESOI SOUTH | AMALO | -0.570158, 35.691877 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: no. Assessor remarks: footbridge not yet started.
10017 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County | To maintain Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Sinendet Road in Amalo Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | AMALO | -0.572453 35.70533 2542.400146484375 4.199999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999360 | 1999360 | 1999360 | Equitable | N/A | 1999360 | 0 | 1983000 | 99.2 | 1983000 | 1999360 | 16360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: partially. Assessor remarks: road requires murraming.
10018 | Construction of 5No.Motor Cycle Sheds in Bahati Ward Bahati Sub County | Construction of 5No.Motor Cycle Sheds in Bahati Ward Bahati Sub County | To construct 5No.Motor Cycle Sheds in Bahati Ward Bahati Sub County | 5No.Motor Cycle Sheds in Bahati Ward Bahati Sub County constructed | 3111504 | N/A | BAHATI | BAHATI | -0.158721, 36.117363 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1380922 | 1380922 | 1380922 | Equitable | N/A | 1380922 | 0 | 0 | 0 | 0 | 1380922 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires rehabilitation.
10019 | Infrastructure, Development & Maintenance | Gwa Kabebe Road and Footbridge | To implement gwa kabebe road and footbridge for road connectivity and accessibility | Gwa Kabebe Road and Footbridge completed | 3111504 | N/A | BAHATI | BAHATI | -0.125847, 36.178007 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Stalled | 75 | N/A | terminated | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition.
10020 | Routine Maintenance and Spot Improvement of Gatitu - Karuri Access Road in Bahati Ward Bahati Sub County | Routine Maintenance and Spot Improvement of Gatitu - Karuri Access Road in Bahati Ward Bahati Sub County | To maintain Spot Improvement of Gatitu - Karuri Access Road in Bahati Ward Bahati Sub County in serviceable condition | Spot Improvement of Gatitu - Karuri Access Road in Bahati Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | BAHATI | -0.160354, 36.18451 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2999910.34 | 2999910.34 | 2999910.34 | Equitable | N/A | 2999910.34 | 0 | 860526 | 28.7 | 860526 | 2999910 | 2139384.34 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in use.
10021 | Infrastructure, Development & Maintenance | Grading and Murruming of St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County | To improve road infrastructure by grading and murraming St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County | St. Lukes - Ndingi road in Barut Ward-Nakuru West Sub County graded and murramed | 3111504 | N/A | NAKURU WEST | BARUT | -0.306306, 36.036551 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016 | 2991350 | 2991350 | 2991350 | Equitable | N/A | 2991350 | 0 | 2991350 | 100 | 2991350 | 2991350 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Nyati E.A Ltd. Assessor remarks: The road is good.
10022 | Infrastructure, Development & Maintenance | installation of barut centre highmast streetlights | To install barut centre highmast streetlights | Barut centre highmast streetlights installed | 3111504 | N/A | NAKURU WEST | BARUT | -0.32425 36.4568 0 2000 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933050 | 96.7 | 1933050 | 1933050 | 66950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M.s Topal Enterprises. Assessor remarks: In good state of repair.
10023 | Infrastructure, Development & Maintenance | installation of Mwariki muungano streetlights | To install Mwariki muungano streetlights | Mwariki muungano streetlights installed | 3111504 | N/A | NAKURU WEST | BARUT | -0.3424 36.042 0 2000 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599000 | 99.9 | 1599000 | 1599000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are functional.
10024 | Murraming and Grading of Mofat-Kikonor Road | Murraming and Grading of Mofat-Kikonor Road | To implement murraming and grading of mofat-kikonor road for road connectivity and accessibility | Murraming and Grading of Mofat-Kikonor Road completed | 3111504 | N/A | NAKURU WEST | BARUT | -0.32713, 36.05335 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Taj azizz limited. Assessor remarks: Done by national government.
10025 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mwariki - Kamasai Road in Barut Ward Nakuru West Sub County | To maintain Spot Improvement of Mwariki - Kamasai Road in Barut Ward Nakuru West Sub County in serviceable condition | Spot Improvement of Mwariki - Kamasai Road in Barut Ward Nakuru West Sub County maintained | 3111504 | N/A | NAKURU WEST | BARUT | -0.324324, 36.054632 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017 | 2999992 | 2999992 | 2999992 | Equitable | N/A | 2999992 | 0 | 2991350 | 99.7 | 2991350 | 2999992 | 8642 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s Jozkim. Assessor remarks: It's in good condition.
10026 | Infrastructure, Development & Maintenance | Construction and installation of BCC Culvert | To construct and installation of BCC Culvert | And installation of BCC Culvert constructed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.63986, 36.517267 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2199355 | 100 | 2199355 | 2200000 | 645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
10027 | Infrastructure, Development & Maintenance | Grading and murraming of good faith - Israel access road | To improve road infrastructure by grading and murraming good faith - Israel access road | Good faith - Israel access road graded and murramed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.70884, 36.48434 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2273598 | 90.9 | 2273598 | 2273598 | 226402 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs further gravelling and spot maintenance.
10028 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Nyonjoro borehole road | To implement grading, gravelling and compaction of nyonjoro borehole road for road connectivity and accessibility | Grading, Gravelling and compaction of Nyonjoro borehole road completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.664802, 36.484093 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 3000001 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999289 | 0 | 2999289 | 3298560 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors. Assessor remarks: Routine maintenance and drainages ..
10029 | Infrastructure, Development & Maintenance | grading, gravelling and culvert installation of Gituru estate roads | To implement grading, gravelling and culvert installation of gituru estate roads for road connectivity and accessibility | grading, gravelling and culvert installation of Gituru estate roads completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3300000 | 3300000 | 3300000 | Equitable | N/A | 3300000 | 0 | 3298559 | 100 | 3298559 | 1 | 1441 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10030 | Infrastructure, Development & Maintenance | Grading, murraming and culvert installation of Kinamba Road | To implement grading, murraming and culvert installation of kinamba road for road connectivity and accessibility | Grading, murraming and culvert installation of Kinamba Road completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.722996, 36.476839 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2913801 | 97.1 | 2913801 | 2913801 | 86199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: No. Assessor remarks: Installation of drainage system, encroachment my developers,.
10031 | Infrastructure, Development & Maintenance | Murraming and Grading of Kiambaria-Kahuruko Road | To implement murraming and grading of kiambaria-kahuruko road for road connectivity and accessibility | Murraming and Grading of Kiambaria-Kahuruko Road completed | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | -0.728812, 36.492068 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2458092 | 98.3 | 2458092 | 40534 | 41908 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be redone,grading and unclogging of the culverts.
10032 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County | To maintain Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kimondo Road in Biashara Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1198860 | 1198860 | 1198860 | Equitable | N/A | 1198860 | 0 | 1198860 | 100 | 1198860 | 24244 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10033 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvementof Githinjiro Road in Biashara Ward Naivasha Sub County | To maintain Spot Improvementof Githinjiro Road in Biashara Ward Naivasha Sub County in serviceable condition | Spot Improvementof Githinjiro Road in Biashara Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198860 | 99.9 | 1198860 | 24244 | 1140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10034 | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County | To implement drainage works at abongoloya estate in biashara ward nakuru east sub county for road connectivity and accessibility | Drainage Works at Abongoloya Estate in Biashara Ward Nakuru East Sub County completed | 3111504 | N/A | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 2126583 | 236.3 | 2126583 | 900000 | -1226583 | Stalled | 0 | 100 | Recommended for terminated | 2016 | N/A | -1226583 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Recommended for terminated. % completion at stalling: 100.0%. Estimated cost to complete: KShs -1,226,583.
10035 | Infrastructure, Development & Maintenance | replacement of lights in the whole sale market | To implement replacement of lights in the whole sale market for road connectivity and accessibility | replacement of lights in the whole sale market completed | 3111504 | N/A | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10036 | Infrastructure, Development & Maintenance | tarmacking of coolio stage road | To upgrade coolio stage road through tarmacking for improved road connectivity | Coolio stage road tarmacked and upgraded | 3111504 | N/A | NAKURU EAST | BIASHARA-NAKURU | -0.286835, 36.075509 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4458370 | 89.2 | 4458370 | 1630 | 541630 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very operational.
10037 | Construction of 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | Construction of 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | To construct 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County | 2No. Motorcycle Sheds in Dundori Ward in Bahati Sub County constructed | 3111504 | N/A | BAHATI | DUNDORI | -0.237125, 36.167581 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498406 | 99.7 | 498406 | 498406 | 1594 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Arlington company Ltd. Assessor remarks: In good condition, inaccessible.
10038 | Infrastructure, Development and Maintenance | Grading and gravelling of Dundori access roads | To improve road infrastructure by grading and murraming Dundori access roads | Dundori access roads graded and murramed | 3111504 | N/A | BAHATI | DUNDORI | -0.26376, 36.191805 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1785904 | 81.2 | 1785904 | 1789870 | 414096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Gatemax enterprises limited. Assessor remarks: Good.
10039 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | DUNDORI | -0.261632, 36.190737 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 988200 | 988200 | 988200 | Equitable | N/A | 988200 | 0 | 1382968 | 139.9 | 1382968 | 988200 | -394768 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
10040 | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | DUNDORI | -0.22335, 36.174868 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1488879.3 | 1488879.3 | 1488879.3 | Equitable | N/A | 1488879.3 | 0 | 1382968 | 92.9 | 1382968 | 1488879 | 105911.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lanu contractors ltd. Assessor remarks: Road needs maintenance.
10041 | Infrastructure, Development & Maintenance | Completion of Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County | To complete Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County | Kasambara -Thugunui Road in Eburu/Mbaruk Ward Gilgil Sub County completed | 3111504 | N/A | GILGIL | EBURRU / MBARUK | -0.591883, 36.26228 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 19/20 | 1990000 | 1990000 | 1990000 | Equitable | N/A | 1990000 | 0 | 1990000 | 100 | 1990000 | 1990000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Water channels is the main problem.
10042 | Infrastructure, Development & Maintenance | Grading and Murraming of Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | To improve road infrastructure by grading and murraming Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County | Gema Kamathatha - Nagum road-Eburu/Mbaruk Ward in Gilgil Sub County graded and murramed | 3111504 | N/A | GILGIL | EBURRU / MBARUK | -0.588691, 36.271761 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 18-19 | 1999950 | 1999950 | 1999950 | Equitable | N/A | 1999950 | 0 | 716255 | 35.8 | 716255 | 1283695 | 1283695 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Unspecified. Assessor remarks: Bad road.
10043 | Infrastructure, Development & Maintenance | Grading and Murraming of Thome, Cedar,Sogoroi feeder roads | To improve road infrastructure by grading and murraming Thome, Cedar,Sogoroi feeder roads | Thome, Cedar,Sogoroi feeder roads graded and murramed | 3111504 | N/A | GILGIL | EBURRU / MBARUK | -0.607279, 36.274573 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 19-20 | 2000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1472275 | 147.2 | 1472275 | 1000000 | -472275 | Stalled | 75 | 100 | terminated | 2017 | N/A | -472275 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Work done well.
10044 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County | To maintain Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County in serviceable condition | Spot Improvement of Gachagi Access Roads in Eburu/ Mbaruk Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998000 | 99.8 | 998000 | 998000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10045 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County | To maintain Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County in serviceable condition | Spot Improvement of Kiungururia B Roads in Eburu /Mbaruk Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1491000 | 1491000 | 1491000 | Equitable | N/A | 1491000 | 0 | 1491000 | 100 | 1491000 | 1491000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10046 | Elburgon Ward Streetlights - Continuation/ Completion | Elburgon Ward Streetlights - Continuation/ Completion | To implement elburgon ward streetlights - continuation/ completion for road connectivity and accessibility | Elburgon Ward Streetlights - Continuation/ Completion completed | 3111504 | N/A | MOLO | ELBURGON | -0.264914, 35.831575 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | - | 1999978 | 1999978 | 1999978 | Equitable | N/A | 1999978 | 0 | 2933630 | 146.7 | 2933630 | 1999978 | -933652 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10047 | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County maintained | 3111504 | N/A | MOLO | ELBURGON | -0.302023, 35.813376 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1298411 | 86.6 | 1298411 | 200589 | 201589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10048 | Routine Maintenance and Spot Improvement of Mau -Ndimu-Rumwe Road in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Mau -Ndimu-Rumwe Road in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Mau -Ndimu-Rumwe Road in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Mau -Ndimu-Rumwe Road in Elburgon Ward Molo Sub County maintained | 3111504 | N/A | MOLO | ELBURGON | -0.275375, 35.796528 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1962430 | 1962430 | 1962430 | Equitable | N/A | 1962430 | 0 | 1298411 | 66.2 | 1298411 | 1962430 | 664019 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road motorable.
10049 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Nyakiambi -Karonga Roads in Elburgon Ward Molo Sub County maintained | 3111504 | N/A | MOLO | ELBURGON | -0.284884 35.845889 0 1399.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1099912 | 73.3 | 1099912 | 400088 | 400088 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10050 | Routine Maintenance and Spot Improvement of Tergat Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Tergat Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Tergat Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Tergat Roads in Elburgon Ward Molo Sub County maintained | 3111504 | N/A | MOLO | ELBURGON | -0.294954 35.766447 0 2799.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1543145.6 | 1543145.6 | 1543145.6 | Equitable | N/A | 1543145.6 | 0 | 1298411 | 84.1 | 1298411 | 1543146 | 244734.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair and maintainance.
10051 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Turi Farmers-Karonga House Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Turi Farmers-Karonga House Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Turi Farmers-Karonga House Roads in Elburgon Ward Molo Sub County maintained | 3111504 | N/A | MOLO | ELBURGON | -0.298789, 35.820546 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 983158 | 983158 | 983158 | Equitable | N/A | 983158 | 0 | 1099912 | 111.9 | 1099912 | 983158 | -116754 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is motor Bale.
10052 | Infrastructure, Development & Maintenance | Construction of River Nderit Bridge at Mbombo - Mitimingi Road | To construct River Nderit Bridge at Mbombo - Mitimingi Road | River Nderit Bridge at Mbombo - Mitimingi Road constructed | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.562075, 36.084188 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 2497500 | 2497500 | 2497500 | Equitable | N/A | 2497500 | 0 | 3392375 | 135.8 | 3392375 | 2497500 | -894875 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10053 | Infrastructure, Development & Maintenance | Grading and Murraming of Njeru - Gwachati road | To improve road infrastructure by grading and murraming Njeru - Gwachati road | Njeru - Gwachati road graded and murramed | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.594433, 36.110205 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 1850794 | 52.9 | 1850794 | 3500000 | 1649206 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor state. Road needs Routine Maintenance.
10054 | grading and sport gravelling of Tee - Munyaka -Meli- hakajane | grading and sport gravelling of Tee - Munyaka -Meli- hakajane | To improve road accessibility by grading and sport gravelling of Tee - Munyaka -Meli- hakajane | And sport gravelling of Tee - Munyaka -Meli- hakajane graded | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.658063, 36.11461 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes but maintanance needed. Viable: Yes. Assessor remarks: Needs renovation.
10055 | Infrastructure, Development & Maintenance | Grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts | To improve road accessibility by grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts | And spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts graded | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.585612, 36.114247 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 3600000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596052 | 0 | 3596052 | 3598900 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational although needs Routine Maintenance.
10056 | Infrastructure, Development & Maintenance | Grading sport gravelling of Munada Kanorero - Munyaka Road | To improve road accessibility by grading sport gravelling of Munada Kanorero - Munyaka Road | Sport gravelling of Munada Kanorero - Munyaka Road graded | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.601874 36.106719 2106.511 0.8220000267028809 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 2997417 | 2848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent attention.
10057 | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge | To implement kanorero - quarry bridge -construction of kanorero -quarry bridge for road connectivity and accessibility | Kanorero - Quarry Bridge -construction of Kanorero -quarry bridge completed | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.609053, 36.103382 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3390606 | 99.7 | 3390606 | 3390996 | 9394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
10058 | Proposed Routine Maintenance and Spot Improvement of Elementaita Access Roads II (Miti Mingi - Kilo Bridge Road (1.5km) in Elementaita Ward ,Gilgil Sub County | Proposed Routine Maintenance and Spot Improvement of Elementaita Access Roads II (Miti Mingi - Kilo Bridge Road (1.5km) in Elementaita Ward ,Gilgil Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Elementaita Access Roads II (Miti Mingi - Kilo Bridge Road (1.5km) in Elementaita Ward ,Gilgil Sub County | Proposed Routine Maintenance and Spot Improvement of Elementaita Access Roads II (Miti Mingi - Kilo Bridge Road (1.5km) in Elementaita Ward ,Gilgil Sub County implemented | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.563192 36.117968 1961.0999755859375 1.218000054359436 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1301000 | 1301000 | 1301000 | Equitable | N/A | 1301000 | 0 | 1301000 | 100 | 1301000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10059 | Infrastructure, Development & Maintenance | purchase and installation of Kiptangwany culverts | To procure and install Kiptangwany culverts | Kiptangwany culverts procured and installed | 3111504 | N/A | GILGIL | ELEMENTAITA | -0.56309, 36.117448 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2326985 | 0 | 2300000 | Equitable | N/A | 2300000 | 0 | 6424879 | 0 | 6424879 | 2300000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but requires Maintenance.
10060 | Design and Construction of boda boda shades | Design and Construction of boda boda shades | To design and construct boda boda shades | Boda boda shades designed and constructed | 3111504 | N/A | NAKURU EAST | FLAMINGO | -0.30603, 36.070332 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 2000000 | 18 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin. Assessor remarks: In use.
10061 | Drainage Works at Lakeview Estate (Maragoli Road) | Drainage Works at Lakeview Estate (Maragoli Road) | To implement drainage works at lakeview estate (maragoli road) for road connectivity and accessibility | Drainage Works at Lakeview Estate (Maragoli Road) completed | 3111504 | N/A | NAKURU EAST | FLAMINGO | -0.302897, 36.073214 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/2019 | 3999680 | 0 | 3999680 | Equitable | N/A | 3999680 | 0 | 3999680 | 0 | 3999680 | 3999680 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dentritic construction company. Assessor remarks: In good condition.
10062 | Grading and Murraming of G.G. Area roads | Grading and Murraming of G.G. Area roads | To improve road infrastructure by grading and murraming G.G. Area roads | G.G. Area roads graded and murramed | 3111504 | N/A | GILGIL | GILGIL | -0.448634 36.282639 1893.47802734375 12.605999946594238 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 2000000 | 153.8 | 2000000 | 1300000 | -700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ripasol enterprises. Assessor remarks: In good state.
10063 | Infrastructure, Development & Maintenance | Grading and Murraming of Kambi Somali roads | To improve road infrastructure by grading and murraming Kambi Somali roads | Kambi Somali roads graded and murramed | 3111504 | N/A | GILGIL | GILGIL | -0.50936, 36.317204 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498425 | 99.9 | 1498425 | 575 | 1575 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yed. Assessor remarks: Need culverts, drainage and maintainance.
10064 | Infrastructure, Development & Maintenance | Grading and Murraming of Karura Dispensary road | To improve road infrastructure by grading and murraming Karura Dispensary road | Karura Dispensary road graded and murramed | 3111504 | N/A | GILGIL | GILGIL | -0.509335 36.317226 2005.0999755859375 5.428999900817871 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Elias company limited. Assessor remarks: Road needs maintainance.
10065 | Infrastructure, Development & Maintenance | Grading and Murraming of Kigogo Majimoto roads | To improve road infrastructure by grading and murraming Kigogo Majimoto roads | Kigogo Majimoto roads graded and murramed | 3111504 | N/A | GILGIL | GILGIL | -0.447934, 36.282509 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ripasol enterprises. Assessor remarks: In good state.
10066 | Infrastructure, Development & Maintenance | grading of Elina road at Kikopey trading centre | To improve road accessibility by grading Elina road at Kikopey trading centre | Elina road at Kikopey trading centre graded | 3111504 | N/A | GILGIL | GILGIL | -0.475429, 36.295122 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1979975 | 99 | 1979975 | 1979975 | 20025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Githioro highlands and contractors limited. Assessor remarks: Requires routine maintainance and installation of culverts.
10067 | Repairs and Maintenance of Gilgil Roads and Culverts | Repairs and Maintenance of Gilgil Roads and Culverts | To implement repairs and maintenance of gilgil roads and culverts for road connectivity and accessibility | Repairs and Maintenance of Gilgil Roads and Culverts completed | 3111504 | N/A | GILGIL | GILGIL | -0.489145 36.328342 2004.300048828125 4.9019999504089355 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194674 | 119.5 | 1194674 | 1000000 | -194674 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintainance.
10068 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of Acre Tano-Maji Moto Road in Gilgil Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | GILGIL | -0.486773 36.296013 1900.35205078125 10.619999885559082 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2499500 | 2499500 | 2499500 | Equitable | N/A | 2499500 | 0 | 2499500 | 100 | 2499500 | 2499500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dakes construction. Assessor remarks: Requires routine maintainance and installation of culverts.
10069 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mbegi Feeder Roads in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of Mbegi Feeder Roads in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of Mbegi Feeder Roads in Gilgil Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | GILGIL | -0.534255, 36.342092 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1991720 | 1991720 | 1991720 | Equitable | N/A | 1991720 | 0 | 1851480 | 93 | 1851480 | 140240 | 140240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s starmax international contractors ltd. Assessor remarks: Needs maintainance.
10070 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of Teachers A and B Roads in Gilgil Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | GILGIL | -0.488439, 36.333705 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3974000 | 3974000 | 3974000 | Equitable | N/A | 3974000 | 0 | 3974000 | 100 | 3974000 | 3974000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintainance and culverts needed.
10071 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County | To maintain Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County in serviceable condition | Spot Improvement of View Point - Kasarani Road in Gilgil Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | GILGIL | -0.486773 36.296013 1900.35205078125 10.619999885559082 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1993576 | 1993576 | 1993576 | Equitable | N/A | 1993576 | 0 | 1993576 | 100 | 1993576 | 1993576 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s dakes construction. Assessor remarks: Requires routine maintainance and installation of culverts.
10072 | Murraming & Grading of Kamuyu Roads | Murraming & Grading of Kamuyu Roads | To implement murraming & grading of kamuyu roads for road connectivity and accessibility | Murraming & Grading of Kamuyu Roads completed | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.83107, 36.508986 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2993292 | 99.8 | 2993292 | 2985260 | 6708 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done @2,985,260.
10073 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | To undertake the proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.787946, 36.439583 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2873088 | 1527803.95 | 1527803.95 | Equitable | N/A | 1527803.95 | 0 | 3953280 | 258.8 | 3953280 | 1527804 | -2425476.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Cost of the project was 1,527,804.
10074 | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County | To maintain Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County in serviceable condition | Spot Improvement of Musaka Access Roads in Hells Gate Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.786956, 36.440088 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3953280 | 3953280 | 3953280 | Equitable | N/A | 3953280 | 0 | 3953280 | 100 | 3953280 | 3953280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's a very busy route which needs regular maintaince.
10075 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mwafrika roads in Hells Gate Ward Naivasha Sub County | To maintain Spot Improvement of Mwafrika roads in Hells Gate Ward Naivasha Sub County in serviceable condition | Spot Improvement of Mwafrika roads in Hells Gate Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | HELLS GATE | -0.787299 36.439885 1944.300048828125 13.923999786376953 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1989400 | 99.5 | 1989400 | 12760 | 10600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 7,000,000.
10076 | Construction of 7No. Motor Cycle Sheds at Nakuru County Headquarter | Construction of 7No. Motor Cycle Sheds at Nakuru County Headquarter | To construct 7No. Motor Cycle Sheds at Nakuru County Headquarter | 7No. Motor Cycle Sheds at Nakuru County Headquarter constructed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2104460.4 | 2104460.4 | 2104460.4 | Equitable | N/A | 2104460.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10077 | Infrastructure, Development and Maintenance | Construction of Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | To construct Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County constructed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2547151.2 | 2547151.2 | 2547151.2 | Equitable | N/A | 2547151.2 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10078 | Infrastructure, Development and Maintenance | Construction of Bridge and Road Connecting Korao (Tinet) and Kiptagich Ward in Kuresoi South Sub County | To construct Bridge and Road Connecting Korao (Tinet) and Kiptagich Ward in Kuresoi South Sub County | Bridge and Road Connecting Korao (Tinet) and Kiptagich Ward in Kuresoi South Sub County constructed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 8487400 | 8487400 | 8487400 | Equitable | N/A | 8487400 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10079 | Infrastructure, Development and Maintenance | construction of Kio bridge in kihingo ward | To construct Kio bridge in kihingo ward | Kio bridge in kihingo ward constructed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 6978545 | 697.9 | 6978545 | 4000000 | -5978545 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10080 | Infrastructure, Development and Maintenance | Grading and Gravelling of Elburgon-Salgaa Road in Elburgon Ward Molo Sub County | To improve road infrastructure by grading and murraming Elburgon-Salgaa Road in Elburgon Ward Molo Sub County | Elburgon-Salgaa Road in Elburgon Ward Molo Sub County graded and murramed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 789380 | 789380 | 789380 | Equitable | N/A | 789380 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10081 | Infrastructure, Development and Maintenance | Highmast for Mbaruk | To implement highmast for mbaruk for road connectivity and accessibility | Highmast for Mbaruk completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10082 | Infrastructure, Development and Maintenance | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county | To implement improvement of mashambani matatu stage in biashara ward in nakuru east sub county for road connectivity and accessibility | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 4706955 | 4706955 | 4706955 | Equitable | N/A | 4706955 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10083 | Infrastructure, Development & Maintenance | installation of highmast streetlighting at Greenstead and Barnabas | To improve security lighting through high mast floodlight installation at streetlighting at Greenstead and Barnabas | High mast floodlight installed at streetlighting at Greenstead and Barnabas | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 9793000 | 244.8 | 9793000 | 9793000 | -5793000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10084 | Infrastructure, Development and Maintenance | Periodic and routine Maintenance of Menengai Drive to capita Hill Road (1km) in Menengai Ward Nakuru East Sub County | To implement periodic and routine maintenance of menengai drive to capita hill road (1km) in menengai ward nakuru east sub county for road connectivity and accessibility | Periodic and routine Maintenance of Menengai Drive to capita Hill Road (1km) in Menengai Ward Nakuru East Sub County completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 10620032 | 10620032 | 10620032 | Equitable | N/A | 10620032 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10085 | Infrastructure, Development and Maintenance | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | To undertake the proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 18204565 | 2427.3 | 18204565 | 0 | -17454565 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10086 | Infrastructure, Development and Maintenance | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | To undertake the proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 4619070 | 1316020 | 1316020 | Equitable | N/A | 1316020 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10087 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Periodic Improvement of Bus Park Tarmacking in Gilgil Sub County | To undertake the proposed Routine Maintenance and Periodic Improvement of Bus Park Tarmacking in Gilgil Sub County | Proposed Routine Maintenance and Periodic Improvement of Bus Park Tarmacking in Gilgil Sub County implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 9454080 | 9454080 | 9454080 | Equitable | N/A | 9454080 | 0 | 5237600 | 55.4 | 5237600 | 5237600 | 4216480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10088 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County | Proposed Routine Maintenance and Spot Improvement of Kamurunyu to Kirima Road in Bahati Sub County implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998919 | 2998919 | 2998919 | Equitable | N/A | 2998919 | 0 | 5237600 | 174.6 | 5237600 | 5237600 | -2238681 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10089 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4027926 | 4027926 | 4027926 | Equitable | N/A | 4027926 | 0 | 5237600 | 130 | 5237600 | 5237600 | -1209674 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10090 | Infrastructure, Development and Maintenance | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | To undertake the proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 6029900 | 6029900 | 6029900 | Equitable | N/A | 6029900 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10091 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 9000000 | 9000000 | Equitable | N/A | 9000000 | 0 | 1643700 | 18.3 | 1643700 | 1643700 | 7356300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10092 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County | To maintain Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County in serviceable condition | Spot Improvement of Cheptuech - Kapgunot Road in Kuresoi South Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999660 | 1999660 | 1999660 | Equitable | N/A | 1999660 | 0 | 5237600 | 261.9 | 5237600 | 5237600 | -3237940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10093 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County | To maintain Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County in serviceable condition | Spot Improvement of Eburru Centre Frontage Road (Drainage) in Gilgil Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1989963 | 1989963 | 1989963 | Equitable | N/A | 1989963 | 0 | 5237600 | 263.2 | 5237600 | 5237600 | -3247637 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10094 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County | To maintain Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County in serviceable condition | Spot Improvement of Gwa Kihanga-Magomano-Kwa Haji Road - IDP Road in Subukia Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 8492708 | 8492708 | 8492708 | Equitable | N/A | 8492708 | 0 | 5237600 | 61.7 | 5237600 | 5237600 | 3255108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10095 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Jolly Farm (portion between Main Bus Park and Hospital Road 1km in Molo Sub "County | To maintain Spot Improvement of Jolly Farm (portion between Main Bus Park and Hospital Road 1km in Molo Sub "County in serviceable condition | Spot Improvement of Jolly Farm (portion between Main Bus Park and Hospital Road 1km in Molo Sub "County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2980751 | 2980751 | 2980751 | Equitable | N/A | 2980751 | 0 | 5237600 | 175.7 | 5237600 | 5237600 | -2256849 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10096 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County | To maintain Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County in serviceable condition | Spot Improvement of Kahuho - E1769 Road in Gilgil Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2484000 | 2484000 | 2484000 | Equitable | N/A | 2484000 | 0 | 5237600 | 210.9 | 5237600 | 5237600 | -2753600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10097 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County | To maintain Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County in serviceable condition | Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 12169900 | 5237600 | 5237600 | Equitable | N/A | 5237600 | 0 | 5237600 | 100 | 5237600 | 5237600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10098 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Ndeffo-Mercy-Lare Road (6km) in Njoro Sub County | To maintain Spot Improvement of Ndeffo-Mercy-Lare Road (6km) in Njoro Sub County in serviceable condition | Spot Improvement of Ndeffo-Mercy-Lare Road (6km) in Njoro Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2796064 | 2796064 | 2796064 | Equitable | N/A | 2796064 | 0 | 5237600 | 187.3 | 5237600 | 5237600 | -2441536 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10099 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari & Mutirithia Town Road in Molo Sub County | To maintain Spot Improvement of Tayari & Mutirithia Town Road in Molo Sub County in serviceable condition | Spot Improvement of Tayari & Mutirithia Town Road in Molo Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3982219 | 3982219 | 3982219 | Equitable | N/A | 3982219 | 0 | 5237600 | 131.5 | 5237600 | 5237600 | -1255381 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10100 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county | To maintain Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county in serviceable condition | Spot Improvement : Periodic Maintenance of Mol Bus Park in Molo Sub county maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3988605 | 3988605 | 3988605 | Equitable | N/A | 3988605 | 0 | 5237600 | 131.3 | 5237600 | 5237600 | -1248995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10101 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County | To maintain Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County in serviceable condition | Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 10504000 | 10504000 | 10504000 | Equitable | N/A | 10504000 | 0 | 5237600 | 49.9 | 5237600 | 5237600 | 5266400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10102 | Infrastructure, Development and Maintenance | Routine Maintenance & Spot Improvement : Cabro Paving of Nakuru Blanket Road (400m)Industrial Estate in Nakuru East Sub County | To maintain & Spot Improvement : Cabro Paving of Nakuru Blanket Road (400m)Industrial Estate in Nakuru East Sub County in serviceable condition | & Spot Improvement : Cabro Paving of Nakuru Blanket Road (400m)Industrial Estate in Nakuru East Sub County maintained | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 7955000 | 4325880 | 4325880 | Equitable | N/A | 4325880 | 0 | 5237600 | 121.1 | 5237600 | 5237600 | -911720 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10103 | Infrastructure, Development and Maintenance | Spot Improvement and Routine Maintenance of Printhouse Road (1km) in London Ward Nakuru West Sub County | To improve the condition of and Routine Maintenance of Printhouse Road (1km) in London Ward Nakuru West Sub County | And Routine Maintenance of Printhouse Road (1km) in London Ward Nakuru West Sub County improved | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 938217 | 938217 | 938217 | Equitable | N/A | 938217 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10104 | Supply and Installation of 34 No., 9m, 60W LED Solar lights in Nakuru County | Supply and Installation of 34 No., 9m, 60W LED Solar lights in Nakuru County | To procure and install 34 No., 9m, 60W LED Solar lights in Nakuru County | 34 No., 9m, 60W LED Solar lights in Nakuru County procured and installed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 9860000 | 9860000 | 9860000 | Equitable | N/A | 9860000 | 0 | 9084220 | 92.1 | 9084220 | 9860000 | 775780 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10105 | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | To install floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location installed | 3111504 | N/A | BAHATI | KABATINI | -0.222876, 36.1213 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2404500 | 95.4 | 2404500 | 2404800 | 115500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10106 | Routine Maintenance and Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County | Routine Maintenance and Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County | To maintain Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County in serviceable condition | Spot Patching of Githioro-Kwa Amos Access Roads in Kabatini Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | KABATINI | -0.229651, 36.150158 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2917980 | 2917980 | 2917980 | Equitable | N/A | 2917980 | 0 | 0 | 0 | 0 | 2914651 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes then. Viable: Yes. Contractor: Briter homes limited. Assessor remarks: Operational.
10107 | Infrastructure, Development & Maintenance | construction of Gishego bridge | To construct Gishego bridge | Gishego bridge constructed | 3111504 | N/A | SUBUKIA | KABAZI | -0.08223, 36.16987 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/19 | 2006602.8 | 2006602.8 | 2006602.8 | Equitable | N/A | 2006602.8 | 0 | 0 | 0 | 0 | 2006603 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yez. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires mai.
10108 | Infrastructure, Development and Maintenance | construction of Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | To construct Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward | Maombi and maringu bridges and installation of culverts at Kabazi centre and Road works around kabazi ward constructed | 3111504 | N/A | SUBUKIA | KABAZI | -0.23853 35.86724 2237 0 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1757447 | 35.1 | 1757447 | 1209627 | 3242553 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details available. Assessor remarks: Requires additional ecd classroom, toilets and kitchen.
10109 | design and construction of Boda boda shades at Kabazi centre and solai | design and construction of Boda boda shades at Kabazi centre and solai | To design and construct Boda boda shades at Kabazi centre and solai | Boda boda shades at Kabazi centre and solai designed and constructed | 3111504 | N/A | SUBUKIA | KABAZI | -0.077876, 36.170985 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 993122 | 99.3 | 993122 | 993122 | 6878 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
10110 | Infrastructure, Development & Maintenance | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch | To implement design and installation highmast streetlights at kabazi, solai and kipngochoch for road connectivity and accessibility | design and installation highmast streetlights at Kabazi, Solai and Kipngochoch completed | 3111504 | N/A | SUBUKIA | KABAZI | -0.152618, 36.074977 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497715 | 99.8 | 1497715 | 1497715 | 2285 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
10111 | Infrastructure, Development & Maintenance | Baraka twin bridge in Kamara Ward Kuresoi South Sub County : 1200mm - 1line | To implement baraka twin bridge in kamara ward kuresoi south sub county : 1200mm - 1line for road connectivity and accessibility | Baraka twin bridge in Kamara Ward Kuresoi South Sub County : 1200mm - 1line completed | 3111504 | N/A | KURESOI NORTH | KAMARA | -0.172694 35.679614 2519.9 48.900001525878906 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs concrete fence.
10112 | grading and levelling of Twinpik - Jogoo road | grading and levelling of Twinpik - Jogoo road | To improve road accessibility by grading and levelling of Twinpik - Jogoo road | And levelling of Twinpik - Jogoo road graded | 3111504 | N/A | KURESOI NORTH | KAMARA | -0.17825 35.711258 2501.3 4.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491536 | 99.4 | 1491536 | 8464 | 8464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
10113 | Infrastructure, Development & Maintenance | kamara road maintenance | To implement kamara road maintenance for road connectivity and accessibility | kamara road maintenance completed | 3111504 | N/A | KURESOI NORTH | KAMARA | -0.08778 35.67402 2487.6 4.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: VESTA ENTERPRISES LTD. Assessor remarks: Project constructed in Kamara secondary instead of Kamara primary. It's being used as a classroom for secondary.
10114 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County | To maintain Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | KAMARA | -0.1583 35.693597 2533.000244140625 63.867000579833984 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2997672 | 2997672 | 2997672 | Equitable | N/A | 2997672 | 0 | 2997672 | 100 | 2997672 | 2997672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
10115 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County | To maintain Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County in serviceable condition | Spot Improvement of Soget - Burgei Road in Kapkures Ward Nakuru West Sub County maintained | 3111504 | N/A | NAKURU WEST | KAPKURES | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2813580 | 2813580 | 2813580 | Equitable | N/A | 2813580 | 0 | 2813580 | 100 | 2813580 | 2813580 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10116 | Construction of Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | Construction of Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | To construct Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County | Drainage along Nakuru West Road to Faith in Action -Tubernacle Church in Kaptembwa Ward Nakuru West Sub County constructed | 3111504 | N/A | NAKURU WEST | KAPTEMBWO | -0.300876, 36.041345 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019 | 1999840 | 1999840 | 1999840 | Equitable | N/A | 1999840 | 0 | 202803 | 10.1 | 202803 | 202803 | 1797037 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it reduced flooding. Contractor: Warehouse construction ltd. Assessor remarks: Needs unclogging.
10117 | Infrastructure, Development & Maintenance | Design and construction of Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road | To design and construct Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road | Kabarus-kapbali bridge,Installation of culverts Tabaita-soitaran road and Cutline-kibangui pri road designed and constructed | 3111504 | N/A | KURESOI SOUTH | KERINGET | -0.54442, 35.702437 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999982 | 100 | 1999982 | 1999982 | 18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10118 | Infrastructure, Development and Maintenance | Grading and murraming of Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | To improve road infrastructure by grading and murraming Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road | Cutline to kibangui pri school road, Saptet polytechnic road to daraja mawe road, Kapsimbeiywo-bondet road, Mosiat-quarry-bandiat road, Keringet-bararget road, Tembwo-tachasis road graded and murramed | 3111504 | N/A | KURESOI SOUTH | KERINGET | -0.303966, 36.082876 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11600000 | 11600000 | 11600000 | Equitable | N/A | 11600000 | 0 | 10530782 | 90.8 | 10530782 | 10530782 | 1069218 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
10119 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Bondet - Kapkwen - T.M.C Road in Keringet Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | KERINGET | -0.479282, 35.711138 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019 | 1998620 | 1998620 | 1998620 | Equitable | N/A | 1998620 | 0 | 1998620 | 100 | 1998620 | 1998620 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10120 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Danger - Kapsimbeiywo Road in Keringet Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | KERINGET | -0.486508, 35.722452 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2020 | 1998950 | 1998950 | 1998950 | Equitable | N/A | 1998950 | 0 | 1780092 | 89.1 | 1780092 | 218858 | 218858 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Passablr.
10121 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | KERINGET | -0.460018 35.694096 0 899.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2993600 | 2993600 | 2993600 | Equitable | N/A | 2993600 | 0 | 2947251 | 98.5 | 2947251 | 46349 | 46349 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10122 | Infrastructure, Development & Maintenance | Culvert Installation and Drainage Works at Kiamaina Access Roads in Kiamaina Ward Bahati Sub County | To implement culvert installation and drainage works at kiamaina access roads in kiamaina ward bahati sub county for road connectivity and accessibility | Culvert Installation and Drainage Works at Kiamaina Access Roads in Kiamaina Ward Bahati Sub County completed | 3111504 | N/A | BAHATI | KIAMAINA | -0.26822 36.114538 1863.5 83.51699829101562 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 997136 | 997136 | 997136 | Equitable | N/A | 997136 | 0 | 1938476 | 194.4 | 1938476 | 997136 | -941340 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
10123 | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) | To implement murraming, culverts installation,grading heshima to menengai road (kiamaina roads) for road connectivity and accessibility | Murraming, Culverts Installation,Grading Heshima to Menengai Road (Kiamaina Roads) completed | 3111504 | N/A | BAHATI | KIAMAINA | -0.240721, 36.110365 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 1237275 | 1237275 | 1237275 | Equitable | N/A | 1237275 | 0 | 1236769 | 100 | 1236769 | 1237275 | 506 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10124 | Routine Maintenance and Spot Improvement of Kiangai -Rurii Roads in Kiamaina Ward Bahati Sub County | Routine Maintenance and Spot Improvement of Kiangai -Rurii Roads in Kiamaina Ward Bahati Sub County | To maintain Spot Improvement of Kiangai -Rurii Roads in Kiamaina Ward Bahati Sub County in serviceable condition | Spot Improvement of Kiangai -Rurii Roads in Kiamaina Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | KIAMAINA | -0.256227, 36.127258 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1991778 | 1991778 | 1991778 | Equitable | N/A | 1991778 | 0 | 1938476 | 97.3 | 1938476 | 1991778 | 53302 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
10125 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kirima Access Roads in Kiamaina Ward Bahati Sub County | To maintain Spot Improvement of Kirima Access Roads in Kiamaina Ward Bahati Sub County in serviceable condition | Spot Improvement of Kirima Access Roads in Kiamaina Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | KIAMAINA | -0.26822 36.114538 1863.5 83.51699829101562 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1980236 | 1980236 | 1980236 | Equitable | N/A | 1980236 | 0 | 1938476 | 97.9 | 1938476 | 41760 | 41760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
10126 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County | To undertake the proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County | Proposed installation and commissioning of 6No. 13m floodlights in Kihingo centre (2), stoo mbili (1), Ndeffo (1), Subuku (1), Gachohi centre (1) in Kihingo Ward ,Njoro Sub-County implemented | 3111504 | N/A | NJORO | KIHINGO | -0.433671, 35.973471 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019 | 1799973 | 1799973 | 1799973 | Equitable | N/A | 1799973 | 0 | 1799973 | 100 | 1799973 | 1799973 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10127 | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County | To maintain Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County in serviceable condition | Spot Improvement of Munanda - Kariaini road in Kihingo Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | KIHINGO | -0.464663, 35.987248 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2115840 | 2115840 | 2115840 | Equitable | N/A | 2115840 | 0 | 2115840 | 100 | 2115840 | 2115840 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
10128 | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | Spot Improvement and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | To improve the condition of and Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County | And Routine Maintenance of Stoo Mbili-Cutline Road in KihingoWard - Njoro Sub County improved | 3111504 | N/A | NJORO | KIHINGO | -0.397138 35.959772 2227.2000000000003 4.599999904632568 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1988356 | 1988356 | 1988356 | Equitable | N/A | 1988356 | 0 | 1988356 | 100 | 1988356 | 1988356 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10129 | Spot Improvement and Routine Maintenance of Subuku-Amani in KihingoWard - Njoro Sub County | Spot Improvement and Routine Maintenance of Subuku-Amani in KihingoWard - Njoro Sub County | To improve the condition of and Routine Maintenance of Subuku-Amani in KihingoWard - Njoro Sub County | And Routine Maintenance of Subuku-Amani in KihingoWard - Njoro Sub County improved | 3111504 | N/A | NJORO | KIHINGO | -0.480925 35.990003 2325.6 13.800000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 1990096 | 1990096 | 1990096 | Equitable | N/A | 1990096 | 0 | 1988356 | 99.9 | 1988356 | 1988356 | 1740 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Namba tech. Assessor remarks: More piping required.
10130 | grading and murraming of Kio - Kihonge Road | grading and murraming of Kio - Kihonge Road | To improve road infrastructure by grading and murraming Kio - Kihonge Road | Kio - Kihonge Road graded and murramed | 3111504 | N/A | NJORO | KIHINGO | -0.42804 35.966713 2277.300048828125 27.299999237060547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3190965 | 3190965 | Equitable | N/A | 3190965 | 0 | 3190965 | 100 | 3190965 | 3190965 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10131 | Infrastructure, Development & Maintenance | grading and murraming of Wendani - mutitu road (ndeffo) | To improve road infrastructure by grading and murraming Wendani - mutitu road (ndeffo) | Wendani - mutitu road (ndeffo) graded and murramed | 3111504 | N/A | NJORO | KIHINGO | -0.483175, 35.996643 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1854672 | 92.7 | 1854672 | 1854672 | 145328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: At that time. Viable: That time it met. Assessor remarks: Bush clearing, grading murraming and compaction required.
10132 | Infrastructure, Development & Maintenance | grading and murraming of Emitik - Gikamba road | To improve road infrastructure by grading and murraming Emitik - Gikamba road | Emitik - Gikamba road graded and murramed | 3111504 | N/A | KURESOI SOUTH | KIPTAGICH | -0.623375, 35.608362 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 0 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 3972828 | 0 | 3972828 | 3979032 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes but needs not met. Assessor remarks: Need concrete road.
10133 | Infrastructure, Development & Maintenance | grading and murraming of irector - Lel Banga Road | To improve road infrastructure by grading and murraming irector - Lel Banga Road | Irector - Lel Banga Road graded and murramed | 3111504 | N/A | KURESOI SOUTH | KIPTAGICH | -0.576235, 35.58879 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 988500 | 24.7 | 988500 | 211513 | 3011500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is good.
10134 | grading and murraming of K.T.D.A - Riprip Road | grading and murraming of K.T.D.A - Riprip Road | To improve road infrastructure by grading and murraming K.T.D.A - Riprip Road | K.T.D.A - Riprip Road graded and murramed | 3111504 | N/A | KURESOI SOUTH | KIPTAGICH | -0.561157, 35.592887 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3568147 | 89.2 | 3568147 | 3568147 | 431853 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good.
10135 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County | To maintain Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cheptebes - Sugutek Road in Kiptagich Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | KIPTAGICH | -0.598075 35.639577 2372.7999999999997 59.900001525878906 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 0 | 4999600 | Equitable | N/A | 4999600 | 0 | 1332100 | 0 | 1332100 | 1332100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and needs met. Assessor remarks: Functional.
10136 | Infrastructure, Development & Maintenance | Design and Construction of Bridge in Kongoi | To design and construct Bridge in Kongoi | Bridge in Kongoi designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.327652, 35.53791 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yess. Viable: Yess. Assessor remarks: There is only 3 Calverts but no bridge.
10137 | Infrastructure, Development & Maintenance | design and Construction of Bridge of Chepkosa bridge | To design and construct Bridge of Chepkosa bridge | Bridge of Chepkosa bridge designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.339452 35.480974 2456.8 4.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1272998 | 106.1 | 1272998 | 1950830 | -72998 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They need additional classroom.the existing classroomm is partitioned,PP1 and pp2 share one classroom.
10138 | Infrastructure, Development & Maintenance | design and Construction of Bridge of kiplongony bridge | To design and construct Bridge of kiplongony bridge | Bridge of kiplongony bridge designed and constructed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.37964, 35.548857 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1272998 | 63.6 | 1272998 | 2000000 | 727002 | Stalled | 0 | 63.6 | RECOMMENDED FOR TERMINATION | 2017 | N/A | 727002 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yess. Viable: No. Assessor remarks: Underfunded,not yet started.
10139 | Grading, Culverts and Murraming of Tiriyta Roads | Grading, Culverts and Murraming of Tiriyta Roads | To implement grading, culverts and murraming of tiriyta roads for road connectivity and accessibility | Grading, Culverts and Murraming of Tiriyta Roads completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.377203, 35.505747 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2490077 | 83 | 2490077 | 3000000 | 509923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
10140 | Infrastructure, Development & Maintenance | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County | To implement grading, murraming and culverts for korongo - motogir road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2497065.6 | 2497065.6 | 2497065.6 | Equitable | N/A | 2497065.6 | 0 | 2480265 | 99.3 | 2480265 | 2480265 | 16800.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10141 | Routine Maintenance and Spot Improvement at Kipkoris road in Kiptororo Ward Kuresoi North Sub County | Routine Maintenance and Spot Improvement at Kipkoris road in Kiptororo Ward Kuresoi North Sub County | To maintain Spot Improvement at Kipkoris road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | Spot Improvement at Kipkoris road in Kiptororo Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.385457, 35.486922 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1499986.7 | 1499986.7 | 1499986.7 | Equitable | N/A | 1499986.7 | 0 | 1963156 | 130.9 | 1963156 | 24992 | -463169.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good state.
10142 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.407175, 35.526648 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3999854 | 3999854 | 3999854 | Equitable | N/A | 3999854 | 0 | 3971350 | 99.3 | 3971350 | 3971350 | 28504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10143 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998841.25 | 2998841.25 | 2998841.25 | Equitable | N/A | 2998841.25 | 0 | 2970080 | 99 | 2970080 | 2970080 | 28761.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10144 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation at Kuresoi Centre in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation at kuresoi centre in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation at Kuresoi Centre in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.300926 35.531767 0 68.4000015258789 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 998899 | 998899 | 998899 | Equitable | N/A | 998899 | 0 | 1348714 | 135 | 1348714 | 998899 | -349815 | Stalled | 75 | 100 | Default Notice | 2016 | N/A | -349815 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work in progress.
10145 | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kibaraa road works in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kibaraa road works in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999561 | 1999561 | 1999561 | Equitable | N/A | 1999561 | 0 | 1999561 | 100 | 1999561 | 1999561 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10146 | Routine Maintenance,Spot Improvement and Culverts Installation for Kimugul Road in Kiptororo Ward Kuresoi North Sub County | Routine Maintenance,Spot Improvement and Culverts Installation for Kimugul Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kimugul road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kimugul Road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.389489, 35.568792 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1499706 | 1499706 | 1499706 | Equitable | N/A | 1499706 | 0 | 2970080 | 198 | 2970080 | 1499706 | -1470374 | Stalled | 75 | 100 | Default Notice | 2016 | N/A | -1470374 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable road.
10147 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Kio - Githima Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kio - githima road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kio - Githima Road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.298038, 35.494998 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1998147.2 | 1998147.2 | 1998147.2 | Equitable | N/A | 1998147.2 | 0 | 1999501 | 100.1 | 1999501 | 1998147 | -1353.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Unblocking of culverts and bush clearing.is required.
10148 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Kongoi - Bochege road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for kongoi - bochege road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Kongoi - Bochege road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.300926 35.531767 0 68.4000015258789 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1498604 | 1498604 | 1498604 | Equitable | N/A | 1498604 | 0 | 1348714 | 90 | 1348714 | 1498604 | 149890 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work in progress.
10149 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Korabariet Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for korabariet road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Korabariet Road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1499316.24 | 1499316.24 | 1499316.24 | Equitable | N/A | 1499316.24 | 0 | 1499316 | 100 | 1499316 | 1499316 | 0.24 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10150 | Infrastructure, Development & Maintenance | Routine Maintenance,Spot Improvement and Culverts Installation for Ong'ira - Chorwa Road in Kiptororo Ward Kuresoi North Sub County | To implement routine maintenance,spot improvement and culverts installation for ong'ira - chorwa road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Routine Maintenance,Spot Improvement and Culverts Installation for Ong'ira - Chorwa Road in Kiptororo Ward Kuresoi North Sub County completed | 3111504 | N/A | KURESOI NORTH | KIPTORORO | -0.332747 35.570807 2661.2 16.100000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999501.18 | 1999501.18 | 1999501.18 | Equitable | N/A | 1999501.18 | 0 | 1999501 | 100 | 1999501 | 1999501 | 0.18 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
10151 | Infrastructure, Development & Maintenance | Construction and Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) | To construct and Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) | And Maintainance of Drainage System (Kahawa road, Kipkelion road, Mumias Road) constructed | 3111504 | N/A | NAKURU EAST | KIVUMBINI | -0.297692, 36.080703 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 6400000 | 6400000 | 6400000 | Equitable | N/A | 6400000 | 0 | 6219047 | 97.2 | 6219047 | 6400000 | 180953 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs maintenance.
10152 | Infrastructure, Development and Maintenance | Installation of Security lights, Kivumbini ward | To install Security lights, Kivumbini ward | Security lights, Kivumbini ward installed | 3111504 | N/A | NAKURU EAST | KIVUMBINI | -0.296244, 36.084835 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1852500 | 185.2 | 1852500 | 880200 | -852500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
10153 | Infrastructure, Development & Maintenance | Rehabilitation of Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County | To rehabilitate Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County to restore functionality | Drainage System at Shauri Yako - Shuleni Road -Kivumbini II-AIC/AP Line -Shuleni I Roads in Kivumbini Ward Nakuru East Sub County rehabilitated | 3111504 | N/A | NAKURU EAST | KIVUMBINI | -0.301853, 36.084754 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | June 2020 | 2999641 | 2999641 | 2999641 | Equitable | N/A | 2999641 | 0 | 545107 | 18.2 | 545107 | 545107 | 2454534 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in use.
10154 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of road in phase II in Kivumbini Ward Nakuru East Sub County | To maintain Spot Improvement of road in phase II in Kivumbini Ward Nakuru East Sub County in serviceable condition | Spot Improvement of road in phase II in Kivumbini Ward Nakuru East Sub County maintained | 3111504 | N/A | NAKURU EAST | KIVUMBINI | -0.298055, 36.082716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 950300 | 950300 | 950300 | Equitable | N/A | 950300 | 0 | 545107 | 57.4 | 545107 | 950300 | 405193 | Stalled | 75 | 57.4 | Default Notice | 2016 | N/A | 405193 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved transportation.
10155 | Construction and installation of Culverts in lakeview ward | Construction and installation of Culverts in lakeview ward | To construct and installation of Culverts in lakeview ward | And installation of Culverts in lakeview ward constructed | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.745187, 36.460478 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10156 | Infrastructure, Development & Maintenance | Construction of Neta drainage in Lake View Ward Naivasha Sub County | To construct Neta drainage in Lake View Ward Naivasha Sub County | Neta drainage in Lake View Ward Naivasha Sub County constructed | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.745599, 36.459547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 996440 | 996440 | 996440 | Equitable | N/A | 996440 | 0 | 1905648 | 191.2 | 1905648 | 93264 | -909208 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10157 | Infrastructure, Development & Maintenance | installation of 20 Highmasts streetlights in lakeview ward | To install 20 Highmasts streetlights in lakeview ward | 20 Highmasts streetlights in lakeview ward installed | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.727709, 36.443981 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 934800 | 46.7 | 934800 | 2000000 | 1065200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10158 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.75025, 36.456875 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3498746 | 1737866 | 1737866 | Equitable | N/A | 1737866 | 0 | 1905648 | 109.7 | 1905648 | 1737866 | -167782 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
10159 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Unity Roads in Lake View Ward Naivasha Sub County | To maintain Spot Improvement of Unity Roads in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvement of Unity Roads in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.75025, 36.456875 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1998912 | 1998912 | 1998912 | Equitable | N/A | 1998912 | 0 | 1905648 | 95.3 | 1905648 | 93264 | 93264 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
10160 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvementof Pipeline-Kihoto Road (2km) in Lake View Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | LAKE VIEW | -0.75025, 36.456875 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1488280 | 1488280 | 1488280 | Equitable | N/A | 1488280 | 0 | 1905648 | 128 | 1905648 | 1488280 | -417368 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
10161 | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | Installation of high mast lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | To improve security lighting through high mast floodlight installation at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | High mast floodlight installed at lights at Muronyo (kwa Mzungu), murunyu mugumoini, Giachoge nursery, Giachong'e kwa muhia, karemenu junction, Munyeki catholic junction, St. George grassland junction, Baraka junction, lower murunyu junction, murunyu umoja junction) | 3111504 | N/A | BAHATI | LANET UMOJA | -0.287591, 36.152474 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3204800 | 80.1 | 3204800 | 4000000 | 795200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
10162 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ndege Ndimu Access Roads in Lanet Umoja Ward Bahati Sub County | To maintain Spot Improvement of Ndege Ndimu Access Roads in Lanet Umoja Ward Bahati Sub County in serviceable condition | Spot Improvement of Ndege Ndimu Access Roads in Lanet Umoja Ward Bahati Sub County maintained | 3111504 | N/A | BAHATI | LANET UMOJA | -0.308822, 36.177708 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1996186 | 1996186 | 1996186 | Equitable | N/A | 1996186 | 0 | 0 | 0 | 0 | 1996186 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10163 | Construction of Milimani bridge in Lare Ward Njoro Sub County | Construction of Milimani bridge in Lare Ward Njoro Sub County | To construct Milimani bridge in Lare Ward Njoro Sub County | Milimani bridge in Lare Ward Njoro Sub County constructed | 3111504 | N/A | NJORO | LARE | -0.392153 36.025158 2016.2 25.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2999870 | 2999870 | 2999870 | Equitable | N/A | 2999870 | 0 | 2741870 | 91.4 | 2741870 | 258000 | 258000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not equipped.
10164 | Infrastructure, Development & Maintenance | construction of soweto mbatia footbridge | To construct soweto mbatia footbridge | Soweto mbatia footbridge constructed | 3111504 | N/A | NJORO | LARE | -0.448588, 36.008315 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2020 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need rails.
10165 | Infrastructure, Development & Maintenance | grading and murraming of kware - muthiga road | To improve road infrastructure by grading and murraming kware - muthiga road | Kware - muthiga road graded and murramed | 3111504 | N/A | NJORO | LARE | -0.495563 36.024872 2208.6 11.800000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498937 | 100 | 2498937 | 2000000 | 1063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
10166 | Infrastructure, Development & Maintenance | grading and murraming of Soweto - Matindi -Gathiru road | To improve road infrastructure by grading and murraming Soweto - Matindi -Gathiru road | Soweto - Matindi -Gathiru road graded and murramed | 3111504 | N/A | NJORO | LARE | -0.472562, 36.023302 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 60564 | 2 | 60564 | 60564 | 2939436 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
10167 | Infrastructure, Development & Maintenance | Grading of Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre | To improve road accessibility by grading Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre | Quarry Road and Construction of Culverts - ST. Francis to Naishi game centre graded | 3111504 | N/A | NJORO | LARE | -0.439725, 36.015697 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1826289 | 60.9 | 1826289 | 2996141 | 1173711 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance and has.
10168 | Installation/laying of Cabro Blocks in London Ward Road Works | Installation/laying of Cabro Blocks in London Ward Road Works | To implement installation/laying of cabro blocks in london ward road works for road connectivity and accessibility | Installation/laying of Cabro Blocks in London Ward Road Works completed | 3111504 | N/A | NAKURU WEST | LONDON | -0.273027, 36.05145 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 7084874 | 35.4 | 7084874 | 1165540 | 12915126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
10169 | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | To undertake the proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood light at Mololine ,Golf course,Kenya Meat and Medical in London Ward, Nakuru West Sub County implemented | 3111504 | N/A | NAKURU WEST | LONDON | -0.278201, 36.073897 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 3960356 | 3960356 | 3960356 | Equitable | N/A | 3960356 | 0 | 323657 | 8.2 | 323657 | 323657 | 3636699 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
10170 | Rehabilitation and Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County | Rehabilitation and Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County | To rehabilitate Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County to restore functionality | Maintenance of Bangladesh and Lower Hill access roads in London Nakuru West Sub County rehabilitated | 3111504 | N/A | NAKURU WEST | LONDON | -0.296095, 35.95845 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499500 | 100 | 2499500 | 2499500 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: The road has pot holes.
10171 | Infrastructure, Development & Maintenance | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads | To implement gravelling and murraming and culvert installation of maai mahiu / longonot access roads for road connectivity and accessibility | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads completed | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -1.016438, 36.622719 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 985072 | 49.3 | 985072 | 1014928 | 1014928 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yea. Assessor remarks: Complete.
10172 | installation of floodlights at maai mahiu / longonot | installation of floodlights at maai mahiu / longonot | To install floodlights at maai mahiu / longonot | Floodlights at maai mahiu / longonot installed | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.979019, 36.585983 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 2998280 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not functional. Needs repair.
10173 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County | To undertake the proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County | Proposed installation and commissioning of 7No. 13m. Highmast flood light in Maai Mahiu Ward, Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -1.006983, 36.521808 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1993808 | 1993808 | 1993808 | Equitable | N/A | 1993808 | 0 | 1993808 | 100 | 1993808 | 1993808 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
10174 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | To undertake the proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | Proposed Routine Maintenance and Drain Construction of Mai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.983497, 36.58729 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 588924 | 588924 | 588924 | Equitable | N/A | 588924 | 0 | 588924 | 100 | 588924 | 588924 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs spot filling.
10175 | Routine Maintenance and Spot Improvement of Ereri - Munengi Access Roads in Mai Mahiu Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ereri - Munengi Access Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Ereri - Munengi Access Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ereri - Munengi Access Roads in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1495000 | 1495000 | 1495000 | Equitable | N/A | 1495000 | 0 | 588924 | 39.4 | 588924 | 1495000 | 906076 | Stalled | 0 | 39.4 | Default Notice | 2016 | N/A | 906076 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Default Notice. % completion at stalling: 39.4%. Estimated cost to complete: KShs 906,076.
10176 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiambogo Access Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Kiambogo Access Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kiambogo Access Roads in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.883084, 36.495547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 588924 | 58.9 | 588924 | 1000000 | 411076 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes.. Viable: Yes. Assessor remarks: Needs maintenance..
10177 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.870717, 36.555893 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1904720 | 1904720 | 1904720 | Equitable | N/A | 1904720 | 0 | 588924 | 30.9 | 588924 | 1523725 | 1315796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
10178 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAAI MAHIU | -0.979368, 36.583679 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 588924 | 19.6 | 588924 | 1934900 | 2411076 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state, storm drains to be rennovated.
10179 | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Central - Ndabibi Primary Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10180 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3050800 | 3050800 | 6050800 | Equitable | N/A | 6050800 | 0 | 6050800 | 198.3 | 6050800 | 6050800 | -3000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10181 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2987232 | 2987232 | 2987232 | Equitable | N/A | 2987232 | 0 | 2950463 | 98.8 | 2950463 | 2987232 | 36769 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10182 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3373394 | 91.2 | 3373394 | 3700000 | 326606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10183 | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | MAIELLA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1730720 | 1730720 | 1730720 | Equitable | N/A | 1730720 | 0 | 1695820 | 98 | 1695820 | 1695820 | 34900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10184 | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County | To implement culvert installation across the ward in malewa west ward gilgil sub county for road connectivity and accessibility | Culvert Installation across the ward in Malewa West Ward Gilgil Sub County completed | 3111504 | N/A | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3599695 | 599.9 | 3599695 | 600000 | -2999695 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for more culverts installation.
10185 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County | To maintain Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County in serviceable condition | Spot Improvement of Gwa Tham Road in Malewa West Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | MALEWA WEST | -0.702703, 36.435173 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018/19 | 2593667 | 2593667 | 2593667 | Equitable | N/A | 2593667 | 0 | 757987 | 29.2 | 757987 | 2593667 | 1835680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
10186 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Karati Nyondia Bridge Road in Malewa West Ward Gilgil Sub County | To maintain Spot Improvement of Karati Nyondia Bridge Road in Malewa West Ward Gilgil Sub County in serviceable condition | Spot Improvement of Karati Nyondia Bridge Road in Malewa West Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | MALEWA WEST | -0.702703 36.471211 0 2000 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1670632 | 1670632 | 1670632 | Equitable | N/A | 1670632 | 0 | 757987 | 45.4 | 757987 | 1670632 | 912645 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road has been maintained over years.
10187 | Construction of Onoptich River Bridge 5m High Single Span Double Lane | Construction of Onoptich River Bridge 5m High Single Span Double Lane | To construct Onoptich River Bridge 5m High Single Span Double Lane | Onoptich River Bridge 5m High Single Span Double Lane constructed | 3111504 | N/A | MOLO | MARIOSHONI | -0.316382, 35.846093 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 973865 | 973865 | 973865 | Equitable | N/A | 973865 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10188 | Grading and Murraming of Black- pine Kapsinendet Road | Grading and Murraming of Black- pine Kapsinendet Road | To improve road infrastructure by grading and murraming Black- pine Kapsinendet Road | Black- pine Kapsinendet Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | -0.378629, 35.800637 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance to be done.
10189 | Grading and Murraming of Daraja Mungu- Chaimoto Road | Grading and Murraming of Daraja Mungu- Chaimoto Road | To improve road infrastructure by grading and murraming Daraja Mungu- Chaimoto Road | Daraja Mungu- Chaimoto Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | -0.359266, 35.78789 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Repetitive projects.
10190 | Grading and Murraming of Kaplabos - Kwa Jack Road | Grading and Murraming of Kaplabos - Kwa Jack Road | To improve road infrastructure by grading and murraming Kaplabos - Kwa Jack Road | Kaplabos - Kwa Jack Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10191 | Grading and Murraming of Kapsuman - Kaprop Road | Grading and Murraming of Kapsuman - Kaprop Road | To improve road infrastructure by grading and murraming Kapsuman - Kaprop Road | Kapsuman - Kaprop Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10192 | Infrastructure, Development & Maintenance | Grading and Murraming of Kiptunga- Tertit Road | To improve road infrastructure by grading and murraming Kiptunga- Tertit Road | Kiptunga- Tertit Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10193 | Grading and Murraming of Molem- Mariashoni Road | Grading and Murraming of Molem- Mariashoni Road | To improve road infrastructure by grading and murraming Molem- Mariashoni Road | Molem- Mariashoni Road graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | -0.372008, 35.824192 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10194 | Infrastructure, Development & Maintenance | Grading and Murraming of Mtarakwa- Mariashoni | To improve road infrastructure by grading and murraming Mtarakwa- Mariashoni | Mtarakwa- Mariashoni graded and murramed | 3111504 | N/A | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10195 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county | To maintain Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county in serviceable condition | Spot Improvement of Chai Moto-Daraja Mungu Road in Marioshoni Ward Molo Sub county maintained | 3111504 | N/A | MOLO | MARIOSHONI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 998760 | 998760 | 998760 | Equitable | N/A | 998760 | 0 | 5237600 | 524.4 | 5237600 | 5237600 | -4238840 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10196 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County | To maintain Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County in serviceable condition | Spot Improvement of Kapcholola- Ndashatait Road Road in Mariashoni Ward Molo Sub County maintained | 3111504 | N/A | MOLO | MARIOSHONI | -0.369206, 35.841966 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2898492 | 2898492 | 2898492 | Equitable | N/A | 2898492 | 0 | 5237600 | 180.7 | 5237600 | 5237600 | -2339108 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
10197 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Vikingi Tatu - Daraja Mungu Road in Mariashoni Ward Molo Sub County | To maintain Spot Improvement of Vikingi Tatu - Daraja Mungu Road in Mariashoni Ward Molo Sub County in serviceable condition | Spot Improvement of Vikingi Tatu - Daraja Mungu Road in Mariashoni Ward Molo Sub County maintained | 3111504 | N/A | MOLO | MARIOSHONI | -0.394059, 35.771435 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3138156 | 3138156 | 3138156 | Equitable | N/A | 3138156 | 0 | 5237600 | 166.9 | 5237600 | 5237600 | -2099444 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Completely unusable.
10198 | Routine Maintenance & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County | Routine Maintenance & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County | To maintain & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County in serviceable condition | & Spot Improvement of Gichagi-Ndoswa Road in Mariashoni Ward-Molo Sub County maintained | 3111504 | N/A | MOLO | MARIOSHONI | -0.316734, 35.85321 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1491329.28 | 1491329.28 | 1491329.28 | Equitable | N/A | 1491329.28 | 0 | 5237600 | 351.2 | 5237600 | 5237600 | -3746270.72 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10199 | Routine Maintenance and Spot Improvement of Likia Centre -Likia Police Post Road in Mau Narok Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Likia Centre -Likia Police Post Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Likia Centre -Likia Police Post Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Likia Centre -Likia Police Post Road in Mau Narok Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | MAU NAROK | -0.538865, 35.980263 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1900005 | 1900005 | 1900005 | Equitable | N/A | 1900005 | 0 | 1448144 | 76.2 | 1448144 | 1900005 | 451861 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
10200 | Routine Maintenance and Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Mau Narok Centre -Police Street Road in Mau Narok Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | MAU NAROK | -0.601323, 36.011188 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1448144 | 1448144 | 1448144 | Equitable | N/A | 1448144 | 0 | 1448144 | 100 | 1448144 | 1468429 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes. Assessor remarks: needs improvement.
10201 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County | To maintain Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement of Sugutiek -Kamungei Road in Mau Narok Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | MAU NAROK | -0.588187 36.013644 0 0 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2968440 | 1468430 | 1468430 | Equitable | N/A | 1468430 | 0 | 1468430 | 100 | 1468430 | 1468430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
10202 | Infrastructure, Development & Maintenance | Routine Maintenance of Tepesuet -Major Rop Bridge Road | To maintain Tepesuet -Major Rop Bridge Road in serviceable condition | Tepesuet -Major Rop Bridge Road maintained | 3111504 | N/A | NJORO | MAUCHE | -0.493315, 35.967238 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2020 | 606100 | 606100 | 606100 | Equitable | N/A | 606100 | 0 | 606100 | 100 | 606100 | 606100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
10203 | Infrastructure, Development & Maintenance | Spot Improvement and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | To improve the condition of and Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County | And Routine Maintenance of Sertwet - Kwa James Road in Mauche Ward - Njoro Sub County improved | 3111504 | N/A | NJORO | MAUCHE | -0.513477, 35.962448 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2021 | 593436 | 593436 | 593436 | Equitable | N/A | 593436 | 0 | 593436 | 100 | 593436 | 593436 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
10204 | Infrastructure, Development & Maintenance | construction of drainage system of Teachers Muhoro Road | To construct drainage system of Teachers Muhoro Road | Drainage system of Teachers Muhoro Road constructed | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275864, 36.115309 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2982800 | 99.4 | 2982800 | 2982800 | 17200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs cleaning and clearing.
10205 | installation of highmast streetlighting at Kiratina in Menengai ward | installation of highmast streetlighting at Kiratina in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Kiratina in Menengai ward | High mast floodlight installed at streetlighting at Kiratina in Menengai ward | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275968, 36.114339 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000001 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 0 | 3499400 | 600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10206 | installation of highmast streetlighting at Teachers in Menengai ward | installation of highmast streetlighting at Teachers in Menengai ward | To improve security lighting through high mast floodlight installation at streetlighting at Teachers in Menengai ward | High mast floodlight installed at streetlighting at Teachers in Menengai ward | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.275968, 36.114339 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000002 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499400 | 0 | 3499400 | 600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10207 | maintenance of Menengai ward streetlights | maintenance of Menengai ward streetlights | To implement maintenance of menengai ward streetlights for road connectivity and accessibility | maintenance of Menengai ward streetlights completed | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.28233, 36.114919 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1441416 | 144.1 | 1441416 | 58584 | -441416 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10208 | Infrastructure, Development & Maintenance | Proopsed improvement of Nakuru Blanket Road in Menengai ward Nakru East Sub County | To implement proopsed improvement of nakuru blanket road in menengai ward nakru east sub county for road connectivity and accessibility | Proopsed improvement of Nakuru Blanket Road in Menengai ward Nakru East Sub County completed | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.283971, 36.116543 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1987660 | 1987660 | 1987660 | Equitable | N/A | 1987660 | 0 | 1798568 | 90.5 | 1798568 | 201272 | 189092 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Few flood lights were done, only at teacher's, and ranges view, no flood light in Nyamarutu.
10209 | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | To undertake the proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County | Proposed Installation and commissioning of 20 No.13m. Highmast flood light at Teachers, Ranges View, Nyamarutu in Menengai ward, Nakuru East Sub County implemented | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.278052, 36.117906 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016/17 | 677672 | 677672 | 677672 | Equitable | N/A | 677672 | 0 | 2990484 | 441.3 | 2990484 | 677672 | -2312812 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10210 | Routine Maintenance and Spot Improvement of Emboita roads in Menengai Ward Nakuru East Sub County | Routine Maintenance and Spot Improvement of Emboita roads in Menengai Ward Nakuru East Sub County | To maintain Spot Improvement of Emboita roads in Menengai Ward Nakuru East Sub County in serviceable condition | Spot Improvement of Emboita roads in Menengai Ward Nakuru East Sub County maintained | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.271411 36.111322 1863.5 14.951000213623047 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1487120 | 1487120 | 1487120 | Equitable | N/A | 1487120 | 0 | 2990484 | 201.1 | 2990484 | 1487120 | -1503364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10211 | Routine Maintenance and Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County | Routine Maintenance and Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County | To maintain Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County in serviceable condition | Spot Improvement of Teachers roads in Menengai Ward Nakuru East Sub County maintained | 3111504 | N/A | NAKURU EAST | MENENGAI | -0.274942, 36.117787 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2984680 | 2984680 | 2984680 | Equitable | N/A | 2984680 | 0 | 2990484 | 100.2 | 2990484 | 2984680 | -5804 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10212 | Infrastructure, Development and Maintenance | Installation of HighMast security lights at Eden and Mercy Njeri | To improve security lighting through high mast floodlight installation at security lights at Eden and Mercy Njeri | High mast floodlight installed at security lights at Eden and Mercy Njeri | 3111504 | N/A | RONGAI | MENENGAI WEST | -0.26736, 36.028102 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2023/24 | 6500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5475750 | 182.5 | 5475750 | 2825750 | -2475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10213 | Routine Maintenance and Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County | Routine Maintenance and Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County | To maintain Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement (4km) of Chiefs Access Road in Menengai West Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | MENENGAI WEST | -0.151362 36.01104 1764.7 19.299999237060547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1442638 | 1442638 | 1442638 | Equitable | N/A | 1442638 | 0 | 1442638 | 100 | 1442638 | 2389600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10214 | Routine Maintenance and Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County | Routine Maintenance and Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County | To maintain Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement (6km) of Gitau - Jawabu School Road in Menengai West Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | MENENGAI WEST | -0.171907, 36.011055 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2389600 | 2389600 | 2389600 | Equitable | N/A | 2389600 | 0 | 2389600 | 100 | 2389600 | 2389600 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: 2018. Assessor remarks: Not working needs repair.
10215 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement (6km) of Verovian Ngata gate - Murage Road in Menengai West Ward Rongai Sub County | To maintain Spot Improvement (6km) of Verovian Ngata gate - Murage Road in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement (6km) of Verovian Ngata gate - Murage Road in Menengai West Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | MENENGAI WEST | -0.151362 36.01104 1764.7 19.299999237060547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2309560 | 2309560 | 2309560 | Equitable | N/A | 2309560 | 0 | 2309560 | 100 | 2309560 | 2389600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10216 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Gitari - Kimamo Acess Roads (1.7km) in Menengai West Ward Rongai Sub County | To maintain Spot Improvement of Gitari - Kimamo Acess Roads (1.7km) in Menengai West Ward Rongai Sub County in serviceable condition | Spot Improvement of Gitari - Kimamo Acess Roads (1.7km) in Menengai West Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | MENENGAI WEST | -0.151362 36.01104 1764.7 19.299999237060547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1498720 | 1498720 | 1498720 | Equitable | N/A | 1498720 | 0 | 1498720 | 100 | 1498720 | 2389600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10217 | Infrastructure, Development and Maintenance | Construction of Drainange and waste bins | To construct Drainange and waste bins | Drainange and waste bins constructed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10218 | Infrastructure, Development and Maintenance | Drainage Works at Molo Market | To implement drainage works at molo market for road connectivity and accessibility | Drainage Works at Molo Market completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 603518 | 603518 | 603518 | Equitable | N/A | 603518 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10219 | Infrastructure, Development and Maintenance | Grading, Expansion and Murraming of 20 Acres - Kwa Zakayo Road in Molo Central Ward Molo Sub County | To implement grading, expansion and murraming of 20 acres - kwa zakayo road in molo central ward molo sub county for road connectivity and accessibility | Grading, Expansion and Murraming of 20 Acres - Kwa Zakayo Road in Molo Central Ward Molo Sub County completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10220 | Infrastructure, Development and Maintenance | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines | To implement molo central bridge in molo cental ward molo sub county: 1200mm id - 2lines for road connectivity and accessibility | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10221 | Infrastructure, Development and Maintenance | Rehabilitation of molo central access roads | To rehabilitate molo central access roads to restore functionality | Molo central access roads rehabilitated | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10222 | Infrastructure, Development and Maintenance | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy | To implement rehabillitation of streetlights and maintainance in molo ward, molo sub county, mologreen garden area @tayari,mutirithia kwa daktari, behind molo academy for road connectivity and accessibility | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, mologreen garden area @tayari,Mutirithia kwa daktari, behind molo Academy completed | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 789728 | 3789728 | 3789728 | Equitable | N/A | 3789728 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10223 | Infrastructure, Development and Maintenance | Repair of Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County | To rehabilitate Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County to restore functionality | Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County rehabilitated | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10224 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County | To maintain Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County in serviceable condition | Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County maintained | 3111504 | N/A | MOLO | MOLO CENTRAL | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1817024 | 1817024 | 1817024 | Equitable | N/A | 1817024 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10225 | Infrastructure, Development & Maintenance | Construction of Salgaa Lorry Park (Drainage Works) in Rongai Sub county | To construct Salgaa Lorry Park (Drainage Works) in Rongai Sub county | Salgaa Lorry Park (Drainage Works) in Rongai Sub county constructed | 3111504 | N/A | RONGAI | MOSOP | -0.206783, 35.849527 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2019 | 3975474 | 3975474 | 3975474 | Equitable | N/A | 3975474 | 0 | 3975474 | 100 | 3975474 | 3975474 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Complete.
10226 | mosop ward culverts, drainage works and bridges | mosop ward culverts, drainage works and bridges | To implement mosop ward culverts, drainage works and bridges for road connectivity and accessibility | mosop ward culverts, drainage works and bridges completed | 3111504 | N/A | RONGAI | MOSOP | -0.252383 35.840025 2064.6 3.700000047683716 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000001 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995200 | 0 | 1995200 | 1995200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
10227 | Infrastructure, Development & Maintenance | murraming, drainage and culvert in Salgaa, Rigogo and Sumeek | To implement murraming, drainage and culvert in salgaa, rigogo and sumeek for road connectivity and accessibility | murraming, drainage and culvert in Salgaa, Rigogo and Sumeek completed | 3111504 | N/A | RONGAI | MOSOP | -0.266963 36.0019 2029.9000244140625 20 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 0 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
10228 | Routine Maintenance and Spot Improvement of Elburgon - Wakanguthi -Shawa roads and installation of culverts in Mosop Ward Rongai Sub County | Routine Maintenance and Spot Improvement of Elburgon - Wakanguthi -Shawa roads and installation of culverts in Mosop Ward Rongai Sub County | To maintain Spot Improvement of Elburgon - Wakanguthi -Shawa roads and installation of culverts in Mosop Ward Rongai Sub County in serviceable condition | Spot Improvement of Elburgon - Wakanguthi -Shawa roads and installation of culverts in Mosop Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | MOSOP | -0.234408, 35.827232 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2018 | 2996048 | 2996048 | 2996048 | Equitable | N/A | 2996048 | 0 | 0 | 0 | 0 | 2996048 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: O thine land. Assessor remarks: Good.
10229 | Infrastructure, Development & Maintenance | design and construction of JM bridge | To design and construct JM bridge | JM bridge designed and constructed | 3111504 | N/A | GILGIL | MURINDAT | -0.41071, 36.312388 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1980250 | 99 | 1980250 | 1983716 | 19750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Josi Construction Company. Assessor remarks: Operational.
10230 | Infrastructure, Development & Maintenance | design and construction of Kiarumbwa bridge | To design and construct Kiarumbwa bridge | Kiarumbwa bridge designed and constructed | 3111504 | N/A | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999989 | 100 | 1999989 | 11 | 11 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10231 | Infrastructure, Development & Maintenance | Grading and Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County | To improve road accessibility by grading and Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County | And Culvert Installation (Kibe Bridge) on Kibe Road in Morindat Ward- Gilgil Sub County graded | 3111504 | N/A | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999800 | 1999800 | 1999800 | Equitable | N/A | 1999800 | 0 | 1999800 | 100 | 1999800 | 1999800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10232 | Infrastructure, Development & Maintenance | grading and murraming of 1.5km Gatondo road | To improve road infrastructure by grading and murraming 1.5km Gatondo road | 1.5km Gatondo road graded and murramed | 3111504 | N/A | GILGIL | MURINDAT | -0.403673, 36.302628 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2453350 | 98.1 | 2453350 | 34550 | 46650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Jilsu General & Supplies Ltd. Assessor remarks: Good.
10233 | Infrastructure, Development & Maintenance | grading and murraming of Karunga centre | To improve road infrastructure by grading and murraming Karunga centre | Karunga centre graded and murramed | 3111504 | N/A | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2453350 | 122.7 | 2453350 | 2000000 | -453350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10234 | Infrastructure, Development & Maintenance | grading and murraming of Kwa Munjeshi road 2km | To improve road infrastructure by grading and murraming Kwa Munjeshi road 2km | Kwa Munjeshi road 2km graded and murramed | 3111504 | N/A | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996128 | 99.8 | 1996128 | 2172 | 3872 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10235 | grading and murraming of Nyairoko Road | grading and murraming of Nyairoko Road | To improve road infrastructure by grading and murraming Nyairoko Road | Nyairoko Road graded and murramed | 3111504 | N/A | GILGIL | MURINDAT | -0.479849, 36.379091 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2453350 | 122.7 | 2453350 | 2000000 | -453350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Open Door Investment Ltd. Assessor remarks: There's need for the road to be redone.
10236 | Proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County | Proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County | To undertake the proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County | Proposed Grading and Culvert Installation of Mwicige Road in Morendat Ward Gilgil Sub County implemented | 3111504 | N/A | GILGIL | MURINDAT | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3999950 | 3999950 | 3999950 | Equitable | N/A | 3999950 | 0 | 1999800 | 50 | 1999800 | 3999950 | 2000150 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10237 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 10No. 13m. Highmast flood lights in Selected Centres in Morindat Ward, Gilgil Sub County | To undertake the proposed installation and commissioning of 10No. 13m. Highmast flood lights in Selected Centres in Morindat Ward, Gilgil Sub County | Proposed installation and commissioning of 10No. 13m. Highmast flood lights in Selected Centres in Morindat Ward, Gilgil Sub County implemented | 3111504 | N/A | GILGIL | MURINDAT | -0.502526, 36.367899 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2905220 | 2905220 | 2905220 | Equitable | N/A | 2905220 | 0 | 2905220 | 100 | 2905220 | 3999950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Raylight. Assessor remarks: Need for additional street lights.
10238 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County | To maintain Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County in serviceable condition | Spot Improvement of Murindat - Waishakeri Road(3.5km) in Morendat Ward Gilgil Sub County maintained | 3111504 | N/A | GILGIL | MURINDAT | -0.482094, 36.362844 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2989320 | 2989320 | 2989320 | Equitable | N/A | 2989320 | 0 | 244300 | 8.2 | 244300 | 244300 | 2745020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Joylene Supplies & Constr. Assessor remarks: Good.
10239 | Proposed Construction of Kahuho - Kiambogo Bridge in Naivasha East Ward, Naivasha Sub County | Proposed Construction of Kahuho - Kiambogo Bridge in Naivasha East Ward, Naivasha Sub County | To undertake the proposed Construction of Kahuho - Kiambogo Bridge in Naivasha East Ward, Naivasha Sub County | Proposed Construction of Kahuho - Kiambogo Bridge in Naivasha East Ward, Naivasha Sub County implemented | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.745223 36.476318 2091.500244140625 3.75 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 3499732.5 | 3499732.5 | 3499732.5 | Equitable | N/A | 3499732.5 | 0 | 996000 | 28.5 | 996000 | 3499733 | 2503732.5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ues. Assessor remarks: Require regular maintenance.
10240 | Routine Maintenance and Spot Improvement of Benjei - Ha Wazakaria road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Benjei - Ha Wazakaria road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Benjei - Ha Wazakaria road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Benjei - Ha Wazakaria road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.745223 36.476318 2091.500244140625 3.75 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 998760 | 998760 | 998760 | Equitable | N/A | 998760 | 0 | 960654 | 96.2 | 960654 | 38106 | 38106 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ues. Assessor remarks: Require regular maintenance.
10241 | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Highway - Gieterero road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.817755 36.544871 2503.067626953125 33.86399841308594 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1199440 | 1199440 | 1199440 | Equitable | N/A | 1199440 | 0 | 1199440 | 100 | 1199440 | 1199440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes by that time. Viable: Yes during that time. Assessor remarks: Road in bad condition.
10242 | Routine Maintenance and Spot Improvement of Kiambogo secondary - Sisioni Road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Kiambogo secondary - Sisioni Road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Kiambogo secondary - Sisioni Road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kiambogo secondary - Sisioni Road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.866736 36.534226 2501.2000000000003 4.900000095367432 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999550 | 1999550 | 1999550 | Equitable | N/A | 1999550 | 0 | 996000 | 49.8 | 996000 | 1999550 | 1003550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
10243 | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kimani Mburu - Kambogo Secondary Road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.866736 36.534226 2501.2000000000003 4.900000095367432 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996000 | 99.6 | 996000 | 1000000 | 4000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
10244 | Routine Maintenance and Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maryland Central Road 2.5km in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.74819 36.470822 2071.60009765625 4.199999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1974088 | 1974088 | 1974088 | Equitable | N/A | 1974088 | 0 | 335194 | 17 | 335194 | 1974088 | 1638894 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
10245 | Routine Maintenance and Spot Improvement of of Donkey - Factory - Mutitu Road in Naivasha East Ward Naivasha Sub County | Routine Maintenance and Spot Improvement of of Donkey - Factory - Mutitu Road in Naivasha East Ward Naivasha Sub County | To maintain Spot Improvement of of Donkey - Factory - Mutitu Road in Naivasha East Ward Naivasha Sub County in serviceable condition | Spot Improvement of of Donkey - Factory - Mutitu Road in Naivasha East Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.745223 36.476318 2091.500244140625 3.75 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4994844 | 99.9 | 4994844 | 1999550 | 5156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ues. Assessor remarks: Require regular maintenance.
10246 | Infrastructure, Development & Maintenance | design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka | To implement design and installation of highmast streetlighting at wanyama, muguga, free area and naka for road connectivity and accessibility | design and installation of highmast streetlighting at Wanyama, Muguga, free area and Naka completed | 3111504 | N/A | NAKURU EAST | NAKURU EAST | -0.292381, 36.119131 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11000000 | 11000000 | 11000000 | Equitable | N/A | 11000000 | 0 | 10690650 | 97.2 | 10690650 | 10690650 | 309350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kilewe electrohard and electronics. Assessor remarks: Require maintainance.
10247 | Infrastructure, Development and Maintenance | grading and murraming of Mzee wanyama road | To improve road infrastructure by grading and murraming Mzee wanyama road | Mzee wanyama road graded and murramed | 3111504 | N/A | NAKURU EAST | NAKURU EAST | -0.420525 36.154467 1824.8999999999999 4.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3497837 | 99.9 | 3497837 | 0 | 2163 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot enterprises. Assessor remarks: Project complete.
10248 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Amos Arap Kangongo road | To improve road infrastructure by grading and murraming and Culverts of Amos Arap Kangongo road | And Culverts of Amos Arap Kangongo road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.415259, 35.949121 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999400 | 100 | 1999400 | 1999400 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
10249 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of British- Center Juu Road | To improve road infrastructure by grading and murraming and Culverts of British- Center Juu Road | And Culverts of British- Center Juu Road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.412079, 35.937341 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1967711 | 89.4 | 1967711 | 10089 | 232289 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
10250 | Grading and Murraming and Culverts of Centre Chini- timsales road | Grading and Murraming and Culverts of Centre Chini- timsales road | To improve road infrastructure by grading and murraming and Culverts of Centre Chini- timsales road | And Culverts of Centre Chini- timsales road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.377829, 35.911439 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999834 | 100 | 1999834 | 1999834 | 166 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation to fully operate.
10251 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Cheptebes- Elkana road | To improve road infrastructure by grading and murraming and Culverts of Cheptebes- Elkana road | And Culverts of Cheptebes- Elkana road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.412079, 35.937341 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 619480 | 31 | 619480 | 619480 | 1380520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
10252 | Grading and Murraming and Culverts of Kamara-Takitech road | Grading and Murraming and Culverts of Kamara-Takitech road | To improve road infrastructure by grading and murraming and Culverts of Kamara-Takitech road | And Culverts of Kamara-Takitech road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.419264, 35.931977 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2889131 | 96.3 | 2889131 | 100943 | 110869 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition, it just needs regular maintenance.
10253 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Kapkuluma- Masaita Road | To improve road infrastructure by grading and murraming and Culverts of Kapkuluma- Masaita Road | And Culverts of Kapkuluma- Masaita Road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.362322, 35.893584 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2889131 | 144.5 | 2889131 | 1914232 | -889131 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sanker builders and decorators. Assessor remarks: The road needs improvement.
10254 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Kiberenge-Kamara Road | To improve road infrastructure by grading and murraming and Culverts of Kiberenge-Kamara Road | And Culverts of Kiberenge-Kamara Road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.412079, 35.937341 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2939436 | 98 | 2939436 | 59230 | 60564 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
10255 | Infrastructure, Development & Maintenance | Grading and Murraming and Culverts of Sojami- Mangwai- Recho road | To improve road infrastructure by grading and murraming and Culverts of Sojami- Mangwai- Recho road | And Culverts of Sojami- Mangwai- Recho road graded and murramed | 3111504 | N/A | NJORO | NESSUIT | -0.40816, 35.914615 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2238266 | 89.5 | 2238266 | 245178 | 261734 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainace.
10256 | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | Installation of Culverts at Sigotik in Nessuit Ward Njoro Sub County | To improve drainage and road access through culvert installation at Sigotik in Nessuit Ward Njoro Sub County | Culverts installed at Sigotik in Nessuit Ward Njoro Sub County | 3111504 | N/A | NJORO | NESSUIT | -0.392896 35.898763 2388.13560622558 27.98659896850586 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 973936 | 973936 | 973936 | Equitable | N/A | 973936 | 0 | 1794420 | 184.2 | 1794420 | 973936 | -820484 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
10257 | Routine Maintenance and Spot Improvement of Kaliangat - Kimugul Road in Nessuit Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Kaliangat - Kimugul Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Kaliangat - Kimugul Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Kaliangat - Kimugul Road in Nessuit Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NESSUIT | -0.413708, 35.880413 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017/18 | 2499800 | 2499800 | 2499800 | Equitable | N/A | 2499800 | 0 | 2472726 | 98.9 | 2472726 | 27074 | 27074 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs repair and grading.
10258 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Kasa Roho - Mathias - Kamara Road in Nessuit Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NESSUIT | -0.416054, 35.949283 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 975149 | 97.5 | 975149 | 975212 | 24851 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
10259 | Routine Maintenance and Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Mastaf - Msekekwa Road in Nessuit Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NESSUIT | -0.398441, 35.876715 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2015/16 | 2037424 | 2037424 | 2037424 | Equitable | N/A | 2037424 | 0 | 2037424 | 100 | 2037424 | 2037424 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road requires improvement.
10260 | Routine Maintenance and Spot Improvement of Pastor Geoffrey - Subuku Road in Nessuit Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Pastor Geoffrey - Subuku Road in Nessuit Ward Njoro Sub County | To maintain Spot Improvement of Pastor Geoffrey - Subuku Road in Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement of Pastor Geoffrey - Subuku Road in Nessuit Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NESSUIT | -0.415057, 35.920681 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017/18 | 2499892.8 | 2499892.8 | 2499892.8 | Equitable | N/A | 2499892.8 | 0 | 2498269 | 99.9 | 2498269 | 1624 | 1623.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good working condition.
10261 | Infrastructure, Development & Maintenance | design and construction of utafiti bridge | To design and construct utafiti bridge | Utafiti bridge designed and constructed | 3111504 | N/A | NJORO | NJORO | -0.38562 35.936234 2263.509521484375 16.58799934387207 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
10262 | Infrastructure, Development & Maintenance | Grading of Piave Dam K Apple Centre junction Kikabu Centre Junction Kanugu Road | To improve road accessibility by grading Piave Dam K Apple Centre junction Kikabu Centre Junction Kanugu Road | Piave Dam K Apple Centre junction Kikabu Centre Junction Kanugu Road graded | 3111504 | N/A | NJORO | NJORO | -0.356911, 35.975501 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017 | 2694680.5 | 2694680.5 | 2694680.5 | Equitable | N/A | 2694680.5 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
10263 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 5No. 13m Highmast floodlights in Piave Centre ,Njokerio Centre and Rurii village in Njoro Ward ,Njoro Sub-County | To undertake the proposed installation and commissioning of 5No. 13m Highmast floodlights in Piave Centre ,Njokerio Centre and Rurii village in Njoro Ward ,Njoro Sub-County | Proposed installation and commissioning of 5No. 13m Highmast floodlights in Piave Centre ,Njokerio Centre and Rurii village in Njoro Ward ,Njoro Sub-County implemented | 3111504 | N/A | NJORO | NJORO | -0.37681, 35.933723 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2022 | 1499300 | 1499300 | 1499300 | Equitable | N/A | 1499300 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: mameli solution. Assessor remarks: In good state.
10264 | Infrastructure, Development & Maintenance | relocating of electricity poles in the middle of the road - Ahero Mwigito road | To implement relocating of electricity poles in the middle of the road - ahero mwigito road for road connectivity and accessibility | relocating of electricity poles in the middle of the road - Ahero Mwigito road completed | 3111504 | N/A | NJORO | NJORO | -0.376627, 35.927453 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3500000 | 87.5 | 3500000 | 0 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
10265 | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | Routine Maintenance and Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of AIC Church- Rongai Boarder road in Njoro Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NJORO | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 780100 | 780100 | 780100 | Equitable | N/A | 780100 | 0 | 780100 | 100 | 780100 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10266 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Belbur - Lions roads in Njoro Ward Njoro Sub County | To maintain Spot Improvement of Belbur - Lions roads in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of Belbur - Lions roads in Njoro Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NJORO | -0.376554, 35.965415 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017 | 947140 | 947140 | 947140 | Equitable | N/A | 947140 | 0 | 947140 | 100 | 947140 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Touch mark Africa. Assessor remarks: In good state of maintenance.
10267 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kamwago- Asante Farm Road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of Kamwago- Asante Farm Road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of Kamwago- Asante Farm Road in Njoro Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NJORO | -0.335855 35.950051 2145.000244140625 8.836999893188477 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 868144 | 868144 | 868144 | Equitable | N/A | 868144 | 0 | 868144 | 100 | 868144 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
10268 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Njoro posta - Kaburini road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of Njoro posta - Kaburini road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of Njoro posta - Kaburini road in Njoro Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NJORO | -0.335855 35.950051 2145.000244140625 8.836999893188477 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 795296 | 795296 | 795296 | Equitable | N/A | 795296 | 0 | 795296 | 100 | 795296 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
10269 | Routine Maintenance and Spot Improvement of Rurii Village Road in Njoro Ward Njoro Sub County | Routine Maintenance and Spot Improvement of Rurii Village Road in Njoro Ward Njoro Sub County | To maintain Spot Improvement of Rurii Village Road in Njoro Ward Njoro Sub County in serviceable condition | Spot Improvement of Rurii Village Road in Njoro Ward Njoro Sub County maintained | 3111504 | N/A | NJORO | NJORO | -0.361805, 35.908936 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017 | 1475288 | 1475288 | 1475288 | Equitable | N/A | 1475288 | 0 | 1475288 | 100 | 1475288 | 780100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair state.
10270 | Infrastructure, Development & Maintenance | Spot Improvemebt and Routine Maintenance of Kamwaura-Dispensary Road in Njoro Ward - Njoro Sub County | To implement spot improvemebt and routine maintenance of kamwaura-dispensary road in njoro ward - njoro sub county for road connectivity and accessibility | Spot Improvemebt and Routine Maintenance of Kamwaura-Dispensary Road in Njoro Ward - Njoro Sub County completed | 3111504 | N/A | NJORO | NJORO | -0.281523, 35.867324 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016 | 997020 | 997020 | 997020 | Equitable | N/A | 997020 | 0 | 868144 | 87.1 | 868144 | 780100 | 128876 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Now worn out due to the rains.
10271 | Construction of 11 No.Motorcycle Sheds in 14 centres in Nyota Ward Kuresoi North Sub County | Construction of 11 No.Motorcycle Sheds in 14 centres in Nyota Ward Kuresoi North Sub County | To construct 11 No.Motorcycle Sheds in 14 centres in Nyota Ward Kuresoi North Sub County | 11 No.Motorcycle Sheds in 14 centres in Nyota Ward Kuresoi North Sub County constructed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.409878, 35.655082 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2021-2022 | 3153838.16 | 3153838.16 | 3153838.16 | Equitable | N/A | 3153838.16 | 0 | 3916844 | 124.2 | 3916844 | 3153838 | -763005.84 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Pebbles Enterprises. Assessor remarks: Good- Needs flood lights near by.
10272 | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Grading and Gravelling of Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | To improve road infrastructure by grading and murraming Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County | Kimalany - Masaita- Mwate Road in Nyota Ward in Kuresoi North Sub County graded and murramed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.39393, 35.69199 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016-2017 | 2983700 | 2983700 | 2983700 | Equitable | N/A | 2983700 | 0 | 2999183 | 100.5 | 2999183 | 2983700 | -15483 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10273 | Grading and Gravelling of Sasimwa-Githiriga -Kamwaura Roads in Nyota Ward in Kuresoi North Sub County | Grading and Gravelling of Sasimwa-Githiriga -Kamwaura Roads in Nyota Ward in Kuresoi North Sub County | To improve road infrastructure by grading and murraming Sasimwa-Githiriga -Kamwaura Roads in Nyota Ward in Kuresoi North Sub County | Sasimwa-Githiriga -Kamwaura Roads in Nyota Ward in Kuresoi North Sub County graded and murramed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.350212, 35.637578 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2016-2017 | 4994000 | 4994000 | 4994000 | Equitable | N/A | 4994000 | 0 | 4949040 | 99.1 | 4949040 | 45000 | 44960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs spot patches.
10274 | Routine Maintenance and Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County | Routine Maintenance and Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Baringo B- Temonyotta Road in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.3048, 35.611843 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | _ | 1996440 | 1996440 | 1996440 | Equitable | N/A | 1996440 | 0 | 1997195 | 100 | 1997195 | 1996440 | -755 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEEDS DRAINAGE.
10275 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Langwenda - Tarakwa Road in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.350272 35.637452 2686 16.299999237060547 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1691046 | 99.5 | 1691046 | 1692000 | 8954 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage at some points needed., Culverts as well..
10276 | Routine Maintenance and Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County | Routine Maintenance and Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Mawingu Access Road in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.292573, 35.593885 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | _ | 2295610 | 2295610 | 2295610 | Equitable | N/A | 2295610 | 0 | 1997195 | 87 | 1997195 | 2295610 | 298415 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: ACCESSIBLE ROAD AND NEED IMPROVEMENT.
10277 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Olbumbu Nyota access Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Olbumbu Nyota access Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Olbumbu Nyota access Road in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.339415, 35.689843 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | June-2025 | 3999900 | 3999900 | 3999900 | Equitable | N/A | 3999900 | 0 | 3916844 | 97.9 | 3916844 | 83056 | 83056 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Mugim. Assessor remarks: Complete but needs more culverts.
10278 | Routine Maintenance and Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County | Routine Maintenance and Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Roads in 4 Centres - Sitoito-Seguton-Murinduko - Mugetho (Labour Based) in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.391555, 35.569833 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017-2018 | 3998440 | 3998440 | 3998440 | Equitable | N/A | 3998440 | 0 | 3998440 | 100 | 3998440 | 3998440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good- spot patches on some sections..
10279 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Sitoito - Arimi - Soliat Road in Nyota Ward Kuresoi North Sub County | To maintain Spot Improvement of Sitoito - Arimi - Soliat Road in Nyota Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Sitoito - Arimi - Soliat Road in Nyota Ward Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.385795, 35.574455 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2014-2015 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1997195 | 199.7 | 1997195 | 1000000 | -997195 | Stalled | 25 | 100 | Default Notice | 2016 | N/A | -997195 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: No yet. Viable: If done well.. Assessor remarks: Bad state-Needs urgent attention..
10280 | Infrastructure, Development & Maintenance | Grading and gravelling of Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | To improve road infrastructure by grading and murraming Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road graded and murramed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.350325 35.637462 2686.6 22.600000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 8500000 | 3349718 | 3349718 | Equitable | N/A | 3349718 | 0 | 3349718 | 100 | 3349718 | 3349718 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10281 | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | Construction of 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | To construct 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County | 4No. Motor Cycle Sheds at Kongoni, DCK and Kwa Muhia in Olkaria Ward Naivasha Sub County constructed | 3111504 | N/A | NAIVASHA | OLKARIA | -0.818589 36.259024 1883.4000244140625 10.5 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1188257 | 1188257 | 1188257 | Equitable | N/A | 1188257 | 0 | 1188257 | 100 | 1188257 | 1188257 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes the residents are making use of it. Assessor remarks: The project need some mentainance.
10282 | Infrastructure, Development & Maintenance | Rehabilitation of Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County | To rehabilitate Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County to restore functionality | Road and Culverts Installation at Olemayani - Ngambani Road in Olkaria Ward-Naivasha Sub County rehabilitated | 3111504 | N/A | NAIVASHA | OLKARIA | -0.915222, 36.281005 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 682277 | 682277 | 682277 | Equitable | N/A | 682277 | 0 | 682277 | 100 | 682277 | 682277 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: The project long due cant find the whole information. Assessor remarks: The project is long due it not identifiable.
10283 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | OLKARIA | -0.838224 36.362161 1883.0999755859375 11.142999649047852 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2994784 | 1322790 | 1322790 | Equitable | N/A | 1322790 | 0 | 1034800 | 78.2 | 1034800 | 287990 | 287990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Solar light operational.
10284 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kwa Muhia Estate Access Roads in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Kwa Muhia Estate Access Roads in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Kwa Muhia Estate Access Roads in Olkaria Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | OLKARIA | -0.832364 36.337064 1936.300048828125 6.109000205993652 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2988090 | 99.6 | 2988090 | 11670 | 11910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The place needs more drainages.
10285 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Muhia - Catholic Church Access Roads in Olkaria Ward Naivasha Sub County maintained | 3111504 | N/A | NAIVASHA | OLKARIA | -0.937926 36.364853 1912.552734375 8.583000183105469 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999760 | 100 | 2999760 | 2999760 | 240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
10286 | Infrastructure, Development & Maintenance | Grading, gravelling and culvert installation of Rapland-Kambi Turkana road | To implement grading, gravelling and culvert installation of rapland-kambi turkana road for road connectivity and accessibility | Grading, gravelling and culvert installation of Rapland-Kambi Turkana road completed | 3111504 | N/A | NAIVASHA | OLKARIA | -0.748908 36.530458 2294.7000000000003 4.400000095367432 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3479420 | 99.4 | 3479420 | 12760 | 20580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
10287 | Supply and installation of highmast security lights at Padua secondary school | Supply and installation of highmast security lights at Padua secondary school | To procure and install highmast security lights at Padua secondary school | Highmast security lights at Padua secondary school procured and installed | 3111504 | N/A | NAIVASHA | OLKARIA | -0.831323, 36.338095 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2990600 | 149.5 | 2990600 | 2000000 | -990600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The lights not working .there is electricity shot due to rain for the last one month.
10288 | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Design and Construction of drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | To design and construct drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts | Drainages along Mbugua & Mbugua Kanja square, Jerusalem , P.C.E.A road from Beverly - Game, 11 street road (from game to seventh day Adventist church, Kwazi to Mwariki sec. school to P.C.E.A road (Ndarugu church, tunnel drainage), Maintenance of drainage and culverts designed and constructed | 3111504 | N/A | NAKURU WEST | RHONDA | -0.31665, 36.063007 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 17/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4958000 | 99.2 | 4958000 | 5000000 | 42000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
10289 | Infrastructure, Development & Maintenance | Maintance and repair projects,drainage,culverts, streetlights | To implement maintance and repair projects,drainage,culverts, streetlights for road connectivity and accessibility | Maintance and repair projects,drainage,culverts, streetlights completed | 3111504 | N/A | NAKURU WEST | RHONDA | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1649414 | 1649414 | Equitable | N/A | 1649414 | 0 | 0 | 0 | 0 | 1649414 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10290 | Infrastructure, Development and Maintenance | Gradding and murraming of Ronald Ngala and Mariakani road, Sondu drive, upper Lokicha road | To implement gradding and murraming of ronald ngala and mariakani road, sondu drive, upper lokicha road for road connectivity and accessibility | Gradding and murraming of Ronald Ngala and Mariakani road, Sondu drive, upper Lokicha road completed | 3111504 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2845813 | 94.9 | 2845813 | 2999800 | 154187 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10291 | Infrastructure, Development & Maintenance | Installation of highmast 20m at Gilanis, Pyrethrum and Ngei estate | To improve security lighting through high mast floodlight installation at 20m at Gilanis, Pyrethrum and Ngei estate | High mast floodlight installed at 20m at Gilanis, Pyrethrum and Ngei estate | 3111504 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1996713 | 44.4 | 1996713 | 4500000 | 2503287 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10292 | Infrastructure, Development and Maintenance | Periodic and Routine Maintenance of Mbamba Road(300m) and Part of John Momanyi Road (400m)in Shabab Ward Nakuru West Sub County | To implement periodic and routine maintenance of mbamba road(300m) and part of john momanyi road (400m)in shabab ward nakuru west sub county for road connectivity and accessibility | Periodic and Routine Maintenance of Mbamba Road(300m) and Part of John Momanyi Road (400m)in Shabab Ward Nakuru West Sub County completed | 3111504 | N/A | NAKURU WEST | SHABAB | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 15819359 | 2285954 | 2285954 | Equitable | N/A | 2285954 | 0 | 2285954 | 100 | 2285954 | 2285954 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10293 | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | installation of foot bridges at Kadenye / Sirikwa / Muthenji footbridges | To install foot bridges at Kadenye / Sirikwa / Muthenji footbridges | Foot bridges at Kadenye / Sirikwa / Muthenji footbridges installed | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.264967, 35.68218 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999412 | 100 | 1999412 | 2000000 | 588 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Install guard rails and expand the culverts by construction a box culvert.
10294 | Infrastructure, Development & Maintenance | Installation of Streetlights in Sirikwa ward | To improve lighting and safety through installation of solar streetlights at Sirikwa ward | Solar streetlights installed at Sirikwa ward | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.289543, 35.636241 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 4400000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988254 | 99.7 | 3988254 | 3999600 | 11746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is partially functional, builbs and sensors need to be repaired.
10295 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County | To undertake the proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County | Proposed installation and commissioning of 13No. 13m. Highmast flood lights in Sirikwa Ward, Kuresoi North Sub County implemented | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.257902 35.667988 2735.5 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3908156 | 3908156 | 3908156 | Equitable | N/A | 3908156 | 0 | 319391 | 8.2 | 319391 | 319391 | 3588765 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: The project was not implemented, the facility needs maternity and maternity washrooms, piping, soak pit, septic tank, placenta pit, burning is incomplete, staff toilets are needed and the facility needs water supply and, and ceiling of existing rooms, floor is chipped, and has potholes.
10296 | Routine Maintenance and Spot Improvement of Muthinji - Kadenye Feeder Roads in Sirikwa Ward - Kuresoi North Sub County | Routine Maintenance and Spot Improvement of Muthinji - Kadenye Feeder Roads in Sirikwa Ward - Kuresoi North Sub County | To maintain Spot Improvement of Muthinji - Kadenye Feeder Roads in Sirikwa Ward - Kuresoi North Sub County in serviceable condition | Spot Improvement of Muthinji - Kadenye Feeder Roads in Sirikwa Ward - Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.268393, 35.691305 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3497400 | 3497400 | 3497400 | Equitable | N/A | 3497400 | 0 | 261624 | 7.5 | 261624 | 3497400 | 3235776 | Stalled | 25 | 7.5 | Default Notice | 2016 | N/A | 3235776 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project is currently in a bad state.
10297 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County | To maintain Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County in serviceable condition | Spot Improvement of Nyakinyua Road in Sirikwa Ward - Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.241737, 35.686483 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998948 | 2998948 | 2998948 | Equitable | N/A | 2998948 | 0 | 261624 | 8.7 | 261624 | 261624 | 2737324 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project needs grading,murraming, bush clearing, culvert installation and culvert unblocking.
10298 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Sacharan Road in Sirikwa Ward - Kuresoi North Sub County | To maintain Spot Improvement of Sacharan Road in Sirikwa Ward - Kuresoi North Sub County in serviceable condition | Spot Improvement of Sacharan Road in Sirikwa Ward - Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.260075, 35.667752 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1999144 | 1999144 | 1999144 | Equitable | N/A | 1999144 | 0 | 261624 | 13.1 | 261624 | 1999144 | 1737520 | Stalled | 75 | 13.1 | Default Notice | 2016 | N/A | 1737520 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Grading, murraming, drainage, culvert installation and unblocking of existing culverts.
10299 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Tombo/ Kagondo/Shalom Roads in Sirikwa Ward - Kuresoi North Sub County | To maintain Spot Improvement of Tombo/ Kagondo/Shalom Roads in Sirikwa Ward - Kuresoi North Sub County in serviceable condition | Spot Improvement of Tombo/ Kagondo/Shalom Roads in Sirikwa Ward - Kuresoi North Sub County maintained | 3111504 | N/A | KURESOI NORTH | SIRIKWA | -0.238547, 35.694397 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2496900 | 2496900 | 2496900 | Equitable | N/A | 2496900 | 0 | 261624 | 10.5 | 261624 | 2496900 | 2235276 | Stalled | 75 | 10.5 | Default Notice | 2016 | N/A | 2235276 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project needs bush clearing, grading, murraming, culverts installation, culverts cleaning and drainage works.
10300 | Construction of Kosaimo bridge in Soin Ward Rongai Sub County | Construction of Kosaimo bridge in Soin Ward Rongai Sub County | To construct Kosaimo bridge in Soin Ward Rongai Sub County | Kosaimo bridge in Soin Ward Rongai Sub County constructed | 3111504 | N/A | RONGAI | SOIN | -0.086168, 35.954887 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2017-2018 | 2982560 | 2982560 | 2982560 | Equitable | N/A | 2982560 | 0 | 1398960 | 46.9 | 1398960 | 2982560 | 1583600 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10301 | Infrastructure, Development & Maintenance | Design and construction of bridge connecting Arash and Kijabe-Bridge murraming | To design and construct bridge connecting Arash and Kijabe-Bridge murraming | Bridge connecting Arash and Kijabe-Bridge murraming designed and constructed | 3111504 | N/A | SUBUKIA | SUBUKIA | -0.026248, 36.231765 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: Yes. Contractor: Details not availed. Assessor remarks: The bridge was meant to serve motor vehicle users. But the state of the road doesn't allow vehicles to go through e of the road.
10302 | Infrastructure, Development & Maintenance | Grading and murraming of Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road | To improve road infrastructure by grading and murraming Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road | Kirengero centre - kieni secondary- kieni PCEA -Paul mukurino- Kamemo primary school road graded and murramed | 3111504 | N/A | SUBUKIA | SUBUKIA | -0.030753, 36.197117 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2018 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997926 | 0 | 1997926 | 1997926 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good condition.
10303 | grading and murraming of Mto Mbili- Arash Road | grading and murraming of Mto Mbili- Arash Road | To improve road infrastructure by grading and murraming Mto Mbili- Arash Road | Mto Mbili- Arash Road graded and murramed | 3111504 | N/A | SUBUKIA | SUBUKIA | -0.025148, 36.233823 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1500000 | 60 | 1500000 | 2500000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: A large section of the road NOT murramed.
10304 | Infrastructure, Development and Maintenance | Construction of Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | To construct Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County constructed | 3111504 | N/A | KURESOI SOUTH | TINET | -0.47504 35.631932 0 2400 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1951320 | 1951320 | 1951320 | Equitable | N/A | 1951320 | 0 | 1926890 | 98.7 | 1926890 | 1926890 | 24430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it was never started. Assessor remarks: Never started/established.
10305 | Infrastructure, Development & Maintenance | Design and construction of Kipsotet-chepkesigen bridge, | To design and construct Kipsotet-chepkesigen bridge, | Kipsotet-chepkesigen bridge, designed and constructed | 3111504 | N/A | KURESOI SOUTH | TINET | -0.509848, 35.664498 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2981947 | 99.4 | 2981947 | 2998930 | 18053 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state.
10306 | Grading, gravelling, onTMC-chemaner road | Grading, gravelling, onTMC-chemaner road | To implement grading, gravelling, ontmc-chemaner road for road connectivity and accessibility | Grading, gravelling, onTMC-chemaner road completed | 3111504 | N/A | KURESOI SOUTH | TINET | -0.478177 35.670193 0 1899.9990234375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4999000 | 100 | 4999000 | 5000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes and poor drainage.
10307 | murraming and grvelling of Kapkembu - Tirigoi road | murraming and grvelling of Kapkembu - Tirigoi road | To implement murraming and grvelling of kapkembu - tirigoi road for road connectivity and accessibility | murraming and grvelling of Kapkembu - Tirigoi road completed | 3111504 | N/A | KURESOI SOUTH | TINET | -0.538982 35.643548 0 2900 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2595274 | 99.8 | 2595274 | 2600000 | 4726 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes due to heavy rain.
10308 | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Cherokiet -Chepkosigen road in Tinet Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | TINET | -0.503619, 35.677364 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3099360 | 3099360 | 3099360 | Equitable | N/A | 3099360 | 0 | 239798 | 7.7 | 239798 | 239798 | 2859562 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: No. Assessor remarks: Poor condition murrum washed away no drainage and deep potholes.
10309 | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | Routine Maintenance and Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County | To maintain Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Kipsotet - Kapket Road in Tinet Ward Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | TINET | -0.495392, 35.646623 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 999900 | 999900 | 999900 | Equitable | N/A | 999900 | 0 | 999900 | 100 | 999900 | 999900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Large potholes murrurum wash away by rain.
10310 | Routine Maintenance of Boroon Road in Tinet Ward, Kuresoi South Sub County | Routine Maintenance of Boroon Road in Tinet Ward, Kuresoi South Sub County | To maintain Boroon Road in Tinet Ward, Kuresoi South Sub County in serviceable condition | Boroon Road in Tinet Ward, Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | TINET | -0.474567 35.630565 0 2200 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 632500 | 632500 | 632500 | Equitable | N/A | 632500 | 0 | 869300 | 137.4 | 869300 | 632500 | -236800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition.
10311 | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | Routine Maintenance of Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County | To maintain Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County in serviceable condition | Chemaner-Koita Road in Tinet Ward, Kuresoi South Sub County maintained | 3111504 | N/A | KURESOI SOUTH | TINET | -0.438399, 35.609035 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 869300 | 869300 | 869300 | Equitable | N/A | 869300 | 0 | 869300 | 100 | 869300 | 869300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain water.
10312 | Infrastructure, Development & Maintenance | Construction of the Bridge | To construct the Bridge | The Bridge constructed | 3111504 | N/A | MOLO | TURI | -0.30929, 35.700715 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1805852 | 180.6 | 1805852 | 1000000 | -805852 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
10313 | Infrastructure, Development & Maintenance | Grading and Gravelling of Duka Mbili - meza Road | To improve road infrastructure by grading and murraming Duka Mbili - meza Road | Duka Mbili - meza Road graded and murramed | 3111504 | N/A | MOLO | TURI | -0.313392, 35.716743 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1603775 | 80.2 | 1603775 | 1603775 | 396225 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
10314 | Infrastructure, Development & Maintenance | Grading and Gravelling of Kayole- Milimani Road | To improve road infrastructure by grading and murraming Kayole- Milimani Road | Kayole- Milimani Road graded and murramed | 3111504 | N/A | MOLO | TURI | -0.313392, 35.716743 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
10315 | Infrastructure, Development & Maintenance | Grading and Gravelling of Michatha-Eastleigh Road (2 corners) | To improve road infrastructure by grading and murraming Michatha-Eastleigh Road (2 corners) | Michatha-Eastleigh Road (2 corners) graded and murramed | 3111504 | N/A | MOLO | TURI | -0.286399, 35.74018 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491373 | 99.4 | 1491373 | 8627 | 8627 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road is good but in need of rehabilitation.
10316 | Infrastructure, Development & Maintenance | Grading and Gravelling of Turi spring-turi farmers’ nursery-Miarizim road | To improve road infrastructure by grading and murraming Turi spring-turi farmers’ nursery-Miarizim road | Turi spring-turi farmers’ nursery-Miarizim road graded and murramed | 3111504 | N/A | MOLO | TURI | -1.281229, 36.821402 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1483248 | 98.9 | 1483248 | 16752 | 16752 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: in good condition.
10317 | Infrastructure, Development & Maintenance | Grading and Gravelling of Valley Road | To improve road infrastructure by grading and murraming Valley Road | Valley Road graded and murramed | 3111504 | N/A | MOLO | TURI | -0.313392, 35.716743 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1478426 | 98.6 | 1478426 | 16118 | 21574 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs grading and gravelling afresh.
10318 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Chandera - Kawama Road Turi Ward Molo Sub County | To maintain Spot Improvement of Chandera - Kawama Road Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Chandera - Kawama Road Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.309717 35.735622 2797.2000000000003 11.600000381469727 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1500740 | 800740 | 800740 | Equitable | N/A | 800740 | 0 | 1457880 | 182.1 | 1457880 | 800740 | -657140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is very busy and needs occassional routine maintenance.
10319 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County | To maintain Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Kiambiriria - Gia - Ikamba road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.289744 35.695144 2803.7 76.5999984741211 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1498952 | 1498952 | 1498952 | Equitable | N/A | 1498952 | 0 | 1498952 | 100 | 1498952 | 1498952 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Due to the ongoing heavy rains, the road is adversely affected. It requires rehabilitation.
10320 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kiambu Road in Turi Ward Molo Sub County | To maintain Spot Improvement of Kiambu Road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Kiambu Road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1457880 | 145.8 | 1457880 | 1000000 | -457880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
10321 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Kinamba - St Bredan -Managu Road in Turi Ward Molo Sub County | To maintain Spot Improvement of Kinamba - St Bredan -Managu Road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Kinamba - St Bredan -Managu Road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.327656 35.741556 2689.5 89 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1457880 | 112.1 | 1457880 | 1300000 | -157880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: I. Good state.
10322 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Mukorombosi Road in Turi Ward Molo Sub County | To maintain Spot Improvement of Mukorombosi Road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Mukorombosi Road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1299896 | 1299896 | 1299896 | Equitable | N/A | 1299896 | 0 | 1457880 | 112.2 | 1457880 | 1299896 | -157984 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
10323 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Rafiki Roads Turi Ward Molo Sub County | To maintain Spot Improvement of Rafiki Roads Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Rafiki Roads Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1457880 | 97.2 | 1457880 | 1500000 | 42120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
10324 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Rural Turi Farmers road in Turi Ward Molo Sub County | To maintain Spot Improvement of Rural Turi Farmers road in Turi Ward Molo Sub County in serviceable condition | Spot Improvement of Rural Turi Farmers road in Turi Ward Molo Sub County maintained | 3111504 | N/A | MOLO | TURI | -0.300535 35.723508 2573.9 73.80000305175781 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983431 | 98.3 | 983431 | 16569 | 16569 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
10325 | Infrastructure, Development & Maintenance | Grading and Murraming of County Council- Kayole road | To improve road infrastructure by grading and murraming County Council- Kayole road | County Council- Kayole road graded and murramed | 3111504 | N/A | RONGAI | VISOI | -0.205011 35.84867 1901.199951171875 29.555999755859375 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2395128 | 79.8 | 2395128 | 2990100 | 604872 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10326 | Infrastructure, Development & Maintenance | Proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County | To undertake the proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County | Proposed installation and commissioning of 9No. 13m. Highmast flood light at Kampi ya Moto, Kamukunji and Waka centre, Visoi ward, Rongai Sub County implemented | 3111504 | N/A | RONGAI | VISOI | -0.156022, 35.848131 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2999040.8 | 2999040.8 | 2999040.8 | Equitable | N/A | 2999040.8 | 0 | 2999041 | 100 | 2999041 | 2999041 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: 2023. Viable: Yes. Assessor remarks: Goodness.
10327 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Doloraine - Tabot road in Visoi Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | VISOI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1932560 | 1932560 | 1932560 | Equitable | N/A | 1932560 | 0 | 1404922 | 72.7 | 1404922 | 527638 | 527638 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10328 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Lower Kimangu / EX Butler Road network in Visoi Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | VISOI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2800240 | 2800240 | 2800240 | Equitable | N/A | 2800240 | 0 | 2500000 | 89.3 | 2500000 | 2800240 | 300240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10329 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngesumin - Muricho - Dispensary road in Visoi Ward Rongai Sub County | To maintain Spot Improvement of Ngesumin - Muricho - Dispensary road in Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement of Ngesumin - Muricho - Dispensary road in Visoi Ward Rongai Sub County maintained | 3111504 | N/A | RONGAI | VISOI | N/A | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1999840 | 1999840 | 1999840 | Equitable | N/A | 1999840 | 0 | 1999840 | 100 | 1999840 | 527638 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10330 | Infrastructure, Development & Maintenance | Construction of Shoe Shiner Sheds in Viwandani ward Naivasha Sub County | To construct Shoe Shiner Sheds in Viwandani ward Naivasha Sub County | Shoe Shiner Sheds in Viwandani ward Naivasha Sub County constructed | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.717914, 36.435199 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 849398.4 | 849398.4 | 849398.4 | Equitable | N/A | 849398.4 | 0 | 318524 | 37.5 | 318524 | 318524 | 530874.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: operation.
10331 | design and installation of Viwandani highmast streetlighting | design and installation of Viwandani highmast streetlighting | To implement design and installation of viwandani highmast streetlighting for road connectivity and accessibility | design and installation of Viwandani highmast streetlighting completed | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.710361 36.433995 1907.199951171875 10.710000038146973 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6599810 | 94.3 | 6599810 | 7000000 | 400190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Working.
10332 | Infrastructure, Development & Maintenance | Proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county | To undertake the proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county | Proposed Drainage Construction and Civil Works at Site & Service Kabati in Viwandani Ward Naivasha Sub county implemented | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.71598 36.438907 1917.365 3.75600004196167 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 990864 | 990864 | 990864 | Equitable | N/A | 990864 | 0 | 990864 | 100 | 990864 | 990864 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
10333 | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | Construction of Ndatho bridge Box Culvert 3.0mx2.5x500 long | To construct Ndatho bridge Box Culvert 3.0mx2.5x500 long | Ndatho bridge Box Culvert 3.0mx2.5x500 long constructed | 3111504 | N/A | SUBUKIA | WASEGES | 0.058923, 36.236265 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494797 | 99.8 | 2494797 | 2500000 | 5203 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is in use and in good condition.
10334 | Infrastructure, Development & Maintenance | Grading and murraming of Limuru - St. Ulrich road | To improve road infrastructure by grading and murraming Limuru - St. Ulrich road | Limuru - St. Ulrich road graded and murramed | 3111504 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1051700 | 87.6 | 1051700 | 1052100 | 148300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
10335 | Infrastructure, Development & Maintenance | Grading and murraming of Wiyumiririe ( ngombe mbili to ponda mali road | To improve road infrastructure by grading and murraming Wiyumiririe ( ngombe mbili to ponda mali road | Wiyumiririe ( ngombe mbili to ponda mali road graded and murramed | 3111504 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1473135 | 98.2 | 1473135 | 26865 | 26865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
10336 | Infrastructure, Development & Maintenance | Installation of Culverts and Drainage works at Kerugoya Road in Waseges Ward Subukia Sub County | To improve drainage and road access through culvert installation at and Drainage works at Kerugoya Road in Waseges Ward Subukia Sub County | Culverts installed at and Drainage works at Kerugoya Road in Waseges Ward Subukia Sub County | 3111504 | N/A | SUBUKIA | WASEGES | 0.080012 36.244443 1866.4 16.200000762939453 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 498380.08 | 498380.08 | 498380.08 | Equitable | N/A | 498380.08 | 0 | 498380 | 100 | 498380 | 791676 | 0.08 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilet is in use.
10337 | installation of waseges ward highmast streetlighting | installation of waseges ward highmast streetlighting | To install waseges ward highmast streetlighting | Waseges ward highmast streetlighting installed | 3111504 | N/A | SUBUKIA | WASEGES | 0.166308, 36.249808 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900400 | 90 | 900400 | 1000000 | 99600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
10338 | Infrastructure, Development & Maintenance | Proposed Culverts Installation & Drainage Works at Haji Roads in Waseges Ward - Subukia Sub County | To undertake the proposed Culverts Installation & Drainage Works at Haji Roads in Waseges Ward - Subukia Sub County | Proposed Culverts Installation & Drainage Works at Haji Roads in Waseges Ward - Subukia Sub County implemented | 3111504 | N/A | SUBUKIA | WASEGES | 0.098648 36.250163 1819.6 8 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 392428 | 392428 | 392428 | Equitable | N/A | 392428 | 0 | 392428 | 100 | 392428 | 791676 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in good conditions.
10339 | Infrastructure, Development & Maintenance | Proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County | To undertake the proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County | Proposed Culverts Installation & Drainage Works at Mumoi Kwa Gitahi Road in Waseges Ward -Subukia Sub County implemented | 3111504 | N/A | SUBUKIA | WASEGES | 0.098648 36.250163 1819.6 8 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 791676 | 791676 | 791676 | Equitable | N/A | 791676 | 0 | 791676 | 100 | 791676 | 791676 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in good conditions.
10340 | Infrastructure, Development & Maintenance | Proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County | To undertake the proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County | Proposed Grading and Gravel Works at Akuis-St Ulrich Access Roads in Waseges Ward Subukia Sub County implemented | 3111504 | N/A | SUBUKIA | WASEGES | 0.017343 36.246975 2017.2 6.199999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1510900 | 1510900 | 1510900 | Equitable | N/A | 1510900 | 0 | 1510900 | 100 | 1510900 | 1510900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Good Condition.
10341 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County | To maintain Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County in serviceable condition | Spot Improvement of Shadrack Road in Waseges Ward Subukia Sub County maintained | 3111504 | N/A | SUBUKIA | WASEGES | 0.09975 36.262692 1855.2 3.799999952316284 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1697776 | 1697776 | 1697776 | Equitable | N/A | 1697776 | 0 | 1697776 | 100 | 1697776 | 1697776 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in use.
10342 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Wiyumiririe Road in Waseges Ward Subukia Sub County | To maintain Spot Improvement of Wiyumiririe Road in Waseges Ward Subukia Sub County in serviceable condition | Spot Improvement of Wiyumiririe Road in Waseges Ward Subukia Sub County maintained | 3111504 | N/A | SUBUKIA | WASEGES | 0.09975 36.262692 1855.2 3.799999952316284 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1400004 | 1400004 | 1400004 | Equitable | N/A | 1400004 | 0 | 1400004 | 100 | 1400004 | 1697776 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in use.
10343 | Infrastructure, Development & Maintenance | grading, murraming and culvert installation at Akuis - mama Karuga junction- Baraka - kwa Muchiri Road | To implement grading, murraming and culvert installation at akuis - mama karuga junction- baraka - kwa muchiri road for road connectivity and accessibility | grading, murraming and culvert installation at Akuis - mama Karuga junction- Baraka - kwa Muchiri Road completed | 3111504 | N/A | SUBUKIA | WASEGES | 0.14589 36.242263 1696.7 9.300000190734863 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2484720 | 99.4 | 2484720 | 2484720 | 15280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
10344 | Infrastructure, Development & Maintenance | installation of Waseges highmast streetlights | To install Waseges highmast streetlights | Waseges highmast streetlights installed | 3111504 | N/A | SUBUKIA | WASEGES | 0.080613, 36.244833 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1416745 | 0 | 1416744 | Equitable | N/A | 1416744 | 0 | 1404200 | 0 | 1404200 | 1416744 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: No lights.
10345 | Purchase of land for an Acess road at Sumeek-Atebwo Primary | Purchase of land for an Acess road at Sumeek-Atebwo Primary | To acquire land for an Acess road at Sumeek-Atebwo Primary | Land for an Acess road at Sumeek-Atebwo Primary acquired | 3130101 | Acquisition of Land | RONGAI | MOSOP | -0.250735 35.841887 2190.1 9.699999809265137 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
10346 | Infrastructure, Development & Maintenance | Purchase of land to open an access road at Lelechwet | To acquire land for open an access road at Lelechwet | Land for open an access road at Lelechwet acquired | 3130101 | Acquisition of Land | RONGAI | MOSOP | -0.274397 35.899878 2093.3 9.899999618530273 | VOTE NO. D 07 | MINISTRY OF INFRASTRUCTURE | MINISTRY OF INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha Barabara program. Assessor remarks: Done.
10347 | completion of Kabazi cooperative office | completion of Kabazi cooperative office | To complete Kabazi cooperative office | Kabazi cooperative office completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.077916, 36.171023 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 4400056 | 880 | 4400056 | 4400056 | -3900056 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Operationalized.
10348 | Construction and rehabilitation of Githioro market | Construction and rehabilitation of Githioro market | To construct and rehabilitation of Githioro market | And rehabilitation of Githioro market constructed | 3110299 | Construction of Buildings - Ot | BAHATI | DUNDORI | -0.263465, 36.188982 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/2019 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596977 | 99.9 | 3596977 | 429790 | 3023 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be operationalized.
10349 | construction of kiptangwany market | construction of kiptangwany market | To construct kiptangwany market | Kiptangwany market constructed | 3110299 | Construction of Buildings - Ot | GILGIL | ELEMENTAITA | -0.56569, 36.116668 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 995000 | 33.2 | 995000 | 2999100 | 2005000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but brought down to pave way for ESP Market.
10350 | Purchase of coolers, Pesturizers and milk ATM's | Purchase of coolers, Pesturizers and milk ATM's | To procure coolers, Pesturizers and milk ATM's | Coolers, Pesturizers and milk ATM's procured | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2019/2020 | N/A | 50000000 | 10000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10351 | construction of Karunga market sheds | construction of Karunga market sheds | To construct Karunga market sheds | Karunga market sheds constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.176515 36.165128 2111.300048828125 5.685999870300293 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1395190 | 99.7 | 1395190 | 2000000 | 4810 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it never met it objective. Contractor: Sagra holding ltd. Assessor remarks: Has never been occupied,market obstructed by other permanent stalls.
10352 | Design and construction of public toilet at Heshima market | Design and construction of public toilet at Heshima market | To design and construct public toilet at Heshima market | Public toilet at Heshima market designed and constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KIAMAINA | -0.244109 36.112062 1921.5 3.700000047683716 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | N/A | 1099308.8 | 1099309 | 1099309 | Equitable | N/A | 1099309 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was demolished.
10353 | Fencing of Kiamaina Market | Fencing of Kiamaina Market | To secure Kiamaina Market through fencing | Kiamaina Market fenced and secured | 3110299 | Construction of Buildings - Ot | BAHATI | KIAMAINA | -0.245597 36.112729 1918.0999755859375 44.12699890136719 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The market is now named Heshima market.
10354 | Construction of Latrine at Kiptororo market | Construction of Latrine at Kiptororo market | To construct Latrine at Kiptororo market | Latrine at Kiptororo market constructed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | KIPTORORO | -0.382307, 35.503002 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599590 | 99.9 | 599590 | 600000 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: It's not complete,not functional.It requires painting and renovations of the floor and doors.
10355 | Construction of 2 toilet at Karate Market | Construction of 2 toilet at Karate Market | To construct 2 toilet at Karate Market | 2 toilet at Karate Market constructed | 3110299 | Construction of Buildings - Ot | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 699973 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
10356 | Construction of toilet at Kasarani market | Construction of toilet at Kasarani market | To construct toilet at Kasarani market | Toilet at Kasarani market constructed | 3110299 | Construction of Buildings - Ot | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 699973 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
10357 | Construction of Lock-ups in Menengai West ward | Construction of Lock-ups in Menengai West ward | To construct Lock-ups in Menengai West ward | Lock-ups in Menengai West ward constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.146632, 36.009458 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997749 | 99.9 | 2997749 | 3000000 | 2251 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: No. Assessor remarks: Not yet.
10358 | Proposed Construction of 6 No doors pit latrine for Ihindu Market | Proposed Construction of 6 No doors pit latrine for Ihindu Market | To undertake the proposed Construction of 6 No doors pit latrine for Ihindu Market | Proposed Construction of 6 No doors pit latrine for Ihindu Market implemented | 3110299 | Construction of Buildings - Ot | NAIVASHA | NAIVASHA EAST | -0.840408, 36.550014 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2013-14 | 1053130.36 | 1053130 | 1053130 | Equitable | N/A | 1053130 | 0 | 2987510 | 283.7 | 2987510 | 1053130 | -1934380 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
10359 | Design and construction of Seguton Market Toilets | Design and construction of Seguton Market Toilets | To design and construct Seguton Market Toilets | Seguton Market Toilets designed and constructed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | NYOTA | -0.372456 35.685272 2759.400146484375 64.0999984741211 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497942 | 99.6 | 497942 | 690896 | 2058 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets were demolished.
10360 | Proposed construction of 6No. pit latrine at Muchorwe market | Proposed construction of 6No. pit latrine at Muchorwe market | To undertake the proposed construction of 6No. pit latrine at Muchorwe market | Proposed construction of 6No. pit latrine at Muchorwe market implemented | 3110299 | Construction of Buildings - Ot | MOLO | TURI | -0.329982, 35.68764 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | N/A | 1062571 | 1062571 | 1062571 | Equitable | N/A | 1062571 | 0 | 899000 | 84.6 | 899000 | 7000000 | 163571 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The facility has been vandalised.
10361 | Construction of toilet at Rongai market | Construction of toilet at Rongai market | To construct toilet at Rongai market | Toilet at Rongai market constructed | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998052 | 99.8 | 998052 | 4000000 | 1948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10362 | Construction and Rehabilitation of Markets | Construction and Rehabilitation of Markets | To construct and Rehabilitation of Markets | And Rehabilitation of Markets constructed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2020/2021 | 2020/2021 | 124200000 | 80000000 | 80000000 | N/A | N/A | 80000000 | 0 | 5989050 | 7.5 | 5989050 | 18483845 | 74010950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10363 | Laying of cabro and drainage at Wakulima Wholesale Market | Laying of cabro and drainage at Wakulima Wholesale Market | To implement laying of cabro and drainage at wakulima wholesale market for economic growth and market access | Laying of cabro and drainage at Wakulima Wholesale Market completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10364 | Purchase of land and construction of organic and fish market | Purchase of land and construction of organic and fish market | To acquire land and construct organic and fish market | Land acquired and organic and fish market constructed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10365 | construction of market shed inside wholesale market | construction of market shed inside wholesale market | To construct market shed inside wholesale market | Market shed inside wholesale market constructed | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2997058 | 59.9 | 2997058 | 1498915 | 2002942 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10366 | Fencing and Gate at Mbaruk Market | Fencing and Gate at Mbaruk Market | To secure and Gate at Mbaruk Market through fencing | And Gate at Mbaruk Market fenced and secured | 3110504 | Other Infrastructure and Civil Works | GILGIL | EBURU-MBARUK | -0.34847, 36.217858 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2022 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not at all. Contractor: No details. Assessor remarks: Not viable project.
10367 | Rehabilitation of the Olenguruone Market drainage | Rehabilitation of the Olenguruone Market drainage | To rehabilitate the Olenguruone Market drainage to restore functionality | The Olenguruone Market drainage rehabilitated | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.589169, 35.685563 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2020 | 500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 996953 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: drainage needs covering to avoid accident or grid to avoid blockages.
10368 | Construction of 2 market sheds in Wakulima Market | Construction of 2 market sheds in Wakulima Market | To construct 2 market sheds in Wakulima Market | 2 market sheds in Wakulima Market constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | -0.285416, 36.077196 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2020/21 | 10000000 | 0 | 3887144 | Equitable | N/A | 3887144 | 0 | 2997058 | 0 | 2997058 | 1498915 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for rehabilitation roof leakages and lighting.
10369 | Construction of market sheds inside wholesale market | Construction of market sheds inside wholesale market | To construct market sheds inside wholesale market | Market sheds inside wholesale market constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2997058 | 59.9 | 2997058 | 1498915 | 2002942 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10370 | Design and construction of banana stalls, Spices Shades and Timato Section) at wakulima banana market | Design and construction of banana stalls, Spices Shades and Timato Section) at wakulima banana market | To design and construct banana stalls, Spices Shades and Timato Section) at wakulima banana market | Banana stalls, Spices Shades and Timato Section) at wakulima banana market designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | -0.285404, 36.077304 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2018/19 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 4981650 | 49.8 | 4981650 | 2100000 | 5018350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S ridgerok enterprise. Assessor remarks: Meeting threshold.
10371 | Design and construction of Toilets and infrastractures at NASHA market | Design and construction of Toilets and infrastractures at NASHA market | To design and construct Toilets and infrastractures at NASHA market | Toilets and infrastractures at NASHA market designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 4816735 | 60.2 | 4816735 | 1178018 | 3183265 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10372 | Construction of Market sheds at Kongasis | Construction of Market sheds at Kongasis | To construct Market sheds at Kongasis | Market sheds at Kongasis constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | EBURU-MBARUK | -0.552511, 36.151373 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 18-19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Unspecified.
10373 | Construction of Elburgon market | Construction of Elburgon market | To construct Elburgon market | Elburgon market constructed | 3110599 | Other Infrastructure and Civil Works | MOLO | ELBURGON | -0.303366 35.81419 0 2000 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 6900000 | 6800000 | 8300000 | Equitable | N/A | 8300000 | 0 | 7995880 | 117.6 | 7995880 | 1000000 | -1195880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Yet to start.
10374 | design and construction of modern stalls at Racecourse | design and construction of modern stalls at Racecourse | To design and construct modern stalls at Racecourse | Modern stalls at Racecourse designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.302752 36.073162 1798.300048828125 39.14099884033203 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | N/A | 2998568.88 | 2998569 | 2998569 | Equitable | N/A | 2998569 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: The structures were vandalised. Does Not exist.
10375 | Design and construction of mitumba market sheds | Design and construction of mitumba market sheds | To design and construct mitumba market sheds | Mitumba market sheds designed and constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | GILGIL | -0.504716, 36.328314 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2021/22 | 1999254 | 1999254 | 1999254 | Equitable | N/A | 1999254 | 0 | 1925610 | 96.3 | 1925610 | 1925610 | 73644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cider collections. Assessor remarks: In good state.
10376 | Design and construction of Trade one stop shop | Design and construction of Trade one stop shop | To design and construct Trade one stop shop | Trade one stop shop designed and constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/20 | 2018/20 | N/A | 10000001 | 8000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10377 | renovation of Kabazi centre market | renovation of Kabazi centre market | To rehabilitate Kabazi centre market to restore functionality | Kabazi centre market rehabilitated | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | KABAZI | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2970700 | 594.1 | 2970700 | 2970700 | -2470700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
10378 | construction of stalls at Kapkures centre | construction of stalls at Kapkures centre | To construct stalls at Kapkures centre | Stalls at Kapkures centre constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.306306, 36.036551 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1492978 | 99.5 | 1492978 | 1000000 | 7022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been implemented. Assessor remarks: Not done. There's no public land available for market and so the stalls were not constructed.
10379 | Construction of stalls at Kapnandi Centre | Construction of stalls at Kapnandi Centre | To construct stalls at Kapnandi Centre | Stalls at Kapnandi Centre constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493560 | 99.6 | 1493560 | 1000000 | 6440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Place is very isolated. Assessor remarks: Location is Not viable, very isolated. Not operational.
10380 | Construction of stalls at Tulwet | Construction of stalls at Tulwet | To construct stalls at Tulwet | Stalls at Tulwet constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999770 | 100 | 1999770 | 1000000 | 230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Not accessible. Assessor remarks: Done but not operational. Poor accessibility.
10381 | Construction of Pondamali fish market fish washing stand connected to the sewer line | Construction of Pondamali fish market fish washing stand connected to the sewer line | To construct Pondamali fish market fish washing stand connected to the sewer line | Pondamali fish market fish washing stand connected to the sewer line constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.311409, 36.059612 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499979 | 100 | 1499979 | 0 | 21 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: It was viable but it's a project that has not benefited the residents since it's not yet in use. Contractor: SANKA BUILDERS. Assessor remarks: Floor chipped and potholes,vandalized and needs total renovation to be functional.
10382 | construction of shades for traders in Rhonda market | construction of shades for traders in Rhonda market | To construct shades for traders in Rhonda market | Shades for traders in Rhonda market constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.311362, 36.059653 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019/20 | 4000001 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 3982860 | 0 | 3982860 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,if secured and renovated. Contractor: FLASHDIL CONNECTIONS. Assessor remarks: Chipped floors and vandalized doorsrs.
10383 | Design and construction of market shed at Keringet market | Design and construction of market shed at Keringet market | To design and construct market shed at Keringet market | Market shed at Keringet market designed and constructed | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KERINGET | -0.424835 35.690778 2699.500244140625 92.9000015258789 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 4617339 | 4617339 | 4617339 | Equitable | N/A | 4617339 | 0 | 4521428 | 97.9 | 4521428 | 1000000 | 95911 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
10384 | Construction of market sheds, installation of flood lights and water point in Heshima market | Construction of market sheds, installation of flood lights and water point in Heshima market | To construct market sheds, installation of flood lights and water point in Heshima market | Market sheds, installation of flood lights and water point in Heshima market constructed | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.243599 36.111466 1944.4000244140625 65.03500366210938 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 3596178 | 0 | 3596178 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
10385 | Expansion of the stalls and construction of a public toilet | Expansion of the stalls and construction of a public toilet | To expand the stalls and construction of a public toilet to increase capacity | The stalls and construction of a public toilet expanded | 3110599 | Other Infrastructure and Civil Works | BAHATI | KIAMAINA | -0.268293 36.107548 1876.4000244140625 21.638999938964844 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is not use.
10386 | Proposed double unit stalls in Kivumbini | Proposed double unit stalls in Kivumbini | To undertake the proposed double unit stalls in Kivumbini | Proposed double unit stalls in Kivumbini implemented | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.297668, 36.082411 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 3997900 | 3997900 | 3997900 | Equitable | N/A | 3997900 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect traders from harsh weather conditions.
10387 | Design and construction of Curios along Kabarak road | Design and construction of Curios along Kabarak road | To design and construct Curios along Kabarak road | Curios along Kabarak road designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.281086, 36.057575 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3399947 | 97.1 | 3399947 | 0 | 100053 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10388 | Design and construction of Curios along Riva road | Design and construction of Curios along Riva road | To design and construct Curios along Riva road | Curios along Riva road designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.281086, 36.057575 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 3499421 | 3499421 | 3499421 | Equitable | N/A | 3499421 | 0 | 3399947 | 97.2 | 3399947 | 0 | 99474 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10389 | Design and construction of curios and bodaboda sheds in London centre | Design and construction of curios and bodaboda sheds in London centre | To design and construct curios and bodaboda sheds in London centre | Curios and bodaboda sheds in London centre designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.269087, 36.052567 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2020 | 3491553.6 | 3491554 | 3491554 | Equitable | N/A | 3491554 | 0 | 3399947 | 97.4 | 3399947 | 0 | 91607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floor of the sheds are in bad shape.
10390 | Construction of curio shops/stalls in London Ward | Construction of curio shops/stalls in London Ward | To construct curio shops/stalls in London Ward | Curio shops/stalls in London Ward constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | LONDON | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3395523 | 97 | 3395523 | 0 | 104477 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
10391 | rehabilitation of Longonot Market | rehabilitation of Longonot Market | To rehabilitate Longonot Market to restore functionality | Longonot Market rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3991386 | 99.8 | 3991386 | 0 | 8614 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10392 | Construction of additional roof, gutters and cementing of Maai Mahiu Market | Construction of additional roof, gutters and cementing of Maai Mahiu Market | To construct additional roof, gutters and cementing of Maai Mahiu Market | Additional roof, gutters and cementing of Maai Mahiu Market constructed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | MAAI MAHIU | -0.980266, 36.584425 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999435 | 100 | 2999435 | 2032772 | 565 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floor to be renovated.
10393 | Kiratina market construction | Kiratina market construction | To implement kiratina market construction for economic growth and market access | Kiratina market construction completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.269168 36.098984 1908.0999755859375 44.15700149536133 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | N/A | 3972851.2 | 3972851 | 3972851 | Equitable | N/A | 3972851 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10394 | Design and construction of market stalls | Design and construction of market stalls | To design and construct market stalls | Market stalls designed and constructed | 3110599 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.211397 35.852585 1911.5 12.199999809265137 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 1982730 | 1982730 | 1982730 | Equitable | N/A | 1982730 | 0 | 1951584 | 98.4 | 1951584 | 446985 | 31146 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: It is no operational.
10395 | Design and construction of Ogilgei market stall | Design and construction of Ogilgei market stall | To design and construct Ogilgei market stall | Ogilgei market stall designed and constructed | 3110599 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.297218, 35.95813 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1951584 | 97.6 | 1951584 | 446985 | 48416 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Randrop. Assessor remarks: Good.
10396 | Construction of Market sheds, toilet and water tank at Gitare market | Construction of Market sheds, toilet and water tank at Gitare market | To construct Market sheds, toilet and water tank at Gitare market | Market sheds, toilet and water tank at Gitare market constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MURINDAT | -0.409902, 36.312118 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2996964 | 99.9 | 2996964 | 3900000 | 3036 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONSTRUCTION. Assessor remarks: On-going.
10397 | Construction of market sheds and toilets at Ihendu, Maraigushu and Kinungi Markets | Construction of market sheds and toilets at Ihendu, Maraigushu and Kinungi Markets | To construct market sheds and toilets at Ihendu, Maraigushu and Kinungi Markets | Market sheds and toilets at Ihendu, Maraigushu and Kinungi Markets constructed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | NAIVASHA EAST | -0.750596, 36.524971 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2020 | 9000000 | 9000000 | 9000000 | Equitable | N/A | 9000000 | 0 | 2998020 | 33.3 | 2998020 | 0 | 6001980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: No. Assessor remarks: Market shed not occupied.
10398 | design and construction of Green food market at Free Area | design and construction of Green food market at Free Area | To design and construct Green food market at Free Area | Green food market at Free Area designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | NAKURU EAST | -0.292632, 36.119376 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2013/2014 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1489359 | 99.3 | 1489359 | 4000000 | 10641 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project ok.
10399 | design and construction of mitumba market at Free Area | design and construction of mitumba market at Free Area | To design and construct mitumba market at Free Area | Mitumba market at Free Area designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | NAKURU EAST | -0.292957, 36.119988 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3991444 | 99.8 | 3991444 | 4000000 | 8556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction limited. Assessor remarks: Project.
10400 | Fencing and Construction of Toilets of Kamwaura market | Fencing and Construction of Toilets of Kamwaura market | To secure and Construction of Toilets of Kamwaura market through fencing | And Construction of Toilets of Kamwaura market fenced and secured | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | NYOTA | -0.412588 35.578735 2528.3 12.899999618530273 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 690895 | 98.7 | 690895 | 690896 | 9105 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: If constructed. Assessor remarks: Stalled, play ground of children..
10401 | Fencing and Construction of Toilets of Mung'etho Market toilet | Fencing and Construction of Toilets of Mung'etho Market toilet | To secure and Construction of Toilets of Mung'etho Market toilet through fencing | And Construction of Toilets of Mung'etho Market toilet fenced and secured | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | NYOTA | -0.412588 35.578735 2528.3 12.899999618530273 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 690896 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: If constructed. Assessor remarks: Stalled, play ground of children..
10402 | Design and construction of stalls and bodaboda shed | Design and construction of stalls and bodaboda shed | To design and construct stalls and bodaboda shed | Stalls and bodaboda shed designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.306041, 36.063317 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 19/20 | 1999937.44 | 1999937 | 1999937 | Equitable | N/A | 1999937 | 0 | 1999937 | 100 | 1999937 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
10403 | Proposed double unit curio shops and bodaboda shed in Mwariki | Proposed double unit curio shops and bodaboda shed in Mwariki | To undertake the proposed double unit curio shops and bodaboda shed in Mwariki | Proposed double unit curio shops and bodaboda shed in Mwariki implemented | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.313546, 36.060871 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 19/20 | 2999959.52 | 2999960 | 2999960 | Equitable | N/A | 2999960 | 0 | 2999960 | 100 | 2999960 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
10404 | Construction of modern stalls in Kipanga | Construction of modern stalls in Kipanga | To construct modern stalls in Kipanga | Modern stalls in Kipanga constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | RHONDA | -0.306454, 36.063687 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2019/20 | 19/20 | 6000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2960772 | 98.7 | 2960772 | 1500000 | 39228 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction. Assessor remarks: Complete.
10405 | Design and construction of SME stalls in Githima estate | Design and construction of SME stalls in Githima estate | To design and construct SME stalls in Githima estate | SME stalls in Githima estate designed and constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 5799981 | 5799981 | 5799981 | Equitable | N/A | 5799981 | 0 | 5799981 | 100 | 5799981 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10406 | Fencing and Construction of Gacharage Toilet | Fencing and Construction of Gacharage Toilet | To secure and Construction of Gacharage Toilet through fencing | And Construction of Gacharage Toilet fenced and secured | 3110599 | Other Infrastructure and Civil Works | KURESOI NORTH | SIRIKWA | -0.289194, 35.634283 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, the market has a public toilet that is operational. Viable: Yes. Assessor remarks: The project is not fenced and it is on a private land..
10407 | Design and construction of curio lockups | Design and construction of curio lockups | To design and construct curio lockups | Curio lockups designed and constructed | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | SUBUKIA | 0.003144 36.229224 1992.0999755859375 20 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/17 | N/A | 995280 | 995280 | 995280 | Equitable | N/A | 995280 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Details not availed. Assessor remarks: Constructed but later demolished to pave way for A market shed and modern ESp market.
10408 | fencing of subukia market | fencing of subukia market | To secure subukia market through fencing | Subukia market fenced and secured | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | SUBUKIA | 0.00313 36.229321 1992.0999755859375 32.0989990234375 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 2058372 | 66.4 | 2058372 | 2058336 | 1041628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, the safety and security issues at the facility resolved.. Viable: Yes, the premises and facilities at the market are secured by provision of fence.. Contractor: Details not availed. Assessor remarks: Proposed fencing works completed as per contract period.
10409 | construction of Turi market sheds | construction of Turi market sheds | To construct Turi market sheds | Turi market sheds constructed | 3110599 | Other Infrastructure and Civil Works | MOLO | TURI | -0.282631, 35.758417 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1060777 | 1060777 | 1060777 | Equitable | N/A | 1060777 | 0 | 899000 | 84.7 | 899000 | 7000000 | 161777 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not fully operational.
10410 | Design and Construction of muchorwe lockups | Design and Construction of muchorwe lockups | To design and construct muchorwe lockups | Muchorwe lockups designed and constructed | 3110599 | Other Infrastructure and Civil Works | MOLO | TURI | -0.330145 35.687556 2765.7001953125 77.5999984741211 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project has been vandalised.
10411 | Construction of pit latrines at Moricho market | Construction of pit latrines at Moricho market | To construct pit latrines at Moricho market | Pit latrines at Moricho market constructed | 3110599 | Other Infrastructure and Civil Works | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2016/17 | 2016/2018 | 2016/2018 | 446985 | 0 | 446985 | Equitable | N/A | 446985 | 0 | 4991080 | 0 | 4991080 | 4991080 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10412 | Completion of market shed in Viwandani market | Completion of market shed in Viwandani market | To complete market shed in Viwandani market | Market shed in Viwandani market completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.715028 36.434489 1901.199951171875 11.230999946594238 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2956408 | 0 | 2956408 | 366850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
10413 | Construction of market sheds in Viwandani market | Construction of market sheds in Viwandani market | To construct market sheds in Viwandani market | Market sheds in Viwandani market constructed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.713012, 36.43553 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 3965912 | 0 | 3965912 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Partially. Viable: Viable. Assessor remarks: Operational.
10414 | Laying of cabro and drainage works in Viwandani market | Laying of cabro and drainage works in Viwandani market | To implement laying of cabro and drainage works in viwandani market for economic growth and market access | Laying of cabro and drainage works in Viwandani market completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.714893 36.434213 1900.199951171875 19.398000717163086 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2991640 | 0 | 2991640 | 366850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
10415 | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market | To implement plumbing works, sewer connection, drainage connections and electrification at viwandani market for economic growth and market access | Plumbing works, sewer connection, drainage connections and electrification at Viwandani market completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.715133, 36.434178 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999850 | 0 | 2999850 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good.
10416 | Rehabilitation of toilets in Viwandani market | Rehabilitation of toilets in Viwandani market | To rehabilitate toilets in Viwandani market to restore functionality | Toilets in Viwandani market rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.714472, 36.434091 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 366850 | 0 | 366850 | 366850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
10417 | Purchase of garbage skips | Purchase of garbage skips | To procure garbage skips | Garbage skips procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4600000 | 92 | 4600000 | 0 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10418 | purchase of Skip loader | purchase of Skip loader | To procure Skip loader | Skip loader procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 8500000 | 8500000 | N/A | N/A | 8500000 | 0 | 4600000 | 54.1 | 4600000 | 0 | 3900000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10419 | construction of ablution block at Rhonda market | construction of ablution block at Rhonda market | To construct ablution block at Rhonda market | Ablution block at Rhonda market constructed | 3111101 | Purchase of Medical and Dental Equipment | NAKURU WEST | KAPTEMBWO | -0.311509, 36.059121 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2019/20 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990080 | 0 | 1990080 | 1450000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,it was viable but has not met the needs of the residents. Contractor: U187. Assessor remarks: It's fully vandalized, with no water.
10420 | Purchase of land for construction of a market at Ngondi Trading Centre | Purchase of land for construction of a market at Ngondi Trading Centre | To acquire land for construction of a market at Ngondi Trading Centre | Land for construction of a market at Ngondi Trading Centre acquired | 3111103 | Purchase of Agricultural Machinery and Equipment | NAIVASHA | MAIELLA | -0.832803 36.203925 1761.6 19.399999618530273 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3386560 | 3386560 | Equitable | N/A | 3386560 | 0 | 3365400 | 99.4 | 3365400 | 3386560 | 21160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
10421 | wholesale market sewer system | wholesale market sewer system | To implement wholesale market sewer system for economic growth and market access | wholesale market sewer system completed | 3111502 | N/A | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1493256 | 99.6 | 1493256 | 1493256 | 6744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10422 | Purchase of land for construction of a market at Kayole | Purchase of land for construction of a market at Kayole | To acquire land for construction of a market at Kayole | Land for construction of a market at Kayole acquired | 3130101 | Acquisition of Land | NAIVASHA | LAKE VIEW | -0.748186, 36.465787 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No done. Assessor remarks: Land not purchased.
10423 | purchase of market land at Lanet Umoja | purchase of market land at Lanet Umoja | To procure market land at Lanet Umoja | Market land at Lanet Umoja procured | 3130101 | Acquisition of Land | BAHATI | LANET UMOJA | -0.267767, 36.171715 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Land has disputes.
10424 | Purchase of land for Langalanga Centre Market | Purchase of land for Langalanga Centre Market | To acquire land for Langalanga Centre Market | Land for Langalanga Centre Market acquired | 3130101 | Acquisition of Land | GILGIL | MURINDAT | -0.49925, 36.370528 | VOTE NO. D06 | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | MINISTRY OF TRADE, INDUSTRY, MARKETING AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2400000 | 60 | 2400000 | 2400000 | 1600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Peter Wambugu. Assessor remarks: Land purchased.
10425 | Conditional allocation for development of youth polytechnics | Conditional allocation for development of youth polytechnics | To implement conditional allocation for development of youth polytechnics for access to quality education and training | Conditional allocation for development of youth polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 35431434 | 26573575 | 0 | Equitable | N/A | 0 | 26573575 | 10193360 | 38.4 | 10193360 | 66289894 | 16380215 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10426 | Conditional Allocation for Rehabilitation of Youth Polytechnics | Conditional Allocation for Rehabilitation of Youth Polytechnics | To implement conditional allocation for rehabilitation of youth polytechnics for access to quality education and training | Conditional Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 47800000 | 47800000 | 0 | Equitable | N/A | 0 | 47800000 | 10193360 | 21.3 | 10193360 | 66289894 | 37606640 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10427 | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic | To implement purchasing of masonry, textile design and hair dressing equipment for barut polytechnic for access to quality education and training | Purchasing of masonry, textile design and hair dressing equipment for Barut polytechnic completed | 3110109 | N/A | NAKURU WEST | BARUT | -0.342342, 36.054698 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
10428 | fencing and land levelling of resource centre at sewage village | fencing and land levelling of resource centre at sewage village | To secure and land levelling of resource centre at sewage village through fencing | And land levelling of resource centre at sewage village fenced and secured | 3110201 | Residential Buildings (including hostels) | NAKURU WEST | KAPTEMBWO | -0.317911, 36.053019 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2023/24 | 2999999 | 0 | 3000000 | Equitable | Equitable | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes,it secured the resource center. Viable: Yes,it met the needs of the residents. Contractor: U71.
10429 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ereri ECD constructed | 3110201 | Residential Buildings (including hostels) | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 0 | 1199672 | 1199240 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10430 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kitopen ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.570768, 35.664825 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499996 | 100 | 1499996 | 4 | 4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
10431 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kwendo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.570768, 35.664825 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1499996 | 150 | 1499996 | 992345 | -499996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
10432 | Pangani Ecd | Pangani Ecd | To implement pangani ecd for access to quality education and training | Pangani Ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.589155, 35.674233 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 499380 | 49.9 | 499380 | 0 | 500620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes.
10433 | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point | To implement saptet ecd - design and construction of 1 no ecd classroom, pupils toilet and watering point for access to quality education and training | Saptet ECD - Design and construction of 1 No ECD classroom, pupils toilet and watering point completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.63516 35.678194 2480.126708984375 6.038000106811523 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499858 | 100 | 1499858 | 992345 | 142 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: done well ,but teacher and pupils toilet ..
10434 | Construction of latrines and guttering of ECDE class Kiptenden | Construction of latrines and guttering of ECDE class Kiptenden | To construct latrines and guttering of ECDE class Kiptenden | Latrines and guttering of ECDE class Kiptenden constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.565397, 35.697377 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 1240000 | 1240000 | 1240000 | Equitable | N/A | 1240000 | 0 | 416194 | 33.6 | 416194 | 1240000 | 823806 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: no. Viable: not yet.
10435 | Construction of pupil toilets at Ndasiata ECDE | Construction of pupil toilets at Ndasiata ECDE | To construct pupil toilets at Ndasiata ECDE | Pupil toilets at Ndasiata ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | AMALO | -0.638682, 35.65877 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2020 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 416194 | 52 | 416194 | 416194 | 383806 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10436 | Bahati pcea ECD | Bahati pcea ECD | To implement bahati pcea ecd for access to quality education and training | Bahati pcea ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.143336, 36.169812 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1698089 | 1698089 | 1698089 | Equitable | Equitable | 1698089 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
10437 | Construction of 1.No ECD classroom,pupilsToilets, and equipping | Construction of 1.No ECD classroom,pupilsToilets, and equipping | To construct 1.No ECD classroom,pupilsToilets, and equipping | 1.No ECD classroom,pupilsToilets, and equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.146885 36.121438 0 2700 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: They require another classroom.
10438 | Construction of an ECDE class, toilet, water tank and playing equipment at Jacaranda school | Construction of an ECDE class, toilet, water tank and playing equipment at Jacaranda school | To construct an ECDE class, toilet, water tank and playing equipment at Jacaranda school | An ECDE class, toilet, water tank and playing equipment at Jacaranda school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.178734, 36.121884 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1997862 | 133.2 | 1997862 | 2000000 | -497862 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It is viable.
10439 | Construction of an ECDE class, toilet, water tank and playing equipment at our Lady of mercy | Construction of an ECDE class, toilet, water tank and playing equipment at our Lady of mercy | To construct an ECDE class, toilet, water tank and playing equipment at our Lady of mercy | An ECDE class, toilet, water tank and playing equipment at our Lady of mercy constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.178734, 36.121884 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1997862 | 133.2 | 1997862 | 1997862 | -497862 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It is viable.
10440 | Spring Valley ECD | Spring Valley ECD | To implement spring valley ecd for access to quality education and training | Spring Valley ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.161335 36.111929 0 699.9990234375 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1196343 | 1196343 | 1196343 | Equitable | Equitable | 1196343 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project is stalled.
10441 | Barut Ward ECDs - Design and construction of 1 ECD classroom at Barut Special school | Barut Ward ECDs - Design and construction of 1 ECD classroom at Barut Special school | To implement barut ward ecds - design and construction of 1 ecd classroom at barut special school for access to quality education and training | Barut Ward ECDs - Design and construction of 1 ECD classroom at Barut Special school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | BARUT | -0.325565, 36.054039 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated..
10442 | Construction of 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | Construction of 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | To construct 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD | 1No. ECD Class, pupils toilet, watering point, equiping and Constrution of Perimter wall at Parkview ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | BARUT | 0.353373 36.049497 1834.1 503.205993652 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999051 | 1999051 | 1999051 | Equitable | N/A | 1999051 | 0 | 1999051 | 100 | 1999051 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Yet to be completed.good progress seen..
10443 | Design and Construction of 2 No. classroms at Barut Polytechnic | Design and Construction of 2 No. classroms at Barut Polytechnic | To design and construct 2 No. classroms at Barut Polytechnic | 2 No. classroms at Barut Polytechnic designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | BARUT | -0.342342, 36.036679 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 2498030 | 2498030 | 2498030 | Equitable | Equitable | 2498030 | 0 | 0 | 0 | 0 | 1194400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10444 | Soimmet ECD - Fencing of Land and Construction of ECD | Soimmet ECD - Fencing of Land and Construction of ECD | To implement soimmet ecd - fencing of land and construction of ecd for access to quality education and training | Soimmet ECD - Fencing of Land and Construction of ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | BARUT | -0.3656, 36.05254 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: PIRAKIL COMPANY LIMITED.
10445 | Construction of 1.No ECD classroom at Nyonjoro ECD | Construction of 1.No ECD classroom at Nyonjoro ECD | To construct 1.No ECD classroom at Nyonjoro ECD | 1.No ECD classroom at Nyonjoro ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | BIASHARA-NAIVASHA | -0.718757, 36.483535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2021 | 1199406.36 | 1199406.36 | 1199406.36 | Equitable | N/A | 1199406.36 | 0 | 1199406 | 100 | 1199406 | 2389990 | 0.36 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
10446 | Construction of ECD classroom at Freehold Primary school | Construction of ECD classroom at Freehold Primary school | To construct ECD classroom at Freehold Primary school | ECD classroom at Freehold Primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1190650 | 99.2 | 1190650 | 700000 | 9350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10447 | Construction of ECD classroom at Harambee Khalsa primary | Construction of ECD classroom at Harambee Khalsa primary | To construct ECD classroom at Harambee Khalsa primary | ECD classroom at Harambee Khalsa primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1190650 | 99.2 | 1190650 | 700000 | 9350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10448 | Construction of ECD classroom at Menengai Primary | Construction of ECD classroom at Menengai Primary | To construct ECD classroom at Menengai Primary | ECD classroom at Menengai Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | -0.286007, 36.087163 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199771 | 100 | 1199771 | 2000000 | 229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10449 | Design, construction and equipping of an ECD classroom and toilet at Umoja Primary school | Design, construction and equipping of an ECD classroom and toilet at Umoja Primary school | To implement design, construction and equipping of an ecd classroom and toilet at umoja primary school for access to quality education and training | Design, construction and equipping of an ECD classroom and toilet at Umoja Primary school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | -0.298776, 36.065947 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 0 | 1600000 | Equitable | Equitable | 1600000 | 0 | 2932410 | 0 | 2932410 | 2932410 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Yes, there's need for more classrooms as the population of ECDE leaners of about 100 pupils.
10450 | Upgrading of Harambee Khalsa Primary School ECD | Upgrading of Harambee Khalsa Primary School ECD | To upgrade Harambee Khalsa Primary School ECD through tarmacking for improved road connectivity | Harambee Khalsa Primary School ECD tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 799999.8 | 799999.8 | 799999.8 | Equitable | Equitable | 799999.8 | 0 | 1190650 | 148.8 | 1190650 | 0 | -390650.2 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10451 | Upgrading of Kariba Primary School ECD | Upgrading of Kariba Primary School ECD | To upgrade Kariba Primary School ECD through tarmacking for improved road connectivity | Kariba Primary School ECD tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | BIASHARA-NAKURU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 799356 | 99.9 | 799356 | 10 | 644 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10452 | Construction of 1No ECD Classrooms at ,Kianda Ecd, | Construction of 1No ECD Classrooms at ,Kianda Ecd, | To construct 1No ECD Classrooms at ,Kianda Ecd, | 1No ECD Classrooms at ,Kianda Ecd, constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.254931, 36.18657 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 22 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction.
10453 | Construction of 1.No ECD Classrooms Bavuni ECD, | Construction of 1.No ECD Classrooms Bavuni ECD, | To construct 1.No ECD Classrooms Bavuni ECD, | 1.No ECD Classrooms Bavuni ECD, constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.233853, 36.179481 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki construction company Ltd.
10454 | Construction of 1.No ECD Classrooms Kamburi ECD | Construction of 1.No ECD Classrooms Kamburi ECD | To construct 1.No ECD Classrooms Kamburi ECD | 1.No ECD Classrooms Kamburi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.254345 36.232745 2326.400146484375 7.199999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200001 | 1200001 | 1200001 | Equitable | Equitable | 1200001 | 0 | 1200000 | 100 | 1200000 | 1200000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
10455 | Construction of 1.No ECD Classrooms Tabuga ECD | Construction of 1.No ECD Classrooms Tabuga ECD | To construct 1.No ECD Classrooms Tabuga ECD | 1.No ECD Classrooms Tabuga ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.262307, 36.180044 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Durhas construction.
10456 | Construction of 1.No ECD Classrooms Wanyororo ECD | Construction of 1.No ECD Classrooms Wanyororo ECD | To construct 1.No ECD Classrooms Wanyororo ECD | 1.No ECD Classrooms Wanyororo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.255109, 36.185958 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 22 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes construction.
10457 | Construction of an ECD classroom at Dundori primary school | Construction of an ECD classroom at Dundori primary school | To construct an ECD classroom at Dundori primary school | An ECD classroom at Dundori primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.25394, 36.238355 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199978 | 100 | 1199978 | 22 | 22 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms Top Notch.
10458 | construction of Mikeu ECDE classroom | construction of Mikeu ECDE classroom | To construct Mikeu ECDE classroom | Mikeu ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.249596 36.231481 2331.10009765625 20 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done under NKU/CITY/222/2013-2014 no septic tank constructed.
10459 | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic | To implement dundori polytechnic - design and construction of 1 dormitory at dundori polytechnic for access to quality education and training | Dundori polytechnic - Design and Construction of 1 dormitory at Dundori polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.2496, 36.231092 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3487282 | 99.6 | 3487282 | 0 | 12718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wilkin ventures.
10460 | Kaburi ECDE - Construction of I classroom | Kaburi ECDE - Construction of I classroom | To implement kaburi ecde - construction of i classroom for access to quality education and training | Kaburi ECDE - Construction of I classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.237247 36.23572 2418 3.0999999046325684 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
10461 | Kirima ECD | Kirima ECD | To implement kirima ecd for access to quality education and training | Kirima ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.275245, 36.211228 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1140732.4 | 1140732.4 | 1140732.4 | Equitable | Equitable | 1140732.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10462 | Umoja ECDE - Construction of I classroom | Umoja ECDE - Construction of I classroom | To implement umoja ecde - construction of i classroom for access to quality education and training | Umoja ECDE - Construction of I classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | DUNDORI | -0.237247 36.23572 2418 3.0999999046325684 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
10463 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Elementaita ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU / MBARUK | -0.489692, 36.156969 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 18-19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1197000 | 99.8 | 1197000 | 156146 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
10464 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Itherero ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU / MBARUK | -0.346156, 36.21343 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1195536 | 99.6 | 1195536 | 156146 | 4464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Partially done. Viable: Yes.
10465 | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | Construction of 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | To construct 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD | 1No. ECD classroom, Teachers toilet, pupils toilet and watering point at Kapkures ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1195536 | 99.6 | 1195536 | 156146 | 4464 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10466 | Thugunui ECD | Thugunui ECD | To implement thugunui ecd for access to quality education and training | Thugunui ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1196343 | 1196343 | 1196343 | Equitable | Equitable | 1196343 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10467 | Completion of Kongasis Polytechnic | Completion of Kongasis Polytechnic | To complete Kongasis Polytechnic | Kongasis Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURU-MBARUK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 623800 | 41.6 | 623800 | 659133 | 876200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10468 | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | Construction of 3 ECD classroom at Morop Primary and Kiungururia primary | To construct 3 ECD classroom at Morop Primary and Kiungururia primary | 3 ECD classroom at Morop Primary and Kiungururia primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | EBURU-MBARUK | -0.605373, 36.164023 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Unspecified | 3600000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unspecified.
10469 | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) | To implement constuction of 3 ecd classrom in (mukinyai ecd, st. stephen ecd and mutate primary ecd) for access to quality education and training | Constuction of 3 ECD Classrom in (Mukinyai ECD, St. Stephen ECD and Mutate Primary ECD) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | ELBURGON | -0.203536, 35.817258 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | - | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 1192608 | 33.1 | 1192608 | 1222382 | 2407392 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10470 | Construction of 1No. Classroom at Ebenezer ECD | Construction of 1No. Classroom at Ebenezer ECD | To construct 1No. Classroom at Ebenezer ECD | 1No. Classroom at Ebenezer ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.5412 36.07037 2057.4 10.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199700 | 100 | 1199700 | 1200000 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10471 | Construction of 1No. Classroom at Kiambogo Township ECD | Construction of 1No. Classroom at Kiambogo Township ECD | To construct 1No. Classroom at Kiambogo Township ECD | 1No. Classroom at Kiambogo Township ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.595422 36.130154 0 98.4000015258789 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1166090 | 97.2 | 1166090 | 1200000 | 33910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
10472 | Construction of 1No. Classroom at MAHIGA ECD | Construction of 1No. Classroom at MAHIGA ECD | To construct 1No. Classroom at MAHIGA ECD | 1No. Classroom at MAHIGA ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.566526 36.119802 1961.0999755859375 1.0700000524520874 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 80430 | 6.7 | 80430 | 81930 | 1119570 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10473 | Construction of 1No. Classroom at Muriricua Primary ECD | Construction of 1No. Classroom at Muriricua Primary ECD | To construct 1No. Classroom at Muriricua Primary ECD | 1No. Classroom at Muriricua Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.566243 36.119887 1951.9 7.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198280 | 1198280 | 1198280 | Equitable | N/A | 1198280 | 0 | 1166090 | 97.3 | 1166090 | 409770 | 32190 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10474 | Construction of a classroom at Gwachati ECD | Construction of a classroom at Gwachati ECD | To construct a classroom at Gwachati ECD | A classroom at Gwachati ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.616893 36.148898 2042.8999999999999 16.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 80430 | 8 | 80430 | 81930 | 919570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
10475 | Munanda pry ecd | Munanda pry ecd | To implement munanda pry ecd for access to quality education and training | Munanda pry ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.594733, 36.109841 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199923 | 100 | 1199923 | 0 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10476 | Muthaiti pri. School ECDE - Construction of One Classroom at Muthaiti pri. School ECDE | Muthaiti pri. School ECDE - Construction of One Classroom at Muthaiti pri. School ECDE | To implement muthaiti pri. school ecde - construction of one classroom at muthaiti pri. school ecde for access to quality education and training | Muthaiti pri. School ECDE - Construction of One Classroom at Muthaiti pri. School ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.616893 36.148898 2042.8999999999999 16.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 119 | 0 | 119 | 119 | 1199881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
10477 | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | Njeru ECDE - Construction of one Classrooms at Njeru ECDE | To implement njeru ecde - construction of one classrooms at njeru ecde for access to quality education and training | Njeru ECDE - Construction of one Classrooms at Njeru ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.585127 36.13751 2039.304 5.4679999351501465 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 119 | 0 | 119 | 119 | 1199881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10478 | Ole Sultan polytechnic administration blocks and toilets | Ole Sultan polytechnic administration blocks and toilets | To implement ole sultan polytechnic administration blocks and toilets for access to quality education and training | Ole Sultan polytechnic administration blocks and toilets completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.567384 36.1137 1948.66 1.1130000352859497 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 3799982.4 | 3500000.4 | 3800000 | Equitable | N/A | 3800000 | 0 | 3799733 | 108.6 | 3799733 | 3800000 | -299732.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10479 | Tangi tano ecd | Tangi tano ecd | To implement tangi tano ecd for access to quality education and training | Tangi tano ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | ELEMENTAITA | -0.64194, 36.11936 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1299784 | 100 | 1299784 | 0 | 216 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10480 | Rehabilitation of Langalanga Pri and Lakeview pry. | Rehabilitation of Langalanga Pri and Lakeview pry. | To rehabilitate Langalanga Pri and Lakeview pry to restore functionality | Langalanga Pri and Lakeview pry rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | FLAMINGO | -0.305426, 36.078777 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | Fy/2016/17 | 2902087.8 | 2902087.8 | 2902087.8 | Equitable | N/A | 2902087.8 | 0 | 2084532 | 71.8 | 2084532 | 0 | 817555.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Contractor: Steadfast international Limited.
10481 | Design and construction of 2 ECDE classes at Lake view primary school | Design and construction of 2 ECDE classes at Lake view primary school | To design and construct 2 ECDE classes at Lake view primary school | 2 ECDE classes at Lake view primary school designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | FLAMINGO | -0.305357, 36.078337 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019/2020 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2385216 | 99.4 | 2385216 | 360243 | 14784 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s NaxxyLimited.
10482 | Design and construction of 2 ECDE classes at Race track primary school | Design and construction of 2 ECDE classes at Race track primary school | To design and construct 2 ECDE classes at Race track primary school | 2 ECDE classes at Race track primary school designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | FLAMINGO | -0.312617, 36.069464 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Fy2018-2019 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 352009 | 14.7 | 352009 | 360243 | 2047991 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Almaio Holdings.
10483 | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | Construction of 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | To construct 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point | 2no. ECD classrooms, Teachers toilet, pupils toilet and watering point constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.484536 36.336413 2011.800048828125 9.114999771118164 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999840 | 100 | 1999840 | 160 | 160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: One ECDE classroom constructed.
10484 | Construction of ECD classroom, equipping and construction of toilet at View point ECD centre | Construction of ECD classroom, equipping and construction of toilet at View point ECD centre | To construct ECD classroom, equipping and construction of toilet at View point ECD centre | ECD classroom, equipping and construction of toilet at View point ECD centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.507431 36.327348 1989.199951171875 12.510000228881836 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1079308 | 54 | 1079308 | 1682085 | 920692 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project description does not match whats on the ground.
10485 | Mbegi Primary ECD - Construction of 2. No ECD Classrooms | Mbegi Primary ECD - Construction of 2. No ECD Classrooms | To implement mbegi primary ecd - construction of 2. no ecd classrooms for access to quality education and training | Mbegi Primary ECD - Construction of 2. No ECD Classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.534619, 36.341851 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 3509 | 0.2 | 3509 | 2000000 | 1996491 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10486 | Ngomongo ECD equipments - equipping of Ngomongo ECD and purchase of water tank and piping | Ngomongo ECD equipments - equipping of Ngomongo ECD and purchase of water tank and piping | To implement ngomongo ecd equipments - equipping of ngomongo ecd and purchase of water tank and piping for access to quality education and training | Ngomongo ECD equipments - equipping of Ngomongo ECD and purchase of water tank and piping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.490013 36.320046 1998.323974609375 5.228000164031982 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
10487 | Teachers A ECD | Teachers A ECD | To implement teachers a ecd for access to quality education and training | Teachers A ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | GILGIL | -0.488439, 36.333706 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399615.44 | 1975994.44 | 1975994.44 | Equitable | Equitable | 1975994.44 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10488 | Airstrip ECDE - Construction of One Classroom and Equiping | Airstrip ECDE - Construction of One Classroom and Equiping | To implement airstrip ecde - construction of one classroom and equiping for access to quality education and training | Airstrip ECDE - Construction of One Classroom and Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.776669, 36.433058 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1171977 | 58.6 | 1171977 | 1173036 | 828023 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
10489 | Karagita ECDE - Construction of One Classroom and Equiping | Karagita ECDE - Construction of One Classroom and Equiping | To implement karagita ecde - construction of one classroom and equiping for access to quality education and training | Karagita ECDE - Construction of One Classroom and Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.776669, 36.433058 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998654 | 99.9 | 1998654 | 1998654 | 1346 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
10490 | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping | To implement longonot deb pri school ecde - construction of two classrooms and equiping for access to quality education and training | Longonot DEB Pri School ECDE - Construction of two Classrooms and Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.814865, 36.399555 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2600000 | 86.7 | 2600000 | 3000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10491 | Construction of a Rehabilitation Centre at YMCA | Construction of a Rehabilitation Centre at YMCA | To construct a Rehabilitation Centre at YMCA | A Rehabilitation Centre at YMCA constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | HELLS GATE | -0.778267, 36.429562 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998000 | 99.9 | 2998000 | 2988000 | 2000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10492 | Construction of Resource and Training centre-Nakuru VTC. | Construction of Resource and Training centre-Nakuru VTC. | To construct Resource and Training centre-Nakuru VTC | Resource and Training centre-Nakuru VTC constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 14000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 19900008 | 199 | 19900008 | 4986452 | -9900008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10493 | Construction of workshops- Njoro VTC | Construction of workshops- Njoro VTC | To construct workshops- Njoro VTC | Workshops- Njoro VTC constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.337502, 35.952445 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 6000000 | 4000000 | 4000000 | Equitable | Equitable | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Yes. Contractor: Fabrica Building and construction company Ltd.
10494 | Pangani special school | Pangani special school | To implement pangani special school for access to quality education and training | Pangani special school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | Equitable | 4000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10495 | Rehabilitation Of Nakuru Polytechnic PHASE2 | Rehabilitation Of Nakuru Polytechnic PHASE2 | To rehabilitate Nakuru Polytechnic PHASE2 to restore functionality | Nakuru Polytechnic PHASE2 rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999984 | 3999984 | 3999984 | Equitable | N/A | 3999984 | 0 | 3905534 | 97.6 | 3905534 | 11000000 | 94450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10496 | Revitalization Of youth Polytechnic | Revitalization Of youth Polytechnic | To implement revitalization of youth polytechnic for access to quality education and training | Revitalization Of youth Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 20000000 | 18346368 | 18346368 | Equitable | N/A | 18346368 | 0 | 623800 | 3.4 | 623800 | 659133 | 17722568 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10497 | Construction of 2 No. Classrooms at Wendo Polytechnic | Construction of 2 No. Classrooms at Wendo Polytechnic | To construct 2 No. Classrooms at Wendo Polytechnic | 2 No. Classrooms at Wendo Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.180871, 36.180667 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 2499985.6 | 2499985.6 | 2499985.6 | Equitable | Equitable | 2499985.6 | 0 | 2135 | 0.1 | 2135 | 2135 | 2497850.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Johtech construction co limited.
10498 | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, | To implement kabatini ward ecds - design and construction of 2 no. ecd classroom at wendo and kiugu, design and construction of teachers toilet, for access to quality education and training | Kabatini Ward ECDs - Design and Construction of 2 No. ECD classroom at wendo and Kiugu, design and construction of Teachers toilet, completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.232131 36.147748 1941.300048828125 37.290000915527344 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2400000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s max victor enterprise. Assessor remarks: Currently not operational,boda.-boda riders relocated because its in accessible requires installation of culvert.
10499 | Murungani ECD | Murungani ECD | To implement murungani ecd for access to quality education and training | Murungani ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KABATINI | -0.240744 36.153679 1941.800048828125 30.25 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 668700.8 | 668700.8 | 668700.8 | Equitable | Equitable | 668700.8 | 0 | 1070 | 0.2 | 1070 | 1070 | 667630.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational but should be renovated especially the floor, painting and ceiling.
10500 | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | construction of 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | To construct 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms | 1 ECDE classroon and toilets at Mburu gichua and Kihoto ECDE classrooms constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.08223 36.16987 0 1381 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2700000 | 2700000 | 2700000 | Equitable | Equitable | 2700000 | 0 | 2700000 | 100 | 2700000 | 2700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works Ltd. Assessor remarks: Requires equipping, toilets and kitchen.
10501 | Construction Of 3 ECD classroom at Kimochoch, Marigu B and Kihoto | Construction Of 3 ECD classroom at Kimochoch, Marigu B and Kihoto | To construct 3 ECD classroom at Kimochoch, Marigu B and Kihoto | 3 ECD classroom at Kimochoch, Marigu B and Kihoto constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | KABAZI | -0.08223, 36.16987 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399056 | 100 | 2399056 | 37 | 944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
10502 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Maraba ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Maraba ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Maraba ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Maraba ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.127778 35.68447 2569 3.200000047683716 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1191453 | 1191453 | 1191453 | Equitable | Equitable | 1191453 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Complete and functional.
10503 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Mau ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Mau ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Mau ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Mau ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.127778 35.68447 2569 3.200000047683716 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199892.4 | 783092.4 | 783092.4 | Equitable | Equitable | 783092.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Complete and functional.
10504 | Construction of ECD class at Bureti ECD | Construction of ECD class at Bureti ECD | To construct ECD class at Bureti ECD | ECD class at Bureti ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2020/21 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 830 | 0.1 | 830 | 830 | 1199170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
10505 | Construction of ECD class at Choronok ECD | Construction of ECD class at Choronok ECD | To construct ECD class at Choronok ECD | ECD class at Choronok ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.176655, 35.698202 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2020/21 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1199975 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
10506 | Construction of ECD class at Taban ECD | Construction of ECD class at Taban ECD | To construct ECD class at Taban ECD | ECD class at Taban ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KAMARA | -0.07866 35.672895 2565.1 2.9000000953674316 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2314 | 0.2 | 2314 | 2314 | 1197686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
10507 | Construction of 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | Construction of 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | To construct 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD | 1No. ECD Class and an administration block, pupils toilet, watering point, equiping at Lalwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.306306, 36.036551 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399998 | 2399998 | 2399998 | Equitable | N/A | 2399998 | 0 | 2399945 | 100 | 2399945 | 800 | 53 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving well.
10508 | Ingobor phase 2 | Ingobor phase 2 | To implement ingobor phase 2 for access to quality education and training | Ingobor phase 2 completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.288288 36.000456 0 2000 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1352110 | 1352110 | 1352110 | Equitable | N/A | 1352110 | 0 | 1105828 | 81.8 | 1105828 | 246282 | 246282 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has improved work environment. Assessor remarks: Done and in use.
10509 | kapkures Ward ECDs - Design and construction of 1 classroom at Tulwet ECD, teachers toilet, pupils toilet , water point at Tulwet primary | kapkures Ward ECDs - Design and construction of 1 classroom at Tulwet ECD, teachers toilet, pupils toilet , water point at Tulwet primary | To implement kapkures ward ecds - design and construction of 1 classroom at tulwet ecd, teachers toilet, pupils toilet , water point at tulwet primary for access to quality education and training | kapkures Ward ECDs - Design and construction of 1 classroom at Tulwet ECD, teachers toilet, pupils toilet , water point at Tulwet primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.36036 36.054767 0 2000 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Viable. But the market land requires to be developed to become operational. Currently it's idle land. Assessor remarks: Money used to purchase Land. The land has been purchased but is yet to be developed. Initially there was no land for construction of market.
10510 | toilet desks,desk and washing point ingobor | toilet desks,desk and washing point ingobor | To implement toilet desks,desk and washing point ingobor for access to quality education and training | toilet desks,desk and washing point ingobor completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPKURES | -0.306306 36.018533 0 2000 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2949834.6 | 2949834.6 | 2949834.6 | Equitable | N/A | 2949834.6 | 0 | 1635 | 0.1 | 1635 | 1635 | 2948199.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. But did not meet needs. Assessor remarks: Stalled. Not completed.
10511 | Construction of 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | Construction of 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | To construct 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school | 1No. ECD Class, pupils toilet, watering point at Kibowen Komen primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPTEMBWO | -0.310577 36.05279 1787.5 72.9000015258789 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 271440 | 0 | 271440 | 3800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Contractor: PANASCOPE HOLDINGS LTD. Assessor remarks: Complete but it has chipped and pothole floors need renovation.
10512 | construction of 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | construction of 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | To construct 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school | 1 ECDE classroom, toilet, water tank and equipping at Kibowen komen primary school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | KAPTEMBWO | -0.310577 36.05279 1787.5 72.9000015258789 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1599994 | 100 | 1599994 | 3800000 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Contractor: PANASCOPE HOLDINGS LTD. Assessor remarks: Complete but it has chipped and pothole floors need renovation.
10513 | Bararget ukwala ecd | Bararget ukwala ecd | To implement bararget ukwala ecd for access to quality education and training | Bararget ukwala ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.391032, 35.7425 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 999532 | 999532 | 999532 | Equitable | N/A | 999532 | 0 | 0 | 0 | 0 | 999532 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10514 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Highlands ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.442733 35.65781 2608.1 6.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 340868 | 28.4 | 340868 | 1199950 | 859082 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
10515 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkali ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkali ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkali ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkali ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199992.16 | 1199992.16 | 1199992.16 | Equitable | N/A | 1199992.16 | 0 | 156143 | 13 | 156143 | 156143 | 1043849.16 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10516 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkores ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.442733 35.65781 2608.1 6.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 1199997.8 | 1199997.8 | Equitable | N/A | 1199997.8 | 0 | 156143 | 13 | 156143 | 156143 | 1043854.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
10517 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipkoibet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10518 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Maziwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 497952 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10519 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangate ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.442733 35.65781 2608.1 6.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 340868 | 34.1 | 340868 | 497952 | 659132 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
10520 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tegat ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.442733 35.65781 2608.1 6.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 1199997.8 | 1199997.8 | Equitable | N/A | 1199997.8 | 0 | 340868 | 28.4 | 340868 | 340868 | 859129.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
10521 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tembwo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.421928 35.666268 2651.5 5.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199990 | 1199990 | 1199990 | Equitable | N/A | 1199990 | 0 | 1199990 | 100 | 1199990 | 1199990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
10522 | Construction of 2 No classrooms at Upendo | Construction of 2 No classrooms at Upendo | To construct 2 No classrooms at Upendo | 2 No classrooms at Upendo constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.463932 35.69647 2646.3 6.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1693833 | 1693833 | 1693833 | Equitable | N/A | 1693833 | 0 | 667928 | 39.4 | 667928 | 1693833 | 1025905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10523 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10524 | Construction of Kapkwen ECD Classroom | Construction of Kapkwen ECD Classroom | To construct Kapkwen ECD Classroom | Kapkwen ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.50589, 35.698535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 667928 | 55.7 | 667928 | 1200000 | 532072 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10525 | construction of Lelaibei ECDE classroom | construction of Lelaibei ECDE classroom | To construct Lelaibei ECDE classroom | Lelaibei ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.50589, 35.698535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 312620 | 26.1 | 312620 | 1200000 | 887380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10526 | Construction of Saptet ECD Classroom | Construction of Saptet ECD Classroom | To construct Saptet ECD Classroom | Saptet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.50589, 35.698535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 667928 | 50.2 | 667928 | 183305 | 662072 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10527 | Construction of Tendwet ECD Classroom | Construction of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KERINGET | -0.50589, 35.698535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 1330000 | 1330000 | Equitable | N/A | 1330000 | 0 | 312620 | 23.5 | 312620 | 538613 | 1017380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10528 | Construction of 1 No. ECD classroom, and pupils toilet at Workers Primary ECD | Construction of 1 No. ECD classroom, and pupils toilet at Workers Primary ECD | To construct 1 No. ECD classroom, and pupils toilet at Workers Primary ECD | 1 No. ECD classroom, and pupils toilet at Workers Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.269097, 36.114788 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1800000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 1782004 | 99 | 1782004 | 1045171 | 17996 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes.
10529 | Construction of 1 No. ECD classroom and pupils toilets at Rurii Primary ECD | Construction of 1 No. ECD classroom and pupils toilets at Rurii Primary ECD | To construct 1 No. ECD classroom and pupils toilets at Rurii Primary ECD | 1 No. ECD classroom and pupils toilets at Rurii Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.269097, 36.114788 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1800000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 1782004 | 99 | 1782004 | 1045171 | 17996 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes.
10530 | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD | To implement kiamaina ward ecds - purchase of land for ecd expansion for st peter primary ecd and central primary ecd for access to quality education and training | Kiamaina ward ECDs - Purchase of land for ECD expansion for St peter Primary ECD and Central primary ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.236625 36.133717 1909.5 3.200000047683716 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 0 | 0 | 0 | 3400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It's viable if can be purchased. Assessor remarks: No land purchased.
10531 | St. Peter ECD Kiamaina | St. Peter ECD Kiamaina | To implement st. peter ecd kiamaina for access to quality education and training | St. Peter ECD Kiamaina completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.241438, 36.138954 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199289 | 1199289 | 1199289 | Equitable | Equitable | 1199289 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10532 | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet | To implement workers primary ecd - design and construction of 1 ecd class room and pupils toilet for access to quality education and training | Workers Primary ECD - Design and Construction of 1 ECD class room and pupils toilet completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | KIAMAINA | -0.268707 36.114891 1863.5 48.20000076293945 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1782004 | 99 | 1782004 | 0 | 17996 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
10533 | 2 class Davishon ECD and Kariaini ECD | 2 class Davishon ECD and Kariaini ECD | To implement 2 class davishon ecd and kariaini ecd for access to quality education and training | 2 class Davishon ECD and Kariaini ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.476213 35.988603 2288 17.100000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1849000 | 1849000 | 1849000 | Equitable | N/A | 1849000 | 0 | 1849000 | 100 | 1849000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: At that time yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
10534 | Construction of 1 no ECD classroom at Davishon ECD | Construction of 1 no ECD classroom at Davishon ECD | To construct 1 no ECD classroom at Davishon ECD | 1 no ECD classroom at Davishon ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.440443 35.983555 2278.2001953125 4.400000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199612 | 100 | 1199612 | 1200000 | 388 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation required.
10535 | Construction of 1 no ECD classroom at Mutitu B ECD | Construction of 1 no ECD classroom at Mutitu B ECD | To construct 1 no ECD classroom at Mutitu B ECD | 1 no ECD classroom at Mutitu B ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.433837 35.96382 2225.1000000000004 12.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1185259 | 1185259 | 1185259 | Equitable | Equitable | 1185259 | 0 | 219716 | 18.5 | 219716 | 0 | 965543 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10536 | Construction of 1 no ECD classroom at Njugu ini ECD | Construction of 1 no ECD classroom at Njugu ini ECD | To construct 1 no ECD classroom at Njugu ini ECD | 1 no ECD classroom at Njugu ini ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.440443 35.983555 2278.2001953125 4.400000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199612 | 100 | 1199612 | 219716 | 388 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovation required.
10537 | KARIAINI ECD | KARIAINI ECD | To implement kariaini ecd for access to quality education and training | KARIAINI ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1080098 | 1080098 | 1080098 | Equitable | N/A | 1080098 | 0 | 1080098 | 100 | 1080098 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10538 | Kihonge ECD classroom - construction of a ECDE classroom and toilets Kihonge ECD classroom | Kihonge ECD classroom - construction of a ECDE classroom and toilets Kihonge ECD classroom | To implement kihonge ecd classroom - construction of a ecde classroom and toilets kihonge ecd classroom for access to quality education and training | Kihonge ECD classroom - construction of a ECDE classroom and toilets Kihonge ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.455877 35.985462 2286.60009765625 16.200000762939453 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1800000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 1199393 | 66.6 | 1199393 | 0 | 600607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10539 | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom | To implement kio ecd classroom - construction of a ecde classroom kio ecd classroom for access to quality education and training | Kio ECD classroom - construction of a ECDE classroom Kio ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.455877 35.985462 2286.60009765625 16.200000762939453 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199393 | 99.9 | 1199393 | 600000 | 607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10540 | Mutamaiyu ECD classroom - construction of a ECDE classroom Mutamaiyu ECD classroom | Mutamaiyu ECD classroom - construction of a ECDE classroom Mutamaiyu ECD classroom | To implement mutamaiyu ecd classroom - construction of a ecde classroom mutamaiyu ecd classroom for access to quality education and training | Mutamaiyu ECD classroom - construction of a ECDE classroom Mutamaiyu ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.433837 35.96382 2225.1000000000004 12.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199393 | 99.9 | 1199393 | 0 | 607 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10541 | Mutumburu ECD | Mutumburu ECD | To implement mutumburu ecd for access to quality education and training | Mutumburu ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | KIHINGO | -0.494685, 36.011653 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2016 | 1499264 | 1499264 | 1499264 | Equitable | Equitable | 1499264 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
10542 | Cheptuech polytechnic | Cheptuech polytechnic | To implement cheptuech polytechnic for access to quality education and training | Cheptuech polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.59162 35.645365 2576.7 24.700000762939453 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road for a permanent solution.
10543 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kibirech ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1270177 | 84.7 | 1270177 | 229823 | 229823 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
10544 | Construction of Emitik ECD Classroom | Construction of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1799740 | 5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
10545 | Construction of Konoin ECD Classroom | Construction of Konoin ECD Classroom | To construct Konoin ECD Classroom | Konoin ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1200000 | 5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
10546 | Construction of Sitotwet ECD Classroom | Construction of Sitotwet ECD Classroom | To construct Sitotwet ECD Classroom | Sitotwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.598048 35.611248 2413 13.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 202597 | 5 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
10547 | ECD classes:-Sototwet | ECD classes:-Sototwet | To implement ecd classes:-sototwet for access to quality education and training | ECD classes:-Sototwet completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.656443 35.6033 2446.4 5.599999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | N/A | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 0 | 0 | 0 | 999363 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional but there are no toilets..
10548 | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom | To implement ketitui central ecde classroom - design and construction of ketitui ecde classroom for access to quality education and training | Ketitui Central ECDE classroom - design and construction of Ketitui ECDE classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1200000 | 52340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
10549 | Seger ECDE classroom - design and construction of Seger ECDE classroom | Seger ECDE classroom - design and construction of Seger ECDE classroom | To implement seger ecde classroom - design and construction of seger ecde classroom for access to quality education and training | Seger ECDE classroom - design and construction of Seger ECDE classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | KIPTAGICH | -0.536993 35.578477 2446.5 5.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 519198 | 43.3 | 519198 | 1200000 | 680802 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
10550 | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD | To implement chemare ecd - design and construction of 1. no ecd classroom at kipkoimet ecd for access to quality education and training | Chemare ECD - Design and Construction of 1. No ECD classroom at Kipkoimet ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 648869 | 54.1 | 648869 | 376428 | 551131 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
10551 | Chepkoburot AGPO(YOUTH) polytechnic | Chepkoburot AGPO(YOUTH) polytechnic | To implement chepkoburot agpo(youth) polytechnic for access to quality education and training | Chepkoburot AGPO(YOUTH) polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.438436, 35.510129 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999994 | 100 | 1999994 | 0 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes.
10552 | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD | To implement chorwa ecd - design and construction of 1. no ecd classroom at chorwa ecd for access to quality education and training | Chorwa ECD - Design and Construction of 1. No ECD classroom at Chorwa ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1625 | 0.1 | 1625 | 1625 | 1198375 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
10553 | Construction and equipping of an ECD classroom at Kibara | Construction and equipping of an ECD classroom at Kibara | To construct and equip an ECD classroom at Kibara | An ECD classroom at Kibara constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.356669 35.481787 0 2099.9990234375 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1999909 | 100 | 1999909 | 91 | 91 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
10554 | Construction of an ECD classroom at Chebuiyot | Construction of an ECD classroom at Chebuiyot | To construct an ECD classroom at Chebuiyot | An ECD classroom at Chebuiyot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.376802 35.529802 2495.7 15.600000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
10555 | Construction of an ECD classroom at Kapsongop | Construction of an ECD classroom at Kapsongop | To construct an ECD classroom at Kapsongop | An ECD classroom at Kapsongop constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.385457 35.486922 0 2900 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete requires minor repair and it requres permanent pit latrine.
10556 | Githima ECD | Githima ECD | To implement githima ecd for access to quality education and training | Githima ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.302533, 35.5297 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1499913 | 1499913 | 1499913 | Equitable | N/A | 1499913 | 0 | 1499913 | 100 | 1499913 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
10557 | Korabariet ECD | Korabariet ECD | To implement korabariet ecd for access to quality education and training | Korabariet ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.377434 35.558775 0 3400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2999940 | 1883860 | 1883860 | Equitable | Equitable | 1883860 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yess. Assessor remarks: The classroom is complete but cracked.
10558 | Lemechonik ECD | Lemechonik ECD | To implement lemechonik ecd for access to quality education and training | Lemechonik ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.35001 35.567448 2687.8 8.100000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1495414 | 1495414 | 1495414 | Equitable | N/A | 1495414 | 0 | 1495414 | 100 | 1495414 | 1495414 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovations and painting of classrooms.
10559 | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD | To implement tiloa ecde - design and construction of 1. no ecd classroom at kipkewa ecd for access to quality education and training | Tiloa ECDE - Design and Construction of 1. No ECD classroom at Kipkewa ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | KIPTORORO | -0.374828 35.553043 2592.5 3.799999952316284 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 648869 | 54.1 | 648869 | 376428 | 551131 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
10560 | Baharini And Nakuru Primary ECD - Construction of I classroom Each | Baharini And Nakuru Primary ECD - Construction of I classroom Each | To implement baharini and nakuru primary ecd - construction of i classroom each for access to quality education and training | Baharini And Nakuru Primary ECD - Construction of I classroom Each completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.298432, 36.080159 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2190474 | 91.3 | 2190474 | 0 | 209526 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
10561 | Kivumbini ward ECDs - Construction of 1 No.ECD classroom at Kaloleni Primary ECD | Kivumbini ward ECDs - Construction of 1 No.ECD classroom at Kaloleni Primary ECD | To implement kivumbini ward ecds - construction of 1 no.ecd classroom at kaloleni primary ecd for access to quality education and training | Kivumbini ward ECDs - Construction of 1 No.ECD classroom at Kaloleni Primary ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.302534 36.086781 1773.199951171875 34.400001525878906 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Classroom well utilized.
10562 | Construction of ECD classroom at Baharini Primary School | Construction of ECD classroom at Baharini Primary School | To construct ECD classroom at Baharini Primary School | ECD classroom at Baharini Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.302534, 36.086781 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yed.
10563 | Construction of ECD classroom at Nakuru Primary School and equipping | Construction of ECD classroom at Nakuru Primary School and equipping | To construct ECD classroom at Nakuru Primary School and equipping | ECD classroom at Nakuru Primary School and equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.294451, 36.093247 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199994 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10564 | Refurbishment of ECD classrooms within the ward | Refurbishment of ECD classrooms within the ward | To implement refurbishment of ecd classrooms within the ward for access to quality education and training | Refurbishment of ECD classrooms within the ward completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | KIVUMBINI | -0.297797 36.080779 1790.699951171875 56.099998474121094 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997681 | 99.8 | 997681 | 0 | 2319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance required.
10565 | Lakeview ECD Classrooms Construction of 4 ECD classrooms | Lakeview ECD Classrooms Construction of 4 ECD classrooms | To implement lakeview ecd classrooms construction of 4 ecd classrooms for access to quality education and training | Lakeview ECD Classrooms Construction of 4 ECD classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKE VIEW | -0.734197, 36.435788 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10566 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lakeview primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.734177, 36.4362 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2099948 | 2099948 | 2099948 | Equitable | N/A | 2099948 | 0 | 1282392 | 61.1 | 1282392 | 0 | 817556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Chipped floor. Viable: Yes.
10567 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Manera Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.709459, 36.425593 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099890 | 100 | 2099890 | 1200000 | 110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10568 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Miliani Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.722083, 36.440268 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 906432 | 43.2 | 906432 | 1200000 | 1193568 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10569 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Unity Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Unity Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Unity Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Unity Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | LAKEVIEW | -0.733802, 36.43561 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2099900 | 1058957 | 1058957 | Equitable | Equitable | 1058957 | 0 | 906432 | 85.6 | 906432 | 1200000 | 152525 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10570 | ECD classes completion Lanet umoja | ECD classes completion Lanet umoja | To implement ecd classes completion lanet umoja for access to quality education and training | ECD classes completion Lanet umoja completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | LANET UMOJA | -0.269849, 36.163805 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 999664.8 | 999664.8 | 999664.8 | Equitable | Equitable | 999664.8 | 0 | 999665 | 100 | 999665 | 999665 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes.
10571 | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs | To implement kamoronyo primary ecdes - design and construction of 2no. ecdes classrooms at kamoronyo primary ecdes for access to quality education and training | Kamoronyo Primary ECDEs - Design and construction of 2No. ECDEs classrooms at Kamoronyo primary ECDEs completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | LANET UMOJA | -0.254878 36.160631 1938.800048828125 7.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1695002 | 339 | 1695002 | 500000 | -1195002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10572 | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic | To implement ndege ndimu polytechnic - design and construction of of ndege ndimu polytechnic for access to quality education and training | Ndege ndimu polytechnic - Design and Construction of of Ndege Ndimu polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | LANET UMOJA | -0.299253, 36.17216 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 3163654 | 57.5 | 3163654 | 32853 | 2336346 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10573 | Construction of 1 no ECD classroom at Bagaria ECD | Construction of 1 no ECD classroom at Bagaria ECD | To construct 1 no ECD classroom at Bagaria ECD | 1 no ECD classroom at Bagaria ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.392153 36.025158 2016.2 25.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198770.4 | 1198770.4 | 1198770.4 | Equitable | Equitable | 1198770.4 | 0 | 0 | 0 | 0 | 600000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not equipped.
10574 | Construction of 1 no ECD classroom at Gichobo ECD | Construction of 1 no ECD classroom at Gichobo ECD | To construct 1 no ECD classroom at Gichobo ECD | 1 no ECD classroom at Gichobo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.392153 36.025158 2016.2 25.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198770 | 1198770 | 1198770 | Equitable | Equitable | 1198770 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not equipped.
10575 | ECDs Kapyemit | ECDs Kapyemit | To implement ecds kapyemit for access to quality education and training | ECDs Kapyemit completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199755 | 1199755 | 1199755 | Equitable | N/A | 1199755 | 0 | 1127 | 0.1 | 1127 | 1127 | 1198628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10576 | Mwenyere ECD | Mwenyere ECD | To implement mwenyere ecd for access to quality education and training | Mwenyere ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.528065, 36.044693 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198372 | 99.9 | 1198372 | 1200000 | 1628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10577 | Renovation of classroom and Construction of toilets at Ndemi ECD | Renovation of classroom and Construction of toilets at Ndemi ECD | To rehabilitate classroom and Construction of toilets at Ndemi ECD to restore functionality | Classroom and Construction of toilets at Ndemi ECD rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | LARE | -0.43906, 36.022495 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1200000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10578 | Build Classes & Prov. Moi ECD | Build Classes & Prov. Moi ECD | To implement build classes & prov. moi ecd for access to quality education and training | Build Classes & Prov. Moi ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.277192, 36.067441 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2773951 | 2773951 | 2773951 | Equitable | Equitable | 2773951 | 0 | 2773951 | 100 | 2773951 | 2773951 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10579 | Milimani With Teachers Tools | Milimani With Teachers Tools | To implement milimani with teachers tools for access to quality education and training | Milimani With Teachers Tools completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.275947, 36.056465 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3558649 | 3558649 | 3558649 | Equitable | N/A | 3558649 | 0 | 2807500 | 78.9 | 2807500 | 0 | 751149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10580 | Construction of ECD classes and toilet at Moi Primary ECD | Construction of ECD classes and toilet at Moi Primary ECD | To construct ECD classes and toilet at Moi Primary ECD | ECD classes and toilet at Moi Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | LONDON | -0.277232 36.067338 1862.4909989898247 8 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | Equitable | 3000000 | 0 | 1480 | 0 | 1480 | 1763240 | 2998520 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: ..
10581 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kijabe ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kijabe ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kijabe ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kijabe ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10582 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Munengi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10583 | ECD, Namuncha primary school | ECD, Namuncha primary school | To implement ecd, namuncha primary school for access to quality education and training | ECD, Namuncha primary school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10584 | Oiti ecd | Oiti ecd | To implement oiti ecd for access to quality education and training | Oiti ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAAI MAHIU | -1.102478, 36.48795 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1195682 | 1195682 | 1195682 | Equitable | Equitable | 1195682 | 0 | 1195682 | 100 | 1195682 | 1195682 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10585 | Completion of Crater nursery school | Completion of Crater nursery school | To complete Crater nursery school | Crater nursery school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.83119 36.203515 0 156.89999389648438 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3894092 | 649 | 3894092 | 600000 | -3294092 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
10586 | Kid ilonyo nursery ECD | Kid ilonyo nursery ECD | To implement kid ilonyo nursery ecd for access to quality education and training | Kid ilonyo nursery ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.781803, 36.219695 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 2399924 | 2399924 | 2399924 | Equitable | Equitable | 2399924 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10587 | Maiella Township Nursery | Maiella Township Nursery | To implement maiella township nursery for access to quality education and training | Maiella Township Nursery completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.901682 36.201828 2295.2 12.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance f the classroom needed.
10588 | Ndabibi polytechnic | Ndabibi polytechnic | To implement ndabibi polytechnic for access to quality education and training | Ndabibi polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.892283 36.198894 2353.60009765625 10 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1335596 | 1335596 | 1335596 | Equitable | N/A | 1335596 | 0 | 996500 | 74.6 | 996500 | 1335596 | 339096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
10589 | Nkampani nursery school | Nkampani nursery school | To implement nkampani nursery school for access to quality education and training | Nkampani nursery school completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.920628 36.204578 2270.4 7.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
10590 | Construction of classrooms at Ndabibi and Kipkonyo Polytechnics | Construction of classrooms at Ndabibi and Kipkonyo Polytechnics | To construct classrooms at Ndabibi and Kipkonyo Polytechnics | Classrooms at Ndabibi and Kipkonyo Polytechnics constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | MAIELLA | -0.804803 36.246244 0 22.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 497700 | 10 | 497700 | 5000000 | 4502300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
10591 | Construction of 2 ECD classrooms at Marula primary School | Construction of 2 ECD classrooms at Marula primary School | To construct 2 ECD classrooms at Marula primary School | 2 ECD classrooms at Marula primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MALEWA WEST | -0.684685, 36.417015 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Yet to start | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1197794 | 54.4 | 1197794 | 2200000 | 1002206 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It will once complete. Viable: It will.
10592 | Construction of ECD classroom at North Karate primary and 2 toilets | Construction of ECD classroom at North Karate primary and 2 toilets | To construct ECD classroom at North Karate primary and 2 toilets | ECD classroom at North Karate primary and 2 toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MALEWA WEST | -0.684685 36.489092 0 2000 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1197794 | 79.9 | 1197794 | 302206 | 302206 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovations.
10593 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Daraja central ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.367273, 35.780127 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10594 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Ndoswa ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Ndoswa ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Ndoswa ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Ndoswa ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.353668, 35.870307 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999999 | 1999999 | 1999999 | Equitable | Equitable | 1999999 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10595 | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | Construction of ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | To construct ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE | ECD classrooms, Teachers toilet, pupils toilet and watering point at Rombei ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.336003, 35.790239 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10596 | Onoiptich ECD | Onoiptich ECD | To implement onoiptich ecd for access to quality education and training | Onoiptich ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 607822.2 | 607822.2 | 607822.2 | Equitable | Equitable | 607822.2 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10597 | Block 10 ECD - Construction of I classroom and a toilet | Block 10 ECD - Construction of I classroom and a toilet | To implement block 10 ecd - construction of i classroom and a toilet for access to quality education and training | Block 10 ECD - Construction of I classroom and a toilet completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1900000 | 1900000 | 1900000 | Equitable | Equitable | 1900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10598 | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | Construction and equipping of Tuiyobei ECD classrooms, toilets and water tank | To construct and equip Tuiyobei ECD classrooms, toilets and water tank | Tuiyobei ECD classrooms, toilets and water tank constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.349579, 35.801559 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 269520 | 13.5 | 269520 | 509920 | 1730480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10599 | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | Construction of 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | To construct 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank | 1 Kiplelmoi ECD classrooms, toilets, purchase of equipments and water tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.343994, 35.846228 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10600 | Construction of 1. Kondamet ECD classrooms, toilets and equipping and water tank | Construction of 1. Kondamet ECD classrooms, toilets and equipping and water tank | To construct 1. Kondamet ECD classrooms, toilets and equipping and water tank | 1. Kondamet ECD classrooms, toilets and equipping and water tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | -0.343994, 35.846228 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10601 | purchase of furniture, water tank and construction of toilets for Marioshoni ECDE | purchase of furniture, water tank and construction of toilets for Marioshoni ECDE | To procure furniture, water tank and construction of toilets for Marioshoni ECDE | Furniture, water tank and construction of toilets for Marioshoni ECDE procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MARIOSHONI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10602 | Construction of 2 workshops in Mathangauta Polytechnic | Construction of 2 workshops in Mathangauta Polytechnic | To construct 2 workshops in Mathangauta Polytechnic | 2 workshops in Mathangauta Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.558488, 35.978437 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | Equitable | 2400000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No, the classes were not equipped. Viable: No.
10603 | Constructon of ECD Classroom at Gacembe Primary | Constructon of ECD Classroom at Gacembe Primary | To implement constructon of ecd classroom at gacembe primary for access to quality education and training | Constructon of ECD Classroom at Gacembe Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.674452, 35.969013 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1643 | 0.1 | 1643 | 1643 | 1198357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10604 | Constructon of ECD Classroom at IKinu Primary | Constructon of ECD Classroom at IKinu Primary | To implement constructon of ecd classroom at ikinu primary for access to quality education and training | Constructon of ECD Classroom at IKinu Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.626036, 36.026932 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199920 | 100 | 1199920 | 1643 | 80 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
10605 | Constructon of ECD Classroom at Kianjoya Primary | Constructon of ECD Classroom at Kianjoya Primary | To implement constructon of ecd classroom at kianjoya primary for access to quality education and training | Constructon of ECD Classroom at Kianjoya Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -1.2841 36.8155 0 83800 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198408 | 99.9 | 1198408 | 1643 | 1592 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
10606 | Constructon of ECD Classroom at Makutano Primary | Constructon of ECD Classroom at Makutano Primary | To implement constructon of ecd classroom at makutano primary for access to quality education and training | Constructon of ECD Classroom at Makutano Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -1.2841, 36.8155 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198555 | 99.9 | 1198555 | 1643 | 1445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: VIABLE.
10607 | Constructon of ECD Classroom at Utalii Primary | Constructon of ECD Classroom at Utalii Primary | To implement constructon of ecd classroom at utalii primary for access to quality education and training | Constructon of ECD Classroom at Utalii Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU NAROK | -0.597762, 35.99593 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198407 | 99.9 | 1198407 | 1643 | 1593 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable.
10608 | Bondeni ECD - Design and construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point | Bondeni ECD - Design and construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point | To implement bondeni ecd - design and construction of 1. no ecd classrooms, teachers toilet, pupils toilet and watering point for access to quality education and training | Bondeni ECD - Design and construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1499490 | 149.9 | 1499490 | 0 | -499490 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10609 | Construction of 2.no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Mau Narok ECDE | Construction of 2.no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Mau Narok ECDE | To construct 2.no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Mau Narok ECDE | 2.no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Mau Narok ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | -1.2841, 36.8155 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2398978.6 | 2398978.6 | 2398978.6 | Equitable | Equitable | 2398978.6 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable.
10610 | Mahiga ECD - design and Construction of 1 ECDE classroom | Mahiga ECD - design and Construction of 1 ECDE classroom | To implement mahiga ecd - design and construction of 1 ecde classroom for access to quality education and training | Mahiga ECD - design and Construction of 1 ECDE classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | -0.506468, 36.054437 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 19/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499490 | 100 | 1499490 | 1500000 | 510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10611 | Maji mingi ECD | Maji mingi ECD | To implement maji mingi ecd for access to quality education and training | Maji mingi ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 0 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: stalled and readvertised.
10612 | Mathangauta polytechnic | Mathangauta polytechnic | To implement mathangauta polytechnic for access to quality education and training | Mathangauta polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2893648 | 2893648 | 2893648 | Equitable | Equitable | 2893648 | 0 | 0 | 0 | 0 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10613 | Ngwataniro ECD | Ngwataniro ECD | To implement ngwataniro ecd for access to quality education and training | Ngwataniro ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAU-NAROK | -1.2841, 36.8155 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2020/21 | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | Stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes.
10614 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chebitet ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 70 | 0 | 70 | 70 | 1199930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
10615 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chelalach ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.558049, 36.031574 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1180000 | 98.3 | 1180000 | 567777 | 20000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
10616 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Chemaluk ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.49448 35.97722 2413 13.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 567199 | 47.3 | 567199 | 567777 | 632801 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: No water tank & toilet for pupils & teachers & watering point needed.
10617 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Kamungei ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.527288 35.981027 2478.8999999999996 15.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 4221 | 0.4 | 4221 | 4221 | 1195779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Good.
10618 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Siryat ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Siryat ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Siryat ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Siryat ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.512097, 35.95945 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2018 | 1199231 | 1199231 | 1199231 | Equitable | Equitable | 1199231 | 0 | 70 | 0 | 70 | 70 | 1199161 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
10619 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Taita ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Taita ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Taita ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Taita ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.512097, 35.95945 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2018 | 1199231 | 1199231 | 1199231 | Equitable | Equitable | 1199231 | 0 | 70 | 0 | 70 | 70 | 1199161 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
10620 | Kapkembu ECDE - Design and Construction of 1 No ECD classroom, | Kapkembu ECDE - Design and Construction of 1 No ECD classroom, | To implement kapkembu ecde - design and construction of 1 no ecd classroom, for access to quality education and training | Kapkembu ECDE - Design and Construction of 1 No ECD classroom, completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.481287, 35.963452 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2020 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 5542 | 0.5 | 5542 | 5542 | 1194458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
10621 | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE | To implement koilonget ecde - design and construction of 1 no ecd classroom - koilonget ecde for access to quality education and training | Koilonget ECDE - Design and Construction of 1 No ECD classroom - Koilonget ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.481008 35.963225 2456.5 10 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 5542 | 0.5 | 5542 | 5542 | 1194458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
10622 | Sigor ECDE | Sigor ECDE | To implement sigor ecde for access to quality education and training | Sigor ECDE completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | MAUCHE | -0.547055 36.008958 2457 12.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: A fresh construction.
10623 | Construction of 1.No classroom at St Johns Primary ECD | Construction of 1.No classroom at St Johns Primary ECD | To construct 1.No classroom at St Johns Primary ECD | 1.No classroom at St Johns Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | MENENGAI | -0.266241, 36.100621 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499981 | 100 | 3499981 | 1700000 | 19 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Leskar enterprises limited.
10624 | Construction of 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | Construction of 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | To construct 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD | 1. No ECD classroom, Teachers toilet, pupils toilet and watering point at Maciaro ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 1144900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10625 | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | To construct 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD | 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiamungei ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399880 | 100 | 2399880 | 1144900 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10626 | Construction of 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | Construction of 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | To construct 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD | 3. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Menengai Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399500.6 | 2399500.6 | 2399500.6 | Equitable | N/A | 2399500.6 | 0 | 2399500 | 100 | 2399500 | 1144900 | 0.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10627 | Kiamunyi High School 3 ECD | Kiamunyi High School 3 ECD | To implement kiamunyi high school 3 ecd for access to quality education and training | Kiamunyi High School 3 ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.2466 36.013657 2010.9 9.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1329170.8 | 1329170.8 | 1329170.8 | Equitable | N/A | 1329170.8 | 0 | 0 | 0 | 0 | 1329171 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10628 | Menengai polytechnic | Menengai polytechnic | To implement menengai polytechnic for access to quality education and training | Menengai polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.168667 36.000048 1898 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1987858.4 | 1987858.4 | 1987858.4 | Equitable | N/A | 1987858.4 | 0 | 1797768 | 90.4 | 1797768 | 1987858 | 190090.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
10629 | Olrongai polytechnic - Design and Construction of an administration block and equipping | Olrongai polytechnic - Design and Construction of an administration block and equipping | To implement olrongai polytechnic - design and construction of an administration block and equipping for access to quality education and training | Olrongai polytechnic - Design and Construction of an administration block and equipping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.168873, 36.000358 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2453665 | 98.1 | 2453665 | 46335 | 46335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10630 | Construction of 2 classrooms at Kichwa ECD and a water tank | Construction of 2 classrooms at Kichwa ECD and a water tank | To construct 2 classrooms at Kichwa ECD and a water tank | 2 classrooms at Kichwa ECD and a water tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MENENGAI WEST | -0.122357, 36.008043 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019/20 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399998 | 100 | 2399998 | 999844 | 2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s mburu.
10631 | construction of Kapcholola ECD Centre & toilet | construction of Kapcholola ECD Centre & toilet | To construct Kapcholola ECD Centre & toilet | Kapcholola ECD Centre & toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MOLO CENTRAL | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1195000 | 1195000 | 1195000 | Equitable | N/A | 1195000 | 0 | 19900008 | 1665.3 | 19900008 | 3566331 | -18705008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10632 | Sachangwan ECD | Sachangwan ECD | To implement sachangwan ecd for access to quality education and training | Sachangwan ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | MOLO CENTRAL | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10633 | construction and equipping of 1 Muthiga ECDE Classroom | construction and equipping of 1 Muthiga ECDE Classroom | To construct and equip 1 Muthiga ECDE Classroom | 1 Muthiga ECDE Classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.279457 35.88394 2110.2 6.099999904632568 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/29 | 2018/29 | 0 | 0 | 1400000 | Equitable | N/A | 1400000 | 0 | 1198000 | 0 | 1198000 | 1400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
10634 | Construction of 1. No ECD classrooms and toilets at EX Margret ECD | Construction of 1. No ECD classrooms and toilets at EX Margret ECD | To construct 1. No ECD classrooms and toilets at EX Margret ECD | 1. No ECD classrooms and toilets at EX Margret ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.266003 35.881008 2093.4 16.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1300000 | 1300000 | 1300000 | Equitable | Equitable | 1300000 | 0 | 2099576 | 161.5 | 2099576 | 3000000 | -799576 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
10635 | Construction of 1. No ECD classrooms and watering point at San Mariko ECD | Construction of 1. No ECD classrooms and watering point at San Mariko ECD | To construct 1. No ECD classrooms and watering point at San Mariko ECD | 1. No ECD classrooms and watering point at San Mariko ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.266003 35.881008 2093.4 16.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1100000 | 1100000 | 1100000 | Equitable | Equitable | 1100000 | 0 | 2099576 | 190.9 | 2099576 | 2911820 | -999576 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
10636 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kirobon Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.291287 35.98659 2132.2999999999997 16.799999237060547 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099576 | 100 | 2099576 | 464606 | 424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
10637 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngondu ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.266003 35.881008 2093.4 16.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2099576 | 100 | 2099576 | 464606 | 424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Poor workmanship.
10638 | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Boror ECD | Construction of 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Boror ECD | To construct 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Boror ECD | 2. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Boror ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.229995, 35.843322 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 2098050.24 | 2098050.24 | 2098050.24 | Equitable | Equitable | 2098050.24 | 0 | 2099576 | 100.1 | 2099576 | 464606 | -1525.76 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
10639 | Design and Construction of 3 No classrooms at Ogilgei polytechnic | Design and Construction of 3 No classrooms at Ogilgei polytechnic | To design and construct 3 No classrooms at Ogilgei polytechnic | 3 No classrooms at Ogilgei polytechnic designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.211275 35.852425 1887.3999999999999 15.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 968873 | 968873 | Equitable | N/A | 968873 | 0 | 1499996 | 154.8 | 1499996 | 968873 | -531123 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Stalled.
10640 | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point | To implement ngata primary ecd - design and construction of 1 no. classroom, pupils toilet and water point for access to quality education and training | Ngata primary ECD - Design and construction of 1 No. classroom, pupils toilet and water point completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.24922 35.83006 2174.3999999999996 7 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2100000 | 2100000 | 2100000 | Equitable | Equitable | 2100000 | 0 | 464606 | 22.1 | 464606 | 464606 | 1635394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Chapakaz. Assessor remarks: Good work.
10641 | San Marco ECD | San Marco ECD | To implement san marco ecd for access to quality education and training | San Marco ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.3179 35.967392 2041.9999999999998 18.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1379950.44 | 1379950.44 | 1379950.44 | Equitable | N/A | 1379950.44 | 0 | 498974 | 36.2 | 498974 | 498974 | 880976.44 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good workmanship.
10642 | Renovation of Kerma primary ECD toilets | Renovation of Kerma primary ECD toilets | To rehabilitate Kerma primary ECD toilets to restore functionality | Kerma primary ECD toilets rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | MOSOP | -0.3179 35.967392 2041.9999999999998 18.899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497999 | 99.6 | 497999 | 600000 | 2001 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good workmanship.
10643 | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | Construction of 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | To construct 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD | 1 No. ECD classroom, Teachers toilet, pupils toilet and watering point at Chemichemi primary school ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MURINDAT | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10644 | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms | To implement nganoini ecde classroom - design and construction of nganoini 2 classrooms for access to quality education and training | Nganoini ECDE classroom - design and construction of Nganoini 2 classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MURINDAT | -0.410535, 36.358684 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1194649 | 59.7 | 1194649 | 805351 | 805351 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partly. Viable: Yes. Contractor: Murmur sobs and fabricators.
10645 | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom | To implement wanguhu ecde classroom - design and construction of wanguhu ecde 1 classroom for access to quality education and training | Wanguhu ECDE classroom - design and construction of Wanguhu ECDE 1 classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MURINDAT | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1210000 | 80.7 | 1210000 | 290000 | 290000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10646 | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | Construction of 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | To construct 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD | 2 ECD classroom and purchase of tank at Kigogo ECD and Shoka ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | GILGIL | MURINDAT | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 112 | 0 | 112 | 112 | 2399888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10647 | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | To construct 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD | 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Ihindu Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.841832, 36.557322 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199939 | 100 | 1199939 | 0 | 61 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10648 | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | To construct 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD | 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Kinungi Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.801348, 36.532968 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2018-19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199766 | 100 | 1199766 | 0 | 234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10649 | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Sisioni Primary ECD | Construction of 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Sisioni Primary ECD | To construct 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Sisioni Primary ECD | 1.No ECD classroom, teachers and pupils toilet, equipping and watering point at Sisioni Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.861896, 36.540491 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | Equitable | 1199950 | 0 | 1199939 | 100 | 1199939 | 0 | 11 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10650 | Construction of Mwega Polytechnic | Construction of Mwega Polytechnic | To construct Mwega Polytechnic | Mwega Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.846847 36.508492 2379 6.66 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 936 | 0 | 936 | 936 | 2999064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not devolve function.
10651 | construction and equipping of Mwega polytechnic | construction and equipping of Mwega polytechnic | To construct and equip Mwega polytechnic | Mwega polytechnic constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.826406 36.536507 2471.60009765625 5.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999064 | 100 | 2999064 | 3000000 | 936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
10652 | Construction of ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | Construction of ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | To construct ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs | ECD classrooms and toilet blocks at Gacuga, Kayole, Kiambogo and Kinungi ECDs constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.868073 36.520145 2307.2000000000003 4.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 3600022 | 75 | 3600022 | 359377 | 1199978 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Ecd was constructed but later coneveeted to be a dispensary which non fuctional.
10653 | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary | To implement naivasha east ward ecds - design and construction of 2 no ecd classroom, at nyakairu and mweega primary for access to quality education and training | Naivasha east ward ECDs - Design and Construction of 2 No ECD classroom, at Nyakairu and mweega primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.782198, 36.533643 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | Not done | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 4260 | 0.2 | 4260 | 4260 | 2395740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
10654 | Sindano ECD - Design and Construction and equiping of 1. No ECD classroom | Sindano ECD - Design and Construction and equiping of 1. No ECD classroom | To implement sindano ecd - design and construction and equiping of 1. no ecd classroom for access to quality education and training | Sindano ECD - Design and Construction and equiping of 1. No ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | NAIVASHA EAST | -0.826406 36.536507 2471.60009765625 5.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1800000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 4260 | 0.2 | 4260 | 1473625 | 1795740 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
10655 | Construction of 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | Construction of 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | To construct 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools | 5 No. ECD classrooms at Lion Hill Primary, Madaraka Primary, Nairobi Road primary School, Rhino Primary and Mburu Gichua Primary Schools constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU EAST | NAKURU EAST | -0.301508, 36.127579 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5998775 | 100 | 5998775 | 284968 | 1225 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakes constrution Dakuki comstruction,Durhas construction.
10656 | Construction Of ECDEs:-Tagitech Primary School | Construction Of ECDEs:-Tagitech Primary School | To construct ECDEs:-Tagitech Primary School | ECDEs:-Tagitech Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.433359 35.91906 2583.1005859375 4.107999801635742 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1194730 | 1194730 | 1194730 | Equitable | N/A | 1194730 | 0 | 1194730 | 100 | 1194730 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs repairs and repainting. Furniture for pupils is also required. Due to the huge population of pupils in ECDEs ,they were relocated to use temporary classrooms..
10657 | Nginye ECD | Nginye ECD | To implement nginye ecd for access to quality education and training | Nginye ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.401883 35.907934 2429.297805547889 4.23799991607666 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
10658 | Tiritagoi ECD - Construction of 1 classroom | Tiritagoi ECD - Construction of 1 classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction of 1 classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.417516 35.906162 2476.5755676023055 30 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
10659 | design and construction of Kipgogo ECDE classroom | design and construction of Kipgogo ECDE classroom | To design and construct Kipgogo ECDE classroom | Kipgogo ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.410761 35.899338 2463.547607421875 10.36299991607666 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 569 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
10660 | design and construction of Korovio ECDE classroom | design and construction of Korovio ECDE classroom | To design and construct Korovio ECDE classroom | Korovio ECDE classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.410761 35.899338 2463.547607421875 10.36299991607666 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
10661 | design and construction of Masaita ECDE classroom and Toilets | design and construction of Masaita ECDE classroom and Toilets | To design and construct Masaita ECDE classroom and Toilets | Masaita ECDE classroom and Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
10662 | design and construction of Missipei ECDE classroom and Toilets | design and construction of Missipei ECDE classroom and Toilets | To design and construct Missipei ECDE classroom and Toilets | Missipei ECDE classroom and Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NESSUIT | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 1105445 | 569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
10663 | ECD Tengecha | ECD Tengecha | To implement ecd tengecha for access to quality education and training | ECD Tengecha completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.369383 35.901138 1512.2 77.69999694824219 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799960.4 | 1799960.4 | 1799960.4 | Equitable | N/A | 1799960.4 | 0 | 0 | 0 | 0 | 1799960 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: working well.
10664 | Njokerio ECD - Construction of Toilet and equiping | Njokerio ECD - Construction of Toilet and equiping | To implement njokerio ecd - construction of toilet and equiping for access to quality education and training | Njokerio ECD - Construction of Toilet and equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.384924, 35.935535 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 110660 | 6.1 | 110660 | 110660 | 1689340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
10665 | Utafiti ECD - design and Construction of 1 ECDE classroom | Utafiti ECD - design and Construction of 1 ECDE classroom | To implement utafiti ecd - design and construction of 1 ecde classroom for access to quality education and training | Utafiti ECD - design and Construction of 1 ECDE classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NJORO | NJORO | -0.338641 35.945581 2148.10009765625 82.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Floor worn out.
10666 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point Matiku ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.395862, 35.616267 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2023-2024 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199970 | 100 | 1199970 | 800002 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10667 | Langwenda youth polytechnic | Langwenda youth polytechnic | To implement langwenda youth polytechnic for access to quality education and training | Langwenda youth polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.38905, 35.653547 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | - | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 689140 | 34.5 | 689140 | 800200 | 1310860 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: If at all it was realized. Viable: Yes.
10668 | Mawingu youth polytechnic | Mawingu youth polytechnic | To implement mawingu youth polytechnic for access to quality education and training | Mawingu youth polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.30101, 35.590975 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 689140 | 34.5 | 689140 | 800200 | 1310860 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
10669 | Mworoto youth polytechnic | Mworoto youth polytechnic | To implement mworoto youth polytechnic for access to quality education and training | Mworoto youth polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 689140 | 34.5 | 689140 | 1374262 | 1310860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10670 | Tachasis ECD | Tachasis ECD | To implement tachasis ecd for access to quality education and training | Tachasis ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.364898, 35.697293 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015-2016 | 2170000 | 2170000 | 2170000 | Equitable | Equitable | 2170000 | 0 | 2172100 | 100.1 | 2172100 | 2172100 | -2100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S NEO TECHNICS LIMITED.
10671 | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita | To implement nyota ward ecds - design and construction of 1.no ecd classrooms, teachers toilet, pupils toilet and watering point at chemorut, mawingu, masasita for access to quality education and training | Nyota ward ECDs - Design and construction of 1.No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chemorut, Mawingu, Masasita completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | NYOTA | -0.3756, 35.726818 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018-2019 | 4800000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 1199999 | 37.5 | 1199999 | 800002 | 2000001 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S WESJOY GENERAL SUPPLIES..
10672 | Construction of laboratory and equipping of St. Padua Girls school | Construction of laboratory and equipping of St. Padua Girls school | To construct laboratory and equipping of St. Padua Girls school | Laboratory and equipping of St. Padua Girls school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.936641 36.369939 1908.19287109375 13.87600040435791 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Equitable | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes.since the facility they are using is busy. Assessor remarks: The structure there was built by kengen.
10673 | Mvuke ecd | Mvuke ecd | To implement mvuke ecd for access to quality education and training | Mvuke ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197887.77 | 1197887.77 | Equitable | N/A | 1197887.77 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46127.77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
10674 | Narasha ECD | Narasha ECD | To implement narasha ecd for access to quality education and training | Narasha ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.917012, 36.266132 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1195717 | 1195717 | 1195717 | Equitable | N/A | 1195717 | 0 | 0 | 0 | 0 | 1195717 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: No since the class room is not operational because of clarks.
10675 | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary | To implement olkaria ward ecde classroom refurbishments - refurbishments of olkaria ecdes at narasha, mvuke, oserian, maua, sher primary for access to quality education and training | Olkaria ward ECDE classroom refurbishments - refurbishments of Olkaria ECDEs at Narasha, Mvuke, Oserian, Maua, Sher primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.836891 36.366302 1881.9000244140625 12.005999565124512 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 192163 | 9.6 | 192163 | 192163 | 1807837 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No not done. Assessor remarks: At sher moi not done.
10676 | Olkaria ward | Olkaria ward | To implement olkaria ward for access to quality education and training | Olkaria ward completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.832364 36.337064 1936.300048828125 6.109000205993652 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1296000 | 1296000 | 1296000 | Equitable | N/A | 1296000 | 0 | 0 | 0 | 0 | 1296000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The place needs more drainages.
10677 | Sher Moi ECD | Sher Moi ECD | To implement sher moi ecd for access to quality education and training | Sher Moi ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | -0.835686, 36.366152 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1136734 | 1136734 | 1136734 | Equitable | N/A | 1136734 | 0 | 0 | 0 | 0 | 1136734 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: It was not good.
10678 | equipping of ECDE centres | equipping of ECDE centres | To equip ECDE centres with necessary facilities and equipment | ECDE centres equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | OLKARIA | 0.833976, 36.342019 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2410640 | 80.4 | 2410640 | 0 | 589360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10679 | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Design and construction of administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | To design and construct administration block, polytechnic, and equipping of classrooms at Rhonda resource centre | Administration block, polytechnic, and equipping of classrooms at Rhonda resource centre designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | RHONDA | -0.31321, 36.069056 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 16/17 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 9139 | 0.1 | 9139 | 9139 | 6990861 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers General Supplies and Construction.
10680 | Mwariki ECD - Construction of Administration Block and Equiping | Mwariki ECD - Construction of Administration Block and Equiping | To implement mwariki ecd - construction of administration block and equiping for access to quality education and training | Mwariki ECD - Construction of Administration Block and Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | RHONDA | -0.316418, 36.06582 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 17/18 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4978558 | 99.6 | 4978558 | 1200000 | 21442 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Arlington company limited.
10681 | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | Construction of an ECD classroom, toilet and tank at Mwariki Primary ECD | To construct an ECD classroom, toilet and tank at Mwariki Primary ECD | An ECD classroom, toilet and tank at Mwariki Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | RHONDA | -0.752322, 36.527363 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996330 | 99.8 | 1996330 | 2000000 | 3670 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.
10682 | Construction of a PWD classroom at Koinange | Construction of a PWD classroom at Koinange | To construct a PWD classroom at Koinange | A PWD classroom at Koinange constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAAB | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Equitable | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10683 | Design and Construction of 1 no ECD Nakuru West ECD) | Design and Construction of 1 no ECD Nakuru West ECD) | To design and construct 1 no ECD Nakuru West ECD) | 1 no ECD Nakuru West ECD) designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAB | -0.293881, 36.054851 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199057 | 1199057 | 1199057 | Equitable | Equitable | 1199057 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10684 | Design and Construction of classrooms 1 no Mama Ngina ECD | Design and Construction of classrooms 1 no Mama Ngina ECD | To design and construct classrooms 1 no Mama Ngina ECD | Classrooms 1 no Mama Ngina ECD designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAB | -0.295114, 36.061468 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199428 | 1199428 | 1199428 | Equitable | Equitable | 1199428 | 0 | 2498895 | 208.3 | 2498895 | 746875 | -1299467 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10685 | Equipping of Shabab ECDs | Equipping of Shabab ECDs | To equip Shabab ECDs with necessary facilities and equipment | Shabab ECDs equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAKURU WEST | SHABAB | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 998680 | 998680 | 998680 | Equitable | Equitable | 998680 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10686 | Baringo ECD, | Baringo ECD, | To implement baringo ecd, for access to quality education and training | Baringo ECD, completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.289637 35.642573 2687.6 9.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199442 | 1199442 | 1199442 | Equitable | N/A | 1199442 | 0 | 407000 | 33.9 | 407000 | 73625 | 792442 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and in use, however the school needs another classroom to accommodate pp1 and pp2. The roof needs repair as its leaking, blackboard needs repainting, it also electricity, gutters and tank for water collection needed, they also require a pit latrine, seats and tables needs maintenance.
10687 | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | Completion of Upendo ECD, Kadenye ECD, and Ngenia ECD | To complete Upendo ECD, Kadenye ECD, and Ngenia ECD | Upendo ECD, Kadenye ECD, and Ngenia ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.289225 35.684677 2731.4 4.699999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 28737 | 2.4 | 28737 | 28737 | 1171263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good and in use, however the ceiling needs some repairs, one classroom doesn't have ceiling.
10688 | Construction of 1. No ECD classrooms at Set Kotes ECD | Construction of 1. No ECD classrooms at Set Kotes ECD | To construct 1. No ECD classrooms at Set Kotes ECD | 1. No ECD classrooms at Set Kotes ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.309613 35.677798 2719.7 7.699999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 539491 | 45 | 539491 | 539491 | 660509 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Classroom is in use and it is currently hosting both PP1&2. There are missing gutters and water tank is broken. The walls need repainting and some sections of the roof needs repairs to address a leaking, electrical works needs to be worked on to remove loose wires, broken window pages need to be replaced.
10689 | Construction of 2 No ECD classrooms at Ngenia school | Construction of 2 No ECD classrooms at Ngenia school | To construct 2 No ECD classrooms at Ngenia school | 2 No ECD classrooms at Ngenia school constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.289225 35.684677 2731.4 4.699999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2355675 | 1446815 | 1446815 | Equitable | Equitable | 1446815 | 0 | 539491 | 37.3 | 539491 | 539491 | 907324 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good and in use, however the ceiling needs some repairs, one classroom doesn't have ceiling.
10690 | kangawa ecde | kangawa ecde | To implement kangawa ecde for access to quality education and training | kangawa ecde completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.289637 35.642573 2687.6 9.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1196262 | 1196262 | 1196262 | Equitable | Equitable | 1196262 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and in use, however the school needs another classroom to accommodate pp1 and pp2. The roof needs repair as its leaking, blackboard needs repainting, it also electricity, gutters and tank for water collection needed, they also require a pit latrine, seats and tables needs maintenance.
10691 | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa | To implement sirikwa ward ecds - design and construction of 2 no ecd classroom, teachers toilet, pupils toilet and watering point set kotes and sirikwa for access to quality education and training | Sirikwa ward ECDs - Design and construction of 2 No ECD classroom, Teachers toilet, pupils toilet and watering point Set kotes and Sirikwa completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI NORTH | SIRIKWA | -0.257757, 35.666868 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3600000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10692 | AIC Kabarnet farm ECD | AIC Kabarnet farm ECD | To implement aic kabarnet farm ecd for access to quality education and training | AIC Kabarnet farm ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.092735 36.011073 1680.2 5.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199986 | 1199986 | 1199986 | Equitable | Equitable | 1199986 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Modern kitchen,Learners and staff toilets,Alot of repair needed Terrazo installation, Additional of water storage Tank, furnitures and out door play materials.
10693 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapsetek ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.09054, 35.873892 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499555 | 100 | 1499555 | 0 | 445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes but the school needs additional toilets for the students,the ceiling needs repair it's sinking.
10694 | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | Construction of 2 No classrooms and equpping of Majani Mingi Polytechnic | To construct 2 No classrooms and equpping of Majani Mingi Polytechnic | 2 No classrooms and equpping of Majani Mingi Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.041969 36.024345 1647 8 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999796 | 3999796 | 3999796 | Equitable | N/A | 3999796 | 0 | 2230341 | 55.8 | 2230341 | 116000 | 1769455 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Equipment transferred to Kipsyenan Polytechnic because Majani Mingi Polytechnic is hosting Athinai IDPs.
10695 | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms | To implement kipsyenan polytechnic - design and construction of 2 no. classrooms for access to quality education and training | Kipsyenan polytechnic - Design and Construction of 2 No. classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.061705 36.062868 1618.2 9.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 540 | 0 | 540 | 540 | 2399460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class needs repairs, installation Terrazo,furniture's,ECDE Toilet, Electricity installation,Purchase of outdoor equipments and painting.
10696 | Construction of End classrooms at Ruyobei, Koyumtich, | Construction of End classrooms at Ruyobei, Koyumtich, | To construct End classrooms at Ruyobei, Koyumtich, | End classrooms at Ruyobei, Koyumtich, constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOIN | -0.056816 35.963252 1604 8.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 2400000 | 2400000 | Equitable | Equitable | 2400000 | 0 | 423576 | 17.6 | 423576 | 423576 | 1976424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require an overhaul repair,including installation of terrazzo, furniture, outdoor activities. Additional modern kitchen also needed.
10697 | Chemachei ECD | Chemachei ECD | To implement chemachei ecd for access to quality education and training | Chemachei ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | -0.005736, 36.138072 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1799299.6 | 1799299.6 | 1799299.6 | Equitable | N/A | 1799299.6 | 0 | 699162 | 38.9 | 699162 | 1799300 | 1100137.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10698 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapkaturu ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | 0.099233, 36.173895 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 102253 | 5.7 | 102253 | 1800000 | 1697747 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10699 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Tuiyomoi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | 0.099233, 36.173895 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 538822 | 538822 | Equitable | N/A | 538822 | 0 | 102253 | 19 | 102253 | 436569 | 436569 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10700 | Kapndege ECD | Kapndege ECD | To implement kapndege ecd for access to quality education and training | Kapndege ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10701 | Mahinga ECD | Mahinga ECD | To implement mahinga ecd for access to quality education and training | Mahinga ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | 0.023445, 36.146794 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2022 | 1799542.8 | 1799542.8 | 1799542.8 | Equitable | N/A | 1799542.8 | 0 | 699162 | 38.9 | 699162 | 1100381 | 1100380.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10702 | Sigito ECD | Sigito ECD | To implement sigito ecd for access to quality education and training | Sigito ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | SOLAI | 0.078648 36.19437 1940.5 6 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1799229.6 | 1799229.6 | 1799229.6 | Equitable | N/A | 1799229.6 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100067.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Solo m general enterprise. Assessor remarks: Good.
10703 | Completion of stalled LATF project (Magomano Secondary School laboratory) | Completion of stalled LATF project (Magomano Secondary School laboratory) | To complete stalled LATF project (Magomano Secondary School laboratory) | Stalled LATF project (Magomano Secondary School laboratory) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.042296 36.190617 2284.5 8.199999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1505000 | 1505000 | Equitable | Equitable | 1505000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good working condition.
10704 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwarash Githaigas ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.018283 36.216618 2016.9000244140625 6.940000057220459 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1650000 | 1650000 | 1650000 | Equitable | N/A | 1650000 | 0 | 1646614 | 99.8 | 1646614 | 0 | 3386 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: The class serves learners. Contractor: Information not available. Assessor remarks: Yes..
10705 | Construction of ECD classroom and toilet at Morro Hill | Construction of ECD classroom and toilet at Morro Hill | To construct ECD classroom and toilet at Morro Hill | ECD classroom and toilet at Morro Hill constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | 0.003134, 36.229214 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 12/05/2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499984 | 100 | 1499984 | 2892 | 16 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure the class looks good.. Contractor: Information not known.
10706 | Construction of toilet and fencing at Munanda ECDE Umoja | Construction of toilet and fencing at Munanda ECDE Umoja | To construct toilet and fencing at Munanda ECDE Umoja | Toilet and fencing at Munanda ECDE Umoja constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.031217, 36.202857 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999980 | 100 | 999980 | 1500000 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
10707 | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom | To implement arash primary school-ecd - design and construction of 2 no. ecd classroom for access to quality education and training | Arash primary school-ECD - Design and Construction of 2 No. ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | SUBUKIA | -0.016571, 36.209792 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 12/02/2018 | 2400000 | 2400000 | 2400000 | Equitable | Equitable | 2400000 | 0 | 1994000 | 83.1 | 1994000 | 406000 | 406000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The project helps many learners. Contractor: Information not available.
10708 | Aon ECD | Aon ECD | To implement aon ecd for access to quality education and training | Aon ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844.4 | 1190844.4 | 1190844.4 | Equitable | N/A | 1190844.4 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10709 | Banana ECD | Banana ECD | To implement banana ecd for access to quality education and training | Banana ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10710 | Chepkosigen ecd | Chepkosigen ecd | To implement chepkosigen ecd for access to quality education and training | Chepkosigen ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.547198, 35.674974 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1195682 | 119.6 | 1195682 | 0 | -195682 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10711 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ang'urwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 296992 | 24.7 | 296992 | 296998 | 903008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10712 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Chebirwobei ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 689454 | 57.5 | 689454 | 1200000 | 510546 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10713 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Cherokiet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199220 | 99.9 | 1199220 | 1200000 | 780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10714 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kapande ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399500.6 | 2399500.6 | 2399500.6 | Equitable | N/A | 2399500.6 | 0 | 2399500 | 100 | 2399500 | 1200000 | 0.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10715 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kaprengero ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1186982 | 98.9 | 1186982 | 1200000 | 13018 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10716 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipsotet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipsotet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipsotet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kipsotet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 708583 | 59 | 708583 | 1200000 | 491417 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10717 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Lelechwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 803509 | 67 | 803509 | 803564 | 396491 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10718 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ngenda ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999950 | 1999950 | 1999950 | Equitable | N/A | 1999950 | 0 | 800000 | 40 | 800000 | 800000 | 1199950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10719 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Ng'etundo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199900 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1199900 | 100 | 1199900 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10720 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Sotiki ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.544292 35.677364 0 2400 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 708583 | 59 | 708583 | 1200000 | 491417 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
10721 | Construction of 2 No ECD classrooms at Kimomoroch | Construction of 2 No ECD classrooms at Kimomoroch | To construct 2 No ECD classrooms at Kimomoroch | 2 No ECD classrooms at Kimomoroch constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.475432 35.583279 2524.075 2.687999963760376 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1269806.15 | 1269806.15 | 1269806.15 | Equitable | N/A | 1269806.15 | 0 | 1151750 | 90.7 | 1151750 | 1269806 | 118056.15 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
10722 | Finishing of 2. No ECD classrooms at Kipleljin ECD | Finishing of 2. No ECD classrooms at Kipleljin ECD | To implement finishing of 2. no ecd classrooms at kipleljin ecd for access to quality education and training | Finishing of 2. No ECD classrooms at Kipleljin ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.509537 35.634567 2510.2 5.699999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 998516.4 | 998516.4 | 998516.4 | Equitable | N/A | 998516.4 | 0 | 1199930 | 120.2 | 1199930 | 998516 | -201413.6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
10723 | Tinet ECD | Tinet ECD | To implement tinet ecd for access to quality education and training | Tinet ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.497564 35.684194 0 1600 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1180063.3 | 1180063.3 | 1180063.3 | Equitable | N/A | 1180063.3 | 0 | 1180063 | 100 | 1180063 | 0 | 0.3 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition but leaking roof and cracked floor.
10724 | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. | To implement tinet ward ecds -constrruction of 1 ecd classroom at buchechet, cheram, kipsirat, rwaget,maluo, kapnanda,kamwaura and kapnandi. for access to quality education and training | Tinet ward ECDs -Constrruction of 1 ECD classroom at Buchechet, Cheram, Kipsirat, Rwaget,Maluo, Kapnanda,Kamwaura and Kapnandi. completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | KURESOI SOUTH | TINET | -0.513813 35.683561 2568.666 3.1989998817443848 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 8400000 | 8400000 | 8400000 | Equitable | N/A | 8400000 | 0 | 2750018 | 32.7 | 2750018 | 878968 | 5649982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
10725 | Chandera polytechnic 2 classrooms | Chandera polytechnic 2 classrooms | To implement chandera polytechnic 2 classrooms for access to quality education and training | Chandera polytechnic 2 classrooms completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.30802, 35.729738 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2399724 | 2399724 | 2399724 | Equitable | N/A | 2399724 | 0 | 2399600 | 100 | 2399600 | 0 | 124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10726 | Chandora ecd | Chandora ecd | To implement chandora ecd for access to quality education and training | Chandora ecd completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.311867, 35.731635 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199940 | 100 | 1199940 | 30 | 60 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10727 | Construction of 1 classroom at Muchorwe Polytechnic | Construction of 1 classroom at Muchorwe Polytechnic | To construct 1 classroom at Muchorwe Polytechnic | 1 classroom at Muchorwe Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.324365, 35.698888 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199997 | 100 | 1199997 | 1199997 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Was viable but the needs never met.
10728 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiharu ECD construction | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiharu ECD construction | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiharu ECD construction | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kiharu ECD construction constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.2988 35.723748 2615.9 7.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1199994 | 100 | 1199994 | 1199997 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: The classroom is good. Viable: Yes. Assessor remarks: No toilets and water point constructef.
10729 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mwangaza primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.248077 35.730962 2517.6 200 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199996.8 | 1199996.8 | 1199996.8 | Equitable | N/A | 1199996.8 | 0 | 1199994 | 100 | 1199994 | 1199997 | 2.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
10730 | Gwataniro ECD | Gwataniro ECD | To implement gwataniro ecd for access to quality education and training | Gwataniro ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.329513 35.694993 2755.300048828125 86.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199986 | 1199986 | 1199986 | Equitable | N/A | 1199986 | 0 | 1199986 | 100 | 1199986 | 30 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Very Good. Objective met: No. Viable: No. Assessor remarks: The project was drilled at someone's land. The owner of the land owns the project.
10731 | Migaa ECD | Migaa ECD | To implement migaa ecd for access to quality education and training | Migaa ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.273188 35.732858 2517.6 18 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1186662.6 | 1186662.6 | 1186662.6 | Equitable | N/A | 1186662.6 | 0 | 30 | 0 | 30 | 30 | 1186632.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is in dilapidated condition..
10732 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10733 | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | Construction of ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | To construct ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School | ECD Classrooms at Mwangaza, Chesengele and Gathigi primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.32942 35.686729 2755.300048828125 96.13099670410156 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1199994 | 50 | 1199994 | 1200006 | 1200006 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is under the Chesingele, Gathigi and Mwangaza ECDs.
10734 | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Construction of Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | To construct Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD | Toilet and tank at Ndenderu B ECD and constrcution of toilets at Ngwataniro and Ndenderu A ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.319855 35.739007 2667.3 8.600000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 1100000 | Equitable | Equitable | 1100000 | 0 | 1095771 | 99.6 | 1095771 | 4229 | 4229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been painted afresh.
10735 | Renovation of existing ECD classroom at Rafiki ECD | Renovation of existing ECD classroom at Rafiki ECD | To rehabilitate existing ECD classroom at Rafiki ECD to restore functionality | Existing ECD classroom at Rafiki ECD rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | MOLO | TURI | -0.303263 35.728955 2630.6 8.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 1199940 | 600 | 1199940 | 199960 | -999940 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
10736 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kanga ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10737 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kayanet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kayanet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kayanet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kayanet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199996 | 1199996 | 1199996 | Equitable | Equitable | 1199996 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10738 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mogoiwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199643 | 1199643 | 1199643 | Equitable | Equitable | 1199643 | 0 | 379239 | 31.6 | 379239 | 379239 | 820404 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10739 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Waka ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1114636 | 92.9 | 1114636 | 85364 | 85364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10740 | ECD - Gisumini ECD | ECD - Gisumini ECD | To implement ecd - gisumini ecd for access to quality education and training | ECD - Gisumini ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 829173 | 0 | 829173 | Equitable | Equitable | 829173 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10741 | Legetio ECD | Legetio ECD | To implement legetio ecd for access to quality education and training | Legetio ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1199162 | 1199162 | 1199162 | Equitable | N/A | 1199162 | 0 | 178052 | 14.8 | 178052 | 547290 | 1021110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
10742 | Lengenet ECD | Lengenet ECD | To implement lengenet ecd for access to quality education and training | Lengenet ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.136537, 35.896727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2016/17 | 1183447.66 | 1183447.66 | 1183447.66 | Equitable | N/A | 1183447.66 | 0 | 547290 | 46.2 | 547290 | 547290 | 636157.66 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Menengai TUMAINI 4.
10743 | Munanda tuyoitich ECDE - Construction of I classroom and Toilets | Munanda tuyoitich ECDE - Construction of I classroom and Toilets | To implement munanda tuyoitich ecde - construction of i classroom and toilets for access to quality education and training | Munanda tuyoitich ECDE - Construction of I classroom and Toilets completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1799914 | 100 | 1799914 | 600000 | 86 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10744 | Shalom ECD | Shalom ECD | To implement shalom ecd for access to quality education and training | Shalom ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1160093.96 | 1160093.96 | 1160093.96 | Equitable | N/A | 1160093.96 | 0 | 178052 | 15.3 | 178052 | 1160094 | 982041.96 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
10745 | Completion of Burgei ECD classroom | Completion of Burgei ECD classroom | To complete Burgei ECD classroom | Burgei ECD classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.17174 35.922497 1749.5 8.645999908447266 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1798100 | 449.5 | 1798100 | 600000 | -1398100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10746 | Construction of a classroom at Kipsaos ECD | Construction of a classroom at Kipsaos ECD | To construct a classroom at Kipsaos ECD | A classroom at Kipsaos ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
10747 | Construction of Thirandu ECD toilet | Construction of Thirandu ECD toilet | To construct Thirandu ECD toilet | Thirandu ECD toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.112228 35.887368 1817.7 20.799999237060547 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 399446 | 99.9 | 399446 | 600000 | 554 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10748 | central pry viwandani | central pry viwandani | To implement central pry viwandani for access to quality education and training | central pry viwandani completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.710843 36.433726 1903.699951171875 7.052999973297119 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 77 | 0 | 77 | 77 | 1199923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Standard.
10749 | Construction and equipping of 1.No ECD classroom at Kabati Highway Primary ECD | Construction and equipping of 1.No ECD classroom at Kabati Highway Primary ECD | To construct and equip 1.No ECD classroom at Kabati Highway Primary ECD | 1.No ECD classroom at Kabati Highway Primary ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.721695 36.44449 1940.699951171875 77.5999984741211 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499439 | 100 | 1499439 | 1500000 | 561 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes The project objective met. Viable: Yes. Assessor remarks: Complete.
10750 | Construction and equipping of 1.No ECD classroom at Mithuri ECD | Construction and equipping of 1.No ECD classroom at Mithuri ECD | To construct and equip 1.No ECD classroom at Mithuri ECD | 1.No ECD classroom at Mithuri ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.711251, 36.436063 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499845 | 100 | 1499845 | 1500000 | 155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
10751 | Kabati Highway Primary ECD | Kabati Highway Primary ECD | To implement kabati highway primary ecd for access to quality education and training | Kabati Highway Primary ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.720522 36.445398 1940.199951171875 100 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199922 | 100 | 1199922 | 0 | 78 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yet to start. Assessor remarks: Yet to start.
10752 | Mithuri ECD | Mithuri ECD | To implement mithuri ecd for access to quality education and training | Mithuri ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.711189, 36.436021 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
10753 | Renovation of proposed ICT hub in Viwandani ward | Renovation of proposed ICT hub in Viwandani ward | To rehabilitate proposed ICT hub in Viwandani ward to restore functionality | Proposed ICT hub in Viwandani ward rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | NAIVASHA | VIWANDANI | -0.718566 36.435168 1899.5 17.726999282836914 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 0 | 0 | 1000000 | Equitable | Equitable | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
10754 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Gatagati ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.168615 36.250903 1712.4 9 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 401975 | 33.5 | 401975 | 798025 | 798025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Teacher Toilet and Pupils Not Constructed.
10755 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kericho ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kericho ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kericho ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Kericho ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.09978 36.263945 1824.8 12 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199996 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 137 | 0 | 137 | 137 | 1199859 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
10756 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Loremeta ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 916423 | 76.4 | 916423 | 283577 | 283577 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
10757 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mihango ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mihango ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mihango ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mihango ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.09978 36.263945 1824.8 12 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 1199997.8 | 1199997.8 | Equitable | N/A | 1199997.8 | 0 | 137 | 0 | 137 | 137 | 1199860.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
10758 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Mikima ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.09978 36.263945 1824.8 12 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 137 | 0 | 137 | 137 | 1199863 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
10759 | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Olmanyatta ECD | Construction of 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Olmanyatta ECD | To construct 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Olmanyatta ECD | 1. No ECD classrooms, Teachers toilet, pupils toilet and watering point at Olmanyatta ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.098807 36.2446 1851.5 13.199999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 916423 | 76.4 | 916423 | 283577 | 283577 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
10760 | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | Construction of 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | To construct 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs | 2 classroom at Kaptarakwa Nairobi area ECDE and Kiriko ECDs constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | 0.08177, 36.226511 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2364444 | 98.5 | 2364444 | 35496 | 35556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10761 | Gitudaga ECDEs | Gitudaga ECDEs | To implement gitudaga ecdes for access to quality education and training | Gitudaga ECDEs completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | SUBUKIA | WASEGES | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1149769.96 | 1149769.96 | 1149769.96 | Equitable | N/A | 1149769.96 | 0 | 0 | 0 | 0 | 1149770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10762 | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | Construction of 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | To construct 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE | 1 no ECD classroom, teachers toilet, pupils toilet, equipping and watering point at Lelechonik ECDE constructed | 3110203 | N/A | NJORO | MAUCHE | -0.506942, 35.997022 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1200001 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1196609 | 0 | 1196609 | 70 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
10763 | Kaplamboi Ecd - Construction of a toilet and Furniture | Kaplamboi Ecd - Construction of a toilet and Furniture | To implement kaplamboi ecd - construction of a toilet and furniture for access to quality education and training | Kaplamboi Ecd - Construction of a toilet and Furniture completed | 3110299 | Construction of Buildings - Ot | KURESOI SOUTH | AMALO | -0.660928, 35.617525 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
10764 | Construction of Gituru Polytechnic | Construction of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | BIASHARA-NAIVASHA | -0.661007, 36.50238 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2020 | 16000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 8683480 | 124 | 8683480 | 21997 | -1683480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Dakuki.
10765 | Construction of 1 ECD class and toilet at Mirera Primary | Construction of 1 ECD class and toilet at Mirera Primary | To construct 1 ECD class and toilet at Mirera Primary | 1 ECD class and toilet at Mirera Primary constructed | 3110299 | Construction of Buildings - Ot | NAIVASHA | HELLS GATE | -0.78239, 36.445743 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1487282 | 99.2 | 1487282 | 1199658 | 12718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: If it was done would be more viable because the population of the school is so high.
10766 | Establishment of a Data Centre at the County HQ | Establishment of a Data Centre at the County HQ | To implement establishment of a data centre at the county hq for access to quality education and training | Establishment of a Data Centre at the County HQ completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 10000000 | 10000000 | Equitable | Equitable | 10000000 | 0 | 8735600 | 87.4 | 8735600 | 1264400 | 1264400 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10767 | Construction of Toilets at ST. John ECD | Construction of Toilets at ST. John ECD | To construct Toilets at ST. John ECD | Toilets at ST. John ECD constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.194273, 36.144206 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | June 2019 | 600000 | 600000 | 600000 | Equitable | Equitable | 600000 | 0 | 5 | 0 | 5 | 5 | 599995 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10768 | Construction of Wendo polytechnic | Construction of Wendo polytechnic | To construct Wendo polytechnic | Wendo polytechnic constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.181071, 36.180736 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2135 | 0.1 | 2135 | 2135 | 1997865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers general supplies and company.
10769 | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | construction of Mahinga ECDE toilet - construction of Mahinga ECDE toilet | To construct Mahinga ECDE toilet - construction of Mahinga ECDE toilet | Mahinga ECDE toilet - construction of Mahinga ECDE toilet constructed | 3110299 | Construction of Buildings - Ot | SUBUKIA | KABAZI | -0.12904 36.15429 0 220 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 699162 | 99.9 | 699162 | 699162 | 838 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
10770 | Construction Of 4 Door Pit Latrine For Gents At Lalwet ECD | Construction Of 4 Door Pit Latrine For Gents At Lalwet ECD | To construct 4 Door Pit Latrine For Gents At Lalwet ECD | 4 Door Pit Latrine For Gents At Lalwet ECD constructed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPKURES | -0.332602 36.02549 1955.7529296875 13.935999870300293 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 800 | 0.1 | 800 | 800 | 999200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The latrines are complete and in use.
10771 | Mogoon resource centre - Design and Construction of resource centre at Tachasis | Mogoon resource centre - Design and Construction of resource centre at Tachasis | To implement mogoon resource centre - design and construction of resource centre at tachasis for access to quality education and training | Mogoon resource centre - Design and Construction of resource centre at Tachasis completed | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPKURES | -0.309609, 36.024561 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | Equitable | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No.
10772 | Toilet block njuguini | Toilet block njuguini | To implement toilet block njuguini for access to quality education and training | Toilet block njuguini completed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.440014 35.974624 2303.300048828125 98.4000015258789 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
10773 | Construction of ECD classroom at KIO ECD Centre | Construction of ECD classroom at KIO ECD Centre | To construct ECD classroom at KIO ECD Centre | ECD classroom at KIO ECD Centre constructed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.455877 35.985462 2286.60009765625 16.200000762939453 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 219716 | 18.3 | 219716 | 600000 | 980284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
10774 | Construction of ECD classroom at Mutarakwa Primary | Construction of ECD classroom at Mutarakwa Primary | To construct ECD classroom at Mutarakwa Primary | ECD classroom at Mutarakwa Primary constructed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.476557 35.987107 2230.1 12.600000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1148599 | 95.7 | 1148599 | 51401 | 51401 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation and ECDE toilets.
10775 | Construction of ECD Toilets at Mutito ECD Centre | Construction of ECD Toilets at Mutito ECD Centre | To construct ECD Toilets at Mutito ECD Centre | ECD Toilets at Mutito ECD Centre constructed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.426452 35.9737 2257.5 14.600000381469727 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 219716 | 36.6 | 219716 | 600000 | 380284 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
10776 | Construction of ECD Toilets at Mutiume Primary | Construction of ECD Toilets at Mutiume Primary | To construct ECD Toilets at Mutiume Primary | ECD Toilets at Mutiume Primary constructed | 3110299 | Construction of Buildings - Ot | NJORO | KIHINGO | -0.440608, 35.991652 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1148599 | 191.4 | 1148599 | 600000 | -548599 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
10777 | Kuresoi centre social hall - Design and Construction of a social hall in Kuresoi centre | Kuresoi centre social hall - Design and Construction of a social hall in Kuresoi centre | To implement kuresoi centre social hall - design and construction of a social hall in kuresoi centre for access to quality education and training | Kuresoi centre social hall - Design and Construction of a social hall in Kuresoi centre completed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | KIPTORORO | -0.301375 35.532968 2561.4 7.5 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Partially. Assessor remarks: The facility requires electricity,and equipments.
10778 | Baharini Primary ECD school - Completion of a toilet block | Baharini Primary ECD school - Completion of a toilet block | To implement baharini primary ecd school - completion of a toilet block for access to quality education and training | Baharini Primary ECD school - Completion of a toilet block completed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | KIVUMBINI | -0.298431, 36.080159 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 984109 | 98.4 | 984109 | 0 | 15891 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10779 | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet | To implement chorwet primary ecde toilet construction - design and construction of chorwet primary ecde toilet for access to quality education and training | Chorwet primary ECDE toilet construction - Design and Construction of Chorwet primary ECDE toilet completed | 3110299 | Construction of Buildings - Ot | NJORO | MAUCHE | -0.527215, 35.981072 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2015 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599970 | 100 | 599970 | 0 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know.
10780 | construction of Toilet at Ol-Rongai Polytechnic | construction of Toilet at Ol-Rongai Polytechnic | To construct Toilet at Ol-Rongai Polytechnic | Toilet at Ol-Rongai Polytechnic constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.168652, 36.000173 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999240 | 99.9 | 999240 | 1000000 | 760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10781 | Completion and equipping of Molo Youth Polytechnic | Completion and equipping of Molo Youth Polytechnic | To complete and equip Molo Youth Polytechnic | Molo Youth Polytechnic completed and equipped | 3110299 | Construction of Buildings - Ot | MOLO | MOLO | -0.25195 35.736914 2459.413818359375 12.755999565124512 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 3039053 | 60.8 | 3039053 | 1960947 | 1960947 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
10782 | Construction of Kirandich ECD Centre | Construction of Kirandich ECD Centre | To construct Kirandich ECD Centre | Kirandich ECD Centre constructed | 3110299 | Construction of Buildings - Ot | MOLO | MOLO | -0.230647, 35.785055 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2018/19 | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199997 | 100 | 1199997 | 1195000 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10783 | Construction of migaa ECD centre | Construction of migaa ECD centre | To construct migaa ECD centre | Migaa ECD centre constructed | 3110299 | Construction of Buildings - Ot | MOLO | MOLO | -0.201864, 35.819985 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2017/2018 | 2000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199617 | 100 | 1199617 | 1195000 | 383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable. Contractor: Joly general merchants Ltd.
10784 | Administration Block For Molo Polytechnic | Administration Block For Molo Polytechnic | To implement administration block for molo polytechnic for access to quality education and training | Administration Block For Molo Polytechnic completed | 3110299 | Construction of Buildings - Ot | MOLO | MOLO CENTRAL | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3448808.38 | 1623270.38 | 1623270.38 | Equitable | N/A | 1623270.38 | 0 | 623800 | 38.4 | 623800 | 659133 | 999470.38 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10785 | Construction of Toilets and Fencing of Ngeteti ECD | Construction of Toilets and Fencing of Ngeteti ECD | To construct Toilets and Fencing of Ngeteti ECD | Toilets and Fencing of Ngeteti ECD constructed | 3110299 | Construction of Buildings - Ot | GILGIL | MURINDAT | -0.418758, 36.372043 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999456 | 99.9 | 999456 | 1200000 | 544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Murmur sobs and fabricators.
10786 | Construction of ECD classrooms at Kiletten | Construction of ECD classrooms at Kiletten | To construct ECD classrooms at Kiletten | ECD classrooms at Kiletten constructed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | SIRIKWA | -0.235118, 35.662517 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 402405 | 33.5 | 402405 | 402691 | 797595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10787 | Construction of ECD classrooms at Silibwet | Construction of ECD classrooms at Silibwet | To construct ECD classrooms at Silibwet | ECD classrooms at Silibwet constructed | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | SIRIKWA | -0.292835 35.62624 2714.216290890812 23 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1196609 | 99.7 | 1196609 | 3391 | 3391 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,they however need another classroom,PP2 pupils are using a temporary structure that is adjacent to kitchen as a result learners are affected by smoke. Assessor remarks: The seats and tables are broken,the floor has potholes,missing window panes,the walls need to be repainted, leaking roof and sagging ceiling board,black board is still in good condition,ECD pupils dont have their own pit latrine,.
10788 | purchase of land for Tombo / Kaptembwo ECDE | purchase of land for Tombo / Kaptembwo ECDE | To acquire land for Tombo / Kaptembwo ECDE | Land for Tombo / Kaptembwo ECDE acquired | 3110299 | Construction of Buildings - Ot | KURESOI NORTH | SIRIKWA | -0.249192 35.682062 2664.4 19.399999618530273 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No land purchased.
10789 | Construction of Staff toilet at Subukia Polytechnic | Construction of Staff toilet at Subukia Polytechnic | To construct Staff toilet at Subukia Polytechnic | Staff toilet at Subukia Polytechnic constructed | 3110299 | Construction of Buildings - Ot | SUBUKIA | SUBUKIA | 0.003135 36.229308 1992.0999755859375 23.988000869750977 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 350000 | 100 | 350000 | 2892 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the staff have been using this toilet since it was constructed.. Contractor: No information available. Assessor remarks: The toilet is still in good standing.
10790 | Naiswet ECDE -Construction of Toilets | Naiswet ECDE -Construction of Toilets | To implement naiswet ecde -construction of toilets for access to quality education and training | Naiswet ECDE -Construction of Toilets completed | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.119997 35.932339 1710.7 13.199999809265137 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599592 | 99.9 | 599592 | 600000 | 408 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10791 | Umoja ECDE - Construction of Toilets | Umoja ECDE - Construction of Toilets | To implement umoja ecde - construction of toilets for access to quality education and training | Umoja ECDE - Construction of Toilets completed | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.199048, 35.935822 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2022/23 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 593502 | 98.9 | 593502 | 600000 | 6498 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10792 | Construction of ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | Construction of ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | To construct ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations | ECDs ( I classroom each) at Orthodox, Mwangi Michuki, Ndimu,St James, Nyakiambi,Elburgon, New Creations constructed | 3110302 | Refurbishment of Non-Residential Buildings | MOLO | ELBURGON | -0.303254, 35.816855 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | - | 7200001 | 0 | 7200000 | Equitable | N/A | 7200000 | 0 | 3961667 | 0 | 3961667 | 1402494 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
10793 | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties | To implement reinforcement of county server rooms and digital centres in all sub counties for access to quality education and training | Reinforcement of County Server Rooms and Digital Centres in all Sub Counties completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2217197 | 44.3 | 2217197 | 414583 | 2782803 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10794 | Renovation of 2 ECD classrooms and installation of electricity at Mugumo Primary | Renovation of 2 ECD classrooms and installation of electricity at Mugumo Primary | To rehabilitate 2 ECD classrooms and installation of electricity at Mugumo Primary to restore functionality | 2 ECD classrooms and installation of electricity at Mugumo Primary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | NJORO | LARE | -0.446409 36.00843 2071.900146484375 12 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1199999 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
10795 | Renovation of 2 ECD classrooms and purchase of water tank for Naishi Game Primary | Renovation of 2 ECD classrooms and purchase of water tank for Naishi Game Primary | To rehabilitate 2 ECD classrooms and purchase of water tank for Naishi Game Primary to restore functionality | 2 ECD classrooms and purchase of water tank for Naishi Game Primary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | NJORO | LARE | -0.446409 36.00843 2071.900146484375 12 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1199999 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
10796 | fencing of Ol Rongai polytechnic | fencing of Ol Rongai polytechnic | To secure Ol Rongai polytechnic through fencing | Ol Rongai polytechnic fenced and secured | 3110499 | Construction of Roads - Other | RONGAI | MENENGAI WEST | -0.168667 36.000048 1898 6.900000095367432 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797768 | 99.9 | 1797768 | 3000000 | 2232 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not in existence.
10797 | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic | To implement fencing, construction of a toilet and equipping of ogilgei polytechnic for access to quality education and training | Fencing, construction of a toilet and equipping of Ogilgei Polytechnic completed | 3110504 | Other Infrastructure and Civil Works | RONGAI | MOSOP | -0.28415, 35.966517 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499996 | 100 | 1499996 | 968873 | 4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated.
10798 | Fencing of Parkview ECD field | Fencing of Parkview ECD field | To secure Parkview ECD field through fencing | Parkview ECD field fenced and secured | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | 0.353373, 36.049 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499380 | 99.9 | 499380 | 0 | 620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alfary supplies.
10799 | Construction of an ICT Resource Centre in Shabab | Construction of an ICT Resource Centre in Shabab | To construct an ICT Resource Centre in Shabab | An ICT Resource Centre in Shabab constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAAB | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | Equitable | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10800 | Installation of e-signage boards in Office of the Governor, Deputy Governor, County Secretary and 10 County Executive Committee Members | Installation of e-signage boards in Office of the Governor, Deputy Governor, County Secretary and 10 County Executive Committee Members | To install e-signage boards in Office of the Governor, Deputy Governor, County Secretary and 10 County Executive Committee Members | E-signage boards in Office of the Governor, Deputy Governor, County Secretary and 10 County Executive Committee Members installed | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10801 | Equipping of 3 No. ECD classrooms with Indoor and outdoor equipment at Barut and Kiptenden primary - Barut Ward ECDs | Equipping of 3 No. ECD classrooms with Indoor and outdoor equipment at Barut and Kiptenden primary - Barut Ward ECDs | To equip 3 No. ECD classrooms with Indoor and outdoor equipment at Barut and Kiptenden primary - Barut Ward ECDs with necessary facilities and equipment | 3 No. ECD classrooms with Indoor and outdoor equipment at Barut and Kiptenden primary - Barut Ward ECDs equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAKURU WEST | BARUT | -0.331904, 36.045261 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2024 | 900000 | 900000 | 900000 | Equitable | Equitable | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogea enter.
10802 | Installation of lightning arresters at Elementaita ECD | Installation of lightning arresters at Elementaita ECD | To install lightning arresters at Elementaita ECD | Lightning arresters at Elementaita ECD installed | 3111109 | Purchase of Educational Aids and Related Equipment | GILGIL | ELEMENTAITA | -0.616691, 36.125577 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10803 | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) | To implement puchase of sport uniforms and equipments (hells gate youth empowerment) for access to quality education and training | Puchase of sport uniforms and equipments (Hells Gate youth empowerment) completed | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | HELLS GATE | -0.778058 36.450916 1944.048828125 5.145999908447266 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999700 | 1999700 | 1999700 | Equitable | N/A | 1999700 | 0 | 1999700 | 100 | 1999700 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project cost is not indicated.
10804 | Equiping youth polytechnics | Equiping youth polytechnics | To implement equiping youth polytechnics for access to quality education and training | Equiping youth polytechnics completed | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 4123683 | 343.6 | 4123683 | 8800000 | -2923683 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10805 | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties | To implement improvement of learning environment through equipping of ecde centres in all sub counties for access to quality education and training | Improvement of learning environment through equipping of ECDE Centres in all Sub Counties completed | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 20597085 | 20597085 | 20597085 | Equitable | N/A | 20597085 | 0 | 1744000 | 8.5 | 1744000 | 1745742 | 18853085 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10806 | Equipping of Kamara polytechnic | Equipping of Kamara polytechnic | To equip Kamara polytechnic with necessary facilities and equipment | Kamara polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | KURESOI NORTH | KAMARA | -0.167952 35.675978 2630.6 10.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 987900 | 98.8 | 987900 | 1000000 | 12100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs more equipments.
10807 | equipping of ECDE classroom at Kiriri primary school | equipping of ECDE classroom at Kiriri primary school | To equip ECDE classroom at Kiriri primary school with necessary facilities and equipment | ECDE classroom at Kiriri primary school equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NJORO | LARE | -0.434022, 36.008367 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 1200000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10808 | equipping of ECDE classroom at nguriga primary school | equipping of ECDE classroom at nguriga primary school | To equip ECDE classroom at nguriga primary school with necessary facilities and equipment | ECDE classroom at nguriga primary school equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NJORO | LARE | -0.525137 36.044187 2325.000244140625 13.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 400000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water and electricity.
10809 | Equipping with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs | Equipping with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs | To equip with chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs with necessary facilities and equipment | With chairs and tables in Kipkonyo ECD,Ngunyumu ECD, DRT, Huruma, Kiburuti, Ndibithi, Tangi Tatu, Maiella township and Nkampani ECDs equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | MAIELLA | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999800 | 1999800 | 1999800 | Equitable | N/A | 1999800 | 0 | 1999800 | 100 | 1999800 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10810 | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate | To implement menengai polytechnic equipments - purchase of menengai polytechnic equipments and construction of the gate for access to quality education and training | Menengai polytechnic equipments - Purchase of Menengai polytechnic equipments and construction of the Gate completed | 3111109 | Purchase of Educational Aids and Related Equipment | RONGAI | MENENGAI WEST | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998374 | 99.9 | 1998374 | 1626 | 1626 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10811 | Molo youth Polytechnic - Equiping of Youth Polytechnic | Molo youth Polytechnic - Equiping of Youth Polytechnic | To implement molo youth polytechnic - equiping of youth polytechnic for access to quality education and training | Molo youth Polytechnic - Equiping of Youth Polytechnic completed | 3111109 | Purchase of Educational Aids and Related Equipment | MOLO | MOLO CENTRAL | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10812 | Equipping of Mbegi polytechnic | Equipping of Mbegi polytechnic | To equip Mbegi polytechnic with necessary facilities and equipment | Mbegi polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | GILGIL | MURINDAT | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2830 | 0.3 | 2830 | 2830 | 997170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10813 | Purchase of sport equipment for youths (Youth empowerment programme) | Purchase of sport equipment for youths (Youth empowerment programme) | To procure sport equipment for youths (Youth empowerment programme) | Sport equipment for youths (Youth empowerment programme) procured | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | OLKARIA | 0.830138 36.338593 1895.69951171875 27.18400001525879 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999700 | 1999700 | 1999700 | Equitable | N/A | 1999700 | 0 | 1999700 | 100 | 1999700 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
10814 | Equipping of Ruiyobei polytechnic equipment | Equipping of Ruiyobei polytechnic equipment | To equip Ruiyobei polytechnic equipment with necessary facilities and equipment | Ruiyobei polytechnic equipment equipped | 3111109 | Purchase of Educational Aids and Related Equipment | RONGAI | SOLAI | 0.045811 36.125512 1547.9873046875 17.819000244140625 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 748942 | 93.6 | 748942 | 21580 | 51058 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Non functional.
10815 | Equipping of Gakingi polytechnic | Equipping of Gakingi polytechnic | To equip Gakingi polytechnic with necessary facilities and equipment | Gakingi polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | SUBUKIA | WASEGES | 0.116708, 36.224264 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910200 | 91 | 910200 | 89800 | 89800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes.
10816 | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto | To implement establishment of wi-fi hotspots at county hq- nyayo gardens, naivasha recreational park, kuresoi south digital centres, subukia digital centre, rongai - kampi ya moto for access to quality education and training | Establishment of Wi-Fi hotspots at County HQ- Nyayo gardens, Naivasha Recreational Park, Kuresoi South Digital Centres, Subukia Digital Centre, Rongai - Kampi ya Moto completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 18750000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5747366 | 95.8 | 5747366 | 0 | 252634 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Status: Complete. Recommendation: Retain and archive.
10817 | Installation of Local Area Network (LANs) at Nakuru West Sub-County offices | Installation of Local Area Network (LANs) at Nakuru West Sub-County offices | To install Local Area Network (LANs) at Nakuru West Sub-County offices | Local Area Network (LANs) at Nakuru West Sub-County offices installed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.113577, 35.796542 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2022/2023 | 15000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not meet the need. Contractor: Rynix construction limited.
10818 | Software development - Email solution, Bursary and feeding programme management software | Software development - Email solution, Bursary and feeding programme management software | To implement software development - email solution, bursary and feeding programme management software for access to quality education and training | Software development - Email solution, Bursary and feeding programme management software completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 884500 | 8.8 | 884500 | 723403 | 9115500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10819 | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall | To implement wide area network (wan) connectivity at county hq, regional coordinator's complex, all sub-counties, department of infrastructure department of lands, housing & physical planning, subukia digital centre, kuresoi south digital centre, old town hall for access to quality education and training | Wide Area Network (WAN) Connectivity at County HQ, Regional Coordinator's Complex, All Sub-counties, Department of Infrastructure Department of Lands, Housing & Physical Planning, Subukia Digital Centre, Kuresoi South Digital Centre, Old Town Hall completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 65000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5983283 | 99.7 | 5983283 | 0 | 16717 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10820 | Construction of the administration block and Toilets at Kaplamai Polytechnic | Construction of the administration block and Toilets at Kaplamai Polytechnic | To construct the administration block and Toilets at Kaplamai Polytechnic | The administration block and Toilets at Kaplamai Polytechnic constructed | 3111504 | N/A | KURESOI SOUTH | AMALO | -0.658488, 35.639393 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996557 | 99.8 | 1996557 | 2000000 | 3443 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
10821 | construction of Toilet and fencing at Pangani ECD | construction of Toilet and fencing at Pangani ECD | To construct Toilet and fencing at Pangani ECD | Toilet and fencing at Pangani ECD constructed | 3111504 | N/A | KURESOI SOUTH | AMALO | -0.589148, 35.674193 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 499500 | 99.9 | 499500 | 500000 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
10822 | Construction of septic tank for Barut Primary school for disabled toilet | Construction of septic tank for Barut Primary school for disabled toilet | To construct septic tank for Barut Primary school for disabled toilet | Septic tank for Barut Primary school for disabled toilet constructed | 3111504 | N/A | NAKURU WEST | BARUT | -0.3255565, 36.054039 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PIRAKIL COMPANY LIMITED.
10823 | Construction of ECD Administration block at Racetrack Primary School ECD | Construction of ECD Administration block at Racetrack Primary School ECD | To construct ECD Administration block at Racetrack Primary School ECD | ECD Administration block at Racetrack Primary School ECD constructed | 3111504 | N/A | NAKURU EAST | FLAMINGO | -0.309876, 36.070075 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | Fy2016/17 | 2999417.8 | 2999417.8 | 2999417.8 | Equitable | Equitable | 2999417.8 | 0 | 3449870 | 115 | 3449870 | 1068473 | -450452.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10824 | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate | To implement lakeview ecde center - construction of a perimetre wall and gate for access to quality education and training | Lakeview ECDE Center - Construction of a Perimetre Wall and Gate completed | 3111504 | N/A | NAKURU EAST | FLAMINGO | -0.30524, 36.078817 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | fy2017/18 | 5000000 | 3300000 | 3300000 | Equitable | N/A | 3300000 | 0 | 135987 | 4.1 | 135987 | 135987 | 3164013 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Peshmac Enteprises.
10825 | Digital Centres internet setup | Digital Centres internet setup | To implement digital centres internet setup for access to quality education and training | Digital Centres internet setup completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4672484 | 233.6 | 4672484 | 4942144 | -2672484 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10826 | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | Construction of perimeter wall, gate and toilet at Ndege Polytechnic | To construct perimeter wall, gate and toilet at Ndege Polytechnic | Perimeter wall, gate and toilet at Ndege Polytechnic constructed | 3111504 | N/A | BAHATI | LANET UMOJA | -0.302095, 36.172122 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998040 | 99.9 | 1998040 | 2000000 | 1960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10827 | Chepseon ecd - Renovations and toilets | Chepseon ecd - Renovations and toilets | To implement chepseon ecd - renovations and toilets for access to quality education and training | Chepseon ecd - Renovations and toilets completed | 3111504 | N/A | RONGAI | MOSOP | -0.265783 35.881283 2093.3 12.800000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 497999 | 35.6 | 497999 | 1400000 | 902001 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
10828 | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Construction of Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | To construct Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic | Toilets, fencing, connecting electricity and purchase of equipments at Sitoito polytechnic constructed | 3111504 | N/A | KURESOI NORTH | NYOTA | -0.38946, 35.568755 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
10829 | Construction of kitchen and fencing of Kware polytechnic | Construction of kitchen and fencing of Kware polytechnic | To construct kitchen and fencing of Kware polytechnic | Kitchen and fencing of Kware polytechnic constructed | 3111504 | N/A | RONGAI | VISOI | -0.123667 35.824817 1897.9 9.300000190734863 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 970000 | 48.5 | 970000 | 30000 | 1030000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: Not achieved. Viable: Yes. Assessor remarks: Poor.
10830 | Purchase of 1acre Land for Kimugul ECDE | Purchase of 1acre Land for Kimugul ECDE | To procure 1acre Land for Kimugul ECDE | 1acre Land for Kimugul ECDE procured | 3130101 | Acquisition of Land | KURESOI SOUTH | AMALO | -0.640943, 35.623492 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 75 | N/A | STALLED. TO BE SUPPLEMENTED | 2018 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10831 | Rironi ecd LAND | Rironi ecd LAND | To implement rironi ecd land for access to quality education and training | Rironi ecd LAND completed | 3130101 | Acquisition of Land | KURESOI NORTH | KAMARA | -0.176747 35.712237 2487.6 3.799999952316284 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Land not purchased.
10832 | Lalwet ECD land | Lalwet ECD land | To implement lalwet ecd land for access to quality education and training | Lalwet ECD land completed | 3130101 | Acquisition of Land | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving as school. Assessor remarks: About 1and quarter acreLand purchased and serving.
10833 | Purchase of land for construction of a Polytechnic in Ingobor | Purchase of land for construction of a Polytechnic in Ingobor | To acquire land for construction of a Polytechnic in Ingobor | Land for construction of a Polytechnic in Ingobor acquired | 3130101 | Acquisition of Land | NAKURU WEST | KAPKURES | -0.324324 36.018595 0 2591.7880859375 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but has not been developed. Assessor remarks: Land was bought. Has not been developed.
10834 | Purchase of land for public utility - Resource Centre - at sewage village (additional) | Purchase of land for public utility - Resource Centre - at sewage village (additional) | To acquire land for public utility - Resource Centre - at sewage village (additional) | Land for public utility - Resource Centre - at sewage village (additional) acquired | 3130101 | Acquisition of Land | NAKURU WEST | KAPTEMBWO | -0.317729, 36.052932 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it met the needs of the residents. Contractor: U97.
10835 | Purchase of land for construction of an ECD and Baby Care Centre at Kihoto | Purchase of land for construction of an ECD and Baby Care Centre at Kihoto | To acquire land for construction of an ECD and Baby Care Centre at Kihoto | Land for construction of an ECD and Baby Care Centre at Kihoto acquired | 3130101 | Acquisition of Land | NAIVASHA | LAKE VIEW | -0.73409, 36.436208 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Equitable | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
10836 | purchase of land for construction of sosiot ECDE | purchase of land for construction of sosiot ECDE | To acquire land for construction of sosiot ECDE | Land for construction of sosiot ECDE acquired | 3130101 | Acquisition of Land | NJORO | NJORO | -0.32681 35.940695 2151.900146484375 5.441999912261963 | VOTE NO. D08 | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | MINISTRY OF EDUCATION, VOCATIONAL TRAINING, ICT & E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2492710 | 2492710 | 2492710 | Equitable | N/A | 2492710 | 0 | 1197000 | 48 | 1197000 | 2492710 | 1295710 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Samues merchants. Assessor remarks: In good state.
10837 | Crop Development and Management | Emergency Response for Pests and Diseases | To implement emergency response for pests and diseases for agricultural development and food production | Emergency Response for Pests and Diseases completed | 2211004 | Fungicides, Insecticides and Sprays | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10838 | Livestock Resource Management and Development | Purchase of vaccines | To procure vaccines | Vaccines procured | 2211026 | Purchase of Vaccines and Sera | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 50416356 | 60416356 | 60416356 | Equitable | N/A | 60416356 | 0 | 59499996 | 98.5 | 59499996 | 0 | 916360 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10839 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 2640499 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 6000000 | Equitable | EQUITABLE | 6000000 | 0 | 1500000 | 30 | 1500000 | 4500000 | 3500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10840 | Crop Development and Management | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640499 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 5000000 | 6500000 | Equitable | Equitable | 6500000 | 0 | 6500000 | 130 | 6500000 | 3910461 | -1500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10841 | Crop Development and Management | Agricultural Sector Development Support Projects (ASDSP) | To implement agricultural sector development support projects (asdsp) for agricultural development and food production | Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 0 | 0 | 0 | ASDSP II | ASDSP II | 0 | 21983635 | 197358 | 0 | 197358 | 696453 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10842 | Crop Development and Management | National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 140435163 | 140435163 | 0 | NARIGP | NARIGP | 0 | 140435163 | 351365 | 0.3 | 351365 | 3910461 | 140083798 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10843 | Crop Development and Management | World Bank Loan for National Agriculture & Rural inclusive Growth project | To implement development programme activities under World Bank Loan for National Agriculture & Rural inclusive Growth project | Programme activities completed | 2640503 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 50000000 | 22333550 | 0 | Grant | Grant | 0 | 22333550 | 22333550 | 100 | 22333550 | 3910461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10844 | Fisheries Development | ATC (8 km) Farm perimeter / concrete pillar posts / chain link | To implement atc (8 km) farm perimeter / concrete pillar posts / chain link for agricultural development and food production | ATC (8 km) Farm perimeter / concrete pillar posts / chain link completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10845 | Fisheries Development | Completion of Fish builking, preservation and processing centre at Naivasha | To complete Fish builking, preservation and processing centre at Naivasha | Fish builking, preservation and processing centre at Naivasha completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5316542 | 5316542 | 5316542 | Equitable | N/A | 5316542 | 0 | 5289728 | 99.5 | 5289728 | 0 | 26814 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10846 | Fisheries Development | Construction and equipping honey processing facility (Mau Narok) | To construct and equip honey processing facility (Mau Narok) | Honey processing facility (Mau Narok) constructed and equipped | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 4416356 | 4416356 | 4416356 | Equitable | N/A | 4416356 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10847 | Administration, Planning and Support Services | Construction of Data collection shades at fish landing beaches.. | To construct Data collection shades at fish landing beaches | Data collection shades at fish landing beaches constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 0 | 0 | 0 | 999800 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
10848 | Fisheries Development | Fencing of Gilgil and Tinet wards Slaughter House | To secure Gilgil and Tinet wards Slaughter House through fencing | Gilgil and Tinet wards Slaughter House fenced and secured | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10849 | Fisheries Development | Potato Stores in Kuresoi South and Njoro | To implement potato stores in kuresoi south and njoro for agricultural development and food production | Potato Stores in Kuresoi South and Njoro completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10850 | Crop Development and Management | Rehabilitation of KMC SLAUGHTER House in Nakuru East | To rehabilitate KMC SLAUGHTER House in Nakuru East to restore functionality | KMC SLAUGHTER House in Nakuru East rehabilitated | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2980492 | 0 | 2980492 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10851 | Crop Development and Management | Renovation of slaughterhouse at Nguriga | To rehabilitate slaughterhouse at Nguriga to restore functionality | Slaughterhouse at Nguriga rehabilitated | 3110299 | Construction of Buildings - Ot | NJORO | LARE | -0.446195, 36.013001 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Promax General Supplies. Assessor remarks: No renovation yet and not operational and the area need to be secured with a concrete fence.
10852 | Crop Development and Management | Construction and completion of Milk cooler plant | To construct and completion of Milk cooler plant | And completion of Milk cooler plant constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.168207 35.999097 1886.9 728.802001953125 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | EQUITABLE | 3500000 | 0 | 1766448 | 50.5 | 1766448 | 1773421 | 1733552 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped as in the description.
10853 | Completion of Burgei milk cooling plan | Completion of Burgei milk cooling plan | To complete Burgei milk cooling plan | Burgei milk cooling plan completed | 3110299 | Construction of Buildings - Ot | RONGAI | VISOI | -0.148545 35.873142 1880.4 14.699999809265137 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10854 | Crop Development and Management | Purchase of land for construction of Farm input Centre at Wei Centre | To acquire land for construction of Farm input Centre at Wei Centre | Land for construction of Farm input Centre at Wei Centre acquired | 3110299 | Construction of Buildings - Ot | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 0 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2000000 | 0 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
10855 | Crop Development and Management | Kaptembwo tea buying centre - construction of kaptembwo tea buying centre | To implement kaptembwo tea buying centre - construction of kaptembwo tea buying centre for agricultural development and food production | Kaptembwo tea buying centre - construction of kaptembwo tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.634983, 35.657973 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936166 | 93.6 | 936166 | 1500000 | 63834 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
10856 | Crop Development and Management | Singorwet tea buying centre - completion of a tea buying centre at Singorwet | To implement singorwet tea buying centre - completion of a tea buying centre at singorwet for agricultural development and food production | Singorwet tea buying centre - completion of a tea buying centre at Singorwet completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.62289, 35.672618 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998602 | 99.9 | 998602 | 699886 | 1398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
10857 | Administration, Planning and Support Services | Construction of Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | To construct Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei | Tea Buying Centres at Ambusket, Chelalang, Saosa and Tuiyobei constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | AMALO | -0.667318, 35.61563 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2023 | 5360000 | 5360000 | 5360000 | Equitable | Equitable | 5360000 | 0 | 891679 | 16.6 | 891679 | 279520 | 4468321 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
10858 | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip | To implement kabianga cattle dip - purchase of land and construction of kabianga cattle dip for agricultural development and food production | Kabianga cattle dip - purchase of land and construction of Kabianga cattle dip completed | 3110504 | Other Infrastructure and Civil Works | KURESOI NORTH | KAMARA | -0.131288, 35.609787 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Land was never purchased. Cattles get vaccinated along Kabianga Kiplelechon road..
10859 | Administration, Planning and Support Services | completion of Saptet tea buying centre | To complete Saptet tea buying centre | Saptet tea buying centre completed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.592825, 35.636085 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 399040 | 99.8 | 399040 | 393820 | 960 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
10860 | Administration, Planning and Support Services | construction of Chepkiswet tea buying centre | To construct Chepkiswet tea buying centre | Chepkiswet tea buying centre constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 600000 | 75 | 600000 | 698687 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
10861 | Administration, Planning and Support Services | construction of Seger Kap mugei tea buying centre | To construct Seger Kap mugei tea buying centre | Seger Kap mugei tea buying centre constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.579623, 35.574247 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Constructed UpTo lental.
10862 | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Construction of Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | To construct Tea Buying Centres at banana, Ainamoi, and Kapset buying centre | Tea Buying Centres at banana, Ainamoi, and Kapset buying centre constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.604183 35.596885 2414.8 10.899999618530273 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2400000 | 3600000 | Equitable | EQUITABLE | 3600000 | 0 | 1199220 | 50 | 1199220 | 1303809 | 1200780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good and functional.
10863 | Administration, Planning and Support Services | construction of Tuyobei Ketit tea buying centre | To construct Tuyobei Ketit tea buying centre | Tuyobei Ketit tea buying centre constructed | 3110504 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 726010 | 90.8 | 726010 | 726010 | 73990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
10864 | Crop Development and Management | Establishment of a fish hatchery in Lakeview | To implement establishment of a fish hatchery in lakeview for agricultural development and food production | Establishment of a fish hatchery in Lakeview completed | 3110504 | Other Infrastructure and Civil Works | NAIVASHA | LAKE VIEW | -0.742104, 36.432755 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Submerged.
10865 | Rehabilitation of Nairobi cattle dip in Arutani | Rehabilitation of Nairobi cattle dip in Arutani | To rehabilitate Nairobi cattle dip in Arutani to restore functionality | Nairobi cattle dip in Arutani rehabilitated | 3110504 | Other Infrastructure and Civil Works | RONGAI | SOLAI | -0.039489, 36.122165 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799472 | 99.9 | 799472 | 597667 | 528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10866 | Crop Development and Management | youth and woment urban farming support | To implement youth and woment urban farming support for agricultural development and food production | youth and woment urban farming support completed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | KAPTEMBWO | -0.312059, 36.053008 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2020/21 | 4000000 | 4000000 | 4000000 | Equitable | EQUITABLE | 4000000 | 0 | 1999996 | 50 | 1999996 | 501200 | 2000004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly since the residents benefited from the incubators. Viable: Had it not been vandalized it could been a viable project. Contractor: WEIROD LIMITED. Assessor remarks: The incubators served its purpose but the greenhouses were vandalized and driplines and seedbeds destroyed s.
10867 | Crop Development and Management | Purchase of KCC fish ponds | To procure KCC fish ponds | KCC fish ponds procured | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 493000 | 98.6 | 493000 | 0 | 7000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need continuous improvement.
10868 | Crop Development and Management | Fencing of Cooling Plant at Milima Mitatu | To secure Cooling Plant at Milima Mitatu through fencing | Cooling Plant at Milima Mitatu fenced and secured | 3110599 | Other Infrastructure and Civil Works | MOLO | TURI | -0.297121 35.713899 2654.8 72.9000015258789 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
10869 | Fisheries Development | Procurement of 40Hp out board boat engines | To procure and supply 40Hp out board boat engines | 40Hp out board boat engines procured and supplied | 3110702 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998000 | 99.8 | 998000 | 0 | 2000 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10870 | Crop Development and Management | Repair of fish ponds - Tarabete landing beach | To rehabilitate fish ponds - Tarabete landing beach to restore functionality | Fish ponds - Tarabete landing beach rehabilitated | 3110702 | N/A | GILGIL | MALEWA WEST | -0.684685 36.471073 0 2000 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999203 | 100 | 1999203 | 1200000 | 797 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yea. Assessor remarks: Has been maintained over years.
10871 | Crop Development and Management | Procure 1 farm tractor | To implement procure 1 farm tractor for agricultural development and food production | Procure 1 farm tractor completed | 3110706 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3404999 | 97.3 | 3404999 | 1 | 95001 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10872 | Administration, Planning and Support Services | erecting of a fence around Olenguruone Dairies society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | erecting of a fence around Olenguruone Dairies society completed | 3111103 | Purchase of Agricultural Machinery and Equipment | KURESOI SOUTH | AMALO | -0.592109, 35.684406 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2023 | 2000001 | 0 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
10873 | Supply Installation and Testing of Drip Irrigation Kits for Mwariki Farmers in Nakuru East Sub-County | Supply Installation and Testing of Drip Irrigation Kits for Mwariki Farmers in Nakuru East Sub-County | To implement supply installation and testing of drip irrigation kits for mwariki farmers in nakuru east sub-county for agricultural development and food production | Supply Installation and Testing of Drip Irrigation Kits for Mwariki Farmers in Nakuru East Sub-County completed | 3111103 | Purchase of Agricultural Machinery and Equipment | NAKURU WEST | BARUT WARD | -0.173672, 35.862823 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10874 | Crop Development and Management | construction of of milk cooler house at Mutamaiyo | To construct of milk cooler house at Mutamaiyo | Of milk cooler house at Mutamaiyo constructed | 3111103 | Purchase of Agricultural Machinery and Equipment | MOLO | ELBURGON | -0.267627, 35.796427 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | - | 1500000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1371380 | 98 | 1371380 | 1400000 | 28620 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational.
10875 | Tractor purchase for Inua hustler cooperative - purchase of Tractor, bailer, Harrow, and Trailer for the Inua Hustler cooperative | Tractor purchase for Inua hustler cooperative - purchase of Tractor, bailer, Harrow, and Trailer for the Inua Hustler cooperative | To implement tractor purchase for inua hustler cooperative - purchase of tractor, bailer, harrow, and trailer for the inua hustler cooperative for agricultural development and food production | Tractor purchase for Inua hustler cooperative - purchase of Tractor, bailer, Harrow, and Trailer for the Inua Hustler cooperative completed | 3111103 | Purchase of Agricultural Machinery and Equipment | GILGIL | ELEMENTAITA | -0.567032, 36.114817 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 9500000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9813200 | 98.1 | 9813200 | 0 | 186800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some of the equipments have broken down.
10876 | Crop Development and Management | Purchase of milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives | To procure milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives | Milk pasteurizers, cooling system and dispensers (1000lts system) Mangu Tomato, Lare Njoro, Kamarus, Kamugendo Dairy Farmers Co-operatives procured | 3111103 | Purchase of Agricultural Machinery and Equipment | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 17500000 | 10000000 | 10000000 | Equitable | EQUITABLE | 10000000 | 0 | 8191456 | 81.9 | 8191456 | 8191456 | 1808544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10877 | Crop Development and Management | kiptororo cooling plant - completion of Kiptororo cooling plant | To implement kiptororo cooling plant - completion of kiptororo cooling plant for agricultural development and food production | kiptororo cooling plant - completion of Kiptororo cooling plant completed | 3111103 | Purchase of Agricultural Machinery and Equipment | KURESOI NORTH | KIPTORORO | -0.300889 35.533228 0 20.100000381469727 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999956 | 100 | 1999956 | 0 | 44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Request for construction of toilet.
10878 | Soil Conservation and Water Harvesting Structure at Maella Ward Naivasha Sub-County | Soil Conservation and Water Harvesting Structure at Maella Ward Naivasha Sub-County | To implement soil conservation and water harvesting structure at maella ward naivasha sub-county for agricultural development and food production | Soil Conservation and Water Harvesting Structure at Maella Ward Naivasha Sub-County completed | 3111103 | Purchase of Agricultural Machinery and Equipment | NAIVASHA | MAIELLA | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 3336740 | 3336740 | 3336740 | Equitable | N/A | 3336740 | 0 | 3336740 | 100 | 3336740 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10879 | Construction of a milk cooling plants at Ndabibi and Maiella | Construction of a milk cooling plants at Ndabibi and Maiella | To construct a milk cooling plants at Ndabibi and Maiella | A milk cooling plants at Ndabibi and Maiella constructed | 3111103 | Purchase of Agricultural Machinery and Equipment | NAIVASHA | MAIELLA | -0.730135, 36.230433 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6998825 | 100 | 6998825 | 1500000 | 1175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in use.
10880 | Purchase of incubators for Bahati ward | Purchase of incubators for Bahati ward | To procure incubators for Bahati ward | Incubators for Bahati ward procured | 3111120 | Purchase of Specialized Plant. - | BAHATI | BAHATI | -0.186792, 36.125241 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999950 | 100 | 1999950 | 1500000 | 50 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
10881 | Crop Development and Management | Construction of Milk Bulking and Chilling Plant in Naivasha | To construct Milk Bulking and Chilling Plant in Naivasha | Milk Bulking and Chilling Plant in Naivasha constructed | 3111120 | Purchase of Specialized Plant. - | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 8399983.4 | 8399983 | 8399983 | Equitable | N/A | 8399983 | 0 | 8399983 | 100 | 8399983 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10882 | Purchase of Hatching Incubators | Purchase of Hatching Incubators | To procure Hatching Incubators | Hatching Incubators procured | 3111120 | Purchase of Specialized Plant. - | GILGIL | EBURU-MBARUK | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10883 | Administration, Planning and Support Services | Purchase of Pulping Machine for Jumatatu society | To procure Pulping Machine for Jumatatu society | Pulping Machine for Jumatatu society procured | 3111120 | Purchase of Specialized Plant. - | SUBUKIA | KABAZI | -0.08223 36.16987 0 1381 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
10884 | Purchase of Incubators and backup generators - purchase of Incubators and backup generators for Kihoto youth group, Lari young farmers, Mwireri women welfare group, Gakingi young turks group and Gatitu women group | Purchase of Incubators and backup generators - purchase of Incubators and backup generators for Kihoto youth group, Lari young farmers, Mwireri women welfare group, Gakingi young turks group and Gatitu women group | To procure Incubators and backup generators - purchase of Incubators and backup generators for Kihoto youth group, Lari young farmers, Mwireri women welfare group, Gakingi young turks group and Gatitu women group | Incubators and backup generators - purchase of Incubators and backup generators for Kihoto youth group, Lari young farmers, Mwireri women welfare group, Gakingi young turks group and Gatitu women group procured | 3111120 | Purchase of Specialized Plant. - | SUBUKIA | WASEGES | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998960 | 99.9 | 998960 | 0 | 1040 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10885 | planting material support ( purchase of Avocados) | planting material support ( purchase of Avocados) | To implement planting material support ( purchase of avocados) for agricultural development and food production | planting material support ( purchase of Avocados) completed | 3111301 | Purchase of Certified Crop Seed | GILGIL | ELEMENTAITA | -0.583872, 36.10833 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999600 | 100 | 3999600 | 0 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
10886 | Crop Development and Management | Planting materials support projects-Avocado Seedlings | To implement planting materials support projects-avocado seedlings for agricultural development and food production | Planting materials support projects-Avocado Seedlings completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 30000000 | 15000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 13399497 | 89.3 | 13399497 | 1 | 1600503 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10887 | Crop Development and Management | Planting materials support projects-Coffee seedlings | To implement planting materials support projects-coffee seedlings for agricultural development and food production | Planting materials support projects-Coffee seedlings completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 4966169.6 | 4966169.6 | 4966169.6 | Equitable | N/A | 4966169.6 | 0 | 1999999 | 40.3 | 1999999 | 1 | 2966170.6 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10888 | Crop Development and Management | Planting materials support projects-Macadamia Seedlings | To implement planting materials support projects-macadamia seedlings for agricultural development and food production | Planting materials support projects-Macadamia Seedlings completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 13399497 | 191.4 | 13399497 | 1 | -6399497 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10889 | Supply of supplies for production - Supply of avocado, macadamia seedlings | Supply of supplies for production - Supply of avocado, macadamia seedlings | To implement supply of supplies for production - supply of avocado, macadamia seedlings for agricultural development and food production | Supply of supplies for production - Supply of avocado, macadamia seedlings completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 10500000 | 6633500 | 6633500 | Equitable | N/A | 6633500 | 0 | 10397600 | 156.7 | 10397600 | 2519316 | -3764100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10890 | Naivasha East onion Project - Purchase and distribution of Onion Seeds (texas grano and leans) for Mwega and Kinungi | Naivasha East onion Project - Purchase and distribution of Onion Seeds (texas grano and leans) for Mwega and Kinungi | To implement naivasha east onion project - purchase and distribution of onion seeds (texas grano and leans) for mwega and kinungi for agricultural development and food production | Naivasha East onion Project - Purchase and distribution of Onion Seeds (texas grano and leans) for Mwega and Kinungi completed | 3111301 | Purchase of Certified Crop Seed | NAIVASHA | NAIVASHA EAST | -0.805153, 36.533642 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1449472 | 96.6 | 1449472 | 0 | 50528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Successful project but it was not enough for all farmers.
10891 | Crop Development and Management | Livestock support ( breeding of Dorpers) for Elementaita ward | To implement livestock support ( breeding of dorpers) for elementaita ward for agricultural development and food production | Livestock support ( breeding of Dorpers) for Elementaita ward completed | 3111302 | Purchase of Animals and Breeding Stock | GILGIL | ELEMENTAITA | -0.583778, 36.10824 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499800 | 100 | 1499800 | 0 | 200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
10892 | Crop Development and Management | Procurement and stocking of fish fingerlings. | To procure and supply and stocking of fish fingerlings | And stocking of fish fingerlings procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 4533338 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10893 | Fisheries Development | Restocking of Lake Naivasha, Solai and public dams. | To implement restocking of lake naivasha, solai and public dams. for agricultural development and food production | Restocking of Lake Naivasha, Solai and public dams. completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | 0.063644, 36.167486 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 4533338 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Restocked.
10894 | Purchase of Avocado seedlings | Purchase of Avocado seedlings | To procure Avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | NJORO | MAU NAROK | -0.601279 36.011185 2655.500244140625 25.384000778198242 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
10895 | purchase of avocado seedlings | purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | NJORO | NJORO | -0.359647 35.911945 2312.690673828125 7.51800012588501 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Only one working. The other 3 not.
10896 | Administration, Planning and Support Services | Purchase of Avocado seedlings | To procure Avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4762700 | 95.3 | 4762700 | 0 | 237300 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
10897 | Completion of Elburgon Slaughterhouse | Completion of Elburgon Slaughterhouse | To complete Elburgon Slaughterhouse | Elburgon Slaughterhouse completed | 3111504 | N/A | MOLO | ELBURGON | -0.295278, 35.809428 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1485172 | 99 | 1485172 | 0 | 14828 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No documents.
10898 | Development, Demarcation, provision of tap water and fencing and Kamere beach area, Naivasha | Development, Demarcation, provision of tap water and fencing and Kamere beach area, Naivasha | To implement development, demarcation, provision of tap water and fencing and kamere beach area, naivasha for agricultural development and food production | Development, Demarcation, provision of tap water and fencing and Kamere beach area, Naivasha completed | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1550000 | 1550000 | 1550000 | Equitable | N/A | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10899 | Crop Development and Management | Procurement and installation of fish pond liners. | To procure and supply and installation of fish pond liners | And installation of fish pond liners procured and supplied | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997000 | 99.9 | 1997000 | 0 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10900 | Crop Development and Management | Proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County. | To undertake the proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County | Proposed construction of Fish Processing Market, 1 No. Fish Banda and a modern Toilet Block with Septic Tank at Naivasha Sub-County implemented | 3111504 | N/A | HQ | HQ | N/A | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 8046747.16 | 8046747 | 8046747 | Equitable | N/A | 8046747 | 0 | 247400 | 3.1 | 247400 | 0 | 7799347 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10901 | Crop Development and Management | Supply installation of Green House and Water Tank at Bahati Sub-County Kabatini Ward | To implement supply installation of green house and water tank at bahati sub-county kabatini ward for agricultural development and food production | Supply installation of Green House and Water Tank at Bahati Sub-County Kabatini Ward completed | 3111504 | N/A | BAHATI | KABATINI | -0.217183, 36.161807 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2017 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes by then. Viable: Yes. Contractor: M/s pro max general supplies. Assessor remarks: Green house need repair for it to be in use again(pvc paper is torn),was functional for 2 year.
10902 | Construction of Teret Cattle Dip | Construction of Teret Cattle Dip | To construct Teret Cattle Dip | Teret Cattle Dip constructed | 3111504 | N/A | NJORO | MAUCHE | -0.451225, 35.952134 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2018 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 3413 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
10903 | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision | To implement naivasha east fish project - purchase and distribution of dam liners for kimunyu, maraigushu and sision for agricultural development and food production | Naivasha East Fish Project - Purchase and distribution of Dam liners for Kimunyu, Maraigushu and Sision completed | 3111504 | N/A | NAIVASHA | NAIVASHA EAST | -0.850102, 36.535011 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2018-19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1935450 | 96.8 | 1935450 | 0 | 64550 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10904 | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip | To implement soin ward cattle dips - construction of a cattle dip at lobisil cattle dip, banita cattle dip for agricultural development and food production | Soin Ward cattle dips - Construction of a cattle dip at Lobisil cattle dip, Banita cattle dip completed | 3111504 | N/A | RONGAI | SOIN | -0.065365 36.063149 1637 9.5 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 1400000 | 50 | 1400000 | 0 | 1400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require renovation.
10905 | Construction of Kianugu Cattle Dip | Construction of Kianugu Cattle Dip | To construct Kianugu Cattle Dip | Kianugu Cattle Dip constructed | 3111504 | N/A | RONGAI | SOLAI | -0.036028 36.095694 1609.0078125 7.103000164031982 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1940216 | 97 | 1940216 | 1990000 | 59784 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No sufficient acaricide. Assessor remarks: Not in use.
10906 | Construction of Tuiyomoi Cattle Dip | Construction of Tuiyomoi Cattle Dip | To construct Tuiyomoi Cattle Dip | Tuiyomoi Cattle Dip constructed | 3111504 | N/A | RONGAI | SOLAI | 0.045811 36.125512 1547.9873046875 17.819000244140625 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1990000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Non functional.
10907 | Crop Development and Management | Renovation of Limuru Cattle Dip | To rehabilitate Limuru Cattle Dip to restore functionality | Limuru Cattle Dip rehabilitated | 3111504 | N/A | RONGAI | SOLAI | 0.151221 36.195465 1713.139404296875 7.593999862670898 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 1940216 | 323.4 | 1940216 | 597667 | -1340216 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10908 | Renovation of Legetio Cattle Dip | Renovation of Legetio Cattle Dip | To rehabilitate Legetio Cattle Dip to restore functionality | Legetio Cattle Dip rehabilitated | 3111504 | N/A | RONGAI | VISOI | -0.13549 35.794188 2186.6000000000004 22 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599712 | 100 | 599712 | 600000 | 288 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
10909 | Construction of Olmanyatta Cattle Dip | Construction of Olmanyatta Cattle Dip | To construct Olmanyatta Cattle Dip | Olmanyatta Cattle Dip constructed | 3111504 | N/A | SUBUKIA | WASEGES | 0.166288, 36.231724 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498950 | 99.8 | 498950 | 499066 | 1050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Ye. Assessor remarks: Needs to be operationalize.
10910 | Rehabilitation of KT Cattle Dip | Rehabilitation of KT Cattle Dip | To rehabilitate KT Cattle Dip to restore functionality | KT Cattle Dip rehabilitated | 3111504 | N/A | SUBUKIA | WASEGES | 0.111637, 36.241873 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498950 | 99.8 | 498950 | 499066 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Should operational and rehabilitate.
10911 | Administration, Planning and Support Services | Purchase of land for milk coolers, Water and Electricity at Wei Centre | To acquire land for milk coolers, Water and Electricity at Wei Centre | Land for milk coolers, Water and Electricity at Wei Centre acquired | 3130101 | Acquisition of Land | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO. D09 | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | MINISTRY OF AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 0 | 2000000 | Equitable | equitable | 2000000 | 0 | 1200000 | 0 | 1200000 | 800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
10912 | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) | To implement county spatial plan - completion of contract price for the development of county spatial plan.(preparation of plans ,interpretation and localize strategic national and regional polices and procedure, production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic development) for orderly land use and housing provision | County spatial plan - Completion of contract price for the Development of County Spatial plan.(Preparation of plans ,Interpretation and localize strategic national and Regional polices and procedure, Production of topo graphic maps identification of vital natural resource and provision of revitalization framework for industries trade and commerce to spur economic Development) completed | 2211310 | Contracted Professional Services | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 121182048 | 1532016 | 1532016 | Equitable | N/A | 1532016 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10913 | Development of Urban centres | Development of Urban centres | To develop Urban centres | Urban centres developed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 77500000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 19500000 | 130 | 19500000 | 23103900 | -4500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10914 | planning of urban centres | planning of urban centres | To develop of urban centres | Of urban centres developed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 0 | 0 | 20000000 | Equitable | N/A | 20000000 | 0 | 1688125 | 0 | 1688125 | 2156959 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10915 | Survey and mapping (titling of land) | Survey and mapping (titling of land) | To survey and mapping (titling of land) for planning and development | And mapping (titling of land) surveyed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 0 | 0 | 25000000 | Equitable | N/A | 25000000 | 0 | 2250750 | 0 | 2250750 | 10740580 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10916 | Survey and Mapping | Survey and Mapping | To survey and Mapping for planning and development | And Mapping surveyed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2250750 | 45 | 2250750 | 5000000 | 2749250 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10917 | Survey, mapping and Planning for Bahati Centre | Survey, mapping and Planning for Bahati Centre | To implement survey, mapping and planning for bahati centre for orderly land use and housing provision | Survey, mapping and Planning for Bahati Centre completed | 2211311 | N/A | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2250750 | 150 | 2250750 | 10740580 | -750750 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10918 | Conditional Fund -Kenya Urban Support Project (KUSP) | Conditional Fund -Kenya Urban Support Project (KUSP) | To implement conditional fund -kenya urban support project (kusp) for orderly land use and housing provision | Conditional Fund -Kenya Urban Support Project (KUSP) completed | 2640503 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 1084843300 | 1084843300 | 0 | KUSP | N/A | 0 | 1084843300 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10919 | Kenya Urban Support Programme - urban institutional grants | Kenya Urban Support Programme - urban institutional grants | To implement kenya urban support programme - urban institutional grants for orderly land use and housing provision | Kenya Urban Support Programme - urban institutional grants completed | 2640503 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2018/19 | 2018/19 | 0 | 0 | 0 | N/A | N/A | 0 | 41200000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10920 | Establishment of Survey and Mapping Centres | Establishment of Survey and Mapping Centres | To implement establishment of survey and mapping centres for orderly land use and housing provision | Establishment of Survey and Mapping Centres completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 19500000 | 130 | 19500000 | 23103900 | -4500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10921 | Rehabilitation of County Estates | Rehabilitation of County Estates | To rehabilitate County Estates to restore functionality | County Estates rehabilitated | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 40200000 | 25200000 | 25200000 | N/A | N/A | 25200000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10922 | rehabilitation of Kimathi Toilets | rehabilitation of Kimathi Toilets | To rehabilitate Kimathi Toilets to restore functionality | Kimathi Toilets rehabilitated | 3110301 | Refurbishment of Residential Buildings | NAKURU EAST | FLAMINGO | -0.303539, 36.078562 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2017/18 | 5195712 | 5195712 | 5195712 | Equitable | N/A | 5195712 | 0 | 4621115 | 88.9 | 4621115 | 3800000 | 574597 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dame group Africa Ltd.
10923 | Flamingo ward Estate Project - Reroofing of Kimathi Estate | Flamingo ward Estate Project - Reroofing of Kimathi Estate | To implement flamingo ward estate project - reroofing of kimathi estate for orderly land use and housing provision | Flamingo ward Estate Project - Reroofing of Kimathi Estate completed | 3110301 | Refurbishment of Residential Buildings | NAKURU EAST | FLAMINGO | -0.302255, 36.079451 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2024/25 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1989052 | 49.7 | 1989052 | 4000000 | 2010948 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
10924 | Development of housing infrastructure | Development of housing infrastructure | To develop housing infrastructure | Housing infrastructure developed | 3110301 | Refurbishment of Residential Buildings | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 19500000 | 97.5 | 19500000 | 23103900 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10925 | Baharini I & II estate re-roofing | Baharini I & II estate re-roofing | To implement baharini i & ii estate re-roofing for orderly land use and housing provision | Baharini I & II estate re-roofing completed | 3110301 | Refurbishment of Residential Buildings | NAKURU EAST | KIVUMBINI | -0.299839, 36.085466 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3893714 | 97.3 | 3893714 | 106286 | 106286 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
10926 | Kaloleni 'A' estate re-roofing | Kaloleni 'A' estate re-roofing | To implement kaloleni 'a' estate re-roofing for orderly land use and housing provision | Kaloleni 'A' estate re-roofing completed | 3110301 | Refurbishment of Residential Buildings | NAKURU EAST | KIVUMBINI | -0.300759, 36.086506 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 1995084 | 1995084 | 1995084 | Equitable | N/A | 1995084 | 0 | 1982368 | 99.4 | 1982368 | 106286 | 12716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
10927 | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment of G.I.S Laboratory (Land Information Management (LIMS)) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2014/15 | 2014/15 | N/A | 16977976 | 8488989 | 8488989 | Equitable | N/A | 8488989 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
10928 | Housing Technology Transfer | Housing Technology Transfer | To implement housing technology transfer for orderly land use and housing provision | Housing Technology Transfer completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2015/16 | 2095464.6 | 2095464.6 | 2095464.6 | Equitable | N/A | 2095464.6 | 0 | 904098 | 43.1 | 904098 | 0 | 1191366.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10929 | Preparation of Valuation Roll | Preparation of Valuation Roll | To implement preparation of valuation roll for orderly land use and housing provision | Preparation of Valuation Roll completed | 3111402 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 8000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10930 | Purchase Market Ground | Purchase Market Ground | To procure Market Ground | Market Ground procured | 3130101 | Acquisition of Land | NAKURU WEST | BARUT | -0.324324, 36.054632 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 750000 | 62.5 | 750000 | 4200000 | 450000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yee. Assessor remarks: The land is there and developed.
10931 | Purchase of Land for Soimet ECD | Purchase of Land for Soimet ECD | To acquire land for Soimet ECD | Land for Soimet ECD acquired | 3130101 | Acquisition of Land | NAKURU WEST | BARUT | -0.3425 36.042 0 2000 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 750000 | 37.5 | 750000 | 3000000 | 1250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: No land has been purchased for soimet ecd.
10932 | Purchase of land for Gicheha community borehole | Purchase of land for Gicheha community borehole | To acquire land for Gicheha community borehole | Land for Gicheha community borehole acquired | 3130101 | Acquisition of Land | NAIVASHA | BIASHARA-NAIVASHA | -0.728632, 36.50234 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2022 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 700000 | 87.5 | 700000 | 1000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fastracking of title deed by county government..
10933 | Purchase of land for Kahuruko community borehole | Purchase of land for Kahuruko community borehole | To acquire land for Kahuruko community borehole | Land for Kahuruko community borehole acquired | 3130101 | Acquisition of Land | NAIVASHA | BIASHARA-NAIVASHA | -0.728632, 36.50234 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2022 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fastracking of title deed by county government..
10934 | Purchase of land for the Giachonge ECDE | Purchase of land for the Giachonge ECDE | To acquire land for the Giachonge ECDE | Land for the Giachonge ECDE acquired | 3130101 | Acquisition of Land | BAHATI | DUNDORI | -0.236778 36.167465 1979.699951171875 52.400001525878906 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Marimaya investment ltd. Assessor remarks: Good.
10935 | purchase of land for Mbombo ECDE | purchase of land for Mbombo ECDE | To acquire land for Mbombo ECDE | Land for Mbombo ECDE acquired | 3130101 | Acquisition of Land | GILGIL | ELEMENTAITA | -0.556018 36.104887 1961.0999755859375 18.899999618530273 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 3500000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 4490000 | 0 | 4490000 | 4200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Owners are yet to be paid..
10936 | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | Purchase of Land - Slaughter House land in Gilgil (additional Funding) | To acquire land for - Slaughter House land in Gilgil (additional Funding) | Land for - Slaughter House land in Gilgil (additional Funding) acquired | 3130101 | Acquisition of Land | GILGIL | GILGIL | -0.508071 36.319004 2000.9000244140625 87.68000030517578 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 994874 | 994874 | Equitable | N/A | 994874 | 0 | 2000000 | 201 | 2000000 | 0 | -1005126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
10937 | Kihingo market - Purchase of market land for Kihingo Community | Kihingo market - Purchase of market land for Kihingo Community | To implement kihingo market - purchase of market land for kihingo community for orderly land use and housing provision | Kihingo market - Purchase of market land for Kihingo Community completed | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2015/16 | 5500000 | 5500000 | 5500000 | N/A | N/A | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10938 | Purchase of land for the ECD | Purchase of land for the ECD | To acquire land for the ECD | Land for the ECD acquired | 3130101 | Acquisition of Land | BAHATI | KABATINI | -0.233983 36.154465 1965.599609375 11.258999824523926 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes by then. Viable: Yes. Assessor remarks: Road needs routine maintenance (bulk project).
10939 | Purchase of land for Kabianga dispensary | Purchase of land for Kabianga dispensary | To acquire land for Kabianga dispensary | Land for Kabianga dispensary acquired | 3130101 | Acquisition of Land | KURESOI NORTH | KAMARA | -0.168763 35.689192 2508 7.900000095367432 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 9800000 | 653.3 | 9800000 | 1500000 | -8300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Land not bought.
10940 | Purchase of land for Kapkures ECD | Purchase of land for Kapkures ECD | To acquire land for Kapkures ECD | Land for Kapkures ECD acquired | 3130101 | Acquisition of Land | NAKURU WEST | KAPKURES | -0.306306 36.036551 0 2000 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5000000 | 83.3 | 5000000 | 1000000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Class was never done. No land available.
10941 | Purchase of land for Tachasis market | Purchase of land for Tachasis market | To acquire land for Tachasis market | Land for Tachasis market acquired | 3130101 | Acquisition of Land | NAKURU WEST | KAPKURES | -0.324324, 36.018595 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Provide space for trading and job opportunity.
10942 | Purchase of land for a public playground at Kihingo Centre | Purchase of land for a public playground at Kihingo Centre | To acquire land for a public playground at Kihingo Centre | Land for a public playground at Kihingo Centre acquired | 3130101 | Acquisition of Land | NJORO | KIHINGO | -0.44293, 35.969328 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2021 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4000000 | 88.9 | 4000000 | 0 | 500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
10943 | Purchase of land for Longonot water project | Purchase of land for Longonot water project | To acquire land for Longonot water project | Land for Longonot water project acquired | 3130101 | Acquisition of Land | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10944 | Purchase of borehole land in Ngecha | Purchase of borehole land in Ngecha | To procure borehole land in Ngecha | Borehole land in Ngecha procured | 3130101 | Acquisition of Land | RONGAI | MOSOP | -0.308665 35.93839 2141.6 5 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 770000 | 77 | 770000 | 0 | 230000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: La-mac. Assessor remarks: Good work.
10945 | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | Purchase of Public Utility Land for Livestock and Chepkinoiyo Retail Market | To procure Public Utility Land for Livestock and Chepkinoiyo Retail Market | Public Utility Land for Livestock and Chepkinoiyo Retail Market procured | 3130101 | Acquisition of Land | KURESOI NORTH | NYOTA | -0.362015, 35.598653 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016-2017 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
10946 | Purchase of land for establishment of a Dispensary in Rhonda | Purchase of land for establishment of a Dispensary in Rhonda | To acquire land for establishment of a Dispensary in Rhonda | Land for establishment of a Dispensary in Rhonda acquired | 3130101 | Acquisition of Land | NAKURU WEST | RHONDA | N/A | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2019/20 | N/A | 20000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
10947 | Purchase of land for Public use in Subukia ward | Purchase of land for Public use in Subukia ward | To acquire land for Public use in Subukia ward | Land for Public use in Subukia ward acquired | 3130101 | Acquisition of Land | SUBUKIA | SUBUKIA | 0.002793 36.233127 1991.4000244140625 22.82200050354004 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1400000 | 1400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 1200000 | 85.7 | 1200000 | 2400000 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the streetlights serve the, town. Contractor: Information not available. Assessor remarks: The streetlights are still working..
10948 | purchase of land for Turi Health Center (Land Buying) | purchase of land for Turi Health Center (Land Buying) | To acquire land for Turi Health Center (Land Buying) | Land for Turi Health Center (Land Buying) acquired | 3130101 | Acquisition of Land | MOLO | TURI | -0.279395 35.753738 2477.9 9.800000190734863 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2900000 | 96.7 | 2900000 | 3000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
10949 | purchase of land for Kware kapkwen borehole | purchase of land for Kware kapkwen borehole | To acquire land for Kware kapkwen borehole | Land for Kware kapkwen borehole acquired | 3130101 | Acquisition of Land | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10950 | Purchase of land for Igwamiti ECD | Purchase of land for Igwamiti ECD | To acquire land for Igwamiti ECD | Land for Igwamiti ECD acquired | 3130101 | Acquisition of Land | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO. D10 | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | MINISTRY OF LANDS, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
10951 | Administration, Planning and support services | completion of Rongai social hall | To complete Rongai social hall | Rongai social hall completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | RONGAI | VISOI | -0.173053 35.86075 1861.5999755859375 10.399999618530273 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 0 | 0 | 0 | 332 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10952 | Establishing and equipping of a GBV Centre | Establishing and equipping of a GBV Centre | To implement establishing and equipping of a gbv centre for youth empowerment and social inclusion | Establishing and equipping of a GBV Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 10000000 | 5000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10953 | Establishing and equipping of cultural facilities | Establishing and equipping of cultural facilities | To implement establishing and equipping of cultural facilities for youth empowerment and social inclusion | Establishing and equipping of cultural facilities completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 10000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10954 | Nurturing of sports talents through Development of sports centres | Nurturing of sports talents through Development of sports centres | To implement nurturing of sports talents through development of sports centres for youth empowerment and social inclusion | Nurturing of sports talents through Development of sports centres completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10955 | refurbishment of old Town Hall and offices | refurbishment of old Town Hall and offices | To implement refurbishment of old town hall and offices for youth empowerment and social inclusion | refurbishment of old Town Hall and offices completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 8000000 | 8000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10956 | Administration, Planning and support services | Construction of social hall at mwaki Mugi Chief ground | To construct social hall at mwaki Mugi Chief ground | Social hall at mwaki Mugi Chief ground constructed | 3110299 | Construction of Buildings - Ot | BAHATI | KABATINI | -0.232477 36.147302 1941.300048828125 51.319000244140625 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | Equitable | 4,780,076 | 5000000 | 0 | 0 | 0 | 0 | 11803 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational,but need installation of electricity.
10957 | Administration, Planning and support services | Construction and equipping of a Resource Centre at Mogoon Centre | To construct and equip a Resource Centre at Mogoon Centre | A Resource Centre at Mogoon Centre constructed and equipped | 3110299 | Construction of Buildings - Ot | NAKURU WEST | KAPKURES | -0.306306 36.000514 0 2000 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | 2,973,420 | 3000000 | 0 | 0 | 0 | 0 | 316 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Was bought but about quarter has been privatised..
10958 | Administration, Planning and support services | Completion of Teacher social Hall | To complete Teacher social Hall | Teacher social Hall completed | 3110299 | Construction of Buildings - Ot | NAKURU EAST | MENENGAI | -0.27578, 36.115322 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2019/20 | 6498843 | 6498843 | 6498843 | Equitable | - | 6498843 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10959 | Administration, Planning and support services | Construction of Social hall at Mercy Njeri | To construct Social hall at Mercy Njeri | Social hall at Mercy Njeri constructed | 3110299 | Construction of Buildings - Ot | RONGAI | MENENGAI WEST | -0.242492 36.006959 2007.199951171875 47.21500015258789 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need mainenance.
10960 | Construction of library Molo Town | Construction of library Molo Town | To construct library Molo Town | Library Molo Town constructed | 3110299 | Construction of Buildings - Ot | MOLO | MOLO CENTRAL | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | 2014/15 | 1036883.2 | 1036883.2 | 1036883.2 | Equitable | N/A | 1036883.2 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10961 | Enhanced care and support of the elderly through expansion of new rooms at Alms house | Enhanced care and support of the elderly through expansion of new rooms at Alms house | To implement enhanced care and support of the elderly through expansion of new rooms at alms house for youth empowerment and social inclusion | Enhanced care and support of the elderly through expansion of new rooms at Alms house completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10962 | Administration, Planning and support services | Leveling and compacting of Menengai West field and goal post | To implement leveling and compacting of menengai west field and goal post for youth empowerment and social inclusion | Leveling and compacting of Menengai West field and goal post completed | 3110499 | Construction of Roads - Other | RONGAI | MENENGAI WEST | -0.255223 35.990582 1983.5 2.700000047683716 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | 498,972 | 500000 | 0 | 0 | 0 | 0 | 11898 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
10963 | Administration, Planning and support services | Rehabilitation of Bahati Stadium i.e. levelling, fencing and new goal posts | To rehabilitate Bahati Stadium i.e. levelling, fencing and new goal posts to restore functionality | Bahati Stadium i.e. levelling, fencing and new goal posts rehabilitated | 3110504 | Other Infrastructure and Civil Works | BAHATI | BAHATI | -0.183297 36.123632 1931 9.64799976348877 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 500000 | Equitable | 498,995 | 500000 | 0 | 0 | 0 | 0 | 11805 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
10964 | Administration, Planning and support services | Construction of perimeter wall and metallic gate at Bondeni Social hall | To construct perimeter wall and metallic gate at Bondeni Social hall | Perimeter wall and metallic gate at Bondeni Social hall constructed | 3110504 | Other Infrastructure and Civil Works | GILGIL | GILGIL | -0.504943, 36.326059 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | 1,999,999 | 2000000 | 0 | 0 | 0 | 0 | 333 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
10965 | Administration, Planning and support services | Construction of recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" | To construct recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" | Recreation area, stalls and erection of a perimeter wall around "Mlima Ugali" constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | BARUT | -0.326886, 36.044487 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2019 | 3300000 | 3300000 | 3300000 | Equitable | 3,295,000 | 3300000 | 0 | 0 | 0 | 0 | 11888 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Cider collect.
10966 | Administration, Planning and support services | Equipping and fencing of Elburgon social hall | To equip and fencing of Elburgon social hall with necessary facilities and equipment | And fencing of Elburgon social hall equipped | 3110599 | Other Infrastructure and Civil Works | MOLO | ELBURGON | -0.307065 35.810187 2407.60009765625 27.5 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 16 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: PETMAT LTD. Assessor remarks: Ongoing.
10967 | Administration, Planning and support services | construction of Kiptangwanyi social hall | To construct Kiptangwanyi social hall | Kiptangwanyi social hall constructed | 3110599 | Other Infrastructure and Civil Works | GILGIL | ELEMENTAITA | -0.563416 36.116992 1960.699951171875 0.6940000057220459 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
10968 | Administration, Planning and support services | Completion of changing room at Kimathi Grounds | To complete changing room at Kimathi Grounds | Changing room at Kimathi Grounds completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.303687, 36.078603 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
10969 | Administration, Planning and support services | AGPO youth development | To implement agpo youth development for youth empowerment and social inclusion | AGPO youth development completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | HELLS GATE | -0.77815 36.429658 1909.5999755859375 16.07900047302246 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: At a cost of 1,000,000.
10970 | Administration, Planning and support services | Kabazi 3 playfields rehabilitation - levelling and rehabilitation of 3 playfields at Kabazi, Solai centre and Ndungiri | To implement kabazi 3 playfields rehabilitation - levelling and rehabilitation of 3 playfields at kabazi, solai centre and ndungiri for youth empowerment and social inclusion | Kabazi 3 playfields rehabilitation - levelling and rehabilitation of 3 playfields at Kabazi, Solai centre and Ndungiri completed | 3110599 | Other Infrastructure and Civil Works | SUBUKIA | KABAZI | -0.108053, 36.054603 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
10971 | Administration, Planning and support services | equipping of Kiptangich Social Hall | To equip Kiptangich Social Hall with necessary facilities and equipment | Kiptangich Social Hall equipped | 3110599 | Other Infrastructure and Civil Works | KURESOI SOUTH | KIPTAGICH | -0.572849, 35.613061 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | Not yet started | 999944 | 0 | 999943 | Equitable | 999,300 | 999943 | 0 | 0 | 0 | 0 | 29036 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started. Contractor: Don't know.
10972 | Administration, Planning and Support Services | construction of a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | To construct a sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court | A sport centre at St Teresa ECDE - swimming pool, basket ball court, netball court, Volleyball court constructed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | KIVUMBINI | -0.29986, 36.084106 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 0 | 0 | 10500000 | Equitable | 252,416 | 10500000 | 0 | 0 | 0 | 0 | 11803 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
10973 | Administration, Planning and support services | Maai mahiu social hall | To implement maai mahiu social hall for youth empowerment and social inclusion | Maai mahiu social hall completed | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2015/16 | 2015/16 | N/A | 2145555 | 2145555 | 2145555 | Equitable | N/A | 2145555 | 0 | 789 | 0 | 789 | 0 | 2144766 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10974 | Administration, Planning and support services | Kasarani social hall | To implement kasarani social hall for youth empowerment and social inclusion | Kasarani social hall completed | 3110599 | Other Infrastructure and Civil Works | GILGIL | MALEWA WEST | -0.702703 36.309037 0 2000 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2015/16 | 2015/16 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 2,499,720 | 1500000 | 0 | 0 | 0 | 0 | 335 | 0 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
10975 | Administration, Planning and support services | Natewa agpo youth centre | To implement natewa agpo youth centre for youth empowerment and social inclusion | Natewa agpo youth centre completed | 3110599 | Other Infrastructure and Civil Works | NAKURU EAST | MENENGAI | -0.277152 36.115829 1856.199951171875 26.469999313354492 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2015/16 | 2015/16 | N/A | 4000000 | 1227739 | 1227739 | Equitable | 1,499,856 | 1227739 | 0 | 0 | 0 | 0 | 42281 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not complete especially the toilets.
10976 | Renovation of Molo Social Hall, Electricity Connection and equipping | Renovation of Molo Social Hall, Electricity Connection and equipping | To rehabilitate Molo Social Hall, Electricity Connection and equipping to restore functionality | Molo Social Hall, Electricity Connection and equipping rehabilitated | 3110599 | Other Infrastructure and Civil Works | MOLO | MOLO CENTRAL | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2016/17 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10977 | Administration, Planning and support services | Social Hall (Shabab Grounds) | To implement social hall (shabab grounds) for youth empowerment and social inclusion | Social Hall (Shabab Grounds) completed | 3110599 | Other Infrastructure and Civil Works | NAKURU WEST | SHABAB | N/A | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | N/A | 998664 | 998664 | 998664 | Equitable | N/A | 998664 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10978 | Administration, Planning and support services | Rehabilitation Levelling and Upgrading of Site and Service Playground | To rehabilitate Levelling and Upgrading of Site and Service Playground to restore functionality | Levelling and Upgrading of Site and Service Playground rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.715344 36.437888 1915.0999755859375 44.79999923706055 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 1925126 | 1925126 | 1925126 | Equitable | N/A | 1925126 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Assessor remarks: Yet to start.
10979 | Administration, Planning and support services | Equipping of Bondeni social hall | To equip Bondeni social hall with necessary facilities and equipment | Bondeni social hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | GILGIL | GILGIL | -0.50498, 36.326032 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
10980 | Administration, Planning and support services | Kayole Social Hall - Equipping of Kayole Social Hall | To implement kayole social hall - equipping of kayole social hall for youth empowerment and social inclusion | Kayole Social Hall - Equipping of Kayole Social Hall completed | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | LAKE VIEW | -0.757179, 36.463786 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10981 | Administration, Planning and support services | Equipping of Social hall in London | To equip Social hall in London with necessary facilities and equipment | Social hall in London equipped | 3111109 | Purchase of Educational Aids and Related Equipment | NAKURU WEST | LONDON | -0.277619, 36.053618 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 41 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes.
10982 | Administration, Planning and support services | Maai mahiu Art and culture - purchase of studio / theatre equipments for maai mahiu social hall | To implement maai mahiu art and culture - purchase of studio / theatre equipments for maai mahiu social hall for youth empowerment and social inclusion | Maai mahiu Art and culture - purchase of studio / theatre equipments for maai mahiu social hall completed | 3111109 | Purchase of Educational Aids and Related Equipment | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,970,000 | 2000000 | 0 | 0 | 0 | 0 | 29037 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10983 | Administration, Planning and support services | Sports Enhancement - Purchase of Sports Equipment for the Olive Inn Mercy Njeri football and Volley Ball teams | To implement sports enhancement - purchase of sports equipment for the olive inn mercy njeri football and volley ball teams for youth empowerment and social inclusion | Sports Enhancement - Purchase of Sports Equipment for the Olive Inn Mercy Njeri football and Volley Ball teams completed | 3111109 | Purchase of Educational Aids and Related Equipment | RONGAI | MENENGAI WEST | N/A | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 500000 | 500000 | 500000 | Equitable | 499,650 | 500000 | 0 | 0 | 0 | 0 | 29411 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
10984 | Administration, Planning and support services | Viwandani social hall completion - completion of Viwandani social hall and construction of a toilet | To implement viwandani social hall completion - completion of viwandani social hall and construction of a toilet for youth empowerment and social inclusion | Viwandani social hall completion - completion of Viwandani social hall and construction of a toilet completed | 3111504 | N/A | NAIVASHA | VIWANDANI | -0.708377, 36.432697 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 0 | 3000000 | Equitable | 2,999,000 | 3000000 | 0 | 0 | 0 | 0 | 11886 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
10985 | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet | To implement athletes complex - purchase of 30 acres of land for establishing a sports centre at keringet for youth empowerment and social inclusion | Athletes Complex - Purchase of 30 acres of land for establishing a Sports Centre at Keringet completed | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | 2017/18 | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10986 | Administration, Planning and support services | Kamara social hall - purchase of land for kamara social hall | To implement kamara social hall - purchase of land for kamara social hall for youth empowerment and social inclusion | Kamara social hall - purchase of land for kamara social hall completed | 3130101 | Acquisition of Land | KURESOI NORTH | KAMARA | -0.168763 35.689192 2508 7.900000095367432 | VOTE NO. D11 | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | MINISTRY OF YOUTH, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Land not bought.
10987 | Water and Sewerage Management | construction of a water tank at Old Bahati dispensary | To construct a water tank at Old Bahati dispensary | A water tank at Old Bahati dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.161366 36.11427 1838.094970703125 88.09379577636719 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable. Assessor remarks: Good.
10988 | Water and Sewerage Management | drilling of borehole at old Bahati dispensary | To provide access to clean water through borehole drilling at old Bahati dispensary | Borehole drilled at old Bahati dispensary | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.170071 36.121778 0 2400 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
10989 | Water And Sewerage Management | piping Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto | To provide water distribution infrastructure at Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto | Water piping at Old Bahati dispensary intake to Matangi kenda and Old Bahati to Bishop Geto completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.154823 36.152876 2079.1091818588393 7.083000183105469 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 3483328 | 0 | 3483328 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable. Assessor remarks: The tank is there but there is no water also pipes are there.
10990 | Water and Sewerage Management | purchase and installation of solar panel at Old Bahati dispensary | To procure and install solar panel at Old Bahati dispensary | Solar panel at Old Bahati dispensary procured and installed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.154613, 36.157595 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 788916 | 0 | 788916 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's working.
10991 | Water and Sewerage Management | purchase of 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | To procure 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School | 5 water tank for our lady of Fatuma secondary school, St. Lwanga, St. Francis Secondary School procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499973 | 100 | 499973 | 27 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10992 | Water and Sewerage Management | Renovation of 2 Gatangi tanks in Wanyororo | To rehabilitate 2 Gatangi tanks in Wanyororo to restore functionality | 2 Gatangi tanks in Wanyororo rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.160234 36.102195 1851.86962890625 30.295000076293945 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 1737845 | 99.3 | 1737845 | 1745951 | 12155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Nor started.
10993 | Water and Sewerage Management | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti | To implement water piping for bahati farmer water, bahati trading centre, jomokenyatta area maili kumi and wanyororo gatangi to ngoti for access to clean water and environmental sustainability | water piping for Bahati farmer water, Bahati trading centre, Jomokenyatta area maili kumi and Wanyororo Gatangi to Ngoti completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | BAHATI | BAHATI | -0.160193, 36.102193 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499926 | 100 | 499926 | 500000 | 74 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes. Assessor remarks: The projects is on use.
10994 | Refurbishment of Offices (HQs) WEENR) | Refurbishment of Offices (HQs) WEENR) | To implement refurbishment of offices (hqs) weenr) for access to clean water and environmental sustainability | Refurbishment of Offices (HQs) WEENR) completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 7099750 | 2099750 | 2099750 | N/A | N/A | 2099750 | 0 | 2456688 | 117 | 2456688 | 0 | -356938 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10995 | Environmental Management | Construction of Access roads to Gioto and Naivasha Dumping site | To construct Access roads to Gioto and Naivasha Dumping site | Access roads to Gioto and Naivasha Dumping site constructed | 3110402 | Access Roads | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 7789133 | 129.8 | 7789133 | 8000000 | -1789133 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
10996 | Water and Sewerage Management | Ndimu water project completion | To implement ndimu water project completion for access to clean water and environmental sustainability | Ndimu water project completion completed | 3110501 | Bridges | MOLO | ELBURGON | -0.294145, 35.7941 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | - | 0 | 0 | 2700000 | Equitable | N/A | 2700000 | 0 | 2698749 | 0 | 2698749 | 3500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Only solarization was done by county government,borehole was done by NG-CDF.
10997 | Water And Sewerage Management | Purchase of water pump for Tergat borehole | To procure water pump for Tergat borehole | Water pump for Tergat borehole procured | 3110501 | Bridges | MOLO | ELBURGON | -0.301449 35.816235 0 600 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
10998 | Water and Sewerage Management | Construction of Bondeni Water intake | To construct Bondeni Water intake | Bondeni Water intake constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | AMALO | -0.590476 35.686102 2581.1123046875 9.741999626159668 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599824 | 100 | 599824 | 1000000 | 176 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: yes. Viable: yes. Contractor: m/s koros. Assessor remarks: works going on well.
10999 | Water and Sewerage Management | construction of water tank for Karunga DCC borehole | To construct water tank for Karunga DCC borehole | Water tank for Karunga DCC borehole constructed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.161802 36.114986 0 800 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 100000 | 0 | 100000 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work on progress.
11000 | Water and Sewerage Management | Drilling of borehole at Karunga DCC area | To provide access to clean water through borehole drilling at Karunga DCC area | Borehole drilled at Karunga DCC area | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.170071 36.121778 0 2400 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11001 | Water And Sewerage Management | Kamiruri 2 Water Project | To implement kamiruri 2 water project for access to clean water and environmental sustainability | Kamiruri 2 Water Project completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.175187 36.128404 1957.54638671875 5.360000133514404 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1998704.36 | 1998704.36 | 1998704.36 | Equitable | N/A | 1998704.36 | 0 | 1999722.14 | 100.1 | 1999722.14 | 1999573.2 | -1017.78 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11002 | Water And Sewerage Management | Karunga Last Water project | To implement karunga last water project for access to clean water and environmental sustainability | Karunga Last Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.175187 36.128404 1957.54638671875 5.360000133514404 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3899521.48 | 3899521.48 | 3899521.48 | Equitable | N/A | 3899521.48 | 0 | 1984730.93 | 50.9 | 1984730.93 | 1999573.2 | 1914790.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11003 | Water and Sewerage Management | piping Karunga DCC area to St. John Secondary - phase I | To provide water distribution infrastructure at Karunga DCC area to St. John Secondary - phase I | Water piping at Karunga DCC area to St. John Secondary - phase I completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.127321 36.178713 2275.578125 5.429999828338623 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 0 | 1183988 | Equitable | N/A | 1183988 | 0 | 0 | 0 | 0 | 1183988 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is working well.
11004 | Water and Sewerage Management | purchase and installation of solar panels at Karunga DCC borehole | To procure and install solar panels at Karunga DCC borehole | Solar panels at Karunga DCC borehole procured and installed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.150455 36.146665 2036.32080078125 5.013999938964844 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 788916 | 0 | 788916 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
11005 | Water And Sewerage Management | Rumathi Water project | To implement rumathi water project for access to clean water and environmental sustainability | Rumathi Water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | BAHATI | -0.127386, 36.178531 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 999589.25 | 999589.25 | 999589.25 | Equitable | N/A | 999589.25 | 0 | 1984730.93 | 198.6 | 1984730.93 | 1999573.2 | -985141.68 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water is in use.
11006 | Water And Sewerage Management | Barut Ward water works - Design and construction of water tank and piping Parkview primary water tank, Piping to Flamingo estate and Mwariki | To implement barut ward water works - design and construction of water tank and piping parkview primary water tank, piping to flamingo estate and mwariki for access to clean water and environmental sustainability | Barut Ward water works - Design and construction of water tank and piping Parkview primary water tank, Piping to Flamingo estate and Mwariki completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.342767, 36.042631 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 3000000 | 995700 | 995700 | Equitable | N/A | 995700 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PETRESHA KENYA LTD. Assessor remarks: Construction was done.
11007 | Water and Sewerage Management | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol | To implement soimet water borehole - piping to kapkwen village,soimet village and kiptenden village and kipsimbol for access to clean water and environmental sustainability | Soimet Water Borehole - Piping to Kapkwen village,Soimet village and Kiptenden village and Kipsimbol completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | -0.342342, 36.036679 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797921 | 99.9 | 1797921 | 2079 | 2079 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: CIDER COLLECTIONS. Assessor remarks: There was no project done.
11008 | Water And Sewerage Management | Water reticulation and construction of water tank, construction of a pump house and installation of a pump at KIGONOR Borehole | To provide clean water access at and construction of water tank, construction of a pump house and installation of a pump at KIGONOR Borehole | Water supply at and construction of water tank, construction of a pump house and installation of a pump at KIGONOR Borehole completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | 0.306306 36.054569 0 2200 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2993749.58 | 2993749.58 | 2993749.58 | Equitable | N/A | 2993749.58 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RYSON INVESTMENT. Assessor remarks: Project was completed.
11009 | Water and Sewerage Management | Drilling borehole in Mwariki area and piping | To implement drilling borehole in mwariki area and piping for access to clean water and environmental sustainability | Drilling borehole in Mwariki area and piping completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | BARUT | 0.324324, 36.054632 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 1921 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1463150 | 48.8 | 1463150 | 1473237 | 1536850 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
11010 | Water and Sewerage Management | Completion of milimani tower tank | To complete milimani tower tank | Milimani tower tank completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2797826 | 99.9 | 2797826 | 1979714 | 2174 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11011 | Water and Sewerage Management | Drilling of Gituamba borehole | To implement drilling of gituamba borehole for access to clean water and environmental sustainability | Drilling of Gituamba borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2588981.6 | 2588981.6 | 2588981.6 | Equitable | N/A | 2588981.6 | 0 | 2586423 | 99.9 | 2586423 | 2559 | 2558.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11012 | Water and Sewerage Management | Drilling of Kambi Ndoro borehole | To implement drilling of kambi ndoro borehole for access to clean water and environmental sustainability | Drilling of Kambi Ndoro borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | -0.728758, 36.502177 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 2516508 | 2516508 | 2516508 | Equitable | N/A | 2516508 | 0 | 2510298 | 99.8 | 2510298 | 55145 | 6210 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project is ongoing ,solarisation and pumbing ,tower..and tanks.
11013 | Water And Sewerage Management | Equipping, piping and water kiosk for Kamurugu borehole project | To implement equipping, piping and water kiosk for kamurugu borehole project for access to clean water and environmental sustainability | Equipping, piping and water kiosk for Kamurugu borehole project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1991160 | 99.6 | 1991160 | 2897000 | 8840 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11014 | Water And Sewerage Management | Equipping, piping and water kiosk for Kirima borehole project | To implement equipping, piping and water kiosk for kirima borehole project for access to clean water and environmental sustainability | Equipping, piping and water kiosk for Kirima borehole project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1999000 | 1999000 | 1999000 | Equitable | N/A | 1999000 | 0 | 1780720 | 89.1 | 1780720 | 2499366 | 218280 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11015 | Water and Sewerage Management | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house | To implement kambi ndoro borehole - purchase of pumps and construction of pump house for access to clean water and environmental sustainability | Kambi Ndoro Borehole - Purchase of Pumps and Construction of pump house completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | -0.701617, 36.532842 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998664 | 99.9 | 1998664 | 1336 | 1336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
11016 | Water and Sewerage Management | Kamurugu borehole pump - purchase of pump for kamurugu borehole | To implement kamurugu borehole pump - purchase of pump for kamurugu borehole for access to clean water and environmental sustainability | Kamurugu borehole pump - purchase of pump for kamurugu borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1469109.14 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11017 | Water and Sewerage Management | Muteithia Borehole - Drilling of Muteithia borehole | To implement muteithia borehole - drilling of muteithia borehole for access to clean water and environmental sustainability | Muteithia Borehole - Drilling of Muteithia borehole completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2798082 | 99.9 | 2798082 | 1918 | 1918 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11018 | Water And Sewerage Management | Piping of water at Mununga Dispensary | To provide water distribution infrastructure at water at Mununga Dispensary | Water piping at water at Mununga Dispensary completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | -0.705515, 36.515067 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019 | 698308.03 | 698308.03 | 698308.03 | Equitable | N/A | 698308.03 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Plenty of water at the facility.
11019 | Water And Sewerage Management | Piping of water in upper kinamba water project | To provide water distribution infrastructure at water in upper kinamba water project | Water piping at water in upper kinamba water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | BIASHARA-NAIVASHA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 1780720 | 254.4 | 1780720 | 2499366 | -1080720 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11020 | Water and Sewerage Management | Drilling and purchase of water pump for Wanyororo water project | To implement drilling and purchase of water pump for wanyororo water project for access to clean water and environmental sustainability | Drilling and purchase of water pump for Wanyororo water project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.252388, 36.187673 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1369685 | 34.2 | 1369685 | 1369685 | 2630315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Naxxy limited. Assessor remarks: Ongoing project.
11021 | Water and Sewerage Management | Dundori polytechnic water works water works Construction of an intake, Piping and construction of water tank | To implement dundori polytechnic water works water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Dundori polytechnic water works water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1078369 | 98 | 1078369 | 0 | 21631 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
11022 | Water and Sewerage Management | Dundori water project water works Construction of an intake, Piping and construction of water tank | To implement dundori water project water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Dundori water project water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494853 | 99 | 494853 | 0 | 5147 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
11023 | Water and Sewerage Management | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump | To implement mugwathi dundori water project - drilling of mugwathi dundori borehole and purchase of pump for access to clean water and environmental sustainability | Mugwathi Dundori water project - drilling of mugwathi dundori borehole and purchase of pump completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.235918, 36.182103 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11024 | Water and Sewerage Management | Nyumba Kumi water project water works Construction of an intake, Piping and construction of water tank | To implement nyumba kumi water project water works construction of an intake, piping and construction of water tank for access to clean water and environmental sustainability | Nyumba Kumi water project water works Construction of an intake, Piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.249796, 36.231777 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2191959 | 73.1 | 2191959 | 0 | 808041 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Came general supplies Ltd. Assessor remarks: Good condition.
11025 | Water And Sewerage Management | Water works Construction of an intake, Piping and construction of water tank at Githioro Water Project | To implement water works construction of an intake, piping and construction of water tank at githioro water project for access to clean water and environmental sustainability | Water works Construction of an intake, Piping and construction of water tank at Githioro Water Project completed | 3110502 | Water Supplies and Sewerage | BAHATI | DUNDORI | -0.262998 36.187494 1987.800048828125 16.464000701904297 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 999400.09 | 999400.09 | 999400.09 | Equitable | N/A | 999400.09 | 0 | 494853 | 49.5 | 494853 | 1500000 | 504547.09 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11026 | Water And Sewerage Management | Completion of borehole and construction of tank of Oljorai borehole | To complete borehole and construction of tank of Oljorai borehole | Borehole and construction of tank of Oljorai borehole completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2961344 | 2961344 | 2961344 | Equitable | N/A | 2961344 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11027 | Water And Sewerage Management | Extension of Barnabas water piping | To expand Barnabas water piping to increase capacity | Barnabas water piping expanded | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 995947 | 995947 | 995947 | Equitable | N/A | 995947 | 0 | 1000000 | 100.4 | 1000000 | 1000000 | -4053 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11028 | Water and Sewerage Management | Mbaruk / Eburru ward water project - water works - piping and tank renovations for Sogonoi, borehole and solar panel for Morop, borehole and solar for Echariria, piping in Ngorika ndogo, pema piping, piping meleleshwa, piping Oljorai, piping Gema water, Kiungururia East gate main piping, Thome dam repair and desilting, Jaika dam repair and desilting | To implement mbaruk / eburru ward water project - water works - piping and tank renovations for sogonoi, borehole and solar panel for morop, borehole and solar for echariria, piping in ngorika ndogo, pema piping, piping meleleshwa, piping oljorai, piping gema water, kiungururia east gate main piping, thome dam repair and desilting, jaika dam repair and desilting for access to clean water and environmental sustainability | Mbaruk / Eburru ward water project - water works - piping and tank renovations for Sogonoi, borehole and solar panel for Morop, borehole and solar for Echariria, piping in Ngorika ndogo, pema piping, piping meleleshwa, piping Oljorai, piping Gema water, Kiungururia East gate main piping, Thome dam repair and desilting, Jaika dam repair and desilting completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 18000000 | 16500000 | 16500000 | Equitable | N/A | 16500000 | 0 | 11588481 | 70.2 | 11588481 | 0 | 4911519 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11029 | Water and Sewerage Management | Nagum piping | To implement nagum piping for access to clean water and environmental sustainability | Nagum piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU / MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2831499.91 | 2831499.91 | 2831499.91 | Equitable | N/A | 2831499.91 | 0 | 2831500 | 100 | 2831500 | 444810 | -0.09 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11030 | University -Ngorika ndogo piping | University -Ngorika ndogo piping | To implement university -ngorika ndogo piping for access to clean water and environmental sustainability | University -Ngorika ndogo piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURRU / MBARUK | -0.361044, 36.19708 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | 17/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 489725 | 97.9 | 489725 | 0 | 10275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Water connected to few people.
11031 | Water and Sewerage Management | Piping of water from Gilgil through Gema to Kamathatha | To provide water distribution infrastructure at water from Gilgil through Gema to Kamathatha | Water piping at water from Gilgil through Gema to Kamathatha completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURU-MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11032 | Water and Sewerage Management | Piping of water in Barnabas area | To provide water distribution infrastructure at water in Barnabas area | Water piping at water in Barnabas area completed | 3110502 | Water Supplies and Sewerage | GILGIL | EBURU-MBARUK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11033 | Water and Sewerage Management | Construction of water tank and installation of pump at Cheponde/Ribotfarm Water project | To construct water tank and installation of pump at Cheponde/Ribotfarm Water project | Water tank and installation of pump at Cheponde/Ribotfarm Water project constructed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.165752 35.696828 0 2299.9990234375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2756113 | 2756113 | 2756113 | Equitable | N/A | 2756113 | 0 | 2756113 | 100 | 2756113 | 264026 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
11034 | Water and Sewerage Management | Green estate water works | To implement green estate water works for access to clean water and environmental sustainability | Green estate water works completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.305135 35.798927 2498.4 6.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2500001 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187550 | 0 | 1187550 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet connected to borehole.
11035 | Water and Sewerage Management | Ndimu borehole | To implement ndimu borehole for access to clean water and environmental sustainability | Ndimu borehole completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.292714 35.791345 0 2700 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2799698 | 186.6 | 2799698 | 989608 | -1299698 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
11036 | Water and Sewerage Management | Nyakiambi/Karunga Borehole Completion | To implement nyakiambi/karunga borehole completion for access to clean water and environmental sustainability | Nyakiambi/Karunga Borehole Completion completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.264914, 35.831575 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
11037 | Water and Sewerage Management | Nyariche community water projects- purchase of water pipes to supply water to Nyakiambi, Arimi and Ribot areas | To implement nyariche community water projects- purchase of water pipes to supply water to nyakiambi, arimi and ribot areas for access to clean water and environmental sustainability | Nyariche community water projects- purchase of water pipes to supply water to Nyakiambi, Arimi and Ribot areas completed | 3110502 | Water Supplies and Sewerage | MOLO | ELBURGON | -0.284884 35.845889 0 1399.9990234375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 0 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499965 | 0 | 2499965 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11038 | Water and Sewerage Management | Council Tank to Mbombo piping - purchase of water pipes for Council Tank to Mbombo | To implement council tank to mbombo piping - purchase of water pipes for council tank to mbombo for access to clean water and environmental sustainability | Council Tank to Mbombo piping - purchase of water pipes for Council Tank to Mbombo completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.569973, 36.108448 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995525 | 99.6 | 995525 | 0 | 4475 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipes laid from kiptawanyi to aMakongo.
11039 | Water and Sewerage Management | Gituamba / Kamugunda water project - purchase of water pipes for Gituamba / Kamugunda water project | To implement gituamba / kamugunda water project - purchase of water pipes for gituamba / kamugunda water project for access to clean water and environmental sustainability | Gituamba / Kamugunda water project - purchase of water pipes for Gituamba / Kamugunda water project completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799343 | 99.9 | 799343 | 0 | 657 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11040 | Water and Sewerage Management | Kahuho west Water Tank - Construction of water tank | To implement kahuho west water tank - construction of water tank for access to clean water and environmental sustainability | Kahuho west Water Tank - Construction of water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.640563, 36.145693 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995672 | 99.6 | 995672 | 4328 | 4328 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
11041 | Water and Sewerage Management | Makongo Tank - Construction of Water tank and Piping | To implement makongo tank - construction of water tank and piping for access to clean water and environmental sustainability | Makongo Tank - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1480515 | 98.7 | 1480515 | 19485 | 19485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11042 | Water and Sewerage Management | Miti Miti centre - design and construction of water tank and water piping | To implement miti miti centre - design and construction of water tank and water piping for access to clean water and environmental sustainability | Miti Miti centre - design and construction of water tank and water piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1500000 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11043 | Mugaa Water Tank | Mugaa Water Tank | To implement mugaa water tank for access to clean water and environmental sustainability | Mugaa Water Tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.558901, 36.076289 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 998812 | 998812 | 998812 | Equitable | N/A | 998812 | 0 | 1979879 | 198.2 | 1979879 | 998812 | -981067 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
11044 | Water and Sewerage Management | Munanda police water tank - Construction of tank police water tank | To implement munanda police water tank - construction of tank police water tank for access to clean water and environmental sustainability | Munanda police water tank - Construction of tank police water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.597591, 36.111653 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998341 | 99.8 | 998341 | 1000000 | 1659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
11045 | Water and Sewerage Management | Muririgua Tan - Construction of Water tank and Piping | To implement muririgua tan - construction of water tank and piping for access to clean water and environmental sustainability | Muririgua Tan - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1500000 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11046 | Water and Sewerage Management | Ndamu Tank - Construction of Water tank and Piping | To implement ndamu tank - construction of water tank and piping for access to clean water and environmental sustainability | Ndamu Tank - Construction of Water tank and Piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.570322, 36.095922 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1480515 | 123.4 | 1480515 | 19485 | -280515 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11047 | Water and Sewerage Management | Ndibai village - design and construction of water tank and water piping | To implement ndibai village - design and construction of water tank and water piping for access to clean water and environmental sustainability | Ndibai village - design and construction of water tank and water piping completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.553445 36.112768 2020.2 15 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1588887 | 132.4 | 1588887 | 6113 | -388887 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11048 | Water And Sewerage Management | Ngesha A water tank | To implement ngesha a water tank for access to clean water and environmental sustainability | Ngesha A water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.582928, 36.115417 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1979879.08 | 1979879.08 | 1979879.08 | Equitable | N/A | 1979879.08 | 0 | 1979879 | 100 | 1979879 | 998812 | 0.08 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11049 | Water and Sewerage Management | Njeru water tank | To implement njeru water tank for access to clean water and environmental sustainability | Njeru water tank completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.558886, 36.07641 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1998598 | 1998598 | 1998598 | Equitable | N/A | 1998598 | 0 | 1979879 | 99.1 | 1979879 | 1998598 | 18719 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
11050 | Water And Sewerage Management | Nyarienda Borehole - installation of solar panels and submersible water pump | To implement nyarienda borehole - installation of solar panels and submersible water pump for access to clean water and environmental sustainability | Nyarienda Borehole - installation of solar panels and submersible water pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.63291, 36.115567 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2000000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3398520 | 169.9 | 3398520 | 1480 | -1398520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Operational.
11051 | Water and Sewerage Management | Nyarienda - Kanorero water works | To implement nyarienda - kanorero water works for access to clean water and environmental sustainability | Nyarienda - Kanorero water works completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.633168 36.115234 2504.494 4.165999889373779 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2100000 | 0 | 2700000 | Equitable | N/A | 2700000 | 0 | 2699650 | 0 | 2699650 | 3300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs renovation.
11052 | Rerechua Borehole - Instalation of Solar Panel and Booster Pump | Rerechua Borehole - Instalation of Solar Panel and Booster Pump | To implement rerechua borehole - instalation of solar panel and booster pump for access to clean water and environmental sustainability | Rerechua Borehole - Instalation of Solar Panel and Booster Pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.563339 36.117975 1961.0999755859375 1.0069999694824219 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3697674 | 184.9 | 3697674 | 1480 | -1697674 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11053 | Water and Sewerage Management | Rerechua Water Project - Purchase of PPI pipes(3 inches) | To implement rerechua water project - purchase of ppi pipes(3 inches) for access to clean water and environmental sustainability | Rerechua Water Project - Purchase of PPI pipes(3 inches) completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.563372, 36.117994 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996788 | 99.8 | 1996788 | 0 | 3212 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11054 | Water And Sewerage Management | Settlement Borehole - installation of solar panel and purchase of submersible water pump | To implement settlement borehole - installation of solar panel and purchase of submersible water pump for access to clean water and environmental sustainability | Settlement Borehole - installation of solar panel and purchase of submersible water pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | ELEMENTAITA | -0.529775, 36.090549 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3398520 | 169.9 | 3398520 | 1480 | -1398520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Function.
11055 | Water and Sewerage Management | Sinking a borehole and pump of installation at Gilgil sub county Hospital | To implement sinking a borehole and pump of installation at gilgil sub county hospital for access to clean water and environmental sustainability | Sinking a borehole and pump of installation at Gilgil sub county Hospital completed | 3110502 | Water Supplies and Sewerage | GILGIL | GILGIL | -0.503559, 36.321536 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996302 | 99.8 | 1996302 | 3228677 | 3698 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: KASCOM ENTERPRISE. Assessor remarks: Functional but required piping to other areas within the hospital and the borehole was drilled by a donor the county did equipping..
11056 | Water And Sewerage Management | Installation of pump, repair of tank and piping and installation of Electricity at Nyamathi Water project | To install pump, repair of tank and piping and installation of Electricity at Nyamathi Water project | Pump, repair of tank and piping and installation of Electricity at Nyamathi Water project installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.779876, 36.519852 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 6999000 | 6999000 | 6999000 | Equitable | N/A | 6999000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 6,999,000.
11057 | Water And Sewerage Management | Mountain view water project drilling of borehole and installation of pump and piping | To implement mountain view water project drilling of borehole and installation of pump and piping for access to clean water and environmental sustainability | Mountain view water project drilling of borehole and installation of pump and piping completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.777377, 36.456881 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2321284 | 58 | 2321284 | 873268 | 1678716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole is still in use, few repairs from then have been made.
11058 | Water and Sewerage Management | Drilling of borehole at Mirera focus water project water project | To provide access to clean water through borehole drilling at Mirera focus water project water project | Borehole drilled at Mirera focus water project water project | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.837765, 36.55962 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2950064 | 98.3 | 2950064 | 3000000 | 49936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project cost 3,000,000.
11059 | Water And Sewerage Management | Installation of water pipes at Mwiciringiri water project | To install water pipes at Mwiciringiri water project | Water pipes at Mwiciringiri water project installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.807774 36.509428 2223.9853515625 29.85300064086914 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3999549.79 | 266.6 | 3999549.79 | 1821159 | -2499549.79 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: MERICH INTERNATIONAL LIMITED. Assessor remarks: The project was well done but it's not operational.
11060 | Water and Sewerage Management | Installation of water pumps and repair of existing wells at Mirera suswa | To install water pumps and repair of existing wells at Mirera suswa | Water pumps and repair of existing wells at Mirera suswa installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | HELLS GATE | -0.782138, 36.447091 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997737 | 99.9 | 2997737 | 1821159 | 2263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 3,000,000.
11061 | Water and Sewerage Management | County Water Works | To implement county water works for access to clean water and environmental sustainability | County Water Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 7143492.61 | 7143492.61 | 7143492.61 | N/A | N/A | 7143492.61 | 0 | 941663 | 13.2 | 941663 | 1696992 | 6201829.61 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11062 | Water And Sewerage Management | Equipping of Njoro Golf Club Kirima borehole | To equip Njoro Golf Club Kirima borehole with necessary facilities and equipment | Njoro Golf Club Kirima borehole equipped | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
11063 | Water and Sewerage Management | Grogon Water Works | To implement grogon water works for access to clean water and environmental sustainability | Grogon Water Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1253078.2 | 1253078.2 | 1253078.2 | N/A | N/A | 1253078.2 | 0 | 1253078 | 100 | 1253078 | 1253078 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11064 | Water and Sewerage Management | Litawa water project | To implement litawa water project for access to clean water and environmental sustainability | Litawa water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 8200000 | 8200000 | 8200000 | N/A | N/A | 8200000 | 0 | 4855031 | 59.2 | 4855031 | 499112 | 3344969 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11065 | Water and Sewerage Management | Mawalebo Water Project | To implement mawalebo water project for access to clean water and environmental sustainability | Mawalebo Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 1116806 | 22.3 | 1116806 | 916219 | 3883194 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11066 | Water and Sewerage Management | Morop Dam desilting | To implement morop dam desilting for access to clean water and environmental sustainability | Morop Dam desilting completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11067 | Water and Sewerage Management | Naivawass Works | To implement naivawass works for access to clean water and environmental sustainability | Naivawass Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 1750000 | 1750000 | N/A | N/A | 1750000 | 0 | 1750000 | 100 | 1750000 | 1750000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11068 | Water and Sewerage Management | Naruwasco Works | To implement naruwasco works for access to clean water and environmental sustainability | Naruwasco Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 1750000 | 70 | 1750000 | 2500000 | 750000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11069 | Water and Sewerage Management | Nawasco Works | To implement nawasco works for access to clean water and environmental sustainability | Nawasco Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 1750000 | 1750000 | N/A | N/A | 1750000 | 0 | 1750000 | 100 | 1750000 | 2500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11070 | Water and Sewerage Management | Nyondia water project | To implement nyondia water project for access to clean water and environmental sustainability | Nyondia water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 5161292 | 5161292 | 5161292 | N/A | N/A | 5161292 | 0 | 485466 | 9.4 | 485466 | 4675826 | 4675826 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11071 | Water and Sewerage Management | Other Developments | To implement other developments for access to clean water and environmental sustainability | Other Developments completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3135512 | 3135512 | 3135512 | N/A | N/A | 3135512 | 0 | 3115644 | 99.4 | 3115644 | 3728738 | 19868 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11072 | Water And Sewerage Management | Proposed BH Drilling at Karigi | To undertake the proposed BH Drilling at Karigi | Proposed BH Drilling at Karigi implemented | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2339910.24 | 2339910.24 | 2339910.24 | Equitable | N/A | 2339910.24 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
11073 | Water and Sewerage Management | Proposed Rerouting From Ngosur Intake And Mariru Storage Tank And Ex Railway | To undertake the proposed Rerouting From Ngosur Intake And Mariru Storage Tank And Ex Railway | Proposed Rerouting From Ngosur Intake And Mariru Storage Tank And Ex Railway implemented | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/2017 | 2015/2017 | 3794728.05 | 2414438.81 | 2414438.81 | N/A | N/A | 2414438.81 | 0 | 689594 | 28.6 | 689594 | 0 | 1724844.81 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11074 | Provision Of Water And Sewerage Services (Mawalebo Water Project) | Provision Of Water And Sewerage Services (Mawalebo Water Project) | To implement provision of water and sewerage services (mawalebo water project) for access to clean water and environmental sustainability | Provision Of Water And Sewerage Services (Mawalebo Water Project) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 4160283.4 | 4160283.4 | 4160283.4 | N/A | N/A | 4160283.4 | 0 | 0 | 0 | 0 | 4160283 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
11075 | Water And Sewerage Management | Quarry Water Project | To implement quarry water project for access to clean water and environmental sustainability | Quarry Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2471705.82 | 2471705.82 | 2471705.82 | Equitable | N/A | 2471705.82 | 0 | 4855031 | 196.4 | 4855031 | 499112 | -2383325.18 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11076 | Water and Sewerage Management | Rehabilitation Of Naruwassco Water Works | To rehabilitate Naruwassco Water Works to restore functionality | Naruwassco Water Works rehabilitated | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 945567.85 | 945567.85 | 945567.85 | N/A | N/A | 945567.85 | 0 | 2994378 | 316.7 | 2994378 | 945568 | -2048810.15 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11077 | Water and Sewerage Management | Sanitation Projects | To implement sanitation projects for access to clean water and environmental sustainability | Sanitation Projects completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 1936626 | 19.4 | 1936626 | 10000000 | 8063374 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11078 | Water And Sewerage Management | Supply of water at Gichobo | To implement supply of water at gichobo for access to clean water and environmental sustainability | Supply of water at Gichobo completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1439568 | 1439568 | 1439568 | Equitable | N/A | 1439568 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
11079 | Water and Sewerage Management | Construction of water tank of 100m3 diameter and piping of water at Thayu | To construct water tank of 100m3 diameter and piping of water at Thayu | Water tank of 100m3 diameter and piping of water at Thayu constructed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.188492, 36.170466 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 28 August 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1494013 | 99.6 | 1494013 | 1000000 | 5987 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Ms ridgerock enterprise. Assessor remarks: Initially the piping was to go up to thayu sublocation,the tank intake pipe is small it doesn't sustain their consumption.
11080 | Water and Sewerage Management | Expansion and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende | To expand and distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende to increase capacity | And distillation of Crater dam,Gozul dam; construction of water tank at wendo tank at UT public utility ground, Jonathan ground, Mariru ground ; piping of Thayu, Gatitu and Muchina farm water project, Rurii Moi Ndeffo and Kimende expanded | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.230755, 36.163102 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 10880000 | 8880000 | 8880000 | Equitable | N/A | 8880000 | 0 | 6661068 | 75 | 6661068 | 141927 | 2218932 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11081 | Water and Sewerage Management | Installation of Solar and piping at Kabatini borehole | To install Solar and piping at Kabatini borehole | Solar and piping at Kabatini borehole installed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.196066, 36.197552 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1841804 | 184.2 | 1841804 | 1841804 | -841804 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
11082 | Water And Sewerage Management | Piping of Jonathan borehole and installation of solar panels | To provide water distribution infrastructure at Jonathan borehole and installation of solar panels | Water piping at Jonathan borehole and installation of solar panels completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.230798 36.163034 2003.17626953125 8.472000122070312 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2500000 | 166.7 | 2500000 | 2500000 | -1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11083 | Water and Sewerage Management | piping of water from Thayu tank | To provide water distribution infrastructure at water from Thayu tank | Water piping at water from Thayu tank completed | 3110502 | Water Supplies and Sewerage | BAHATI | KABATINI | -0.188579 36.170613 2132.299560546875 11.930000305175781 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996394 | 99.8 | 1996394 | 1996394 | 3606 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
11084 | Water and Sewerage Management | Gitura water works | To implement gitura water works for access to clean water and environmental sustainability | Gitura water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.077916 36.171023 0 213.90570068359375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2547005 | 84.9 | 2547005 | 1165035 | 452995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Operationalized.
11085 | Water And Sewerage Management | Jumuia water projects drilling of borehole and installation of machines, pumps and solar panels | To implement jumuia water projects drilling of borehole and installation of machines, pumps and solar panels for access to clean water and environmental sustainability | Jumuia water projects drilling of borehole and installation of machines, pumps and solar panels completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.09011, 36.16711 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018/19 | 6130520 | 6130520 | 6130520 | Equitable | N/A | 6130520 | 0 | 0 | 0 | 0 | 7000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Atronach k ltd. Assessor remarks: Requires repairs and pipping.
11086 | Water and Sewerage Management | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward | To implement kabazi ward greening and beautitification - tree planting and beautification of kabazi ward for access to clean water and environmental sustainability | Kabazi ward greening and beautitification - tree planting and beautification of Kabazi ward completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 485500 | 48.5 | 485500 | 501021 | 514500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11087 | Water and Sewerage Management | Kabazi Ward water works - design and piping of Jumuia water project, construction of water tank and piping of Kabazi Rugongo water projects, water tanks at mutukanio A and Ime | To implement kabazi ward water works - design and piping of jumuia water project, construction of water tank and piping of kabazi rugongo water projects, water tanks at mutukanio a and ime for access to clean water and environmental sustainability | Kabazi Ward water works - design and piping of Jumuia water project, construction of water tank and piping of Kabazi Rugongo water projects, water tanks at mutukanio A and Ime completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.09011 36.16711 0 2117 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 9000000 | 9000000 | 9000000 | Equitable | N/A | 9000000 | 0 | 2006739 | 22.3 | 2006739 | 0 | 6993261 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated.
11088 | Water and Sewerage Management | Renovation of Kingochoch water tank | To rehabilitate Kingochoch water tank to restore functionality | Kingochoch water tank rehabilitated | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.158008 36.079218 1887.2 9 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 499210.64 | 499210.64 | 499210.64 | Equitable | N/A | 499210.64 | 0 | 2718933 | 544.6 | 2718933 | 499211 | -2219722.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
11089 | Water and Sewerage Management | construction of Kiawairi water project (intake. Storage tank and piping) | To construct Kiawairi water project (intake. Storage tank and piping) | Kiawairi water project (intake. Storage tank and piping) constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.09011 36.16711 0 2117 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997398 | 99.9 | 1997398 | 2000000 | 2602 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated.
11090 | Water and Sewerage Management | Kabazi water works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | KABAZI | -0.077902 36.17096 2259.4 11.899999618530273 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 6300000 | 6300000 | Equitable | N/A | 6300000 | 0 | 2547005 | 40.4 | 2547005 | 1165035 | 3752995 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
11091 | Water and Sewerage Management | Completion of Kamara water project | To complete Kamara water project | Kamara water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149131, 35.715047 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999697 | 100 | 1999697 | 1376603 | 303 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
11092 | Water and Sewerage Management | Completion of Mlima water project | To complete Mlima water project | Mlima water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149131, 35.715047 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 1376602.6 | 1376602.6 | 1376602.6 | Equitable | N/A | 1376602.6 | 0 | 1999697 | 145.3 | 1999697 | 1376603 | -623094.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
11093 | Water And Sewerage Management | Extension of piping at Mau summit water project | To expand piping at Mau summit water project to increase capacity | Piping at Mau summit water project expanded | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.172851, 35.678283 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1996470.2 | 1996470.2 | 1996470.2 | Equitable | N/A | 1996470.2 | 0 | 1976188.99 | 99 | 1976188.99 | 1376603 | 20281.21 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
11094 | Water and Sewerage Management | Haraka / kipseret water project - drilling and solar equiping kipseret water project | To implement haraka / kipseret water project - drilling and solar equiping kipseret water project for access to clean water and environmental sustainability | Haraka / kipseret water project - drilling and solar equiping kipseret water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.16308, 35.684305 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2399771 | 120 | 2399771 | 2000000 | -399771 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
11095 | Water and Sewerage Management | Kamara / Tarakwet water project - piping and construction of water tank | To implement kamara / tarakwet water project - piping and construction of water tank for access to clean water and environmental sustainability | Kamara / Tarakwet water project - piping and construction of water tank completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.21323 35.661657 2695.9 4.699999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3732679 | 93.3 | 3732679 | 1000000 | 267321 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
11096 | Water and Sewerage Management | mlima water project - piping of mlima water project | To implement mlima water project - piping of mlima water project for access to clean water and environmental sustainability | mlima water project - piping of mlima water project completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149078, 35.715007 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 2500000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399771 | 100 | 2399771 | 1376603 | 229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
11097 | Water and Sewerage Management | Piping and installation of a tank at Mau | To provide water distribution infrastructure at and installation of a tank at Mau | Water piping at and installation of a tank at Mau completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.160328 35.694146 2529.500244140625 64.0999984741211 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999077 | 100 | 2999077 | 429568 | 923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
11098 | Water and Sewerage Management | Protection and piping of Koige spring | To implement protection and piping of koige spring for access to clean water and environmental sustainability | Protection and piping of Koige spring completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.149078, 35.715007 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498201 | 99.9 | 1498201 | 2999995 | 1799 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
11099 | Water and Sewerage Management | Protection and piping of Sarambei spring | To implement protection and piping of sarambei spring for access to clean water and environmental sustainability | Protection and piping of Sarambei spring completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KAMARA | -0.097643, 35.68589 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 31/06/2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999995 | 100 | 2999995 | 2999995 | 5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
11100 | Water And Sewerage Management | Kapkures ward water works - Borehole drilling and equiping at kapkures maternity; piping of Ingobor community water project , purchase of complete water motor and water tank for mogoon borehole, and construction of a perimeter wall at Ingobor water project; Installation of a solar panel at Ingobor water project | To implement kapkures ward water works - borehole drilling and equiping at kapkures maternity; piping of ingobor community water project , purchase of complete water motor and water tank for mogoon borehole, and construction of a perimeter wall at ingobor water project; installation of a solar panel at ingobor water project for access to clean water and environmental sustainability | Kapkures ward water works - Borehole drilling and equiping at kapkures maternity; piping of Ingobor community water project , purchase of complete water motor and water tank for mogoon borehole, and construction of a perimeter wall at Ingobor water project; Installation of a solar panel at Ingobor water project completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
11101 | Water and Sewerage Management | Purchase of land and drilling of new Ingobor borehole and equipping | To acquire land for and drilling of new Ingobor borehole and equipping | Land for and drilling of new Ingobor borehole and equipping acquired | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2431841 | 48.6 | 2431841 | 5256 | 2568159 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operational.
11102 | Water and Sewerage Management | Drilling of borehole and piping at Tulwet | To provide access to clean water through borehole drilling at and piping at Tulwet | Borehole drilled at and piping at Tulwet | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.324324, 36.036613 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 1998494 | 57.1 | 1998494 | 1501506 | 1501506 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Collapsed during drilling.
11103 | Water and Sewerage Management | fencing of Tulwet borehole land | To secure Tulwet borehole land through fencing | Tulwet borehole land fenced and secured | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.324324 36.036613 0 2000 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 2924609 | 0 | 2924609 | 700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Security enhanced. Assessor remarks: Stone fencing done.
11104 | Water and Sewerage Management | Installation of pipes and water tank at Tachasis (Kapkures borehole) | To install pipes and water tank at Tachasis (Kapkures borehole) | Pipes and water tank at Tachasis (Kapkures borehole) installed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPKURES | -0.306306, 36.018533 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1898510 | 94.9 | 1898510 | 2000000 | 101490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
11105 | Water and Sewerage Management | Construction and renovation of 14 water kiosks across Kaptembwo Ward | To construct and renovation of 14 water kiosks across Kaptembwo Ward | And renovation of 14 water kiosks across Kaptembwo Ward constructed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPTEMBWO | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
11106 | Water and Sewerage Management | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks | To implement purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across kaptembwo ward, painting and branding of the kiosks for access to clean water and environmental sustainability | Purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across Kaptembwo Ward, painting and branding of the kiosks completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | KAPTEMBWO | -0.29996 36.051202 1804.199951171875 26.304000854492188 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 601180 | 0 | 601180 | 2398820 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
11107 | Water and Sewerage Management | Construction of water tank at Chebara | To construct water tank at Chebara | Water tank at Chebara constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.471803, 35.68375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 799008 | 99.9 | 799008 | 992 | 992 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
11108 | Water and Sewerage Management | Drilling of borehole at Silibwet | To provide access to clean water through borehole drilling at Silibwet | Borehole drilled at Silibwet | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.515322, 35.718285 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 627823 | 31.4 | 627823 | 627823 | 1372177 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pump failure.
11109 | Water and Sewerage Management | Extension of piping / Pump at Kapseger Borehole | To expand piping / Pump at Kapseger Borehole to increase capacity | Piping / Pump at Kapseger Borehole expanded | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KERINGET | -0.500082, 35.714228 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998665 | 99.9 | 1998665 | 500000 | 1335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
11110 | Piping extension at Menengai Water Project and St. Peters Primary Water Project | Piping extension at Menengai Water Project and St. Peters Primary Water Project | To provide water distribution infrastructure at extension at Menengai Water Project and St. Peters Primary Water Project | Water piping at extension at Menengai Water Project and St. Peters Primary Water Project completed | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.241438 36.138958 0 45.599998474121094 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000112 | 2000112 | 2000112 | Equitable | N/A | 2000112 | 0 | 1999596 | 100 | 1999596 | 516 | 516 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Not operating because of lack of water pump.
11111 | Water and Sewerage Management | Purchase of solar pumps, piping, equipment for water projects at Kiamaina ward | To procure solar pumps, piping, equipment for water projects at Kiamaina ward | Solar pumps, piping, equipment for water projects at Kiamaina ward procured | 3110502 | Water Supplies and Sewerage | BAHATI | KIAMAINA | -0.234598 36.103832 1939 3.4000000953674316 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9981591 | 99.8 | 9981591 | 0 | 18409 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete but no water on site.
11112 | Water and Sewerage Management | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project | To implement mutito a water project - drilling of borehole , construction of water tank and water kiosk and piping mutito a water project for access to clean water and environmental sustainability | Mutito A water project - drilling of borehole , construction of water tank and water kiosk and piping Mutito A water project completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.433157, 35.959162 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3145607 | 52.4 | 3145607 | 2854393 | 2854393 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires fencing.
11113 | Water and Sewerage Management | Lusiru water project - water priping for Lusiru water project | To implement lusiru water project - water priping for lusiru water project for access to clean water and environmental sustainability | Lusiru water project - water priping for Lusiru water project completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.498868 35.997912 2387.8 4.099999904632568 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2986993 | 99.6 | 2986993 | 188846 | 13007 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11114 | Water and Sewerage Management | Water works at stoo mbili | To implement water works at stoo mbili for access to clean water and environmental sustainability | Water works at stoo mbili completed | 3110502 | Water Supplies and Sewerage | NJORO | KIHINGO | -0.456623 35.981843 2308.8999999999996 6.599999904632568 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 151400 | 2.5 | 151400 | 151401 | 5848600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: More piping and connection.
11115 | Water and Sewerage Management | Construction of weir , water Tank and piping at Cheptuech - Irongo water project | To construct weir , water Tank and piping at Cheptuech - Irongo water project | Weir , water Tank and piping at Cheptuech - Irongo water project constructed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998496 | 100 | 3998496 | 4000000 | 1504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
11116 | Water and Sewerage Management | Oromoit water project construction of generator house | To implement oromoit water project construction of generator house for access to clean water and environmental sustainability | Oromoit water project construction of generator house completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.590645 35.59291 2486.400146484375 50.5 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 90 | N/A | Land Dispute | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functions.
11117 | Water and Sewerage Management | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project | To implement simatwet water project - design and construction of water tank, perimeter fence and piping of simatwet water project for access to clean water and environmental sustainability | Simatwet water project - Design and construction of water tank, perimeter fence and piping of simatwet water project completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | KIPTAGICH | -0.500035 35.714295 2648.1 6.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
11118 | Water and Sewerage Management | Construction of a water collection point at Kuresoi Centre | To construct a water collection point at Kuresoi Centre | A water collection point at Kuresoi Centre constructed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | KIPTORORO | -0.300932, 35.531763 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 2950807 | 1475.4 | 2950807 | 200000 | -2750807 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Due to stolen solar panel it's making it non functional.
11119 | Water and Sewerage Management | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks | To implement nakuru press estate - rehabilitation of kivumbini estate sewerage networks for access to clean water and environmental sustainability | Nakuru Press Estate - Rehabilitation of Kivumbini Estate Sewerage Networks completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | KIVUMBINI | -0.300433, 36.082496 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
11120 | Water and Sewerage Management | Rehabilitation of sewer line at Shauri Yako | To rehabilitate sewer line at Shauri Yako to restore functionality | Sewer line at Shauri Yako rehabilitated | 3110502 | Water Supplies and Sewerage | NAKURU EAST | KIVUMBINI | -0.298813, 36.081315 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3031776 | 75.8 | 3031776 | 4000000 | 968224 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sewerline.
11121 | Water and Sewerage Management | Drilling and equipping boreholes at Milimani and Unity primary school | To implement drilling and equipping boreholes at milimani and unity primary school for access to clean water and environmental sustainability | Drilling and equipping boreholes at Milimani and Unity primary school completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | LAKE VIEW | -0.720739, 36.43967 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: High flouride levels, water not safe for drinking.
11122 | Water and Sewerage Management | Lanet Umoja Water Works | To implement lanet umoja water works for access to clean water and environmental sustainability | Lanet Umoja Water Works completed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.235204, 36.165713 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1125737.92 | 1125737.92 | 1125737.92 | Equitable | N/A | 1125737.92 | 0 | 1113059 | 98.9 | 1113059 | 1500001 | 12678.92 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11123 | Water And Sewerage Management | Proposed Baraka WP in Lanet Umoja | To undertake the proposed Baraka WP in Lanet Umoja | Proposed Baraka WP in Lanet Umoja implemented | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.262468, 36.150582 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2095145.6 | 2095145.6 | 2095145.6 | Equitable | N/A | 2095145.6 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
11124 | Water And Sewerage Management | Proposed Modern CWP in Lanet Umoja | To undertake the proposed Modern CWP in Lanet Umoja | Proposed Modern CWP in Lanet Umoja implemented | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.28217, 36.1556 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2439206.24 | 2439206.24 | 2439206.24 | Equitable | N/A | 2439206.24 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11125 | Water and Sewerage Management | Installation of pump and purchase of 10000 litres of water tank at baraka | To install pump and purchase of 10000 litres of water tank at baraka | Pump and purchase of 10000 litres of water tank at baraka installed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.282202, 36.155693 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3993388 | 99.8 | 3993388 | 340755 | 6612 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11126 | Water and Sewerage Management | Installation of pump and purchase of 10000 litres water tank at modern | To install pump and purchase of 10000 litres water tank at modern | Pump and purchase of 10000 litres water tank at modern installed | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.282202, 36.155693 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1529199 | 38.2 | 1529199 | 340755 | 2470801 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11127 | Water and Sewerage Management | Repair of 2 water tanks in Kiamunyeki | To rehabilitate 2 water tanks in Kiamunyeki to restore functionality | 2 water tanks in Kiamunyeki rehabilitated | 3110502 | Water Supplies and Sewerage | BAHATI | LANET UMOJA | -0.283645, 36.150508 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1995900 | 99.8 | 1995900 | 4100 | 4100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but the repaired tank is not functional due to leakages.
11128 | Water And Sewerage Management | Lare Center - piping Water to Lare Center | To implement lare center - piping water to lare center for access to clean water and environmental sustainability | Lare Center - piping Water to Lare Center completed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.444369 36.012939 2058.2001953125 45.599998474121094 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to be secured with a fence.
11129 | Water and Sewerage Management | Nganoini Naishi game water project - piping of water from Kihingo - mutiume to Nganoini naishi game | To implement nganoini naishi game water project - piping of water from kihingo - mutiume to nganoini naishi game for access to clean water and environmental sustainability | Nganoini Naishi game water project - piping of water from Kihingo - mutiume to Nganoini naishi game completed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.423142, 36.038682 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3374605 | 99.3 | 3374605 | 0 | 25395 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
11130 | Water and Sewerage Management | Installation of pipes at Bagaria | To install pipes at Bagaria | Pipes at Bagaria installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.479368, 36.052937 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498845 | 100 | 2498845 | 54100 | 1155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need electricity connection and the project taken over NARUWASCO.
11131 | Water and Sewerage Management | Installation of pipes at Karogoe mugumo | To install pipes at Karogoe mugumo | Pipes at Karogoe mugumo installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.46423, 36.044957 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2445900 | 97.8 | 2445900 | 54100 | 54100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
11132 | Water and Sewerage Management | Installation of pipes at lower zone block 3 | To install pipes at lower zone block 3 | Pipes at lower zone block 3 installed | 3110502 | Water Supplies and Sewerage | NJORO | LARE | -0.46423, 36.044957 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499279 | 100 | 2499279 | 54100 | 721 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
11133 | Water and Sewerage Management | Extension piping network in London and milimani apartments | To expand piping network in London and milimani apartments to increase capacity | Piping network in London and milimani apartments expanded | 3110502 | Water Supplies and Sewerage | NAKURU WEST | LONDON | -0.274103 36.054114 1880.728105673961 24 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3500000 | 5358649 | 5358649 | Equitable | N/A | 5358649 | 0 | 4770829 | 89 | 4770829 | 587820 | 587820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
11134 | Water And Sewerage Management | Completion and piping of Kijabe water project | To complete and piping of Kijabe water project | And piping of Kijabe water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 996724 | 996724 | 996724 | Equitable | N/A | 996724 | 0 | 3279350 | 329 | 3279350 | 1699581.37 | -2282626 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11135 | Water And Sewerage Management | Completion and piping of Longonot water project | To complete and piping of Longonot water project | And piping of Longonot water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1990573.43 | 1990573.43 | 1990573.43 | Equitable | N/A | 1990573.43 | 0 | 3279350 | 164.7 | 3279350 | 1699581.37 | -1288776.57 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11136 | Water And Sewerage Management | Completion and piping of Maai - Mahiu water project | To complete and piping of Maai - Mahiu water project | And piping of Maai - Mahiu water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1995110 | 1995110 | 1995110 | Equitable | N/A | 1995110 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11137 | Water And Sewerage Management | Completion of Satellite water project | To complete Satellite water project | Satellite water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1990456.4 | 1990456.4 | 1990456.4 | Equitable | N/A | 1990456.4 | 0 | 3279350 | 164.8 | 3279350 | 1699581.37 | -1288893.6 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11138 | Water and Sewerage Management | design and construction of Kijabe water intake ( monkey conrner) | To design and construct Kijabe water intake ( monkey conrner) | Kijabe water intake ( monkey conrner) designed and constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000001 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11139 | Longonot water project Phase 2(Pipe work and construction of water kiosk) | Longonot water project Phase 2(Pipe work and construction of water kiosk) | To implement longonot water project phase 2(pipe work and construction of water kiosk) for access to clean water and environmental sustainability | Longonot water project Phase 2(Pipe work and construction of water kiosk) completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1699581.37 | 1699581.37 | 1699581.37 | Equitable | N/A | 1699581.37 | 0 | 13454643 | 791.6 | 13454643 | 14000000 | -11755061.63 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
11140 | Water And Sewerage Management | Longonot water project (piping) | To implement longonot water project (piping) for access to clean water and environmental sustainability | Longonot water project (piping) completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | N/A | 920650 | 920650 | 920650 | Equitable | N/A | 920650 | 0 | 3279350 | 356.2 | 3279350 | 1699581.37 | -2358700 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11141 | Water And Sewerage Management | Longonot water project | To implement longonot water project for access to clean water and environmental sustainability | Longonot water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1279350 | 1279350 | 1279350 | Equitable | N/A | 1279350 | 0 | 3279350 | 256.3 | 3279350 | 1699581.37 | -2000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11142 | Water and Sewerage Management | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project | To implement maai mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; karima water project, githima water project, longonot water project, gichungu water project, satelite water project, vumilia camp water project, ruiru water project and car wash association water project for access to clean water and environmental sustainability | Maai Mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; Karima water project, Githima water project, Longonot water project, Gichungu water project, satelite water project, Vumilia camp water project, Ruiru water project and car wash association water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | -1.007345, 36.534153 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 11000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 889299 | 8.9 | 889299 | 1203066 | 9110701 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: Needs to be made operational.
11143 | Water and Sewerage Management | Longonot water works | To implement longonot water works for access to clean water and environmental sustainability | Longonot water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | -0.890168, 36.496111 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 9000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3279350 | 54.7 | 3279350 | 6000000 | 2720650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete/water at tap.
11144 | Water and Sewerage Management | Maai Mahiu water works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu water works completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAAI MAHIU | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2176522 | 54.4 | 2176522 | 8318914 | 1823478 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11145 | Water and Sewerage Management | Installation of water pump at Tangi Tatu Water Project | To install water pump at Tangi Tatu Water Project | Water pump at Tangi Tatu Water Project installed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.796872 36.250812 1882.2 6.900000095367432 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 695072 | 695072 | 695072 | Equitable | N/A | 695072 | 0 | 657778 | 94.6 | 657778 | 695072 | 37294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
11146 | Water and Sewerage Management | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi | To implement maella ward water works - drilling, construction and piping of adc manyatta jikaze borehole: installation of a water tank at ngondi for access to clean water and environmental sustainability | Maella Ward water works - Drilling, construction and piping of ADC Manyatta jikaze borehole: installation of a water tank at Ngondi completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 9300000 | 9300000 | 9300000 | Equitable | N/A | 9300000 | 0 | 4959574 | 53.3 | 4959574 | 22738 | 4340426 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11147 | Water and Sewerage Management | Construction of a water reservoir and pipe work in Upper Maiella | To construct a water reservoir and pipe work in Upper Maiella | A water reservoir and pipe work in Upper Maiella constructed | 3110502 | Water Supplies and Sewerage | NAIVASHA | MAIELLA | -0.889533, 36.198517 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 313361 | 6.3 | 313361 | 313361 | 4686639 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Not Operation...Defunct project.
11148 | Water and Sewerage Management | Drilling of borehole at Tarambete | To provide access to clean water through borehole drilling at Tarambete | Borehole drilled at Tarambete | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.324324, 36.054632 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 1250000 | 1250000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2069602 | 165.6 | 2069602 | 1459354 | -819602 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11149 | Water And Sewerage Management | Kasarani Dumpsite Fencing and leveling | To implement kasarani dumpsite fencing and leveling for access to clean water and environmental sustainability | Kasarani Dumpsite Fencing and leveling completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703 36.291018 0 2000 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need continous improvements.
11150 | Water and Sewerage Management | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump | To implement malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of gatamaiyu, kwa njonjo, nyondia and karati centre boreholes and kasarani solar water pump for access to clean water and environmental sustainability | Malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of Gatamaiyu, Kwa Njonjo, Nyondia and Karati centre boreholes and kasarani solar water pump completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703, 36.471211 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 3099636 | 15.5 | 3099636 | 459053 | 16900364 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well maintained.
11151 | Water and Sewerage Management | Piping and purchase of 3 water tank for Gathengera water project | To provide water distribution infrastructure at and purchase of 3 water tank for Gathengera water project | Water piping at and purchase of 3 water tank for Gathengera water project completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.774775 36.417744 0 5099.9990234375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199987 | 100 | 1199987 | 417 | 13 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11152 | Water and Sewerage Management | Purchase of 10000 litres water tank for Corner Nyondia water project and Construction of tank stand | To procure 10000 litres water tank for Corner Nyondia water project and Construction of tank stand | 10000 litres water tank for Corner Nyondia water project and Construction of tank stand procured | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.774775 36.417744 0 5099.9990234375 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 288660 | 82.5 | 288660 | 417 | 61340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11153 | Water and Sewerage Management | purchase of land for borehole at Tarambete | To acquire land for borehole at Tarambete | Land for borehole at Tarambete acquired | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.684685, 36.471073 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2024/25 | 1250001 | 0 | 1650000 | Equitable | N/A | 1650000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11154 | Water and Sewerage Management | purchase of land for Green valley water project | To acquire land for Green valley water project | Land for Green valley water project acquired | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.695009, 36.48094 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 599999 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 699583 | 0 | 699583 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11155 | Water and Sewerage Management | Mugumoini Bore Hole(Pipe network) | To implement mugumoini bore hole(pipe network) for access to clean water and environmental sustainability | Mugumoini Bore Hole(Pipe network) completed | 3110502 | Water Supplies and Sewerage | GILGIL | MALEWA WEST | -0.702703 36.471211 0 2000 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2014/15 | 2014/15 | 2014/15 | 4620000 | 4607332 | 4607332 | Equitable | N/A | 4607332 | 0 | 2990874 | 64.9 | 2990874 | 3308420 | 1616458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
11156 | Water and Sewerage Management | Kiplelmoi water project - laying of pipes and repairing of water intake | To implement kiplelmoi water project - laying of pipes and repairing of water intake for access to clean water and environmental sustainability | Kiplelmoi water project - laying of pipes and repairing of water intake completed | 3110502 | Water Supplies and Sewerage | MOLO | MARIOSHONI | -0.342099, 35.849298 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Water supply okay.
11157 | Water and Sewerage Management | Drilling and equipping of borehole, at Majimingi | To implement drilling and equipping of borehole, at majimingi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Majimingi completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
11158 | Water and Sewerage Management | Drilling and equipping of borehole, at Mukungugu | To implement drilling and equipping of borehole, at mukungugu for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Mukungugu completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
11159 | Water and Sewerage Management | Drilling and equipping of borehole, at Nyakiambi | To implement drilling and equipping of borehole, at nyakiambi for access to clean water and environmental sustainability | Drilling and equipping of borehole, at Nyakiambi completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.601445, 36.011229 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2144654 | 85.8 | 2144654 | 354073 | 355346 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
11160 | Water And Sewerage Management | Drilling of borehole at Mutukanio B | To provide access to clean water through borehole drilling at Mutukanio B | Borehole drilled at Mutukanio B | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -0.60628, 36.008692 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 799565 | 40 | 799565 | 1894 | 1200435 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need solar.
11161 | Water and Sewerage Management | Installation of pipes at Segutiet Borehole | To install pipes at Segutiet Borehole | Pipes at Segutiet Borehole installed | 3110502 | Water Supplies and Sewerage | NJORO | MAU NAROK | -1.2841 36.8155 0 83800 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998959 | 99.9 | 998959 | 1041 | 1041 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
11162 | Water and Sewerage Management | Kianjoya Dam - Construction of dam | To implement kianjoya dam - construction of dam for access to clean water and environmental sustainability | Kianjoya Dam - Construction of dam completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | -0.544487, 36.059952 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1070378 | 97.3 | 1070378 | 29622 | 29622 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not in use.
11163 | Water and Sewerage Management | Likia borehole equipping - equipping, installation of water pump and replacing of pipes for Likia borehole | To implement likia borehole equipping - equipping, installation of water pump and replacing of pipes for likia borehole for access to clean water and environmental sustainability | Likia borehole equipping - equipping, installation of water pump and replacing of pipes for Likia borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990000 | 99.5 | 1990000 | 0 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11164 | Water and Sewerage Management | Metta Water Project - Construction/completion/operationalization | To implement metta water project - construction/completion/operationalization for access to clean water and environmental sustainability | Metta Water Project - Construction/completion/operationalization completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | -0.580995, 36.032157 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2861816 | 95.4 | 2861816 | 138183 | 138184 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need extra piping.
11165 | Water and Sewerage Management | Mutukanio B borehole Drilling | To implement mutukanio b borehole drilling for access to clean water and environmental sustainability | Mutukanio B borehole Drilling completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | -0.59713, 35.996263 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 670248 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Assessor remarks: Projected stalled.
11166 | Water and Sewerage Management | Mutukanio Dam - desilting and Construction of Mutukanio Dam | To implement mutukanio dam - desilting and construction of mutukanio dam for access to clean water and environmental sustainability | Mutukanio Dam - desilting and Construction of Mutukanio Dam completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | -0.597373, 35.998823 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499353 | 99.9 | 499353 | 499353 | 647 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need fencing.
11167 | Water and Sewerage Management | Nyakiambi Borehole Drilling | To implement nyakiambi borehole drilling for access to clean water and environmental sustainability | Nyakiambi Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | NJORO | MAU-NAROK | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1329752 | 66.5 | 1329752 | 670248 | 670248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11168 | Water and Sewerage Management | Building of Tank and piping at Kaptich water project | To implement building of tank and piping at kaptich water project for access to clean water and environmental sustainability | Building of Tank and piping at Kaptich water project completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.565457, 36.036751 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019 | 2848617 | 2848617 | 2848617 | Equitable | N/A | 2848617 | 0 | 3436946 | 120.7 | 3436946 | 2848617 | -588329 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not. Assessor remarks: Needs improvement.
11169 | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | Construction of a weir wall for gravity water flow and buying of pipes at Teret sub location water project | To construct a weir wall for gravity water flow and buying of pipes at Teret sub location water project | A weir wall for gravity water flow and buying of pipes at Teret sub location water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.465378, 35.952084 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 1939139.97 | 3939139.97 | 3939139.97 | Equitable | N/A | 3939139.97 | 0 | 1999993 | 50.8 | 1999993 | 7 | 1939146.97 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
11170 | Water And Sewerage Management | Kaptich water project | To implement kaptich water project for access to clean water and environmental sustainability | Kaptich water project completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.517562 35.973678 2471 8.399999618530273 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2861233 | 95.4 | 2861233 | 238767 | 138767 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good.
11171 | Water and Sewerage Management | Tachasis community water project - design and Construction of Tachasis community water project- piping | To implement tachasis community water project - design and construction of tachasis community water project- piping for access to clean water and environmental sustainability | Tachasis community water project - design and Construction of Tachasis community water project- piping completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.530473, 35.949265 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2014 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
11172 | Tegunot / Siryat water project piping of water | Tegunot / Siryat water project piping of water | To implement tegunot / siryat water project piping of water for access to clean water and environmental sustainability | Tegunot / Siryat water project piping of water completed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.501963 35.980358 2388.7999999999997 13.699999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 499937 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
11173 | Water and Sewerage Management | construction of water tank and piping work at Kaptich water project | To construct water tank and piping work at Kaptich water project | Water tank and piping work at Kaptich water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.539043, 36.016872 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3436946 | 85.9 | 3436946 | 563054 | 563054 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
11174 | Water and Sewerage Management | construction of water tank and piping work at Tulyotich community water project | To construct water tank and piping work at Tulyotich community water project | Water tank and piping work at Tulyotich community water project constructed | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.539043, 36.016872 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3436946 | 85.9 | 3436946 | 4000000 | 563054 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
11175 | Water and Sewerage Management | drilling of borehole at kamunget | To provide access to clean water through borehole drilling at kamunget | Borehole drilled at kamunget | 3110502 | Water Supplies and Sewerage | NJORO | MAUCHE | -0.568588, 36.034408 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs piping.
11176 | Water and Sewerage Management | Menengai ward water piping and sewer - piping of Kiratina, Teachers, Nyamarutu and Nguta / Mireri estate in Menengai Ward and sewer at Bismack | To implement menengai ward water piping and sewer - piping of kiratina, teachers, nyamarutu and nguta / mireri estate in menengai ward and sewer at bismack for access to clean water and environmental sustainability | Menengai ward water piping and sewer - piping of Kiratina, Teachers, Nyamarutu and Nguta / Mireri estate in Menengai Ward and sewer at Bismack completed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | MENENGAI | -0.274763 36.113326 1858.4000244140625 8.986000061035156 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2432541 | 97.3 | 2432541 | 0 | 67459 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11177 | Water and Sewerage Management | Ol Rongai water works and piping - piping of Ol Rongai water project | To implement ol rongai water works and piping - piping of ol rongai water project for access to clean water and environmental sustainability | Ol Rongai water works and piping - piping of Ol Rongai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MENENGAI WEST | -0.146435 36.009523 1826 13.850000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999709 | 100 | 3999709 | 3999709 | 291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
11178 | Water and Sewerage Management | Rehabilitation Mercy Njeri tank | To rehabilitate Mercy Njeri tank to restore functionality | Mercy Njeri tank rehabilitated | 3110502 | Water Supplies and Sewerage | RONGAI | MENENGAI WEST | -0.150263 36.010846 1900.199951171875 123.6719970703125 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1858667 | 103.3 | 1858667 | 1800000 | -58667 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11179 | Water And Sewerage Management | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project | To implement rehabiltation works at maishani area and mutiruthia; extension of piping at tayari water project and kiambogo water project for access to clean water and environmental sustainability | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO | -0.23299, 35.704347 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2023/24 | 2601108.39 | 2601108.39 | 2601108.39 | Equitable | N/A | 2601108.39 | 0 | 2596033 | 99.8 | 2596033 | 0 | 5075.39 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11180 | Water and Sewerage Management | Molo Dumping site | To implement molo dumping site for access to clean water and environmental sustainability | Molo Dumping site completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11181 | Water and Sewerage Management | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project | To implement rehabiltation works at maishani area and mutiruthia; extension of piping at tayari water project and kiambogo water project for access to clean water and environmental sustainability | Rehabiltation Works at Maishani Area and Mutiruthia; Extension of Piping at Tayari Water Project and Kiambogo Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | MOLO CENTRAL | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2098891.61 | 2098891.61 | 2098891.61 | Equitable | N/A | 2098891.61 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
11182 | Water and Sewerage Management | Boror Nairobi water projects - purchase and laying of water pipes | To implement boror nairobi water projects - purchase and laying of water pipes for access to clean water and environmental sustainability | Boror Nairobi water projects - purchase and laying of water pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 0 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 2002493 | 0 | 2002493 | 2002493 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11183 | Water and Sewerage Management | Chelele water project - construction of 50m3 tank and laying of pipes | To implement chelele water project - construction of 50m3 tank and laying of pipes for access to clean water and environmental sustainability | Chelele water project - construction of 50m3 tank and laying of pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.215495 35.822015 1909.6000000000001 23.200000762939453 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 14000003 | 0 | 3900000 | Equitable | N/A | 3900000 | 0 | 3900000 | 0 | 3900000 | 55200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kina investment. Assessor remarks: Good work.
11184 | Water and Sewerage Management | Chepseon water project- laying of pipes | To implement chepseon water project- laying of pipes for access to clean water and environmental sustainability | Chepseon water project- laying of pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.236822 35.826233 1903.300048828125 5.300000190734863 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 14000004 | 0 | 3100000 | Equitable | N/A | 3100000 | 0 | 2997208 | 0 | 2997208 | 55200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11185 | Water and Sewerage Management | Keriko water project - purchase and laying of water pipes | To implement keriko water project - purchase and laying of water pipes for access to clean water and environmental sustainability | Keriko water project - purchase and laying of water pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 625000 | 625000 | 625000 | Equitable | N/A | 625000 | 0 | 624344 | 99.9 | 624344 | 2002493 | 656 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11186 | Water and Sewerage Management | Kerma borehole - purchase and installation of pump and water piping | To implement kerma borehole - purchase and installation of pump and water piping for access to clean water and environmental sustainability | Kerma borehole - purchase and installation of pump and water piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.314718, 35.970947 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2479575 | 99.2 | 2479575 | 2500000 | 20425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Marileon. Assessor remarks: Good.
11187 | Water and Sewerage Management | Lelechwet water tank - construction of 200m3 water tank and pipes | To implement lelechwet water tank - construction of 200m3 water tank and pipes for access to clean water and environmental sustainability | Lelechwet water tank - construction of 200m3 water tank and pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2024 | 14000002 | 0 | 3900000 | Equitable | N/A | 3900000 | 0 | 1231519 | 0 | 1231519 | 1231519 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11188 | Water and Sewerage Management | Mbama Intake project - intake works | To implement mbama intake project - intake works for access to clean water and environmental sustainability | Mbama Intake project - intake works completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.21216, 35.816242 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 14000001 | 0 | 3100000 | Equitable | N/A | 3100000 | 0 | 1356326 | 0 | 1356326 | 30825 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Contractor: Roy n alvis. Assessor remarks: Stalled.
11189 | Water and Sewerage Management | Ndusu / Rigogo / Sumeek - construction of intake and piping | To implement ndusu / rigogo / sumeek - construction of intake and piping for access to clean water and environmental sustainability | Ndusu / Rigogo / Sumeek - construction of intake and piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | 2024 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3663643 | 91.6 | 3663643 | 0 | 336357 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11190 | Water and Sewerage Management | Waldai water projects works - intake and pipes | To implement waldai water projects works - intake and pipes for access to clean water and environmental sustainability | Waldai water projects works - intake and pipes completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.23233, 35.837018 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 0 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498800 | 0 | 1498800 | 2002493 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11191 | Water and Sewerage Management | Construction of Ngondu Water tank | To construct Ngondu Water tank | Ngondu Water tank constructed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.248192, 35.808833 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1202617 | 80.2 | 1202617 | 1998043 | 297383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
11192 | Water and Sewerage Management | Piping of Sumeek water project | To provide water distribution infrastructure at Sumeek water project | Water piping at Sumeek water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | MOSOP | -0.318548, 35.973835 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | To be vired | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495931 | 99.8 | 2495931 | 4069 | 4069 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
11193 | Water and Sewerage Management | Ihindu water project installation of solar panels | To implement ihindu water project installation of solar panels for access to clean water and environmental sustainability | Ihindu water project installation of solar panels completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.842147, 36.561961 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1522836 | 76.1 | 1522836 | 2000000 | 477164 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project was not done.
11194 | Water And Sewerage Management | Drilling of borehole, installation of water tanks, pump and piping at Sosioni water project | To implement drilling of borehole, installation of water tanks, pump and piping at sosioni water project for access to clean water and environmental sustainability | Drilling of borehole, installation of water tanks, pump and piping at Sosioni water project completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | -0.883081, 36.565678 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020-21 | 3200000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 319308 | 10 | 319308 | 319308 | 2880692 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: 2022. Assessor remarks: Good project fully operational.
11195 | Water And Sewerage Management | Naivasha East Ward water works - Purchase of land for a Borehole; drilling of borehole; construction and piping of water tanks at Magumu; Sision primary school and Ruwanyaga and piping; | To implement naivasha east ward water works - purchase of land for a borehole; drilling of borehole; construction and piping of water tanks at magumu; sision primary school and ruwanyaga and piping; for access to clean water and environmental sustainability | Naivasha East Ward water works - Purchase of land for a Borehole; drilling of borehole; construction and piping of water tanks at Magumu; Sision primary school and Ruwanyaga and piping; completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | NAIVASHA EAST | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
11196 | Water And Sewerage Management | Installation of water pipes in Naka, free Area, Mwariki, and Mzee Wanyama | To install water pipes in Naka, free Area, Mwariki, and Mzee Wanyama | Water pipes in Naka, free Area, Mwariki, and Mzee Wanyama installed | 3110502 | Water Supplies and Sewerage | NAKURU EAST | NAKURU EAST | -0.369888, 36.149362 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Pipes disconnected.
11197 | Water And Sewerage Management | Cheptoroi borehole installation of pump and construction of water tank and piping | To implement cheptoroi borehole installation of pump and construction of water tank and piping for access to clean water and environmental sustainability | Cheptoroi borehole installation of pump and construction of water tank and piping completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.368773, 35.897801 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1851471 | 92.6 | 1851471 | 148529 | 148529 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Pump has never been installed.
11198 | Water and Sewerage Management | Construction of weir intake and fencing of Kware springs and Tarakwet spring | To construct weir intake and fencing of Kware springs and Tarakwet spring | Weir intake and fencing of Kware springs and Tarakwet spring constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.37894, 35.898381 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499867 | 100 | 499867 | 133 | 133 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was vandalized and human encroachment led to cutting of trees and volume of water has reduced..
11199 | Water and Sewerage Management | Takitech borehole piping and construction of water kiosks | To implement takitech borehole piping and construction of water kiosks for access to clean water and environmental sustainability | Takitech borehole piping and construction of water kiosks completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.424694, 35.92853 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1878095 | 93.9 | 1878095 | 2000000 | 121905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds were used to construct 50M³ masonry water tank at Ruto's residence and piping done from the borehole to the water tank.
11200 | Water and Sewerage Management | Takitech borehole | To implement takitech borehole for access to clean water and environmental sustainability | Takitech borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.433936 35.919127 2591.218994140625 3.7899999618530273 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5913775 | 98.6 | 5913775 | 4021803 | 86225 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds drilled borehole, constructed control panel, 100,000 litre water tank and water kiosk..
11201 | Water And Sewerage Management | construction of Tuwei water tank and piping | To construct Tuwei water tank and piping | Tuwei water tank and piping constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.410121 35.870639 2595.9511054621485 3.7899999618530273 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 1554958 | 172.8 | 1554958 | 1100000 | -654958 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: SADDABRI PROPERTIES KENYA LIMITED. Assessor remarks: The tank constructed was 50,000 litres instead of 100,000 due to insufficient funds compared to the scope of work indicated. Piping was done from the borehole to the tank about 300 meters to the neighboring households. The intended objective of supplying water across Nessuit ward not fullt met since the piping hasn't been done to completion to serve the entire ward..
11202 | Water and Sewerage Management | design and construction of Tagitech water kiosk and piping | To design and construct Tagitech water kiosk and piping | Tagitech water kiosk and piping designed and constructed | 3110502 | Water Supplies and Sewerage | NJORO | NESSUIT | -0.356677 35.883444 2389.259997959072 5.46999979019165 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4600000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1851471 | 168.3 | 1851471 | 1100000 | -751471 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
11203 | Water and Sewerage Management | Drilling and equipping of Jordan borehole | To implement drilling and equipping of jordan borehole for access to clean water and environmental sustainability | Drilling and equipping of Jordan borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.288202, 35.87854 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2025 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1843027 | 41 | 1843027 | 1872774 | 2656973 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Not available. Assessor remarks: Only drilling and lining done.
11204 | Water and Sewerage Management | Drilling and equipping of Njoro police post borehole | To implement drilling and equipping of njoro police post borehole for access to clean water and environmental sustainability | Drilling and equipping of Njoro police post borehole completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.331744, 35.945973 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2649576 | 53 | 2649576 | 1350424 | 2350424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprise. Assessor remarks: Complete awaiting Jewathu piping.
11205 | Water and Sewerage Management | Equipping and piping of Njokerio Borehole | To equip and piping of Njokerio Borehole with necessary facilities and equipment | And piping of Njokerio Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 611390 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
11206 | Water and Sewerage Management | Equipping of Natu Borehole | To equip Natu Borehole with necessary facilities and equipment | Natu Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.338884, 36.004589 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 305611 | 23.5 | 305611 | 305611 | 994389 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Trizah logistics. Assessor remarks: In good state.
11207 | Water and Sewerage Management | Equipping of Piave Borehole | To equip Piave Borehole with necessary facilities and equipment | Piave Borehole equipped | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.336684, 35.995746 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1298950 | 99.9 | 1298950 | 1298950 | 1050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprises. Assessor remarks: Good work.
11208 | Water and Sewerage Management | Kamwayo Water Project - Piping of kamwayo water project | To implement kamwayo water project - piping of kamwayo water project for access to clean water and environmental sustainability | Kamwayo Water Project - Piping of kamwayo water project completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.296612 35.883503 2158.858642578125 11.8100004196167 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998568 | 99.9 | 1998568 | 1433 | 1432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
11209 | Water And Sewerage Management | Njoro Golf Phase 1 - Drilling, Equiping,Pump, Electricity House and Electricity House | To implement njoro golf phase 1 - drilling, equiping,pump, electricity house and electricity house for access to clean water and environmental sustainability | Njoro Golf Phase 1 - Drilling, Equiping,Pump, Electricity House and Electricity House completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.338368 35.946329 2148.10009765625 100 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 8600000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Ongoing. Contractor: BFC enterprises. Assessor remarks: Progressing well.
11210 | Water and Sewerage Management | Piave water project | To implement piave water project for access to clean water and environmental sustainability | Piave water project completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.332133, 35.945717 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999325 | 100 | 2999325 | 1000000 | 675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Live World Enterprise. Assessor remarks: Work incomplete.
11211 | Water and Sewerage Management | water piping at Eriithia borehole, Mwigito , Njokerio and Mwihoti water projects | To implement water piping at eriithia borehole, mwigito , njokerio and mwihoti water projects for access to clean water and environmental sustainability | water piping at Eriithia borehole, Mwigito , Njokerio and Mwihoti water projects completed | 3110502 | Water Supplies and Sewerage | NJORO | NJORO | -0.394635, 35.922432 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2014 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Fair work.
11212 | Water and Sewerage Management | Kuresoi Water Project - Drilling of Borehole | To implement kuresoi water project - drilling of borehole for access to clean water and environmental sustainability | Kuresoi Water Project - Drilling of Borehole completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | -0.41092 35.65578 2673.7 19 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1500000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 2235726 | 203.2 | 2235726 | 1100000 | -1135726 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good. Pump needs repairs..
11213 | Water and Sewerage Management | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) | To implement ongoing temoyotta water project pumping unit, pump house, tank renovation piping and power connection) for access to clean water and environmental sustainability | Ongoing Temoyotta Water Project Pumping unit, pump house, tank renovation piping and power connection) completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | NYOTA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2479793.48 | 2479793.48 | 2479793.48 | Equitable | N/A | 2479793.48 | 0 | 0 | 0 | 0 | 2479793 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11214 | Water And Sewerage Management | Kamere Centre Refuse disposal Points (Construction/dust bins purchase) | To implement kamere centre refuse disposal points (construction/dust bins purchase) for access to clean water and environmental sustainability | Kamere Centre Refuse disposal Points (Construction/dust bins purchase) completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | -0.816569 36.323666 1881.300048828125 7.736999988555908 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1499940.27 | 1499940.27 | 1499940.27 | Equitable | N/A | 1499940.27 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational since mentainance us beenn done.
11215 | Water and Sewerage Management | Olkaria Waste Management Plan - Purchase and installation of of waste disposal bins at Kwa muhia and Kamere beach | To implement olkaria waste management plan - purchase and installation of of waste disposal bins at kwa muhia and kamere beach for access to clean water and environmental sustainability | Olkaria Waste Management Plan - Purchase and installation of of waste disposal bins at Kwa muhia and Kamere beach completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | -0.816175 36.323888 1876.199951171875 11.899999618530273 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999956 | 100 | 1999956 | 3300044 | 44 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
11216 | Water and Sewerage Management | Sher academy water tank - installation of a water tank at sher academy | To implement sher academy water tank - installation of a water tank at sher academy for access to clean water and environmental sustainability | Sher academy water tank - installation of a water tank at sher academy completed | 3110502 | Water Supplies and Sewerage | NAIVASHA | OLKARIA | 0.837016, 36.366272 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2410512 | 80.4 | 2410512 | 2988940 | 589488 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Ni it was not done. Assessor remarks: Yet to start.
11217 | Water and Sewerage Management | Rhonda Sewage Construction - Construction at Mwariki, Pembe mbili | To implement rhonda sewage construction - construction at mwariki, pembe mbili for access to clean water and environmental sustainability | Rhonda Sewage Construction - Construction at Mwariki, Pembe mbili completed | 3110502 | Water Supplies and Sewerage | NAKURU WEST | RHONDA | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3963197 | 99.1 | 3963197 | 0 | 36803 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11218 | Water and Sewerage Management | Piping and distribution of water in Sirikwa | To provide water distribution infrastructure at water in Sirikwa | Water piping at water in Sirikwa completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | SIRIKWA | -0.283492, 35.673157 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997851 | 99.9 | 2997851 | 3000000 | 2149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank needs fencing, enhance distribution to all the villages.
11219 | Water and Sewerage Management | Sirikwa water project - Design and construction of tank, Piping and distribution | To implement sirikwa water project - design and construction of tank, piping and distribution for access to clean water and environmental sustainability | Sirikwa water project - Design and construction of tank, Piping and distribution completed | 3110502 | Water Supplies and Sewerage | KURESOI NORTH | SIRIKWA | -0.297153, 35.629421 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 3262001 | 32.6 | 3262001 | 592903 | 6737999 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,but it has not meet the needs of the residents, money needs to be allocated for water source. Assessor remarks: Project is not operational the source has high water turbidity,the tank nèeds to be fenced to secure it,,.
11220 | Water and Sewerage Management | Construction of Lomolo Borehole and piping | To construct Lomolo Borehole and piping | Lomolo Borehole and piping constructed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | 0.018446, 36.032083 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2671062 | 2671062 | 2671062 | Equitable | N/A | 2671062 | 0 | 0 | 0 | 0 | 2671062 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working q.
11221 | Water And Sewerage Management | Kipsienan water project piping | To implement kipsienan water project piping for access to clean water and environmental sustainability | Kipsienan water project piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | -0.096449 35.935984 1693 9 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2915876.69 | 2915876.69 | 2915876.69 | Equitable | N/A | 2915876.69 | 0 | 0 | 0 | 0 | 1990264 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping work needed.
11222 | Water And Sewerage Management | Kipsyenan water project | To implement kipsyenan water project for access to clean water and environmental sustainability | Kipsyenan water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | -0.096449 35.935984 1693 9 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2015/16 | 2015/16 | N/A | 4497860.56 | 4497860.56 | 4497860.56 | Equitable | N/A | 4497860.56 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping work needed.
11223 | Water and Sewerage Management | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita | To implement soin ward water projects - drilling of morop borehole and kokwomoi borehole and water works at testai / banita for access to clean water and environmental sustainability | Soin Ward water projects - drilling of Morop borehole and Kokwomoi borehole and water works at Testai / Banita completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOIN | -0.062307, 36.062092 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 11400000 | 10400000 | 10400000 | Equitable | N/A | 10400000 | 0 | 2851216 | 27.4 | 2851216 | 334334 | 7548784 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water in use.
11224 | Water and Sewerage Management | Barafu Water Project - Expansion of Intake and piping | To implement barafu water project - expansion of intake and piping for access to clean water and environmental sustainability | Barafu Water Project - Expansion of Intake and piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.044788, 36.171572 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | September 2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194431 | 99.5 | 1194431 | 2298889 | 5569 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ekay contractors and General supplies. Assessor remarks: Functional.
11225 | Water and Sewerage Management | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project | To implement lower solai water project - construction of water reservoir and piping of lower solai water project for access to clean water and environmental sustainability | Lower Solai water project - construction of water reservoir and piping of Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.097788, 36.178758 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 630663 | 9 | 630663 | 631107 | 6369337 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11226 | Water and Sewerage Management | Ngendaptich tuiyotich water project piping | To implement ngendaptich tuiyotich water project piping for access to clean water and environmental sustainability | Ngendaptich tuiyotich water project piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.04618, 36.140841 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1260630 | 63 | 1260630 | 739370 | 739370 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11227 | Water and Sewerage Management | Nyamamithi water project - Drilling of borehole and Installation of pump | To implement nyamamithi water project - drilling of borehole and installation of pump for access to clean water and environmental sustainability | Nyamamithi water project - Drilling of borehole and Installation of pump completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.113312, 36.222792 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2045996 | 51.1 | 2045996 | 2056072 | 1954004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11228 | Water and Sewerage Management | Sigito water project - piping | To implement sigito water project - piping for access to clean water and environmental sustainability | Sigito water project - piping completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.04618, 36.140841 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998215 | 99.8 | 998215 | 1000000 | 1785 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
11229 | Water and Sewerage Management | Completion of lower Solai water project | To complete lower Solai water project | Lower Solai water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.18324 36.184717 1648.8 7.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3491285 | 87.3 | 3491285 | 508715 | 508715 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11230 | Water and Sewerage Management | Piping of Sigito water project | To provide water distribution infrastructure at Sigito water project | Water piping at Sigito water project completed | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | 0.11082 36.218 1789.6 15.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997984 | 99.9 | 1997984 | 1000000 | 2016 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11231 | Water and Sewerage Management | Rehabilitation of Chemasis water project | To rehabilitate Chemasis water project to restore functionality | Chemasis water project rehabilitated | 3110502 | Water Supplies and Sewerage | RONGAI | SOLAI | -0.010666 36.166707 1752.446044921875 37.472999572753906 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1075924 | 1075924 | Equitable | N/A | 1075924 | 0 | 1069046 | 99.4 | 1069046 | 1000000 | 6878 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
11232 | Water and Sewerage Management | construction of 2 water tanks at the Shrine | To construct 2 water tanks at the Shrine | 2 water tanks at the Shrine constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.024925 36.251015 2248.60009765625 4 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1253078 | 83.5 | 1253078 | 1253078 | 246922 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, community enjoying access to clean water.. Viable: Yes. Contractor: Details not provided. Assessor remarks: Water tanks constructed and piping done.
11233 | Water and Sewerage Management | Construction of Gituamba Kianoe (Nguba farm) water Tank | To construct Gituamba Kianoe (Nguba farm) water Tank | Gituamba Kianoe (Nguba farm) water Tank constructed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.004125 36.219987 1997.199951171875 8.61400032043457 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198895 | 99.9 | 1198895 | 1200000 | 1105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes.. Contractor: Information not available. Assessor remarks: Water tank in good condition.
11234 | Water and Sewerage Management | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project | To implement drilling of borehole, installation of pump and solar panels and piping of subukia valley water project for access to clean water and environmental sustainability | drilling of borehole, installation of pump and solar panels and piping of Subukia valley water project completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.040933 36.220476 2150.7001953125 100 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 4245277 | Equitable | N/A | 4245277 | 0 | 1658854 | 110.6 | 1658854 | 1658854 | -158854 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
11235 | Water and Sewerage Management | Drilling of Tetu Kirima Kibugi borehole | To implement drilling of tetu kirima kibugi borehole for access to clean water and environmental sustainability | Drilling of Tetu Kirima Kibugi borehole completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.04678 36.170557 2107.6 2.5 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3996217 | 3996217 | 2996217 | Equitable | N/A | 2996217 | 0 | 3661174 | 91.6 | 3661174 | 2000000 | 335043 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
11236 | Water and Sewerage Management | installation of water pipes at ACK Munanda water | To install water pipes at ACK Munanda water | Water pipes at ACK Munanda water installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.042368, 36.190708 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2918/2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494803 | 99 | 494803 | 500000 | 5197 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water Supply to the local community provided and functional.
11237 | Water And Sewerage Management | Kirengero Water borehole - plot compensation | To implement kirengero water borehole - plot compensation for access to clean water and environmental sustainability | Kirengero Water borehole - plot compensation completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.041156 36.220377 2150.7001953125 56.099998474121094 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3661174 | 732.2 | 3661174 | 338826 | -3161174 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
11238 | Water and Sewerage Management | Miloreni water women | To implement miloreni water women for access to clean water and environmental sustainability | Miloreni water women completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.030765 36.234948 2103.5849609375 9.105999946594238 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2993702 | 2993702 | 2993702 | Equitable | N/A | 2993702 | 0 | 0 | 0 | 0 | 2993702 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Sure the water serves the community.. Contractor: Information not available. Assessor remarks: Good work.
11239 | Water and Sewerage Management | purchase and installation of water pump, solar panels and construction of water tank for Arash B Kirima borehole | To procure and install water pump, solar panels and construction of water tank for Arash B Kirima borehole | Water pump, solar panels and construction of water tank for Arash B Kirima borehole procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 5245277 | Equitable | N/A | 5245277 | 0 | 2734410 | 109.4 | 2734410 | 2510867 | -234410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
11240 | Water and Sewerage Management | purchase and installation of water pump, solar pannels and piping for Arash A Mutito mumui water projects | To procure and install water pump, solar pannels and piping for Arash A Mutito mumui water projects | Water pump, solar pannels and piping for Arash A Mutito mumui water projects procured and installed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.031385 36.202473 2223.800048828125 12.100000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1999999 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966642 | 0 | 2966642 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
11241 | Water and Sewerage Management | purchase of Hydrum pump for Gatongu water project (GAWASU) | To procure Hydrum pump for Gatongu water project (GAWASU) | Hydrum pump for Gatongu water project (GAWASU) procured | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | 0.007568 36.223208 2011.8999999999999 7.300000190734863 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 500000 | 500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2997632 | 599.5 | 2997632 | 1500000 | -2497632 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the boreho.
11242 | Water and Sewerage Management | repair of tank at Gathima Kirengero | To rehabilitate tank at Gathima Kirengero to restore functionality | Tank at Gathima Kirengero rehabilitated | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.030926 36.197107 2206.2999999999997 30 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 299999 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 0 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The school has only one ECDE classroom, without a toilet. Toilet URGENTLY needed.
11243 | Water and Sewerage Management | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects | To implement subukia ward water works - construction of water intake, purchase of land and piping at kware subukia town water projects for access to clean water and environmental sustainability | Subukia ward water works - construction of water intake, purchase of land and piping at Kware subukia town water projects completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | SUBUKIA | -0.006257, 36.23544 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 12/12/2019 | 4000000 | 4000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999876 | 50 | 1999876 | 1999876 | 2000124 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.. Contractor: Information not known. Assessor remarks: The water tank is in good condition.
11244 | Water and Sewerage Management | Kamwaura Sinking of Borehole | To implement kamwaura sinking of borehole for access to clean water and environmental sustainability | Kamwaura Sinking of Borehole completed | 3110502 | Water Supplies and Sewerage | KURESOI SOUTH | TINET | -0.538982 35.643548 0 2900 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2013/14 | 2013/14 | N/A | 828149 | 828149 | 828149 | Equitable | N/A | 828149 | 0 | 2200000 | 265.7 | 2200000 | 828149 | -1371851 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational use by Kapkeet secondary school.
11245 | Water And Sewerage Management | Completion of mona water project | To complete mona water project | Mona water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30139, 35.70918 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1797909 | 1797909 | 1797909 | Equitable | N/A | 1797909 | 0 | 797936 | 44.4 | 797936 | 617162 | 999973 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: So far it is only Michatha and Mona are using the water and locals collect at the water kiosk next to the project.
11246 | Water And Sewerage Management | Completion of Muchorwe water project | To complete Muchorwe water project | Muchorwe water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.329538 35.694883 2755.300048828125 8.5 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 2689680 | 158.2 | 2689680 | 1310320 | -989680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: Yes. Assessor remarks: The project is on an individual's land. The owner of the land does not give the community water. The is no access to the project. The gate is locked.
11247 | Water And Sewerage Management | Installation of electric power and equipping at Sakaitim water project | To install electric power and equipping at Sakaitim water project | Electric power and equipping at Sakaitim water project installed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.301265 35.709033 2678.3 22.100000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1588605.74 | 1588605.74 | 1588605.74 | Equitable | N/A | 1588605.74 | 0 | 999941 | 62.9 | 999941 | 1000000 | 588664.74 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but not fully operational. Assessor remarks: The ownership documents are under the custody of a self-help group.
11248 | Water and Sewerage Management | Michatha water project - Piping of Michatha water project | To implement michatha water project - piping of michatha water project for access to clean water and environmental sustainability | Michatha water project - Piping of Michatha water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.27483, 35.724585 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998760 | 99.9 | 998760 | 500000 | 1240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
11249 | Water and Sewerage Management | Michatha water project Piping works | To implement michatha water project piping works for access to clean water and environmental sustainability | Michatha water project Piping works completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499923 | 100 | 499923 | 77 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
11250 | Water and Sewerage Management | Mona-michatha water project - Piping of Mona-michatha water project | To implement mona-michatha water project - piping of mona-michatha water project for access to clean water and environmental sustainability | Mona-michatha water project - Piping of Mona-michatha water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.27483, 35.724585 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
11251 | Water and Sewerage Management | Muchorwe water project - Piping of Muchorwa water project | To implement muchorwe water project - piping of muchorwa water project for access to clean water and environmental sustainability | Muchorwe water project - Piping of Muchorwa water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 796157 | 99.5 | 796157 | 77 | 3843 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
11252 | Water and Sewerage Management | Segaitim water project - Piping of Segaitim water project | To implement segaitim water project - piping of segaitim water project for access to clean water and environmental sustainability | Segaitim water project - Piping of Segaitim water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 998760 | 66.6 | 998760 | 1500000 | 501240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
11253 | Water and Sewerage Management | Construction of water tank and piping at Mukorombo dispensary | To construct water tank and piping at Mukorombo dispensary | Water tank and piping at Mukorombo dispensary constructed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.330008 35.687633 2765.800048828125 39.599998474121094 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 999941 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Both the fence and the gate house were vandalised.
11254 | Water and Sewerage Management | Piping at Geteru borehole | To provide water distribution infrastructure at Geteru borehole | Water piping at Geteru borehole completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.268852, 35.77511 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999973 | 100 | 999973 | 499923 | 27 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project was completed but not in use. No water connection to the tank.
11255 | Water and Sewerage Management | Piping at Kiambu Water Project | To provide water distribution infrastructure at Kiambu Water Project | Water piping at Kiambu Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.330019 35.68764 2765.800048828125 42.5 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499752 | 100 | 499752 | 499923 | 248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Viable but it did not meet the needs of the residents. Assessor remarks: The project was abandoned and now vandalised.
11256 | Water and Sewerage Management | Piping at Michatha Water Project | To provide water distribution infrastructure at Michatha Water Project | Water piping at Michatha Water Project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.30192 35.711143 2702.8 12.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 499923 | 55.5 | 499923 | 499923 | 400077 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
11257 | Water and Sewerage Management | Piping at Mona Water project | To provide water distribution infrastructure at Mona Water project | Water piping at Mona Water project completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.301305, 35.709012 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499923 | 100 | 499923 | 499923 | 77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping was done.
11258 | Water and Sewerage Management | Piping at water valley | To provide water distribution infrastructure at water valley | Water piping at water valley completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.270953, 35.756172 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999949 | 100 | 999949 | 499923 | 51 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well built.
11259 | Water and Sewerage Management | Renovation of borehole at Kapsita | To rehabilitate borehole at Kapsita to restore functionality | Borehole at Kapsita rehabilitated | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -1.281229 36.821402 0 291468.7964650597 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 898925 | 99.9 | 898925 | 2300000 | 1075 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: YES. Assessor remarks: THE TOILET INSIDE THE OPD IS NOT FUNCTIONAL. THE WORK WAS NOT DONE SATISFACTORY MANNER.
11260 | Water and Sewerage Management | Water tank renovation and piping at Sagaitim | To implement water tank renovation and piping at sagaitim for access to clean water and environmental sustainability | Water tank renovation and piping at Sagaitim completed | 3110502 | Water Supplies and Sewerage | MOLO | TURI | -0.303666 35.690293 2745.8 23.200000762939453 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 700000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499918 | 100 | 499918 | 50067 | 82 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
11261 | Water And Sewerage Management | Construction of a borehole; Piping-Rajuera farm, Westlands farm, Scheme farm, Slaughter house, | To construct a borehole; Piping-Rajuera farm, Westlands farm, Scheme farm, Slaughter house, | A borehole; Piping-Rajuera farm, Westlands farm, Scheme farm, Slaughter house, constructed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.173526 35.860517 1868.199951171875 54.09400177001953 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2614215.45 | 2614215.45 | 2614215.45 | Equitable | N/A | 2614215.45 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
11262 | Water and Sewerage Management | Kware Kapkwen Borehole - Drilling of Borehole | To implement kware kapkwen borehole - drilling of borehole for access to clean water and environmental sustainability | Kware Kapkwen Borehole - Drilling of Borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2229709 | 96.9 | 2229709 | 0 | 70291 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11263 | Water And Sewerage Management | Shalom B borehole renovation | To implement shalom b borehole renovation for access to clean water and environmental sustainability | Shalom B borehole renovation completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.149943 35.881463 1841.6 9.300000190734863 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
11264 | Water and Sewerage Management | Visoi ward water works | To implement visoi ward water works for access to clean water and environmental sustainability | Visoi ward water works completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.137292 35.824637 1889.3 9.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 4385784.55 | 4385784.5 | 4385784.5 | Equitable | N/A | 4385784.5 | 0 | 2335647 | 53.3 | 2335647 | 2000000 | 2050137.5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment. Assessor remarks: Good.
11265 | Water and Sewerage Management | Completion of Belbur water project (Additional solar panels) | To complete Belbur water project (Additional solar panels) | Belbur water project (Additional solar panels) completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125295 35.935638 1744.699951171875 6 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 1100000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2298866 | 209 | 2298866 | 2298866 | -1198866 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
11266 | Water and Sewerage Management | Completion of Rajuera water project (Piping and pump and water tank) | To complete Rajuera water project (Piping and pump and water tank) | Rajuera water project (Piping and pump and water tank) completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.113343 35.830298 1856.1000000000001 9.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1959594 | 98 | 1959594 | 3449399 | 40406 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: 2018/19. Assessor remarks: Good.
11267 | Water and Sewerage Management | Construction of Gogar water pan and digging of trench | To construct Gogar water pan and digging of trench | Gogar water pan and digging of trench constructed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.123667 35.824817 1897.9 9.300000190734863 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3550334 | 88.8 | 3550334 | 120000 | 449666 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: Not achieved. Viable: Yes. Assessor remarks: Poor.
11268 | Water and Sewerage Management | Drilling and completion of Umoja water borehole | To implement drilling and completion of umoja water borehole for access to clean water and environmental sustainability | Drilling and completion of Umoja water borehole completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.119957 35.933578 1710.7 7 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 1300000 | 4231790 | Equitable | N/A | 4231790 | 0 | 1342243 | 103.2 | 1342243 | 1342243 | -42243 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11269 | Water and Sewerage Management | water piping, purchase of water tank and fencing for Lenginet dispensary | To implement water piping, purchase of water tank and fencing for lenginet dispensary for access to clean water and environmental sustainability | water piping, purchase of water tank and fencing for Lenginet dispensary completed | 3110502 | Water Supplies and Sewerage | RONGAI | VISOI | -0.125197 35.935737 1744.699951171875 6.599999904632568 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599659 | 99.9 | 599659 | 0 | 341 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
11270 | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole | To implement akuiz borehole - drilling, equipping construction of water tank and installation of solar panels at akuiz borehole for access to clean water and environmental sustainability | Akuiz Borehole - Drilling, Equipping construction of water tank and installation of solar panels at Akuiz borehole completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.116735 36.274342 1803.2 9.800000190734863 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 5000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 394500 | 7.9 | 394500 | 394720 | 4605500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
11271 | Chania Igana / Nganoini water works | Chania Igana / Nganoini water works | To implement chania igana / nganoini water works for access to clean water and environmental sustainability | Chania Igana / Nganoini water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.02338 36.262172 1995.300048828125 5.199999809265137 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 997931.01 | 997931.01 | 997931.01 | Equitable | N/A | 997931.01 | 0 | 912210 | 91.4 | 912210 | 997931 | 85721.01 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
11272 | Water and Sewerage Management | Chania storage tank and piping - construction of storage tank and piping of chania water | To implement chania storage tank and piping - construction of storage tank and piping of chania water for access to clean water and environmental sustainability | Chania storage tank and piping - construction of storage tank and piping of chania water completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 1999045 | 249.9 | 1999045 | 639 | -1199045 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
11273 | Water and Sewerage Management | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well | To implement gathiini gustion shallow wells - excavation and digging of gathiini shallows well for access to clean water and environmental sustainability | Gathiini gustion shallow wells - excavation and digging of Gathiini shallows well completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1198074 | 0 | Stalled | 0 | N/A | Residents Prefer Borehole instead of shallow wells and hence require Additional funding | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Residents Prefer Borehole instead of shallow wells and hence require Additional funding.
11274 | Water and Sewerage Management | Gathima water project (Marana water tank ) | To implement gathima water project (marana water tank ) for access to clean water and environmental sustainability | Gathima water project (Marana water tank ) completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1144051 | 1144051 | 2144051 | Equitable | N/A | 2144051 | 0 | 983544 | 86 | 983544 | 0 | 160507 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
11275 | Water And Sewerage Management | Guston water project | To implement guston water project for access to clean water and environmental sustainability | Guston water project completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.019851, 36.210494 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 999456.28 | 999456 | 999456 | Equitable | N/A | 999456 | 0 | 0 | 0 | 0 | 999456.28 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water project is operational.
11276 | Water And Sewerage Management | Kagochi water works | To implement kagochi water works for access to clean water and environmental sustainability | Kagochi water works completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 996926 | 996926 | 996926 | Equitable | N/A | 996926 | 0 | 489000 | 49.1 | 489000 | 996926 | 507926 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11277 | Ngamini water works - drilling of borehole and equipping | Ngamini water works - drilling of borehole and equipping | To implement ngamini water works - drilling of borehole and equipping for access to clean water and environmental sustainability | Ngamini water works - drilling of borehole and equipping completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.027937 36.257645 2098.1 63.17599868774414 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000001 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998643 | 0 | 2998643 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
11278 | Water And Sewerage Management | Wei borehole and equipping - driiling of Wei borehole and equipping | To implement wei borehole and equipping - driiling of wei borehole and equipping for access to clean water and environmental sustainability | Wei borehole and equipping - driiling of Wei borehole and equipping completed | 3110502 | Water Supplies and Sewerage | SUBUKIA | WASEGES | 0.126515 36.265512 1675.1 8.600000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
11279 | Water and Sewerage Management | Rehabilitation of toilet and new sewer line system at Kimathi estate | To rehabilitate toilet and new sewer line system at Kimathi estate to restore functionality | Toilet and new sewer line system at Kimathi estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | NAKURU EAST | FLAMINGO | -0.30363, 36.078623 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020/21 | 5000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3485179 | 87.1 | 3485179 | 514821 | 514821 | Stalled | 75 | 87.1 | STALLED DUE TO INSUFFICIEN FUNDS | 2018 | N/A | 514821 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
11280 | Water and Sewerage Management | Completion of desilting of Storm Water retention Pond at Old Town treatment Works | To complete desilting of Storm Water retention Pond at Old Town treatment Works | Desilting of Storm Water retention Pond at Old Town treatment Works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 27000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 4941252 | 98.8 | 4941252 | 497054 | 58748 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11281 | Water and Sewerage Management | Construction of Office and Sanitary facility Eco-Toilets I (Gioto) | To construct Office and Sanitary facility Eco-Toilets I (Gioto) | Office and Sanitary facility Eco-Toilets I (Gioto) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 7025864 | 351.3 | 7025864 | 2000000 | -5025864 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11282 | Environmental Management | Fencing of Gioto Disposal Site | To secure Gioto Disposal Site through fencing | Gioto Disposal Site fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 4696751 | 58.7 | 4696751 | 3303249 | 3303249 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11283 | Water and Sewerage Management | Other County Development Projects | To implement other county development projects for access to clean water and environmental sustainability | Other County Development Projects completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 27963000 | 10963000 | 10963000 | N/A | N/A | 10963000 | 0 | 7089732 | 64.7 | 7089732 | 3728738 | 3873268 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11284 | Water And Sewerage Management | Desilting Of Storm Water Retention Ponds - Naivasha (Variation For Desilting Of Retention Ponds) | To implement desilting of storm water retention ponds - naivasha (variation for desilting of retention ponds) for access to clean water and environmental sustainability | Desilting Of Storm Water Retention Ponds - Naivasha (Variation For Desilting Of Retention Ponds) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1979999.8 | 1979999.8 | 1979999.8 | Equitable | N/A | 1979999.8 | 0 | 4899098 | 247.4 | 4899098 | 497054 | -2919098.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11285 | Environmental Management | Nyayo Gardens - Rehabilitation of Nyayo Gardens (Ongoing 2017/18) | To implement nyayo gardens - rehabilitation of nyayo gardens (ongoing 2017/18) for access to clean water and environmental sustainability | Nyayo Gardens - Rehabilitation of Nyayo Gardens (Ongoing 2017/18) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 20000000 | 100 | 20000000 | 8000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11286 | Water and Sewerage Management | Rehabilitation Of Naruwassco Water Works | To rehabilitate Naruwassco Water Works to restore functionality | Naruwassco Water Works rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 3997079 | 3997079 | 3997079 | N/A | N/A | 3997079 | 0 | 2994378 | 74.9 | 2994378 | 945568 | 1002701 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
11287 | Water and Sewerage Management | Rehabilitation of Municipal Park | To rehabilitate Municipal Park to restore functionality | Municipal Park rehabilitated | 3110599 | Other Infrastructure and Civil Works | NAIVASHA | VIWANDANI | -0.71433 36.434014 1901.0999755859375 0.5360000133514404 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 3223399 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Amount allocated not justifiable.
11288 | Water and Sewerage Management | Purchase Of 2 No. Refuse Trucks for Naivasha And Bahati/Subukia | To procure 2 No. Refuse Trucks for Naivasha And Bahati/Subukia | 2 No. Refuse Trucks for Naivasha And Bahati/Subukia procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 8000000 | 100 | 8000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11289 | Water and Sewerage Management | Purchase of 5No. Skips | To procure 5No. Skips | 5No. Skips procured | 3110705 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494000 | 99.8 | 2494000 | 1900000 | 6000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11290 | Water and Sewerage Management | Purchase of Skip Loader (Tractor) | To procure Skip Loader (Tractor) | Skip Loader (Tractor) procured | 3110706 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 7849770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11291 | Water and Sewerage Management | Purchase of Terrameter (1 No.) | To procure Terrameter (1 No.) | Terrameter (1 No.) procured | 3111114 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 13000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 5800000 | 72.5 | 5800000 | 1000000 | 2200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11292 | Water and Sewerage Management | Electronic Theodolite (2 No.) | To implement electronic theodolite (2 no.) for access to clean water and environmental sustainability | Electronic Theodolite (2 No.) completed | 3111115 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 6000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 5000000 | 166.7 | 5000000 | 3000000 | -2000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11293 | Water and Sewerage Management | Quantum GPS(2 No.) | To implement quantum gps(2 no.) for access to clean water and environmental sustainability | Quantum GPS(2 No.) completed | 3111116 | N/A | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11294 | Water And Sewerage Management | Purchase of solar energy equipment for Kamasi water project and solar panels for borehole soimet kigon | To procure solar energy equipment for Kamasi water project and solar panels for borehole soimet kigon | Solar energy equipment for Kamasi water project and solar panels for borehole soimet kigon procured | 3111120 | Purchase of Specialized Plant. - | NAKURU WEST | BARUT | -0.342342, 36.036679 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2018 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There was no solarization done.
11295 | Water and Sewerage Management | Purchase of water pump for Menengai water project | To procure water pump for Menengai water project | Water pump for Menengai water project procured | 3111120 | Purchase of Specialized Plant. - | BAHATI | DUNDORI | -0.271495, 36.206253 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2261527 | 98.3 | 2261527 | 1369685 | 38473 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jawap general contractors ltd. Assessor remarks: Not functioning.
11296 | Water and Sewerage Management | Beautification and rehabilitation of Naivasha Gardens | To implement beautification and rehabilitation of naivasha gardens for access to clean water and environmental sustainability | Beautification and rehabilitation of Naivasha Gardens completed | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 19000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 20000000 | 250 | 20000000 | 8000000 | -12000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11297 | Water and Sewerage Management | Climate Change Mitigation and Adaptation | To implement climate change mitigation and adaptation for access to clean water and environmental sustainability | Climate Change Mitigation and Adaptation completed | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 20000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 4997450 | 50 | 4997450 | 10000000 | 5002550 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11298 | Water and Sewerage Management | climate Change Mitigation and Adaptation- planting / growing of trees | To implement climate change mitigation and adaptation- planting / growing of trees for access to clean water and environmental sustainability | climate Change Mitigation and Adaptation- planting / growing of trees completed | 3111305 | Beautification and Tree Planting | NAIVASHA | OLKARIA | -0.816383 36.324117 1932.699951171875 7.5 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999232 | 100 | 2999232 | 0 | 768 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been damaged by rain so requires maintenance.
11299 | Water and Sewerage Management | Physical Planning relating to energy | To implement physical planning relating to energy for access to clean water and environmental sustainability | Physical Planning relating to energy completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
11300 | Water and Sewerage Management | Purchase of Dumpsites | To procure Dumpsites | Dumpsites procured | 3130101 | Acquisition of Land | HQ | HQ | N/A | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 20000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 14790000 | 98.6 | 14790000 | 14790000 | 210000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
11301 | Water And Sewerage Management | purchase of land for construction of Thayu water tank | To acquire land for construction of Thayu water tank | Land for construction of Thayu water tank acquired | 3130101 | Acquisition of Land | BAHATI | KABATINI | -0.16447 36.177669 2195.08544921875 16.350000381469727 | VOTE NO. D12 | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | MINISTRY OF ENVIRONMENT, WATER, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1998796 | 199.9 | 1998796 | 1204 | -998796 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Renald Yatow enterprise. Assessor remarks: Operational no Ash pit provided.
11302 | Construction of Speaker's House | Construction of Speaker's House | To construct Speaker's House | Speaker's House constructed | 3110199 | N/A | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2017/2018 | 2017/2018 | 40155707 | 33307092 | 33307092 | N/A | N/A | 33307092 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11303 | completion of the office block | completion of the office block | To complete the office block | The office block completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/2019 | 2018/2019 | 75000000 | 70000000 | 34065394 | N/A | N/A | 34065394 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11304 | Construction of Office Block | Construction of Office Block | To construct Office Block | Office Block constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2017/18 | 2017/18 | 206822818 | 82785828.3 | 82785828.3 | N/A | N/A | 82785828.3 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11305 | construction of phase II office block and consultancy | construction of phase II office block and consultancy | To construct phase II office block and consultancy | Phase II office block and consultancy constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/2019 | 2018/2019 | 362154769 | 0 | 62154769 | N/A | N/A | 62154769 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11306 | Refurbishment of buildings | Refurbishment of buildings | To implement refurbishment of buildings for improved service delivery | Refurbishment of buildings completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/2019 | 2018/2019 | 10000000 | 10000000 | 3277812 | N/A | N/A | 3277812 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11307 | Refurbishment of Building | Refurbishment of Building | To implement refurbishment of building for improved service delivery | Refurbishment of Building completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2017/18 | 2017/18 | 37338255 | 24665240 | 24665240 | N/A | N/A | 24665240 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11308 | Refurbishment of Hansard Equipment | Refurbishment of Hansard Equipment | To implement refurbishment of hansard equipment for improved service delivery | Refurbishment of Hansard Equipment completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2018/19 | 2018/2019 | 2018/2019 | 3000000 | 0 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11309 | Completion of Public Gallery | Completion of Public Gallery | To complete Public Gallery | Public Gallery completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2017/18 | 2017/18 | 14867165 | 9620550 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11310 | Equipping and Configuration of the Chamber | Equipping and Configuration of the Chamber | To equip and Configuration of the Chamber with necessary facilities and equipment | And Configuration of the Chamber equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | VOTE NO. D13 | NAKURU COUNTY ASSEMBLY | NAKURU COUNTY ASSEMBLY | N/A | 2017/18 | 2017/18 | 2017/18 | 40768562 | 26205677 | 26205677 | N/A | N/A | 26205677 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.